## Summary
Task ID | Task Name | Status | Start Date | End Date | Duration | Actual Duration | Duration % | Invoice | Income Received | Income % | Planned Spend | Actual Spend | Spent Cost % | Profit % | Planned Labor Days | Actual Labor Days | Applied Labor %
200 | Design Activities | Completed | 2025-04-02 | 2025-06-24 | 60 | 60 | 100% | 96480 | 96480 | 100% | 80400 | 19628.44 | 24% | 392% | 134 | 22.75 | 17%
300 | Pre-Mobilization, Procurement and Manufacturing | Completed | 2025-06-25 | 2025-09-19 | 63 | 63 | 100% | 414181.3668 | 0 | 0% | 201344.6951 | 77086.355 | 38% | -100% | 21 | 64.5 | 512.7%
400 | Drilling and Subsurface Installation | In Progress | 2025-09-22 | 2025-11-11 | 37 | 18 | 49% | 392239.0516 | 0 | 0% | 303239.3908 | 38241.71 | 13% | -100% | 316.125 | 41 | 23%
500 | Field Construction | Future | 2025-11-12 | 2026-02-03 | 60 |  |  | 361680.2306 | 0 | 0% | 280440.1921 | 0 |  |  | 287.6 | 0
600 | Operation | Future | 2026-02-04 | 2026-08-12 | 190 |  |  | 376851.0145 | 0 | 0% | 313382.9288 | 0 |  |  | 370 | 0
700 | Demobilization | Future | 2026-08-13 | 2026-09-15 | 24 |  |  | 78952.6325 | 0 | 0% | 64960.5271 | 0 |  |  | 98.2 | 0
TOTAL | PROJECT TOTAL |  | 2025-04-02 | 2026-09-15 | 434 | 141 | 0.32488 | 1720384.296 | 96480 | 0.05608 | 1243767.734 | 134956.505 | 0.10851 | -0.2851 | 1226.925 | 128.25 | 0.10453

## Invoice Sum
Date | Planned Income (Cumulative) | Actual Income (Daily) | Actual Income (Cumulative) | Planned Labor Sum (Cumulative) | Planned Travel&perdiem (Direct Cost) Sum (Cumulative) | Planned Parts&materials (Direct Cost) Sum (Cumulative) | Planned Outsource (Direct Cost) Sum (Cumulative) | Planned Equipment (Cumulative) | Planned 1805 · EQUIPMENT - FORKLIFT (Cumulative) | Planned 1818 · EQUIPMENT - BCU (Cumulative) | Planned 1819 · EQUIPMENT - TPMB (Cumulative) | Planned 1820 · EQUIPMENT & TOOLS (Cumulative) | Planned 1821 · EQUIPMENT - C3 (Cumulative) | Planned 1822 · EQUIPMENT - C2 (Cumulative) | Planned 1823 · EQUIPMENT - TCU BASIC (Cumulative) | Planned 1824 · EQUIPMENT - TCU PLC (Cumulative) | Planned 1825 · EQUIPMENT - BLOWER SKIDS (Cumulative) | Planned 1826 · EQUIPMENT - WELL HEADS (Cumulative) | Planned 1827 · EQUIPMENT - THERMAL WELLS (Cumulative) | Planned 1829 · EQUIPMENT - WATER TREATMENT SYS (Cumulative) | Planned 1830 · EQUIPMENT - VAPOR EXTRACTION (Cumulative) | Planned 1831 · EQUIPMENT - GTR/C3 COMPONENTS (Cumulative) | Planned 1832 · EQUIP - CONTROL/DIST PANELS (Cumulative) | Planned 1833 · EQUIPMENT - OFFICE & COMPUTER (Cumulative) | Planned 5004 · GTR COST OF SALES - PARTS (Cumulative) | Planned 5006 · DRILLING EXPENSE (Cumulative) | Planned 5101 · SALARY AND WAGES (DIRECT) (Cumulative) | Planned 5102 · PAYROLL TAXES (DIRECT) (Cumulative) | Planned 5105 · TRAVEL - AIRFARE (DIRECT) (Cumulative) | Planned 5106 · TRAVEL - HOTEL (DIRECT) (Cumulative) | Planned 5107 · TRAVEL - OTHER (DIRECT) (Cumulative) | Planned 5108 · MEALS & ENTERTAINMENT (DIRECT) (Cumulative) | Planned 5110 · TEMPORARY LABOR (DIRECT) (Cumulative) | Planned 5111 · PARTS & MATERIAL COSTS (DIRECT) (Cumulative) | Planned 5112 · CARBON & LAB SAMPLIES (DRIECT) (Cumulative) | Planned 5113 · REPAIRS & MAINT (DIRECT) (Cumulative) | Planned 5114 · RENT - BUILDING (DIRECT) (Cumulative) | Planned 5115 · RENT - EQUIPMENT (DIRECT) (Cumulative) | Planned 5116 · Rent - Storage (Direct) (Cumulative) | Planned 5120 · OUTSIDE SERVICES (DIRECT) (Cumulative) | Planned 5121 · FREIGHT & SHIPPING (DIRECT) (Cumulative) | Planned 5122 · MOTOR VEHICLE EXP (DIRECT) (Cumulative) | Planned 5123 · AUTO FUEL (DIRECT) (Cumulative) | Planned 5124 · LICENSE AND PERMITS (DIRECT) (Cumulative) | Planned 5128 · HEALTH & SAFETY EQUIP (DIRECT) (Cumulative) | Planned 5129 · MISC EXPENSES (DIRECT) (Cumulative) | Planned 5132 · INTERNET FEE (DIRECT) (Cumulative) | Planned 6999 · UNCATEGORIZED EXPENSES (Cumulative)
2025-04-02 | 1148.5714 | 0 | 0 | 1148.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 2297.1429 | 0 | 0 | 2297.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2297.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 3445.7143 | 0 | 0 | 3445.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3445.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 4594.2857 | 0 | 0 | 4594.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4594.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 5742.8571 | 0 | 0 | 5742.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5742.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 6891.4286 | 0 | 0 | 6891.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6891.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 8040 | 0 | 0 | 8040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 9188.5714 | 51408 | 51408 | 9188.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9188.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 10337.1429 | 0 | 51408 | 10337.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10337.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 11485.7143 | 0 | 51408 | 11485.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11485.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 12634.2857 | 0 | 51408 | 12634.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12634.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 13782.8571 | 0 | 51408 | 13782.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13782.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 14931.4286 | 0 | 51408 | 14931.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14931.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 16080 | 0 | 51408 | 16080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 17228.5714 | 0 | 51408 | 17228.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17228.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 18377.1429 | 0 | 51408 | 18377.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18377.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 19525.7143 | 0 | 51408 | 19525.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19525.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 20674.2857 | 0 | 51408 | 20674.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20674.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 21822.8571 | 0 | 51408 | 21822.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21822.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 22971.4286 | 0 | 51408 | 22971.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22971.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 24120 | 0 | 51408 | 24120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 25268.5714 | 0 | 51408 | 25268.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25268.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 26417.1429 | 0 | 51408 | 26417.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26417.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 27565.7143 | 0 | 51408 | 27565.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27565.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 28714.2857 | 0 | 51408 | 28714.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28714.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 29862.8571 | 0 | 51408 | 29862.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29862.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 31011.4286 | 0 | 51408 | 31011.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31011.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 32160 | 0 | 51408 | 32160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 33308.5714 | 0 | 51408 | 33308.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33308.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 34457.1429 | 0 | 51408 | 34457.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34457.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 35605.7143 | 0 | 51408 | 35605.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35605.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 36754.2857 | 0 | 51408 | 36754.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36754.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 37902.8571 | 0 | 51408 | 37902.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37902.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 39051.4286 | 0 | 51408 | 39051.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39051.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 40200 | 0 | 51408 | 40200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 41348.5714 | 0 | 51408 | 41348.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41348.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 42497.1429 | 0 | 51408 | 42497.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42497.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 43645.7143 | 0 | 51408 | 43645.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43645.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 44794.2857 | 0 | 51408 | 44794.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44794.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 45942.8571 | 0 | 51408 | 45942.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45942.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 47091.4286 | 0 | 51408 | 47091.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47091.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 48240 | 0 | 51408 | 48240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 49388.5714 | 0 | 51408 | 49388.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49388.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 50537.1429 | 0 | 51408 | 50537.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50537.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 51685.7143 | 0 | 51408 | 51685.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51685.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 52834.2857 | 0 | 51408 | 52834.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52834.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 53982.8571 | 0 | 51408 | 53982.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53982.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 55131.4286 | 0 | 51408 | 55131.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55131.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 56280 | 0 | 51408 | 56280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 57428.5714 | 0 | 51408 | 57428.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57428.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 58577.1429 | 0 | 51408 | 58577.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58577.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 59725.7143 | 0 | 51408 | 59725.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59725.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 60874.2857 | 0 | 51408 | 60874.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60874.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 62022.8571 | 0 | 51408 | 62022.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62022.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 63171.4286 | 0 | 51408 | 63171.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63171.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 64320 | 0 | 51408 | 64320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 65468.5714 | 45072 | 96480 | 65468.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65468.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 66617.1429 | 0 | 96480 | 66617.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66617.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 67765.7143 | 0 | 96480 | 67765.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67765.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 68914.2857 | 0 | 96480 | 68914.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68914.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 70062.8571 | 0 | 96480 | 70062.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70062.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 71211.4286 | 0 | 96480 | 71211.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71211.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 72360 | 0 | 96480 | 72360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 73508.5714 | 0 | 96480 | 73508.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73508.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 74657.1429 | 0 | 96480 | 74657.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74657.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 75805.7143 | 0 | 96480 | 75805.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75805.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 76954.2857 | 0 | 96480 | 76954.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76954.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 78102.8571 | 0 | 96480 | 78102.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78102.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 79251.4286 | 0 | 96480 | 79251.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79251.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 80400 | 0 | 96480 | 80400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 81548.5714 | 0 | 96480 | 81548.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81548.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 82697.1429 | 0 | 96480 | 82697.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82697.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 83845.7143 | 0 | 96480 | 83845.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83845.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 84994.2857 | 0 | 96480 | 84994.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84994.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 86142.8571 | 0 | 96480 | 86142.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86142.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 87291.4286 | 0 | 96480 | 87291.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87291.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 88440 | 0 | 96480 | 88440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 89588.5714 | 0 | 96480 | 89588.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89588.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 90737.1429 | 0 | 96480 | 90737.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90737.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 91885.7143 | 0 | 96480 | 91885.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91885.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 93034.2857 | 0 | 96480 | 93034.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93034.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 94182.8571 | 0 | 96480 | 94182.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94182.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 95331.4286 | 0 | 96480 | 95331.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95331.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 96480 | 0 | 96480 | 96480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 101240.7054 | 0 | 96480 | 96712.4954 | 166.0432 | 1803.4231 | 149.4253 | 2409.3184 | 0 | 0 | 65.0897 | 0 | 0 | 1915.6322 | 107.5862 | 0 | 0 | 50.2069 | 0 | 0 | 113.9069 | 156.8966 | 0 | 0 | 0 | 0 | 96712.4954 | 0 | 64.3191 | 67.2414 | 3.4483 | 8.6207 | 0 | 1495.9518 | 0 | 0 | 1.1494 | 29.8851 | 74.7126 | 149.4253 | 149.4253 | 22.4138 | 0 | 0 | 0 | 0 | 29.8851 | 0
2025-06-26 | 106001.4107 | 0 | 96480 | 96944.9907 | 332.0864 | 3606.8462 | 298.8506 | 4818.6368 | 0 | 0 | 130.1793 | 0 | 0 | 3831.2644 | 215.1724 | 0 | 0 | 100.4138 | 0 | 0 | 227.8138 | 313.7931 | 0 | 0 | 0 | 0 | 96944.9907 | 0 | 128.6382 | 134.4828 | 6.8966 | 17.2414 | 0 | 2991.9037 | 0 | 0 | 2.2989 | 59.7701 | 149.4253 | 298.8506 | 298.8506 | 44.8276 | 0 | 0 | 0 | 0 | 59.7701 | 0
2025-06-27 | 110762.1161 | 0 | 96480 | 97177.4861 | 498.1297 | 5410.2693 | 448.2759 | 7227.9552 | 0 | 0 | 195.269 | 0 | 0 | 5746.8966 | 322.7586 | 0 | 0 | 150.6207 | 0 | 0 | 341.7207 | 470.6897 | 0 | 0 | 0 | 0 | 97177.4861 | 0 | 192.9572 | 201.7241 | 10.3448 | 25.8621 | 0 | 4487.8555 | 0 | 0 | 3.4483 | 89.6552 | 224.1379 | 448.2759 | 448.2759 | 67.2414 | 0 | 0 | 0 | 0 | 89.6552 | 0
2025-06-28 | 115522.8215 | 0 | 96480 | 97409.9815 | 664.1729 | 7213.6924 | 597.7011 | 9637.2736 | 0 | 0 | 260.3586 | 0 | 0 | 7662.5287 | 430.3448 | 0 | 0 | 200.8276 | 0 | 0 | 455.6276 | 627.5862 | 0 | 0 | 0 | 0 | 97409.9815 | 0 | 257.2763 | 268.9655 | 13.7931 | 34.4828 | 0 | 5983.8074 | 0 | 0 | 4.5977 | 119.5402 | 298.8506 | 597.7011 | 597.7011 | 89.6552 | 0 | 0 | 0 | 0 | 119.5402 | 0
2025-06-29 | 120283.5268 | 0 | 96480 | 97642.4768 | 830.2161 | 9017.1155 | 747.1264 | 12046.592 | 0 | 0 | 325.4483 | 0 | 0 | 9578.1609 | 537.931 | 0 | 0 | 251.0345 | 0 | 0 | 569.5345 | 784.4828 | 0 | 0 | 0 | 0 | 97642.4768 | 0 | 321.5954 | 336.2069 | 17.2414 | 43.1034 | 0 | 7479.7592 | 0 | 0 | 5.7471 | 149.4253 | 373.5632 | 747.1264 | 747.1264 | 112.069 | 0 | 0 | 0 | 0 | 149.4253 | 0
2025-06-30 | 125044.2322 | 0 | 96480 | 97874.9722 | 996.2593 | 10820.5386 | 896.5517 | 14455.9103 | 0 | 0 | 390.5379 | 0 | 0 | 11493.7931 | 645.5172 | 0 | 0 | 301.2414 | 0 | 0 | 683.4414 | 941.3793 | 0 | 0 | 0 | 0 | 97874.9722 | 0 | 385.9145 | 403.4483 | 20.6897 | 51.7241 | 0 | 8975.711 | 0 | 0 | 6.8966 | 179.3103 | 448.2759 | 896.5517 | 896.5517 | 134.4828 | 0 | 0 | 0 | 0 | 179.3103 | 0
2025-07-01 | 129804.9376 | 0 | 96480 | 98107.4676 | 1162.3025 | 12623.9617 | 1045.977 | 16865.2287 | 0 | 0 | 455.6276 | 0 | 0 | 13409.4253 | 753.1034 | 0 | 0 | 351.4483 | 0 | 0 | 797.3483 | 1098.2759 | 0 | 0 | 0 | 0 | 98107.4676 | 0 | 450.2336 | 470.6897 | 24.1379 | 60.3448 | 0 | 10471.6629 | 0 | 0 | 8.046 | 209.1954 | 522.9885 | 1045.977 | 1045.977 | 156.8966 | 0 | 0 | 0 | 0 | 209.1954 | 0
2025-07-02 | 134565.6429 | 0 | 96480 | 98339.9629 | 1328.3457 | 14427.3848 | 1195.4023 | 19274.5471 | 0 | 0 | 520.7172 | 0 | 0 | 15325.0575 | 860.6897 | 0 | 0 | 401.6552 | 0 | 0 | 911.2552 | 1255.1724 | 0 | 0 | 0 | 0 | 98339.9629 | 0 | 514.5526 | 537.931 | 27.5862 | 68.9655 | 0 | 11967.6147 | 0 | 0 | 9.1954 | 239.0805 | 597.7011 | 1195.4023 | 1195.4023 | 179.3103 | 0 | 0 | 0 | 0 | 239.0805 | 0
2025-07-03 | 139326.3483 | 0 | 96480 | 98572.4583 | 1494.389 | 16230.8079 | 1344.8276 | 21683.8655 | 0 | 0 | 585.8069 | 0 | 0 | 17240.6897 | 968.2759 | 0 | 0 | 451.8621 | 0 | 0 | 1025.1621 | 1412.069 | 0 | 0 | 0 | 0 | 98572.4583 | 0 | 578.8717 | 605.1724 | 31.0345 | 77.5862 | 0 | 13463.5666 | 0 | 0 | 10.3448 | 268.9655 | 672.4138 | 1344.8276 | 1344.8276 | 201.7241 | 0 | 0 | 0 | 0 | 268.9655 | 0
2025-07-04 | 144087.0537 | 0 | 96480 | 98804.9537 | 1660.4322 | 18034.231 | 1494.2529 | 24093.1839 | 0 | 0 | 650.8966 | 0 | 0 | 19156.3218 | 1075.8621 | 0 | 0 | 502.069 | 0 | 0 | 1139.069 | 1568.9655 | 0 | 0 | 0 | 0 | 98804.9537 | 0 | 643.1908 | 672.4138 | 34.4828 | 86.2069 | 0 | 14959.5184 | 0 | 0 | 11.4943 | 298.8506 | 747.1264 | 1494.2529 | 1494.2529 | 224.1379 | 0 | 0 | 0 | 0 | 298.8506 | 0
2025-07-05 | 148847.759 | 0 | 96480 | 99037.449 | 1826.4754 | 19837.6541 | 1643.6782 | 26502.5023 | 0 | 0 | 715.9862 | 0 | 0 | 21071.954 | 1183.4483 | 0 | 0 | 552.2759 | 0 | 0 | 1252.9759 | 1725.8621 | 0 | 0 | 0 | 0 | 99037.449 | 0 | 707.5099 | 739.6552 | 37.931 | 94.8276 | 0 | 16455.4702 | 0 | 0 | 12.6437 | 328.7356 | 821.8391 | 1643.6782 | 1643.6782 | 246.5517 | 0 | 0 | 0 | 0 | 328.7356 | 0
2025-07-06 | 153608.4644 | 0 | 96480 | 99269.9444 | 1992.5186 | 21641.0772 | 1793.1034 | 28911.8207 | 0 | 0 | 781.0759 | 0 | 0 | 22987.5862 | 1291.0345 | 0 | 0 | 602.4828 | 0 | 0 | 1366.8828 | 1882.7586 | 0 | 0 | 0 | 0 | 99269.9444 | 0 | 771.829 | 806.8966 | 41.3793 | 103.4483 | 0 | 17951.4221 | 0 | 0 | 13.7931 | 358.6207 | 896.5517 | 1793.1034 | 1793.1034 | 268.9655 | 0 | 0 | 0 | 0 | 358.6207 | 0
2025-07-07 | 158369.1697 | 0 | 96480 | 99502.4397 | 2158.5618 | 23444.5003 | 1942.5287 | 31321.1391 | 0 | 0 | 846.1655 | 0 | 0 | 24903.2184 | 1398.6207 | 0 | 0 | 652.6897 | 0 | 0 | 1480.7897 | 2039.6552 | 0 | 0 | 0 | 0 | 99502.4397 | 0 | 836.148 | 874.1379 | 44.8276 | 112.069 | 0 | 19447.3739 | 0 | 0 | 14.9425 | 388.5057 | 971.2644 | 1942.5287 | 1942.5287 | 291.3793 | 0 | 0 | 0 | 0 | 388.5057 | 0
2025-07-08 | 163129.8751 | 0 | 96480 | 99734.9351 | 2324.6051 | 25247.9234 | 2091.954 | 33730.4575 | 0 | 0 | 911.2552 | 0 | 0 | 26818.8506 | 1506.2069 | 0 | 0 | 702.8966 | 0 | 0 | 1594.6966 | 2196.5517 | 0 | 0 | 0 | 0 | 99734.9351 | 0 | 900.4671 | 941.3793 | 48.2759 | 120.6897 | 0 | 20943.3257 | 0 | 0 | 16.092 | 418.3908 | 1045.977 | 2091.954 | 2091.954 | 313.7931 | 0 | 0 | 0 | 0 | 418.3908 | 0
2025-07-09 | 167890.5805 | 0 | 96480 | 99967.4305 | 2490.6483 | 27051.3466 | 2241.3793 | 36139.7759 | 0 | 0 | 976.3448 | 0 | 0 | 28734.4828 | 1613.7931 | 0 | 0 | 753.1034 | 0 | 0 | 1708.6034 | 2353.4483 | 0 | 0 | 0 | 0 | 99967.4305 | 0 | 964.7862 | 1008.6207 | 51.7241 | 129.3103 | 0 | 22439.2776 | 0 | 0 | 17.2414 | 448.2759 | 1120.6897 | 2241.3793 | 2241.3793 | 336.2069 | 0 | 0 | 0 | 0 | 448.2759 | 0
2025-07-10 | 172651.2858 | 0 | 96480 | 100199.9258 | 2656.6915 | 28854.7697 | 2390.8046 | 38549.0943 | 0 | 0 | 1041.4345 | 0 | 0 | 30650.1149 | 1721.3793 | 0 | 0 | 803.3103 | 0 | 0 | 1822.5103 | 2510.3448 | 0 | 0 | 0 | 0 | 100199.9258 | 0 | 1029.1053 | 1075.8621 | 55.1724 | 137.931 | 0 | 23935.2294 | 0 | 0 | 18.3908 | 478.1609 | 1195.4023 | 2390.8046 | 2390.8046 | 358.6207 | 0 | 0 | 0 | 0 | 478.1609 | 0
2025-07-11 | 177411.9912 | 0 | 96480 | 100432.4212 | 2822.7347 | 30658.1928 | 2540.2299 | 40958.4126 | 0 | 0 | 1106.5241 | 0 | 0 | 32565.7471 | 1828.9655 | 0 | 0 | 853.5172 | 0 | 0 | 1936.4172 | 2667.2414 | 0 | 0 | 0 | 0 | 100432.4212 | 0 | 1093.4244 | 1143.1034 | 58.6207 | 146.5517 | 0 | 25431.1813 | 0 | 0 | 19.5402 | 508.046 | 1270.1149 | 2540.2299 | 2540.2299 | 381.0345 | 0 | 0 | 0 | 0 | 508.046 | 0
2025-07-12 | 182172.6966 | 0 | 96480 | 100664.9166 | 2988.7779 | 32461.6159 | 2689.6552 | 43367.731 | 0 | 0 | 1171.6138 | 0 | 0 | 34481.3793 | 1936.5517 | 0 | 0 | 903.7241 | 0 | 0 | 2050.3241 | 2824.1379 | 0 | 0 | 0 | 0 | 100664.9166 | 0 | 1157.7434 | 1210.3448 | 62.069 | 155.1724 | 0 | 26927.1331 | 0 | 0 | 20.6897 | 537.931 | 1344.8276 | 2689.6552 | 2689.6552 | 403.4483 | 0 | 0 | 0 | 0 | 537.931 | 0
2025-07-13 | 186933.4019 | 0 | 96480 | 100897.4119 | 3154.8211 | 34265.039 | 2839.0805 | 45777.0494 | 0 | 0 | 1236.7034 | 0 | 0 | 36397.0115 | 2044.1379 | 0 | 0 | 953.931 | 0 | 0 | 2164.231 | 2981.0345 | 0 | 0 | 0 | 0 | 100897.4119 | 0 | 1222.0625 | 1277.5862 | 65.5172 | 163.7931 | 0 | 28423.0849 | 0 | 0 | 21.8391 | 567.8161 | 1419.5402 | 2839.0805 | 2839.0805 | 425.8621 | 0 | 0 | 0 | 0 | 567.8161 | 0
2025-07-14 | 191694.1073 | 0 | 96480 | 101129.9073 | 3320.8644 | 36068.4621 | 2988.5057 | 48186.3678 | 0 | 0 | 1301.7931 | 0 | 0 | 38312.6437 | 2151.7241 | 0 | 0 | 1004.1379 | 0 | 0 | 2278.1379 | 3137.931 | 0 | 0 | 0 | 0 | 101129.9073 | 0 | 1286.3816 | 1344.8276 | 68.9655 | 172.4138 | 0 | 29919.0368 | 0 | 0 | 22.9885 | 597.7011 | 1494.2529 | 2988.5057 | 2988.5057 | 448.2759 | 0 | 0 | 0 | 0 | 597.7011 | 0
2025-07-15 | 196454.8127 | 0 | 96480 | 101362.4027 | 3486.9076 | 37871.8852 | 3137.931 | 50595.6862 | 0 | 0 | 1366.8828 | 0 | 0 | 40228.2759 | 2259.3103 | 0 | 0 | 1054.3448 | 0 | 0 | 2392.0448 | 3294.8276 | 0 | 0 | 0 | 0 | 101362.4027 | 0 | 1350.7007 | 1412.069 | 72.4138 | 181.0345 | 0 | 31414.9886 | 0 | 0 | 24.1379 | 627.5862 | 1568.9655 | 3137.931 | 3137.931 | 470.6897 | 0 | 0 | 0 | 0 | 627.5862 | 0
2025-07-16 | 201215.518 | 0 | 96480 | 101594.898 | 3652.9508 | 39675.3083 | 3287.3563 | 53005.0046 | 0 | 0 | 1431.9724 | 0 | 0 | 42143.908 | 2366.8966 | 0 | 0 | 1104.5517 | 0 | 0 | 2505.9517 | 3451.7241 | 0 | 0 | 0 | 0 | 101594.898 | 0 | 1415.0198 | 1479.3103 | 75.8621 | 189.6552 | 0 | 32910.9405 | 0 | 0 | 25.2874 | 657.4713 | 1643.6782 | 3287.3563 | 3287.3563 | 493.1034 | 0 | 0 | 0 | 0 | 657.4713 | 0
2025-07-17 | 205976.2234 | 0 | 96480 | 101827.3934 | 3818.994 | 41478.7314 | 3436.7816 | 55414.323 | 0 | 0 | 1497.0621 | 0 | 0 | 44059.5402 | 2474.4828 | 0 | 0 | 1154.7586 | 0 | 0 | 2619.8586 | 3608.6207 | 0 | 0 | 0 | 0 | 101827.3934 | 0 | 1479.3389 | 1546.5517 | 79.3103 | 198.2759 | 0 | 34406.8923 | 0 | 0 | 26.4368 | 687.3563 | 1718.3908 | 3436.7816 | 3436.7816 | 515.5172 | 0 | 0 | 0 | 0 | 687.3563 | 0
2025-07-18 | 210736.9288 | 0 | 96480 | 102059.8888 | 3985.0372 | 43282.1545 | 3586.2069 | 57823.6414 | 0 | 0 | 1562.1517 | 0 | 0 | 45975.1724 | 2582.069 | 0 | 0 | 1204.9655 | 0 | 0 | 2733.7655 | 3765.5172 | 0 | 0 | 0 | 0 | 102059.8888 | 0 | 1543.6579 | 1613.7931 | 82.7586 | 206.8966 | 0 | 35902.8441 | 0 | 0 | 27.5862 | 717.2414 | 1793.1034 | 3586.2069 | 3586.2069 | 537.931 | 0 | 0 | 0 | 0 | 717.2414 | 0
2025-07-19 | 215497.6341 | 0 | 96480 | 102292.3841 | 4151.0805 | 45085.5776 | 3735.6322 | 60232.9598 | 0 | 0 | 1627.2414 | 0 | 0 | 47890.8046 | 2689.6552 | 0 | 0 | 1255.1724 | 0 | 0 | 2847.6724 | 3922.4138 | 0 | 0 | 0 | 0 | 102292.3841 | 0 | 1607.977 | 1681.0345 | 86.2069 | 215.5172 | 0 | 37398.796 | 0 | 0 | 28.7356 | 747.1264 | 1867.8161 | 3735.6322 | 3735.6322 | 560.3448 | 0 | 0 | 0 | 0 | 747.1264 | 0
2025-07-20 | 220258.3395 | 0 | 96480 | 102524.8795 | 4317.1237 | 46889.0007 | 3885.0575 | 62642.2782 | 0 | 0 | 1692.331 | 0 | 0 | 49806.4368 | 2797.2414 | 0 | 0 | 1305.3793 | 0 | 0 | 2961.5793 | 4079.3103 | 0 | 0 | 0 | 0 | 102524.8795 | 0 | 1672.2961 | 1748.2759 | 89.6552 | 224.1379 | 0 | 38894.7478 | 0 | 0 | 29.8851 | 777.0115 | 1942.5287 | 3885.0575 | 3885.0575 | 582.7586 | 0 | 0 | 0 | 0 | 777.0115 | 0
2025-07-21 | 225019.0449 | 0 | 96480 | 102757.3749 | 4483.1669 | 48692.4238 | 4034.4828 | 65051.5966 | 0 | 0 | 1757.4207 | 0 | 0 | 51722.069 | 2904.8276 | 0 | 0 | 1355.5862 | 0 | 0 | 3075.4862 | 4236.2069 | 0 | 0 | 0 | 0 | 102757.3749 | 0 | 1736.6152 | 1815.5172 | 93.1034 | 232.7586 | 0 | 40390.6997 | 0 | 0 | 31.0345 | 806.8966 | 2017.2414 | 4034.4828 | 4034.4828 | 605.1724 | 0 | 0 | 0 | 0 | 806.8966 | 0
2025-07-22 | 229779.7502 | 0 | 96480 | 102989.8702 | 4649.2101 | 50495.8469 | 4183.908 | 67460.9149 | 0 | 0 | 1822.5103 | 0 | 0 | 53637.7011 | 3012.4138 | 0 | 0 | 1405.7931 | 0 | 0 | 3189.3931 | 4393.1034 | 0 | 0 | 0 | 0 | 102989.8702 | 0 | 1800.9343 | 1882.7586 | 96.5517 | 241.3793 | 0 | 41886.6515 | 0 | 0 | 32.1839 | 836.7816 | 2091.954 | 4183.908 | 4183.908 | 627.5862 | 0 | 0 | 0 | 0 | 836.7816 | 0
2025-07-23 | 234540.4556 | 0 | 96480 | 103222.3656 | 4815.2533 | 52299.27 | 4333.3333 | 69870.2333 | 0 | 0 | 1887.6 | 0 | 0 | 55553.3333 | 3120 | 0 | 0 | 1456 | 0 | 0 | 3303.3 | 4550 | 0 | 0 | 0 | 0 | 103222.3656 | 0 | 1865.2533 | 1950 | 100 | 250 | 0 | 43382.6033 | 0 | 0 | 33.3333 | 866.6667 | 2166.6667 | 4333.3333 | 4333.3333 | 650 | 0 | 0 | 0 | 0 | 866.6667 | 0
2025-07-24 | 239301.161 | 0 | 96480 | 103454.861 | 4981.2966 | 54102.6931 | 4482.7586 | 72279.5517 | 0 | 0 | 1952.6897 | 0 | 0 | 57468.9655 | 3227.5862 | 0 | 0 | 1506.2069 | 0 | 0 | 3417.2069 | 4706.8966 | 0 | 0 | 0 | 0 | 103454.861 | 0 | 1929.5724 | 2017.2414 | 103.4483 | 258.6207 | 0 | 44878.5552 | 0 | 0 | 34.4828 | 896.5517 | 2241.3793 | 4482.7586 | 4482.7586 | 672.4138 | 0 | 0 | 0 | 0 | 896.5517 | 0
2025-07-25 | 244061.8663 | 0 | 96480 | 103687.3563 | 5147.3398 | 55906.1162 | 4632.1839 | 74688.8701 | 0 | 0 | 2017.7793 | 0 | 0 | 59384.5977 | 3335.1724 | 0 | 0 | 1556.4138 | 0 | 0 | 3531.1138 | 4863.7931 | 0 | 0 | 0 | 0 | 103687.3563 | 0 | 1993.8915 | 2084.4828 | 106.8966 | 267.2414 | 0 | 46374.507 | 0 | 0 | 35.6322 | 926.4368 | 2316.092 | 4632.1839 | 4632.1839 | 694.8276 | 0 | 0 | 0 | 0 | 926.4368 | 0
2025-07-26 | 248822.5717 | 0 | 96480 | 103919.8517 | 5313.383 | 57709.5393 | 4781.6092 | 77098.1885 | 0 | 0 | 2082.869 | 0 | 0 | 61300.2299 | 3442.7586 | 0 | 0 | 1606.6207 | 0 | 0 | 3645.0207 | 5020.6897 | 0 | 0 | 0 | 0 | 103919.8517 | 0 | 2058.2106 | 2151.7241 | 110.3448 | 275.8621 | 0 | 47870.4589 | 0 | 0 | 36.7816 | 956.3218 | 2390.8046 | 4781.6092 | 4781.6092 | 717.2414 | 0 | 0 | 0 | 0 | 956.3218 | 0
2025-07-27 | 253583.2771 | 0 | 96480 | 104152.3471 | 5479.4262 | 59512.9624 | 4931.0345 | 79507.5069 | 0 | 0 | 2147.9586 | 0 | 0 | 63215.8621 | 3550.3448 | 0 | 0 | 1656.8276 | 0 | 0 | 3758.9276 | 5177.5862 | 0 | 0 | 0 | 0 | 104152.3471 | 0 | 2122.5297 | 2218.9655 | 113.7931 | 284.4828 | 0 | 49366.4107 | 0 | 0 | 37.931 | 986.2069 | 2465.5172 | 4931.0345 | 4931.0345 | 739.6552 | 0 | 0 | 0 | 0 | 986.2069 | 0
2025-07-28 | 258343.9824 | 0 | 96480 | 104384.8424 | 5645.4694 | 61316.3855 | 5080.4598 | 81916.8253 | 0 | 0 | 2213.0483 | 0 | 0 | 65131.4943 | 3657.931 | 0 | 0 | 1707.0345 | 0 | 0 | 3872.8345 | 5334.4828 | 0 | 0 | 0 | 0 | 104384.8424 | 0 | 2186.8487 | 2286.2069 | 117.2414 | 293.1034 | 0 | 50862.3625 | 0 | 0 | 39.0805 | 1016.092 | 2540.2299 | 5080.4598 | 5080.4598 | 762.069 | 0 | 0 | 0 | 0 | 1016.092 | 0
2025-07-29 | 263104.6878 | 0 | 96480 | 104617.3378 | 5811.5126 | 63119.8086 | 5229.8851 | 84326.1437 | 0 | 0 | 2278.1379 | 0 | 0 | 67047.1264 | 3765.5172 | 0 | 0 | 1757.2414 | 0 | 0 | 3986.7414 | 5491.3793 | 0 | 0 | 0 | 0 | 104617.3378 | 0 | 2251.1678 | 2353.4483 | 120.6897 | 301.7241 | 0 | 52358.3144 | 0 | 0 | 40.2299 | 1045.977 | 2614.9425 | 5229.8851 | 5229.8851 | 784.4828 | 0 | 0 | 0 | 0 | 1045.977 | 0
2025-07-30 | 267865.3931 | 0 | 96480 | 104849.8331 | 5977.5559 | 64923.2317 | 5379.3103 | 86735.4621 | 0 | 0 | 2343.2276 | 0 | 0 | 68962.7586 | 3873.1034 | 0 | 0 | 1807.4483 | 0 | 0 | 4100.6483 | 5648.2759 | 0 | 0 | 0 | 0 | 104849.8331 | 0 | 2315.4869 | 2420.6897 | 124.1379 | 310.3448 | 0 | 53854.2662 | 0 | 0 | 41.3793 | 1075.8621 | 2689.6552 | 5379.3103 | 5379.3103 | 806.8966 | 0 | 0 | 0 | 0 | 1075.8621 | 0
2025-07-31 | 272626.0985 | 0 | 96480 | 105082.3285 | 6143.5991 | 66726.6548 | 5528.7356 | 89144.7805 | 0 | 0 | 2408.3172 | 0 | 0 | 70878.3908 | 3980.6897 | 0 | 0 | 1857.6552 | 0 | 0 | 4214.5552 | 5805.1724 | 0 | 0 | 0 | 0 | 105082.3285 | 0 | 2379.806 | 2487.931 | 127.5862 | 318.9655 | 0 | 55350.218 | 0 | 0 | 42.5287 | 1105.7471 | 2764.3678 | 5528.7356 | 5528.7356 | 829.3103 | 0 | 0 | 0 | 0 | 1105.7471 | 0
2025-08-01 | 277386.8039 | 0 | 96480 | 105314.8239 | 6309.6423 | 68530.0779 | 5678.1609 | 91554.0989 | 0 | 0 | 2473.4069 | 0 | 0 | 72794.023 | 4088.2759 | 0 | 0 | 1907.8621 | 0 | 0 | 4328.4621 | 5962.069 | 0 | 0 | 0 | 0 | 105314.8239 | 0 | 2444.1251 | 2555.1724 | 131.0345 | 327.5862 | 0 | 56846.1699 | 0 | 0 | 43.6782 | 1135.6322 | 2839.0805 | 5678.1609 | 5678.1609 | 851.7241 | 0 | 0 | 0 | 0 | 1135.6322 | 0
2025-08-02 | 282147.5092 | 0 | 96480 | 105547.3192 | 6475.6855 | 70333.501 | 5827.5862 | 93963.4172 | 0 | 0 | 2538.4966 | 0 | 0 | 74709.6552 | 4195.8621 | 0 | 0 | 1958.069 | 0 | 0 | 4442.369 | 6118.9655 | 0 | 0 | 0 | 0 | 105547.3192 | 0 | 2508.4441 | 2622.4138 | 134.4828 | 336.2069 | 0 | 58342.1217 | 0 | 0 | 44.8276 | 1165.5172 | 2913.7931 | 5827.5862 | 5827.5862 | 874.1379 | 0 | 0 | 0 | 0 | 1165.5172 | 0
2025-08-03 | 286908.2146 | 0 | 96480 | 105779.8146 | 6641.7287 | 72136.9241 | 5977.0115 | 96372.7356 | 0 | 0 | 2603.5862 | 0 | 0 | 76625.2874 | 4303.4483 | 0 | 0 | 2008.2759 | 0 | 0 | 4556.2759 | 6275.8621 | 0 | 0 | 0 | 0 | 105779.8146 | 0 | 2572.7632 | 2689.6552 | 137.931 | 344.8276 | 0 | 59838.0736 | 0 | 0 | 45.977 | 1195.4023 | 2988.5057 | 5977.0115 | 5977.0115 | 896.5517 | 0 | 0 | 0 | 0 | 1195.4023 | 0
2025-08-04 | 291668.92 | 0 | 96480 | 106012.31 | 6807.772 | 73940.3472 | 6126.4368 | 98782.054 | 0 | 0 | 2668.6759 | 0 | 0 | 78540.9195 | 4411.0345 | 0 | 0 | 2058.4828 | 0 | 0 | 4670.1828 | 6432.7586 | 0 | 0 | 0 | 0 | 106012.31 | 0 | 2637.0823 | 2756.8966 | 141.3793 | 353.4483 | 0 | 61334.0254 | 0 | 0 | 47.1264 | 1225.2874 | 3063.2184 | 6126.4368 | 6126.4368 | 918.9655 | 0 | 0 | 0 | 0 | 1225.2874 | 0
2025-08-05 | 296429.6253 | 0 | 96480 | 106244.8053 | 6973.8152 | 75743.7703 | 6275.8621 | 101191.3724 | 0 | 0 | 2733.7655 | 0 | 0 | 80456.5517 | 4518.6207 | 0 | 0 | 2108.6897 | 0 | 0 | 4784.0897 | 6589.6552 | 0 | 0 | 0 | 0 | 106244.8053 | 0 | 2701.4014 | 2824.1379 | 144.8276 | 362.069 | 0 | 62829.9772 | 0 | 0 | 48.2759 | 1255.1724 | 3137.931 | 6275.8621 | 6275.8621 | 941.3793 | 0 | 0 | 0 | 0 | 1255.1724 | 0
2025-08-06 | 301190.3307 | 0 | 96480 | 106477.3007 | 7139.8584 | 77547.1934 | 6425.2874 | 103600.6908 | 0 | 0 | 2798.8552 | 0 | 0 | 82372.1839 | 4626.2069 | 0 | 0 | 2158.8966 | 0 | 0 | 4897.9966 | 6746.5517 | 0 | 0 | 0 | 0 | 106477.3007 | 0 | 2765.7205 | 2891.3793 | 148.2759 | 370.6897 | 0 | 64325.9291 | 0 | 0 | 49.4253 | 1285.0575 | 3212.6437 | 6425.2874 | 6425.2874 | 963.7931 | 0 | 0 | 0 | 0 | 1285.0575 | 0
2025-08-07 | 305951.0361 | 0 | 96480 | 106709.7961 | 7305.9016 | 79350.6166 | 6574.7126 | 106010.0092 | 0 | 0 | 2863.9448 | 0 | 0 | 84287.8161 | 4733.7931 | 0 | 0 | 2209.1034 | 0 | 0 | 5011.9034 | 6903.4483 | 0 | 0 | 0 | 0 | 106709.7961 | 0 | 2830.0395 | 2958.6207 | 151.7241 | 379.3103 | 0 | 65821.8809 | 0 | 0 | 50.5747 | 1314.9425 | 3287.3563 | 6574.7126 | 6574.7126 | 986.2069 | 0 | 0 | 0 | 0 | 1314.9425 | 0
2025-08-08 | 310711.7414 | 0 | 96480 | 106942.2914 | 7471.9448 | 81154.0397 | 6724.1379 | 108419.3276 | 0 | 0 | 2929.0345 | 0 | 0 | 86203.4483 | 4841.3793 | 0 | 0 | 2259.3103 | 0 | 0 | 5125.8103 | 7060.3448 | 0 | 0 | 0 | 0 | 106942.2914 | 0 | 2894.3586 | 3025.8621 | 155.1724 | 387.931 | 0 | 67317.8328 | 0 | 0 | 51.7241 | 1344.8276 | 3362.069 | 6724.1379 | 6724.1379 | 1008.6207 | 0 | 0 | 0 | 0 | 1344.8276 | 0
2025-08-09 | 315472.4468 | 0 | 96480 | 107174.7868 | 7637.988 | 82957.4628 | 6873.5632 | 110828.646 | 0 | 0 | 2994.1241 | 0 | 0 | 88119.0805 | 4948.9655 | 0 | 0 | 2309.5172 | 0 | 0 | 5239.7172 | 7217.2414 | 0 | 0 | 0 | 0 | 107174.7868 | 0 | 2958.6777 | 3093.1034 | 158.6207 | 396.5517 | 0 | 68813.7846 | 0 | 0 | 52.8736 | 1374.7126 | 3436.7816 | 6873.5632 | 6873.5632 | 1031.0345 | 0 | 0 | 0 | 0 | 1374.7126 | 0
2025-08-10 | 320233.1522 | 0 | 96480 | 107407.2822 | 7804.0313 | 84760.8859 | 7022.9885 | 113237.9644 | 0 | 0 | 3059.2138 | 0 | 0 | 90034.7126 | 5056.5517 | 0 | 0 | 2359.7241 | 0 | 0 | 5353.6241 | 7374.1379 | 0 | 0 | 0 | 0 | 107407.2822 | 0 | 3022.9968 | 3160.3448 | 162.069 | 405.1724 | 0 | 70309.7364 | 0 | 0 | 54.023 | 1404.5977 | 3511.4943 | 7022.9885 | 7022.9885 | 1053.4483 | 0 | 0 | 0 | 0 | 1404.5977 | 0
2025-08-11 | 324993.8575 | 0 | 96480 | 107639.7775 | 7970.0745 | 86564.309 | 7172.4138 | 115647.2828 | 0 | 0 | 3124.3034 | 0 | 0 | 91950.3448 | 5164.1379 | 0 | 0 | 2409.931 | 0 | 0 | 5467.531 | 7531.0345 | 0 | 0 | 0 | 0 | 107639.7775 | 0 | 3087.3159 | 3227.5862 | 165.5172 | 413.7931 | 0 | 71805.6883 | 0 | 0 | 55.1724 | 1434.4828 | 3586.2069 | 7172.4138 | 7172.4138 | 1075.8621 | 0 | 0 | 0 | 0 | 1434.4828 | 0
2025-08-12 | 329754.5629 | 0 | 96480 | 107872.2729 | 8136.1177 | 88367.7321 | 7321.8391 | 118056.6011 | 0 | 0 | 3189.3931 | 0 | 0 | 93865.977 | 5271.7241 | 0 | 0 | 2460.1379 | 0 | 0 | 5581.4379 | 7687.931 | 0 | 0 | 0 | 0 | 107872.2729 | 0 | 3151.6349 | 3294.8276 | 168.9655 | 422.4138 | 0 | 73301.6401 | 0 | 0 | 56.3218 | 1464.3678 | 3660.9195 | 7321.8391 | 7321.8391 | 1098.2759 | 0 | 0 | 0 | 0 | 1464.3678 | 0
2025-08-13 | 334515.2683 | 0 | 96480 | 108104.7683 | 8302.1609 | 90171.1552 | 7471.2644 | 120465.9195 | 0 | 0 | 3254.4828 | 0 | 0 | 95781.6092 | 5379.3103 | 0 | 0 | 2510.3448 | 0 | 0 | 5695.3448 | 7844.8276 | 0 | 0 | 0 | 0 | 108104.7683 | 0 | 3215.954 | 3362.069 | 172.4138 | 431.0345 | 0 | 74797.592 | 0 | 0 | 57.4713 | 1494.2529 | 3735.6322 | 7471.2644 | 7471.2644 | 1120.6897 | 0 | 0 | 0 | 0 | 1494.2529 | 0
2025-08-14 | 339275.9736 | 0 | 96480 | 108337.2636 | 8468.2041 | 91974.5783 | 7620.6897 | 122875.2379 | 0 | 0 | 3319.5724 | 0 | 0 | 97697.2414 | 5486.8966 | 0 | 0 | 2560.5517 | 0 | 0 | 5809.2517 | 8001.7241 | 0 | 0 | 0 | 0 | 108337.2636 | 0 | 3280.2731 | 3429.3103 | 175.8621 | 439.6552 | 0 | 76293.5438 | 0 | 0 | 58.6207 | 1524.1379 | 3810.3448 | 7620.6897 | 7620.6897 | 1143.1034 | 0 | 0 | 0 | 0 | 1524.1379 | 0
2025-08-15 | 344036.679 | 0 | 96480 | 108569.759 | 8634.2474 | 93778.0014 | 7770.1149 | 125284.5563 | 0 | 0 | 3384.6621 | 0 | 0 | 99612.8736 | 5594.4828 | 0 | 0 | 2610.7586 | 0 | 0 | 5923.1586 | 8158.6207 | 0 | 0 | 0 | 0 | 108569.759 | 0 | 3344.5922 | 3496.5517 | 179.3103 | 448.2759 | 0 | 77789.4956 | 0 | 0 | 59.7701 | 1554.023 | 3885.0575 | 7770.1149 | 7770.1149 | 1165.5172 | 0 | 0 | 0 | 0 | 1554.023 | 0
2025-08-16 | 348797.3844 | 0 | 96480 | 108802.2544 | 8800.2906 | 95581.4245 | 7919.5402 | 127693.8747 | 0 | 0 | 3449.7517 | 0 | 0 | 101528.5057 | 5702.069 | 0 | 0 | 2660.9655 | 0 | 0 | 6037.0655 | 8315.5172 | 0 | 0 | 0 | 0 | 108802.2544 | 0 | 3408.9113 | 3563.7931 | 182.7586 | 456.8966 | 0 | 79285.4475 | 0 | 0 | 60.9195 | 1583.908 | 3959.7701 | 7919.5402 | 7919.5402 | 1187.931 | 0 | 0 | 0 | 0 | 1583.908 | 0
2025-08-17 | 353558.0897 | 0 | 96480 | 109034.7497 | 8966.3338 | 97384.8476 | 8068.9655 | 130103.1931 | 0 | 0 | 3514.8414 | 0 | 0 | 103444.1379 | 5809.6552 | 0 | 0 | 2711.1724 | 0 | 0 | 6150.9724 | 8472.4138 | 0 | 0 | 0 | 0 | 109034.7497 | 0 | 3473.2303 | 3631.0345 | 186.2069 | 465.5172 | 0 | 80781.3993 | 0 | 0 | 62.069 | 1613.7931 | 4034.4828 | 8068.9655 | 8068.9655 | 1210.3448 | 0 | 0 | 0 | 0 | 1613.7931 | 0
2025-08-18 | 358318.7951 | 0 | 96480 | 109267.2451 | 9132.377 | 99188.2707 | 8218.3908 | 132512.5115 | 0 | 0 | 3579.931 | 0 | 0 | 105359.7701 | 5917.2414 | 0 | 0 | 2761.3793 | 0 | 0 | 6264.8793 | 8629.3103 | 0 | 0 | 0 | 0 | 109267.2451 | 0 | 3537.5494 | 3698.2759 | 189.6552 | 474.1379 | 0 | 82277.3511 | 0 | 0 | 63.2184 | 1643.6782 | 4109.1954 | 8218.3908 | 8218.3908 | 1232.7586 | 0 | 0 | 0 | 0 | 1643.6782 | 0
2025-08-19 | 363079.5005 | 0 | 96480 | 109499.7405 | 9298.4202 | 100991.6938 | 8367.8161 | 134921.8299 | 0 | 0 | 3645.0207 | 0 | 0 | 107275.4023 | 6024.8276 | 0 | 0 | 2811.5862 | 0 | 0 | 6378.7862 | 8786.2069 | 0 | 0 | 0 | 0 | 109499.7405 | 0 | 3601.8685 | 3765.5172 | 193.1034 | 482.7586 | 0 | 83773.303 | 0 | 0 | 64.3678 | 1673.5632 | 4183.908 | 8367.8161 | 8367.8161 | 1255.1724 | 0 | 0 | 0 | 0 | 1673.5632 | 0
2025-08-20 | 367840.2058 | 0 | 96480 | 109732.2358 | 9464.4634 | 102795.1169 | 8517.2414 | 137331.1483 | 0 | 0 | 3710.1103 | 0 | 0 | 109191.0345 | 6132.4138 | 0 | 0 | 2861.7931 | 0 | 0 | 6492.6931 | 8943.1034 | 0 | 0 | 0 | 0 | 109732.2358 | 0 | 3666.1876 | 3832.7586 | 196.5517 | 491.3793 | 0 | 85269.2548 | 0 | 0 | 65.5172 | 1703.4483 | 4258.6207 | 8517.2414 | 8517.2414 | 1277.5862 | 0 | 0 | 0 | 0 | 1703.4483 | 0
2025-08-21 | 372600.9112 | 0 | 96480 | 109964.7312 | 9630.5067 | 104598.54 | 8666.6667 | 139740.4667 | 0 | 0 | 3775.2 | 0 | 0 | 111106.6667 | 6240 | 0 | 0 | 2912 | 0 | 0 | 6606.6 | 9100 | 0 | 0 | 0 | 0 | 109964.7312 | 0 | 3730.5067 | 3900 | 200 | 500 | 0 | 86765.2067 | 0 | 0 | 66.6667 | 1733.3333 | 4333.3333 | 8666.6667 | 8666.6667 | 1300 | 0 | 0 | 0 | 0 | 1733.3333 | 0
2025-08-22 | 377361.6165 | 0 | 96480 | 110197.2265 | 9796.5499 | 106401.9631 | 8816.092 | 142149.7851 | 0 | 0 | 3840.2897 | 0 | 0 | 113022.2989 | 6347.5862 | 0 | 0 | 2962.2069 | 0 | 0 | 6720.5069 | 9256.8966 | 0 | 0 | 0 | 0 | 110197.2265 | 0 | 3794.8257 | 3967.2414 | 203.4483 | 508.6207 | 0 | 88261.1585 | 0 | 0 | 67.8161 | 1763.2184 | 4408.046 | 8816.092 | 8816.092 | 1322.4138 | 0 | 0 | 0 | 0 | 1763.2184 | 0
2025-08-23 | 382122.3219 | 0 | 96480 | 110429.7219 | 9962.5931 | 108205.3862 | 8965.5172 | 144559.1034 | 0 | 0 | 3905.3793 | 0 | 0 | 114937.931 | 6455.1724 | 0 | 0 | 3012.4138 | 0 | 0 | 6834.4138 | 9413.7931 | 0 | 0 | 0 | 0 | 110429.7219 | 0 | 3859.1448 | 4034.4828 | 206.8966 | 517.2414 | 0 | 89757.1103 | 0 | 0 | 68.9655 | 1793.1034 | 4482.7586 | 8965.5172 | 8965.5172 | 1344.8276 | 0 | 0 | 0 | 0 | 1793.1034 | 0
2025-08-24 | 386883.0273 | 0 | 96480 | 110662.2173 | 10128.6363 | 110008.8093 | 9114.9425 | 146968.4218 | 0 | 0 | 3970.469 | 0 | 0 | 116853.5632 | 6562.7586 | 0 | 0 | 3062.6207 | 0 | 0 | 6948.3207 | 9570.6897 | 0 | 0 | 0 | 0 | 110662.2173 | 0 | 3923.4639 | 4101.7241 | 210.3448 | 525.8621 | 0 | 91253.0622 | 0 | 0 | 70.1149 | 1822.9885 | 4557.4713 | 9114.9425 | 9114.9425 | 1367.2414 | 0 | 0 | 0 | 0 | 1822.9885 | 0
2025-08-25 | 391643.7326 | 0 | 96480 | 110894.7126 | 10294.6795 | 111812.2324 | 9264.3678 | 149377.7402 | 0 | 0 | 4035.5586 | 0 | 0 | 118769.1954 | 6670.3448 | 0 | 0 | 3112.8276 | 0 | 0 | 7062.2276 | 9727.5862 | 0 | 0 | 0 | 0 | 110894.7126 | 0 | 3987.783 | 4168.9655 | 213.7931 | 534.4828 | 0 | 92749.014 | 0 | 0 | 71.2644 | 1852.8736 | 4632.1839 | 9264.3678 | 9264.3678 | 1389.6552 | 0 | 0 | 0 | 0 | 1852.8736 | 0
2025-08-26 | 396404.438 | 0 | 96480 | 111127.208 | 10460.7228 | 113615.6555 | 9413.7931 | 151787.0586 | 0 | 0 | 4100.6483 | 0 | 0 | 120684.8276 | 6777.931 | 0 | 0 | 3163.0345 | 0 | 0 | 7176.1345 | 9884.4828 | 0 | 0 | 0 | 0 | 111127.208 | 0 | 4052.1021 | 4236.2069 | 217.2414 | 543.1034 | 0 | 94244.9659 | 0 | 0 | 72.4138 | 1882.7586 | 4706.8966 | 9413.7931 | 9413.7931 | 1412.069 | 0 | 0 | 0 | 0 | 1882.7586 | 0
2025-08-27 | 401165.1434 | 0 | 96480 | 111359.7034 | 10626.766 | 115419.0786 | 9563.2184 | 154196.377 | 0 | 0 | 4165.7379 | 0 | 0 | 122600.4598 | 6885.5172 | 0 | 0 | 3213.2414 | 0 | 0 | 7290.0414 | 10041.3793 | 0 | 0 | 0 | 0 | 111359.7034 | 0 | 4116.4211 | 4303.4483 | 220.6897 | 551.7241 | 0 | 95740.9177 | 0 | 0 | 73.5632 | 1912.6437 | 4781.6092 | 9563.2184 | 9563.2184 | 1434.4828 | 0 | 0 | 0 | 0 | 1912.6437 | 0
2025-08-28 | 405925.8487 | 0 | 96480 | 111592.1987 | 10792.8092 | 117222.5017 | 9712.6437 | 156605.6954 | 0 | 0 | 4230.8276 | 0 | 0 | 124516.092 | 6993.1034 | 0 | 0 | 3263.4483 | 0 | 0 | 7403.9483 | 10198.2759 | 0 | 0 | 0 | 0 | 111592.1987 | 0 | 4180.7402 | 4370.6897 | 224.1379 | 560.3448 | 0 | 97236.8695 | 0 | 0 | 74.7126 | 1942.5287 | 4856.3218 | 9712.6437 | 9712.6437 | 1456.8966 | 0 | 0 | 0 | 0 | 1942.5287 | 0
2025-08-29 | 410686.5541 | 0 | 96480 | 111824.6941 | 10958.8524 | 119025.9248 | 9862.069 | 159015.0138 | 0 | 0 | 4295.9172 | 0 | 0 | 126431.7241 | 7100.6897 | 0 | 0 | 3313.6552 | 0 | 0 | 7517.8552 | 10355.1724 | 0 | 0 | 0 | 0 | 111824.6941 | 0 | 4245.0593 | 4437.931 | 227.5862 | 568.9655 | 0 | 98732.8214 | 0 | 0 | 75.8621 | 1972.4138 | 4931.0345 | 9862.069 | 9862.069 | 1479.3103 | 0 | 0 | 0 | 0 | 1972.4138 | 0
2025-08-30 | 415447.2595 | 0 | 96480 | 112057.1895 | 11124.8956 | 120829.3479 | 10011.4943 | 161424.3322 | 0 | 0 | 4361.0069 | 0 | 0 | 128347.3563 | 7208.2759 | 0 | 0 | 3363.8621 | 0 | 0 | 7631.7621 | 10512.069 | 0 | 0 | 0 | 0 | 112057.1895 | 0 | 4309.3784 | 4505.1724 | 231.0345 | 577.5862 | 0 | 100228.7732 | 0 | 0 | 77.0115 | 2002.2989 | 5005.7471 | 10011.4943 | 10011.4943 | 1501.7241 | 0 | 0 | 0 | 0 | 2002.2989 | 0
2025-08-31 | 420207.9648 | 0 | 96480 | 112289.6848 | 11290.9389 | 122632.771 | 10160.9195 | 163833.6506 | 0 | 0 | 4426.0966 | 0 | 0 | 130262.9885 | 7315.8621 | 0 | 0 | 3414.069 | 0 | 0 | 7745.669 | 10668.9655 | 0 | 0 | 0 | 0 | 112289.6848 | 0 | 4373.6975 | 4572.4138 | 234.4828 | 586.2069 | 0 | 101724.7251 | 0 | 0 | 78.1609 | 2032.1839 | 5080.4598 | 10160.9195 | 10160.9195 | 1524.1379 | 0 | 0 | 0 | 0 | 2032.1839 | 0
2025-09-01 | 424968.6702 | 0 | 96480 | 112522.1802 | 11456.9821 | 124436.1941 | 10310.3448 | 166242.969 | 0 | 0 | 4491.1862 | 0 | 0 | 132178.6207 | 7423.4483 | 0 | 0 | 3464.2759 | 0 | 0 | 7859.5759 | 10825.8621 | 0 | 0 | 0 | 0 | 112522.1802 | 0 | 4438.0166 | 4639.6552 | 237.931 | 594.8276 | 0 | 103220.6769 | 0 | 0 | 79.3103 | 2062.069 | 5155.1724 | 10310.3448 | 10310.3448 | 1546.5517 | 0 | 0 | 0 | 0 | 2062.069 | 0
2025-09-02 | 429729.3756 | 0 | 96480 | 112754.6756 | 11623.0253 | 126239.6172 | 10459.7701 | 168652.2874 | 0 | 0 | 4556.2759 | 0 | 0 | 134094.2529 | 7531.0345 | 0 | 0 | 3514.4828 | 0 | 0 | 7973.4828 | 10982.7586 | 0 | 0 | 0 | 0 | 112754.6756 | 0 | 4502.3356 | 4706.8966 | 241.3793 | 603.4483 | 0 | 104716.6287 | 0 | 0 | 80.4598 | 2091.954 | 5229.8851 | 10459.7701 | 10459.7701 | 1568.9655 | 0 | 0 | 0 | 0 | 2091.954 | 0
2025-09-03 | 434490.0809 | 0 | 96480 | 112987.1709 | 11789.0685 | 128043.0403 | 10609.1954 | 171061.6057 | 0 | 0 | 4621.3655 | 0 | 0 | 136009.8851 | 7638.6207 | 0 | 0 | 3564.6897 | 0 | 0 | 8087.3897 | 11139.6552 | 0 | 0 | 0 | 0 | 112987.1709 | 0 | 4566.6547 | 4774.1379 | 244.8276 | 612.069 | 0 | 106212.5806 | 0 | 0 | 81.6092 | 2121.8391 | 5304.5977 | 10609.1954 | 10609.1954 | 1591.3793 | 0 | 0 | 0 | 0 | 2121.8391 | 0
2025-09-04 | 439250.7863 | 0 | 96480 | 113219.6663 | 11955.1117 | 129846.4634 | 10758.6207 | 173470.9241 | 0 | 0 | 4686.4552 | 0 | 0 | 137925.5172 | 7746.2069 | 0 | 0 | 3614.8966 | 0 | 0 | 8201.2966 | 11296.5517 | 0 | 0 | 0 | 0 | 113219.6663 | 0 | 4630.9738 | 4841.3793 | 248.2759 | 620.6897 | 0 | 107708.5324 | 0 | 0 | 82.7586 | 2151.7241 | 5379.3103 | 10758.6207 | 10758.6207 | 1613.7931 | 0 | 0 | 0 | 0 | 2151.7241 | 0
2025-09-05 | 444011.4917 | 0 | 96480 | 113452.1617 | 12121.1549 | 131649.8866 | 10908.046 | 175880.2425 | 0 | 0 | 4751.5448 | 0 | 0 | 139841.1494 | 7853.7931 | 0 | 0 | 3665.1034 | 0 | 0 | 8315.2034 | 11453.4483 | 0 | 0 | 0 | 0 | 113452.1617 | 0 | 4695.2929 | 4908.6207 | 251.7241 | 629.3103 | 0 | 109204.4843 | 0 | 0 | 83.908 | 2181.6092 | 5454.023 | 10908.046 | 10908.046 | 1636.2069 | 0 | 0 | 0 | 0 | 2181.6092 | 0
2025-09-06 | 448772.197 | 0 | 96480 | 113684.657 | 12287.1982 | 133453.3097 | 11057.4713 | 178289.5609 | 0 | 0 | 4816.6345 | 0 | 0 | 141756.7816 | 7961.3793 | 0 | 0 | 3715.3103 | 0 | 0 | 8429.1103 | 11610.3448 | 0 | 0 | 0 | 0 | 113684.657 | 0 | 4759.612 | 4975.8621 | 255.1724 | 637.931 | 0 | 110700.4361 | 0 | 0 | 85.0575 | 2211.4943 | 5528.7356 | 11057.4713 | 11057.4713 | 1658.6207 | 0 | 0 | 0 | 0 | 2211.4943 | 0
2025-09-07 | 453532.9024 | 0 | 96480 | 113917.1524 | 12453.2414 | 135256.7328 | 11206.8966 | 180698.8793 | 0 | 0 | 4881.7241 | 0 | 0 | 143672.4138 | 8068.9655 | 0 | 0 | 3765.5172 | 0 | 0 | 8543.0172 | 11767.2414 | 0 | 0 | 0 | 0 | 113917.1524 | 0 | 4823.931 | 5043.1034 | 258.6207 | 646.5517 | 0 | 112196.3879 | 0 | 0 | 86.2069 | 2241.3793 | 5603.4483 | 11206.8966 | 11206.8966 | 1681.0345 | 0 | 0 | 0 | 0 | 2241.3793 | 0
2025-09-08 | 458293.6078 | 0 | 96480 | 114149.6478 | 12619.2846 | 137060.1559 | 11356.3218 | 183108.1977 | 0 | 0 | 4946.8138 | 0 | 0 | 145588.046 | 8176.5517 | 0 | 0 | 3815.7241 | 0 | 0 | 8656.9241 | 11924.1379 | 0 | 0 | 0 | 0 | 114149.6478 | 0 | 4888.2501 | 5110.3448 | 262.069 | 655.1724 | 0 | 113692.3398 | 0 | 0 | 87.3563 | 2271.2644 | 5678.1609 | 11356.3218 | 11356.3218 | 1703.4483 | 0 | 0 | 0 | 0 | 2271.2644 | 0
2025-09-09 | 463054.3131 | 0 | 96480 | 114382.1431 | 12785.3278 | 138863.579 | 11505.7471 | 185517.5161 | 0 | 0 | 5011.9034 | 0 | 0 | 147503.6782 | 8284.1379 | 0 | 0 | 3865.931 | 0 | 0 | 8770.831 | 12081.0345 | 0 | 0 | 0 | 0 | 114382.1431 | 0 | 4952.5692 | 5177.5862 | 265.5172 | 663.7931 | 0 | 115188.2916 | 0 | 0 | 88.5057 | 2301.1494 | 5752.8736 | 11505.7471 | 11505.7471 | 1725.8621 | 0 | 0 | 0 | 0 | 2301.1494 | 0
2025-09-10 | 467815.0185 | 0 | 96480 | 114614.6385 | 12951.371 | 140667.0021 | 11655.1724 | 187926.8345 | 0 | 0 | 5076.9931 | 0 | 0 | 149419.3103 | 8391.7241 | 0 | 0 | 3916.1379 | 0 | 0 | 8884.7379 | 12237.931 | 0 | 0 | 0 | 0 | 114614.6385 | 0 | 5016.8883 | 5244.8276 | 268.9655 | 672.4138 | 0 | 116684.2434 | 0 | 0 | 89.6552 | 2331.0345 | 5827.5862 | 11655.1724 | 11655.1724 | 1748.2759 | 0 | 0 | 0 | 0 | 2331.0345 | 0
2025-09-11 | 472575.7239 | 0 | 96480 | 114847.1339 | 13117.4143 | 142470.4252 | 11804.5977 | 190336.1529 | 0 | 0 | 5142.0828 | 0 | 0 | 151334.9425 | 8499.3103 | 0 | 0 | 3966.3448 | 0 | 0 | 8998.6448 | 12394.8276 | 0 | 0 | 0 | 0 | 114847.1339 | 0 | 5081.2074 | 5312.069 | 272.4138 | 681.0345 | 0 | 118180.1953 | 0 | 0 | 90.8046 | 2360.9195 | 5902.2989 | 11804.5977 | 11804.5977 | 1770.6897 | 0 | 0 | 0 | 0 | 2360.9195 | 0
2025-09-12 | 477336.4292 | 0 | 96480 | 115079.6292 | 13283.4575 | 144273.8483 | 11954.023 | 192745.4713 | 0 | 0 | 5207.1724 | 0 | 0 | 153250.5747 | 8606.8966 | 0 | 0 | 4016.5517 | 0 | 0 | 9112.5517 | 12551.7241 | 0 | 0 | 0 | 0 | 115079.6292 | 0 | 5145.5264 | 5379.3103 | 275.8621 | 689.6552 | 0 | 119676.1471 | 0 | 0 | 91.954 | 2390.8046 | 5977.0115 | 11954.023 | 11954.023 | 1793.1034 | 0 | 0 | 0 | 0 | 2390.8046 | 0
2025-09-13 | 482097.1346 | 0 | 96480 | 115312.1246 | 13449.5007 | 146077.2714 | 12103.4483 | 195154.7897 | 0 | 0 | 5272.2621 | 0 | 0 | 155166.2069 | 8714.4828 | 0 | 0 | 4066.7586 | 0 | 0 | 9226.4586 | 12708.6207 | 0 | 0 | 0 | 0 | 115312.1246 | 0 | 5209.8455 | 5446.5517 | 279.3103 | 698.2759 | 0 | 121172.099 | 0 | 0 | 93.1034 | 2420.6897 | 6051.7241 | 12103.4483 | 12103.4483 | 1815.5172 | 0 | 0 | 0 | 0 | 2420.6897 | 0
2025-09-14 | 486857.8399 | 0 | 96480 | 115544.6199 | 13615.5439 | 147880.6945 | 12252.8736 | 197564.108 | 0 | 0 | 5337.3517 | 0 | 0 | 157081.8391 | 8822.069 | 0 | 0 | 4116.9655 | 0 | 0 | 9340.3655 | 12865.5172 | 0 | 0 | 0 | 0 | 115544.6199 | 0 | 5274.1646 | 5513.7931 | 282.7586 | 706.8966 | 0 | 122668.0508 | 0 | 0 | 94.2529 | 2450.5747 | 6126.4368 | 12252.8736 | 12252.8736 | 1837.931 | 0 | 0 | 0 | 0 | 2450.5747 | 0
2025-09-15 | 491618.5453 | 0 | 96480 | 115777.1153 | 13781.5871 | 149684.1176 | 12402.2989 | 199973.4264 | 0 | 0 | 5402.4414 | 0 | 0 | 158997.4713 | 8929.6552 | 0 | 0 | 4167.1724 | 0 | 0 | 9454.2724 | 13022.4138 | 0 | 0 | 0 | 0 | 115777.1153 | 0 | 5338.4837 | 5581.0345 | 286.2069 | 715.5172 | 0 | 124164.0026 | 0 | 0 | 95.4023 | 2480.4598 | 6201.1494 | 12402.2989 | 12402.2989 | 1860.3448 | 0 | 0 | 0 | 0 | 2480.4598 | 0
2025-09-16 | 496379.2507 | 0 | 96480 | 116009.6107 | 13947.6303 | 151487.5407 | 12551.7241 | 202382.7448 | 0 | 0 | 5467.531 | 0 | 0 | 160913.1034 | 9037.2414 | 0 | 0 | 4217.3793 | 0 | 0 | 9568.1793 | 13179.3103 | 0 | 0 | 0 | 0 | 116009.6107 | 0 | 5402.8028 | 5648.2759 | 289.6552 | 724.1379 | 0 | 125659.9545 | 0 | 0 | 96.5517 | 2510.3448 | 6275.8621 | 12551.7241 | 12551.7241 | 1882.7586 | 0 | 0 | 0 | 0 | 2510.3448 | 0
2025-09-17 | 501139.956 | 0 | 96480 | 116242.106 | 14113.6736 | 153290.9638 | 12701.1494 | 204792.0632 | 0 | 0 | 5532.6207 | 0 | 0 | 162828.7356 | 9144.8276 | 0 | 0 | 4267.5862 | 0 | 0 | 9682.0862 | 13336.2069 | 0 | 0 | 0 | 0 | 116242.106 | 0 | 5467.1218 | 5715.5172 | 293.1034 | 732.7586 | 0 | 127155.9063 | 0 | 0 | 97.7011 | 2540.2299 | 6350.5747 | 12701.1494 | 12701.1494 | 1905.1724 | 0 | 0 | 0 | 0 | 2540.2299 | 0
2025-09-18 | 505900.6614 | 0 | 96480 | 116474.6014 | 14279.7168 | 155094.3869 | 12850.5747 | 207201.3816 | 0 | 0 | 5597.7103 | 0 | 0 | 164744.3678 | 9252.4138 | 0 | 0 | 4317.7931 | 0 | 0 | 9795.9931 | 13493.1034 | 0 | 0 | 0 | 0 | 116474.6014 | 0 | 5531.4409 | 5782.7586 | 296.5517 | 741.3793 | 0 | 128651.8582 | 0 | 0 | 98.8506 | 2570.1149 | 6425.2874 | 12850.5747 | 12850.5747 | 1927.5862 | 0 | 0 | 0 | 0 | 2570.1149 | 0
2025-09-19 | 510661.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 156897.81 | 13000 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-20 | 510661.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 156897.81 | 13000 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-21 | 510661.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 156897.81 | 13000 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-22 | 518352.3286 | 0 | 96480 | 121235.7135 | 15652.8678 | 158555.008 | 13020.5882 | 209888.151 | 277.451 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 557.4039 | 121235.7135 | 0 | 5636.5443 | 6390 | 361.1765 | 902.9412 | 0 | 130595.1629 | 0 | 0 | 100 | 2796.1176 | 6500 | 13020.5882 | 13044.1176 | 2273.5294 | 88.6765 | 0 | 0 | 0 | 2600 | 0
2025-09-23 | 526043.2904 | 0 | 96480 | 125764.3302 | 16859.9757 | 160212.2061 | 13041.1765 | 210165.602 | 554.902 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 1114.8078 | 125764.3302 | 0 | 5677.3286 | 6930 | 422.3529 | 1055.8824 | 0 | 131042.5159 | 0 | 0 | 100 | 2992.2353 | 6500 | 13041.1765 | 13088.2353 | 2597.0588 | 177.3529 | 0 | 0 | 0 | 2600 | 0
2025-09-24 | 533734.2522 | 0 | 96480 | 130292.9469 | 18067.0835 | 161869.4041 | 13061.7647 | 210443.0529 | 832.3529 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 1672.2118 | 130292.9469 | 0 | 5718.1129 | 7470 | 483.5294 | 1208.8235 | 0 | 131489.8688 | 0 | 0 | 100 | 3188.3529 | 6500 | 13061.7647 | 13132.3529 | 2920.5882 | 266.0294 | 0 | 0 | 0 | 2600 | 0
2025-09-25 | 541425.214 | 0 | 96480 | 134821.5636 | 19274.1914 | 163526.6022 | 13082.3529 | 210720.5039 | 1109.8039 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 2229.6157 | 134821.5636 | 0 | 5758.8973 | 8010 | 544.7059 | 1361.7647 | 0 | 131937.2218 | 0 | 0 | 100 | 3384.4706 | 6500 | 13082.3529 | 13176.4706 | 3244.1176 | 354.7059 | 0 | 0 | 0 | 2600 | 0
2025-09-26 | 549116.1758 | 0 | 96480 | 139350.1803 | 20481.2992 | 165183.8002 | 13102.9412 | 210997.9549 | 1387.2549 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 2787.0196 | 139350.1803 | 0 | 5799.6816 | 8550 | 605.8824 | 1514.7059 | 0 | 132384.5747 | 0 | 0 | 100 | 3580.5882 | 6500 | 13102.9412 | 13220.5882 | 3567.6471 | 443.3824 | 0 | 0 | 0 | 2600 | 0
2025-09-27 | 556807.1376 | 0 | 96480 | 143878.797 | 21688.4071 | 166840.9982 | 13123.5294 | 211275.4059 | 1664.7059 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 3344.4235 | 143878.797 | 0 | 5840.4659 | 9090 | 667.0588 | 1667.6471 | 0 | 132831.9276 | 0 | 0 | 100 | 3776.7059 | 6500 | 13123.5294 | 13264.7059 | 3891.1765 | 532.0588 | 0 | 0 | 0 | 2600 | 0
2025-09-28 | 564498.0993 | 0 | 96480 | 148407.4137 | 22895.5149 | 168498.1963 | 13144.1176 | 211552.8569 | 1942.1569 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 3901.8275 | 148407.4137 | 0 | 5881.2502 | 9630 | 728.2353 | 1820.5882 | 0 | 133279.2806 | 0 | 0 | 100 | 3972.8235 | 6500 | 13144.1176 | 13308.8235 | 4214.7059 | 620.7353 | 0 | 0 | 0 | 2600 | 0
2025-09-29 | 572189.0611 | 0 | 96480 | 152936.0304 | 24102.6227 | 170155.3943 | 13164.7059 | 211830.3078 | 2219.6078 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 4459.2314 | 152936.0304 | 0 | 5922.0345 | 10170 | 789.4118 | 1973.5294 | 0 | 133726.6335 | 0 | 0 | 100 | 4168.9412 | 6500 | 13164.7059 | 13352.9412 | 4538.2353 | 709.4118 | 0 | 0 | 0 | 2600 | 0
2025-09-30 | 579880.0229 | 0 | 96480 | 157464.6471 | 25309.7306 | 171812.5924 | 13185.2941 | 212107.7588 | 2497.0588 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 5016.6353 | 157464.6471 | 0 | 5962.8188 | 10710 | 850.5882 | 2126.4706 | 0 | 134173.9865 | 0 | 0 | 100 | 4365.0588 | 6500 | 13185.2941 | 13397.0588 | 4861.7647 | 798.0882 | 0 | 0 | 0 | 2600 | 0
2025-10-01 | 587570.9847 | 0 | 96480 | 161993.2638 | 26516.8384 | 173469.7904 | 13205.8824 | 212385.2098 | 2774.5098 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 5574.0392 | 161993.2638 | 0 | 6003.6031 | 11250 | 911.7647 | 2279.4118 | 0 | 134621.3394 | 0 | 0 | 100 | 4561.1765 | 6500 | 13205.8824 | 13441.1765 | 5185.2941 | 886.7647 | 0 | 0 | 0 | 2600 | 0
2025-10-02 | 595261.9465 | 0 | 96480 | 166521.8805 | 27723.9463 | 175126.9884 | 13226.4706 | 212662.6608 | 3051.9608 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 6131.4431 | 166521.8805 | 0 | 6044.3875 | 11790 | 972.9412 | 2432.3529 | 0 | 135068.6924 | 0 | 0 | 100 | 4757.2941 | 6500 | 13226.4706 | 13485.2941 | 5508.8235 | 975.4412 | 0 | 0 | 0 | 2600 | 0
2025-10-03 | 602952.9083 | 0 | 96480 | 171050.4972 | 28931.0541 | 176784.1865 | 13247.0588 | 212940.1118 | 3329.4118 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 6688.8471 | 171050.4972 | 0 | 6085.1718 | 12330 | 1034.1176 | 2585.2941 | 0 | 135516.0453 | 0 | 0 | 100 | 4953.4118 | 6500 | 13247.0588 | 13529.4118 | 5832.3529 | 1064.1176 | 0 | 0 | 0 | 2600 | 0
2025-10-04 | 610643.8701 | 0 | 96480 | 175579.1139 | 30138.162 | 178441.3845 | 13267.6471 | 213217.5627 | 3606.8627 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 7246.251 | 175579.1139 | 0 | 6125.9561 | 12870 | 1095.2941 | 2738.2353 | 0 | 135963.3982 | 0 | 0 | 100 | 5149.5294 | 6500 | 13267.6471 | 13573.5294 | 6155.8824 | 1152.7941 | 0 | 0 | 0 | 2600 | 0
2025-10-05 | 618334.8319 | 0 | 96480 | 180107.7306 | 31345.2698 | 180098.5825 | 13288.2353 | 213495.0137 | 3884.3137 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 7803.6549 | 180107.7306 | 0 | 6166.7404 | 13410 | 1156.4706 | 2891.1765 | 0 | 136410.7512 | 0 | 0 | 100 | 5345.6471 | 6500 | 13288.2353 | 13617.6471 | 6479.4118 | 1241.4706 | 0 | 0 | 0 | 2600 | 0
2025-10-06 | 626025.7937 | 0 | 96480 | 184636.3472 | 32552.3776 | 181755.7806 | 13308.8235 | 213772.4647 | 4161.7647 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 8361.0588 | 184636.3472 | 0 | 6207.5247 | 13950 | 1217.6471 | 3044.1176 | 0 | 136858.1041 | 0 | 0 | 100 | 5541.7647 | 6500 | 13308.8235 | 13661.7647 | 6802.9412 | 1330.1471 | 0 | 0 | 0 | 2600 | 0
2025-10-07 | 633716.7555 | 0 | 96480 | 189164.9639 | 33759.4855 | 183412.9786 | 13329.4118 | 214049.9157 | 4439.2157 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 8918.4627 | 189164.9639 | 0 | 6248.309 | 14490 | 1278.8235 | 3197.0588 | 0 | 137305.4571 | 0 | 0 | 100 | 5737.8824 | 6500 | 13329.4118 | 13705.8824 | 7126.4706 | 1418.8235 | 0 | 0 | 0 | 2600 | 0
2025-10-08 | 641407.7173 | 0 | 96480 | 193693.5806 | 34966.5933 | 185070.1767 | 13350 | 214327.3667 | 4716.6667 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 9475.8667 | 193693.5806 | 0 | 6289.0933 | 15030 | 1340 | 3350 | 0 | 137752.81 | 0 | 0 | 100 | 5934 | 6500 | 13350 | 13750 | 7450 | 1507.5 | 0 | 0 | 0 | 2600 | 0
2025-10-09 | 649098.6791 | 0 | 96480 | 198222.1973 | 36173.7012 | 186727.3747 | 13370.5882 | 214604.8176 | 4994.1176 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 10033.2706 | 198222.1973 | 0 | 6329.8776 | 15570 | 1401.1765 | 3502.9412 | 0 | 138200.1629 | 0 | 0 | 100 | 6130.1176 | 6500 | 13370.5882 | 13794.1176 | 7773.5294 | 1596.1765 | 0 | 0 | 0 | 2600 | 0
2025-10-10 | 656789.6409 | 0 | 96480 | 202750.814 | 37380.809 | 188384.5727 | 13391.1765 | 214882.2686 | 5271.5686 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 10590.6745 | 202750.814 | 0 | 6370.662 | 16110 | 1462.3529 | 3655.8824 | 0 | 138647.5159 | 0 | 0 | 100 | 6326.2353 | 6500 | 13391.1765 | 13838.2353 | 8097.0588 | 1684.8529 | 0 | 0 | 0 | 2600 | 0
2025-10-11 | 664480.6027 | 0 | 96480 | 207279.4307 | 38587.9169 | 190041.7708 | 13411.7647 | 215159.7196 | 5549.0196 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 11148.0784 | 207279.4307 | 0 | 6411.4463 | 16650 | 1523.5294 | 3808.8235 | 0 | 139094.8688 | 0 | 0 | 100 | 6522.3529 | 6500 | 13411.7647 | 13882.3529 | 8420.5882 | 1773.5294 | 0 | 0 | 0 | 2600 | 0
2025-10-12 | 672171.5645 | 0 | 96480 | 211808.0474 | 39795.0247 | 191698.9688 | 13432.3529 | 215437.1706 | 5826.4706 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 11705.4824 | 211808.0474 | 0 | 6452.2306 | 17190 | 1584.7059 | 3961.7647 | 0 | 139542.2218 | 0 | 0 | 100 | 6718.4706 | 6500 | 13432.3529 | 13926.4706 | 8744.1176 | 1862.2059 | 0 | 0 | 0 | 2600 | 0
2025-10-13 | 679862.5263 |  |  | 216336.6641 | 41002.1325 | 193356.1669 | 13452.9412 | 215714.6216 | 6103.9216 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 12262.8863 | 216336.6641 | 0 | 6493.0149 | 17730 | 1645.8824 | 4114.7059 | 0 | 139989.5747 | 0 | 0 | 100 | 6914.5882 | 6500 | 13452.9412 | 13970.5882 | 9067.6471 | 1950.8824 | 0 | 0 | 0 | 2600 | 0
2025-10-14 | 687553.4881 |  |  | 220865.2808 | 42209.2404 | 195013.3649 | 13473.5294 | 215992.0725 | 6381.3725 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 12820.2902 | 220865.2808 | 0 | 6533.7992 | 18270 | 1707.0588 | 4267.6471 | 0 | 140436.9276 | 0 | 0 | 100 | 7110.7059 | 6500 | 13473.5294 | 14014.7059 | 9391.1765 | 2039.5588 | 0 | 0 | 0 | 2600 | 0
2025-10-15 | 695244.4499 |  |  | 225393.8975 | 43416.3482 | 196670.5629 | 13494.1176 | 216269.5235 | 6658.8235 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 13377.6941 | 225393.8975 | 0 | 6574.5835 | 18810 | 1768.2353 | 4420.5882 | 0 | 140884.2806 | 0 | 0 | 100 | 7306.8235 | 6500 | 13494.1176 | 14058.8235 | 9714.7059 | 2128.2353 | 0 | 0 | 0 | 2600 | 0
2025-10-16 | 702935.4117 |  |  | 229922.5142 | 44623.4561 | 198327.761 | 13514.7059 | 216546.9745 | 6936.2745 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 13935.098 | 229922.5142 | 0 | 6615.3678 | 19350 | 1829.4118 | 4573.5294 | 0 | 141331.6335 | 0 | 0 | 100 | 7502.9412 | 6500 | 13514.7059 | 14102.9412 | 10038.2353 | 2216.9118 | 0 | 0 | 0 | 2600 | 0
2025-10-17 | 710626.3735 |  |  | 234451.1309 | 45830.5639 | 199984.959 | 13535.2941 | 216824.4255 | 7213.7255 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 14492.502 | 234451.1309 | 0 | 6656.1522 | 19890 | 1890.5882 | 4726.4706 | 0 | 141778.9865 | 0 | 0 | 100 | 7699.0588 | 6500 | 13535.2941 | 14147.0588 | 10361.7647 | 2305.5882 | 0 | 0 | 0 | 2600 | 0
2025-10-18 | 718317.3353 |  |  | 238979.7476 | 47037.6718 | 201642.1571 | 13555.8824 | 217101.8765 | 7491.1765 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 15049.9059 | 238979.7476 | 0 | 6696.9365 | 20430 | 1951.7647 | 4879.4118 | 0 | 142226.3394 | 0 | 0 | 100 | 7895.1765 | 6500 | 13555.8824 | 14191.1765 | 10685.2941 | 2394.2647 | 0 | 0 | 0 | 2600 | 0
2025-10-19 | 726008.2971 |  |  | 243508.3643 | 48244.7796 | 203299.3551 | 13576.4706 | 217379.3275 | 7768.6275 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 15607.3098 | 243508.3643 | 0 | 6737.7208 | 20970 | 2012.9412 | 5032.3529 | 0 | 142673.6924 | 0 | 0 | 100 | 8091.2941 | 6500 | 13576.4706 | 14235.2941 | 11008.8235 | 2482.9412 | 0 | 0 | 0 | 2600 | 0
2025-10-20 | 733699.2589 |  |  | 248036.981 | 49451.8875 | 204956.5531 | 13597.0588 | 217656.7784 | 8046.0784 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 16164.7137 | 248036.981 | 0 | 6778.5051 | 21510 | 2074.1176 | 5185.2941 | 0 | 143121.0453 | 0 | 0 | 100 | 8287.4118 | 6500 | 13597.0588 | 14279.4118 | 11332.3529 | 2571.6176 | 0 | 0 | 0 | 2600 | 0
2025-10-21 | 741390.2207 |  |  | 252565.5977 | 50658.9953 | 206613.7512 | 13617.6471 | 217934.2294 | 8323.5294 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 16722.1176 | 252565.5977 | 0 | 6819.2894 | 22050 | 2135.2941 | 5338.2353 | 0 | 143568.3982 | 0 | 0 | 100 | 8483.5294 | 6500 | 13617.6471 | 14323.5294 | 11655.8824 | 2660.2941 | 0 | 0 | 0 | 2600 | 0
2025-10-22 | 749081.1825 |  |  | 257094.2144 | 51866.1031 | 208270.9492 | 13638.2353 | 218211.6804 | 8600.9804 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 17279.5216 | 257094.2144 | 0 | 6860.0737 | 22590 | 2196.4706 | 5491.1765 | 0 | 144015.7512 | 0 | 0 | 100 | 8679.6471 | 6500 | 13638.2353 | 14367.6471 | 11979.4118 | 2748.9706 | 0 | 0 | 0 | 2600 | 0
2025-10-23 | 756772.1443 |  |  | 261622.8311 | 53073.211 | 209928.1473 | 13658.8235 | 218489.1314 | 8878.4314 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 17836.9255 | 261622.8311 | 0 | 6900.858 | 23130 | 2257.6471 | 5644.1176 | 0 | 144463.1041 | 0 | 0 | 100 | 8875.7647 | 6500 | 13658.8235 | 14411.7647 | 12302.9412 | 2837.6471 | 0 | 0 | 0 | 2600 | 0
2025-10-24 | 764463.1061 |  |  | 266151.4478 | 54280.3188 | 211585.3453 | 13679.4118 | 218766.5824 | 9155.8824 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 18394.3294 | 266151.4478 | 0 | 6941.6424 | 23670 | 2318.8235 | 5797.0588 | 0 | 144910.4571 | 0 | 0 | 100 | 9071.8824 | 6500 | 13679.4118 | 14455.8824 | 12626.4706 | 2926.3235 | 0 | 0 | 0 | 2600 | 0
2025-10-25 | 772154.0678 |  |  | 270680.0645 | 55487.4267 | 213242.5433 | 13700 | 219044.0333 | 9433.3333 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 18951.7333 | 270680.0645 | 0 | 6982.4267 | 24210 | 2380 | 5950 | 0 | 145357.81 | 0 | 0 | 100 | 9268 | 6500 | 13700 | 14500 | 12950 | 3015 | 0 | 0 | 0 | 2600 | 0
2025-10-26 | 779845.0296 |  |  | 275208.6812 | 56694.5345 | 214899.7414 | 13720.5882 | 219321.4843 | 9710.7843 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 19509.1373 | 275208.6812 | 0 | 7023.211 | 24750 | 2441.1765 | 6102.9412 | 0 | 145805.1629 | 0 | 0 | 100 | 9464.1176 | 6500 | 13720.5882 | 14544.1176 | 13273.5294 | 3103.6765 | 0 | 0 | 0 | 2600 | 0
2025-10-27 | 787535.9914 |  |  | 279737.2979 | 57901.6424 | 216556.9394 | 13741.1765 | 219598.9353 | 9988.2353 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 20066.5412 | 279737.2979 | 0 | 7063.9953 | 25290 | 2502.3529 | 6255.8824 | 0 | 146252.5159 | 0 | 0 | 100 | 9660.2353 | 6500 | 13741.1765 | 14588.2353 | 13597.0588 | 3192.3529 | 0 | 0 | 0 | 2600 | 0
2025-10-28 | 795226.9532 |  |  | 284265.9146 | 59108.7502 | 218214.1375 | 13761.7647 | 219876.3863 | 10265.6863 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 20623.9451 | 284265.9146 | 0 | 7104.7796 | 25830 | 2563.5294 | 6408.8235 | 0 | 146699.8688 | 0 | 0 | 100 | 9856.3529 | 6500 | 13761.7647 | 14632.3529 | 13920.5882 | 3281.0294 | 0 | 0 | 0 | 2600 | 0
2025-10-29 | 802917.915 |  |  | 288794.5313 | 60315.858 | 219871.3355 | 13782.3529 | 220153.8373 | 10543.1373 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 21181.349 | 288794.5313 | 0 | 7145.5639 | 26370 | 2624.7059 | 6561.7647 | 0 | 147147.2218 | 0 | 0 | 100 | 10052.4706 | 6500 | 13782.3529 | 14676.4706 | 14244.1176 | 3369.7059 | 0 | 0 | 0 | 2600 | 0
2025-10-30 | 810608.8768 |  |  | 293323.148 | 61522.9659 | 221528.5335 | 13802.9412 | 220431.2882 | 10820.5882 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 21738.7529 | 293323.148 | 0 | 7186.3482 | 26910 | 2685.8824 | 6714.7059 | 0 | 147594.5747 | 0 | 0 | 100 | 10248.5882 | 6500 | 13802.9412 | 14720.5882 | 14567.6471 | 3458.3824 | 0 | 0 | 0 | 2600 | 0
2025-10-31 | 818299.8386 |  |  | 297851.7647 | 62730.0737 | 223185.7316 | 13823.5294 | 220708.7392 | 11098.0392 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 22296.1569 | 297851.7647 | 0 | 7227.1325 | 27450 | 2747.0588 | 6867.6471 | 0 | 148041.9276 | 0 | 0 | 100 | 10444.7059 | 6500 | 13823.5294 | 14764.7059 | 14891.1765 | 3547.0588 | 0 | 0 | 0 | 2600 | 0
2025-11-01 | 825990.8004 |  |  | 302380.3814 | 63937.1816 | 224842.9296 | 13844.1176 | 220986.1902 | 11375.4902 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 22853.5608 | 302380.3814 | 0 | 7267.9169 | 27990 | 2808.2353 | 7020.5882 | 0 | 148489.2806 | 0 | 0 | 100 | 10640.8235 | 6500 | 13844.1176 | 14808.8235 | 15214.7059 | 3635.7353 | 0 | 0 | 0 | 2600 | 0
2025-11-02 | 833681.7622 |  |  | 306908.9981 | 65144.2894 | 226500.1276 | 13864.7059 | 221263.6412 | 11652.9412 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 23410.9647 | 306908.9981 | 0 | 7308.7012 | 28530 | 2869.4118 | 7173.5294 | 0 | 148936.6335 | 0 | 0 | 100 | 10836.9412 | 6500 | 13864.7059 | 14852.9412 | 15538.2353 | 3724.4118 | 0 | 0 | 0 | 2600 | 0
2025-11-03 | 841372.724 |  |  | 311437.6148 | 66351.3973 | 228157.3257 | 13885.2941 | 221541.0922 | 11930.3922 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 23968.3686 | 311437.6148 | 0 | 7349.4855 | 29070 | 2930.5882 | 7326.4706 | 0 | 149383.9865 | 0 | 0 | 100 | 11033.0588 | 6500 | 13885.2941 | 14897.0588 | 15861.7647 | 3813.0882 | 0 | 0 | 0 | 2600 | 0
2025-11-04 | 849063.6858 |  |  | 315966.2315 | 67558.5051 | 229814.5237 | 13905.8824 | 221818.5431 | 12207.8431 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 24525.7725 | 315966.2315 | 0 | 7390.2698 | 29610 | 2991.7647 | 7479.4118 | 0 | 149831.3394 | 0 | 0 | 100 | 11229.1765 | 6500 | 13905.8824 | 14941.1765 | 16185.2941 | 3901.7647 | 0 | 0 | 0 | 2600 | 0
2025-11-05 | 856754.6476 |  |  | 320494.8482 | 68765.6129 | 231471.7218 | 13926.4706 | 222095.9941 | 12485.2941 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 25083.1765 | 320494.8482 | 0 | 7431.0541 | 30150 | 3052.9412 | 7632.3529 | 0 | 150278.6924 | 0 | 0 | 100 | 11425.2941 | 6500 | 13926.4706 | 14985.2941 | 16508.8235 | 3990.4412 | 0 | 0 | 0 | 2600 | 0
2025-11-06 | 864445.6094 |  |  | 325023.4649 | 69972.7208 | 233128.9198 | 13947.0588 | 222373.4451 | 12762.7451 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 25640.5804 | 325023.4649 | 0 | 7471.8384 | 30690 | 3114.1176 | 7785.2941 | 0 | 150726.0453 | 0 | 0 | 100 | 11621.4118 | 6500 | 13947.0588 | 15029.4118 | 16832.3529 | 4079.1176 | 0 | 0 | 0 | 2600 | 0
2025-11-07 | 872136.5712 |  |  | 329552.0816 | 71179.8286 | 234786.1178 | 13967.6471 | 222650.8961 | 13040.1961 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 26197.9843 | 329552.0816 | 0 | 7512.6227 | 31230 | 3175.2941 | 7938.2353 | 0 | 151173.3982 | 0 | 0 | 100 | 11817.5294 | 6500 | 13967.6471 | 15073.5294 | 17155.8824 | 4167.7941 | 0 | 0 | 0 | 2600 | 0
2025-11-08 | 879827.533 |  |  | 334080.6983 | 72386.9365 | 236443.3159 | 13988.2353 | 222928.3471 | 13317.6471 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 26755.3882 | 334080.6983 | 0 | 7553.4071 | 31770 | 3236.4706 | 8091.1765 | 0 | 151620.7512 | 0 | 0 | 100 | 12013.6471 | 6500 | 13988.2353 | 15117.6471 | 17479.4118 | 4256.4706 | 0 | 0 | 0 | 2600 | 0
2025-11-09 | 887518.4948 |  |  | 338609.315 | 73594.0443 | 238100.5139 | 14008.8235 | 223205.798 | 13595.098 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 27312.7922 | 338609.315 | 0 | 7594.1914 | 32310 | 3297.6471 | 8244.1176 | 0 | 152068.1041 | 0 | 0 | 100 | 12209.7647 | 6500 | 14008.8235 | 15161.7647 | 17802.9412 | 4345.1471 | 0 | 0 | 0 | 2600 | 0
2025-11-10 | 895209.4566 |  |  | 343137.9317 | 74801.1522 | 239757.712 | 14029.4118 | 223483.249 | 13872.549 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 27870.1961 | 343137.9317 | 0 | 7634.9757 | 32850 | 3358.8235 | 8397.0588 | 0 | 152515.4571 | 0 | 0 | 100 | 12405.8824 | 6500 | 14029.4118 | 15205.8824 | 18126.4706 | 4433.8235 | 0 | 0 | 0 | 2600 | 0
2025-11-11 | 902900.4184 |  |  | 347666.5484 | 76008.26 | 241414.91 | 14050 | 223760.7 | 14150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 28427.6 | 347666.5484 | 0 | 7675.76 | 33390 | 3420 | 8550 | 0 | 152962.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-12 | 907206.1354 |  |  | 349525.6464 | 76730.879 | 242308.1957 | 14050 | 224591.4143 | 14459.5238 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 521.1905 | 0 | 0 | 28427.6 | 349525.6464 | 0 | 7719.8076 | 33831.0714 | 3487.8571 | 8719.6429 | 0 | 153856.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-13 | 911511.8524 |  |  | 351384.7444 | 77453.4981 | 243201.4814 | 14050 | 225422.1286 | 14769.0476 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 1042.381 | 0 | 0 | 28427.6 | 351384.7444 | 0 | 7763.8552 | 34272.1429 | 3555.7143 | 8889.2857 | 0 | 154749.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-14 | 915817.5695 |  |  | 353243.8423 | 78176.1171 | 244094.7671 | 14050 | 226252.8429 | 15078.5714 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 1563.5714 | 0 | 0 | 28427.6 | 353243.8423 | 0 | 7807.9029 | 34713.2143 | 3623.5714 | 9058.9286 | 0 | 155642.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-15 | 920123.2865 |  |  | 355102.9403 | 78898.7362 | 244988.0529 | 14050 | 227083.5571 | 15388.0952 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 2084.7619 | 0 | 0 | 28427.6 | 355102.9403 | 0 | 7851.9505 | 35154.2857 | 3691.4286 | 9228.5714 | 0 | 156535.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-16 | 924429.0035 |  |  | 356962.0383 | 79621.3552 | 245881.3386 | 14050 | 227914.2714 | 15697.619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 2605.9524 | 0 | 0 | 28427.6 | 356962.0383 | 0 | 7895.9981 | 35595.3571 | 3759.2857 | 9398.2143 | 0 | 157429.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-17 | 928734.7206 |  |  | 358821.1363 | 80343.9743 | 246774.6243 | 14050 | 228744.9857 | 16007.1429 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 3127.1429 | 0 | 0 | 28427.6 | 358821.1363 | 0 | 7940.0457 | 36036.4286 | 3827.1429 | 9567.8571 | 0 | 158322.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-18 | 933040.4376 |  |  | 360680.2343 | 81066.5933 | 247667.91 | 14050 | 229575.7 | 16316.6667 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 3648.3333 | 0 | 0 | 28427.6 | 360680.2343 | 0 | 7984.0933 | 36477.5 | 3895 | 9737.5 | 0 | 159215.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-19 | 937346.1546 |  |  | 362539.3323 | 81789.2124 | 248561.1957 | 14050 | 230406.4143 | 16626.1905 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 4169.5238 | 0 | 0 | 28427.6 | 362539.3323 | 0 | 8028.141 | 36918.5714 | 3962.8571 | 9907.1429 | 0 | 160109.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-20 | 941651.8717 |  |  | 364398.4302 | 82511.8314 | 249454.4814 | 14050 | 231237.1286 | 16935.7143 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 4690.7143 | 0 | 0 | 28427.6 | 364398.4302 | 0 | 8072.1886 | 37359.6429 | 4030.7143 | 10076.7857 | 0 | 161002.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-21 | 945957.5887 |  |  | 366257.5282 | 83234.4505 | 250347.7671 | 14050 | 232067.8429 | 17245.2381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 5211.9048 | 0 | 0 | 28427.6 | 366257.5282 | 0 | 8116.2362 | 37800.7143 | 4098.5714 | 10246.4286 | 0 | 161895.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-22 | 950263.3057 |  |  | 368116.6262 | 83957.0695 | 251241.0529 | 14050 | 232898.5571 | 17554.7619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 5733.0952 | 0 | 0 | 28427.6 | 368116.6262 | 0 | 8160.2838 | 38241.7857 | 4166.4286 | 10416.0714 | 0 | 162788.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-23 | 954569.0228 |  |  | 369975.7242 | 84679.6886 | 252134.3386 | 14050 | 233729.2714 | 17864.2857 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 6254.2857 | 0 | 0 | 28427.6 | 369975.7242 | 0 | 8204.3314 | 38682.8571 | 4234.2857 | 10585.7143 | 0 | 163682.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-24 | 958874.7398 |  |  | 371834.8222 | 85402.3076 | 253027.6243 | 14050 | 234559.9857 | 18173.8095 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 6775.4762 | 0 | 0 | 28427.6 | 371834.8222 | 0 | 8248.379 | 39123.9286 | 4302.1429 | 10755.3571 | 0 | 164575.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-25 | 963180.4568 |  |  | 373693.9201 | 86124.9267 | 253920.91 | 14050 | 235390.7 | 18483.3333 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 7296.6667 | 0 | 0 | 28427.6 | 373693.9201 | 0 | 8292.4267 | 39565 | 4370 | 10925 | 0 | 165468.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-26 | 967486.1738 |  |  | 375553.0181 | 86847.5457 | 254814.1957 | 14050 | 236221.4143 | 18792.8571 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 7817.8571 | 0 | 0 | 28427.6 | 375553.0181 | 0 | 8336.4743 | 40006.0714 | 4437.8571 | 11094.6429 | 0 | 166362.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-27 | 971791.8909 |  |  | 377412.1161 | 87570.1648 | 255707.4814 | 14050 | 237052.1286 | 19102.381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 8339.0476 | 0 | 0 | 28427.6 | 377412.1161 | 0 | 8380.5219 | 40447.1429 | 4505.7143 | 11264.2857 | 0 | 167255.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-28 | 976097.6079 |  |  | 379271.2141 | 88292.7838 | 256600.7671 | 14050 | 237882.8429 | 19411.9048 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 8860.2381 | 0 | 0 | 28427.6 | 379271.2141 | 0 | 8424.5695 | 40888.2143 | 4573.5714 | 11433.9286 | 0 | 168148.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-29 | 980403.3249 |  |  | 381130.3121 | 89015.4029 | 257494.0529 | 14050 | 238713.5571 | 19721.4286 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 9381.4286 | 0 | 0 | 28427.6 | 381130.3121 | 0 | 8468.6171 | 41329.2857 | 4641.4286 | 11603.5714 | 0 | 169041.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-30 | 984709.042 |  |  | 382989.4101 | 89738.0219 | 258387.3386 | 14050 | 239544.2714 | 20030.9524 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 9902.619 | 0 | 0 | 28427.6 | 382989.4101 | 0 | 8512.6648 | 41770.3571 | 4709.2857 | 11773.2143 | 0 | 169935.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-01 | 989014.759 |  |  | 384848.508 | 90460.641 | 259280.6243 | 14050 | 240374.9857 | 20340.4762 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 10423.8095 | 0 | 0 | 28427.6 | 384848.508 | 0 | 8556.7124 | 42211.4286 | 4777.1429 | 11942.8571 | 0 | 170828.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-02 | 993320.476 |  |  | 386707.606 | 91183.26 | 260173.91 | 14050 | 241205.7 | 20650 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 10945 | 0 | 0 | 28427.6 | 386707.606 | 0 | 8600.76 | 42652.5 | 4845 | 12112.5 | 0 | 171721.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-03 | 997626.1931 |  |  | 388566.704 | 91905.879 | 261067.1957 | 14050 | 242036.4143 | 20959.5238 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 11466.1905 | 0 | 0 | 28427.6 | 388566.704 | 0 | 8644.8076 | 43093.5714 | 4912.8571 | 12282.1429 | 0 | 172615.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-04 | 1001931.9101 |  |  | 390425.802 | 92628.4981 | 261960.4814 | 14050 | 242867.1286 | 21269.0476 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 11987.381 | 0 | 0 | 28427.6 | 390425.802 | 0 | 8688.8552 | 43534.6429 | 4980.7143 | 12451.7857 | 0 | 173508.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-05 | 1006237.6271 |  |  | 392284.9 | 93351.1171 | 262853.7671 | 14050 | 243697.8429 | 21578.5714 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 12508.5714 | 0 | 0 | 28427.6 | 392284.9 | 0 | 8732.9029 | 43975.7143 | 5048.5714 | 12621.4286 | 0 | 174401.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-06 | 1010543.3442 |  |  | 394143.998 | 94073.7362 | 263747.0529 | 14050 | 244528.5571 | 21888.0952 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 13029.7619 | 0 | 0 | 28427.6 | 394143.998 | 0 | 8776.9505 | 44416.7857 | 5116.4286 | 12791.0714 | 0 | 175294.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-07 | 1014849.0612 |  |  | 396003.0959 | 94796.3552 | 264640.3386 | 14050 | 245359.2714 | 22197.619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 13550.9524 | 0 | 0 | 28427.6 | 396003.0959 | 0 | 8820.9981 | 44857.8571 | 5184.2857 | 12960.7143 | 0 | 176188.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-08 | 1019154.7782 |  |  | 397862.1939 | 95518.9743 | 265533.6243 | 14050 | 246189.9857 | 22507.1429 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 14072.1429 | 0 | 0 | 28427.6 | 397862.1939 | 0 | 8865.0457 | 45298.9286 | 5252.1429 | 13130.3571 | 0 | 177081.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-09 | 1023460.4952 |  |  | 399721.2919 | 96241.5933 | 266426.91 | 14050 | 247020.7 | 22816.6667 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 14593.3333 | 0 | 0 | 28427.6 | 399721.2919 | 0 | 8909.0933 | 45740 | 5320 | 13300 | 0 | 177974.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-10 | 1027766.2123 |  |  | 401580.3899 | 96964.2124 | 267320.1957 | 14050 | 247851.4143 | 23126.1905 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 15114.5238 | 0 | 0 | 28427.6 | 401580.3899 | 0 | 8953.141 | 46181.0714 | 5387.8571 | 13469.6429 | 0 | 178868.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-11 | 1032071.9293 |  |  | 403439.4879 | 97686.8314 | 268213.4814 | 14050 | 248682.1286 | 23435.7143 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 15635.7143 | 0 | 0 | 28427.6 | 403439.4879 | 0 | 8997.1886 | 46622.1429 | 5455.7143 | 13639.2857 | 0 | 179761.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-12 | 1036377.6463 |  |  | 405298.5859 | 98409.4505 | 269106.7671 | 14050 | 249512.8429 | 23745.2381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 16156.9048 | 0 | 0 | 28427.6 | 405298.5859 | 0 | 9041.2362 | 47063.2143 | 5523.5714 | 13808.9286 | 0 | 180654.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-13 | 1040683.3634 |  |  | 407157.6838 | 99132.0695 | 270000.0529 | 14050 | 250343.5571 | 24054.7619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 16678.0952 | 0 | 0 | 28427.6 | 407157.6838 | 0 | 9085.2838 | 47504.2857 | 5591.4286 | 13978.5714 | 0 | 181547.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-14 | 1044989.0804 |  |  | 409016.7818 | 99854.6886 | 270893.3386 | 14050 | 251174.2714 | 24364.2857 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 17199.2857 | 0 | 0 | 28427.6 | 409016.7818 | 0 | 9129.3314 | 47945.3571 | 5659.2857 | 14148.2143 | 0 | 182441.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-15 | 1049294.7974 |  |  | 410875.8798 | 100577.3076 | 271786.6243 | 14050 | 252004.9857 | 24673.8095 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 17720.4762 | 0 | 0 | 28427.6 | 410875.8798 | 0 | 9173.379 | 48386.4286 | 5727.1429 | 14317.8571 | 0 | 183334.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-16 | 1053600.5145 |  |  | 412734.9778 | 101299.9267 | 272679.91 | 14050 | 252835.7 | 24983.3333 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 18241.6667 | 0 | 0 | 28427.6 | 412734.9778 | 0 | 9217.4267 | 48827.5 | 5795 | 14487.5 | 0 | 184227.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-17 | 1057906.2315 |  |  | 414594.0758 | 102022.5457 | 273573.1957 | 14050 | 253666.4143 | 25292.8571 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 18762.8571 | 0 | 0 | 28427.6 | 414594.0758 | 0 | 9261.4743 | 49268.5714 | 5862.8571 | 14657.1429 | 0 | 185121.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-18 | 1062211.9485 |  |  | 416453.1738 | 102745.1648 | 274466.4814 | 14050 | 254497.1286 | 25602.381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 19284.0476 | 0 | 0 | 28427.6 | 416453.1738 | 0 | 9305.5219 | 49709.6429 | 5930.7143 | 14826.7857 | 0 | 186014.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-19 | 1066517.6655 |  |  | 418312.2717 | 103467.7838 | 275359.7671 | 14050 | 255327.8429 | 25911.9048 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 19805.2381 | 0 | 0 | 28427.6 | 418312.2717 | 0 | 9349.5695 | 50150.7143 | 5998.5714 | 14996.4286 | 0 | 186907.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-20 | 1070823.3826 |  |  | 420171.3697 | 104190.4029 | 276253.0529 | 14050 | 256158.5571 | 26221.4286 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 20326.4286 | 0 | 0 | 28427.6 | 420171.3697 | 0 | 9393.6171 | 50591.7857 | 6066.4286 | 15166.0714 | 0 | 187800.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-21 | 1075129.0996 |  |  | 422030.4677 | 104913.0219 | 277146.3386 | 14050 | 256989.2714 | 26530.9524 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 20847.619 | 0 | 0 | 28427.6 | 422030.4677 | 0 | 9437.6648 | 51032.8571 | 6134.2857 | 15335.7143 | 0 | 188694.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-22 | 1079434.8166 |  |  | 423889.5657 | 105635.641 | 278039.6243 | 14050 | 257819.9857 | 26840.4762 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 21368.8095 | 0 | 0 | 28427.6 | 423889.5657 | 0 | 9481.7124 | 51473.9286 | 6202.1429 | 15505.3571 | 0 | 189587.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-23 | 1083740.5337 |  |  | 425748.6637 | 106358.26 | 278932.91 | 14050 | 258650.7 | 27150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 21890 | 0 | 0 | 28427.6 | 425748.6637 | 0 | 9525.76 | 51915 | 6270 | 15675 | 0 | 190480.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-24 | 1088046.2507 |  |  | 427607.7617 | 107080.879 | 279826.1957 | 14050 | 259481.4143 | 27459.5238 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 22411.1905 | 0 | 0 | 28427.6 | 427607.7617 | 0 | 9569.8076 | 52356.0714 | 6337.8571 | 15844.6429 | 0 | 191374.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-25 | 1092351.9677 |  |  | 429466.8596 | 107803.4981 | 280719.4814 | 14050 | 260312.1286 | 27769.0476 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 22932.381 | 0 | 0 | 28427.6 | 429466.8596 | 0 | 9613.8552 | 52797.1429 | 6405.7143 | 16014.2857 | 0 | 192267.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-26 | 1096657.6848 |  |  | 431325.9576 | 108526.1171 | 281612.7671 | 14050 | 261142.8429 | 28078.5714 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 23453.5714 | 0 | 0 | 28427.6 | 431325.9576 | 0 | 9657.9029 | 53238.2143 | 6473.5714 | 16183.9286 | 0 | 193160.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-27 | 1100963.4018 |  |  | 433185.0556 | 109248.7362 | 282506.0529 | 14050 | 261973.5571 | 28388.0952 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 23974.7619 | 0 | 0 | 28427.6 | 433185.0556 | 0 | 9701.9505 | 53679.2857 | 6541.4286 | 16353.5714 | 0 | 194053.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-28 | 1105269.1188 |  |  | 435044.1536 | 109971.3552 | 283399.3386 | 14050 | 262804.2714 | 28697.619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 24495.9524 | 0 | 0 | 28427.6 | 435044.1536 | 0 | 9745.9981 | 54120.3571 | 6609.2857 | 16523.2143 | 0 | 194947.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-29 | 1109574.8359 |  |  | 436903.2516 | 110693.9743 | 284292.6243 | 14050 | 263634.9857 | 29007.1429 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 25017.1429 | 0 | 0 | 28427.6 | 436903.2516 | 0 | 9790.0457 | 54561.4286 | 6677.1429 | 16692.8571 | 0 | 195840.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-30 | 1113880.5529 |  |  | 438762.3496 | 111416.5933 | 285185.91 | 14050 | 264465.7 | 29316.6667 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 25538.3333 | 0 | 0 | 28427.6 | 438762.3496 | 0 | 9834.0933 | 55002.5 | 6745 | 16862.5 | 0 | 196733.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-31 | 1118186.2699 |  |  | 440621.4475 | 112139.2124 | 286079.1957 | 14050 | 265296.4143 | 29626.1905 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 26059.5238 | 0 | 0 | 28427.6 | 440621.4475 | 0 | 9878.141 | 55443.5714 | 6812.8571 | 17032.1429 | 0 | 197627.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-01 | 1122491.9869 |  |  | 442480.5455 | 112861.8314 | 286972.4814 | 14050 | 266127.1286 | 29935.7143 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 26580.7143 | 0 | 0 | 28427.6 | 442480.5455 | 0 | 9922.1886 | 55884.6429 | 6880.7143 | 17201.7857 | 0 | 198520.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-02 | 1126797.704 |  |  | 444339.6435 | 113584.4505 | 287865.7671 | 14050 | 266957.8429 | 30245.2381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 27101.9048 | 0 | 0 | 28427.6 | 444339.6435 | 0 | 9966.2362 | 56325.7143 | 6948.5714 | 17371.4286 | 0 | 199413.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-03 | 1131103.421 |  |  | 446198.7415 | 114307.0695 | 288759.0529 | 14050 | 267788.5571 | 30554.7619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 27623.0952 | 0 | 0 | 28427.6 | 446198.7415 | 0 | 10010.2838 | 56766.7857 | 7016.4286 | 17541.0714 | 0 | 200306.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-04 | 1135409.138 |  |  | 448057.8395 | 115029.6886 | 289652.3386 | 14050 | 268619.2714 | 30864.2857 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 28144.2857 | 0 | 0 | 28427.6 | 448057.8395 | 0 | 10054.3314 | 57207.8571 | 7084.2857 | 17710.7143 | 0 | 201200.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-05 | 1139714.8551 |  |  | 449916.9374 | 115752.3076 | 290545.6243 | 14050 | 269449.9857 | 31173.8095 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 28665.4762 | 0 | 0 | 28427.6 | 449916.9374 | 0 | 10098.379 | 57648.9286 | 7152.1429 | 17880.3571 | 0 | 202093.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-06 | 1144020.5721 |  |  | 451776.0354 | 116474.9267 | 291438.91 | 14050 | 270280.7 | 31483.3333 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 29186.6667 | 0 | 0 | 28427.6 | 451776.0354 | 0 | 10142.4267 | 58090 | 7220 | 18050 | 0 | 202986.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-07 | 1148326.2891 |  |  | 453635.1334 | 117197.5457 | 292332.1957 | 14050 | 271111.4143 | 31792.8571 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 29707.8571 | 0 | 0 | 28427.6 | 453635.1334 | 0 | 10186.4743 | 58531.0714 | 7287.8571 | 18219.6429 | 0 | 203880.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-08 | 1152632.0062 |  |  | 455494.2314 | 117920.1648 | 293225.4814 | 14050 | 271942.1286 | 32102.381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 30229.0476 | 0 | 0 | 28427.6 | 455494.2314 | 0 | 10230.5219 | 58972.1429 | 7355.7143 | 18389.2857 | 0 | 204773.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-09 | 1156937.7232 |  |  | 457353.3294 | 118642.7838 | 294118.7671 | 14050 | 272772.8429 | 32411.9048 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 30750.2381 | 0 | 0 | 28427.6 | 457353.3294 | 0 | 10274.5695 | 59413.2143 | 7423.5714 | 18558.9286 | 0 | 205666.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-10 | 1161243.4402 |  |  | 459212.4274 | 119365.4029 | 295012.0529 | 14050 | 273603.5571 | 32721.4286 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 31271.4286 | 0 | 0 | 28427.6 | 459212.4274 | 0 | 10318.6171 | 59854.2857 | 7491.4286 | 18728.5714 | 0 | 206559.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-11 | 1165549.1573 |  |  | 461071.5253 | 120088.0219 | 295905.3386 | 14050 | 274434.2714 | 33030.9524 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 31792.619 | 0 | 0 | 28427.6 | 461071.5253 | 0 | 10362.6648 | 60295.3571 | 7559.2857 | 18898.2143 | 0 | 207453.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-12 | 1169854.8743 |  |  | 462930.6233 | 120810.641 | 296798.6243 | 14050 | 275264.9857 | 33340.4762 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 32313.8095 | 0 | 0 | 28427.6 | 462930.6233 | 0 | 10406.7124 | 60736.4286 | 7627.1429 | 19067.8571 | 0 | 208346.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-13 | 1174160.5913 |  |  | 464789.7213 | 121533.26 | 297691.91 | 14050 | 276095.7 | 33650 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 32835 | 0 | 0 | 28427.6 | 464789.7213 | 0 | 10450.76 | 61177.5 | 7695 | 19237.5 | 0 | 209239.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-14 | 1178466.3083 |  |  | 466648.8193 | 122255.879 | 298585.1957 | 14050 | 276926.4143 | 33959.5238 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 33356.1905 | 0 | 0 | 28427.6 | 466648.8193 | 0 | 10494.8076 | 61618.5714 | 7762.8571 | 19407.1429 | 0 | 210133.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-15 | 1182772.0254 |  |  | 468507.9173 | 122978.4981 | 299478.4814 | 14050 | 277757.1286 | 34269.0476 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 33877.381 | 0 | 0 | 28427.6 | 468507.9173 | 0 | 10538.8552 | 62059.6429 | 7830.7143 | 19576.7857 | 0 | 211026.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-16 | 1187077.7424 |  |  | 470367.0153 | 123701.1171 | 300371.7671 | 14050 | 278587.8429 | 34578.5714 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 34398.5714 | 0 | 0 | 28427.6 | 470367.0153 | 0 | 10582.9029 | 62500.7143 | 7898.5714 | 19746.4286 | 0 | 211919.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-17 | 1191383.4594 |  |  | 472226.1132 | 124423.7362 | 301265.0529 | 14050 | 279418.5571 | 34888.0952 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 34919.7619 | 0 | 0 | 28427.6 | 472226.1132 | 0 | 10626.9505 | 62941.7857 | 7966.4286 | 19916.0714 | 0 | 212812.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-18 | 1195689.1765 |  |  | 474085.2112 | 125146.3552 | 302158.3386 | 14050 | 280249.2714 | 35197.619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 35440.9524 | 0 | 0 | 28427.6 | 474085.2112 | 0 | 10670.9981 | 63382.8571 | 8034.2857 | 20085.7143 | 0 | 213706.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-19 | 1199994.8935 |  |  | 475944.3092 | 125868.9743 | 303051.6243 | 14050 | 281079.9857 | 35507.1429 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 35962.1429 | 0 | 0 | 28427.6 | 475944.3092 | 0 | 10715.0457 | 63823.9286 | 8102.1429 | 20255.3571 | 0 | 214599.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-20 | 1204300.6105 |  |  | 477803.4072 | 126591.5933 | 303944.91 | 14050 | 281910.7 | 35816.6667 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 36483.3333 | 0 | 0 | 28427.6 | 477803.4072 | 0 | 10759.0933 | 64265 | 8170 | 20425 | 0 | 215492.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-21 | 1208606.3276 |  |  | 479662.5052 | 127314.2124 | 304838.1957 | 14050 | 282741.4143 | 36126.1905 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 37004.5238 | 0 | 0 | 28427.6 | 479662.5052 | 0 | 10803.141 | 64706.0714 | 8237.8571 | 20594.6429 | 0 | 216386.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-22 | 1212912.0446 |  |  | 481521.6032 | 128036.8314 | 305731.4814 | 14050 | 283572.1286 | 36435.7143 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 37525.7143 | 0 | 0 | 28427.6 | 481521.6032 | 0 | 10847.1886 | 65147.1429 | 8305.7143 | 20764.2857 | 0 | 217279.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-23 | 1217217.7616 |  |  | 483380.7011 | 128759.4505 | 306624.7671 | 14050 | 284402.8429 | 36745.2381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 38046.9048 | 0 | 0 | 28427.6 | 483380.7011 | 0 | 10891.2362 | 65588.2143 | 8373.5714 | 20933.9286 | 0 | 218172.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-24 | 1221523.4786 |  |  | 485239.7991 | 129482.0695 | 307518.0529 | 14050 | 285233.5571 | 37054.7619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 38568.0952 | 0 | 0 | 28427.6 | 485239.7991 | 0 | 10935.2838 | 66029.2857 | 8441.4286 | 21103.5714 | 0 | 219065.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-25 | 1225829.1957 |  |  | 487098.8971 | 130204.6886 | 308411.3386 | 14050 | 286064.2714 | 37364.2857 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 39089.2857 | 0 | 0 | 28427.6 | 487098.8971 | 0 | 10979.3314 | 66470.3571 | 8509.2857 | 21273.2143 | 0 | 219959.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-26 | 1230134.9127 |  |  | 488957.9951 | 130927.3076 | 309304.6243 | 14050 | 286894.9857 | 37673.8095 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 39610.4762 | 0 | 0 | 28427.6 | 488957.9951 | 0 | 11023.379 | 66911.4286 | 8577.1429 | 21442.8571 | 0 | 220852.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-27 | 1234440.6297 |  |  | 490817.0931 | 131649.9267 | 310197.91 | 14050 | 287725.7 | 37983.3333 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 40131.6667 | 0 | 0 | 28427.6 | 490817.0931 | 0 | 11067.4267 | 67352.5 | 8645 | 21612.5 | 0 | 221745.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-28 | 1238746.3468 |  |  | 492676.1911 | 132372.5457 | 311091.1957 | 14050 | 288556.4143 | 38292.8571 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 40652.8571 | 0 | 0 | 28427.6 | 492676.1911 | 0 | 11111.4743 | 67793.5714 | 8712.8571 | 21782.1429 | 0 | 222639.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-29 | 1243052.0638 |  |  | 494535.289 | 133095.1648 | 311984.4814 | 14050 | 289387.1286 | 38602.381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 41174.0476 | 0 | 0 | 28427.6 | 494535.289 | 0 | 11155.5219 | 68234.6429 | 8780.7143 | 21951.7857 | 0 | 223532.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-30 | 1247357.7808 |  |  | 496394.387 | 133817.7838 | 312877.7671 | 14050 | 290217.8429 | 38911.9048 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 41695.2381 | 0 | 0 | 28427.6 | 496394.387 | 0 | 11199.5695 | 68675.7143 | 8848.5714 | 22121.4286 | 0 | 224425.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-31 | 1251663.4979 |  |  | 498253.485 | 134540.4029 | 313771.0529 | 14050 | 291048.5571 | 39221.4286 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 42216.4286 | 0 | 0 | 28427.6 | 498253.485 | 0 | 11243.6171 | 69116.7857 | 8916.4286 | 22291.0714 | 0 | 225318.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-01 | 1255969.2149 |  |  | 500112.583 | 135263.0219 | 314664.3386 | 14050 | 291879.2714 | 39530.9524 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 42737.619 | 0 | 0 | 28427.6 | 500112.583 | 0 | 11287.6648 | 69557.8571 | 8984.2857 | 22460.7143 | 0 | 226212.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-02 | 1260274.9319 |  |  | 501971.681 | 135985.641 | 315557.6243 | 14050 | 292709.9857 | 39840.4762 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43258.8095 | 0 | 0 | 28427.6 | 501971.681 | 0 | 11331.7124 | 69998.9286 | 9052.1429 | 22630.3571 | 0 | 227105.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-03 | 1264580.649 |  |  | 503830.779 | 136708.26 | 316450.91 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 503830.779 | 0 | 11375.76 | 70440 | 9120 | 22800 | 0 | 227998.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-04 | 1266564.0753 |  |  | 505376.4711 | 137091.8389 | 316505.0653 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 505376.4711 | 0 | 11389.8653 | 70680.1579 | 9156.9474 | 22892.3684 | 0 | 228052.9653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-05 | 1268547.5017 |  |  | 506922.1633 | 137475.4179 | 316559.2205 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 506922.1633 | 0 | 11403.9705 | 70920.3158 | 9193.8947 | 22984.7368 | 0 | 228107.1205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-06 | 1270530.9281 |  |  | 508467.8555 | 137858.9968 | 316613.3758 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 508467.8555 | 0 | 11418.0758 | 71160.4737 | 9230.8421 | 23077.1053 | 0 | 228161.2758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-07 | 1272514.3545 |  |  | 510013.5477 | 138242.5758 | 316667.5311 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 510013.5477 | 0 | 11432.1811 | 71400.6316 | 9267.7895 | 23169.4737 | 0 | 228215.4311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-08 | 1274497.7809 |  |  | 511559.2399 | 138626.1547 | 316721.6863 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 511559.2399 | 0 | 11446.2863 | 71640.7895 | 9304.7368 | 23261.8421 | 0 | 228269.5863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-09 | 1276481.2073 |  |  | 513104.932 | 139009.7337 | 316775.8416 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 513104.932 | 0 | 11460.3916 | 71880.9474 | 9341.6842 | 23354.2105 | 0 | 228323.7416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-10 | 1278464.6337 |  |  | 514650.6242 | 139393.3126 | 316829.9968 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 514650.6242 | 0 | 11474.4968 | 72121.1053 | 9378.6316 | 23446.5789 | 0 | 228377.8968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-11 | 1280448.0601 |  |  | 516196.3164 | 139776.8916 | 316884.1521 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 516196.3164 | 0 | 11488.6021 | 72361.2632 | 9415.5789 | 23538.9474 | 0 | 228432.0521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-12 | 1282431.4865 |  |  | 517742.0086 | 140160.4705 | 316938.3074 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 517742.0086 | 0 | 11502.7074 | 72601.4211 | 9452.5263 | 23631.3158 | 0 | 228486.2074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-13 | 1284414.9129 |  |  | 519287.7008 | 140544.0495 | 316992.4626 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 519287.7008 | 0 | 11516.8126 | 72841.5789 | 9489.4737 | 23723.6842 | 0 | 228540.3626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-14 | 1286398.3393 |  |  | 520833.393 | 140927.6284 | 317046.6179 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 520833.393 | 0 | 11530.9179 | 73081.7368 | 9526.4211 | 23816.0526 | 0 | 228594.5179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-15 | 1288381.7657 |  |  | 522379.0851 | 141311.2074 | 317100.7732 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 522379.0851 | 0 | 11545.0232 | 73321.8947 | 9563.3684 | 23908.4211 | 0 | 228648.6732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-16 | 1290365.1921 |  |  | 523924.7773 | 141694.7863 | 317154.9284 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 523924.7773 | 0 | 11559.1284 | 73562.0526 | 9600.3158 | 24000.7895 | 0 | 228702.8284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-17 | 1292348.6184 |  |  | 525470.4695 | 142078.3653 | 317209.0837 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 525470.4695 | 0 | 11573.2337 | 73802.2105 | 9637.2632 | 24093.1579 | 0 | 228756.9837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-18 | 1294332.0448 |  |  | 527016.1617 | 142461.9442 | 317263.2389 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 527016.1617 | 0 | 11587.3389 | 74042.3684 | 9674.2105 | 24185.5263 | 0 | 228811.1389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-19 | 1296315.4712 |  |  | 528561.8539 | 142845.5232 | 317317.3942 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 528561.8539 | 0 | 11601.4442 | 74282.5263 | 9711.1579 | 24277.8947 | 0 | 228865.2942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-20 | 1298298.8976 |  |  | 530107.546 | 143229.1021 | 317371.5495 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 530107.546 | 0 | 11615.5495 | 74522.6842 | 9748.1053 | 24370.2632 | 0 | 228919.4495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-21 | 1300282.324 |  |  | 531653.2382 | 143612.6811 | 317425.7047 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 531653.2382 | 0 | 11629.6547 | 74762.8421 | 9785.0526 | 24462.6316 | 0 | 228973.6047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-22 | 1302265.7504 |  |  | 533198.9304 | 143996.26 | 317479.86 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 533198.9304 | 0 | 11643.76 | 75003 | 9822 | 24555 | 0 | 229027.76 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-23 | 1304249.1768 |  |  | 534744.6226 | 144379.8389 | 317534.0153 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 534744.6226 | 0 | 11657.8653 | 75243.1579 | 9858.9474 | 24647.3684 | 0 | 229081.9153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-24 | 1306232.6032 |  |  | 536290.3148 | 144763.4179 | 317588.1705 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 536290.3148 | 0 | 11671.9705 | 75483.3158 | 9895.8947 | 24739.7368 | 0 | 229136.0705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-25 | 1308216.0296 |  |  | 537836.007 | 145146.9968 | 317642.3258 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 537836.007 | 0 | 11686.0758 | 75723.4737 | 9932.8421 | 24832.1053 | 0 | 229190.2258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-26 | 1310199.456 |  |  | 539381.6991 | 145530.5758 | 317696.4811 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 539381.6991 | 0 | 11700.1811 | 75963.6316 | 9969.7895 | 24924.4737 | 0 | 229244.3811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-27 | 1312182.8824 |  |  | 540927.3913 | 145914.1547 | 317750.6363 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 540927.3913 | 0 | 11714.2863 | 76203.7895 | 10006.7368 | 25016.8421 | 0 | 229298.5363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-28 | 1314166.3088 |  |  | 542473.0835 | 146297.7337 | 317804.7916 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 542473.0835 | 0 | 11728.3916 | 76443.9474 | 10043.6842 | 25109.2105 | 0 | 229352.6916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-01 | 1316149.7352 |  |  | 544018.7757 | 146681.3126 | 317858.9468 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 544018.7757 | 0 | 11742.4968 | 76684.1053 | 10080.6316 | 25201.5789 | 0 | 229406.8468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-02 | 1318133.1615 |  |  | 545564.4679 | 147064.8916 | 317913.1021 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 545564.4679 | 0 | 11756.6021 | 76924.2632 | 10117.5789 | 25293.9474 | 0 | 229461.0021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-03 | 1320116.5879 |  |  | 547110.16 | 147448.4705 | 317967.2574 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 547110.16 | 0 | 11770.7074 | 77164.4211 | 10154.5263 | 25386.3158 | 0 | 229515.1574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-04 | 1322100.0143 |  |  | 548655.8522 | 147832.0495 | 318021.4126 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 548655.8522 | 0 | 11784.8126 | 77404.5789 | 10191.4737 | 25478.6842 | 0 | 229569.3126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-05 | 1324083.4407 |  |  | 550201.5444 | 148215.6284 | 318075.5679 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 550201.5444 | 0 | 11798.9179 | 77644.7368 | 10228.4211 | 25571.0526 | 0 | 229623.4679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-06 | 1326066.8671 |  |  | 551747.2366 | 148599.2074 | 318129.7232 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 551747.2366 | 0 | 11813.0232 | 77884.8947 | 10265.3684 | 25663.4211 | 0 | 229677.6232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-07 | 1328050.2935 |  |  | 553292.9288 | 148982.7863 | 318183.8784 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 553292.9288 | 0 | 11827.1284 | 78125.0526 | 10302.3158 | 25755.7895 | 0 | 229731.7784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-08 | 1330033.7199 |  |  | 554838.621 | 149366.3653 | 318238.0337 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 554838.621 | 0 | 11841.2337 | 78365.2105 | 10339.2632 | 25848.1579 | 0 | 229785.9337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-09 | 1332017.1463 |  |  | 556384.3131 | 149749.9442 | 318292.1889 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 556384.3131 | 0 | 11855.3389 | 78605.3684 | 10376.2105 | 25940.5263 | 0 | 229840.0889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-10 | 1334000.5727 |  |  | 557930.0053 | 150133.5232 | 318346.3442 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 557930.0053 | 0 | 11869.4442 | 78845.5263 | 10413.1579 | 26032.8947 | 0 | 229894.2442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-11 | 1335983.9991 |  |  | 559475.6975 | 150517.1021 | 318400.4995 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 559475.6975 | 0 | 11883.5495 | 79085.6842 | 10450.1053 | 26125.2632 | 0 | 229948.3995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-12 | 1337967.4255 |  |  | 561021.3897 | 150900.6811 | 318454.6547 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 561021.3897 | 0 | 11897.6547 | 79325.8421 | 10487.0526 | 26217.6316 | 0 | 230002.5547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-13 | 1339950.8519 |  |  | 562567.0819 | 151284.26 | 318508.81 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 562567.0819 | 0 | 11911.76 | 79566 | 10524 | 26310 | 0 | 230056.71 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-14 | 1341934.2783 |  |  | 564112.774 | 151667.8389 | 318562.9653 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 564112.774 | 0 | 11925.8653 | 79806.1579 | 10560.9474 | 26402.3684 | 0 | 230110.8653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-15 | 1343917.7046 |  |  | 565658.4662 | 152051.4179 | 318617.1205 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 565658.4662 | 0 | 11939.9705 | 80046.3158 | 10597.8947 | 26494.7368 | 0 | 230165.0205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-16 | 1345901.131 |  |  | 567204.1584 | 152434.9968 | 318671.2758 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 567204.1584 | 0 | 11954.0758 | 80286.4737 | 10634.8421 | 26587.1053 | 0 | 230219.1758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-17 | 1347884.5574 |  |  | 568749.8506 | 152818.5758 | 318725.4311 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 568749.8506 | 0 | 11968.1811 | 80526.6316 | 10671.7895 | 26679.4737 | 0 | 230273.3311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-18 | 1349867.9838 |  |  | 570295.5428 | 153202.1547 | 318779.5863 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 570295.5428 | 0 | 11982.2863 | 80766.7895 | 10708.7368 | 26771.8421 | 0 | 230327.4863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-19 | 1351851.4102 |  |  | 571841.235 | 153585.7337 | 318833.7416 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 571841.235 | 0 | 11996.3916 | 81006.9474 | 10745.6842 | 26864.2105 | 0 | 230381.6416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-20 | 1353834.8366 |  |  | 573386.9271 | 153969.3126 | 318887.8968 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 573386.9271 | 0 | 12010.4968 | 81247.1053 | 10782.6316 | 26956.5789 | 0 | 230435.7968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-21 | 1355818.263 |  |  | 574932.6193 | 154352.8916 | 318942.0521 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 574932.6193 | 0 | 12024.6021 | 81487.2632 | 10819.5789 | 27048.9474 | 0 | 230489.9521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-22 | 1357801.6894 |  |  | 576478.3115 | 154736.4705 | 318996.2074 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 576478.3115 | 0 | 12038.7074 | 81727.4211 | 10856.5263 | 27141.3158 | 0 | 230544.1074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-23 | 1359785.1158 |  |  | 578024.0037 | 155120.0495 | 319050.3626 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 578024.0037 | 0 | 12052.8126 | 81967.5789 | 10893.4737 | 27233.6842 | 0 | 230598.2626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-24 | 1361768.5422 |  |  | 579569.6959 | 155503.6284 | 319104.5179 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 579569.6959 | 0 | 12066.9179 | 82207.7368 | 10930.4211 | 27326.0526 | 0 | 230652.4179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-25 | 1363751.9686 |  |  | 581115.388 | 155887.2074 | 319158.6732 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 581115.388 | 0 | 12081.0232 | 82447.8947 | 10967.3684 | 27418.4211 | 0 | 230706.5732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-26 | 1365735.395 |  |  | 582661.0802 | 156270.7863 | 319212.8284 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 582661.0802 | 0 | 12095.1284 | 82688.0526 | 11004.3158 | 27510.7895 | 0 | 230760.7284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-27 | 1367718.8214 |  |  | 584206.7724 | 156654.3653 | 319266.9837 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 584206.7724 | 0 | 12109.2337 | 82928.2105 | 11041.2632 | 27603.1579 | 0 | 230814.8837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-28 | 1369702.2477 |  |  | 585752.4646 | 157037.9442 | 319321.1389 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 585752.4646 | 0 | 12123.3389 | 83168.3684 | 11078.2105 | 27695.5263 | 0 | 230869.0389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-29 | 1371685.6741 |  |  | 587298.1568 | 157421.5232 | 319375.2942 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 587298.1568 | 0 | 12137.4442 | 83408.5263 | 11115.1579 | 27787.8947 | 0 | 230923.1942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-30 | 1373669.1005 |  |  | 588843.849 | 157805.1021 | 319429.4495 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 588843.849 | 0 | 12151.5495 | 83648.6842 | 11152.1053 | 27880.2632 | 0 | 230977.3495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-31 | 1375652.5269 |  |  | 590389.5411 | 158188.6811 | 319483.6047 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 590389.5411 | 0 | 12165.6547 | 83888.8421 | 11189.0526 | 27972.6316 | 0 | 231031.5047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-01 | 1377635.9533 |  |  | 591935.2333 | 158572.26 | 319537.76 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 591935.2333 | 0 | 12179.76 | 84129 | 11226 | 28065 | 0 | 231085.66 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-02 | 1379619.3797 |  |  | 593480.9255 | 158955.8389 | 319591.9153 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 593480.9255 | 0 | 12193.8653 | 84369.1579 | 11262.9474 | 28157.3684 | 0 | 231139.8153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-03 | 1381602.8061 |  |  | 595026.6177 | 159339.4179 | 319646.0705 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 595026.6177 | 0 | 12207.9705 | 84609.3158 | 11299.8947 | 28249.7368 | 0 | 231193.9705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-04 | 1383586.2325 |  |  | 596572.3099 | 159722.9968 | 319700.2258 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 596572.3099 | 0 | 12222.0758 | 84849.4737 | 11336.8421 | 28342.1053 | 0 | 231248.1258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-05 | 1385569.6589 |  |  | 598118.002 | 160106.5758 | 319754.3811 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 598118.002 | 0 | 12236.1811 | 85089.6316 | 11373.7895 | 28434.4737 | 0 | 231302.2811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-06 | 1387553.0853 |  |  | 599663.6942 | 160490.1547 | 319808.5363 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 599663.6942 | 0 | 12250.2863 | 85329.7895 | 11410.7368 | 28526.8421 | 0 | 231356.4363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-07 | 1389536.5117 |  |  | 601209.3864 | 160873.7337 | 319862.6916 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 601209.3864 | 0 | 12264.3916 | 85569.9474 | 11447.6842 | 28619.2105 | 0 | 231410.5916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-08 | 1391519.9381 |  |  | 602755.0786 | 161257.3126 | 319916.8468 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 602755.0786 | 0 | 12278.4968 | 85810.1053 | 11484.6316 | 28711.5789 | 0 | 231464.7468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-09 | 1393503.3645 |  |  | 604300.7708 | 161640.8916 | 319971.0021 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 604300.7708 | 0 | 12292.6021 | 86050.2632 | 11521.5789 | 28803.9474 | 0 | 231518.9021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-10 | 1395486.7908 |  |  | 605846.463 | 162024.4705 | 320025.1574 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 605846.463 | 0 | 12306.7074 | 86290.4211 | 11558.5263 | 28896.3158 | 0 | 231573.0574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-11 | 1397470.2172 |  |  | 607392.1551 | 162408.0495 | 320079.3126 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 607392.1551 | 0 | 12320.8126 | 86530.5789 | 11595.4737 | 28988.6842 | 0 | 231627.2126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-12 | 1399453.6436 |  |  | 608937.8473 | 162791.6284 | 320133.4679 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 608937.8473 | 0 | 12334.9179 | 86770.7368 | 11632.4211 | 29081.0526 | 0 | 231681.3679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-13 | 1401437.07 |  |  | 610483.5395 | 163175.2074 | 320187.6232 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 610483.5395 | 0 | 12349.0232 | 87010.8947 | 11669.3684 | 29173.4211 | 0 | 231735.5232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-14 | 1403420.4964 |  |  | 612029.2317 | 163558.7863 | 320241.7784 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 612029.2317 | 0 | 12363.1284 | 87251.0526 | 11706.3158 | 29265.7895 | 0 | 231789.6784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-15 | 1405403.9228 |  |  | 613574.9239 | 163942.3653 | 320295.9337 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 613574.9239 | 0 | 12377.2337 | 87491.2105 | 11743.2632 | 29358.1579 | 0 | 231843.8337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-16 | 1407387.3492 |  |  | 615120.616 | 164325.9442 | 320350.0889 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 615120.616 | 0 | 12391.3389 | 87731.3684 | 11780.2105 | 29450.5263 | 0 | 231897.9889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-17 | 1409370.7756 |  |  | 616666.3082 | 164709.5232 | 320404.2442 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 616666.3082 | 0 | 12405.4442 | 87971.5263 | 11817.1579 | 29542.8947 | 0 | 231952.1442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-18 | 1411354.202 |  |  | 618212.0004 | 165093.1021 | 320458.3995 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 618212.0004 | 0 | 12419.5495 | 88211.6842 | 11854.1053 | 29635.2632 | 0 | 232006.2995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-19 | 1413337.6284 |  |  | 619757.6926 | 165476.6811 | 320512.5547 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 619757.6926 | 0 | 12433.6547 | 88451.8421 | 11891.0526 | 29727.6316 | 0 | 232060.4547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-20 | 1415321.0548 |  |  | 621303.3848 | 165860.26 | 320566.71 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 621303.3848 | 0 | 12447.76 | 88692 | 11928 | 29820 | 0 | 232114.61 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-21 | 1417304.4812 |  |  | 622849.077 | 166243.8389 | 320620.8653 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 622849.077 | 0 | 12461.8653 | 88932.1579 | 11964.9474 | 29912.3684 | 0 | 232168.7653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-22 | 1419287.9076 |  |  | 624394.7691 | 166627.4179 | 320675.0205 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 624394.7691 | 0 | 12475.9705 | 89172.3158 | 12001.8947 | 30004.7368 | 0 | 232222.9205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-23 | 1421271.3339 |  |  | 625940.4613 | 167010.9968 | 320729.1758 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 625940.4613 | 0 | 12490.0758 | 89412.4737 | 12038.8421 | 30097.1053 | 0 | 232277.0758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-24 | 1423254.7603 |  |  | 627486.1535 | 167394.5758 | 320783.3311 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 627486.1535 | 0 | 12504.1811 | 89652.6316 | 12075.7895 | 30189.4737 | 0 | 232331.2311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-25 | 1425238.1867 |  |  | 629031.8457 | 167778.1547 | 320837.4863 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 629031.8457 | 0 | 12518.2863 | 89892.7895 | 12112.7368 | 30281.8421 | 0 | 232385.3863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-26 | 1427221.6131 |  |  | 630577.5379 | 168161.7337 | 320891.6416 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 630577.5379 | 0 | 12532.3916 | 90132.9474 | 12149.6842 | 30374.2105 | 0 | 232439.5416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-27 | 1429205.0395 |  |  | 632123.23 | 168545.3126 | 320945.7968 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 632123.23 | 0 | 12546.4968 | 90373.1053 | 12186.6316 | 30466.5789 | 0 | 232493.6968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-28 | 1431188.4659 |  |  | 633668.9222 | 168928.8916 | 320999.9521 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 633668.9222 | 0 | 12560.6021 | 90613.2632 | 12223.5789 | 30558.9474 | 0 | 232547.8521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-29 | 1433171.8923 |  |  | 635214.6144 | 169312.4705 | 321054.1074 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 635214.6144 | 0 | 12574.7074 | 90853.4211 | 12260.5263 | 30651.3158 | 0 | 232602.0074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-30 | 1435155.3187 |  |  | 636760.3066 | 169696.0495 | 321108.2626 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 636760.3066 | 0 | 12588.8126 | 91093.5789 | 12297.4737 | 30743.6842 | 0 | 232656.1626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-01 | 1437138.7451 |  |  | 638305.9988 | 170079.6284 | 321162.4179 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 638305.9988 | 0 | 12602.9179 | 91333.7368 | 12334.4211 | 30836.0526 | 0 | 232710.3179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-02 | 1439122.1715 |  |  | 639851.691 | 170463.2074 | 321216.5732 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 639851.691 | 0 | 12617.0232 | 91573.8947 | 12371.3684 | 30928.4211 | 0 | 232764.4732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-03 | 1441105.5979 |  |  | 641397.3831 | 170846.7863 | 321270.7284 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 641397.3831 | 0 | 12631.1284 | 91814.0526 | 12408.3158 | 31020.7895 | 0 | 232818.6284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-04 | 1443089.0243 |  |  | 642943.0753 | 171230.3653 | 321324.8837 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 642943.0753 | 0 | 12645.2337 | 92054.2105 | 12445.2632 | 31113.1579 | 0 | 232872.7837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-05 | 1445072.4507 |  |  | 644488.7675 | 171613.9442 | 321379.0389 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 644488.7675 | 0 | 12659.3389 | 92294.3684 | 12482.2105 | 31205.5263 | 0 | 232926.9389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-06 | 1447055.877 |  |  | 646034.4597 | 171997.5232 | 321433.1942 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 646034.4597 | 0 | 12673.4442 | 92534.5263 | 12519.1579 | 31297.8947 | 0 | 232981.0942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-07 | 1449039.3034 |  |  | 647580.1519 | 172381.1021 | 321487.3495 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 647580.1519 | 0 | 12687.5495 | 92774.6842 | 12556.1053 | 31390.2632 | 0 | 233035.2495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-08 | 1451022.7298 |  |  | 649125.844 | 172764.6811 | 321541.5047 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 649125.844 | 0 | 12701.6547 | 93014.8421 | 12593.0526 | 31482.6316 | 0 | 233089.4047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-09 | 1453006.1562 |  |  | 650671.5362 | 173148.26 | 321595.66 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 650671.5362 | 0 | 12715.76 | 93255 | 12630 | 31575 | 0 | 233143.56 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-10 | 1454989.5826 |  |  | 652217.2284 | 173531.8389 | 321649.8153 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 652217.2284 | 0 | 12729.8653 | 93495.1579 | 12666.9474 | 31667.3684 | 0 | 233197.7153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-11 | 1456973.009 |  |  | 653762.9206 | 173915.4179 | 321703.9705 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 653762.9206 | 0 | 12743.9705 | 93735.3158 | 12703.8947 | 31759.7368 | 0 | 233251.8705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-12 | 1458956.4354 |  |  | 655308.6128 | 174298.9968 | 321758.1258 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 655308.6128 | 0 | 12758.0758 | 93975.4737 | 12740.8421 | 31852.1053 | 0 | 233306.0258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-13 | 1460939.8618 |  |  | 656854.305 | 174682.5758 | 321812.2811 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 656854.305 | 0 | 12772.1811 | 94215.6316 | 12777.7895 | 31944.4737 | 0 | 233360.1811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-14 | 1462923.2882 |  |  | 658399.9971 | 175066.1547 | 321866.4363 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 658399.9971 | 0 | 12786.2863 | 94455.7895 | 12814.7368 | 32036.8421 | 0 | 233414.3363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-15 | 1464906.7146 |  |  | 659945.6893 | 175449.7337 | 321920.5916 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 659945.6893 | 0 | 12800.3916 | 94695.9474 | 12851.6842 | 32129.2105 | 0 | 233468.4916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-16 | 1466890.141 |  |  | 661491.3815 | 175833.3126 | 321974.7468 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 661491.3815 | 0 | 12814.4968 | 94936.1053 | 12888.6316 | 32221.5789 | 0 | 233522.6468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-17 | 1468873.5674 |  |  | 663037.0737 | 176216.8916 | 322028.9021 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 663037.0737 | 0 | 12828.6021 | 95176.2632 | 12925.5789 | 32313.9474 | 0 | 233576.8021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-18 | 1470856.9938 |  |  | 664582.7659 | 176600.4705 | 322083.0574 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 664582.7659 | 0 | 12842.7074 | 95416.4211 | 12962.5263 | 32406.3158 | 0 | 233630.9574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-19 | 1472840.4201 |  |  | 666128.458 | 176984.0495 | 322137.2126 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 666128.458 | 0 | 12856.8126 | 95656.5789 | 12999.4737 | 32498.6842 | 0 | 233685.1126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-20 | 1474823.8465 |  |  | 667674.1502 | 177367.6284 | 322191.3679 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 667674.1502 | 0 | 12870.9179 | 95896.7368 | 13036.4211 | 32591.0526 | 0 | 233739.2679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-21 | 1476807.2729 |  |  | 669219.8424 | 177751.2074 | 322245.5232 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 669219.8424 | 0 | 12885.0232 | 96136.8947 | 13073.3684 | 32683.4211 | 0 | 233793.4232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-22 | 1478790.6993 |  |  | 670765.5346 | 178134.7863 | 322299.6784 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 670765.5346 | 0 | 12899.1284 | 96377.0526 | 13110.3158 | 32775.7895 | 0 | 233847.5784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-23 | 1480774.1257 |  |  | 672311.2268 | 178518.3653 | 322353.8337 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 672311.2268 | 0 | 12913.2337 | 96617.2105 | 13147.2632 | 32868.1579 | 0 | 233901.7337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-24 | 1482757.5521 |  |  | 673856.919 | 178901.9442 | 322407.9889 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 673856.919 | 0 | 12927.3389 | 96857.3684 | 13184.2105 | 32960.5263 | 0 | 233955.8889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-25 | 1484740.9785 |  |  | 675402.6111 | 179285.5232 | 322462.1442 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 675402.6111 | 0 | 12941.4442 | 97097.5263 | 13221.1579 | 33052.8947 | 0 | 234010.0442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-26 | 1486724.4049 |  |  | 676948.3033 | 179669.1021 | 322516.2995 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 676948.3033 | 0 | 12955.5495 | 97337.6842 | 13258.1053 | 33145.2632 | 0 | 234064.1995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-27 | 1488707.8313 |  |  | 678493.9955 | 180052.6811 | 322570.4547 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 678493.9955 | 0 | 12969.6547 | 97577.8421 | 13295.0526 | 33237.6316 | 0 | 234118.3547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-28 | 1490691.2577 |  |  | 680039.6877 | 180436.26 | 322624.61 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 680039.6877 | 0 | 12983.76 | 97818 | 13332 | 33330 | 0 | 234172.51 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-29 | 1492674.6841 |  |  | 681585.3799 | 180819.8389 | 322678.7653 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 681585.3799 | 0 | 12997.8653 | 98058.1579 | 13368.9474 | 33422.3684 | 0 | 234226.6653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-30 | 1494658.1105 |  |  | 683131.072 | 181203.4179 | 322732.9205 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 683131.072 | 0 | 13011.9705 | 98298.3158 | 13405.8947 | 33514.7368 | 0 | 234280.8205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-31 | 1496641.5369 |  |  | 684676.7642 | 181586.9968 | 322787.0758 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 684676.7642 | 0 | 13026.0758 | 98538.4737 | 13442.8421 | 33607.1053 | 0 | 234334.9758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-01 | 1498624.9632 |  |  | 686222.4564 | 181970.5758 | 322841.2311 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 686222.4564 | 0 | 13040.1811 | 98778.6316 | 13479.7895 | 33699.4737 | 0 | 234389.1311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-02 | 1500608.3896 |  |  | 687768.1486 | 182354.1547 | 322895.3863 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 687768.1486 | 0 | 13054.2863 | 99018.7895 | 13516.7368 | 33791.8421 | 0 | 234443.2863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-03 | 1502591.816 |  |  | 689313.8408 | 182737.7337 | 322949.5416 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 689313.8408 | 0 | 13068.3916 | 99258.9474 | 13553.6842 | 33884.2105 | 0 | 234497.4416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-04 | 1504575.2424 |  |  | 690859.533 | 183121.3126 | 323003.6968 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 690859.533 | 0 | 13082.4968 | 99499.1053 | 13590.6316 | 33976.5789 | 0 | 234551.5968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-05 | 1506558.6688 |  |  | 692405.2251 | 183504.8916 | 323057.8521 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 692405.2251 | 0 | 13096.6021 | 99739.2632 | 13627.5789 | 34068.9474 | 0 | 234605.7521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-06 | 1508542.0952 |  |  | 693950.9173 | 183888.4705 | 323112.0074 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 693950.9173 | 0 | 13110.7074 | 99979.4211 | 13664.5263 | 34161.3158 | 0 | 234659.9074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-07 | 1510525.5216 |  |  | 695496.6095 | 184272.0495 | 323166.1626 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 695496.6095 | 0 | 13124.8126 | 100219.5789 | 13701.4737 | 34253.6842 | 0 | 234714.0626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-08 | 1512508.948 |  |  | 697042.3017 | 184655.6284 | 323220.3179 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 697042.3017 | 0 | 13138.9179 | 100459.7368 | 13738.4211 | 34346.0526 | 0 | 234768.2179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-09 | 1514492.3744 |  |  | 698587.9939 | 185039.2074 | 323274.4732 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 698587.9939 | 0 | 13153.0232 | 100699.8947 | 13775.3684 | 34438.4211 | 0 | 234822.3732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-10 | 1516475.8008 |  |  | 700133.686 | 185422.7863 | 323328.6284 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 700133.686 | 0 | 13167.1284 | 100940.0526 | 13812.3158 | 34530.7895 | 0 | 234876.5284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-11 | 1518459.2272 |  |  | 701679.3782 | 185806.3653 | 323382.7837 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 701679.3782 | 0 | 13181.2337 | 101180.2105 | 13849.2632 | 34623.1579 | 0 | 234930.6837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-12 | 1520442.6536 |  |  | 703225.0704 | 186189.9442 | 323436.9389 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 703225.0704 | 0 | 13195.3389 | 101420.3684 | 13886.2105 | 34715.5263 | 0 | 234984.8389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-13 | 1522426.08 |  |  | 704770.7626 | 186573.5232 | 323491.0942 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 704770.7626 | 0 | 13209.4442 | 101660.5263 | 13923.1579 | 34807.8947 | 0 | 235038.9942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-14 | 1524409.5063 |  |  | 706316.4548 | 186957.1021 | 323545.2495 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 706316.4548 | 0 | 13223.5495 | 101900.6842 | 13960.1053 | 34900.2632 | 0 | 235093.1495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-15 | 1526392.9327 |  |  | 707862.147 | 187340.6811 | 323599.4047 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 707862.147 | 0 | 13237.6547 | 102140.8421 | 13997.0526 | 34992.6316 | 0 | 235147.3047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-16 | 1528376.3591 |  |  | 709407.8391 | 187724.26 | 323653.56 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 709407.8391 | 0 | 13251.76 | 102381 | 14034 | 35085 | 0 | 235201.46 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-17 | 1530359.7855 |  |  | 710953.5313 | 188107.8389 | 323707.7153 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 710953.5313 | 0 | 13265.8653 | 102621.1579 | 14070.9474 | 35177.3684 | 0 | 235255.6153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-18 | 1532343.2119 |  |  | 712499.2235 | 188491.4179 | 323761.8705 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 712499.2235 | 0 | 13279.9705 | 102861.3158 | 14107.8947 | 35269.7368 | 0 | 235309.7705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-19 | 1534326.6383 |  |  | 714044.9157 | 188874.9968 | 323816.0258 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 714044.9157 | 0 | 13294.0758 | 103101.4737 | 14144.8421 | 35362.1053 | 0 | 235363.9258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-20 | 1536310.0647 |  |  | 715590.6079 | 189258.5758 | 323870.1811 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 715590.6079 | 0 | 13308.1811 | 103341.6316 | 14181.7895 | 35454.4737 | 0 | 235418.0811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-21 | 1538293.4911 |  |  | 717136.3 | 189642.1547 | 323924.3363 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 717136.3 | 0 | 13322.2863 | 103581.7895 | 14218.7368 | 35546.8421 | 0 | 235472.2363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-22 | 1540276.9175 |  |  | 718681.9922 | 190025.7337 | 323978.4916 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 718681.9922 | 0 | 13336.3916 | 103821.9474 | 14255.6842 | 35639.2105 | 0 | 235526.3916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-23 | 1542260.3439 |  |  | 720227.6844 | 190409.3126 | 324032.6468 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 720227.6844 | 0 | 13350.4968 | 104062.1053 | 14292.6316 | 35731.5789 | 0 | 235580.5468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-24 | 1544243.7703 |  |  | 721773.3766 | 190792.8916 | 324086.8021 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 721773.3766 | 0 | 13364.6021 | 104302.2632 | 14329.5789 | 35823.9474 | 0 | 235634.7021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-25 | 1546227.1967 |  |  | 723319.0688 | 191176.4705 | 324140.9574 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 723319.0688 | 0 | 13378.7074 | 104542.4211 | 14366.5263 | 35916.3158 | 0 | 235688.8574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-26 | 1548210.6231 |  |  | 724864.761 | 191560.0495 | 324195.1126 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 724864.761 | 0 | 13392.8126 | 104782.5789 | 14403.4737 | 36008.6842 | 0 | 235743.0126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-27 | 1550194.0494 |  |  | 726410.4531 | 191943.6284 | 324249.2679 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 726410.4531 | 0 | 13406.9179 | 105022.7368 | 14440.4211 | 36101.0526 | 0 | 235797.1679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-28 | 1552177.4758 |  |  | 727956.1453 | 192327.2074 | 324303.4232 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 727956.1453 | 0 | 13421.0232 | 105262.8947 | 14477.3684 | 36193.4211 | 0 | 235851.3232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-29 | 1554160.9022 |  |  | 729501.8375 | 192710.7863 | 324357.5784 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 729501.8375 | 0 | 13435.1284 | 105503.0526 | 14514.3158 | 36285.7895 | 0 | 235905.4784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-30 | 1556144.3286 |  |  | 731047.5297 | 193094.3653 | 324411.7337 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 731047.5297 | 0 | 13449.2337 | 105743.2105 | 14551.2632 | 36378.1579 | 0 | 235959.6337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-01 | 1558127.755 |  |  | 732593.2219 | 193477.9442 | 324465.8889 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 732593.2219 | 0 | 13463.3389 | 105983.3684 | 14588.2105 | 36470.5263 | 0 | 236013.7889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-02 | 1560111.1814 |  |  | 734138.914 | 193861.5232 | 324520.0442 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 734138.914 | 0 | 13477.4442 | 106223.5263 | 14625.1579 | 36562.8947 | 0 | 236067.9442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-03 | 1562094.6078 |  |  | 735684.6062 | 194245.1021 | 324574.1995 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 735684.6062 | 0 | 13491.5495 | 106463.6842 | 14662.1053 | 36655.2632 | 0 | 236122.0995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-04 | 1564078.0342 |  |  | 737230.2984 | 194628.6811 | 324628.3547 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 737230.2984 | 0 | 13505.6547 | 106703.8421 | 14699.0526 | 36747.6316 | 0 | 236176.2547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-05 | 1566061.4606 |  |  | 738775.9906 | 195012.26 | 324682.51 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 738775.9906 | 0 | 13519.76 | 106944 | 14736 | 36840 | 0 | 236230.41 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-06 | 1568044.887 |  |  | 740321.6828 | 195395.8389 | 324736.6653 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 740321.6828 | 0 | 13533.8653 | 107184.1579 | 14772.9474 | 36932.3684 | 0 | 236284.5653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-07 | 1570028.3134 |  |  | 741867.375 | 195779.4179 | 324790.8205 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 741867.375 | 0 | 13547.9705 | 107424.3158 | 14809.8947 | 37024.7368 | 0 | 236338.7205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-08 | 1572011.7398 |  |  | 743413.0671 | 196162.9968 | 324844.9758 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 743413.0671 | 0 | 13562.0758 | 107664.4737 | 14846.8421 | 37117.1053 | 0 | 236392.8758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-09 | 1573995.1662 |  |  | 744958.7593 | 196546.5758 | 324899.1311 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 744958.7593 | 0 | 13576.1811 | 107904.6316 | 14883.7895 | 37209.4737 | 0 | 236447.0311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-10 | 1575978.5925 |  |  | 746504.4515 | 196930.1547 | 324953.2863 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 746504.4515 | 0 | 13590.2863 | 108144.7895 | 14920.7368 | 37301.8421 | 0 | 236501.1863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-11 | 1577962.0189 |  |  | 748050.1437 | 197313.7337 | 325007.4416 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 748050.1437 | 0 | 13604.3916 | 108384.9474 | 14957.6842 | 37394.2105 | 0 | 236555.3416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-12 | 1579945.4453 |  |  | 749595.8359 | 197697.3126 | 325061.5968 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 749595.8359 | 0 | 13618.4968 | 108625.1053 | 14994.6316 | 37486.5789 | 0 | 236609.4968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-13 | 1581928.8717 |  |  | 751141.528 | 198080.8916 | 325115.7521 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 751141.528 | 0 | 13632.6021 | 108865.2632 | 15031.5789 | 37578.9474 | 0 | 236663.6521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-14 | 1583912.2981 |  |  | 752687.2202 | 198464.4705 | 325169.9074 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 752687.2202 | 0 | 13646.7074 | 109105.4211 | 15068.5263 | 37671.3158 | 0 | 236717.8074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-15 | 1585895.7245 |  |  | 754232.9124 | 198848.0495 | 325224.0626 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 754232.9124 | 0 | 13660.8126 | 109345.5789 | 15105.4737 | 37763.6842 | 0 | 236771.9626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-16 | 1587879.1509 |  |  | 755778.6046 | 199231.6284 | 325278.2179 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 755778.6046 | 0 | 13674.9179 | 109585.7368 | 15142.4211 | 37856.0526 | 0 | 236826.1179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-17 | 1589862.5773 |  |  | 757324.2968 | 199615.2074 | 325332.3732 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 757324.2968 | 0 | 13689.0232 | 109825.8947 | 15179.3684 | 37948.4211 | 0 | 236880.2732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-18 | 1591846.0037 |  |  | 758869.989 | 199998.7863 | 325386.5284 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 758869.989 | 0 | 13703.1284 | 110066.0526 | 15216.3158 | 38040.7895 | 0 | 236934.4284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-19 | 1593829.4301 |  |  | 760415.6811 | 200382.3653 | 325440.6837 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 760415.6811 | 0 | 13717.2337 | 110306.2105 | 15253.2632 | 38133.1579 | 0 | 236988.5837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-20 | 1595812.8565 |  |  | 761961.3733 | 200765.9442 | 325494.8389 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 761961.3733 | 0 | 13731.3389 | 110546.3684 | 15290.2105 | 38225.5263 | 0 | 237042.7389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-21 | 1597796.2829 |  |  | 763507.0655 | 201149.5232 | 325548.9942 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 763507.0655 | 0 | 13745.4442 | 110786.5263 | 15327.1579 | 38317.8947 | 0 | 237096.8942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-22 | 1599779.7093 |  |  | 765052.7577 | 201533.1021 | 325603.1495 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 765052.7577 | 0 | 13759.5495 | 111026.6842 | 15364.1053 | 38410.2632 | 0 | 237151.0495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-23 | 1601763.1356 |  |  | 766598.4499 | 201916.6811 | 325657.3047 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 766598.4499 | 0 | 13773.6547 | 111266.8421 | 15401.0526 | 38502.6316 | 0 | 237205.2047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-24 | 1603746.562 |  |  | 768144.142 | 202300.26 | 325711.46 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 768144.142 | 0 | 13787.76 | 111507 | 15438 | 38595 | 0 | 237259.36 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-25 | 1605729.9884 |  |  | 769689.8342 | 202683.8389 | 325765.6153 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 769689.8342 | 0 | 13801.8653 | 111747.1579 | 15474.9474 | 38687.3684 | 0 | 237313.5153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-26 | 1607713.4148 |  |  | 771235.5264 | 203067.4179 | 325819.7705 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 771235.5264 | 0 | 13815.9705 | 111987.3158 | 15511.8947 | 38779.7368 | 0 | 237367.6705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-27 | 1609696.8412 |  |  | 772781.2186 | 203450.9968 | 325873.9258 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 772781.2186 | 0 | 13830.0758 | 112227.4737 | 15548.8421 | 38872.1053 | 0 | 237421.8258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-28 | 1611680.2676 |  |  | 774326.9108 | 203834.5758 | 325928.0811 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 774326.9108 | 0 | 13844.1811 | 112467.6316 | 15585.7895 | 38964.4737 | 0 | 237475.9811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-29 | 1613663.694 |  |  | 775872.603 | 204218.1547 | 325982.2363 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 775872.603 | 0 | 13858.2863 | 112707.7895 | 15622.7368 | 39056.8421 | 0 | 237530.1363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-30 | 1615647.1204 |  |  | 777418.2951 | 204601.7337 | 326036.3916 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 777418.2951 | 0 | 13872.3916 | 112947.9474 | 15659.6842 | 39149.2105 | 0 | 237584.2916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-31 | 1617630.5468 |  |  | 778963.9873 | 204985.3126 | 326090.5468 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 778963.9873 | 0 | 13886.4968 | 113188.1053 | 15696.6316 | 39241.5789 | 0 | 237638.4468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-01 | 1619613.9732 |  |  | 780509.6795 | 205368.8916 | 326144.7021 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 780509.6795 | 0 | 13900.6021 | 113428.2632 | 15733.5789 | 39333.9474 | 0 | 237692.6021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-02 | 1621597.3996 |  |  | 782055.3717 | 205752.4705 | 326198.8574 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 782055.3717 | 0 | 13914.7074 | 113668.4211 | 15770.5263 | 39426.3158 | 0 | 237746.7574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-03 | 1623580.826 |  |  | 783601.0639 | 206136.0495 | 326253.0126 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 783601.0639 | 0 | 13928.8126 | 113908.5789 | 15807.4737 | 39518.6842 | 0 | 237800.9126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-04 | 1625564.2524 |  |  | 785146.756 | 206519.6284 | 326307.1679 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 785146.756 | 0 | 13942.9179 | 114148.7368 | 15844.4211 | 39611.0526 | 0 | 237855.0679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-05 | 1627547.6787 |  |  | 786692.4482 | 206903.2074 | 326361.3232 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 786692.4482 | 0 | 13957.0232 | 114388.8947 | 15881.3684 | 39703.4211 | 0 | 237909.2232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-06 | 1629531.1051 |  |  | 788238.1404 | 207286.7863 | 326415.4784 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 788238.1404 | 0 | 13971.1284 | 114629.0526 | 15918.3158 | 39795.7895 | 0 | 237963.3784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-07 | 1631514.5315 |  |  | 789783.8326 | 207670.3653 | 326469.6337 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 789783.8326 | 0 | 13985.2337 | 114869.2105 | 15955.2632 | 39888.1579 | 0 | 238017.5337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-08 | 1633497.9579 |  |  | 791329.5248 | 208053.9442 | 326523.7889 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 791329.5248 | 0 | 13999.3389 | 115109.3684 | 15992.2105 | 39980.5263 | 0 | 238071.6889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-09 | 1635481.3843 |  |  | 792875.217 | 208437.5232 | 326577.9442 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 792875.217 | 0 | 14013.4442 | 115349.5263 | 16029.1579 | 40072.8947 | 0 | 238125.8442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-10 | 1637464.8107 |  |  | 794420.9091 | 208821.1021 | 326632.0995 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 794420.9091 | 0 | 14027.5495 | 115589.6842 | 16066.1053 | 40165.2632 | 0 | 238179.9995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-11 | 1639448.2371 |  |  | 795966.6013 | 209204.6811 | 326686.2547 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 795966.6013 | 0 | 14041.6547 | 115829.8421 | 16103.0526 | 40257.6316 | 0 | 238234.1547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-12 | 1641431.6635 |  |  | 797512.2935 | 209588.26 | 326740.41 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 797512.2935 | 0 | 14055.76 | 116070 | 16140 | 40350 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-13 | 1643753.7997 |  |  | 798929.1356 | 210111.2012 | 327122.7629 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 798929.1356 | 0 | 14084.5835 | 116391.1765 | 16189.4118 | 40473.5294 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15632.3529 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-14 | 1646075.936 |  |  | 800345.9778 | 210634.1424 | 327505.1159 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 800345.9778 | 0 | 14113.4071 | 116712.3529 | 16238.8235 | 40597.0588 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16014.7059 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-15 | 1648398.0722 |  |  | 801762.8199 | 211157.0835 | 327887.4688 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 801762.8199 | 0 | 14142.2306 | 117033.5294 | 16288.2353 | 40720.5882 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16397.0588 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-16 | 1650720.2085 |  |  | 803179.662 | 211680.0247 | 328269.8218 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 803179.662 | 0 | 14171.0541 | 117354.7059 | 16337.6471 | 40844.1176 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16779.4118 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-17 | 1653042.3447 |  |  | 804596.5042 | 212202.9659 | 328652.1747 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 804596.5042 | 0 | 14199.8776 | 117675.8824 | 16387.0588 | 40967.6471 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 17161.7647 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-18 | 1655364.481 |  |  | 806013.3463 | 212725.9071 | 329034.5276 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 806013.3463 | 0 | 14228.7012 | 117997.0588 | 16436.4706 | 41091.1765 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 17544.1176 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-19 | 1657686.6172 |  |  | 807430.1884 | 213248.8482 | 329416.8806 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 807430.1884 | 0 | 14257.5247 | 118318.2353 | 16485.8824 | 41214.7059 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 17926.4706 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-20 | 1660008.7535 |  |  | 808847.0305 | 213771.7894 | 329799.2335 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 808847.0305 | 0 | 14286.3482 | 118639.4118 | 16535.2941 | 41338.2353 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 18308.8235 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-21 | 1662330.8897 |  |  | 810263.8727 | 214294.7306 | 330181.5865 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 810263.8727 | 0 | 14315.1718 | 118960.5882 | 16584.7059 | 41461.7647 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 18691.1765 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-22 | 1664653.026 |  |  | 811680.7148 | 214817.6718 | 330563.9394 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 811680.7148 | 0 | 14343.9953 | 119281.7647 | 16634.1176 | 41585.2941 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 19073.5294 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-23 | 1666975.1622 |  |  | 813097.5569 | 215340.6129 | 330946.2924 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 813097.5569 | 0 | 14372.8188 | 119602.9412 | 16683.5294 | 41708.8235 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 19455.8824 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-24 | 1669297.2985 |  |  | 814514.3991 | 215863.5541 | 331328.6453 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 814514.3991 | 0 | 14401.6424 | 119924.1176 | 16732.9412 | 41832.3529 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 19838.2353 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-25 | 1671619.4347 |  |  | 815931.2412 | 216386.4953 | 331710.9982 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 815931.2412 | 0 | 14430.4659 | 120245.2941 | 16782.3529 | 41955.8824 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 20220.5882 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-26 | 1673941.571 |  |  | 817348.0833 | 216909.4365 | 332093.3512 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 817348.0833 | 0 | 14459.2894 | 120566.4706 | 16831.7647 | 42079.4118 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 20602.9412 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-27 | 1676263.7072 |  |  | 818764.9255 | 217432.3776 | 332475.7041 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 818764.9255 | 0 | 14488.1129 | 120887.6471 | 16881.1765 | 42202.9412 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 20985.2941 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-28 | 1678585.8435 |  |  | 820181.7676 | 217955.3188 | 332858.0571 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 820181.7676 | 0 | 14516.9365 | 121208.8235 | 16930.5882 | 42326.4706 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 21367.6471 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-29 | 1680907.9797 |  |  | 821598.6097 | 218478.26 | 333240.41 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 821598.6097 | 0 | 14545.76 | 121530 | 16980 | 42450 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 21750 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-30 | 1683230.116 |  |  | 823015.4519 | 219001.2012 | 333622.7629 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 823015.4519 | 0 | 14574.5835 | 121851.1765 | 17029.4118 | 42573.5294 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 22132.3529 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-31 | 1685552.2522 |  |  | 824432.294 | 219524.1424 | 334005.1159 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 824432.294 | 0 | 14603.4071 | 122172.3529 | 17078.8235 | 42697.0588 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 22514.7059 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-01 | 1687874.3885 |  |  | 825849.1361 | 220047.0835 | 334387.4688 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 825849.1361 | 0 | 14632.2306 | 122493.5294 | 17128.2353 | 42820.5882 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 22897.0588 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-02 | 1690196.5247 |  |  | 827265.9783 | 220570.0247 | 334769.8218 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 827265.9783 | 0 | 14661.0541 | 122814.7059 | 17177.6471 | 42944.1176 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 23279.4118 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-03 | 1692518.661 |  |  | 828682.8204 | 221092.9659 | 335152.1747 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 828682.8204 | 0 | 14689.8776 | 123135.8824 | 17227.0588 | 43067.6471 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 23661.7647 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-04 | 1694840.7972 |  |  | 830099.6625 | 221615.9071 | 335534.5276 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 830099.6625 | 0 | 14718.7012 | 123457.0588 | 17276.4706 | 43191.1765 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 24044.1176 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-05 | 1697162.9335 |  |  | 831516.5047 | 222138.8482 | 335916.8806 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 831516.5047 | 0 | 14747.5247 | 123778.2353 | 17325.8824 | 43314.7059 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 24426.4706 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-06 | 1699485.0697 |  |  | 832933.3468 | 222661.7894 | 336299.2335 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 832933.3468 | 0 | 14776.3482 | 124099.4118 | 17375.2941 | 43438.2353 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 24808.8235 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-07 | 1701807.206 |  |  | 834350.1889 | 223184.7306 | 336681.5865 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 834350.1889 | 0 | 14805.1718 | 124420.5882 | 17424.7059 | 43561.7647 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25191.1765 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-08 | 1704129.3422 |  |  | 835767.031 | 223707.6718 | 337063.9394 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 835767.031 | 0 | 14833.9953 | 124741.7647 | 17474.1176 | 43685.2941 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25573.5294 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-09 | 1706451.4785 |  |  | 837183.8732 | 224230.6129 | 337446.2924 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 837183.8732 | 0 | 14862.8188 | 125062.9412 | 17523.5294 | 43808.8235 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25955.8824 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-10 | 1708773.6147 |  |  | 838600.7153 | 224753.5541 | 337828.6453 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 838600.7153 | 0 | 14891.6424 | 125384.1176 | 17572.9412 | 43932.3529 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 26338.2353 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-11 | 1711095.751 |  |  | 840017.5574 | 225276.4953 | 338210.9982 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 840017.5574 | 0 | 14920.4659 | 125705.2941 | 17622.3529 | 44055.8824 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 26720.5882 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-12 | 1713417.8872 |  |  | 841434.3996 | 225799.4365 | 338593.3512 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 841434.3996 | 0 | 14949.2894 | 126026.4706 | 17671.7647 | 44179.4118 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27102.9412 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-13 | 1715740.0235 |  |  | 842851.2417 | 226322.3776 | 338975.7041 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 842851.2417 | 0 | 14978.1129 | 126347.6471 | 17721.1765 | 44302.9412 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27485.2941 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-14 | 1718062.1597 |  |  | 844268.0838 | 226845.3188 | 339358.0571 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 844268.0838 | 0 | 15006.9365 | 126668.8235 | 17770.5882 | 44426.4706 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27867.6471 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-15 | 1720384.296 |  |  | 845684.926 | 227368.26 | 339740.41 | 14050 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 845684.926 | 0 | 15035.76 | 126990 | 17820 | 44550 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 28250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0

## Cost Sum
Date | Planned Total Cost (Cumulative) | Actual Total Cost (Cumulative) | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Planned Total Cost (Daily) | Actual Total Cost (Daily) | Planned Labor (Daily) | Actual Labor (Daily) | Planned Travel&perdiem (Daily) | Actual Travel&perdiem (Daily) | Planned Parts&materials (Daily) | Actual Parts&materials (Daily) | Planned Outsource (Daily) | Actual Outsource (Daily) | Planned Equipment (Daily) | Actual Equipment (Daily)
2025-04-02 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 1914.2857 | 5000 | 1914.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 5000 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
2025-04-04 | 2871.4286 | 5000 | 2871.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 3828.5714 | 5000 | 3828.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 4785.7143 | 5000 | 4785.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 5742.8571 | 6126.6 | 5742.8571 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1126.6 | 957.1429 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 6700 | 7253.2 | 6700 | 2253.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1126.6 | 957.1429 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 7657.1429 | 8379.8 | 7657.1429 | 3379.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1126.6 | 957.1429 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 8614.2857 | 9716.32 | 8614.2857 | 4506.4 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1336.52 | 957.1429 | 1126.6 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 9571.4286 | 10879.95 | 9571.4286 | 5633 | 0 | 209.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 1163.63 | 957.1429 | 1126.6 | 0 | 0 | 0 | 37.03 | 0 | 0 | 0 | 0
2025-04-12 | 10528.5714 | 10897.95 | 10528.5714 | 5633 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 18 | 957.1429 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 11485.7143 | 10897.95 | 11485.7143 | 5633 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 12442.8571 | 11112.35 | 12442.8571 | 5847.4 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 13400 | 11326.75 | 13400 | 6061.8 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 14357.1429 | 11541.15 | 14357.1429 | 6276.2 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 15314.2857 | 11755.55 | 15314.2857 | 6490.6 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 16271.4286 | 11969.95 | 16271.4286 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 17228.5714 | 11969.95 | 17228.5714 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 18185.7143 | 11969.95 | 18185.7143 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 19142.8571 | 12352.1 | 19142.8571 | 7087.15 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 20100 | 12734.25 | 20100 | 7469.3 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 21057.1429 | 13116.4 | 21057.1429 | 7851.45 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 22014.2857 | 13498.55 | 22014.2857 | 8233.6 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 22971.4286 | 13880.7 | 22971.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 23928.5714 | 13880.7 | 23928.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 24885.7143 | 13880.7 | 24885.7143 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 25842.8571 | 13880.7 | 25842.8571 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 26800 | 13880.7 | 26800 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 27757.1429 | 13880.7 | 27757.1429 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 28714.2857 | 13880.7 | 28714.2857 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 29671.4286 | 13880.7 | 29671.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 30628.5714 | 13880.7 | 30628.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 31585.7143 | 13880.7 | 31585.7143 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 32542.8571 | 13880.7 | 32542.8571 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 33500 | 13880.7 | 33500 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 34457.1429 | 13880.7 | 34457.1429 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 35414.2857 | 13880.7 | 35414.2857 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 36371.4286 | 13880.7 | 36371.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 37328.5714 | 13880.7 | 37328.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 38285.7143 | 13880.7 | 38285.7143 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 39242.8571 | 13880.7 | 39242.8571 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 40200 | 13880.7 | 40200 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 41157.1429 | 13880.7 | 41157.1429 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 42114.2857 | 13880.7 | 42114.2857 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 43071.4286 | 13880.7 | 43071.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 44028.5714 | 13880.7 | 44028.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 44985.7143 | 14644.31 | 44985.7143 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 763.61 | 957.1429 | 0 | 0 | 0 | 0 | 763.61 | 0 | 0 | 0 | 0
2025-05-19 | 45942.8571 | 14644.31 | 45942.8571 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 46900 | 14644.31 | 46900 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 47857.1429 | 14644.31 | 47857.1429 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 48814.2857 | 14644.31 | 48814.2857 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 49771.4286 | 14823.29 | 49771.4286 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 178.98 | 957.1429 | 0 | 0 | 0 | 0 | 178.98 | 0 | 0 | 0 | 0
2025-05-24 | 50728.5714 | 14823.29 | 50728.5714 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 51685.7143 | 14823.29 | 51685.7143 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 52642.8571 | 14823.29 | 52642.8571 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 53600 | 14823.29 | 53600 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 54557.1429 | 14823.29 | 54557.1429 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 55514.2857 | 14823.29 | 55514.2857 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 56471.4286 | 14823.29 | 56471.4286 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 57428.5714 | 14823.29 | 57428.5714 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 58385.7143 | 14823.29 | 58385.7143 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 59342.8571 | 15252.09 | 59342.8571 | 9044.55 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 428.8 | 957.1429 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 60300 | 15680.89 | 60300 | 9473.35 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 428.8 | 957.1429 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 61257.1429 | 16109.69 | 61257.1429 | 9902.15 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 428.8 | 957.1429 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 62214.2857 | 16538.49 | 62214.2857 | 10330.95 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 428.8 | 957.1429 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 63171.4286 | 16967.29 | 63171.4286 | 10759.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 428.8 | 957.1429 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 64128.5714 | 16967.29 | 64128.5714 | 10759.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 65085.7143 | 16967.29 | 65085.7143 | 10759.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 66042.8571 | 17074.49 | 66042.8571 | 10866.95 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 67000 | 17181.69 | 67000 | 10974.15 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 67957.1429 | 17288.89 | 67957.1429 | 11081.35 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 68914.2857 | 17396.09 | 68914.2857 | 11188.55 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 69871.4286 | 17503.29 | 69871.4286 | 11295.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 70828.5714 | 17503.29 | 70828.5714 | 11295.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 71785.7143 | 17503.29 | 71785.7143 | 11295.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 72742.8571 | 17885.44 | 72742.8571 | 11677.9 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 73700 | 18267.59 | 73700 | 12060.05 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 74657.1429 | 18649.74 | 74657.1429 | 12442.2 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 75614.2857 | 19031.89 | 75614.2857 | 12824.35 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 76571.4286 | 19414.04 | 76571.4286 | 13206.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 77528.5714 | 19414.04 | 77528.5714 | 13206.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 78485.7143 | 19414.04 | 78485.7143 | 13206.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 79442.8571 | 19521.24 | 79442.8571 | 13313.7 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 80400 | 19628.44 | 80400 | 13420.9 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 82714.3068 | 19735.64 | 80522.9722 | 13528.1 | 143.0527 | 227.92 | 948.9331 | 979.62 | 129.935 | 0 | 969.4138 | 5000 | 2314.3068 | 107.2 | 122.9722 | 107.2 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-06-26 | 85028.6137 | 19842.84 | 80645.9444 | 13635.3 | 286.1055 | 227.92 | 1897.8662 | 979.62 | 259.8701 | 0 | 1938.8276 | 5000 | 2314.3068 | 107.2 | 122.9722 | 107.2 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-06-27 | 87342.9205 | 19950.04 | 80768.9166 | 13742.5 | 429.1582 | 227.92 | 2846.7993 | 979.62 | 389.8051 | 0 | 2908.2414 | 5000 | 2314.3068 | 107.2 | 122.9722 | 107.2 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-06-28 | 89657.2274 | 19950.04 | 80891.8888 | 13742.5 | 572.211 | 227.92 | 3795.7323 | 979.62 | 519.7401 | 0 | 3877.6552 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-06-29 | 91971.5342 | 19950.04 | 81014.861 | 13742.5 | 715.2637 | 227.92 | 4744.6654 | 979.62 | 649.6752 | 0 | 4847.069 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-06-30 | 94285.841 | 20399.19 | 81137.8331 | 14191.65 | 858.3164 | 227.92 | 5693.5985 | 979.62 | 779.6102 | 0 | 5816.4828 | 5000 | 2314.3068 | 449.15 | 122.9722 | 449.15 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-01 | 96600.1479 | 20848.34 | 81260.8053 | 14640.8 | 1001.3692 | 227.92 | 6642.5316 | 979.62 | 909.5452 | 0 | 6785.8966 | 5000 | 2314.3068 | 449.15 | 122.9722 | 449.15 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-02 | 98914.4547 | 21297.49 | 81383.7775 | 15089.95 | 1144.4219 | 227.92 | 7591.4647 | 979.62 | 1039.4803 | 0 | 7755.3103 | 5000 | 2314.3068 | 449.15 | 122.9722 | 449.15 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-03 | 101228.7616 | 21746.64 | 81506.7497 | 15539.1 | 1287.4747 | 227.92 | 8540.3978 | 979.62 | 1169.4153 | 0 | 8724.7241 | 5000 | 2314.3068 | 449.15 | 122.9722 | 449.15 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-04 | 103543.0684 | 22195.79 | 81629.7219 | 15988.25 | 1430.5274 | 227.92 | 9489.3308 | 979.62 | 1299.3503 | 0 | 9694.1379 | 5000 | 2314.3068 | 449.15 | 122.9722 | 449.15 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-05 | 105857.3752 | 22195.79 | 81752.6941 | 15988.25 | 1573.5801 | 227.92 | 10438.2639 | 979.62 | 1429.2854 | 0 | 10663.5517 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-06 | 108171.6821 | 22195.79 | 81875.6663 | 15988.25 | 1716.6329 | 227.92 | 11387.197 | 979.62 | 1559.2204 | 0 | 11632.9655 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-07 | 110485.9889 | 22597.79 | 81998.6385 | 16390.25 | 1859.6856 | 227.92 | 12336.1301 | 979.62 | 1689.1554 | 0 | 12602.3793 | 5000 | 2314.3068 | 402 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-08 | 112800.2958 | 22999.79 | 82121.6107 | 16792.25 | 2002.7384 | 227.92 | 13285.0632 | 979.62 | 1819.0905 | 0 | 13571.7931 | 5000 | 2314.3068 | 402 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-09 | 115114.6026 | 23401.79 | 82244.5829 | 17194.25 | 2145.7911 | 227.92 | 14233.9963 | 979.62 | 1949.0255 | 0 | 14541.2069 | 5000 | 2314.3068 | 402 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-10 | 117428.9095 | 23803.79 | 82367.5551 | 17596.25 | 2288.8438 | 227.92 | 15182.9293 | 979.62 | 2078.9605 | 0 | 15510.6207 | 5000 | 2314.3068 | 402 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-11 | 119743.2163 | 24205.79 | 82490.5273 | 17998.25 | 2431.8966 | 227.92 | 16131.8624 | 979.62 | 2208.8956 | 0 | 16480.0345 | 5000 | 2314.3068 | 402 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-12 | 122057.5231 | 24205.79 | 82613.4994 | 17998.25 | 2574.9493 | 227.92 | 17080.7955 | 979.62 | 2338.8306 | 0 | 17449.4483 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-13 | 124371.83 | 24205.79 | 82736.4716 | 17998.25 | 2718.0021 | 227.92 | 18029.7286 | 979.62 | 2468.7656 | 0 | 18418.8621 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-14 | 126686.1368 | 26149.69 | 82859.4438 | 18400.25 | 2861.0548 | 1769.82 | 18978.6617 | 979.62 | 2598.7006 | 0 | 19388.2759 | 5000 | 2314.3068 | 1943.9 | 122.9722 | 402 | 143.0527 | 1541.9 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-15 | 129000.4437 | 26551.69 | 82982.416 | 18802.25 | 3004.1075 | 1769.82 | 19927.5948 | 979.62 | 2728.6357 | 0 | 20357.6897 | 5000 | 2314.3068 | 402 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-16 | 131314.7505 | 26953.69 | 83105.3882 | 19204.25 | 3147.1603 | 1769.82 | 20876.5278 | 979.62 | 2858.5707 | 0 | 21327.1034 | 5000 | 2314.3068 | 402 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-17 | 133629.0573 | 27420.14 | 83228.3604 | 19606.25 | 3290.213 | 1834.27 | 21825.4609 | 979.62 | 2988.5057 | 0 | 22296.5172 | 5000 | 2314.3068 | 466.45 | 122.9722 | 402 | 143.0527 | 64.45 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-18 | 135943.3642 | 27849.28 | 83351.3326 | 20008.25 | 3433.2658 | 1861.41 | 22774.394 | 979.62 | 3118.4408 | 0 | 23265.931 | 5000 | 2314.3068 | 429.14 | 122.9722 | 402 | 143.0527 | 27.14 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-19 | 138257.671 | 27879.28 | 83474.3048 | 20008.25 | 3576.3185 | 1891.41 | 23723.3271 | 979.62 | 3248.3758 | 0 | 24235.3448 | 5000 | 2314.3068 | 30 | 122.9722 | 0 | 143.0527 | 30 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-20 | 140571.9779 | 27879.28 | 83597.277 | 20008.25 | 3719.3712 | 1891.41 | 24672.2602 | 979.62 | 3378.3108 | 0 | 25204.7586 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-21 | 142886.2847 | 28281.28 | 83720.2492 | 20410.25 | 3862.424 | 1891.41 | 25621.1933 | 979.62 | 3508.2459 | 0 | 26174.1724 | 5000 | 2314.3068 | 402 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-22 | 145200.5915 | 29183.28 | 83843.2214 | 20812.25 | 4005.4767 | 1891.41 | 26570.1263 | 979.62 | 3638.1809 | 500 | 27143.5862 | 5000 | 2314.3068 | 902 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 500 | 969.4138 | 0
2025-07-23 | 147514.8984 | 29585.28 | 83966.1935 | 21214.25 | 4148.5295 | 1891.41 | 27519.0594 | 979.62 | 3768.1159 | 500 | 28113 | 5000 | 2314.3068 | 402 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-24 | 149829.2052 | 29987.28 | 84089.1657 | 21616.25 | 4291.5822 | 1891.41 | 28467.9925 | 979.62 | 3898.051 | 500 | 29082.4138 | 5000 | 2314.3068 | 402 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-25 | 152143.5121 | 30389.28 | 84212.1379 | 22018.25 | 4434.6349 | 1891.41 | 29416.9256 | 979.62 | 4027.986 | 500 | 30051.8276 | 5000 | 2314.3068 | 402 | 122.9722 | 402 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-26 | 154457.8189 | 30389.28 | 84335.1101 | 22018.25 | 4577.6877 | 1891.41 | 30365.8587 | 979.62 | 4157.921 | 500 | 31021.2414 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-27 | 156772.1257 | 30389.28 | 84458.0823 | 22018.25 | 4720.7404 | 1891.41 | 31314.7918 | 979.62 | 4287.8561 | 500 | 31990.6552 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-28 | 159086.4326 | 30737.68 | 84581.0545 | 22366.65 | 4863.7932 | 1891.41 | 32263.7248 | 979.62 | 4417.7911 | 500 | 32960.069 | 5000 | 2314.3068 | 348.4 | 122.9722 | 348.4 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-29 | 161400.7394 | 31086.08 | 84704.0267 | 22715.05 | 5006.8459 | 1891.41 | 33212.6579 | 979.62 | 4547.7261 | 500 | 33929.4828 | 5000 | 2314.3068 | 348.4 | 122.9722 | 348.4 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-30 | 163715.0463 | 31434.48 | 84826.9989 | 23063.45 | 5149.8987 | 1891.41 | 34161.591 | 979.62 | 4677.6612 | 500 | 34898.8966 | 5000 | 2314.3068 | 348.4 | 122.9722 | 348.4 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-07-31 | 166029.3531 | 31782.88 | 84949.9711 | 23411.85 | 5292.9514 | 1891.41 | 35110.5241 | 979.62 | 4807.5962 | 500 | 35868.3103 | 5000 | 2314.3068 | 348.4 | 122.9722 | 348.4 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-01 | 168343.6599 | 32131.28 | 85072.9433 | 23760.25 | 5436.0041 | 1891.41 | 36059.4572 | 979.62 | 4937.5312 | 500 | 36837.7241 | 5000 | 2314.3068 | 348.4 | 122.9722 | 348.4 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-02 | 170657.9668 | 32131.28 | 85195.9155 | 23760.25 | 5579.0569 | 1891.41 | 37008.3903 | 979.62 | 5067.4663 | 500 | 37807.1379 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-03 | 172972.2736 | 32131.28 | 85318.8877 | 23760.25 | 5722.1096 | 1891.41 | 37957.3233 | 979.62 | 5197.4013 | 500 | 38776.5517 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-04 | 175286.5805 | 33768.43 | 85441.8598 | 24028.25 | 5865.1624 | 1891.41 | 38906.2564 | 2348.77 | 5327.3363 | 500 | 39745.9655 | 5000 | 2314.3068 | 1637.15 | 122.9722 | 268 | 143.0527 | 0 | 948.9331 | 1369.15 | 129.935 | 0 | 969.4138 | 0
2025-08-05 | 177600.8873 | 34036.43 | 85564.832 | 24296.25 | 6008.2151 | 1891.41 | 39855.1895 | 2348.77 | 5457.2714 | 500 | 40715.3793 | 5000 | 2314.3068 | 268 | 122.9722 | 268 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-06 | 179915.1941 | 34304.43 | 85687.8042 | 24564.25 | 6151.2678 | 1891.41 | 40804.1226 | 2348.77 | 5587.2064 | 500 | 41684.7931 | 5000 | 2314.3068 | 268 | 122.9722 | 268 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-07 | 182229.501 | 35523.3 | 85810.7764 | 24832.25 | 6294.3206 | 1891.41 | 41753.0557 | 3299.64 | 5717.1414 | 500 | 42654.2069 | 5000 | 2314.3068 | 1218.87 | 122.9722 | 268 | 143.0527 | 0 | 948.9331 | 950.87 | 129.935 | 0 | 969.4138 | 0
2025-08-08 | 184543.8078 | 35791.3 | 85933.7486 | 25100.25 | 6437.3733 | 1891.41 | 42701.9888 | 3299.64 | 5847.0765 | 500 | 43623.6207 | 5000 | 2314.3068 | 268 | 122.9722 | 268 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-09 | 186858.1147 | 35791.3 | 86056.7208 | 25100.25 | 6580.4261 | 1891.41 | 43650.9218 | 3299.64 | 5977.0115 | 500 | 44593.0345 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-10 | 189172.4215 | 35791.3 | 86179.693 | 25100.25 | 6723.4788 | 1891.41 | 44599.8549 | 3299.64 | 6106.9465 | 500 | 45562.4483 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-11 | 191486.7284 | 36272.59 | 86302.6652 | 25314.65 | 6866.5315 | 1891.41 | 45548.788 | 3566.53 | 6236.8816 | 500 | 46531.8621 | 5000 | 2314.3068 | 481.29 | 122.9722 | 214.4 | 143.0527 | 0 | 948.9331 | 266.89 | 129.935 | 0 | 969.4138 | 0
2025-08-12 | 193801.0352 | 36486.99 | 86425.6374 | 25529.05 | 7009.5843 | 1891.41 | 46497.7211 | 3566.53 | 6366.8166 | 500 | 47501.2759 | 5000 | 2314.3068 | 214.4 | 122.9722 | 214.4 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-13 | 196115.342 | 36701.39 | 86548.6096 | 25743.45 | 7152.637 | 1891.41 | 47446.6542 | 3566.53 | 6496.7516 | 500 | 48470.6897 | 5000 | 2314.3068 | 214.4 | 122.9722 | 214.4 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-14 | 198429.6489 | 36915.79 | 86671.5818 | 25957.85 | 7295.6898 | 1891.41 | 48395.5873 | 3566.53 | 6626.6867 | 500 | 49440.1034 | 5000 | 2314.3068 | 214.4 | 122.9722 | 214.4 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-15 | 200743.9557 | 37130.19 | 86794.5539 | 26172.25 | 7438.7425 | 1891.41 | 49344.5203 | 3566.53 | 6756.6217 | 500 | 50409.5172 | 5000 | 2314.3068 | 214.4 | 122.9722 | 214.4 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-16 | 203058.2626 | 37130.19 | 86917.5261 | 26172.25 | 7581.7952 | 1891.41 | 50293.4534 | 3566.53 | 6886.5567 | 500 | 51378.931 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-17 | 205372.5694 | 37130.19 | 87040.4983 | 26172.25 | 7724.848 | 1891.41 | 51242.3865 | 3566.53 | 7016.4918 | 500 | 52348.3448 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-18 | 207686.8762 | 37666.19 | 87163.4705 | 26708.25 | 7867.9007 | 1891.41 | 52191.3196 | 3566.53 | 7146.4268 | 500 | 53317.7586 | 5000 | 2314.3068 | 536 | 122.9722 | 536 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-19 | 210001.1831 | 50711.55 | 87286.4427 | 27244.25 | 8010.9535 | 1891.41 | 53140.2527 | 16075.89 | 7276.3618 | 500 | 54287.1724 | 5000 | 2314.3068 | 13045.36 | 122.9722 | 536 | 143.0527 | 0 | 948.9331 | 12509.36 | 129.935 | 0 | 969.4138 | 0
2025-08-20 | 212315.4899 | 51386.36 | 87409.4149 | 27780.25 | 8154.0062 | 2030.22 | 54089.1858 | 16075.89 | 7406.2969 | 500 | 55256.5862 | 5000 | 2314.3068 | 674.81 | 122.9722 | 536 | 143.0527 | 138.81 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-21 | 214629.7968 | 51922.36 | 87532.3871 | 28316.25 | 8297.0589 | 2030.22 | 55038.1188 | 16075.89 | 7536.2319 | 500 | 56226 | 5000 | 2314.3068 | 536 | 122.9722 | 536 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-22 | 216944.1036 | 52558.36 | 87655.3593 | 28852.25 | 8440.1117 | 2130.22 | 55987.0519 | 16075.89 | 7666.1669 | 500 | 57195.4138 | 5000 | 2314.3068 | 636 | 122.9722 | 536 | 143.0527 | 100 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-23 | 219258.4104 | 52558.36 | 87778.3315 | 28852.25 | 8583.1644 | 2130.22 | 56935.985 | 16075.89 | 7796.1019 | 500 | 58164.8276 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-24 | 221572.7173 | 52558.36 | 87901.3037 | 28852.25 | 8726.2172 | 2130.22 | 57884.9181 | 16075.89 | 7926.037 | 500 | 59134.2414 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-25 | 223887.0241 | 54392.92 | 88024.2759 | 29952.05 | 8869.2699 | 2130.22 | 58833.8512 | 16795.65 | 8055.972 | 515 | 60103.6552 | 5000 | 2314.3068 | 1834.56 | 122.9722 | 1099.8 | 143.0527 | 0 | 948.9331 | 719.76 | 129.935 | 15 | 969.4138 | 0
2025-08-26 | 226201.331 | 58242.72 | 88147.2481 | 31051.85 | 9012.3226 | 2130.22 | 59782.7843 | 16795.65 | 8185.907 | 3265 | 61073.069 | 5000 | 2314.3068 | 3849.8 | 122.9722 | 1099.8 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 2750 | 969.4138 | 0
2025-08-27 | 228515.6378 | 59342.52 | 88270.2202 | 32151.65 | 9155.3754 | 2130.22 | 60731.7173 | 16795.65 | 8315.8421 | 3265 | 62042.4828 | 5000 | 2314.3068 | 1099.8 | 122.9722 | 1099.8 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-28 | 230829.9446 | 60442.32 | 88393.1924 | 33251.45 | 9298.4281 | 2130.22 | 61680.6504 | 16795.65 | 8445.7771 | 3265 | 63011.8966 | 5000 | 2314.3068 | 1099.8 | 122.9722 | 1099.8 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-29 | 233144.2515 | 61542.12 | 88516.1646 | 34351.25 | 9441.4809 | 2130.22 | 62629.5835 | 16795.65 | 8575.7121 | 3265 | 63981.3103 | 5000 | 2314.3068 | 1099.8 | 122.9722 | 1099.8 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-30 | 235458.5583 | 61542.12 | 88639.1368 | 34351.25 | 9584.5336 | 2130.22 | 63578.5166 | 16795.65 | 8705.6472 | 3265 | 64950.7241 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-08-31 | 237772.8652 | 61542.12 | 88762.109 | 34351.25 | 9727.5863 | 2130.22 | 64527.4497 | 16795.65 | 8835.5822 | 3265 | 65920.1379 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-01 | 240087.172 | 62286.07 | 88885.0812 | 35095.2 | 9870.6391 | 2130.22 | 65476.3828 | 16795.65 | 8965.5172 | 3265 | 66889.5517 | 5000 | 2314.3068 | 743.95 | 122.9722 | 743.95 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-02 | 242401.4788 | 66154.82 | 89008.0534 | 35839.15 | 10013.6918 | 2130.22 | 66425.3158 | 19920.45 | 9095.4523 | 3265 | 67858.9655 | 5000 | 2314.3068 | 3868.75 | 122.9722 | 743.95 | 143.0527 | 0 | 948.9331 | 3124.8 | 129.935 | 0 | 969.4138 | 0
2025-09-03 | 244715.7857 | 66898.77 | 89131.0256 | 36583.1 | 10156.7446 | 2130.22 | 67374.2489 | 19920.45 | 9225.3873 | 3265 | 68828.3793 | 5000 | 2314.3068 | 743.95 | 122.9722 | 743.95 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-04 | 247030.0925 | 68329.42 | 89253.9978 | 37327.05 | 10299.7973 | 2130.22 | 68323.182 | 19920.45 | 9355.3223 | 3951.7 | 69797.7931 | 5000 | 2314.3068 | 1430.65 | 122.9722 | 743.95 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 686.7 | 969.4138 | 0
2025-09-05 | 249344.3994 | 69073.37 | 89376.97 | 38071 | 10442.85 | 2130.22 | 69272.1151 | 19920.45 | 9485.2574 | 3951.7 | 70767.2069 | 5000 | 2314.3068 | 743.95 | 122.9722 | 743.95 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-06 | 251658.7062 | 69073.37 | 89499.9422 | 38071 | 10585.9028 | 2130.22 | 70221.0482 | 19920.45 | 9615.1924 | 3951.7 | 71736.6207 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-07 | 253973.013 | 69073.37 | 89622.9143 | 38071 | 10728.9555 | 2130.22 | 71169.9813 | 19920.45 | 9745.1274 | 3951.7 | 72706.0345 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-08 | 256287.3199 | 69576.12 | 89745.8865 | 38573.75 | 10872.0083 | 2130.22 | 72118.9143 | 19920.45 | 9875.0625 | 3951.7 | 73675.4483 | 5000 | 2314.3068 | 502.75 | 122.9722 | 502.75 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-09 | 258601.6267 | 70721.23 | 89868.8587 | 39076.5 | 11015.061 | 2130.22 | 73067.8474 | 20562.81 | 10004.9975 | 3951.7 | 74644.8621 | 5000 | 2314.3068 | 1145.11 | 122.9722 | 502.75 | 143.0527 | 0 | 948.9331 | 642.36 | 129.935 | 0 | 969.4138 | 0
2025-09-10 | 260915.9336 | 71223.98 | 89991.8309 | 39579.25 | 11158.1137 | 2130.22 | 74016.7805 | 20562.81 | 10134.9325 | 3951.7 | 75614.2759 | 5000 | 2314.3068 | 502.75 | 122.9722 | 502.75 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-11 | 263230.2404 | 71726.73 | 90114.8031 | 40082 | 11301.1665 | 2130.22 | 74965.7136 | 20562.81 | 10264.8676 | 3951.7 | 76583.6897 | 5000 | 2314.3068 | 502.75 | 122.9722 | 502.75 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-12 | 265544.5473 | 86455.42 | 90237.7753 | 40584.75 | 11444.2192 | 2241.16 | 75914.6467 | 20562.81 | 10394.8026 | 18066.7 | 77553.1034 | 5000 | 2314.3068 | 14728.69 | 122.9722 | 502.75 | 143.0527 | 110.94 | 948.9331 | 0 | 129.935 | 14115 | 969.4138 | 0
2025-09-13 | 267858.8541 | 86455.42 | 90360.7475 | 40584.75 | 11587.272 | 2241.16 | 76863.5798 | 20562.81 | 10524.7376 | 18066.7 | 78522.5172 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-14 | 270173.1609 | 86455.42 | 90483.7197 | 40584.75 | 11730.3247 | 2241.16 | 77812.5128 | 20562.81 | 10654.6727 | 18066.7 | 79491.931 | 5000 | 2314.3068 | 0 | 122.9722 | 0 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-15 | 272487.4678 | 88867.295 | 90606.6919 | 42546.625 | 11873.3774 | 2691.16 | 78761.4459 | 20562.81 | 10784.6077 | 18066.7 | 80461.3448 | 5000 | 2314.3068 | 2411.875 | 122.9722 | 1961.875 | 143.0527 | 450 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-16 | 274801.7746 | 90829.17 | 90729.6641 | 44508.5 | 12016.4302 | 2691.16 | 79710.379 | 20562.81 | 10914.5427 | 18066.7 | 81430.7586 | 5000 | 2314.3068 | 1961.875 | 122.9722 | 1961.875 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-17 | 277116.0815 | 92791.045 | 90852.6363 | 46470.375 | 12159.4829 | 2691.16 | 80659.3121 | 20562.81 | 11044.4778 | 18066.7 | 82400.1724 | 5000 | 2314.3068 | 1961.875 | 122.9722 | 1961.875 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-18 | 279430.3883 | 94752.92 | 90975.6085 | 48432.25 | 12302.5357 | 2691.16 | 81608.2452 | 20562.81 | 11174.4128 | 18066.7 | 83369.5862 | 5000 | 2314.3068 | 1961.875 | 122.9722 | 1961.875 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-19 | 281744.6951 | 96714.795 | 91098.5806 | 50394.125 | 12445.5884 | 2691.16 | 82557.1783 | 20562.81 | 11304.3478 | 18066.7 | 84339 | 5000 | 2314.3068 | 1961.875 | 122.9722 | 1961.875 | 143.0527 | 0 | 948.9331 | 0 | 129.935 | 0 | 969.4138 | 0
2025-09-20 | 281744.6951 | 96714.795 | 91098.5806 | 50394.125 | 12445.5884 | 2691.16 | 82557.1783 | 20562.81 | 11304.3478 | 18066.7 | 84339 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-21 | 281744.6951 | 96714.795 | 91098.5806 | 50394.125 | 12445.5884 | 2691.16 | 82557.1783 | 20562.81 | 11304.3478 | 18066.7 | 84339 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-22 | 287690.5655 | 100014.37 | 94401.4769 | 51446.2 | 13471.6043 | 2991.16 | 83914.972 | 20562.81 | 11322.2506 | 20014.2 | 84580.2617 | 5000 | 5945.8704 | 3299.575 | 3302.8963 | 1052.075 | 1026.0159 | 300 | 1357.7937 | 0 | 17.9028 | 1947.5 | 241.2617 | 0
2025-09-23 | 293636.436 | 102203.965 | 97704.3732 | 52498.275 | 14497.6202 | 2991.16 | 85272.7656 | 20562.81 | 11340.1535 | 21151.72 | 84821.5234 | 5000 | 5945.8704 | 2189.595 | 3302.8963 | 1052.075 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 1137.52 | 241.2617 | 0
2025-09-24 | 299582.3064 | 116032.98 | 101007.2694 | 53550.35 | 15523.6361 | 2991.16 | 86630.5593 | 23165.94 | 11358.0563 | 31325.53 | 85062.7852 | 5000 | 5945.8704 | 13829.015 | 3302.8963 | 1052.075 | 1026.0159 | 0 | 1357.7937 | 2603.13 | 17.9028 | 10173.81 | 241.2617 | 0
2025-09-25 | 305528.1768 | 117085.055 | 104310.1657 | 54602.425 | 16549.6521 | 2991.16 | 87988.353 | 23165.94 | 11375.9591 | 31325.53 | 85304.0469 | 5000 | 5945.8704 | 1052.075 | 3302.8963 | 1052.075 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-09-26 | 311474.0472 | 118137.13 | 107613.062 | 55654.5 | 17575.668 | 2991.16 | 89346.1467 | 23165.94 | 11393.8619 | 31325.53 | 85545.3086 | 5000 | 5945.8704 | 1052.075 | 3302.8963 | 1052.075 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-09-27 | 317419.9176 | 118137.13 | 110915.9583 | 55654.5 | 18601.6839 | 2991.16 | 90703.9404 | 23165.94 | 11411.7647 | 31325.53 | 85786.5703 | 5000 | 5945.8704 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-09-28 | 323365.788 | 118137.13 | 114218.8545 | 55654.5 | 19627.6998 | 2991.16 | 92061.7341 | 23165.94 | 11429.6675 | 31325.53 | 86027.8321 | 5000 | 5945.8704 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-09-29 | 329311.6584 | 120864.255 | 117521.7508 | 56981.625 | 20653.7157 | 4391.16 | 93419.5278 | 23165.94 | 11447.5703 | 31325.53 | 86269.0938 | 5000 | 5945.8704 | 2727.125 | 3302.8963 | 1327.125 | 1026.0159 | 1400 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-09-30 | 335257.5288 | 122191.38 | 120824.6471 | 58308.75 | 21679.7316 | 4391.16 | 94777.3215 | 23165.94 | 11465.4731 | 31325.53 | 86510.3555 | 5000 | 5945.8704 | 1327.125 | 3302.8963 | 1327.125 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-01 | 341203.3992 | 123518.505 | 124127.5433 | 59635.875 | 22705.7475 | 4391.16 | 96135.1152 | 23165.94 | 11483.376 | 31325.53 | 86751.6172 | 5000 | 5945.8704 | 1327.125 | 3302.8963 | 1327.125 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-02 | 347149.2696 | 124845.63 | 127430.4396 | 60963 | 23731.7635 | 4391.16 | 97492.9089 | 23165.94 | 11501.2788 | 31325.53 | 86992.8789 | 5000 | 5945.8704 | 1327.125 | 3302.8963 | 1327.125 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-03 | 353095.14 | 126672.755 | 130733.3359 | 62290.125 | 24757.7794 | 4891.16 | 98850.7026 | 23165.94 | 11519.1816 | 31325.53 | 87234.1407 | 5000 | 5945.8704 | 1827.125 | 3302.8963 | 1327.125 | 1026.0159 | 500 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-04 | 359041.0104 | 126672.755 | 134036.2321 | 62290.125 | 25783.7953 | 4891.16 | 100208.4962 | 23165.94 | 11537.0844 | 31325.53 | 87475.4024 | 5000 | 5945.8704 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-05 | 364986.8809 | 126672.755 | 137339.1284 | 62290.125 | 26809.8112 | 4891.16 | 101566.2899 | 23165.94 | 11554.9872 | 31325.53 | 87716.6641 | 5000 | 5945.8704 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-06 | 370932.7513 | 128329.505 | 140642.0247 | 63946.875 | 27835.8271 | 4891.16 | 102924.0836 | 23165.94 | 11572.89 | 31325.53 | 87957.9258 | 5000 | 5945.8704 | 1656.75 | 3302.8963 | 1656.75 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-07 | 376878.6217 | 129986.255 | 143944.9209 | 65603.625 | 28861.843 | 4891.16 | 104281.8773 | 23165.94 | 11590.7928 | 31325.53 | 88199.1876 | 5000 | 5945.8704 | 1656.75 | 3302.8963 | 1656.75 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-08 | 382824.4921 | 131643.005 | 147247.8172 | 67260.375 | 29887.8589 | 4891.16 | 105639.671 | 23165.94 | 11608.6957 | 31325.53 | 88440.4493 | 5000 | 5945.8704 | 1656.75 | 3302.8963 | 1656.75 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-09 | 388770.3625 | 133299.755 | 150550.7135 | 68917.125 | 30913.8749 | 4891.16 | 106997.4647 | 23165.94 | 11626.5985 | 31325.53 | 88681.711 | 5000 | 5945.8704 | 1656.75 | 3302.8963 | 1656.75 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-10 | 394716.2329 | 134956.505 | 153853.6097 | 70573.875 | 31939.8908 | 4891.16 | 108355.2584 | 23165.94 | 11644.5013 | 31325.53 | 88922.9727 | 5000 | 5945.8704 | 1656.75 | 3302.8963 | 1656.75 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-11 | 400662.1033 | 134956.505 | 157156.506 | 70573.875 | 32965.9067 | 4891.16 | 109713.0521 | 23165.94 | 11662.4041 | 31325.53 | 89164.2344 | 5000 | 5945.8704 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-12 | 406607.9737 | 134956.505 | 160459.4023 | 70573.875 | 33991.9226 | 4891.16 | 111070.8458 | 23165.94 | 11680.3069 | 31325.53 | 89405.4962 | 5000 | 5945.8704 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 1357.7937 | 0 | 17.9028 | 0 | 241.2617 | 0
2025-10-13 | 412553.8441 |  | 163762.2985 |  | 35017.9385 |  | 112428.6395 |  | 11698.2097 |  | 89646.7579 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-14 | 418499.7145 |  | 167065.1948 |  | 36043.9544 |  | 113786.4332 |  | 11716.1125 |  | 89888.0196 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-15 | 424445.5849 |  | 170368.0911 |  | 37069.9703 |  | 115144.2269 |  | 11734.0153 |  | 90129.2813 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-16 | 430391.4554 |  | 173670.9873 |  | 38095.9862 |  | 116502.0205 |  | 11751.9182 |  | 90370.5431 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-17 | 436337.3258 |  | 176973.8836 |  | 39122.0022 |  | 117859.8142 |  | 11769.821 |  | 90611.8048 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-18 | 442283.1962 |  | 180276.7799 |  | 40148.0181 |  | 119217.6079 |  | 11787.7238 |  | 90853.0665 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-19 | 448229.0666 |  | 183579.6762 |  | 41174.034 |  | 120575.4016 |  | 11805.6266 |  | 91094.3282 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-20 | 454174.937 |  | 186882.5724 |  | 42200.0499 |  | 121933.1953 |  | 11823.5294 |  | 91335.5899 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-21 | 460120.8074 |  | 190185.4687 |  | 43226.0658 |  | 123290.989 |  | 11841.4322 |  | 91576.8517 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-22 | 466066.6778 |  | 193488.365 |  | 44252.0817 |  | 124648.7827 |  | 11859.335 |  | 91818.1134 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-23 | 472012.5482 |  | 196791.2612 |  | 45278.0976 |  | 126006.5764 |  | 11877.2379 |  | 92059.3751 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-24 | 477958.4186 |  | 200094.1575 |  | 46304.1136 |  | 127364.3701 |  | 11895.1407 |  | 92300.6368 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-25 | 483904.289 |  | 203397.0538 |  | 47330.1295 |  | 128722.1638 |  | 11913.0435 |  | 92541.8986 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-26 | 489850.1594 |  | 206699.95 |  | 48356.1454 |  | 130079.9575 |  | 11930.9463 |  | 92783.1603 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-27 | 495796.0298 |  | 210002.8463 |  | 49382.1613 |  | 131437.7512 |  | 11948.8491 |  | 93024.422 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-28 | 501741.9003 |  | 213305.7426 |  | 50408.1772 |  | 132795.5448 |  | 11966.7519 |  | 93265.6837 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-29 | 507687.7707 |  | 216608.6388 |  | 51434.1931 |  | 134153.3385 |  | 11984.6547 |  | 93506.9454 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-30 | 513633.6411 |  | 219911.5351 |  | 52460.209 |  | 135511.1322 |  | 12002.5575 |  | 93748.2072 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-10-31 | 519579.5115 |  | 223214.4314 |  | 53486.225 |  | 136868.9259 |  | 12020.4604 |  | 93989.4689 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-01 | 525525.3819 |  | 226517.3276 |  | 54512.2409 |  | 138226.7196 |  | 12038.3632 |  | 94230.7306 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-02 | 531471.2523 |  | 229820.2239 |  | 55538.2568 |  | 139584.5133 |  | 12056.266 |  | 94471.9923 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-03 | 537417.1227 |  | 233123.1202 |  | 56564.2727 |  | 140942.307 |  | 12074.1688 |  | 94713.254 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-04 | 543362.9931 |  | 236426.0164 |  | 57590.2886 |  | 142300.1007 |  | 12092.0716 |  | 94954.5158 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-05 | 549308.8635 |  | 239728.9127 |  | 58616.3045 |  | 143657.8944 |  | 12109.9744 |  | 95195.7775 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-06 | 555254.7339 |  | 243031.809 |  | 59642.3204 |  | 145015.6881 |  | 12127.8772 |  | 95437.0392 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-07 | 561200.6043 |  | 246334.7052 |  | 60668.3363 |  | 146373.4818 |  | 12145.7801 |  | 95678.3009 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-08 | 567146.4747 |  | 249637.6015 |  | 61694.3523 |  | 147731.2754 |  | 12163.6829 |  | 95919.5627 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-09 | 573092.3452 |  | 252940.4978 |  | 62720.3682 |  | 149089.0691 |  | 12181.5857 |  | 96160.8244 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-10 | 579038.2156 |  | 256243.3941 |  | 63746.3841 |  | 150446.8628 |  | 12199.4885 |  | 96402.0861 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-11 | 584984.086 |  | 259546.2903 |  | 64772.4 |  | 151804.6565 |  | 12217.3913 |  | 96643.3478 |  | 5945.8704 |  | 3302.8963 |  | 1026.0159 |  | 1357.7937 |  | 17.9028 |  | 241.2617
2025-11-12 | 588322.6597 |  | 261095.5386 |  | 65374.5825 |  | 152491.7994 |  | 12217.3913 |  | 97143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-13 | 591661.2334 |  | 262644.787 |  | 65976.7651 |  | 153178.9422 |  | 12217.3913 |  | 97643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-14 | 594999.8071 |  | 264194.0353 |  | 66578.9476 |  | 153866.0851 |  | 12217.3913 |  | 98143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-15 | 598338.3808 |  | 265743.2836 |  | 67181.1302 |  | 154553.228 |  | 12217.3913 |  | 98643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-16 | 601676.9546 |  | 267292.5319 |  | 67783.3127 |  | 155240.3708 |  | 12217.3913 |  | 99143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-17 | 605015.5283 |  | 268841.7802 |  | 68385.4952 |  | 155927.5137 |  | 12217.3913 |  | 99643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-18 | 608354.102 |  | 270391.0286 |  | 68987.6778 |  | 156614.6565 |  | 12217.3913 |  | 100143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-19 | 611692.6757 |  | 271940.2769 |  | 69589.8603 |  | 157301.7994 |  | 12217.3913 |  | 100643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-20 | 615031.2494 |  | 273489.5252 |  | 70192.0429 |  | 157988.9422 |  | 12217.3913 |  | 101143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-21 | 618369.8231 |  | 275038.7735 |  | 70794.2254 |  | 158676.0851 |  | 12217.3913 |  | 101643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-22 | 621708.3968 |  | 276588.0218 |  | 71396.4079 |  | 159363.228 |  | 12217.3913 |  | 102143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-23 | 625046.9706 |  | 278137.2702 |  | 71998.5905 |  | 160050.3708 |  | 12217.3913 |  | 102643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-24 | 628385.5443 |  | 279686.5185 |  | 72600.773 |  | 160737.5137 |  | 12217.3913 |  | 103143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-25 | 631724.118 |  | 281235.7668 |  | 73202.9556 |  | 161424.6565 |  | 12217.3913 |  | 103643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-26 | 635062.6917 |  | 282785.0151 |  | 73805.1381 |  | 162111.7994 |  | 12217.3913 |  | 104143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-27 | 638401.2654 |  | 284334.2634 |  | 74407.3206 |  | 162798.9422 |  | 12217.3913 |  | 104643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-28 | 641739.8391 |  | 285883.5117 |  | 75009.5032 |  | 163486.0851 |  | 12217.3913 |  | 105143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-29 | 645078.4129 |  | 287432.7601 |  | 75611.6857 |  | 164173.228 |  | 12217.3913 |  | 105643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-30 | 648416.9866 |  | 288982.0084 |  | 76213.8683 |  | 164860.3708 |  | 12217.3913 |  | 106143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-01 | 651755.5603 |  | 290531.2567 |  | 76816.0508 |  | 165547.5137 |  | 12217.3913 |  | 106643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-02 | 655094.134 |  | 292080.505 |  | 77418.2333 |  | 166234.6565 |  | 12217.3913 |  | 107143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-03 | 658432.7077 |  | 293629.7533 |  | 78020.4159 |  | 166921.7994 |  | 12217.3913 |  | 107643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-04 | 661771.2814 |  | 295179.0017 |  | 78622.5984 |  | 167608.9422 |  | 12217.3913 |  | 108143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-05 | 665109.8552 |  | 296728.25 |  | 79224.781 |  | 168296.0851 |  | 12217.3913 |  | 108643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-06 | 668448.4289 |  | 298277.4983 |  | 79826.9635 |  | 168983.228 |  | 12217.3913 |  | 109143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-07 | 671787.0026 |  | 299826.7466 |  | 80429.146 |  | 169670.3708 |  | 12217.3913 |  | 109643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-08 | 675125.5763 |  | 301375.9949 |  | 81031.3286 |  | 170357.5137 |  | 12217.3913 |  | 110143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-09 | 678464.15 |  | 302925.2433 |  | 81633.5111 |  | 171044.6565 |  | 12217.3913 |  | 110643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-10 | 681802.7237 |  | 304474.4916 |  | 82235.6937 |  | 171731.7994 |  | 12217.3913 |  | 111143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-11 | 685141.2975 |  | 306023.7399 |  | 82837.8762 |  | 172418.9422 |  | 12217.3913 |  | 111643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-12 | 688479.8712 |  | 307572.9882 |  | 83440.0587 |  | 173106.0851 |  | 12217.3913 |  | 112143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-13 | 691818.4449 |  | 309122.2365 |  | 84042.2413 |  | 173793.228 |  | 12217.3913 |  | 112643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-14 | 695157.0186 |  | 310671.4849 |  | 84644.4238 |  | 174480.3708 |  | 12217.3913 |  | 113143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-15 | 698495.5923 |  | 312220.7332 |  | 85246.6063 |  | 175167.5137 |  | 12217.3913 |  | 113643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-16 | 701834.166 |  | 313769.9815 |  | 85848.7889 |  | 175854.6565 |  | 12217.3913 |  | 114143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-17 | 705172.7397 |  | 315319.2298 |  | 86450.9714 |  | 176541.7994 |  | 12217.3913 |  | 114643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-18 | 708511.3135 |  | 316868.4781 |  | 87053.154 |  | 177228.9422 |  | 12217.3913 |  | 115143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-19 | 711849.8872 |  | 318417.7264 |  | 87655.3365 |  | 177916.0851 |  | 12217.3913 |  | 115643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-20 | 715188.4609 |  | 319966.9748 |  | 88257.519 |  | 178603.228 |  | 12217.3913 |  | 116143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-21 | 718527.0346 |  | 321516.2231 |  | 88859.7016 |  | 179290.3708 |  | 12217.3913 |  | 116643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-22 | 721865.6083 |  | 323065.4714 |  | 89461.8841 |  | 179977.5137 |  | 12217.3913 |  | 117143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-23 | 725204.182 |  | 324614.7197 |  | 90064.0667 |  | 180664.6565 |  | 12217.3913 |  | 117643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-24 | 728542.7558 |  | 326163.968 |  | 90666.2492 |  | 181351.7994 |  | 12217.3913 |  | 118143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-25 | 731881.3295 |  | 327713.2164 |  | 91268.4317 |  | 182038.9422 |  | 12217.3913 |  | 118643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-26 | 735219.9032 |  | 329262.4647 |  | 91870.6143 |  | 182726.0851 |  | 12217.3913 |  | 119143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-27 | 738558.4769 |  | 330811.713 |  | 92472.7968 |  | 183413.228 |  | 12217.3913 |  | 119643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-28 | 741897.0506 |  | 332360.9613 |  | 93074.9794 |  | 184100.3708 |  | 12217.3913 |  | 120143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-29 | 745235.6243 |  | 333910.2096 |  | 93677.1619 |  | 184787.5137 |  | 12217.3913 |  | 120643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-30 | 748574.1981 |  | 335459.458 |  | 94279.3444 |  | 185474.6565 |  | 12217.3913 |  | 121143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-31 | 751912.7718 |  | 337008.7063 |  | 94881.527 |  | 186161.7994 |  | 12217.3913 |  | 121643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-01 | 755251.3455 |  | 338557.9546 |  | 95483.7095 |  | 186848.9422 |  | 12217.3913 |  | 122143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-02 | 758589.9192 |  | 340107.2029 |  | 96085.8921 |  | 187536.0851 |  | 12217.3913 |  | 122643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-03 | 761928.4929 |  | 341656.4512 |  | 96688.0746 |  | 188223.228 |  | 12217.3913 |  | 123143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-04 | 765267.0666 |  | 343205.6996 |  | 97290.2571 |  | 188910.3708 |  | 12217.3913 |  | 123643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-05 | 768605.6404 |  | 344754.9479 |  | 97892.4397 |  | 189597.5137 |  | 12217.3913 |  | 124143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-06 | 771944.2141 |  | 346304.1962 |  | 98494.6222 |  | 190284.6565 |  | 12217.3913 |  | 124643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-07 | 775282.7878 |  | 347853.4445 |  | 99096.8048 |  | 190971.7994 |  | 12217.3913 |  | 125143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-08 | 778621.3615 |  | 349402.6928 |  | 99698.9873 |  | 191658.9422 |  | 12217.3913 |  | 125643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-09 | 781959.9352 |  | 350951.9411 |  | 100301.1698 |  | 192346.0851 |  | 12217.3913 |  | 126143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-10 | 785298.5089 |  | 352501.1895 |  | 100903.3524 |  | 193033.228 |  | 12217.3913 |  | 126643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-11 | 788637.0826 |  | 354050.4378 |  | 101505.5349 |  | 193720.3708 |  | 12217.3913 |  | 127143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-12 | 791975.6564 |  | 355599.6861 |  | 102107.7175 |  | 194407.5137 |  | 12217.3913 |  | 127643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-13 | 795314.2301 |  | 357148.9344 |  | 102709.9 |  | 195094.6565 |  | 12217.3913 |  | 128143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-14 | 798652.8038 |  | 358698.1827 |  | 103312.0825 |  | 195781.7994 |  | 12217.3913 |  | 128643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-15 | 801991.3775 |  | 360247.4311 |  | 103914.2651 |  | 196468.9422 |  | 12217.3913 |  | 129143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-16 | 805329.9512 |  | 361796.6794 |  | 104516.4476 |  | 197156.0851 |  | 12217.3913 |  | 129643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-17 | 808668.5249 |  | 363345.9277 |  | 105118.6302 |  | 197843.228 |  | 12217.3913 |  | 130143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-18 | 812007.0987 |  | 364895.176 |  | 105720.8127 |  | 198530.3708 |  | 12217.3913 |  | 130643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-19 | 815345.6724 |  | 366444.4243 |  | 106322.9952 |  | 199217.5137 |  | 12217.3913 |  | 131143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-20 | 818684.2461 |  | 367993.6727 |  | 106925.1778 |  | 199904.6565 |  | 12217.3913 |  | 131643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-21 | 822022.8198 |  | 369542.921 |  | 107527.3603 |  | 200591.7994 |  | 12217.3913 |  | 132143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-22 | 825361.3935 |  | 371092.1693 |  | 108129.5429 |  | 201278.9422 |  | 12217.3913 |  | 132643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-23 | 828699.9672 |  | 372641.4176 |  | 108731.7254 |  | 201966.0851 |  | 12217.3913 |  | 133143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-24 | 832038.541 |  | 374190.6659 |  | 109333.9079 |  | 202653.228 |  | 12217.3913 |  | 133643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-25 | 835377.1147 |  | 375739.9143 |  | 109936.0905 |  | 203340.3708 |  | 12217.3913 |  | 134143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-26 | 838715.6884 |  | 377289.1626 |  | 110538.273 |  | 204027.5137 |  | 12217.3913 |  | 134643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-27 | 842054.2621 |  | 378838.4109 |  | 111140.4556 |  | 204714.6565 |  | 12217.3913 |  | 135143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-28 | 845392.8358 |  | 380387.6592 |  | 111742.6381 |  | 205401.7994 |  | 12217.3913 |  | 135643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-29 | 848731.4095 |  | 381936.9075 |  | 112344.8206 |  | 206088.9422 |  | 12217.3913 |  | 136143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-30 | 852069.9832 |  | 383486.1559 |  | 112947.0032 |  | 206776.0851 |  | 12217.3913 |  | 136643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-31 | 855408.557 |  | 385035.4042 |  | 113549.1857 |  | 207463.228 |  | 12217.3913 |  | 137143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-01 | 858747.1307 |  | 386584.6525 |  | 114151.3683 |  | 208150.3708 |  | 12217.3913 |  | 137643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-02 | 862085.7044 |  | 388133.9008 |  | 114753.5508 |  | 208837.5137 |  | 12217.3913 |  | 138143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-03 | 865424.2781 |  | 389683.1491 |  | 115355.7333 |  | 209524.6565 |  | 12217.3913 |  | 138643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-04 | 867073.6619 |  | 390971.2259 |  | 115675.3825 |  | 209566.3144 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-05 | 868723.0458 |  | 392259.3028 |  | 115995.0316 |  | 209607.9723 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-06 | 870372.4296 |  | 393547.3796 |  | 116314.6807 |  | 209649.6302 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-07 | 872021.8135 |  | 394835.4564 |  | 116634.3298 |  | 209691.2881 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-08 | 873671.1973 |  | 396123.5332 |  | 116953.9789 |  | 209732.946 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-09 | 875320.5811 |  | 397411.61 |  | 117273.6281 |  | 209774.6039 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-10 | 876969.965 |  | 398699.6869 |  | 117593.2772 |  | 209816.2618 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-11 | 878619.3488 |  | 399987.7637 |  | 117912.9263 |  | 209857.9197 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-12 | 880268.7326 |  | 401275.8405 |  | 118232.5754 |  | 209899.5776 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-13 | 881918.1165 |  | 402563.9173 |  | 118552.2246 |  | 209941.2355 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-14 | 883567.5003 |  | 403851.9941 |  | 118871.8737 |  | 209982.8934 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-15 | 885216.8841 |  | 405140.0709 |  | 119191.5228 |  | 210024.5513 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-16 | 886866.268 |  | 406428.1478 |  | 119511.1719 |  | 210066.2092 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-17 | 888515.6518 |  | 407716.2246 |  | 119830.8211 |  | 210107.867 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-18 | 890165.0356 |  | 409004.3014 |  | 120150.4702 |  | 210149.5249 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-19 | 891814.4195 |  | 410292.3782 |  | 120470.1193 |  | 210191.1828 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-20 | 893463.8033 |  | 411580.455 |  | 120789.7684 |  | 210232.8407 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-21 | 895113.1872 |  | 412868.5319 |  | 121109.4175 |  | 210274.4986 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-22 | 896762.571 |  | 414156.6087 |  | 121429.0667 |  | 210316.1565 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-23 | 898411.9548 |  | 415444.6855 |  | 121748.7158 |  | 210357.8144 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-24 | 900061.3387 |  | 416732.7623 |  | 122068.3649 |  | 210399.4723 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-25 | 901710.7225 |  | 418020.8391 |  | 122388.014 |  | 210441.1302 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-26 | 903360.1063 |  | 419308.9159 |  | 122707.6632 |  | 210482.7881 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-27 | 905009.4902 |  | 420596.9928 |  | 123027.3123 |  | 210524.446 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-28 | 906658.874 |  | 421885.0696 |  | 123346.9614 |  | 210566.1039 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-01 | 908308.2578 |  | 423173.1464 |  | 123666.6105 |  | 210607.7618 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-02 | 909957.6417 |  | 424461.2232 |  | 123986.2596 |  | 210649.4197 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-03 | 911607.0255 |  | 425749.3 |  | 124305.9088 |  | 210691.0776 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-04 | 913256.4093 |  | 427037.3769 |  | 124625.5579 |  | 210732.7355 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-05 | 914905.7932 |  | 428325.4537 |  | 124945.207 |  | 210774.3934 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-06 | 916555.177 |  | 429613.5305 |  | 125264.8561 |  | 210816.0513 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-07 | 918204.5609 |  | 430901.6073 |  | 125584.5053 |  | 210857.7092 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-08 | 919853.9447 |  | 432189.6841 |  | 125904.1544 |  | 210899.367 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-09 | 921503.3285 |  | 433477.7609 |  | 126223.8035 |  | 210941.0249 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-10 | 923152.7124 |  | 434765.8378 |  | 126543.4526 |  | 210982.6828 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-11 | 924802.0962 |  | 436053.9146 |  | 126863.1018 |  | 211024.3407 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-12 | 926451.48 |  | 437341.9914 |  | 127182.7509 |  | 211065.9986 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-13 | 928100.8639 |  | 438630.0682 |  | 127502.4 |  | 211107.6565 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-14 | 929750.2477 |  | 439918.145 |  | 127822.0491 |  | 211149.3144 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-15 | 931399.6315 |  | 441206.2219 |  | 128141.6982 |  | 211190.9723 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-16 | 933049.0154 |  | 442494.2987 |  | 128461.3474 |  | 211232.6302 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-17 | 934698.3992 |  | 443782.3755 |  | 128780.9965 |  | 211274.2881 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-18 | 936347.783 |  | 445070.4523 |  | 129100.6456 |  | 211315.946 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-19 | 937997.1669 |  | 446358.5291 |  | 129420.2947 |  | 211357.6039 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-20 | 939646.5507 |  | 447646.6059 |  | 129739.9439 |  | 211399.2618 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-21 | 941295.9346 |  | 448934.6828 |  | 130059.593 |  | 211440.9197 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-22 | 942945.3184 |  | 450222.7596 |  | 130379.2421 |  | 211482.5776 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-23 | 944594.7022 |  | 451510.8364 |  | 130698.8912 |  | 211524.2355 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-24 | 946244.0861 |  | 452798.9132 |  | 131018.5404 |  | 211565.8934 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-25 | 947893.4699 |  | 454086.99 |  | 131338.1895 |  | 211607.5513 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-26 | 949542.8537 |  | 455375.0669 |  | 131657.8386 |  | 211649.2092 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-27 | 951192.2376 |  | 456663.1437 |  | 131977.4877 |  | 211690.867 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-28 | 952841.6214 |  | 457951.2205 |  | 132297.1368 |  | 211732.5249 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-29 | 954491.0052 |  | 459239.2973 |  | 132616.786 |  | 211774.1828 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-30 | 956140.3891 |  | 460527.3741 |  | 132936.4351 |  | 211815.8407 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-31 | 957789.7729 |  | 461815.4509 |  | 133256.0842 |  | 211857.4986 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-01 | 959439.1567 |  | 463103.5278 |  | 133575.7333 |  | 211899.1565 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-02 | 961088.5406 |  | 464391.6046 |  | 133895.3825 |  | 211940.8144 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-03 | 962737.9244 |  | 465679.6814 |  | 134215.0316 |  | 211982.4723 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-04 | 964387.3083 |  | 466967.7582 |  | 134534.6807 |  | 212024.1302 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-05 | 966036.6921 |  | 468255.835 |  | 134854.3298 |  | 212065.7881 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-06 | 967686.0759 |  | 469543.9119 |  | 135173.9789 |  | 212107.446 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-07 | 969335.4598 |  | 470831.9887 |  | 135493.6281 |  | 212149.1039 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-08 | 970984.8436 |  | 472120.0655 |  | 135813.2772 |  | 212190.7618 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-09 | 972634.2274 |  | 473408.1423 |  | 136132.9263 |  | 212232.4197 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-10 | 974283.6113 |  | 474696.2191 |  | 136452.5754 |  | 212274.0776 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-11 | 975932.9951 |  | 475984.2959 |  | 136772.2246 |  | 212315.7355 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-12 | 977582.3789 |  | 477272.3728 |  | 137091.8737 |  | 212357.3934 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-13 | 979231.7628 |  | 478560.4496 |  | 137411.5228 |  | 212399.0513 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-14 | 980881.1466 |  | 479848.5264 |  | 137731.1719 |  | 212440.7092 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-15 | 982530.5304 |  | 481136.6032 |  | 138050.8211 |  | 212482.367 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-16 | 984179.9143 |  | 482424.68 |  | 138370.4702 |  | 212524.0249 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-17 | 985829.2981 |  | 483712.7569 |  | 138690.1193 |  | 212565.6828 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-18 | 987478.682 |  | 485000.8337 |  | 139009.7684 |  | 212607.3407 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-19 | 989128.0658 |  | 486288.9105 |  | 139329.4175 |  | 212648.9986 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-20 | 990777.4496 |  | 487576.9873 |  | 139649.0667 |  | 212690.6565 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-21 | 992426.8335 |  | 488865.0641 |  | 139968.7158 |  | 212732.3144 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-22 | 994076.2173 |  | 490153.1409 |  | 140288.3649 |  | 212773.9723 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-23 | 995725.6011 |  | 491441.2178 |  | 140608.014 |  | 212815.6302 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-24 | 997374.985 |  | 492729.2946 |  | 140927.6632 |  | 212857.2881 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-25 | 999024.3688 |  | 494017.3714 |  | 141247.3123 |  | 212898.946 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-26 | 1000673.7526 |  | 495305.4482 |  | 141566.9614 |  | 212940.6039 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-27 | 1002323.1365 |  | 496593.525 |  | 141886.6105 |  | 212982.2618 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-28 | 1003972.5203 |  | 497881.6019 |  | 142206.2596 |  | 213023.9197 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-29 | 1005621.9041 |  | 499169.6787 |  | 142525.9088 |  | 213065.5776 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-30 | 1007271.288 |  | 500457.7555 |  | 142845.5579 |  | 213107.2355 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-01 | 1008920.6718 |  | 501745.8323 |  | 143165.207 |  | 213148.8934 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-02 | 1010570.0557 |  | 503033.9091 |  | 143484.8561 |  | 213190.5513 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-03 | 1012219.4395 |  | 504321.9859 |  | 143804.5053 |  | 213232.2092 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-04 | 1013868.8233 |  | 505610.0628 |  | 144124.1544 |  | 213273.867 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-05 | 1015518.2072 |  | 506898.1396 |  | 144443.8035 |  | 213315.5249 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-06 | 1017167.591 |  | 508186.2164 |  | 144763.4526 |  | 213357.1828 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-07 | 1018816.9748 |  | 509474.2932 |  | 145083.1018 |  | 213398.8407 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-08 | 1020466.3587 |  | 510762.37 |  | 145402.7509 |  | 213440.4986 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-09 | 1022115.7425 |  | 512050.4469 |  | 145722.4 |  | 213482.1565 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-10 | 1023765.1263 |  | 513338.5237 |  | 146042.0491 |  | 213523.8144 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-11 | 1025414.5102 |  | 514626.6005 |  | 146361.6982 |  | 213565.4723 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-12 | 1027063.894 |  | 515914.6773 |  | 146681.3474 |  | 213607.1302 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-13 | 1028713.2778 |  | 517202.7541 |  | 147000.9965 |  | 213648.7881 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-14 | 1030362.6617 |  | 518490.8309 |  | 147320.6456 |  | 213690.446 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-15 | 1032012.0455 |  | 519778.9078 |  | 147640.2947 |  | 213732.1039 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-16 | 1033661.4294 |  | 521066.9846 |  | 147959.9439 |  | 213773.7618 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-17 | 1035310.8132 |  | 522355.0614 |  | 148279.593 |  | 213815.4197 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-18 | 1036960.197 |  | 523643.1382 |  | 148599.2421 |  | 213857.0776 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-19 | 1038609.5809 |  | 524931.215 |  | 148918.8912 |  | 213898.7355 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-20 | 1040258.9647 |  | 526219.2919 |  | 149238.5404 |  | 213940.3934 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-21 | 1041908.3485 |  | 527507.3687 |  | 149558.1895 |  | 213982.0513 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-22 | 1043557.7324 |  | 528795.4455 |  | 149877.8386 |  | 214023.7092 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-23 | 1045207.1162 |  | 530083.5223 |  | 150197.4877 |  | 214065.367 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-24 | 1046856.5 |  | 531371.5991 |  | 150517.1368 |  | 214107.0249 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-25 | 1048505.8839 |  | 532659.6759 |  | 150836.786 |  | 214148.6828 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-26 | 1050155.2677 |  | 533947.7528 |  | 151156.4351 |  | 214190.3407 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-27 | 1051804.6515 |  | 535235.8296 |  | 151476.0842 |  | 214231.9986 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-28 | 1053454.0354 |  | 536523.9064 |  | 151795.7333 |  | 214273.6565 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-29 | 1055103.4192 |  | 537811.9832 |  | 152115.3825 |  | 214315.3144 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-30 | 1056752.8031 |  | 539100.06 |  | 152435.0316 |  | 214356.9723 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-31 | 1058402.1869 |  | 540388.1369 |  | 152754.6807 |  | 214398.6302 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-01 | 1060051.5707 |  | 541676.2137 |  | 153074.3298 |  | 214440.2881 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-02 | 1061700.9546 |  | 542964.2905 |  | 153393.9789 |  | 214481.946 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-03 | 1063350.3384 |  | 544252.3673 |  | 153713.6281 |  | 214523.6039 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-04 | 1064999.7222 |  | 545540.4441 |  | 154033.2772 |  | 214565.2618 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-05 | 1066649.1061 |  | 546828.5209 |  | 154352.9263 |  | 214606.9197 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-06 | 1068298.4899 |  | 548116.5978 |  | 154672.5754 |  | 214648.5776 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-07 | 1069947.8737 |  | 549404.6746 |  | 154992.2246 |  | 214690.2355 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-08 | 1071597.2576 |  | 550692.7514 |  | 155311.8737 |  | 214731.8934 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-09 | 1073246.6414 |  | 551980.8282 |  | 155631.5228 |  | 214773.5513 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-10 | 1074896.0252 |  | 553268.905 |  | 155951.1719 |  | 214815.2092 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-11 | 1076545.4091 |  | 554556.9819 |  | 156270.8211 |  | 214856.867 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-12 | 1078194.7929 |  | 555845.0587 |  | 156590.4702 |  | 214898.5249 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-13 | 1079844.1768 |  | 557133.1355 |  | 156910.1193 |  | 214940.1828 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-14 | 1081493.5606 |  | 558421.2123 |  | 157229.7684 |  | 214981.8407 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-15 | 1083142.9444 |  | 559709.2891 |  | 157549.4175 |  | 215023.4986 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-16 | 1084792.3283 |  | 560997.3659 |  | 157869.0667 |  | 215065.1565 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-17 | 1086441.7121 |  | 562285.4428 |  | 158188.7158 |  | 215106.8144 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-18 | 1088091.0959 |  | 563573.5196 |  | 158508.3649 |  | 215148.4723 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-19 | 1089740.4798 |  | 564861.5964 |  | 158828.014 |  | 215190.1302 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-20 | 1091389.8636 |  | 566149.6732 |  | 159147.6632 |  | 215231.7881 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-21 | 1093039.2474 |  | 567437.75 |  | 159467.3123 |  | 215273.446 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-22 | 1094688.6313 |  | 568725.8269 |  | 159786.9614 |  | 215315.1039 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-23 | 1096338.0151 |  | 570013.9037 |  | 160106.6105 |  | 215356.7618 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-24 | 1097987.3989 |  | 571301.9805 |  | 160426.2596 |  | 215398.4197 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-25 | 1099636.7828 |  | 572590.0573 |  | 160745.9088 |  | 215440.0776 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-26 | 1101286.1666 |  | 573878.1341 |  | 161065.5579 |  | 215481.7355 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-27 | 1102935.5505 |  | 575166.2109 |  | 161385.207 |  | 215523.3934 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-28 | 1104584.9343 |  | 576454.2878 |  | 161704.8561 |  | 215565.0513 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-29 | 1106234.3181 |  | 577742.3646 |  | 162024.5053 |  | 215606.7092 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-30 | 1107883.702 |  | 579030.4414 |  | 162344.1544 |  | 215648.367 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-01 | 1109533.0858 |  | 580318.5182 |  | 162663.8035 |  | 215690.0249 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-02 | 1111182.4696 |  | 581606.595 |  | 162983.4526 |  | 215731.6828 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-03 | 1112831.8535 |  | 582894.6719 |  | 163303.1018 |  | 215773.3407 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-04 | 1114481.2373 |  | 584182.7487 |  | 163622.7509 |  | 215814.9986 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-05 | 1116130.6211 |  | 585470.8255 |  | 163942.4 |  | 215856.6565 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-06 | 1117780.005 |  | 586758.9023 |  | 164262.0491 |  | 215898.3144 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-07 | 1119429.3888 |  | 588046.9791 |  | 164581.6982 |  | 215939.9723 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-08 | 1121078.7726 |  | 589335.0559 |  | 164901.3474 |  | 215981.6302 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-09 | 1122728.1565 |  | 590623.1328 |  | 165220.9965 |  | 216023.2881 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-10 | 1124377.5403 |  | 591911.2096 |  | 165540.6456 |  | 216064.946 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-11 | 1126026.9242 |  | 593199.2864 |  | 165860.2947 |  | 216106.6039 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-12 | 1127676.308 |  | 594487.3632 |  | 166179.9439 |  | 216148.2618 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-13 | 1129325.6918 |  | 595775.44 |  | 166499.593 |  | 216189.9197 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-14 | 1130975.0757 |  | 597063.5169 |  | 166819.2421 |  | 216231.5776 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-15 | 1132624.4595 |  | 598351.5937 |  | 167138.8912 |  | 216273.2355 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-16 | 1134273.8433 |  | 599639.6705 |  | 167458.5404 |  | 216314.8934 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-17 | 1135923.2272 |  | 600927.7473 |  | 167778.1895 |  | 216356.5513 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-18 | 1137572.611 |  | 602215.8241 |  | 168097.8386 |  | 216398.2092 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-19 | 1139221.9948 |  | 603503.9009 |  | 168417.4877 |  | 216439.867 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-20 | 1140871.3787 |  | 604791.9778 |  | 168737.1368 |  | 216481.5249 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-21 | 1142520.7625 |  | 606080.0546 |  | 169056.786 |  | 216523.1828 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-22 | 1144170.1463 |  | 607368.1314 |  | 169376.4351 |  | 216564.8407 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-23 | 1145819.5302 |  | 608656.2082 |  | 169696.0842 |  | 216606.4986 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-24 | 1147468.914 |  | 609944.285 |  | 170015.7333 |  | 216648.1565 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-25 | 1149118.2979 |  | 611232.3619 |  | 170335.3825 |  | 216689.8144 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-26 | 1150767.6817 |  | 612520.4387 |  | 170655.0316 |  | 216731.4723 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-27 | 1152417.0655 |  | 613808.5155 |  | 170974.6807 |  | 216773.1302 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-28 | 1154066.4494 |  | 615096.5923 |  | 171294.3298 |  | 216814.7881 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-29 | 1155715.8332 |  | 616384.6691 |  | 171613.9789 |  | 216856.446 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-30 | 1157365.217 |  | 617672.7459 |  | 171933.6281 |  | 216898.1039 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-31 | 1159014.6009 |  | 618960.8228 |  | 172253.2772 |  | 216939.7618 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-01 | 1160663.9847 |  | 620248.8996 |  | 172572.9263 |  | 216981.4197 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-02 | 1162313.3685 |  | 621536.9764 |  | 172892.5754 |  | 217023.0776 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-03 | 1163962.7524 |  | 622825.0532 |  | 173212.2246 |  | 217064.7355 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-04 | 1165612.1362 |  | 624113.13 |  | 173531.8737 |  | 217106.3934 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-05 | 1167261.52 |  | 625401.2069 |  | 173851.5228 |  | 217148.0513 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-06 | 1168910.9039 |  | 626689.2837 |  | 174171.1719 |  | 217189.7092 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-07 | 1170560.2877 |  | 627977.3605 |  | 174490.8211 |  | 217231.367 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-08 | 1172209.6716 |  | 629265.4373 |  | 174810.4702 |  | 217273.0249 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-09 | 1173859.0554 |  | 630553.5141 |  | 175130.1193 |  | 217314.6828 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-10 | 1175508.4392 |  | 631841.5909 |  | 175449.7684 |  | 217356.3407 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-11 | 1177157.8231 |  | 633129.6678 |  | 175769.4175 |  | 217397.9986 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-12 | 1178807.2069 |  | 634417.7446 |  | 176089.0667 |  | 217439.6565 |  | 12217.3913 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-13 | 1180717.8106 |  | 635598.4464 |  | 176524.851 |  | 217733.7742 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-14 | 1182628.4144 |  | 636779.1481 |  | 176960.6353 |  | 218027.8918 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-15 | 1184539.0181 |  | 637959.8499 |  | 177396.4196 |  | 218322.0095 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-16 | 1186449.6218 |  | 639140.5517 |  | 177832.2039 |  | 218616.1271 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-17 | 1188360.2256 |  | 640321.2535 |  | 178267.9882 |  | 218910.2448 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-18 | 1190270.8293 |  | 641501.9552 |  | 178703.7725 |  | 219204.3624 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-19 | 1192181.4331 |  | 642682.657 |  | 179139.5569 |  | 219498.4801 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-20 | 1194092.0368 |  | 643863.3588 |  | 179575.3412 |  | 219792.5977 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-21 | 1196002.6405 |  | 645044.0606 |  | 180011.1255 |  | 220086.7153 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-22 | 1197913.2443 |  | 646224.7623 |  | 180446.9098 |  | 220380.833 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-23 | 1199823.848 |  | 647405.4641 |  | 180882.6941 |  | 220674.9506 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-24 | 1201734.4517 |  | 648586.1659 |  | 181318.4784 |  | 220969.0683 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-25 | 1203645.0555 |  | 649766.8677 |  | 181754.2627 |  | 221263.1859 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-26 | 1205555.6592 |  | 650947.5694 |  | 182190.0471 |  | 221557.3036 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-27 | 1207466.263 |  | 652128.2712 |  | 182625.8314 |  | 221851.4212 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-28 | 1209376.8667 |  | 653308.973 |  | 183061.6157 |  | 222145.5389 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-29 | 1211287.4704 |  | 654489.6748 |  | 183497.4 |  | 222439.6565 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-30 | 1213198.0742 |  | 655670.3766 |  | 183933.1843 |  | 222733.7742 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-08-31 | 1215108.6779 |  | 656851.0783 |  | 184368.9686 |  | 223027.8918 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-01 | 1217019.2816 |  | 658031.7801 |  | 184804.7529 |  | 223322.0095 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-02 | 1218929.8854 |  | 659212.4819 |  | 185240.5373 |  | 223616.1271 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-03 | 1220840.4891 |  | 660393.1837 |  | 185676.3216 |  | 223910.2448 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-04 | 1222751.0928 |  | 661573.8854 |  | 186112.1059 |  | 224204.3624 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-05 | 1224661.6966 |  | 662754.5872 |  | 186547.8902 |  | 224498.4801 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-06 | 1226572.3003 |  | 663935.289 |  | 186983.6745 |  | 224792.5977 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-07 | 1228482.9041 |  | 665115.9908 |  | 187419.4588 |  | 225086.7153 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-08 | 1230393.5078 |  | 666296.6925 |  | 187855.2431 |  | 225380.833 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-09 | 1232304.1115 |  | 667477.3943 |  | 188291.0275 |  | 225674.9506 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-10 | 1234214.7153 |  | 668658.0961 |  | 188726.8118 |  | 225969.0683 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-11 | 1236125.319 |  | 669838.7979 |  | 189162.5961 |  | 226263.1859 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-12 | 1238035.9227 |  | 671019.4996 |  | 189598.3804 |  | 226557.3036 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-13 | 1239946.5265 |  | 672200.2014 |  | 190034.1647 |  | 226851.4212 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-14 | 1241857.1302 |  | 673380.9032 |  | 190469.949 |  | 227145.5389 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0
2026-09-15 | 1243767.734 |  | 674561.605 |  | 190905.7333 |  | 227439.6565 |  | 12217.3913 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 294.1176 |  | 0 |  | 0

## Labor Cost
Date | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned 5101 · Salary and wages (Direct) (Cumulative) | Actual 5101 · Salary and wages (Direct) (Cumulative) | Planned 5102 · Payroll taxes (Direct) (Cumulative) | Actual 5102 · Payroll taxes (Direct) (Cumulative)
2025-04-02 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0
2025-04-03 | 1914.2857 | 0 | 1914.2857 | 0 | 0 | 0
2025-04-04 | 2871.4286 | 0 | 2871.4286 | 0 | 0 | 0
2025-04-05 | 3828.5714 | 0 | 3828.5714 | 0 | 0 | 0
2025-04-06 | 4785.7143 | 0 | 4785.7143 | 0 | 0 | 0
2025-04-07 | 5742.8571 | 1126.6 | 5742.8571 | 1126.6 | 0 | 1126.6
2025-04-08 | 6700 | 2253.2 | 6700 | 2253.2 | 0 | 2253.2
2025-04-09 | 7657.1429 | 3379.8 | 7657.1429 | 3379.8 | 0 | 3379.8
2025-04-10 | 8614.2857 | 4506.4 | 8614.2857 | 4506.4 | 0 | 4506.4
2025-04-11 | 9571.4286 | 5633 | 9571.4286 | 5633 | 0 | 5633
2025-04-12 | 10528.5714 | 5633 | 10528.5714 | 5633 | 0 | 5633
2025-04-13 | 11485.7143 | 5633 | 11485.7143 | 5633 | 0 | 5633
2025-04-14 | 12442.8571 | 5847.4 | 12442.8571 | 5847.4 | 0 | 5847.4
2025-04-15 | 13400 | 6061.8 | 13400 | 6061.8 | 0 | 6061.8
2025-04-16 | 14357.1429 | 6276.2 | 14357.1429 | 6276.2 | 0 | 6276.2
2025-04-17 | 15314.2857 | 6490.6 | 15314.2857 | 6490.6 | 0 | 6490.6
2025-04-18 | 16271.4286 | 6705 | 16271.4286 | 6705 | 0 | 6705
2025-04-19 | 17228.5714 | 6705 | 17228.5714 | 6705 | 0 | 6705
2025-04-20 | 18185.7143 | 6705 | 18185.7143 | 6705 | 0 | 6705
2025-04-21 | 19142.8571 | 7087.15 | 19142.8571 | 7087.15 | 0 | 7087.15
2025-04-22 | 20100 | 7469.3 | 20100 | 7469.3 | 0 | 7469.3
2025-04-23 | 21057.1429 | 7851.45 | 21057.1429 | 7851.45 | 0 | 7851.45
2025-04-24 | 22014.2857 | 8233.6 | 22014.2857 | 8233.6 | 0 | 8233.6
2025-04-25 | 22971.4286 | 8615.75 | 22971.4286 | 8615.75 | 0 | 8615.75
2025-04-26 | 23928.5714 | 8615.75 | 23928.5714 | 8615.75 | 0 | 8615.75
2025-04-27 | 24885.7143 | 8615.75 | 24885.7143 | 8615.75 | 0 | 8615.75
2025-04-28 | 25842.8571 | 8615.75 | 25842.8571 | 8615.75 | 0 | 8615.75
2025-04-29 | 26800 | 8615.75 | 26800 | 8615.75 | 0 | 8615.75
2025-04-30 | 27757.1429 | 8615.75 | 27757.1429 | 8615.75 | 0 | 8615.75
2025-05-01 | 28714.2857 | 8615.75 | 28714.2857 | 8615.75 | 0 | 8615.75
2025-05-02 | 29671.4286 | 8615.75 | 29671.4286 | 8615.75 | 0 | 8615.75
2025-05-03 | 30628.5714 | 8615.75 | 30628.5714 | 8615.75 | 0 | 8615.75
2025-05-04 | 31585.7143 | 8615.75 | 31585.7143 | 8615.75 | 0 | 8615.75
2025-05-05 | 32542.8571 | 8615.75 | 32542.8571 | 8615.75 | 0 | 8615.75
2025-05-06 | 33500 | 8615.75 | 33500 | 8615.75 | 0 | 8615.75
2025-05-07 | 34457.1429 | 8615.75 | 34457.1429 | 8615.75 | 0 | 8615.75
2025-05-08 | 35414.2857 | 8615.75 | 35414.2857 | 8615.75 | 0 | 8615.75
2025-05-09 | 36371.4286 | 8615.75 | 36371.4286 | 8615.75 | 0 | 8615.75
2025-05-10 | 37328.5714 | 8615.75 | 37328.5714 | 8615.75 | 0 | 8615.75
2025-05-11 | 38285.7143 | 8615.75 | 38285.7143 | 8615.75 | 0 | 8615.75
2025-05-12 | 39242.8571 | 8615.75 | 39242.8571 | 8615.75 | 0 | 8615.75
2025-05-13 | 40200 | 8615.75 | 40200 | 8615.75 | 0 | 8615.75
2025-05-14 | 41157.1429 | 8615.75 | 41157.1429 | 8615.75 | 0 | 8615.75
2025-05-15 | 42114.2857 | 8615.75 | 42114.2857 | 8615.75 | 0 | 8615.75
2025-05-16 | 43071.4286 | 8615.75 | 43071.4286 | 8615.75 | 0 | 8615.75
2025-05-17 | 44028.5714 | 8615.75 | 44028.5714 | 8615.75 | 0 | 8615.75
2025-05-18 | 44985.7143 | 8615.75 | 44985.7143 | 8615.75 | 0 | 8615.75
2025-05-19 | 45942.8571 | 8615.75 | 45942.8571 | 8615.75 | 0 | 8615.75
2025-05-20 | 46900 | 8615.75 | 46900 | 8615.75 | 0 | 8615.75
2025-05-21 | 47857.1429 | 8615.75 | 47857.1429 | 8615.75 | 0 | 8615.75
2025-05-22 | 48814.2857 | 8615.75 | 48814.2857 | 8615.75 | 0 | 8615.75
2025-05-23 | 49771.4286 | 8615.75 | 49771.4286 | 8615.75 | 0 | 8615.75
2025-05-24 | 50728.5714 | 8615.75 | 50728.5714 | 8615.75 | 0 | 8615.75
2025-05-25 | 51685.7143 | 8615.75 | 51685.7143 | 8615.75 | 0 | 8615.75
2025-05-26 | 52642.8571 | 8615.75 | 52642.8571 | 8615.75 | 0 | 8615.75
2025-05-27 | 53600 | 8615.75 | 53600 | 8615.75 | 0 | 8615.75
2025-05-28 | 54557.1429 | 8615.75 | 54557.1429 | 8615.75 | 0 | 8615.75
2025-05-29 | 55514.2857 | 8615.75 | 55514.2857 | 8615.75 | 0 | 8615.75
2025-05-30 | 56471.4286 | 8615.75 | 56471.4286 | 8615.75 | 0 | 8615.75
2025-05-31 | 57428.5714 | 8615.75 | 57428.5714 | 8615.75 | 0 | 8615.75
2025-06-01 | 58385.7143 | 8615.75 | 58385.7143 | 8615.75 | 0 | 8615.75
2025-06-02 | 59342.8571 | 9044.55 | 59342.8571 | 9044.55 | 0 | 9044.55
2025-06-03 | 60300 | 9473.35 | 60300 | 9473.35 | 0 | 9473.35
2025-06-04 | 61257.1429 | 9902.15 | 61257.1429 | 9902.15 | 0 | 9902.15
2025-06-05 | 62214.2857 | 10330.95 | 62214.2857 | 10330.95 | 0 | 10330.95
2025-06-06 | 63171.4286 | 10759.75 | 63171.4286 | 10759.75 | 0 | 10759.75
2025-06-07 | 64128.5714 | 10759.75 | 64128.5714 | 10759.75 | 0 | 10759.75
2025-06-08 | 65085.7143 | 10759.75 | 65085.7143 | 10759.75 | 0 | 10759.75
2025-06-09 | 66042.8571 | 10866.95 | 66042.8571 | 10866.95 | 0 | 10866.95
2025-06-10 | 67000 | 10974.15 | 67000 | 10974.15 | 0 | 10974.15
2025-06-11 | 67957.1429 | 11081.35 | 67957.1429 | 11081.35 | 0 | 11081.35
2025-06-12 | 68914.2857 | 11188.55 | 68914.2857 | 11188.55 | 0 | 11188.55
2025-06-13 | 69871.4286 | 11295.75 | 69871.4286 | 11295.75 | 0 | 11295.75
2025-06-14 | 70828.5714 | 11295.75 | 70828.5714 | 11295.75 | 0 | 11295.75
2025-06-15 | 71785.7143 | 11295.75 | 71785.7143 | 11295.75 | 0 | 11295.75
2025-06-16 | 72742.8571 | 11677.9 | 72742.8571 | 11677.9 | 0 | 11677.9
2025-06-17 | 73700 | 12060.05 | 73700 | 12060.05 | 0 | 12060.05
2025-06-18 | 74657.1429 | 12442.2 | 74657.1429 | 12442.2 | 0 | 12442.2
2025-06-19 | 75614.2857 | 12824.35 | 75614.2857 | 12824.35 | 0 | 12824.35
2025-06-20 | 76571.4286 | 13206.5 | 76571.4286 | 13206.5 | 0 | 13206.5
2025-06-21 | 77528.5714 | 13206.5 | 77528.5714 | 13206.5 | 0 | 13206.5
2025-06-22 | 78485.7143 | 13206.5 | 78485.7143 | 13206.5 | 0 | 13206.5
2025-06-23 | 79442.8571 | 13313.7 | 79442.8571 | 13313.7 | 0 | 13313.7
2025-06-24 | 80400 | 13420.9 | 80400 | 13420.9 | 0 | 13420.9
2025-06-25 | 80522.9722 | 13528.1 | 80522.9722 | 13528.1 | 0 | 13528.1
2025-06-26 | 80645.9444 | 13635.3 | 80645.9444 | 13635.3 | 0 | 13635.3
2025-06-27 | 80768.9166 | 13742.5 | 80768.9166 | 13742.5 | 0 | 13742.5
2025-06-28 | 80891.8888 | 13742.5 | 80891.8888 | 13742.5 | 0 | 13742.5
2025-06-29 | 81014.861 | 13742.5 | 81014.861 | 13742.5 | 0 | 13742.5
2025-06-30 | 81137.8331 | 14191.65 | 81137.8331 | 14191.65 | 0 | 14191.65
2025-07-01 | 81260.8053 | 14640.8 | 81260.8053 | 14640.8 | 0 | 14640.8
2025-07-02 | 81383.7775 | 15089.95 | 81383.7775 | 15089.95 | 0 | 15089.95
2025-07-03 | 81506.7497 | 15539.1 | 81506.7497 | 15539.1 | 0 | 15539.1
2025-07-04 | 81629.7219 | 15988.25 | 81629.7219 | 15988.25 | 0 | 15988.25
2025-07-05 | 81752.6941 | 15988.25 | 81752.6941 | 15988.25 | 0 | 15988.25
2025-07-06 | 81875.6663 | 15988.25 | 81875.6663 | 15988.25 | 0 | 15988.25
2025-07-07 | 81998.6385 | 16390.25 | 81998.6385 | 16390.25 | 0 | 16390.25
2025-07-08 | 82121.6107 | 16792.25 | 82121.6107 | 16792.25 | 0 | 16792.25
2025-07-09 | 82244.5829 | 17194.25 | 82244.5829 | 17194.25 | 0 | 17194.25
2025-07-10 | 82367.5551 | 17596.25 | 82367.5551 | 17596.25 | 0 | 17596.25
2025-07-11 | 82490.5273 | 17998.25 | 82490.5273 | 17998.25 | 0 | 17998.25
2025-07-12 | 82613.4994 | 17998.25 | 82613.4994 | 17998.25 | 0 | 17998.25
2025-07-13 | 82736.4716 | 17998.25 | 82736.4716 | 17998.25 | 0 | 17998.25
2025-07-14 | 82859.4438 | 18400.25 | 82859.4438 | 18400.25 | 0 | 18400.25
2025-07-15 | 82982.416 | 18802.25 | 82982.416 | 18802.25 | 0 | 18802.25
2025-07-16 | 83105.3882 | 19204.25 | 83105.3882 | 19204.25 | 0 | 19204.25
2025-07-17 | 83228.3604 | 19606.25 | 83228.3604 | 19606.25 | 0 | 19606.25
2025-07-18 | 83351.3326 | 20008.25 | 83351.3326 | 20008.25 | 0 | 20008.25
2025-07-19 | 83474.3048 | 20008.25 | 83474.3048 | 20008.25 | 0 | 20008.25
2025-07-20 | 83597.277 | 20008.25 | 83597.277 | 20008.25 | 0 | 20008.25
2025-07-21 | 83720.2492 | 20410.25 | 83720.2492 | 20410.25 | 0 | 20410.25
2025-07-22 | 83843.2214 | 20812.25 | 83843.2214 | 20812.25 | 0 | 20812.25
2025-07-23 | 83966.1935 | 21214.25 | 83966.1935 | 21214.25 | 0 | 21214.25
2025-07-24 | 84089.1657 | 21616.25 | 84089.1657 | 21616.25 | 0 | 21616.25
2025-07-25 | 84212.1379 | 22018.25 | 84212.1379 | 22018.25 | 0 | 22018.25
2025-07-26 | 84335.1101 | 22018.25 | 84335.1101 | 22018.25 | 0 | 22018.25
2025-07-27 | 84458.0823 | 22018.25 | 84458.0823 | 22018.25 | 0 | 22018.25
2025-07-28 | 84581.0545 | 22366.65 | 84581.0545 | 22366.65 | 0 | 22366.65
2025-07-29 | 84704.0267 | 22715.05 | 84704.0267 | 22715.05 | 0 | 22715.05
2025-07-30 | 84826.9989 | 23063.45 | 84826.9989 | 23063.45 | 0 | 23063.45
2025-07-31 | 84949.9711 | 23411.85 | 84949.9711 | 23411.85 | 0 | 23411.85
2025-08-01 | 85072.9433 | 23760.25 | 85072.9433 | 23760.25 | 0 | 23760.25
2025-08-02 | 85195.9155 | 23760.25 | 85195.9155 | 23760.25 | 0 | 23760.25
2025-08-03 | 85318.8877 | 23760.25 | 85318.8877 | 23760.25 | 0 | 23760.25
2025-08-04 | 85441.8598 | 24028.25 | 85441.8598 | 24028.25 | 0 | 24028.25
2025-08-05 | 85564.832 | 24296.25 | 85564.832 | 24296.25 | 0 | 24296.25
2025-08-06 | 85687.8042 | 24564.25 | 85687.8042 | 24564.25 | 0 | 24564.25
2025-08-07 | 85810.7764 | 24832.25 | 85810.7764 | 24832.25 | 0 | 24832.25
2025-08-08 | 85933.7486 | 25100.25 | 85933.7486 | 25100.25 | 0 | 25100.25
2025-08-09 | 86056.7208 | 25100.25 | 86056.7208 | 25100.25 | 0 | 25100.25
2025-08-10 | 86179.693 | 25100.25 | 86179.693 | 25100.25 | 0 | 25100.25
2025-08-11 | 86302.6652 | 25314.65 | 86302.6652 | 25314.65 | 0 | 25314.65
2025-08-12 | 86425.6374 | 25529.05 | 86425.6374 | 25529.05 | 0 | 25529.05
2025-08-13 | 86548.6096 | 25743.45 | 86548.6096 | 25743.45 | 0 | 25743.45
2025-08-14 | 86671.5818 | 25957.85 | 86671.5818 | 25957.85 | 0 | 25957.85
2025-08-15 | 86794.5539 | 26172.25 | 86794.5539 | 26172.25 | 0 | 26172.25
2025-08-16 | 86917.5261 | 26172.25 | 86917.5261 | 26172.25 | 0 | 26172.25
2025-08-17 | 87040.4983 | 26172.25 | 87040.4983 | 26172.25 | 0 | 26172.25
2025-08-18 | 87163.4705 | 26708.25 | 87163.4705 | 26708.25 | 0 | 26708.25
2025-08-19 | 87286.4427 | 27244.25 | 87286.4427 | 27244.25 | 0 | 27244.25
2025-08-20 | 87409.4149 | 27780.25 | 87409.4149 | 27780.25 | 0 | 27780.25
2025-08-21 | 87532.3871 | 28316.25 | 87532.3871 | 28316.25 | 0 | 28316.25
2025-08-22 | 87655.3593 | 28852.25 | 87655.3593 | 28852.25 | 0 | 28852.25
2025-08-23 | 87778.3315 | 28852.25 | 87778.3315 | 28852.25 | 0 | 28852.25
2025-08-24 | 87901.3037 | 28852.25 | 87901.3037 | 28852.25 | 0 | 28852.25
2025-08-25 | 88024.2759 | 29952.05 | 88024.2759 | 29952.05 | 0 | 29952.05
2025-08-26 | 88147.2481 | 31051.85 | 88147.2481 | 31051.85 | 0 | 31051.85
2025-08-27 | 88270.2202 | 32151.65 | 88270.2202 | 32151.65 | 0 | 32151.65
2025-08-28 | 88393.1924 | 33251.45 | 88393.1924 | 33251.45 | 0 | 33251.45
2025-08-29 | 88516.1646 | 34351.25 | 88516.1646 | 34351.25 | 0 | 34351.25
2025-08-30 | 88639.1368 | 34351.25 | 88639.1368 | 34351.25 | 0 | 34351.25
2025-08-31 | 88762.109 | 34351.25 | 88762.109 | 34351.25 | 0 | 34351.25
2025-09-01 | 88885.0812 | 35095.2 | 88885.0812 | 35095.2 | 0 | 35095.2
2025-09-02 | 89008.0534 | 35839.15 | 89008.0534 | 35839.15 | 0 | 35839.15
2025-09-03 | 89131.0256 | 36583.1 | 89131.0256 | 36583.1 | 0 | 36583.1
2025-09-04 | 89253.9978 | 37327.05 | 89253.9978 | 37327.05 | 0 | 37327.05
2025-09-05 | 89376.97 | 38071 | 89376.97 | 38071 | 0 | 38071
2025-09-06 | 89499.9422 | 38071 | 89499.9422 | 38071 | 0 | 38071
2025-09-07 | 89622.9143 | 38071 | 89622.9143 | 38071 | 0 | 38071
2025-09-08 | 89745.8865 | 38573.75 | 89745.8865 | 38573.75 | 0 | 38573.75
2025-09-09 | 89868.8587 | 39076.5 | 89868.8587 | 39076.5 | 0 | 39076.5
2025-09-10 | 89991.8309 | 39579.25 | 89991.8309 | 39579.25 | 0 | 39579.25
2025-09-11 | 90114.8031 | 40082 | 90114.8031 | 40082 | 0 | 40082
2025-09-12 | 90237.7753 | 40584.75 | 90237.7753 | 40584.75 | 0 | 40584.75
2025-09-13 | 90360.7475 | 40584.75 | 90360.7475 | 40584.75 | 0 | 40584.75
2025-09-14 | 90483.7197 | 40584.75 | 90483.7197 | 40584.75 | 0 | 40584.75
2025-09-15 | 90606.6919 | 42546.625 | 90606.6919 | 42546.625 | 0 | 42546.625
2025-09-16 | 90729.6641 | 44508.5 | 90729.6641 | 44508.5 | 0 | 44508.5
2025-09-17 | 90852.6363 | 46470.375 | 90852.6363 | 46470.375 | 0 | 46470.375
2025-09-18 | 90975.6085 | 48432.25 | 90975.6085 | 48432.25 | 0 | 48432.25
2025-09-19 | 91098.5806 | 50394.125 | 91098.5806 | 50394.125 | 0 | 50394.125
2025-09-20 | 91098.5806 | 50394.125 | 91098.5806 | 50394.125 | 0 | 50394.125
2025-09-21 | 91098.5806 | 50394.125 | 91098.5806 | 50394.125 | 0 | 50394.125
2025-09-22 | 94401.4769 | 51446.2 | 94401.4769 | 51446.2 | 0 | 51446.2
2025-09-23 | 97704.3732 | 52498.275 | 97704.3732 | 52498.275 | 0 | 52498.275
2025-09-24 | 101007.2694 | 53550.35 | 101007.2694 | 53550.35 | 0 | 53550.35
2025-09-25 | 104310.1657 | 54602.425 | 104310.1657 | 54602.425 | 0 | 54602.425
2025-09-26 | 107613.062 | 55654.5 | 107613.062 | 55654.5 | 0 | 55654.5
2025-09-27 | 110915.9583 | 55654.5 | 110915.9583 | 55654.5 | 0 | 55654.5
2025-09-28 | 114218.8545 | 55654.5 | 114218.8545 | 55654.5 | 0 | 55654.5
2025-09-29 | 117521.7508 | 56981.625 | 117521.7508 | 56981.625 | 0 | 56981.625
2025-09-30 | 120824.6471 | 58308.75 | 120824.6471 | 58308.75 | 0 | 58308.75
2025-10-01 | 124127.5433 | 59635.875 | 124127.5433 | 59635.875 | 0 | 59635.875
2025-10-02 | 127430.4396 | 60963 | 127430.4396 | 60963 | 0 | 60963
2025-10-03 | 130733.3359 | 62290.125 | 130733.3359 | 62290.125 | 0 | 62290.125
2025-10-04 | 134036.2321 | 62290.125 | 134036.2321 | 62290.125 | 0 | 62290.125
2025-10-05 | 137339.1284 | 62290.125 | 137339.1284 | 62290.125 | 0 | 62290.125
2025-10-06 | 140642.0247 | 63946.875 | 140642.0247 | 63946.875 | 0 | 63946.875
2025-10-07 | 143944.9209 | 65603.625 | 143944.9209 | 65603.625 | 0 | 65603.625
2025-10-08 | 147247.8172 | 67260.375 | 147247.8172 | 67260.375 | 0 | 67260.375
2025-10-09 | 150550.7135 | 68917.125 | 150550.7135 | 68917.125 | 0 | 68917.125
2025-10-10 | 153853.6097 | 70573.875 | 153853.6097 | 70573.875 | 0 | 70573.875
2025-10-11 | 157156.506 | 70573.875 | 157156.506 | 70573.875 | 0 | 70573.875
2025-10-12 | 160459.4023 | 70573.875 | 160459.4023 | 70573.875 | 0 | 70573.875
2025-10-13 | 163762.2985 |  | 163762.2985 |  | 0
2025-10-14 | 167065.1948 |  | 167065.1948 |  | 0
2025-10-15 | 170368.0911 |  | 170368.0911 |  | 0
2025-10-16 | 173670.9873 |  | 173670.9873 |  | 0
2025-10-17 | 176973.8836 |  | 176973.8836 |  | 0
2025-10-18 | 180276.7799 |  | 180276.7799 |  | 0
2025-10-19 | 183579.6762 |  | 183579.6762 |  | 0
2025-10-20 | 186882.5724 |  | 186882.5724 |  | 0
2025-10-21 | 190185.4687 |  | 190185.4687 |  | 0
2025-10-22 | 193488.365 |  | 193488.365 |  | 0
2025-10-23 | 196791.2612 |  | 196791.2612 |  | 0
2025-10-24 | 200094.1575 |  | 200094.1575 |  | 0
2025-10-25 | 203397.0538 |  | 203397.0538 |  | 0
2025-10-26 | 206699.95 |  | 206699.95 |  | 0
2025-10-27 | 210002.8463 |  | 210002.8463 |  | 0
2025-10-28 | 213305.7426 |  | 213305.7426 |  | 0
2025-10-29 | 216608.6388 |  | 216608.6388 |  | 0
2025-10-30 | 219911.5351 |  | 219911.5351 |  | 0
2025-10-31 | 223214.4314 |  | 223214.4314 |  | 0
2025-11-01 | 226517.3276 |  | 226517.3276 |  | 0
2025-11-02 | 229820.2239 |  | 229820.2239 |  | 0
2025-11-03 | 233123.1202 |  | 233123.1202 |  | 0
2025-11-04 | 236426.0164 |  | 236426.0164 |  | 0
2025-11-05 | 239728.9127 |  | 239728.9127 |  | 0
2025-11-06 | 243031.809 |  | 243031.809 |  | 0
2025-11-07 | 246334.7052 |  | 246334.7052 |  | 0
2025-11-08 | 249637.6015 |  | 249637.6015 |  | 0
2025-11-09 | 252940.4978 |  | 252940.4978 |  | 0
2025-11-10 | 256243.3941 |  | 256243.3941 |  | 0
2025-11-11 | 259546.2903 |  | 259546.2903 |  | 0
2025-11-12 | 261095.5386 |  | 261095.5386 |  | 0
2025-11-13 | 262644.787 |  | 262644.787 |  | 0
2025-11-14 | 264194.0353 |  | 264194.0353 |  | 0
2025-11-15 | 265743.2836 |  | 265743.2836 |  | 0
2025-11-16 | 267292.5319 |  | 267292.5319 |  | 0
2025-11-17 | 268841.7802 |  | 268841.7802 |  | 0
2025-11-18 | 270391.0286 |  | 270391.0286 |  | 0
2025-11-19 | 271940.2769 |  | 271940.2769 |  | 0
2025-11-20 | 273489.5252 |  | 273489.5252 |  | 0
2025-11-21 | 275038.7735 |  | 275038.7735 |  | 0
2025-11-22 | 276588.0218 |  | 276588.0218 |  | 0
2025-11-23 | 278137.2702 |  | 278137.2702 |  | 0
2025-11-24 | 279686.5185 |  | 279686.5185 |  | 0
2025-11-25 | 281235.7668 |  | 281235.7668 |  | 0
2025-11-26 | 282785.0151 |  | 282785.0151 |  | 0
2025-11-27 | 284334.2634 |  | 284334.2634 |  | 0
2025-11-28 | 285883.5117 |  | 285883.5117 |  | 0
2025-11-29 | 287432.7601 |  | 287432.7601 |  | 0
2025-11-30 | 288982.0084 |  | 288982.0084 |  | 0
2025-12-01 | 290531.2567 |  | 290531.2567 |  | 0
2025-12-02 | 292080.505 |  | 292080.505 |  | 0
2025-12-03 | 293629.7533 |  | 293629.7533 |  | 0
2025-12-04 | 295179.0017 |  | 295179.0017 |  | 0
2025-12-05 | 296728.25 |  | 296728.25 |  | 0
2025-12-06 | 298277.4983 |  | 298277.4983 |  | 0
2025-12-07 | 299826.7466 |  | 299826.7466 |  | 0
2025-12-08 | 301375.9949 |  | 301375.9949 |  | 0
2025-12-09 | 302925.2433 |  | 302925.2433 |  | 0
2025-12-10 | 304474.4916 |  | 304474.4916 |  | 0
2025-12-11 | 306023.7399 |  | 306023.7399 |  | 0
2025-12-12 | 307572.9882 |  | 307572.9882 |  | 0
2025-12-13 | 309122.2365 |  | 309122.2365 |  | 0
2025-12-14 | 310671.4849 |  | 310671.4849 |  | 0
2025-12-15 | 312220.7332 |  | 312220.7332 |  | 0
2025-12-16 | 313769.9815 |  | 313769.9815 |  | 0
2025-12-17 | 315319.2298 |  | 315319.2298 |  | 0
2025-12-18 | 316868.4781 |  | 316868.4781 |  | 0
2025-12-19 | 318417.7264 |  | 318417.7264 |  | 0
2025-12-20 | 319966.9748 |  | 319966.9748 |  | 0
2025-12-21 | 321516.2231 |  | 321516.2231 |  | 0
2025-12-22 | 323065.4714 |  | 323065.4714 |  | 0
2025-12-23 | 324614.7197 |  | 324614.7197 |  | 0
2025-12-24 | 326163.968 |  | 326163.968 |  | 0
2025-12-25 | 327713.2164 |  | 327713.2164 |  | 0
2025-12-26 | 329262.4647 |  | 329262.4647 |  | 0
2025-12-27 | 330811.713 |  | 330811.713 |  | 0
2025-12-28 | 332360.9613 |  | 332360.9613 |  | 0
2025-12-29 | 333910.2096 |  | 333910.2096 |  | 0
2025-12-30 | 335459.458 |  | 335459.458 |  | 0
2025-12-31 | 337008.7063 |  | 337008.7063 |  | 0
2026-01-01 | 338557.9546 |  | 338557.9546 |  | 0
2026-01-02 | 340107.2029 |  | 340107.2029 |  | 0
2026-01-03 | 341656.4512 |  | 341656.4512 |  | 0
2026-01-04 | 343205.6996 |  | 343205.6996 |  | 0
2026-01-05 | 344754.9479 |  | 344754.9479 |  | 0
2026-01-06 | 346304.1962 |  | 346304.1962 |  | 0
2026-01-07 | 347853.4445 |  | 347853.4445 |  | 0
2026-01-08 | 349402.6928 |  | 349402.6928 |  | 0
2026-01-09 | 350951.9411 |  | 350951.9411 |  | 0
2026-01-10 | 352501.1895 |  | 352501.1895 |  | 0
2026-01-11 | 354050.4378 |  | 354050.4378 |  | 0
2026-01-12 | 355599.6861 |  | 355599.6861 |  | 0
2026-01-13 | 357148.9344 |  | 357148.9344 |  | 0
2026-01-14 | 358698.1827 |  | 358698.1827 |  | 0
2026-01-15 | 360247.4311 |  | 360247.4311 |  | 0
2026-01-16 | 361796.6794 |  | 361796.6794 |  | 0
2026-01-17 | 363345.9277 |  | 363345.9277 |  | 0
2026-01-18 | 364895.176 |  | 364895.176 |  | 0
2026-01-19 | 366444.4243 |  | 366444.4243 |  | 0
2026-01-20 | 367993.6727 |  | 367993.6727 |  | 0
2026-01-21 | 369542.921 |  | 369542.921 |  | 0
2026-01-22 | 371092.1693 |  | 371092.1693 |  | 0
2026-01-23 | 372641.4176 |  | 372641.4176 |  | 0
2026-01-24 | 374190.6659 |  | 374190.6659 |  | 0
2026-01-25 | 375739.9143 |  | 375739.9143 |  | 0
2026-01-26 | 377289.1626 |  | 377289.1626 |  | 0
2026-01-27 | 378838.4109 |  | 378838.4109 |  | 0
2026-01-28 | 380387.6592 |  | 380387.6592 |  | 0
2026-01-29 | 381936.9075 |  | 381936.9075 |  | 0
2026-01-30 | 383486.1559 |  | 383486.1559 |  | 0
2026-01-31 | 385035.4042 |  | 385035.4042 |  | 0
2026-02-01 | 386584.6525 |  | 386584.6525 |  | 0
2026-02-02 | 388133.9008 |  | 388133.9008 |  | 0
2026-02-03 | 389683.1491 |  | 389683.1491 |  | 0
2026-02-04 | 390971.2259 |  | 390971.2259 |  | 0
2026-02-05 | 392259.3028 |  | 392259.3028 |  | 0
2026-02-06 | 393547.3796 |  | 393547.3796 |  | 0
2026-02-07 | 394835.4564 |  | 394835.4564 |  | 0
2026-02-08 | 396123.5332 |  | 396123.5332 |  | 0
2026-02-09 | 397411.61 |  | 397411.61 |  | 0
2026-02-10 | 398699.6869 |  | 398699.6869 |  | 0
2026-02-11 | 399987.7637 |  | 399987.7637 |  | 0
2026-02-12 | 401275.8405 |  | 401275.8405 |  | 0
2026-02-13 | 402563.9173 |  | 402563.9173 |  | 0
2026-02-14 | 403851.9941 |  | 403851.9941 |  | 0
2026-02-15 | 405140.0709 |  | 405140.0709 |  | 0
2026-02-16 | 406428.1478 |  | 406428.1478 |  | 0
2026-02-17 | 407716.2246 |  | 407716.2246 |  | 0
2026-02-18 | 409004.3014 |  | 409004.3014 |  | 0
2026-02-19 | 410292.3782 |  | 410292.3782 |  | 0
2026-02-20 | 411580.455 |  | 411580.455 |  | 0
2026-02-21 | 412868.5319 |  | 412868.5319 |  | 0
2026-02-22 | 414156.6087 |  | 414156.6087 |  | 0
2026-02-23 | 415444.6855 |  | 415444.6855 |  | 0
2026-02-24 | 416732.7623 |  | 416732.7623 |  | 0
2026-02-25 | 418020.8391 |  | 418020.8391 |  | 0
2026-02-26 | 419308.9159 |  | 419308.9159 |  | 0
2026-02-27 | 420596.9928 |  | 420596.9928 |  | 0
2026-02-28 | 421885.0696 |  | 421885.0696 |  | 0
2026-03-01 | 423173.1464 |  | 423173.1464 |  | 0
2026-03-02 | 424461.2232 |  | 424461.2232 |  | 0
2026-03-03 | 425749.3 |  | 425749.3 |  | 0
2026-03-04 | 427037.3769 |  | 427037.3769 |  | 0
2026-03-05 | 428325.4537 |  | 428325.4537 |  | 0
2026-03-06 | 429613.5305 |  | 429613.5305 |  | 0
2026-03-07 | 430901.6073 |  | 430901.6073 |  | 0
2026-03-08 | 432189.6841 |  | 432189.6841 |  | 0
2026-03-09 | 433477.7609 |  | 433477.7609 |  | 0
2026-03-10 | 434765.8378 |  | 434765.8378 |  | 0
2026-03-11 | 436053.9146 |  | 436053.9146 |  | 0
2026-03-12 | 437341.9914 |  | 437341.9914 |  | 0
2026-03-13 | 438630.0682 |  | 438630.0682 |  | 0
2026-03-14 | 439918.145 |  | 439918.145 |  | 0
2026-03-15 | 441206.2219 |  | 441206.2219 |  | 0
2026-03-16 | 442494.2987 |  | 442494.2987 |  | 0
2026-03-17 | 443782.3755 |  | 443782.3755 |  | 0
2026-03-18 | 445070.4523 |  | 445070.4523 |  | 0
2026-03-19 | 446358.5291 |  | 446358.5291 |  | 0
2026-03-20 | 447646.6059 |  | 447646.6059 |  | 0
2026-03-21 | 448934.6828 |  | 448934.6828 |  | 0
2026-03-22 | 450222.7596 |  | 450222.7596 |  | 0
2026-03-23 | 451510.8364 |  | 451510.8364 |  | 0
2026-03-24 | 452798.9132 |  | 452798.9132 |  | 0
2026-03-25 | 454086.99 |  | 454086.99 |  | 0
2026-03-26 | 455375.0669 |  | 455375.0669 |  | 0
2026-03-27 | 456663.1437 |  | 456663.1437 |  | 0
2026-03-28 | 457951.2205 |  | 457951.2205 |  | 0
2026-03-29 | 459239.2973 |  | 459239.2973 |  | 0
2026-03-30 | 460527.3741 |  | 460527.3741 |  | 0
2026-03-31 | 461815.4509 |  | 461815.4509 |  | 0
2026-04-01 | 463103.5278 |  | 463103.5278 |  | 0
2026-04-02 | 464391.6046 |  | 464391.6046 |  | 0
2026-04-03 | 465679.6814 |  | 465679.6814 |  | 0
2026-04-04 | 466967.7582 |  | 466967.7582 |  | 0
2026-04-05 | 468255.835 |  | 468255.835 |  | 0
2026-04-06 | 469543.9119 |  | 469543.9119 |  | 0
2026-04-07 | 470831.9887 |  | 470831.9887 |  | 0
2026-04-08 | 472120.0655 |  | 472120.0655 |  | 0
2026-04-09 | 473408.1423 |  | 473408.1423 |  | 0
2026-04-10 | 474696.2191 |  | 474696.2191 |  | 0
2026-04-11 | 475984.2959 |  | 475984.2959 |  | 0
2026-04-12 | 477272.3728 |  | 477272.3728 |  | 0
2026-04-13 | 478560.4496 |  | 478560.4496 |  | 0
2026-04-14 | 479848.5264 |  | 479848.5264 |  | 0
2026-04-15 | 481136.6032 |  | 481136.6032 |  | 0
2026-04-16 | 482424.68 |  | 482424.68 |  | 0
2026-04-17 | 483712.7569 |  | 483712.7569 |  | 0
2026-04-18 | 485000.8337 |  | 485000.8337 |  | 0
2026-04-19 | 486288.9105 |  | 486288.9105 |  | 0
2026-04-20 | 487576.9873 |  | 487576.9873 |  | 0
2026-04-21 | 488865.0641 |  | 488865.0641 |  | 0
2026-04-22 | 490153.1409 |  | 490153.1409 |  | 0
2026-04-23 | 491441.2178 |  | 491441.2178 |  | 0
2026-04-24 | 492729.2946 |  | 492729.2946 |  | 0
2026-04-25 | 494017.3714 |  | 494017.3714 |  | 0
2026-04-26 | 495305.4482 |  | 495305.4482 |  | 0
2026-04-27 | 496593.525 |  | 496593.525 |  | 0
2026-04-28 | 497881.6019 |  | 497881.6019 |  | 0
2026-04-29 | 499169.6787 |  | 499169.6787 |  | 0
2026-04-30 | 500457.7555 |  | 500457.7555 |  | 0
2026-05-01 | 501745.8323 |  | 501745.8323 |  | 0
2026-05-02 | 503033.9091 |  | 503033.9091 |  | 0
2026-05-03 | 504321.9859 |  | 504321.9859 |  | 0
2026-05-04 | 505610.0628 |  | 505610.0628 |  | 0
2026-05-05 | 506898.1396 |  | 506898.1396 |  | 0
2026-05-06 | 508186.2164 |  | 508186.2164 |  | 0
2026-05-07 | 509474.2932 |  | 509474.2932 |  | 0
2026-05-08 | 510762.37 |  | 510762.37 |  | 0
2026-05-09 | 512050.4469 |  | 512050.4469 |  | 0
2026-05-10 | 513338.5237 |  | 513338.5237 |  | 0
2026-05-11 | 514626.6005 |  | 514626.6005 |  | 0
2026-05-12 | 515914.6773 |  | 515914.6773 |  | 0
2026-05-13 | 517202.7541 |  | 517202.7541 |  | 0
2026-05-14 | 518490.8309 |  | 518490.8309 |  | 0
2026-05-15 | 519778.9078 |  | 519778.9078 |  | 0
2026-05-16 | 521066.9846 |  | 521066.9846 |  | 0
2026-05-17 | 522355.0614 |  | 522355.0614 |  | 0
2026-05-18 | 523643.1382 |  | 523643.1382 |  | 0
2026-05-19 | 524931.215 |  | 524931.215 |  | 0
2026-05-20 | 526219.2919 |  | 526219.2919 |  | 0
2026-05-21 | 527507.3687 |  | 527507.3687 |  | 0
2026-05-22 | 528795.4455 |  | 528795.4455 |  | 0
2026-05-23 | 530083.5223 |  | 530083.5223 |  | 0
2026-05-24 | 531371.5991 |  | 531371.5991 |  | 0
2026-05-25 | 532659.6759 |  | 532659.6759 |  | 0
2026-05-26 | 533947.7528 |  | 533947.7528 |  | 0
2026-05-27 | 535235.8296 |  | 535235.8296 |  | 0
2026-05-28 | 536523.9064 |  | 536523.9064 |  | 0
2026-05-29 | 537811.9832 |  | 537811.9832 |  | 0
2026-05-30 | 539100.06 |  | 539100.06 |  | 0
2026-05-31 | 540388.1369 |  | 540388.1369 |  | 0
2026-06-01 | 541676.2137 |  | 541676.2137 |  | 0
2026-06-02 | 542964.2905 |  | 542964.2905 |  | 0
2026-06-03 | 544252.3673 |  | 544252.3673 |  | 0
2026-06-04 | 545540.4441 |  | 545540.4441 |  | 0
2026-06-05 | 546828.5209 |  | 546828.5209 |  | 0
2026-06-06 | 548116.5978 |  | 548116.5978 |  | 0
2026-06-07 | 549404.6746 |  | 549404.6746 |  | 0
2026-06-08 | 550692.7514 |  | 550692.7514 |  | 0
2026-06-09 | 551980.8282 |  | 551980.8282 |  | 0
2026-06-10 | 553268.905 |  | 553268.905 |  | 0
2026-06-11 | 554556.9819 |  | 554556.9819 |  | 0
2026-06-12 | 555845.0587 |  | 555845.0587 |  | 0
2026-06-13 | 557133.1355 |  | 557133.1355 |  | 0
2026-06-14 | 558421.2123 |  | 558421.2123 |  | 0
2026-06-15 | 559709.2891 |  | 559709.2891 |  | 0
2026-06-16 | 560997.3659 |  | 560997.3659 |  | 0
2026-06-17 | 562285.4428 |  | 562285.4428 |  | 0
2026-06-18 | 563573.5196 |  | 563573.5196 |  | 0
2026-06-19 | 564861.5964 |  | 564861.5964 |  | 0
2026-06-20 | 566149.6732 |  | 566149.6732 |  | 0
2026-06-21 | 567437.75 |  | 567437.75 |  | 0
2026-06-22 | 568725.8269 |  | 568725.8269 |  | 0
2026-06-23 | 570013.9037 |  | 570013.9037 |  | 0
2026-06-24 | 571301.9805 |  | 571301.9805 |  | 0
2026-06-25 | 572590.0573 |  | 572590.0573 |  | 0
2026-06-26 | 573878.1341 |  | 573878.1341 |  | 0
2026-06-27 | 575166.2109 |  | 575166.2109 |  | 0
2026-06-28 | 576454.2878 |  | 576454.2878 |  | 0
2026-06-29 | 577742.3646 |  | 577742.3646 |  | 0
2026-06-30 | 579030.4414 |  | 579030.4414 |  | 0
2026-07-01 | 580318.5182 |  | 580318.5182 |  | 0
2026-07-02 | 581606.595 |  | 581606.595 |  | 0
2026-07-03 | 582894.6719 |  | 582894.6719 |  | 0
2026-07-04 | 584182.7487 |  | 584182.7487 |  | 0
2026-07-05 | 585470.8255 |  | 585470.8255 |  | 0
2026-07-06 | 586758.9023 |  | 586758.9023 |  | 0
2026-07-07 | 588046.9791 |  | 588046.9791 |  | 0
2026-07-08 | 589335.0559 |  | 589335.0559 |  | 0
2026-07-09 | 590623.1328 |  | 590623.1328 |  | 0
2026-07-10 | 591911.2096 |  | 591911.2096 |  | 0
2026-07-11 | 593199.2864 |  | 593199.2864 |  | 0
2026-07-12 | 594487.3632 |  | 594487.3632 |  | 0
2026-07-13 | 595775.44 |  | 595775.44 |  | 0
2026-07-14 | 597063.5169 |  | 597063.5169 |  | 0
2026-07-15 | 598351.5937 |  | 598351.5937 |  | 0
2026-07-16 | 599639.6705 |  | 599639.6705 |  | 0
2026-07-17 | 600927.7473 |  | 600927.7473 |  | 0
2026-07-18 | 602215.8241 |  | 602215.8241 |  | 0
2026-07-19 | 603503.9009 |  | 603503.9009 |  | 0
2026-07-20 | 604791.9778 |  | 604791.9778 |  | 0
2026-07-21 | 606080.0546 |  | 606080.0546 |  | 0
2026-07-22 | 607368.1314 |  | 607368.1314 |  | 0
2026-07-23 | 608656.2082 |  | 608656.2082 |  | 0
2026-07-24 | 609944.285 |  | 609944.285 |  | 0
2026-07-25 | 611232.3619 |  | 611232.3619 |  | 0
2026-07-26 | 612520.4387 |  | 612520.4387 |  | 0
2026-07-27 | 613808.5155 |  | 613808.5155 |  | 0
2026-07-28 | 615096.5923 |  | 615096.5923 |  | 0
2026-07-29 | 616384.6691 |  | 616384.6691 |  | 0
2026-07-30 | 617672.7459 |  | 617672.7459 |  | 0
2026-07-31 | 618960.8228 |  | 618960.8228 |  | 0
2026-08-01 | 620248.8996 |  | 620248.8996 |  | 0
2026-08-02 | 621536.9764 |  | 621536.9764 |  | 0
2026-08-03 | 622825.0532 |  | 622825.0532 |  | 0
2026-08-04 | 624113.13 |  | 624113.13 |  | 0
2026-08-05 | 625401.2069 |  | 625401.2069 |  | 0
2026-08-06 | 626689.2837 |  | 626689.2837 |  | 0
2026-08-07 | 627977.3605 |  | 627977.3605 |  | 0
2026-08-08 | 629265.4373 |  | 629265.4373 |  | 0
2026-08-09 | 630553.5141 |  | 630553.5141 |  | 0
2026-08-10 | 631841.5909 |  | 631841.5909 |  | 0
2026-08-11 | 633129.6678 |  | 633129.6678 |  | 0
2026-08-12 | 634417.7446 |  | 634417.7446 |  | 0
2026-08-13 | 635598.4464 |  | 635598.4464 |  | 0
2026-08-14 | 636779.1481 |  | 636779.1481 |  | 0
2026-08-15 | 637959.8499 |  | 637959.8499 |  | 0
2026-08-16 | 639140.5517 |  | 639140.5517 |  | 0
2026-08-17 | 640321.2535 |  | 640321.2535 |  | 0
2026-08-18 | 641501.9552 |  | 641501.9552 |  | 0
2026-08-19 | 642682.657 |  | 642682.657 |  | 0
2026-08-20 | 643863.3588 |  | 643863.3588 |  | 0
2026-08-21 | 645044.0606 |  | 645044.0606 |  | 0
2026-08-22 | 646224.7623 |  | 646224.7623 |  | 0
2026-08-23 | 647405.4641 |  | 647405.4641 |  | 0
2026-08-24 | 648586.1659 |  | 648586.1659 |  | 0
2026-08-25 | 649766.8677 |  | 649766.8677 |  | 0
2026-08-26 | 650947.5694 |  | 650947.5694 |  | 0
2026-08-27 | 652128.2712 |  | 652128.2712 |  | 0
2026-08-28 | 653308.973 |  | 653308.973 |  | 0
2026-08-29 | 654489.6748 |  | 654489.6748 |  | 0
2026-08-30 | 655670.3766 |  | 655670.3766 |  | 0
2026-08-31 | 656851.0783 |  | 656851.0783 |  | 0
2026-09-01 | 658031.7801 |  | 658031.7801 |  | 0
2026-09-02 | 659212.4819 |  | 659212.4819 |  | 0
2026-09-03 | 660393.1837 |  | 660393.1837 |  | 0
2026-09-04 | 661573.8854 |  | 661573.8854 |  | 0
2026-09-05 | 662754.5872 |  | 662754.5872 |  | 0
2026-09-06 | 663935.289 |  | 663935.289 |  | 0
2026-09-07 | 665115.9908 |  | 665115.9908 |  | 0
2026-09-08 | 666296.6925 |  | 666296.6925 |  | 0
2026-09-09 | 667477.3943 |  | 667477.3943 |  | 0
2026-09-10 | 668658.0961 |  | 668658.0961 |  | 0
2026-09-11 | 669838.7979 |  | 669838.7979 |  | 0
2026-09-12 | 671019.4996 |  | 671019.4996 |  | 0
2026-09-13 | 672200.2014 |  | 672200.2014 |  | 0
2026-09-14 | 673380.9032 |  | 673380.9032 |  | 0
2026-09-15 | 674561.605 |  | 674561.605 |  | 0

## Travel&perdiem (Direct Cost)
Date | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Planned 5105 · Travel - Airfare (Direct) (Cumulative) | Actual 5105 · Travel - Airfare (Direct) (Cumulative) | Planned 5106 · Travel - Hotel (Direct) (Cumulative) | Actual 5106 · Travel - Hotel (Direct) (Cumulative) | Planned 5107 · Travel - Other (Direct) (Cumulative) | Actual 5107 · Travel - Other (Direct) (Cumulative) | Planned 5108 · Meals & entertainment (Direct) (Cumulative) | Actual 5108 · Meals & entertainment (Direct) (Cumulative) | Planned 5122 · Motor vehicle exp (Direct) (Cumulative) | Actual 5122 · Motor vehicle exp (Direct) (Cumulative) | Planned 5123 · Auto fuel (Direct) (Cumulative) | Actual 5123 · Auto fuel (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 143.0527 | 227.92 | 23.8421 | 0 | 23.8421 | 0 | 23.8421 | 18 | 23.8421 | 0 | 23.8421 | 0 | 23.8421 | 0
2025-06-26 | 286.1055 | 227.92 | 47.6842 | 0 | 47.6842 | 0 | 47.6842 | 18 | 47.6842 | 0 | 47.6842 | 0 | 47.6842 | 0
2025-06-27 | 429.1582 | 227.92 | 71.5264 | 0 | 71.5264 | 0 | 71.5264 | 18 | 71.5264 | 0 | 71.5264 | 0 | 71.5264 | 0
2025-06-28 | 572.211 | 227.92 | 95.3685 | 0 | 95.3685 | 0 | 95.3685 | 18 | 95.3685 | 0 | 95.3685 | 0 | 95.3685 | 0
2025-06-29 | 715.2637 | 227.92 | 119.2106 | 0 | 119.2106 | 0 | 119.2106 | 18 | 119.2106 | 0 | 119.2106 | 0 | 119.2106 | 0
2025-06-30 | 858.3164 | 227.92 | 143.0527 | 0 | 143.0527 | 0 | 143.0527 | 18 | 143.0527 | 0 | 143.0527 | 0 | 143.0527 | 0
2025-07-01 | 1001.3692 | 227.92 | 166.8949 | 0 | 166.8949 | 0 | 166.8949 | 18 | 166.8949 | 0 | 166.8949 | 0 | 166.8949 | 0
2025-07-02 | 1144.4219 | 227.92 | 190.737 | 0 | 190.737 | 0 | 190.737 | 18 | 190.737 | 0 | 190.737 | 0 | 190.737 | 0
2025-07-03 | 1287.4747 | 227.92 | 214.5791 | 0 | 214.5791 | 0 | 214.5791 | 18 | 214.5791 | 0 | 214.5791 | 0 | 214.5791 | 0
2025-07-04 | 1430.5274 | 227.92 | 238.4212 | 0 | 238.4212 | 0 | 238.4212 | 18 | 238.4212 | 0 | 238.4212 | 0 | 238.4212 | 0
2025-07-05 | 1573.5801 | 227.92 | 262.2634 | 0 | 262.2634 | 0 | 262.2634 | 18 | 262.2634 | 0 | 262.2634 | 0 | 262.2634 | 0
2025-07-06 | 1716.6329 | 227.92 | 286.1055 | 0 | 286.1055 | 0 | 286.1055 | 18 | 286.1055 | 0 | 286.1055 | 0 | 286.1055 | 0
2025-07-07 | 1859.6856 | 227.92 | 309.9476 | 0 | 309.9476 | 0 | 309.9476 | 18 | 309.9476 | 0 | 309.9476 | 0 | 309.9476 | 0
2025-07-08 | 2002.7384 | 227.92 | 333.7897 | 0 | 333.7897 | 0 | 333.7897 | 18 | 333.7897 | 0 | 333.7897 | 0 | 333.7897 | 0
2025-07-09 | 2145.7911 | 227.92 | 357.6319 | 0 | 357.6319 | 0 | 357.6319 | 18 | 357.6319 | 0 | 357.6319 | 0 | 357.6319 | 0
2025-07-10 | 2288.8438 | 227.92 | 381.474 | 0 | 381.474 | 0 | 381.474 | 18 | 381.474 | 0 | 381.474 | 0 | 381.474 | 0
2025-07-11 | 2431.8966 | 227.92 | 405.3161 | 0 | 405.3161 | 0 | 405.3161 | 18 | 405.3161 | 0 | 405.3161 | 0 | 405.3161 | 0
2025-07-12 | 2574.9493 | 227.92 | 429.1582 | 0 | 429.1582 | 0 | 429.1582 | 18 | 429.1582 | 0 | 429.1582 | 0 | 429.1582 | 0
2025-07-13 | 2718.0021 | 227.92 | 453.0003 | 0 | 453.0003 | 0 | 453.0003 | 18 | 453.0003 | 0 | 453.0003 | 0 | 453.0003 | 0
2025-07-14 | 2861.0548 | 1769.82 | 476.8425 | 1541.9 | 476.8425 | 0 | 476.8425 | 18 | 476.8425 | 0 | 476.8425 | 0 | 476.8425 | 0
2025-07-15 | 3004.1075 | 1769.82 | 500.6846 | 1541.9 | 500.6846 | 0 | 500.6846 | 18 | 500.6846 | 0 | 500.6846 | 0 | 500.6846 | 0
2025-07-16 | 3147.1603 | 1769.82 | 524.5267 | 1541.9 | 524.5267 | 0 | 524.5267 | 18 | 524.5267 | 0 | 524.5267 | 0 | 524.5267 | 0
2025-07-17 | 3290.213 | 1834.27 | 548.3688 | 1541.9 | 548.3688 | 0 | 548.3688 | 18 | 548.3688 | 0 | 548.3688 | 0 | 548.3688 | 0
2025-07-18 | 3433.2658 | 1861.41 | 572.211 | 1569.04 | 572.211 | 0 | 572.211 | 18 | 572.211 | 0 | 572.211 | 0 | 572.211 | 0
2025-07-19 | 3576.3185 | 1891.41 | 596.0531 | 1569.04 | 596.0531 | 0 | 596.0531 | 48 | 596.0531 | 0 | 596.0531 | 0 | 596.0531 | 0
2025-07-20 | 3719.3712 | 1891.41 | 619.8952 | 1569.04 | 619.8952 | 0 | 619.8952 | 48 | 619.8952 | 0 | 619.8952 | 0 | 619.8952 | 0
2025-07-21 | 3862.424 | 1891.41 | 643.7373 | 1569.04 | 643.7373 | 0 | 643.7373 | 48 | 643.7373 | 0 | 643.7373 | 0 | 643.7373 | 0
2025-07-22 | 4005.4767 | 1891.41 | 667.5795 | 1569.04 | 667.5795 | 0 | 667.5795 | 48 | 667.5795 | 0 | 667.5795 | 0 | 667.5795 | 0
2025-07-23 | 4148.5295 | 1891.41 | 691.4216 | 1569.04 | 691.4216 | 0 | 691.4216 | 48 | 691.4216 | 0 | 691.4216 | 0 | 691.4216 | 0
2025-07-24 | 4291.5822 | 1891.41 | 715.2637 | 1569.04 | 715.2637 | 0 | 715.2637 | 48 | 715.2637 | 0 | 715.2637 | 0 | 715.2637 | 0
2025-07-25 | 4434.6349 | 1891.41 | 739.1058 | 1569.04 | 739.1058 | 0 | 739.1058 | 48 | 739.1058 | 0 | 739.1058 | 0 | 739.1058 | 0
2025-07-26 | 4577.6877 | 1891.41 | 762.9479 | 1569.04 | 762.9479 | 0 | 762.9479 | 48 | 762.9479 | 0 | 762.9479 | 0 | 762.9479 | 0
2025-07-27 | 4720.7404 | 1891.41 | 786.7901 | 1569.04 | 786.7901 | 0 | 786.7901 | 48 | 786.7901 | 0 | 786.7901 | 0 | 786.7901 | 0
2025-07-28 | 4863.7932 | 1891.41 | 810.6322 | 1569.04 | 810.6322 | 0 | 810.6322 | 48 | 810.6322 | 0 | 810.6322 | 0 | 810.6322 | 0
2025-07-29 | 5006.8459 | 1891.41 | 834.4743 | 1569.04 | 834.4743 | 0 | 834.4743 | 48 | 834.4743 | 0 | 834.4743 | 0 | 834.4743 | 0
2025-07-30 | 5149.8987 | 1891.41 | 858.3164 | 1569.04 | 858.3164 | 0 | 858.3164 | 48 | 858.3164 | 0 | 858.3164 | 0 | 858.3164 | 0
2025-07-31 | 5292.9514 | 1891.41 | 882.1586 | 1569.04 | 882.1586 | 0 | 882.1586 | 48 | 882.1586 | 0 | 882.1586 | 0 | 882.1586 | 0
2025-08-01 | 5436.0041 | 1891.41 | 906.0007 | 1569.04 | 906.0007 | 0 | 906.0007 | 48 | 906.0007 | 0 | 906.0007 | 0 | 906.0007 | 0
2025-08-02 | 5579.0569 | 1891.41 | 929.8428 | 1569.04 | 929.8428 | 0 | 929.8428 | 48 | 929.8428 | 0 | 929.8428 | 0 | 929.8428 | 0
2025-08-03 | 5722.1096 | 1891.41 | 953.6849 | 1569.04 | 953.6849 | 0 | 953.6849 | 48 | 953.6849 | 0 | 953.6849 | 0 | 953.6849 | 0
2025-08-04 | 5865.1624 | 1891.41 | 977.5271 | 1569.04 | 977.5271 | 0 | 977.5271 | 48 | 977.5271 | 0 | 977.5271 | 0 | 977.5271 | 0
2025-08-05 | 6008.2151 | 1891.41 | 1001.3692 | 1569.04 | 1001.3692 | 0 | 1001.3692 | 48 | 1001.3692 | 0 | 1001.3692 | 0 | 1001.3692 | 0
2025-08-06 | 6151.2678 | 1891.41 | 1025.2113 | 1569.04 | 1025.2113 | 0 | 1025.2113 | 48 | 1025.2113 | 0 | 1025.2113 | 0 | 1025.2113 | 0
2025-08-07 | 6294.3206 | 1891.41 | 1049.0534 | 1569.04 | 1049.0534 | 0 | 1049.0534 | 48 | 1049.0534 | 0 | 1049.0534 | 0 | 1049.0534 | 0
2025-08-08 | 6437.3733 | 1891.41 | 1072.8956 | 1569.04 | 1072.8956 | 0 | 1072.8956 | 48 | 1072.8956 | 0 | 1072.8956 | 0 | 1072.8956 | 0
2025-08-09 | 6580.4261 | 1891.41 | 1096.7377 | 1569.04 | 1096.7377 | 0 | 1096.7377 | 48 | 1096.7377 | 0 | 1096.7377 | 0 | 1096.7377 | 0
2025-08-10 | 6723.4788 | 1891.41 | 1120.5798 | 1569.04 | 1120.5798 | 0 | 1120.5798 | 48 | 1120.5798 | 0 | 1120.5798 | 0 | 1120.5798 | 0
2025-08-11 | 6866.5315 | 1891.41 | 1144.4219 | 1569.04 | 1144.4219 | 0 | 1144.4219 | 48 | 1144.4219 | 0 | 1144.4219 | 0 | 1144.4219 | 0
2025-08-12 | 7009.5843 | 1891.41 | 1168.264 | 1569.04 | 1168.264 | 0 | 1168.264 | 48 | 1168.264 | 0 | 1168.264 | 0 | 1168.264 | 0
2025-08-13 | 7152.637 | 1891.41 | 1192.1062 | 1569.04 | 1192.1062 | 0 | 1192.1062 | 48 | 1192.1062 | 0 | 1192.1062 | 0 | 1192.1062 | 0
2025-08-14 | 7295.6898 | 1891.41 | 1215.9483 | 1569.04 | 1215.9483 | 0 | 1215.9483 | 48 | 1215.9483 | 0 | 1215.9483 | 0 | 1215.9483 | 0
2025-08-15 | 7438.7425 | 1891.41 | 1239.7904 | 1569.04 | 1239.7904 | 0 | 1239.7904 | 48 | 1239.7904 | 0 | 1239.7904 | 0 | 1239.7904 | 0
2025-08-16 | 7581.7952 | 1891.41 | 1263.6325 | 1569.04 | 1263.6325 | 0 | 1263.6325 | 48 | 1263.6325 | 0 | 1263.6325 | 0 | 1263.6325 | 0
2025-08-17 | 7724.848 | 1891.41 | 1287.4747 | 1569.04 | 1287.4747 | 0 | 1287.4747 | 48 | 1287.4747 | 0 | 1287.4747 | 0 | 1287.4747 | 0
2025-08-18 | 7867.9007 | 1891.41 | 1311.3168 | 1569.04 | 1311.3168 | 0 | 1311.3168 | 48 | 1311.3168 | 0 | 1311.3168 | 0 | 1311.3168 | 0
2025-08-19 | 8010.9535 | 1891.41 | 1335.1589 | 1569.04 | 1335.1589 | 0 | 1335.1589 | 48 | 1335.1589 | 0 | 1335.1589 | 0 | 1335.1589 | 0
2025-08-20 | 8154.0062 | 2030.22 | 1359.001 | 1569.04 | 1359.001 | 0 | 1359.001 | 48 | 1359.001 | 0 | 1359.001 | 0 | 1359.001 | 0
2025-08-21 | 8297.0589 | 2030.22 | 1382.8432 | 1569.04 | 1382.8432 | 0 | 1382.8432 | 48 | 1382.8432 | 0 | 1382.8432 | 0 | 1382.8432 | 0
2025-08-22 | 8440.1117 | 2130.22 | 1406.6853 | 1569.04 | 1406.6853 | 0 | 1406.6853 | 48 | 1406.6853 | 100 | 1406.6853 | 0 | 1406.6853 | 0
2025-08-23 | 8583.1644 | 2130.22 | 1430.5274 | 1569.04 | 1430.5274 | 0 | 1430.5274 | 48 | 1430.5274 | 100 | 1430.5274 | 0 | 1430.5274 | 0
2025-08-24 | 8726.2172 | 2130.22 | 1454.3695 | 1569.04 | 1454.3695 | 0 | 1454.3695 | 48 | 1454.3695 | 100 | 1454.3695 | 0 | 1454.3695 | 0
2025-08-25 | 8869.2699 | 2130.22 | 1478.2116 | 1569.04 | 1478.2116 | 0 | 1478.2116 | 48 | 1478.2116 | 100 | 1478.2116 | 0 | 1478.2116 | 0
2025-08-26 | 9012.3226 | 2130.22 | 1502.0538 | 1569.04 | 1502.0538 | 0 | 1502.0538 | 48 | 1502.0538 | 100 | 1502.0538 | 0 | 1502.0538 | 0
2025-08-27 | 9155.3754 | 2130.22 | 1525.8959 | 1569.04 | 1525.8959 | 0 | 1525.8959 | 48 | 1525.8959 | 100 | 1525.8959 | 0 | 1525.8959 | 0
2025-08-28 | 9298.4281 | 2130.22 | 1549.738 | 1569.04 | 1549.738 | 0 | 1549.738 | 48 | 1549.738 | 100 | 1549.738 | 0 | 1549.738 | 0
2025-08-29 | 9441.4809 | 2130.22 | 1573.5801 | 1569.04 | 1573.5801 | 0 | 1573.5801 | 48 | 1573.5801 | 100 | 1573.5801 | 0 | 1573.5801 | 0
2025-08-30 | 9584.5336 | 2130.22 | 1597.4223 | 1569.04 | 1597.4223 | 0 | 1597.4223 | 48 | 1597.4223 | 100 | 1597.4223 | 0 | 1597.4223 | 0
2025-08-31 | 9727.5863 | 2130.22 | 1621.2644 | 1569.04 | 1621.2644 | 0 | 1621.2644 | 48 | 1621.2644 | 100 | 1621.2644 | 0 | 1621.2644 | 0
2025-09-01 | 9870.6391 | 2130.22 | 1645.1065 | 1569.04 | 1645.1065 | 0 | 1645.1065 | 48 | 1645.1065 | 100 | 1645.1065 | 0 | 1645.1065 | 0
2025-09-02 | 10013.6918 | 2130.22 | 1668.9486 | 1569.04 | 1668.9486 | 0 | 1668.9486 | 48 | 1668.9486 | 100 | 1668.9486 | 0 | 1668.9486 | 0
2025-09-03 | 10156.7446 | 2130.22 | 1692.7908 | 1569.04 | 1692.7908 | 0 | 1692.7908 | 48 | 1692.7908 | 100 | 1692.7908 | 0 | 1692.7908 | 0
2025-09-04 | 10299.7973 | 2130.22 | 1716.6329 | 1569.04 | 1716.6329 | 0 | 1716.6329 | 48 | 1716.6329 | 100 | 1716.6329 | 0 | 1716.6329 | 0
2025-09-05 | 10442.85 | 2130.22 | 1740.475 | 1569.04 | 1740.475 | 0 | 1740.475 | 48 | 1740.475 | 100 | 1740.475 | 0 | 1740.475 | 0
2025-09-06 | 10585.9028 | 2130.22 | 1764.3171 | 1569.04 | 1764.3171 | 0 | 1764.3171 | 48 | 1764.3171 | 100 | 1764.3171 | 0 | 1764.3171 | 0
2025-09-07 | 10728.9555 | 2130.22 | 1788.1593 | 1569.04 | 1788.1593 | 0 | 1788.1593 | 48 | 1788.1593 | 100 | 1788.1593 | 0 | 1788.1593 | 0
2025-09-08 | 10872.0083 | 2130.22 | 1812.0014 | 1569.04 | 1812.0014 | 0 | 1812.0014 | 48 | 1812.0014 | 100 | 1812.0014 | 0 | 1812.0014 | 0
2025-09-09 | 11015.061 | 2130.22 | 1835.8435 | 1569.04 | 1835.8435 | 0 | 1835.8435 | 48 | 1835.8435 | 100 | 1835.8435 | 0 | 1835.8435 | 0
2025-09-10 | 11158.1137 | 2130.22 | 1859.6856 | 1569.04 | 1859.6856 | 0 | 1859.6856 | 48 | 1859.6856 | 100 | 1859.6856 | 0 | 1859.6856 | 0
2025-09-11 | 11301.1665 | 2130.22 | 1883.5277 | 1569.04 | 1883.5277 | 0 | 1883.5277 | 48 | 1883.5277 | 100 | 1883.5277 | 0 | 1883.5277 | 0
2025-09-12 | 11444.2192 | 2241.16 | 1907.3699 | 1569.04 | 1907.3699 | 0 | 1907.3699 | 158.94 | 1907.3699 | 100 | 1907.3699 | 0 | 1907.3699 | 0
2025-09-13 | 11587.272 | 2241.16 | 1931.212 | 1569.04 | 1931.212 | 0 | 1931.212 | 158.94 | 1931.212 | 100 | 1931.212 | 0 | 1931.212 | 0
2025-09-14 | 11730.3247 | 2241.16 | 1955.0541 | 1569.04 | 1955.0541 | 0 | 1955.0541 | 158.94 | 1955.0541 | 100 | 1955.0541 | 0 | 1955.0541 | 0
2025-09-15 | 11873.3774 | 2691.16 | 1978.8962 | 1569.04 | 1978.8962 | 0 | 1978.8962 | 158.94 | 1978.8962 | 550 | 1978.8962 | 0 | 1978.8962 | 0
2025-09-16 | 12016.4302 | 2691.16 | 2002.7384 | 1569.04 | 2002.7384 | 0 | 2002.7384 | 158.94 | 2002.7384 | 550 | 2002.7384 | 0 | 2002.7384 | 0
2025-09-17 | 12159.4829 | 2691.16 | 2026.5805 | 1569.04 | 2026.5805 | 0 | 2026.5805 | 158.94 | 2026.5805 | 550 | 2026.5805 | 0 | 2026.5805 | 0
2025-09-18 | 12302.5357 | 2691.16 | 2050.4226 | 1569.04 | 2050.4226 | 0 | 2050.4226 | 158.94 | 2050.4226 | 550 | 2050.4226 | 0 | 2050.4226 | 0
2025-09-19 | 12445.5884 | 2691.16 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 550 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-20 | 12445.5884 | 2691.16 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 550 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-21 | 12445.5884 | 2691.16 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 550 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-22 | 13471.6043 | 2991.16 | 2245.2674 | 1569.04 | 2245.2674 | 0 | 2245.2674 | 158.94 | 2245.2674 | 850 | 2245.2674 | 0 | 2245.2674 | 0
2025-09-23 | 14497.6202 | 2991.16 | 2416.27 | 1569.04 | 2416.27 | 0 | 2416.27 | 158.94 | 2416.27 | 850 | 2416.27 | 0 | 2416.27 | 0
2025-09-24 | 15523.6361 | 2991.16 | 2587.2727 | 1569.04 | 2587.2727 | 0 | 2587.2727 | 158.94 | 2587.2727 | 850 | 2587.2727 | 0 | 2587.2727 | 0
2025-09-25 | 16549.6521 | 2991.16 | 2758.2753 | 1569.04 | 2758.2753 | 0 | 2758.2753 | 158.94 | 2758.2753 | 850 | 2758.2753 | 0 | 2758.2753 | 0
2025-09-26 | 17575.668 | 2991.16 | 2929.278 | 1569.04 | 2929.278 | 0 | 2929.278 | 158.94 | 2929.278 | 850 | 2929.278 | 0 | 2929.278 | 0
2025-09-27 | 18601.6839 | 2991.16 | 3100.2806 | 1569.04 | 3100.2806 | 0 | 3100.2806 | 158.94 | 3100.2806 | 850 | 3100.2806 | 0 | 3100.2806 | 0
2025-09-28 | 19627.6998 | 2991.16 | 3271.2833 | 1569.04 | 3271.2833 | 0 | 3271.2833 | 158.94 | 3271.2833 | 850 | 3271.2833 | 0 | 3271.2833 | 0
2025-09-29 | 20653.7157 | 4391.16 | 3442.286 | 1569.04 | 3442.286 | 0 | 3442.286 | 158.94 | 3442.286 | 2250 | 3442.286 | 0 | 3442.286 | 0
2025-09-30 | 21679.7316 | 4391.16 | 3613.2886 | 1569.04 | 3613.2886 | 0 | 3613.2886 | 158.94 | 3613.2886 | 2250 | 3613.2886 | 0 | 3613.2886 | 0
2025-10-01 | 22705.7475 | 4391.16 | 3784.2913 | 1569.04 | 3784.2913 | 0 | 3784.2913 | 158.94 | 3784.2913 | 2250 | 3784.2913 | 0 | 3784.2913 | 0
2025-10-02 | 23731.7635 | 4391.16 | 3955.2939 | 1569.04 | 3955.2939 | 0 | 3955.2939 | 158.94 | 3955.2939 | 2250 | 3955.2939 | 0 | 3955.2939 | 0
2025-10-03 | 24757.7794 | 4891.16 | 4126.2966 | 1569.04 | 4126.2966 | 0 | 4126.2966 | 158.94 | 4126.2966 | 2750 | 4126.2966 | 0 | 4126.2966 | 0
2025-10-04 | 25783.7953 | 4891.16 | 4297.2992 | 1569.04 | 4297.2992 | 0 | 4297.2992 | 158.94 | 4297.2992 | 2750 | 4297.2992 | 0 | 4297.2992 | 0
2025-10-05 | 26809.8112 | 4891.16 | 4468.3019 | 1569.04 | 4468.3019 | 0 | 4468.3019 | 158.94 | 4468.3019 | 2750 | 4468.3019 | 0 | 4468.3019 | 0
2025-10-06 | 27835.8271 | 4891.16 | 4639.3045 | 1569.04 | 4639.3045 | 0 | 4639.3045 | 158.94 | 4639.3045 | 2750 | 4639.3045 | 0 | 4639.3045 | 0
2025-10-07 | 28861.843 | 4891.16 | 4810.3072 | 1569.04 | 4810.3072 | 0 | 4810.3072 | 158.94 | 4810.3072 | 2750 | 4810.3072 | 0 | 4810.3072 | 0
2025-10-08 | 29887.8589 | 4891.16 | 4981.3098 | 1569.04 | 4981.3098 | 0 | 4981.3098 | 158.94 | 4981.3098 | 2750 | 4981.3098 | 0 | 4981.3098 | 0
2025-10-09 | 30913.8749 | 4891.16 | 5152.3125 | 1569.04 | 5152.3125 | 0 | 5152.3125 | 158.94 | 5152.3125 | 2750 | 5152.3125 | 0 | 5152.3125 | 0
2025-10-10 | 31939.8908 | 4891.16 | 5323.3151 | 1569.04 | 5323.3151 | 0 | 5323.3151 | 158.94 | 5323.3151 | 2750 | 5323.3151 | 0 | 5323.3151 | 0
2025-10-11 | 32965.9067 | 4891.16 | 5494.3178 | 1569.04 | 5494.3178 | 0 | 5494.3178 | 158.94 | 5494.3178 | 2750 | 5494.3178 | 0 | 5494.3178 | 0
2025-10-12 | 33991.9226 | 4891.16 | 5665.3204 | 1569.04 | 5665.3204 | 0 | 5665.3204 | 158.94 | 5665.3204 | 2750 | 5665.3204 | 0 | 5665.3204 | 0
2025-10-13 | 35017.9385 |  | 5836.3231 |  | 5836.3231 |  | 5836.3231 |  | 5836.3231 |  | 5836.3231 |  | 5836.3231
2025-10-14 | 36043.9544 |  | 6007.3257 |  | 6007.3257 |  | 6007.3257 |  | 6007.3257 |  | 6007.3257 |  | 6007.3257
2025-10-15 | 37069.9703 |  | 6178.3284 |  | 6178.3284 |  | 6178.3284 |  | 6178.3284 |  | 6178.3284 |  | 6178.3284
2025-10-16 | 38095.9862 |  | 6349.331 |  | 6349.331 |  | 6349.331 |  | 6349.331 |  | 6349.331 |  | 6349.331
2025-10-17 | 39122.0022 |  | 6520.3337 |  | 6520.3337 |  | 6520.3337 |  | 6520.3337 |  | 6520.3337 |  | 6520.3337
2025-10-18 | 40148.0181 |  | 6691.3363 |  | 6691.3363 |  | 6691.3363 |  | 6691.3363 |  | 6691.3363 |  | 6691.3363
2025-10-19 | 41174.034 |  | 6862.339 |  | 6862.339 |  | 6862.339 |  | 6862.339 |  | 6862.339 |  | 6862.339
2025-10-20 | 42200.0499 |  | 7033.3417 |  | 7033.3417 |  | 7033.3417 |  | 7033.3417 |  | 7033.3417 |  | 7033.3417
2025-10-21 | 43226.0658 |  | 7204.3443 |  | 7204.3443 |  | 7204.3443 |  | 7204.3443 |  | 7204.3443 |  | 7204.3443
2025-10-22 | 44252.0817 |  | 7375.347 |  | 7375.347 |  | 7375.347 |  | 7375.347 |  | 7375.347 |  | 7375.347
2025-10-23 | 45278.0976 |  | 7546.3496 |  | 7546.3496 |  | 7546.3496 |  | 7546.3496 |  | 7546.3496 |  | 7546.3496
2025-10-24 | 46304.1136 |  | 7717.3523 |  | 7717.3523 |  | 7717.3523 |  | 7717.3523 |  | 7717.3523 |  | 7717.3523
2025-10-25 | 47330.1295 |  | 7888.3549 |  | 7888.3549 |  | 7888.3549 |  | 7888.3549 |  | 7888.3549 |  | 7888.3549
2025-10-26 | 48356.1454 |  | 8059.3576 |  | 8059.3576 |  | 8059.3576 |  | 8059.3576 |  | 8059.3576 |  | 8059.3576
2025-10-27 | 49382.1613 |  | 8230.3602 |  | 8230.3602 |  | 8230.3602 |  | 8230.3602 |  | 8230.3602 |  | 8230.3602
2025-10-28 | 50408.1772 |  | 8401.3629 |  | 8401.3629 |  | 8401.3629 |  | 8401.3629 |  | 8401.3629 |  | 8401.3629
2025-10-29 | 51434.1931 |  | 8572.3655 |  | 8572.3655 |  | 8572.3655 |  | 8572.3655 |  | 8572.3655 |  | 8572.3655
2025-10-30 | 52460.209 |  | 8743.3682 |  | 8743.3682 |  | 8743.3682 |  | 8743.3682 |  | 8743.3682 |  | 8743.3682
2025-10-31 | 53486.225 |  | 8914.3708 |  | 8914.3708 |  | 8914.3708 |  | 8914.3708 |  | 8914.3708 |  | 8914.3708
2025-11-01 | 54512.2409 |  | 9085.3735 |  | 9085.3735 |  | 9085.3735 |  | 9085.3735 |  | 9085.3735 |  | 9085.3735
2025-11-02 | 55538.2568 |  | 9256.3761 |  | 9256.3761 |  | 9256.3761 |  | 9256.3761 |  | 9256.3761 |  | 9256.3761
2025-11-03 | 56564.2727 |  | 9427.3788 |  | 9427.3788 |  | 9427.3788 |  | 9427.3788 |  | 9427.3788 |  | 9427.3788
2025-11-04 | 57590.2886 |  | 9598.3814 |  | 9598.3814 |  | 9598.3814 |  | 9598.3814 |  | 9598.3814 |  | 9598.3814
2025-11-05 | 58616.3045 |  | 9769.3841 |  | 9769.3841 |  | 9769.3841 |  | 9769.3841 |  | 9769.3841 |  | 9769.3841
2025-11-06 | 59642.3204 |  | 9940.3867 |  | 9940.3867 |  | 9940.3867 |  | 9940.3867 |  | 9940.3867 |  | 9940.3867
2025-11-07 | 60668.3363 |  | 10111.3894 |  | 10111.3894 |  | 10111.3894 |  | 10111.3894 |  | 10111.3894 |  | 10111.3894
2025-11-08 | 61694.3523 |  | 10282.392 |  | 10282.392 |  | 10282.392 |  | 10282.392 |  | 10282.392 |  | 10282.392
2025-11-09 | 62720.3682 |  | 10453.3947 |  | 10453.3947 |  | 10453.3947 |  | 10453.3947 |  | 10453.3947 |  | 10453.3947
2025-11-10 | 63746.3841 |  | 10624.3973 |  | 10624.3973 |  | 10624.3973 |  | 10624.3973 |  | 10624.3973 |  | 10624.3973
2025-11-11 | 64772.4 |  | 10795.4 |  | 10795.4 |  | 10795.4 |  | 10795.4 |  | 10795.4 |  | 10795.4
2025-11-12 | 65374.5825 |  | 10895.7638 |  | 10895.7638 |  | 10895.7638 |  | 10895.7638 |  | 10895.7638 |  | 10895.7638
2025-11-13 | 65976.7651 |  | 10996.1275 |  | 10996.1275 |  | 10996.1275 |  | 10996.1275 |  | 10996.1275 |  | 10996.1275
2025-11-14 | 66578.9476 |  | 11096.4913 |  | 11096.4913 |  | 11096.4913 |  | 11096.4913 |  | 11096.4913 |  | 11096.4913
2025-11-15 | 67181.1302 |  | 11196.855 |  | 11196.855 |  | 11196.855 |  | 11196.855 |  | 11196.855 |  | 11196.855
2025-11-16 | 67783.3127 |  | 11297.2188 |  | 11297.2188 |  | 11297.2188 |  | 11297.2188 |  | 11297.2188 |  | 11297.2188
2025-11-17 | 68385.4952 |  | 11397.5825 |  | 11397.5825 |  | 11397.5825 |  | 11397.5825 |  | 11397.5825 |  | 11397.5825
2025-11-18 | 68987.6778 |  | 11497.9463 |  | 11497.9463 |  | 11497.9463 |  | 11497.9463 |  | 11497.9463 |  | 11497.9463
2025-11-19 | 69589.8603 |  | 11598.3101 |  | 11598.3101 |  | 11598.3101 |  | 11598.3101 |  | 11598.3101 |  | 11598.3101
2025-11-20 | 70192.0429 |  | 11698.6738 |  | 11698.6738 |  | 11698.6738 |  | 11698.6738 |  | 11698.6738 |  | 11698.6738
2025-11-21 | 70794.2254 |  | 11799.0376 |  | 11799.0376 |  | 11799.0376 |  | 11799.0376 |  | 11799.0376 |  | 11799.0376
2025-11-22 | 71396.4079 |  | 11899.4013 |  | 11899.4013 |  | 11899.4013 |  | 11899.4013 |  | 11899.4013 |  | 11899.4013
2025-11-23 | 71998.5905 |  | 11999.7651 |  | 11999.7651 |  | 11999.7651 |  | 11999.7651 |  | 11999.7651 |  | 11999.7651
2025-11-24 | 72600.773 |  | 12100.1288 |  | 12100.1288 |  | 12100.1288 |  | 12100.1288 |  | 12100.1288 |  | 12100.1288
2025-11-25 | 73202.9556 |  | 12200.4926 |  | 12200.4926 |  | 12200.4926 |  | 12200.4926 |  | 12200.4926 |  | 12200.4926
2025-11-26 | 73805.1381 |  | 12300.8563 |  | 12300.8563 |  | 12300.8563 |  | 12300.8563 |  | 12300.8563 |  | 12300.8563
2025-11-27 | 74407.3206 |  | 12401.2201 |  | 12401.2201 |  | 12401.2201 |  | 12401.2201 |  | 12401.2201 |  | 12401.2201
2025-11-28 | 75009.5032 |  | 12501.5839 |  | 12501.5839 |  | 12501.5839 |  | 12501.5839 |  | 12501.5839 |  | 12501.5839
2025-11-29 | 75611.6857 |  | 12601.9476 |  | 12601.9476 |  | 12601.9476 |  | 12601.9476 |  | 12601.9476 |  | 12601.9476
2025-11-30 | 76213.8683 |  | 12702.3114 |  | 12702.3114 |  | 12702.3114 |  | 12702.3114 |  | 12702.3114 |  | 12702.3114
2025-12-01 | 76816.0508 |  | 12802.6751 |  | 12802.6751 |  | 12802.6751 |  | 12802.6751 |  | 12802.6751 |  | 12802.6751
2025-12-02 | 77418.2333 |  | 12903.0389 |  | 12903.0389 |  | 12903.0389 |  | 12903.0389 |  | 12903.0389 |  | 12903.0389
2025-12-03 | 78020.4159 |  | 13003.4026 |  | 13003.4026 |  | 13003.4026 |  | 13003.4026 |  | 13003.4026 |  | 13003.4026
2025-12-04 | 78622.5984 |  | 13103.7664 |  | 13103.7664 |  | 13103.7664 |  | 13103.7664 |  | 13103.7664 |  | 13103.7664
2025-12-05 | 79224.781 |  | 13204.1302 |  | 13204.1302 |  | 13204.1302 |  | 13204.1302 |  | 13204.1302 |  | 13204.1302
2025-12-06 | 79826.9635 |  | 13304.4939 |  | 13304.4939 |  | 13304.4939 |  | 13304.4939 |  | 13304.4939 |  | 13304.4939
2025-12-07 | 80429.146 |  | 13404.8577 |  | 13404.8577 |  | 13404.8577 |  | 13404.8577 |  | 13404.8577 |  | 13404.8577
2025-12-08 | 81031.3286 |  | 13505.2214 |  | 13505.2214 |  | 13505.2214 |  | 13505.2214 |  | 13505.2214 |  | 13505.2214
2025-12-09 | 81633.5111 |  | 13605.5852 |  | 13605.5852 |  | 13605.5852 |  | 13605.5852 |  | 13605.5852 |  | 13605.5852
2025-12-10 | 82235.6937 |  | 13705.9489 |  | 13705.9489 |  | 13705.9489 |  | 13705.9489 |  | 13705.9489 |  | 13705.9489
2025-12-11 | 82837.8762 |  | 13806.3127 |  | 13806.3127 |  | 13806.3127 |  | 13806.3127 |  | 13806.3127 |  | 13806.3127
2025-12-12 | 83440.0587 |  | 13906.6765 |  | 13906.6765 |  | 13906.6765 |  | 13906.6765 |  | 13906.6765 |  | 13906.6765
2025-12-13 | 84042.2413 |  | 14007.0402 |  | 14007.0402 |  | 14007.0402 |  | 14007.0402 |  | 14007.0402 |  | 14007.0402
2025-12-14 | 84644.4238 |  | 14107.404 |  | 14107.404 |  | 14107.404 |  | 14107.404 |  | 14107.404 |  | 14107.404
2025-12-15 | 85246.6063 |  | 14207.7677 |  | 14207.7677 |  | 14207.7677 |  | 14207.7677 |  | 14207.7677 |  | 14207.7677
2025-12-16 | 85848.7889 |  | 14308.1315 |  | 14308.1315 |  | 14308.1315 |  | 14308.1315 |  | 14308.1315 |  | 14308.1315
2025-12-17 | 86450.9714 |  | 14408.4952 |  | 14408.4952 |  | 14408.4952 |  | 14408.4952 |  | 14408.4952 |  | 14408.4952
2025-12-18 | 87053.154 |  | 14508.859 |  | 14508.859 |  | 14508.859 |  | 14508.859 |  | 14508.859 |  | 14508.859
2025-12-19 | 87655.3365 |  | 14609.2228 |  | 14609.2228 |  | 14609.2228 |  | 14609.2228 |  | 14609.2228 |  | 14609.2228
2025-12-20 | 88257.519 |  | 14709.5865 |  | 14709.5865 |  | 14709.5865 |  | 14709.5865 |  | 14709.5865 |  | 14709.5865
2025-12-21 | 88859.7016 |  | 14809.9503 |  | 14809.9503 |  | 14809.9503 |  | 14809.9503 |  | 14809.9503 |  | 14809.9503
2025-12-22 | 89461.8841 |  | 14910.314 |  | 14910.314 |  | 14910.314 |  | 14910.314 |  | 14910.314 |  | 14910.314
2025-12-23 | 90064.0667 |  | 15010.6778 |  | 15010.6778 |  | 15010.6778 |  | 15010.6778 |  | 15010.6778 |  | 15010.6778
2025-12-24 | 90666.2492 |  | 15111.0415 |  | 15111.0415 |  | 15111.0415 |  | 15111.0415 |  | 15111.0415 |  | 15111.0415
2025-12-25 | 91268.4317 |  | 15211.4053 |  | 15211.4053 |  | 15211.4053 |  | 15211.4053 |  | 15211.4053 |  | 15211.4053
2025-12-26 | 91870.6143 |  | 15311.769 |  | 15311.769 |  | 15311.769 |  | 15311.769 |  | 15311.769 |  | 15311.769
2025-12-27 | 92472.7968 |  | 15412.1328 |  | 15412.1328 |  | 15412.1328 |  | 15412.1328 |  | 15412.1328 |  | 15412.1328
2025-12-28 | 93074.9794 |  | 15512.4966 |  | 15512.4966 |  | 15512.4966 |  | 15512.4966 |  | 15512.4966 |  | 15512.4966
2025-12-29 | 93677.1619 |  | 15612.8603 |  | 15612.8603 |  | 15612.8603 |  | 15612.8603 |  | 15612.8603 |  | 15612.8603
2025-12-30 | 94279.3444 |  | 15713.2241 |  | 15713.2241 |  | 15713.2241 |  | 15713.2241 |  | 15713.2241 |  | 15713.2241
2025-12-31 | 94881.527 |  | 15813.5878 |  | 15813.5878 |  | 15813.5878 |  | 15813.5878 |  | 15813.5878 |  | 15813.5878
2026-01-01 | 95483.7095 |  | 15913.9516 |  | 15913.9516 |  | 15913.9516 |  | 15913.9516 |  | 15913.9516 |  | 15913.9516
2026-01-02 | 96085.8921 |  | 16014.3153 |  | 16014.3153 |  | 16014.3153 |  | 16014.3153 |  | 16014.3153 |  | 16014.3153
2026-01-03 | 96688.0746 |  | 16114.6791 |  | 16114.6791 |  | 16114.6791 |  | 16114.6791 |  | 16114.6791 |  | 16114.6791
2026-01-04 | 97290.2571 |  | 16215.0429 |  | 16215.0429 |  | 16215.0429 |  | 16215.0429 |  | 16215.0429 |  | 16215.0429
2026-01-05 | 97892.4397 |  | 16315.4066 |  | 16315.4066 |  | 16315.4066 |  | 16315.4066 |  | 16315.4066 |  | 16315.4066
2026-01-06 | 98494.6222 |  | 16415.7704 |  | 16415.7704 |  | 16415.7704 |  | 16415.7704 |  | 16415.7704 |  | 16415.7704
2026-01-07 | 99096.8048 |  | 16516.1341 |  | 16516.1341 |  | 16516.1341 |  | 16516.1341 |  | 16516.1341 |  | 16516.1341
2026-01-08 | 99698.9873 |  | 16616.4979 |  | 16616.4979 |  | 16616.4979 |  | 16616.4979 |  | 16616.4979 |  | 16616.4979
2026-01-09 | 100301.1698 |  | 16716.8616 |  | 16716.8616 |  | 16716.8616 |  | 16716.8616 |  | 16716.8616 |  | 16716.8616
2026-01-10 | 100903.3524 |  | 16817.2254 |  | 16817.2254 |  | 16817.2254 |  | 16817.2254 |  | 16817.2254 |  | 16817.2254
2026-01-11 | 101505.5349 |  | 16917.5892 |  | 16917.5892 |  | 16917.5892 |  | 16917.5892 |  | 16917.5892 |  | 16917.5892
2026-01-12 | 102107.7175 |  | 17017.9529 |  | 17017.9529 |  | 17017.9529 |  | 17017.9529 |  | 17017.9529 |  | 17017.9529
2026-01-13 | 102709.9 |  | 17118.3167 |  | 17118.3167 |  | 17118.3167 |  | 17118.3167 |  | 17118.3167 |  | 17118.3167
2026-01-14 | 103312.0825 |  | 17218.6804 |  | 17218.6804 |  | 17218.6804 |  | 17218.6804 |  | 17218.6804 |  | 17218.6804
2026-01-15 | 103914.2651 |  | 17319.0442 |  | 17319.0442 |  | 17319.0442 |  | 17319.0442 |  | 17319.0442 |  | 17319.0442
2026-01-16 | 104516.4476 |  | 17419.4079 |  | 17419.4079 |  | 17419.4079 |  | 17419.4079 |  | 17419.4079 |  | 17419.4079
2026-01-17 | 105118.6302 |  | 17519.7717 |  | 17519.7717 |  | 17519.7717 |  | 17519.7717 |  | 17519.7717 |  | 17519.7717
2026-01-18 | 105720.8127 |  | 17620.1354 |  | 17620.1354 |  | 17620.1354 |  | 17620.1354 |  | 17620.1354 |  | 17620.1354
2026-01-19 | 106322.9952 |  | 17720.4992 |  | 17720.4992 |  | 17720.4992 |  | 17720.4992 |  | 17720.4992 |  | 17720.4992
2026-01-20 | 106925.1778 |  | 17820.863 |  | 17820.863 |  | 17820.863 |  | 17820.863 |  | 17820.863 |  | 17820.863
2026-01-21 | 107527.3603 |  | 17921.2267 |  | 17921.2267 |  | 17921.2267 |  | 17921.2267 |  | 17921.2267 |  | 17921.2267
2026-01-22 | 108129.5429 |  | 18021.5905 |  | 18021.5905 |  | 18021.5905 |  | 18021.5905 |  | 18021.5905 |  | 18021.5905
2026-01-23 | 108731.7254 |  | 18121.9542 |  | 18121.9542 |  | 18121.9542 |  | 18121.9542 |  | 18121.9542 |  | 18121.9542
2026-01-24 | 109333.9079 |  | 18222.318 |  | 18222.318 |  | 18222.318 |  | 18222.318 |  | 18222.318 |  | 18222.318
2026-01-25 | 109936.0905 |  | 18322.6817 |  | 18322.6817 |  | 18322.6817 |  | 18322.6817 |  | 18322.6817 |  | 18322.6817
2026-01-26 | 110538.273 |  | 18423.0455 |  | 18423.0455 |  | 18423.0455 |  | 18423.0455 |  | 18423.0455 |  | 18423.0455
2026-01-27 | 111140.4556 |  | 18523.4093 |  | 18523.4093 |  | 18523.4093 |  | 18523.4093 |  | 18523.4093 |  | 18523.4093
2026-01-28 | 111742.6381 |  | 18623.773 |  | 18623.773 |  | 18623.773 |  | 18623.773 |  | 18623.773 |  | 18623.773
2026-01-29 | 112344.8206 |  | 18724.1368 |  | 18724.1368 |  | 18724.1368 |  | 18724.1368 |  | 18724.1368 |  | 18724.1368
2026-01-30 | 112947.0032 |  | 18824.5005 |  | 18824.5005 |  | 18824.5005 |  | 18824.5005 |  | 18824.5005 |  | 18824.5005
2026-01-31 | 113549.1857 |  | 18924.8643 |  | 18924.8643 |  | 18924.8643 |  | 18924.8643 |  | 18924.8643 |  | 18924.8643
2026-02-01 | 114151.3683 |  | 19025.228 |  | 19025.228 |  | 19025.228 |  | 19025.228 |  | 19025.228 |  | 19025.228
2026-02-02 | 114753.5508 |  | 19125.5918 |  | 19125.5918 |  | 19125.5918 |  | 19125.5918 |  | 19125.5918 |  | 19125.5918
2026-02-03 | 115355.7333 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556
2026-02-04 | 115675.3825 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304
2026-02-05 | 115995.0316 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053
2026-02-06 | 116314.6807 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801
2026-02-07 | 116634.3298 |  | 19439.055 |  | 19439.055 |  | 19439.055 |  | 19439.055 |  | 19439.055 |  | 19439.055
2026-02-08 | 116953.9789 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298
2026-02-09 | 117273.6281 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047
2026-02-10 | 117593.2772 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795
2026-02-11 | 117912.9263 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544
2026-02-12 | 118232.5754 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292
2026-02-13 | 118552.2246 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041
2026-02-14 | 118871.8737 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789
2026-02-15 | 119191.5228 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538
2026-02-16 | 119511.1719 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287
2026-02-17 | 119830.8211 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035
2026-02-18 | 120150.4702 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784
2026-02-19 | 120470.1193 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532
2026-02-20 | 120789.7684 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281
2026-02-21 | 121109.4175 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029
2026-02-22 | 121429.0667 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778
2026-02-23 | 121748.7158 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526
2026-02-24 | 122068.3649 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275
2026-02-25 | 122388.014 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023
2026-02-26 | 122707.6632 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772
2026-02-27 | 123027.3123 |  | 20504.552 |  | 20504.552 |  | 20504.552 |  | 20504.552 |  | 20504.552 |  | 20504.552
2026-02-28 | 123346.9614 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269
2026-03-01 | 123666.6105 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018
2026-03-02 | 123986.2596 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766
2026-03-03 | 124305.9088 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515
2026-03-04 | 124625.5579 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263
2026-03-05 | 124945.207 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012
2026-03-06 | 125264.8561 |  | 20877.476 |  | 20877.476 |  | 20877.476 |  | 20877.476 |  | 20877.476 |  | 20877.476
2026-03-07 | 125584.5053 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509
2026-03-08 | 125904.1544 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257
2026-03-09 | 126223.8035 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006
2026-03-10 | 126543.4526 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754
2026-03-11 | 126863.1018 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503
2026-03-12 | 127182.7509 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251
2026-03-13 | 127502.4 |  | 21250.4 |  | 21250.4 |  | 21250.4 |  | 21250.4 |  | 21250.4 |  | 21250.4
2026-03-14 | 127822.0491 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749
2026-03-15 | 128141.6982 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497
2026-03-16 | 128461.3474 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246
2026-03-17 | 128780.9965 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994
2026-03-18 | 129100.6456 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743
2026-03-19 | 129420.2947 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491
2026-03-20 | 129739.9439 |  | 21623.324 |  | 21623.324 |  | 21623.324 |  | 21623.324 |  | 21623.324 |  | 21623.324
2026-03-21 | 130059.593 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988
2026-03-22 | 130379.2421 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737
2026-03-23 | 130698.8912 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485
2026-03-24 | 131018.5404 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234
2026-03-25 | 131338.1895 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982
2026-03-26 | 131657.8386 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731
2026-03-27 | 131977.4877 |  | 21996.248 |  | 21996.248 |  | 21996.248 |  | 21996.248 |  | 21996.248 |  | 21996.248
2026-03-28 | 132297.1368 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228
2026-03-29 | 132616.786 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977
2026-03-30 | 132936.4351 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725
2026-03-31 | 133256.0842 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474
2026-04-01 | 133575.7333 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222
2026-04-02 | 133895.3825 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971
2026-04-03 | 134215.0316 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719
2026-04-04 | 134534.6807 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468
2026-04-05 | 134854.3298 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216
2026-04-06 | 135173.9789 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965
2026-04-07 | 135493.6281 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713
2026-04-08 | 135813.2772 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462
2026-04-09 | 136132.9263 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211
2026-04-10 | 136452.5754 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959
2026-04-11 | 136772.2246 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708
2026-04-12 | 137091.8737 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456
2026-04-13 | 137411.5228 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205
2026-04-14 | 137731.1719 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953
2026-04-15 | 138050.8211 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702
2026-04-16 | 138370.4702 |  | 23061.745 |  | 23061.745 |  | 23061.745 |  | 23061.745 |  | 23061.745 |  | 23061.745
2026-04-17 | 138690.1193 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199
2026-04-18 | 139009.7684 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947
2026-04-19 | 139329.4175 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696
2026-04-20 | 139649.0667 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444
2026-04-21 | 139968.7158 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193
2026-04-22 | 140288.3649 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942
2026-04-23 | 140608.014 |  | 23434.669 |  | 23434.669 |  | 23434.669 |  | 23434.669 |  | 23434.669 |  | 23434.669
2026-04-24 | 140927.6632 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439
2026-04-25 | 141247.3123 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187
2026-04-26 | 141566.9614 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936
2026-04-27 | 141886.6105 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684
2026-04-28 | 142206.2596 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433
2026-04-29 | 142525.9088 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181
2026-04-30 | 142845.5579 |  | 23807.593 |  | 23807.593 |  | 23807.593 |  | 23807.593 |  | 23807.593 |  | 23807.593
2026-05-01 | 143165.207 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678
2026-05-02 | 143484.8561 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427
2026-05-03 | 143804.5053 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175
2026-05-04 | 144124.1544 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924
2026-05-05 | 144443.8035 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673
2026-05-06 | 144763.4526 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421
2026-05-07 | 145083.1018 |  | 24180.517 |  | 24180.517 |  | 24180.517 |  | 24180.517 |  | 24180.517 |  | 24180.517
2026-05-08 | 145402.7509 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918
2026-05-09 | 145722.4 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667
2026-05-10 | 146042.0491 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415
2026-05-11 | 146361.6982 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164
2026-05-12 | 146681.3474 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912
2026-05-13 | 147000.9965 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661
2026-05-14 | 147320.6456 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409
2026-05-15 | 147640.2947 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158
2026-05-16 | 147959.9439 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906
2026-05-17 | 148279.593 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655
2026-05-18 | 148599.2421 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404
2026-05-19 | 148918.8912 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152
2026-05-20 | 149238.5404 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901
2026-05-21 | 149558.1895 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649
2026-05-22 | 149877.8386 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398
2026-05-23 | 150197.4877 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146
2026-05-24 | 150517.1368 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895
2026-05-25 | 150836.786 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643
2026-05-26 | 151156.4351 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392
2026-05-27 | 151476.0842 |  | 25246.014 |  | 25246.014 |  | 25246.014 |  | 25246.014 |  | 25246.014 |  | 25246.014
2026-05-28 | 151795.7333 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889
2026-05-29 | 152115.3825 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637
2026-05-30 | 152435.0316 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386
2026-05-31 | 152754.6807 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135
2026-06-01 | 153074.3298 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883
2026-06-02 | 153393.9789 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632
2026-06-03 | 153713.6281 |  | 25618.938 |  | 25618.938 |  | 25618.938 |  | 25618.938 |  | 25618.938 |  | 25618.938
2026-06-04 | 154033.2772 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129
2026-06-05 | 154352.9263 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877
2026-06-06 | 154672.5754 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626
2026-06-07 | 154992.2246 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374
2026-06-08 | 155311.8737 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123
2026-06-09 | 155631.5228 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871
2026-06-10 | 155951.1719 |  | 25991.862 |  | 25991.862 |  | 25991.862 |  | 25991.862 |  | 25991.862 |  | 25991.862
2026-06-11 | 156270.8211 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368
2026-06-12 | 156590.4702 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117
2026-06-13 | 156910.1193 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865
2026-06-14 | 157229.7684 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614
2026-06-15 | 157549.4175 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363
2026-06-16 | 157869.0667 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111
2026-06-17 | 158188.7158 |  | 26364.786 |  | 26364.786 |  | 26364.786 |  | 26364.786 |  | 26364.786 |  | 26364.786
2026-06-18 | 158508.3649 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608
2026-06-19 | 158828.014 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357
2026-06-20 | 159147.6632 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105
2026-06-21 | 159467.3123 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854
2026-06-22 | 159786.9614 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602
2026-06-23 | 160106.6105 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351
2026-06-24 | 160426.2596 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099
2026-06-25 | 160745.9088 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848
2026-06-26 | 161065.5579 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596
2026-06-27 | 161385.207 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345
2026-06-28 | 161704.8561 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094
2026-06-29 | 162024.5053 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842
2026-06-30 | 162344.1544 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591
2026-07-01 | 162663.8035 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339
2026-07-02 | 162983.4526 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088
2026-07-03 | 163303.1018 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836
2026-07-04 | 163622.7509 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585
2026-07-05 | 163942.4 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333
2026-07-06 | 164262.0491 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082
2026-07-07 | 164581.6982 |  | 27430.283 |  | 27430.283 |  | 27430.283 |  | 27430.283 |  | 27430.283 |  | 27430.283
2026-07-08 | 164901.3474 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579
2026-07-09 | 165220.9965 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327
2026-07-10 | 165540.6456 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076
2026-07-11 | 165860.2947 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825
2026-07-12 | 166179.9439 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573
2026-07-13 | 166499.593 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322
2026-07-14 | 166819.2421 |  | 27803.207 |  | 27803.207 |  | 27803.207 |  | 27803.207 |  | 27803.207 |  | 27803.207
2026-07-15 | 167138.8912 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819
2026-07-16 | 167458.5404 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567
2026-07-17 | 167778.1895 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316
2026-07-18 | 168097.8386 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064
2026-07-19 | 168417.4877 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813
2026-07-20 | 168737.1368 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561
2026-07-21 | 169056.786 |  | 28176.131 |  | 28176.131 |  | 28176.131 |  | 28176.131 |  | 28176.131 |  | 28176.131
2026-07-22 | 169376.4351 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058
2026-07-23 | 169696.0842 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807
2026-07-24 | 170015.7333 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556
2026-07-25 | 170335.3825 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304
2026-07-26 | 170655.0316 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053
2026-07-27 | 170974.6807 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801
2026-07-28 | 171294.3298 |  | 28549.055 |  | 28549.055 |  | 28549.055 |  | 28549.055 |  | 28549.055 |  | 28549.055
2026-07-29 | 171613.9789 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298
2026-07-30 | 171933.6281 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047
2026-07-31 | 172253.2772 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795
2026-08-01 | 172572.9263 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544
2026-08-02 | 172892.5754 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292
2026-08-03 | 173212.2246 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041
2026-08-04 | 173531.8737 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789
2026-08-05 | 173851.5228 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538
2026-08-06 | 174171.1719 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287
2026-08-07 | 174490.8211 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035
2026-08-08 | 174810.4702 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784
2026-08-09 | 175130.1193 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532
2026-08-10 | 175449.7684 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281
2026-08-11 | 175769.4175 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029
2026-08-12 | 176089.0667 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778
2026-08-13 | 176524.851 |  | 29420.8085 |  | 29420.8085 |  | 29420.8085 |  | 29420.8085 |  | 29420.8085 |  | 29420.8085
2026-08-14 | 176960.6353 |  | 29493.4392 |  | 29493.4392 |  | 29493.4392 |  | 29493.4392 |  | 29493.4392 |  | 29493.4392
2026-08-15 | 177396.4196 |  | 29566.0699 |  | 29566.0699 |  | 29566.0699 |  | 29566.0699 |  | 29566.0699 |  | 29566.0699
2026-08-16 | 177832.2039 |  | 29638.7007 |  | 29638.7007 |  | 29638.7007 |  | 29638.7007 |  | 29638.7007 |  | 29638.7007
2026-08-17 | 178267.9882 |  | 29711.3314 |  | 29711.3314 |  | 29711.3314 |  | 29711.3314 |  | 29711.3314 |  | 29711.3314
2026-08-18 | 178703.7725 |  | 29783.9621 |  | 29783.9621 |  | 29783.9621 |  | 29783.9621 |  | 29783.9621 |  | 29783.9621
2026-08-19 | 179139.5569 |  | 29856.5928 |  | 29856.5928 |  | 29856.5928 |  | 29856.5928 |  | 29856.5928 |  | 29856.5928
2026-08-20 | 179575.3412 |  | 29929.2235 |  | 29929.2235 |  | 29929.2235 |  | 29929.2235 |  | 29929.2235 |  | 29929.2235
2026-08-21 | 180011.1255 |  | 30001.8542 |  | 30001.8542 |  | 30001.8542 |  | 30001.8542 |  | 30001.8542 |  | 30001.8542
2026-08-22 | 180446.9098 |  | 30074.485 |  | 30074.485 |  | 30074.485 |  | 30074.485 |  | 30074.485 |  | 30074.485
2026-08-23 | 180882.6941 |  | 30147.1157 |  | 30147.1157 |  | 30147.1157 |  | 30147.1157 |  | 30147.1157 |  | 30147.1157
2026-08-24 | 181318.4784 |  | 30219.7464 |  | 30219.7464 |  | 30219.7464 |  | 30219.7464 |  | 30219.7464 |  | 30219.7464
2026-08-25 | 181754.2627 |  | 30292.3771 |  | 30292.3771 |  | 30292.3771 |  | 30292.3771 |  | 30292.3771 |  | 30292.3771
2026-08-26 | 182190.0471 |  | 30365.0078 |  | 30365.0078 |  | 30365.0078 |  | 30365.0078 |  | 30365.0078 |  | 30365.0078
2026-08-27 | 182625.8314 |  | 30437.6386 |  | 30437.6386 |  | 30437.6386 |  | 30437.6386 |  | 30437.6386 |  | 30437.6386
2026-08-28 | 183061.6157 |  | 30510.2693 |  | 30510.2693 |  | 30510.2693 |  | 30510.2693 |  | 30510.2693 |  | 30510.2693
2026-08-29 | 183497.4 |  | 30582.9 |  | 30582.9 |  | 30582.9 |  | 30582.9 |  | 30582.9 |  | 30582.9
2026-08-30 | 183933.1843 |  | 30655.5307 |  | 30655.5307 |  | 30655.5307 |  | 30655.5307 |  | 30655.5307 |  | 30655.5307
2026-08-31 | 184368.9686 |  | 30728.1614 |  | 30728.1614 |  | 30728.1614 |  | 30728.1614 |  | 30728.1614 |  | 30728.1614
2026-09-01 | 184804.7529 |  | 30800.7922 |  | 30800.7922 |  | 30800.7922 |  | 30800.7922 |  | 30800.7922 |  | 30800.7922
2026-09-02 | 185240.5373 |  | 30873.4229 |  | 30873.4229 |  | 30873.4229 |  | 30873.4229 |  | 30873.4229 |  | 30873.4229
2026-09-03 | 185676.3216 |  | 30946.0536 |  | 30946.0536 |  | 30946.0536 |  | 30946.0536 |  | 30946.0536 |  | 30946.0536
2026-09-04 | 186112.1059 |  | 31018.6843 |  | 31018.6843 |  | 31018.6843 |  | 31018.6843 |  | 31018.6843 |  | 31018.6843
2026-09-05 | 186547.8902 |  | 31091.315 |  | 31091.315 |  | 31091.315 |  | 31091.315 |  | 31091.315 |  | 31091.315
2026-09-06 | 186983.6745 |  | 31163.9458 |  | 31163.9458 |  | 31163.9458 |  | 31163.9458 |  | 31163.9458 |  | 31163.9458
2026-09-07 | 187419.4588 |  | 31236.5765 |  | 31236.5765 |  | 31236.5765 |  | 31236.5765 |  | 31236.5765 |  | 31236.5765
2026-09-08 | 187855.2431 |  | 31309.2072 |  | 31309.2072 |  | 31309.2072 |  | 31309.2072 |  | 31309.2072 |  | 31309.2072
2026-09-09 | 188291.0275 |  | 31381.8379 |  | 31381.8379 |  | 31381.8379 |  | 31381.8379 |  | 31381.8379 |  | 31381.8379
2026-09-10 | 188726.8118 |  | 31454.4686 |  | 31454.4686 |  | 31454.4686 |  | 31454.4686 |  | 31454.4686 |  | 31454.4686
2026-09-11 | 189162.5961 |  | 31527.0993 |  | 31527.0993 |  | 31527.0993 |  | 31527.0993 |  | 31527.0993 |  | 31527.0993
2026-09-12 | 189598.3804 |  | 31599.7301 |  | 31599.7301 |  | 31599.7301 |  | 31599.7301 |  | 31599.7301 |  | 31599.7301
2026-09-13 | 190034.1647 |  | 31672.3608 |  | 31672.3608 |  | 31672.3608 |  | 31672.3608 |  | 31672.3608 |  | 31672.3608
2026-09-14 | 190469.949 |  | 31744.9915 |  | 31744.9915 |  | 31744.9915 |  | 31744.9915 |  | 31744.9915 |  | 31744.9915
2026-09-15 | 190905.7333 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222

## Parts&materials (Direct Cost)
Date | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Planned 5004 · GTR Cost of Sales - Parts (Cumulative) | Actual 5004 · GTR Cost of Sales - Parts (Cumulative) | Planned 5111 · Parts & material costs (Direct) (Cumulative) | Actual 5111 · Parts & material costs (Direct) (Cumulative) | Planned 5128 · Health & Safety Equip (Direct) (Cumulative) | Actual 5128 · Health & Safety Equip (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-12 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-13 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-14 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-15 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-16 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-17 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-18 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-19 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-20 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-21 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-22 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-23 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-24 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-25 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-26 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-27 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-28 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-29 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-30 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-01 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-02 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-03 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-04 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-05 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-06 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-07 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-08 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-09 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-10 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-11 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-12 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-13 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-14 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-15 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-16 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-17 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-18 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-19 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-20 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-21 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-22 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-23 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-24 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-25 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-26 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-27 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-28 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-29 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-30 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-31 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-01 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-02 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-03 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-04 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-05 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-06 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-07 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-08 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-09 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-10 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-11 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-12 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-13 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-14 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-15 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-16 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-17 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-18 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-19 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-20 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-21 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-22 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-23 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-24 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-25 | 948.9331 | 979.62 | 316.311 | 0 | 316.311 | 979.62 | 316.311 | 0
2025-06-26 | 1897.8662 | 979.62 | 632.6221 | 0 | 632.6221 | 979.62 | 632.6221 | 0
2025-06-27 | 2846.7993 | 979.62 | 948.9331 | 0 | 948.9331 | 979.62 | 948.9331 | 0
2025-06-28 | 3795.7323 | 979.62 | 1265.2441 | 0 | 1265.2441 | 979.62 | 1265.2441 | 0
2025-06-29 | 4744.6654 | 979.62 | 1581.5551 | 0 | 1581.5551 | 979.62 | 1581.5551 | 0
2025-06-30 | 5693.5985 | 979.62 | 1897.8662 | 0 | 1897.8662 | 979.62 | 1897.8662 | 0
2025-07-01 | 6642.5316 | 979.62 | 2214.1772 | 0 | 2214.1772 | 979.62 | 2214.1772 | 0
2025-07-02 | 7591.4647 | 979.62 | 2530.4882 | 0 | 2530.4882 | 979.62 | 2530.4882 | 0
2025-07-03 | 8540.3978 | 979.62 | 2846.7993 | 0 | 2846.7993 | 979.62 | 2846.7993 | 0
2025-07-04 | 9489.3308 | 979.62 | 3163.1103 | 0 | 3163.1103 | 979.62 | 3163.1103 | 0
2025-07-05 | 10438.2639 | 979.62 | 3479.4213 | 0 | 3479.4213 | 979.62 | 3479.4213 | 0
2025-07-06 | 11387.197 | 979.62 | 3795.7323 | 0 | 3795.7323 | 979.62 | 3795.7323 | 0
2025-07-07 | 12336.1301 | 979.62 | 4112.0434 | 0 | 4112.0434 | 979.62 | 4112.0434 | 0
2025-07-08 | 13285.0632 | 979.62 | 4428.3544 | 0 | 4428.3544 | 979.62 | 4428.3544 | 0
2025-07-09 | 14233.9963 | 979.62 | 4744.6654 | 0 | 4744.6654 | 979.62 | 4744.6654 | 0
2025-07-10 | 15182.9293 | 979.62 | 5060.9764 | 0 | 5060.9764 | 979.62 | 5060.9764 | 0
2025-07-11 | 16131.8624 | 979.62 | 5377.2875 | 0 | 5377.2875 | 979.62 | 5377.2875 | 0
2025-07-12 | 17080.7955 | 979.62 | 5693.5985 | 0 | 5693.5985 | 979.62 | 5693.5985 | 0
2025-07-13 | 18029.7286 | 979.62 | 6009.9095 | 0 | 6009.9095 | 979.62 | 6009.9095 | 0
2025-07-14 | 18978.6617 | 979.62 | 6326.2206 | 0 | 6326.2206 | 979.62 | 6326.2206 | 0
2025-07-15 | 19927.5948 | 979.62 | 6642.5316 | 0 | 6642.5316 | 979.62 | 6642.5316 | 0
2025-07-16 | 20876.5278 | 979.62 | 6958.8426 | 0 | 6958.8426 | 979.62 | 6958.8426 | 0
2025-07-17 | 21825.4609 | 979.62 | 7275.1536 | 0 | 7275.1536 | 979.62 | 7275.1536 | 0
2025-07-18 | 22774.394 | 979.62 | 7591.4647 | 0 | 7591.4647 | 979.62 | 7591.4647 | 0
2025-07-19 | 23723.3271 | 979.62 | 7907.7757 | 0 | 7907.7757 | 979.62 | 7907.7757 | 0
2025-07-20 | 24672.2602 | 979.62 | 8224.0867 | 0 | 8224.0867 | 979.62 | 8224.0867 | 0
2025-07-21 | 25621.1933 | 979.62 | 8540.3978 | 0 | 8540.3978 | 979.62 | 8540.3978 | 0
2025-07-22 | 26570.1263 | 979.62 | 8856.7088 | 0 | 8856.7088 | 979.62 | 8856.7088 | 0
2025-07-23 | 27519.0594 | 979.62 | 9173.0198 | 0 | 9173.0198 | 979.62 | 9173.0198 | 0
2025-07-24 | 28467.9925 | 979.62 | 9489.3308 | 0 | 9489.3308 | 979.62 | 9489.3308 | 0
2025-07-25 | 29416.9256 | 979.62 | 9805.6419 | 0 | 9805.6419 | 979.62 | 9805.6419 | 0
2025-07-26 | 30365.8587 | 979.62 | 10121.9529 | 0 | 10121.9529 | 979.62 | 10121.9529 | 0
2025-07-27 | 31314.7918 | 979.62 | 10438.2639 | 0 | 10438.2639 | 979.62 | 10438.2639 | 0
2025-07-28 | 32263.7248 | 979.62 | 10754.5749 | 0 | 10754.5749 | 979.62 | 10754.5749 | 0
2025-07-29 | 33212.6579 | 979.62 | 11070.886 | 0 | 11070.886 | 979.62 | 11070.886 | 0
2025-07-30 | 34161.591 | 979.62 | 11387.197 | 0 | 11387.197 | 979.62 | 11387.197 | 0
2025-07-31 | 35110.5241 | 979.62 | 11703.508 | 0 | 11703.508 | 979.62 | 11703.508 | 0
2025-08-01 | 36059.4572 | 979.62 | 12019.8191 | 0 | 12019.8191 | 979.62 | 12019.8191 | 0
2025-08-02 | 37008.3903 | 979.62 | 12336.1301 | 0 | 12336.1301 | 979.62 | 12336.1301 | 0
2025-08-03 | 37957.3233 | 979.62 | 12652.4411 | 0 | 12652.4411 | 979.62 | 12652.4411 | 0
2025-08-04 | 38906.2564 | 2348.77 | 12968.7521 | 0 | 12968.7521 | 2348.77 | 12968.7521 | 0
2025-08-05 | 39855.1895 | 2348.77 | 13285.0632 | 0 | 13285.0632 | 2348.77 | 13285.0632 | 0
2025-08-06 | 40804.1226 | 2348.77 | 13601.3742 | 0 | 13601.3742 | 2348.77 | 13601.3742 | 0
2025-08-07 | 41753.0557 | 3299.64 | 13917.6852 | 0 | 13917.6852 | 3299.64 | 13917.6852 | 0
2025-08-08 | 42701.9888 | 3299.64 | 14233.9963 | 0 | 14233.9963 | 3299.64 | 14233.9963 | 0
2025-08-09 | 43650.9218 | 3299.64 | 14550.3073 | 0 | 14550.3073 | 3299.64 | 14550.3073 | 0
2025-08-10 | 44599.8549 | 3299.64 | 14866.6183 | 0 | 14866.6183 | 3299.64 | 14866.6183 | 0
2025-08-11 | 45548.788 | 3566.53 | 15182.9293 | 0 | 15182.9293 | 3566.53 | 15182.9293 | 0
2025-08-12 | 46497.7211 | 3566.53 | 15499.2404 | 0 | 15499.2404 | 3566.53 | 15499.2404 | 0
2025-08-13 | 47446.6542 | 3566.53 | 15815.5514 | 0 | 15815.5514 | 3566.53 | 15815.5514 | 0
2025-08-14 | 48395.5873 | 3566.53 | 16131.8624 | 0 | 16131.8624 | 3566.53 | 16131.8624 | 0
2025-08-15 | 49344.5203 | 3566.53 | 16448.1734 | 0 | 16448.1734 | 3566.53 | 16448.1734 | 0
2025-08-16 | 50293.4534 | 3566.53 | 16764.4845 | 0 | 16764.4845 | 3566.53 | 16764.4845 | 0
2025-08-17 | 51242.3865 | 3566.53 | 17080.7955 | 0 | 17080.7955 | 3566.53 | 17080.7955 | 0
2025-08-18 | 52191.3196 | 3566.53 | 17397.1065 | 0 | 17397.1065 | 3566.53 | 17397.1065 | 0
2025-08-19 | 53140.2527 | 16075.89 | 17713.4176 | 0 | 17713.4176 | 16075.89 | 17713.4176 | 0
2025-08-20 | 54089.1858 | 16075.89 | 18029.7286 | 0 | 18029.7286 | 16075.89 | 18029.7286 | 0
2025-08-21 | 55038.1188 | 16075.89 | 18346.0396 | 0 | 18346.0396 | 16075.89 | 18346.0396 | 0
2025-08-22 | 55987.0519 | 16075.89 | 18662.3506 | 0 | 18662.3506 | 16075.89 | 18662.3506 | 0
2025-08-23 | 56935.985 | 16075.89 | 18978.6617 | 0 | 18978.6617 | 16075.89 | 18978.6617 | 0
2025-08-24 | 57884.9181 | 16075.89 | 19294.9727 | 0 | 19294.9727 | 16075.89 | 19294.9727 | 0
2025-08-25 | 58833.8512 | 16795.65 | 19611.2837 | 0 | 19611.2837 | 16795.65 | 19611.2837 | 0
2025-08-26 | 59782.7843 | 16795.65 | 19927.5948 | 0 | 19927.5948 | 16795.65 | 19927.5948 | 0
2025-08-27 | 60731.7173 | 16795.65 | 20243.9058 | 0 | 20243.9058 | 16795.65 | 20243.9058 | 0
2025-08-28 | 61680.6504 | 16795.65 | 20560.2168 | 0 | 20560.2168 | 16795.65 | 20560.2168 | 0
2025-08-29 | 62629.5835 | 16795.65 | 20876.5278 | 0 | 20876.5278 | 16795.65 | 20876.5278 | 0
2025-08-30 | 63578.5166 | 16795.65 | 21192.8389 | 0 | 21192.8389 | 16795.65 | 21192.8389 | 0
2025-08-31 | 64527.4497 | 16795.65 | 21509.1499 | 0 | 21509.1499 | 16795.65 | 21509.1499 | 0
2025-09-01 | 65476.3828 | 16795.65 | 21825.4609 | 0 | 21825.4609 | 16795.65 | 21825.4609 | 0
2025-09-02 | 66425.3158 | 19920.45 | 22141.7719 | 0 | 22141.7719 | 19920.45 | 22141.7719 | 0
2025-09-03 | 67374.2489 | 19920.45 | 22458.083 | 0 | 22458.083 | 19920.45 | 22458.083 | 0
2025-09-04 | 68323.182 | 19920.45 | 22774.394 | 0 | 22774.394 | 19920.45 | 22774.394 | 0
2025-09-05 | 69272.1151 | 19920.45 | 23090.705 | 0 | 23090.705 | 19920.45 | 23090.705 | 0
2025-09-06 | 70221.0482 | 19920.45 | 23407.0161 | 0 | 23407.0161 | 19920.45 | 23407.0161 | 0
2025-09-07 | 71169.9813 | 19920.45 | 23723.3271 | 0 | 23723.3271 | 19920.45 | 23723.3271 | 0
2025-09-08 | 72118.9143 | 19920.45 | 24039.6381 | 0 | 24039.6381 | 19920.45 | 24039.6381 | 0
2025-09-09 | 73067.8474 | 20562.81 | 24355.9491 | 0 | 24355.9491 | 20562.81 | 24355.9491 | 0
2025-09-10 | 74016.7805 | 20562.81 | 24672.2602 | 0 | 24672.2602 | 20562.81 | 24672.2602 | 0
2025-09-11 | 74965.7136 | 20562.81 | 24988.5712 | 0 | 24988.5712 | 20562.81 | 24988.5712 | 0
2025-09-12 | 75914.6467 | 20562.81 | 25304.8822 | 0 | 25304.8822 | 20562.81 | 25304.8822 | 0
2025-09-13 | 76863.5798 | 20562.81 | 25621.1933 | 0 | 25621.1933 | 20562.81 | 25621.1933 | 0
2025-09-14 | 77812.5128 | 20562.81 | 25937.5043 | 0 | 25937.5043 | 20562.81 | 25937.5043 | 0
2025-09-15 | 78761.4459 | 20562.81 | 26253.8153 | 0 | 26253.8153 | 20562.81 | 26253.8153 | 0
2025-09-16 | 79710.379 | 20562.81 | 26570.1263 | 0 | 26570.1263 | 20562.81 | 26570.1263 | 0
2025-09-17 | 80659.3121 | 20562.81 | 26886.4374 | 0 | 26886.4374 | 20562.81 | 26886.4374 | 0
2025-09-18 | 81608.2452 | 20562.81 | 27202.7484 | 0 | 27202.7484 | 20562.81 | 27202.7484 | 0
2025-09-19 | 82557.1783 | 20562.81 | 27519.0594 | 0 | 27519.0594 | 20562.81 | 27519.0594 | 0
2025-09-20 | 82557.1783 | 20562.81 | 27519.0594 | 0 | 27519.0594 | 20562.81 | 27519.0594 | 0
2025-09-21 | 82557.1783 | 20562.81 | 27519.0594 | 0 | 27519.0594 | 20562.81 | 27519.0594 | 0
2025-09-22 | 83914.972 | 20562.81 | 27971.6573 | 0 | 27971.6573 | 20562.81 | 27971.6573 | 0
2025-09-23 | 85272.7656 | 20562.81 | 28424.2552 | 0 | 28424.2552 | 20562.81 | 28424.2552 | 0
2025-09-24 | 86630.5593 | 23165.94 | 28876.8531 | 0 | 28876.8531 | 23165.94 | 28876.8531 | 0
2025-09-25 | 87988.353 | 23165.94 | 29329.451 | 0 | 29329.451 | 23165.94 | 29329.451 | 0
2025-09-26 | 89346.1467 | 23165.94 | 29782.0489 | 0 | 29782.0489 | 23165.94 | 29782.0489 | 0
2025-09-27 | 90703.9404 | 23165.94 | 30234.6468 | 0 | 30234.6468 | 23165.94 | 30234.6468 | 0
2025-09-28 | 92061.7341 | 23165.94 | 30687.2447 | 0 | 30687.2447 | 23165.94 | 30687.2447 | 0
2025-09-29 | 93419.5278 | 23165.94 | 31139.8426 | 0 | 31139.8426 | 23165.94 | 31139.8426 | 0
2025-09-30 | 94777.3215 | 23165.94 | 31592.4405 | 0 | 31592.4405 | 23165.94 | 31592.4405 | 0
2025-10-01 | 96135.1152 | 23165.94 | 32045.0384 | 0 | 32045.0384 | 23165.94 | 32045.0384 | 0
2025-10-02 | 97492.9089 | 23165.94 | 32497.6363 | 0 | 32497.6363 | 23165.94 | 32497.6363 | 0
2025-10-03 | 98850.7026 | 23165.94 | 32950.2342 | 0 | 32950.2342 | 23165.94 | 32950.2342 | 0
2025-10-04 | 100208.4962 | 23165.94 | 33402.8321 | 0 | 33402.8321 | 23165.94 | 33402.8321 | 0
2025-10-05 | 101566.2899 | 23165.94 | 33855.43 | 0 | 33855.43 | 23165.94 | 33855.43 | 0
2025-10-06 | 102924.0836 | 23165.94 | 34308.0279 | 0 | 34308.0279 | 23165.94 | 34308.0279 | 0
2025-10-07 | 104281.8773 | 23165.94 | 34760.6258 | 0 | 34760.6258 | 23165.94 | 34760.6258 | 0
2025-10-08 | 105639.671 | 23165.94 | 35213.2237 | 0 | 35213.2237 | 23165.94 | 35213.2237 | 0
2025-10-09 | 106997.4647 | 23165.94 | 35665.8216 | 0 | 35665.8216 | 23165.94 | 35665.8216 | 0
2025-10-10 | 108355.2584 | 23165.94 | 36118.4195 | 0 | 36118.4195 | 23165.94 | 36118.4195 | 0
2025-10-11 | 109713.0521 | 23165.94 | 36571.0174 | 0 | 36571.0174 | 23165.94 | 36571.0174 | 0
2025-10-12 | 111070.8458 | 23165.94 | 37023.6153 | 0 | 37023.6153 | 23165.94 | 37023.6153 | 0
2025-10-13 | 112428.6395 |  | 37476.2132 |  | 37476.2132 |  | 37476.2132
2025-10-14 | 113786.4332 |  | 37928.8111 |  | 37928.8111 |  | 37928.8111
2025-10-15 | 115144.2269 |  | 38381.409 |  | 38381.409 |  | 38381.409
2025-10-16 | 116502.0205 |  | 38834.0068 |  | 38834.0068 |  | 38834.0068
2025-10-17 | 117859.8142 |  | 39286.6047 |  | 39286.6047 |  | 39286.6047
2025-10-18 | 119217.6079 |  | 39739.2026 |  | 39739.2026 |  | 39739.2026
2025-10-19 | 120575.4016 |  | 40191.8005 |  | 40191.8005 |  | 40191.8005
2025-10-20 | 121933.1953 |  | 40644.3984 |  | 40644.3984 |  | 40644.3984
2025-10-21 | 123290.989 |  | 41096.9963 |  | 41096.9963 |  | 41096.9963
2025-10-22 | 124648.7827 |  | 41549.5942 |  | 41549.5942 |  | 41549.5942
2025-10-23 | 126006.5764 |  | 42002.1921 |  | 42002.1921 |  | 42002.1921
2025-10-24 | 127364.3701 |  | 42454.79 |  | 42454.79 |  | 42454.79
2025-10-25 | 128722.1638 |  | 42907.3879 |  | 42907.3879 |  | 42907.3879
2025-10-26 | 130079.9575 |  | 43359.9858 |  | 43359.9858 |  | 43359.9858
2025-10-27 | 131437.7512 |  | 43812.5837 |  | 43812.5837 |  | 43812.5837
2025-10-28 | 132795.5448 |  | 44265.1816 |  | 44265.1816 |  | 44265.1816
2025-10-29 | 134153.3385 |  | 44717.7795 |  | 44717.7795 |  | 44717.7795
2025-10-30 | 135511.1322 |  | 45170.3774 |  | 45170.3774 |  | 45170.3774
2025-10-31 | 136868.9259 |  | 45622.9753 |  | 45622.9753 |  | 45622.9753
2025-11-01 | 138226.7196 |  | 46075.5732 |  | 46075.5732 |  | 46075.5732
2025-11-02 | 139584.5133 |  | 46528.1711 |  | 46528.1711 |  | 46528.1711
2025-11-03 | 140942.307 |  | 46980.769 |  | 46980.769 |  | 46980.769
2025-11-04 | 142300.1007 |  | 47433.3669 |  | 47433.3669 |  | 47433.3669
2025-11-05 | 143657.8944 |  | 47885.9648 |  | 47885.9648 |  | 47885.9648
2025-11-06 | 145015.6881 |  | 48338.5627 |  | 48338.5627 |  | 48338.5627
2025-11-07 | 146373.4818 |  | 48791.1606 |  | 48791.1606 |  | 48791.1606
2025-11-08 | 147731.2754 |  | 49243.7585 |  | 49243.7585 |  | 49243.7585
2025-11-09 | 149089.0691 |  | 49696.3564 |  | 49696.3564 |  | 49696.3564
2025-11-10 | 150446.8628 |  | 50148.9543 |  | 50148.9543 |  | 50148.9543
2025-11-11 | 151804.6565 |  | 50601.5522 |  | 50601.5522 |  | 50601.5522
2025-11-12 | 152491.7994 |  | 50830.5998 |  | 50830.5998 |  | 50830.5998
2025-11-13 | 153178.9422 |  | 51059.6474 |  | 51059.6474 |  | 51059.6474
2025-11-14 | 153866.0851 |  | 51288.695 |  | 51288.695 |  | 51288.695
2025-11-15 | 154553.228 |  | 51517.7427 |  | 51517.7427 |  | 51517.7427
2025-11-16 | 155240.3708 |  | 51746.7903 |  | 51746.7903 |  | 51746.7903
2025-11-17 | 155927.5137 |  | 51975.8379 |  | 51975.8379 |  | 51975.8379
2025-11-18 | 156614.6565 |  | 52204.8855 |  | 52204.8855 |  | 52204.8855
2025-11-19 | 157301.7994 |  | 52433.9331 |  | 52433.9331 |  | 52433.9331
2025-11-20 | 157988.9422 |  | 52662.9807 |  | 52662.9807 |  | 52662.9807
2025-11-21 | 158676.0851 |  | 52892.0284 |  | 52892.0284 |  | 52892.0284
2025-11-22 | 159363.228 |  | 53121.076 |  | 53121.076 |  | 53121.076
2025-11-23 | 160050.3708 |  | 53350.1236 |  | 53350.1236 |  | 53350.1236
2025-11-24 | 160737.5137 |  | 53579.1712 |  | 53579.1712 |  | 53579.1712
2025-11-25 | 161424.6565 |  | 53808.2188 |  | 53808.2188 |  | 53808.2188
2025-11-26 | 162111.7994 |  | 54037.2665 |  | 54037.2665 |  | 54037.2665
2025-11-27 | 162798.9422 |  | 54266.3141 |  | 54266.3141 |  | 54266.3141
2025-11-28 | 163486.0851 |  | 54495.3617 |  | 54495.3617 |  | 54495.3617
2025-11-29 | 164173.228 |  | 54724.4093 |  | 54724.4093 |  | 54724.4093
2025-11-30 | 164860.3708 |  | 54953.4569 |  | 54953.4569 |  | 54953.4569
2025-12-01 | 165547.5137 |  | 55182.5046 |  | 55182.5046 |  | 55182.5046
2025-12-02 | 166234.6565 |  | 55411.5522 |  | 55411.5522 |  | 55411.5522
2025-12-03 | 166921.7994 |  | 55640.5998 |  | 55640.5998 |  | 55640.5998
2025-12-04 | 167608.9422 |  | 55869.6474 |  | 55869.6474 |  | 55869.6474
2025-12-05 | 168296.0851 |  | 56098.695 |  | 56098.695 |  | 56098.695
2025-12-06 | 168983.228 |  | 56327.7427 |  | 56327.7427 |  | 56327.7427
2025-12-07 | 169670.3708 |  | 56556.7903 |  | 56556.7903 |  | 56556.7903
2025-12-08 | 170357.5137 |  | 56785.8379 |  | 56785.8379 |  | 56785.8379
2025-12-09 | 171044.6565 |  | 57014.8855 |  | 57014.8855 |  | 57014.8855
2025-12-10 | 171731.7994 |  | 57243.9331 |  | 57243.9331 |  | 57243.9331
2025-12-11 | 172418.9422 |  | 57472.9807 |  | 57472.9807 |  | 57472.9807
2025-12-12 | 173106.0851 |  | 57702.0284 |  | 57702.0284 |  | 57702.0284
2025-12-13 | 173793.228 |  | 57931.076 |  | 57931.076 |  | 57931.076
2025-12-14 | 174480.3708 |  | 58160.1236 |  | 58160.1236 |  | 58160.1236
2025-12-15 | 175167.5137 |  | 58389.1712 |  | 58389.1712 |  | 58389.1712
2025-12-16 | 175854.6565 |  | 58618.2188 |  | 58618.2188 |  | 58618.2188
2025-12-17 | 176541.7994 |  | 58847.2665 |  | 58847.2665 |  | 58847.2665
2025-12-18 | 177228.9422 |  | 59076.3141 |  | 59076.3141 |  | 59076.3141
2025-12-19 | 177916.0851 |  | 59305.3617 |  | 59305.3617 |  | 59305.3617
2025-12-20 | 178603.228 |  | 59534.4093 |  | 59534.4093 |  | 59534.4093
2025-12-21 | 179290.3708 |  | 59763.4569 |  | 59763.4569 |  | 59763.4569
2025-12-22 | 179977.5137 |  | 59992.5046 |  | 59992.5046 |  | 59992.5046
2025-12-23 | 180664.6565 |  | 60221.5522 |  | 60221.5522 |  | 60221.5522
2025-12-24 | 181351.7994 |  | 60450.5998 |  | 60450.5998 |  | 60450.5998
2025-12-25 | 182038.9422 |  | 60679.6474 |  | 60679.6474 |  | 60679.6474
2025-12-26 | 182726.0851 |  | 60908.695 |  | 60908.695 |  | 60908.695
2025-12-27 | 183413.228 |  | 61137.7427 |  | 61137.7427 |  | 61137.7427
2025-12-28 | 184100.3708 |  | 61366.7903 |  | 61366.7903 |  | 61366.7903
2025-12-29 | 184787.5137 |  | 61595.8379 |  | 61595.8379 |  | 61595.8379
2025-12-30 | 185474.6565 |  | 61824.8855 |  | 61824.8855 |  | 61824.8855
2025-12-31 | 186161.7994 |  | 62053.9331 |  | 62053.9331 |  | 62053.9331
2026-01-01 | 186848.9422 |  | 62282.9807 |  | 62282.9807 |  | 62282.9807
2026-01-02 | 187536.0851 |  | 62512.0284 |  | 62512.0284 |  | 62512.0284
2026-01-03 | 188223.228 |  | 62741.076 |  | 62741.076 |  | 62741.076
2026-01-04 | 188910.3708 |  | 62970.1236 |  | 62970.1236 |  | 62970.1236
2026-01-05 | 189597.5137 |  | 63199.1712 |  | 63199.1712 |  | 63199.1712
2026-01-06 | 190284.6565 |  | 63428.2188 |  | 63428.2188 |  | 63428.2188
2026-01-07 | 190971.7994 |  | 63657.2665 |  | 63657.2665 |  | 63657.2665
2026-01-08 | 191658.9422 |  | 63886.3141 |  | 63886.3141 |  | 63886.3141
2026-01-09 | 192346.0851 |  | 64115.3617 |  | 64115.3617 |  | 64115.3617
2026-01-10 | 193033.228 |  | 64344.4093 |  | 64344.4093 |  | 64344.4093
2026-01-11 | 193720.3708 |  | 64573.4569 |  | 64573.4569 |  | 64573.4569
2026-01-12 | 194407.5137 |  | 64802.5046 |  | 64802.5046 |  | 64802.5046
2026-01-13 | 195094.6565 |  | 65031.5522 |  | 65031.5522 |  | 65031.5522
2026-01-14 | 195781.7994 |  | 65260.5998 |  | 65260.5998 |  | 65260.5998
2026-01-15 | 196468.9422 |  | 65489.6474 |  | 65489.6474 |  | 65489.6474
2026-01-16 | 197156.0851 |  | 65718.695 |  | 65718.695 |  | 65718.695
2026-01-17 | 197843.228 |  | 65947.7427 |  | 65947.7427 |  | 65947.7427
2026-01-18 | 198530.3708 |  | 66176.7903 |  | 66176.7903 |  | 66176.7903
2026-01-19 | 199217.5137 |  | 66405.8379 |  | 66405.8379 |  | 66405.8379
2026-01-20 | 199904.6565 |  | 66634.8855 |  | 66634.8855 |  | 66634.8855
2026-01-21 | 200591.7994 |  | 66863.9331 |  | 66863.9331 |  | 66863.9331
2026-01-22 | 201278.9422 |  | 67092.9807 |  | 67092.9807 |  | 67092.9807
2026-01-23 | 201966.0851 |  | 67322.0284 |  | 67322.0284 |  | 67322.0284
2026-01-24 | 202653.228 |  | 67551.076 |  | 67551.076 |  | 67551.076
2026-01-25 | 203340.3708 |  | 67780.1236 |  | 67780.1236 |  | 67780.1236
2026-01-26 | 204027.5137 |  | 68009.1712 |  | 68009.1712 |  | 68009.1712
2026-01-27 | 204714.6565 |  | 68238.2188 |  | 68238.2188 |  | 68238.2188
2026-01-28 | 205401.7994 |  | 68467.2665 |  | 68467.2665 |  | 68467.2665
2026-01-29 | 206088.9422 |  | 68696.3141 |  | 68696.3141 |  | 68696.3141
2026-01-30 | 206776.0851 |  | 68925.3617 |  | 68925.3617 |  | 68925.3617
2026-01-31 | 207463.228 |  | 69154.4093 |  | 69154.4093 |  | 69154.4093
2026-02-01 | 208150.3708 |  | 69383.4569 |  | 69383.4569 |  | 69383.4569
2026-02-02 | 208837.5137 |  | 69612.5046 |  | 69612.5046 |  | 69612.5046
2026-02-03 | 209524.6565 |  | 69841.5522 |  | 69841.5522 |  | 69841.5522
2026-02-04 | 209566.3144 |  | 69855.4381 |  | 69855.4381 |  | 69855.4381
2026-02-05 | 209607.9723 |  | 69869.3241 |  | 69869.3241 |  | 69869.3241
2026-02-06 | 209649.6302 |  | 69883.2101 |  | 69883.2101 |  | 69883.2101
2026-02-07 | 209691.2881 |  | 69897.096 |  | 69897.096 |  | 69897.096
2026-02-08 | 209732.946 |  | 69910.982 |  | 69910.982 |  | 69910.982
2026-02-09 | 209774.6039 |  | 69924.868 |  | 69924.868 |  | 69924.868
2026-02-10 | 209816.2618 |  | 69938.7539 |  | 69938.7539 |  | 69938.7539
2026-02-11 | 209857.9197 |  | 69952.6399 |  | 69952.6399 |  | 69952.6399
2026-02-12 | 209899.5776 |  | 69966.5259 |  | 69966.5259 |  | 69966.5259
2026-02-13 | 209941.2355 |  | 69980.4118 |  | 69980.4118 |  | 69980.4118
2026-02-14 | 209982.8934 |  | 69994.2978 |  | 69994.2978 |  | 69994.2978
2026-02-15 | 210024.5513 |  | 70008.1838 |  | 70008.1838 |  | 70008.1838
2026-02-16 | 210066.2092 |  | 70022.0697 |  | 70022.0697 |  | 70022.0697
2026-02-17 | 210107.867 |  | 70035.9557 |  | 70035.9557 |  | 70035.9557
2026-02-18 | 210149.5249 |  | 70049.8416 |  | 70049.8416 |  | 70049.8416
2026-02-19 | 210191.1828 |  | 70063.7276 |  | 70063.7276 |  | 70063.7276
2026-02-20 | 210232.8407 |  | 70077.6136 |  | 70077.6136 |  | 70077.6136
2026-02-21 | 210274.4986 |  | 70091.4995 |  | 70091.4995 |  | 70091.4995
2026-02-22 | 210316.1565 |  | 70105.3855 |  | 70105.3855 |  | 70105.3855
2026-02-23 | 210357.8144 |  | 70119.2715 |  | 70119.2715 |  | 70119.2715
2026-02-24 | 210399.4723 |  | 70133.1574 |  | 70133.1574 |  | 70133.1574
2026-02-25 | 210441.1302 |  | 70147.0434 |  | 70147.0434 |  | 70147.0434
2026-02-26 | 210482.7881 |  | 70160.9294 |  | 70160.9294 |  | 70160.9294
2026-02-27 | 210524.446 |  | 70174.8153 |  | 70174.8153 |  | 70174.8153
2026-02-28 | 210566.1039 |  | 70188.7013 |  | 70188.7013 |  | 70188.7013
2026-03-01 | 210607.7618 |  | 70202.5873 |  | 70202.5873 |  | 70202.5873
2026-03-02 | 210649.4197 |  | 70216.4732 |  | 70216.4732 |  | 70216.4732
2026-03-03 | 210691.0776 |  | 70230.3592 |  | 70230.3592 |  | 70230.3592
2026-03-04 | 210732.7355 |  | 70244.2452 |  | 70244.2452 |  | 70244.2452
2026-03-05 | 210774.3934 |  | 70258.1311 |  | 70258.1311 |  | 70258.1311
2026-03-06 | 210816.0513 |  | 70272.0171 |  | 70272.0171 |  | 70272.0171
2026-03-07 | 210857.7092 |  | 70285.9031 |  | 70285.9031 |  | 70285.9031
2026-03-08 | 210899.367 |  | 70299.789 |  | 70299.789 |  | 70299.789
2026-03-09 | 210941.0249 |  | 70313.675 |  | 70313.675 |  | 70313.675
2026-03-10 | 210982.6828 |  | 70327.5609 |  | 70327.5609 |  | 70327.5609
2026-03-11 | 211024.3407 |  | 70341.4469 |  | 70341.4469 |  | 70341.4469
2026-03-12 | 211065.9986 |  | 70355.3329 |  | 70355.3329 |  | 70355.3329
2026-03-13 | 211107.6565 |  | 70369.2188 |  | 70369.2188 |  | 70369.2188
2026-03-14 | 211149.3144 |  | 70383.1048 |  | 70383.1048 |  | 70383.1048
2026-03-15 | 211190.9723 |  | 70396.9908 |  | 70396.9908 |  | 70396.9908
2026-03-16 | 211232.6302 |  | 70410.8767 |  | 70410.8767 |  | 70410.8767
2026-03-17 | 211274.2881 |  | 70424.7627 |  | 70424.7627 |  | 70424.7627
2026-03-18 | 211315.946 |  | 70438.6487 |  | 70438.6487 |  | 70438.6487
2026-03-19 | 211357.6039 |  | 70452.5346 |  | 70452.5346 |  | 70452.5346
2026-03-20 | 211399.2618 |  | 70466.4206 |  | 70466.4206 |  | 70466.4206
2026-03-21 | 211440.9197 |  | 70480.3066 |  | 70480.3066 |  | 70480.3066
2026-03-22 | 211482.5776 |  | 70494.1925 |  | 70494.1925 |  | 70494.1925
2026-03-23 | 211524.2355 |  | 70508.0785 |  | 70508.0785 |  | 70508.0785
2026-03-24 | 211565.8934 |  | 70521.9645 |  | 70521.9645 |  | 70521.9645
2026-03-25 | 211607.5513 |  | 70535.8504 |  | 70535.8504 |  | 70535.8504
2026-03-26 | 211649.2092 |  | 70549.7364 |  | 70549.7364 |  | 70549.7364
2026-03-27 | 211690.867 |  | 70563.6223 |  | 70563.6223 |  | 70563.6223
2026-03-28 | 211732.5249 |  | 70577.5083 |  | 70577.5083 |  | 70577.5083
2026-03-29 | 211774.1828 |  | 70591.3943 |  | 70591.3943 |  | 70591.3943
2026-03-30 | 211815.8407 |  | 70605.2802 |  | 70605.2802 |  | 70605.2802
2026-03-31 | 211857.4986 |  | 70619.1662 |  | 70619.1662 |  | 70619.1662
2026-04-01 | 211899.1565 |  | 70633.0522 |  | 70633.0522 |  | 70633.0522
2026-04-02 | 211940.8144 |  | 70646.9381 |  | 70646.9381 |  | 70646.9381
2026-04-03 | 211982.4723 |  | 70660.8241 |  | 70660.8241 |  | 70660.8241
2026-04-04 | 212024.1302 |  | 70674.7101 |  | 70674.7101 |  | 70674.7101
2026-04-05 | 212065.7881 |  | 70688.596 |  | 70688.596 |  | 70688.596
2026-04-06 | 212107.446 |  | 70702.482 |  | 70702.482 |  | 70702.482
2026-04-07 | 212149.1039 |  | 70716.368 |  | 70716.368 |  | 70716.368
2026-04-08 | 212190.7618 |  | 70730.2539 |  | 70730.2539 |  | 70730.2539
2026-04-09 | 212232.4197 |  | 70744.1399 |  | 70744.1399 |  | 70744.1399
2026-04-10 | 212274.0776 |  | 70758.0259 |  | 70758.0259 |  | 70758.0259
2026-04-11 | 212315.7355 |  | 70771.9118 |  | 70771.9118 |  | 70771.9118
2026-04-12 | 212357.3934 |  | 70785.7978 |  | 70785.7978 |  | 70785.7978
2026-04-13 | 212399.0513 |  | 70799.6838 |  | 70799.6838 |  | 70799.6838
2026-04-14 | 212440.7092 |  | 70813.5697 |  | 70813.5697 |  | 70813.5697
2026-04-15 | 212482.367 |  | 70827.4557 |  | 70827.4557 |  | 70827.4557
2026-04-16 | 212524.0249 |  | 70841.3416 |  | 70841.3416 |  | 70841.3416
2026-04-17 | 212565.6828 |  | 70855.2276 |  | 70855.2276 |  | 70855.2276
2026-04-18 | 212607.3407 |  | 70869.1136 |  | 70869.1136 |  | 70869.1136
2026-04-19 | 212648.9986 |  | 70882.9995 |  | 70882.9995 |  | 70882.9995
2026-04-20 | 212690.6565 |  | 70896.8855 |  | 70896.8855 |  | 70896.8855
2026-04-21 | 212732.3144 |  | 70910.7715 |  | 70910.7715 |  | 70910.7715
2026-04-22 | 212773.9723 |  | 70924.6574 |  | 70924.6574 |  | 70924.6574
2026-04-23 | 212815.6302 |  | 70938.5434 |  | 70938.5434 |  | 70938.5434
2026-04-24 | 212857.2881 |  | 70952.4294 |  | 70952.4294 |  | 70952.4294
2026-04-25 | 212898.946 |  | 70966.3153 |  | 70966.3153 |  | 70966.3153
2026-04-26 | 212940.6039 |  | 70980.2013 |  | 70980.2013 |  | 70980.2013
2026-04-27 | 212982.2618 |  | 70994.0873 |  | 70994.0873 |  | 70994.0873
2026-04-28 | 213023.9197 |  | 71007.9732 |  | 71007.9732 |  | 71007.9732
2026-04-29 | 213065.5776 |  | 71021.8592 |  | 71021.8592 |  | 71021.8592
2026-04-30 | 213107.2355 |  | 71035.7452 |  | 71035.7452 |  | 71035.7452
2026-05-01 | 213148.8934 |  | 71049.6311 |  | 71049.6311 |  | 71049.6311
2026-05-02 | 213190.5513 |  | 71063.5171 |  | 71063.5171 |  | 71063.5171
2026-05-03 | 213232.2092 |  | 71077.4031 |  | 71077.4031 |  | 71077.4031
2026-05-04 | 213273.867 |  | 71091.289 |  | 71091.289 |  | 71091.289
2026-05-05 | 213315.5249 |  | 71105.175 |  | 71105.175 |  | 71105.175
2026-05-06 | 213357.1828 |  | 71119.0609 |  | 71119.0609 |  | 71119.0609
2026-05-07 | 213398.8407 |  | 71132.9469 |  | 71132.9469 |  | 71132.9469
2026-05-08 | 213440.4986 |  | 71146.8329 |  | 71146.8329 |  | 71146.8329
2026-05-09 | 213482.1565 |  | 71160.7188 |  | 71160.7188 |  | 71160.7188
2026-05-10 | 213523.8144 |  | 71174.6048 |  | 71174.6048 |  | 71174.6048
2026-05-11 | 213565.4723 |  | 71188.4908 |  | 71188.4908 |  | 71188.4908
2026-05-12 | 213607.1302 |  | 71202.3767 |  | 71202.3767 |  | 71202.3767
2026-05-13 | 213648.7881 |  | 71216.2627 |  | 71216.2627 |  | 71216.2627
2026-05-14 | 213690.446 |  | 71230.1487 |  | 71230.1487 |  | 71230.1487
2026-05-15 | 213732.1039 |  | 71244.0346 |  | 71244.0346 |  | 71244.0346
2026-05-16 | 213773.7618 |  | 71257.9206 |  | 71257.9206 |  | 71257.9206
2026-05-17 | 213815.4197 |  | 71271.8066 |  | 71271.8066 |  | 71271.8066
2026-05-18 | 213857.0776 |  | 71285.6925 |  | 71285.6925 |  | 71285.6925
2026-05-19 | 213898.7355 |  | 71299.5785 |  | 71299.5785 |  | 71299.5785
2026-05-20 | 213940.3934 |  | 71313.4645 |  | 71313.4645 |  | 71313.4645
2026-05-21 | 213982.0513 |  | 71327.3504 |  | 71327.3504 |  | 71327.3504
2026-05-22 | 214023.7092 |  | 71341.2364 |  | 71341.2364 |  | 71341.2364
2026-05-23 | 214065.367 |  | 71355.1223 |  | 71355.1223 |  | 71355.1223
2026-05-24 | 214107.0249 |  | 71369.0083 |  | 71369.0083 |  | 71369.0083
2026-05-25 | 214148.6828 |  | 71382.8943 |  | 71382.8943 |  | 71382.8943
2026-05-26 | 214190.3407 |  | 71396.7802 |  | 71396.7802 |  | 71396.7802
2026-05-27 | 214231.9986 |  | 71410.6662 |  | 71410.6662 |  | 71410.6662
2026-05-28 | 214273.6565 |  | 71424.5522 |  | 71424.5522 |  | 71424.5522
2026-05-29 | 214315.3144 |  | 71438.4381 |  | 71438.4381 |  | 71438.4381
2026-05-30 | 214356.9723 |  | 71452.3241 |  | 71452.3241 |  | 71452.3241
2026-05-31 | 214398.6302 |  | 71466.2101 |  | 71466.2101 |  | 71466.2101
2026-06-01 | 214440.2881 |  | 71480.096 |  | 71480.096 |  | 71480.096
2026-06-02 | 214481.946 |  | 71493.982 |  | 71493.982 |  | 71493.982
2026-06-03 | 214523.6039 |  | 71507.868 |  | 71507.868 |  | 71507.868
2026-06-04 | 214565.2618 |  | 71521.7539 |  | 71521.7539 |  | 71521.7539
2026-06-05 | 214606.9197 |  | 71535.6399 |  | 71535.6399 |  | 71535.6399
2026-06-06 | 214648.5776 |  | 71549.5259 |  | 71549.5259 |  | 71549.5259
2026-06-07 | 214690.2355 |  | 71563.4118 |  | 71563.4118 |  | 71563.4118
2026-06-08 | 214731.8934 |  | 71577.2978 |  | 71577.2978 |  | 71577.2978
2026-06-09 | 214773.5513 |  | 71591.1838 |  | 71591.1838 |  | 71591.1838
2026-06-10 | 214815.2092 |  | 71605.0697 |  | 71605.0697 |  | 71605.0697
2026-06-11 | 214856.867 |  | 71618.9557 |  | 71618.9557 |  | 71618.9557
2026-06-12 | 214898.5249 |  | 71632.8416 |  | 71632.8416 |  | 71632.8416
2026-06-13 | 214940.1828 |  | 71646.7276 |  | 71646.7276 |  | 71646.7276
2026-06-14 | 214981.8407 |  | 71660.6136 |  | 71660.6136 |  | 71660.6136
2026-06-15 | 215023.4986 |  | 71674.4995 |  | 71674.4995 |  | 71674.4995
2026-06-16 | 215065.1565 |  | 71688.3855 |  | 71688.3855 |  | 71688.3855
2026-06-17 | 215106.8144 |  | 71702.2715 |  | 71702.2715 |  | 71702.2715
2026-06-18 | 215148.4723 |  | 71716.1574 |  | 71716.1574 |  | 71716.1574
2026-06-19 | 215190.1302 |  | 71730.0434 |  | 71730.0434 |  | 71730.0434
2026-06-20 | 215231.7881 |  | 71743.9294 |  | 71743.9294 |  | 71743.9294
2026-06-21 | 215273.446 |  | 71757.8153 |  | 71757.8153 |  | 71757.8153
2026-06-22 | 215315.1039 |  | 71771.7013 |  | 71771.7013 |  | 71771.7013
2026-06-23 | 215356.7618 |  | 71785.5873 |  | 71785.5873 |  | 71785.5873
2026-06-24 | 215398.4197 |  | 71799.4732 |  | 71799.4732 |  | 71799.4732
2026-06-25 | 215440.0776 |  | 71813.3592 |  | 71813.3592 |  | 71813.3592
2026-06-26 | 215481.7355 |  | 71827.2452 |  | 71827.2452 |  | 71827.2452
2026-06-27 | 215523.3934 |  | 71841.1311 |  | 71841.1311 |  | 71841.1311
2026-06-28 | 215565.0513 |  | 71855.0171 |  | 71855.0171 |  | 71855.0171
2026-06-29 | 215606.7092 |  | 71868.9031 |  | 71868.9031 |  | 71868.9031
2026-06-30 | 215648.367 |  | 71882.789 |  | 71882.789 |  | 71882.789
2026-07-01 | 215690.0249 |  | 71896.675 |  | 71896.675 |  | 71896.675
2026-07-02 | 215731.6828 |  | 71910.5609 |  | 71910.5609 |  | 71910.5609
2026-07-03 | 215773.3407 |  | 71924.4469 |  | 71924.4469 |  | 71924.4469
2026-07-04 | 215814.9986 |  | 71938.3329 |  | 71938.3329 |  | 71938.3329
2026-07-05 | 215856.6565 |  | 71952.2188 |  | 71952.2188 |  | 71952.2188
2026-07-06 | 215898.3144 |  | 71966.1048 |  | 71966.1048 |  | 71966.1048
2026-07-07 | 215939.9723 |  | 71979.9908 |  | 71979.9908 |  | 71979.9908
2026-07-08 | 215981.6302 |  | 71993.8767 |  | 71993.8767 |  | 71993.8767
2026-07-09 | 216023.2881 |  | 72007.7627 |  | 72007.7627 |  | 72007.7627
2026-07-10 | 216064.946 |  | 72021.6487 |  | 72021.6487 |  | 72021.6487
2026-07-11 | 216106.6039 |  | 72035.5346 |  | 72035.5346 |  | 72035.5346
2026-07-12 | 216148.2618 |  | 72049.4206 |  | 72049.4206 |  | 72049.4206
2026-07-13 | 216189.9197 |  | 72063.3066 |  | 72063.3066 |  | 72063.3066
2026-07-14 | 216231.5776 |  | 72077.1925 |  | 72077.1925 |  | 72077.1925
2026-07-15 | 216273.2355 |  | 72091.0785 |  | 72091.0785 |  | 72091.0785
2026-07-16 | 216314.8934 |  | 72104.9645 |  | 72104.9645 |  | 72104.9645
2026-07-17 | 216356.5513 |  | 72118.8504 |  | 72118.8504 |  | 72118.8504
2026-07-18 | 216398.2092 |  | 72132.7364 |  | 72132.7364 |  | 72132.7364
2026-07-19 | 216439.867 |  | 72146.6223 |  | 72146.6223 |  | 72146.6223
2026-07-20 | 216481.5249 |  | 72160.5083 |  | 72160.5083 |  | 72160.5083
2026-07-21 | 216523.1828 |  | 72174.3943 |  | 72174.3943 |  | 72174.3943
2026-07-22 | 216564.8407 |  | 72188.2802 |  | 72188.2802 |  | 72188.2802
2026-07-23 | 216606.4986 |  | 72202.1662 |  | 72202.1662 |  | 72202.1662
2026-07-24 | 216648.1565 |  | 72216.0522 |  | 72216.0522 |  | 72216.0522
2026-07-25 | 216689.8144 |  | 72229.9381 |  | 72229.9381 |  | 72229.9381
2026-07-26 | 216731.4723 |  | 72243.8241 |  | 72243.8241 |  | 72243.8241
2026-07-27 | 216773.1302 |  | 72257.7101 |  | 72257.7101 |  | 72257.7101
2026-07-28 | 216814.7881 |  | 72271.596 |  | 72271.596 |  | 72271.596
2026-07-29 | 216856.446 |  | 72285.482 |  | 72285.482 |  | 72285.482
2026-07-30 | 216898.1039 |  | 72299.368 |  | 72299.368 |  | 72299.368
2026-07-31 | 216939.7618 |  | 72313.2539 |  | 72313.2539 |  | 72313.2539
2026-08-01 | 216981.4197 |  | 72327.1399 |  | 72327.1399 |  | 72327.1399
2026-08-02 | 217023.0776 |  | 72341.0259 |  | 72341.0259 |  | 72341.0259
2026-08-03 | 217064.7355 |  | 72354.9118 |  | 72354.9118 |  | 72354.9118
2026-08-04 | 217106.3934 |  | 72368.7978 |  | 72368.7978 |  | 72368.7978
2026-08-05 | 217148.0513 |  | 72382.6838 |  | 72382.6838 |  | 72382.6838
2026-08-06 | 217189.7092 |  | 72396.5697 |  | 72396.5697 |  | 72396.5697
2026-08-07 | 217231.367 |  | 72410.4557 |  | 72410.4557 |  | 72410.4557
2026-08-08 | 217273.0249 |  | 72424.3416 |  | 72424.3416 |  | 72424.3416
2026-08-09 | 217314.6828 |  | 72438.2276 |  | 72438.2276 |  | 72438.2276
2026-08-10 | 217356.3407 |  | 72452.1136 |  | 72452.1136 |  | 72452.1136
2026-08-11 | 217397.9986 |  | 72465.9995 |  | 72465.9995 |  | 72465.9995
2026-08-12 | 217439.6565 |  | 72479.8855 |  | 72479.8855 |  | 72479.8855
2026-08-13 | 217733.7742 |  | 72577.9247 |  | 72577.9247 |  | 72577.9247
2026-08-14 | 218027.8918 |  | 72675.9639 |  | 72675.9639 |  | 72675.9639
2026-08-15 | 218322.0095 |  | 72774.0032 |  | 72774.0032 |  | 72774.0032
2026-08-16 | 218616.1271 |  | 72872.0424 |  | 72872.0424 |  | 72872.0424
2026-08-17 | 218910.2448 |  | 72970.0816 |  | 72970.0816 |  | 72970.0816
2026-08-18 | 219204.3624 |  | 73068.1208 |  | 73068.1208 |  | 73068.1208
2026-08-19 | 219498.4801 |  | 73166.16 |  | 73166.16 |  | 73166.16
2026-08-20 | 219792.5977 |  | 73264.1992 |  | 73264.1992 |  | 73264.1992
2026-08-21 | 220086.7153 |  | 73362.2384 |  | 73362.2384 |  | 73362.2384
2026-08-22 | 220380.833 |  | 73460.2777 |  | 73460.2777 |  | 73460.2777
2026-08-23 | 220674.9506 |  | 73558.3169 |  | 73558.3169 |  | 73558.3169
2026-08-24 | 220969.0683 |  | 73656.3561 |  | 73656.3561 |  | 73656.3561
2026-08-25 | 221263.1859 |  | 73754.3953 |  | 73754.3953 |  | 73754.3953
2026-08-26 | 221557.3036 |  | 73852.4345 |  | 73852.4345 |  | 73852.4345
2026-08-27 | 221851.4212 |  | 73950.4737 |  | 73950.4737 |  | 73950.4737
2026-08-28 | 222145.5389 |  | 74048.513 |  | 74048.513 |  | 74048.513
2026-08-29 | 222439.6565 |  | 74146.5522 |  | 74146.5522 |  | 74146.5522
2026-08-30 | 222733.7742 |  | 74244.5914 |  | 74244.5914 |  | 74244.5914
2026-08-31 | 223027.8918 |  | 74342.6306 |  | 74342.6306 |  | 74342.6306
2026-09-01 | 223322.0095 |  | 74440.6698 |  | 74440.6698 |  | 74440.6698
2026-09-02 | 223616.1271 |  | 74538.709 |  | 74538.709 |  | 74538.709
2026-09-03 | 223910.2448 |  | 74636.7483 |  | 74636.7483 |  | 74636.7483
2026-09-04 | 224204.3624 |  | 74734.7875 |  | 74734.7875 |  | 74734.7875
2026-09-05 | 224498.4801 |  | 74832.8267 |  | 74832.8267 |  | 74832.8267
2026-09-06 | 224792.5977 |  | 74930.8659 |  | 74930.8659 |  | 74930.8659
2026-09-07 | 225086.7153 |  | 75028.9051 |  | 75028.9051 |  | 75028.9051
2026-09-08 | 225380.833 |  | 75126.9443 |  | 75126.9443 |  | 75126.9443
2026-09-09 | 225674.9506 |  | 75224.9835 |  | 75224.9835 |  | 75224.9835
2026-09-10 | 225969.0683 |  | 75323.0228 |  | 75323.0228 |  | 75323.0228
2026-09-11 | 226263.1859 |  | 75421.062 |  | 75421.062 |  | 75421.062
2026-09-12 | 226557.3036 |  | 75519.1012 |  | 75519.1012 |  | 75519.1012
2026-09-13 | 226851.4212 |  | 75617.1404 |  | 75617.1404 |  | 75617.1404
2026-09-14 | 227145.5389 |  | 75715.1796 |  | 75715.1796 |  | 75715.1796
2026-09-15 | 227439.6565 |  | 75813.2188 |  | 75813.2188 |  | 75813.2188

## Outsource (Direct Cost)
Date | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Planned 5006 · Drilling Expense (Cumulative) | Actual 5006 · Drilling Expense (Cumulative) | Planned 5110 · Temporary labor (Direct) (Cumulative) | Actual 5110 · Temporary labor (Direct) (Cumulative) | Planned 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Actual 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Planned 5114 · Rent - Building (Direct) (Cumulative) | Actual 5114 · Rent - Building (Direct) (Cumulative) | Planned 5115 · Rent - Equipment (direct) (Cumulative) | Actual 5115 · Rent - Equipment (direct) (Cumulative) | Planned 5116 · Rent - Storage (Direct) (Cumulative) | Actual 5116 · Rent - Storage (Direct) (Cumulative) | Planned 5120 · Outside services (Direct) (Cumulative) | Actual 5120 · Outside services (Direct) (Cumulative) | Planned 5121 · Freight & Shipping (Direct) (Cumulative) | Actual 5121 · Freight & Shipping (Direct) (Cumulative) | Planned 5124 · License and permits (Direct) (Cumulative) | Actual 5124 · License and permits (Direct) (Cumulative) | Planned 5129 · Misc expenses (Direct) (Cumulative) | Actual 5129 · Misc expenses (Direct) (Cumulative) | Planned 5132 · Internet fee (Direct) (Cumulative) | Actual 5132 · Internet fee (Direct) (Cumulative) | Planned 6999 · Uncategorized Expenses (Cumulative) | Actual 6999 · Uncategorized Expenses (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 129.935 | 0 | 10.8279 | 0 | 10.8279 | 0 | 10.8279 | 0 | 10.8279 | 0 | 10.8279 | 0 | 10.8279 | 0 | 10.8279 | 0 | 10.8279 | 0 | 10.8279 | 0 | 10.8279 | 0 | 10.8279 | 0 | 10.8279 | 0
2025-06-26 | 259.8701 | 0 | 21.6558 | 0 | 21.6558 | 0 | 21.6558 | 0 | 21.6558 | 0 | 21.6558 | 0 | 21.6558 | 0 | 21.6558 | 0 | 21.6558 | 0 | 21.6558 | 0 | 21.6558 | 0 | 21.6558 | 0 | 21.6558 | 0
2025-06-27 | 389.8051 | 0 | 32.4838 | 0 | 32.4838 | 0 | 32.4838 | 0 | 32.4838 | 0 | 32.4838 | 0 | 32.4838 | 0 | 32.4838 | 0 | 32.4838 | 0 | 32.4838 | 0 | 32.4838 | 0 | 32.4838 | 0 | 32.4838 | 0
2025-06-28 | 519.7401 | 0 | 43.3117 | 0 | 43.3117 | 0 | 43.3117 | 0 | 43.3117 | 0 | 43.3117 | 0 | 43.3117 | 0 | 43.3117 | 0 | 43.3117 | 0 | 43.3117 | 0 | 43.3117 | 0 | 43.3117 | 0 | 43.3117 | 0
2025-06-29 | 649.6752 | 0 | 54.1396 | 0 | 54.1396 | 0 | 54.1396 | 0 | 54.1396 | 0 | 54.1396 | 0 | 54.1396 | 0 | 54.1396 | 0 | 54.1396 | 0 | 54.1396 | 0 | 54.1396 | 0 | 54.1396 | 0 | 54.1396 | 0
2025-06-30 | 779.6102 | 0 | 64.9675 | 0 | 64.9675 | 0 | 64.9675 | 0 | 64.9675 | 0 | 64.9675 | 0 | 64.9675 | 0 | 64.9675 | 0 | 64.9675 | 0 | 64.9675 | 0 | 64.9675 | 0 | 64.9675 | 0 | 64.9675 | 0
2025-07-01 | 909.5452 | 0 | 75.7954 | 0 | 75.7954 | 0 | 75.7954 | 0 | 75.7954 | 0 | 75.7954 | 0 | 75.7954 | 0 | 75.7954 | 0 | 75.7954 | 0 | 75.7954 | 0 | 75.7954 | 0 | 75.7954 | 0 | 75.7954 | 0
2025-07-02 | 1039.4803 | 0 | 86.6234 | 0 | 86.6234 | 0 | 86.6234 | 0 | 86.6234 | 0 | 86.6234 | 0 | 86.6234 | 0 | 86.6234 | 0 | 86.6234 | 0 | 86.6234 | 0 | 86.6234 | 0 | 86.6234 | 0 | 86.6234 | 0
2025-07-03 | 1169.4153 | 0 | 97.4513 | 0 | 97.4513 | 0 | 97.4513 | 0 | 97.4513 | 0 | 97.4513 | 0 | 97.4513 | 0 | 97.4513 | 0 | 97.4513 | 0 | 97.4513 | 0 | 97.4513 | 0 | 97.4513 | 0 | 97.4513 | 0
2025-07-04 | 1299.3503 | 0 | 108.2792 | 0 | 108.2792 | 0 | 108.2792 | 0 | 108.2792 | 0 | 108.2792 | 0 | 108.2792 | 0 | 108.2792 | 0 | 108.2792 | 0 | 108.2792 | 0 | 108.2792 | 0 | 108.2792 | 0 | 108.2792 | 0
2025-07-05 | 1429.2854 | 0 | 119.1071 | 0 | 119.1071 | 0 | 119.1071 | 0 | 119.1071 | 0 | 119.1071 | 0 | 119.1071 | 0 | 119.1071 | 0 | 119.1071 | 0 | 119.1071 | 0 | 119.1071 | 0 | 119.1071 | 0 | 119.1071 | 0
2025-07-06 | 1559.2204 | 0 | 129.935 | 0 | 129.935 | 0 | 129.935 | 0 | 129.935 | 0 | 129.935 | 0 | 129.935 | 0 | 129.935 | 0 | 129.935 | 0 | 129.935 | 0 | 129.935 | 0 | 129.935 | 0 | 129.935 | 0
2025-07-07 | 1689.1554 | 0 | 140.763 | 0 | 140.763 | 0 | 140.763 | 0 | 140.763 | 0 | 140.763 | 0 | 140.763 | 0 | 140.763 | 0 | 140.763 | 0 | 140.763 | 0 | 140.763 | 0 | 140.763 | 0 | 140.763 | 0
2025-07-08 | 1819.0905 | 0 | 151.5909 | 0 | 151.5909 | 0 | 151.5909 | 0 | 151.5909 | 0 | 151.5909 | 0 | 151.5909 | 0 | 151.5909 | 0 | 151.5909 | 0 | 151.5909 | 0 | 151.5909 | 0 | 151.5909 | 0 | 151.5909 | 0
2025-07-09 | 1949.0255 | 0 | 162.4188 | 0 | 162.4188 | 0 | 162.4188 | 0 | 162.4188 | 0 | 162.4188 | 0 | 162.4188 | 0 | 162.4188 | 0 | 162.4188 | 0 | 162.4188 | 0 | 162.4188 | 0 | 162.4188 | 0 | 162.4188 | 0
2025-07-10 | 2078.9605 | 0 | 173.2467 | 0 | 173.2467 | 0 | 173.2467 | 0 | 173.2467 | 0 | 173.2467 | 0 | 173.2467 | 0 | 173.2467 | 0 | 173.2467 | 0 | 173.2467 | 0 | 173.2467 | 0 | 173.2467 | 0 | 173.2467 | 0
2025-07-11 | 2208.8956 | 0 | 184.0746 | 0 | 184.0746 | 0 | 184.0746 | 0 | 184.0746 | 0 | 184.0746 | 0 | 184.0746 | 0 | 184.0746 | 0 | 184.0746 | 0 | 184.0746 | 0 | 184.0746 | 0 | 184.0746 | 0 | 184.0746 | 0
2025-07-12 | 2338.8306 | 0 | 194.9025 | 0 | 194.9025 | 0 | 194.9025 | 0 | 194.9025 | 0 | 194.9025 | 0 | 194.9025 | 0 | 194.9025 | 0 | 194.9025 | 0 | 194.9025 | 0 | 194.9025 | 0 | 194.9025 | 0 | 194.9025 | 0
2025-07-13 | 2468.7656 | 0 | 205.7305 | 0 | 205.7305 | 0 | 205.7305 | 0 | 205.7305 | 0 | 205.7305 | 0 | 205.7305 | 0 | 205.7305 | 0 | 205.7305 | 0 | 205.7305 | 0 | 205.7305 | 0 | 205.7305 | 0 | 205.7305 | 0
2025-07-14 | 2598.7006 | 0 | 216.5584 | 0 | 216.5584 | 0 | 216.5584 | 0 | 216.5584 | 0 | 216.5584 | 0 | 216.5584 | 0 | 216.5584 | 0 | 216.5584 | 0 | 216.5584 | 0 | 216.5584 | 0 | 216.5584 | 0 | 216.5584 | 0
2025-07-15 | 2728.6357 | 0 | 227.3863 | 0 | 227.3863 | 0 | 227.3863 | 0 | 227.3863 | 0 | 227.3863 | 0 | 227.3863 | 0 | 227.3863 | 0 | 227.3863 | 0 | 227.3863 | 0 | 227.3863 | 0 | 227.3863 | 0 | 227.3863 | 0
2025-07-16 | 2858.5707 | 0 | 238.2142 | 0 | 238.2142 | 0 | 238.2142 | 0 | 238.2142 | 0 | 238.2142 | 0 | 238.2142 | 0 | 238.2142 | 0 | 238.2142 | 0 | 238.2142 | 0 | 238.2142 | 0 | 238.2142 | 0 | 238.2142 | 0
2025-07-17 | 2988.5057 | 0 | 249.0421 | 0 | 249.0421 | 0 | 249.0421 | 0 | 249.0421 | 0 | 249.0421 | 0 | 249.0421 | 0 | 249.0421 | 0 | 249.0421 | 0 | 249.0421 | 0 | 249.0421 | 0 | 249.0421 | 0 | 249.0421 | 0
2025-07-18 | 3118.4408 | 0 | 259.8701 | 0 | 259.8701 | 0 | 259.8701 | 0 | 259.8701 | 0 | 259.8701 | 0 | 259.8701 | 0 | 259.8701 | 0 | 259.8701 | 0 | 259.8701 | 0 | 259.8701 | 0 | 259.8701 | 0 | 259.8701 | 0
2025-07-19 | 3248.3758 | 0 | 270.698 | 0 | 270.698 | 0 | 270.698 | 0 | 270.698 | 0 | 270.698 | 0 | 270.698 | 0 | 270.698 | 0 | 270.698 | 0 | 270.698 | 0 | 270.698 | 0 | 270.698 | 0 | 270.698 | 0
2025-07-20 | 3378.3108 | 0 | 281.5259 | 0 | 281.5259 | 0 | 281.5259 | 0 | 281.5259 | 0 | 281.5259 | 0 | 281.5259 | 0 | 281.5259 | 0 | 281.5259 | 0 | 281.5259 | 0 | 281.5259 | 0 | 281.5259 | 0 | 281.5259 | 0
2025-07-21 | 3508.2459 | 0 | 292.3538 | 0 | 292.3538 | 0 | 292.3538 | 0 | 292.3538 | 0 | 292.3538 | 0 | 292.3538 | 0 | 292.3538 | 0 | 292.3538 | 0 | 292.3538 | 0 | 292.3538 | 0 | 292.3538 | 0 | 292.3538 | 0
2025-07-22 | 3638.1809 | 500 | 303.1817 | 0 | 303.1817 | 0 | 303.1817 | 0 | 303.1817 | 0 | 303.1817 | 0 | 303.1817 | 0 | 303.1817 | 0 | 303.1817 | 0 | 303.1817 | 500 | 303.1817 | 0 | 303.1817 | 0 | 303.1817 | 0
2025-07-23 | 3768.1159 | 500 | 314.0097 | 0 | 314.0097 | 0 | 314.0097 | 0 | 314.0097 | 0 | 314.0097 | 0 | 314.0097 | 0 | 314.0097 | 0 | 314.0097 | 0 | 314.0097 | 500 | 314.0097 | 0 | 314.0097 | 0 | 314.0097 | 0
2025-07-24 | 3898.051 | 500 | 324.8376 | 0 | 324.8376 | 0 | 324.8376 | 0 | 324.8376 | 0 | 324.8376 | 0 | 324.8376 | 0 | 324.8376 | 0 | 324.8376 | 0 | 324.8376 | 500 | 324.8376 | 0 | 324.8376 | 0 | 324.8376 | 0
2025-07-25 | 4027.986 | 500 | 335.6655 | 0 | 335.6655 | 0 | 335.6655 | 0 | 335.6655 | 0 | 335.6655 | 0 | 335.6655 | 0 | 335.6655 | 0 | 335.6655 | 0 | 335.6655 | 500 | 335.6655 | 0 | 335.6655 | 0 | 335.6655 | 0
2025-07-26 | 4157.921 | 500 | 346.4934 | 0 | 346.4934 | 0 | 346.4934 | 0 | 346.4934 | 0 | 346.4934 | 0 | 346.4934 | 0 | 346.4934 | 0 | 346.4934 | 0 | 346.4934 | 500 | 346.4934 | 0 | 346.4934 | 0 | 346.4934 | 0
2025-07-27 | 4287.8561 | 500 | 357.3213 | 0 | 357.3213 | 0 | 357.3213 | 0 | 357.3213 | 0 | 357.3213 | 0 | 357.3213 | 0 | 357.3213 | 0 | 357.3213 | 0 | 357.3213 | 500 | 357.3213 | 0 | 357.3213 | 0 | 357.3213 | 0
2025-07-28 | 4417.7911 | 500 | 368.1493 | 0 | 368.1493 | 0 | 368.1493 | 0 | 368.1493 | 0 | 368.1493 | 0 | 368.1493 | 0 | 368.1493 | 0 | 368.1493 | 0 | 368.1493 | 500 | 368.1493 | 0 | 368.1493 | 0 | 368.1493 | 0
2025-07-29 | 4547.7261 | 500 | 378.9772 | 0 | 378.9772 | 0 | 378.9772 | 0 | 378.9772 | 0 | 378.9772 | 0 | 378.9772 | 0 | 378.9772 | 0 | 378.9772 | 0 | 378.9772 | 500 | 378.9772 | 0 | 378.9772 | 0 | 378.9772 | 0
2025-07-30 | 4677.6612 | 500 | 389.8051 | 0 | 389.8051 | 0 | 389.8051 | 0 | 389.8051 | 0 | 389.8051 | 0 | 389.8051 | 0 | 389.8051 | 0 | 389.8051 | 0 | 389.8051 | 500 | 389.8051 | 0 | 389.8051 | 0 | 389.8051 | 0
2025-07-31 | 4807.5962 | 500 | 400.633 | 0 | 400.633 | 0 | 400.633 | 0 | 400.633 | 0 | 400.633 | 0 | 400.633 | 0 | 400.633 | 0 | 400.633 | 0 | 400.633 | 500 | 400.633 | 0 | 400.633 | 0 | 400.633 | 0
2025-08-01 | 4937.5312 | 500 | 411.4609 | 0 | 411.4609 | 0 | 411.4609 | 0 | 411.4609 | 0 | 411.4609 | 0 | 411.4609 | 0 | 411.4609 | 0 | 411.4609 | 0 | 411.4609 | 500 | 411.4609 | 0 | 411.4609 | 0 | 411.4609 | 0
2025-08-02 | 5067.4663 | 500 | 422.2889 | 0 | 422.2889 | 0 | 422.2889 | 0 | 422.2889 | 0 | 422.2889 | 0 | 422.2889 | 0 | 422.2889 | 0 | 422.2889 | 0 | 422.2889 | 500 | 422.2889 | 0 | 422.2889 | 0 | 422.2889 | 0
2025-08-03 | 5197.4013 | 500 | 433.1168 | 0 | 433.1168 | 0 | 433.1168 | 0 | 433.1168 | 0 | 433.1168 | 0 | 433.1168 | 0 | 433.1168 | 0 | 433.1168 | 0 | 433.1168 | 500 | 433.1168 | 0 | 433.1168 | 0 | 433.1168 | 0
2025-08-04 | 5327.3363 | 500 | 443.9447 | 0 | 443.9447 | 0 | 443.9447 | 0 | 443.9447 | 0 | 443.9447 | 0 | 443.9447 | 0 | 443.9447 | 0 | 443.9447 | 0 | 443.9447 | 500 | 443.9447 | 0 | 443.9447 | 0 | 443.9447 | 0
2025-08-05 | 5457.2714 | 500 | 454.7726 | 0 | 454.7726 | 0 | 454.7726 | 0 | 454.7726 | 0 | 454.7726 | 0 | 454.7726 | 0 | 454.7726 | 0 | 454.7726 | 0 | 454.7726 | 500 | 454.7726 | 0 | 454.7726 | 0 | 454.7726 | 0
2025-08-06 | 5587.2064 | 500 | 465.6005 | 0 | 465.6005 | 0 | 465.6005 | 0 | 465.6005 | 0 | 465.6005 | 0 | 465.6005 | 0 | 465.6005 | 0 | 465.6005 | 0 | 465.6005 | 500 | 465.6005 | 0 | 465.6005 | 0 | 465.6005 | 0
2025-08-07 | 5717.1414 | 500 | 476.4285 | 0 | 476.4285 | 0 | 476.4285 | 0 | 476.4285 | 0 | 476.4285 | 0 | 476.4285 | 0 | 476.4285 | 0 | 476.4285 | 0 | 476.4285 | 500 | 476.4285 | 0 | 476.4285 | 0 | 476.4285 | 0
2025-08-08 | 5847.0765 | 500 | 487.2564 | 0 | 487.2564 | 0 | 487.2564 | 0 | 487.2564 | 0 | 487.2564 | 0 | 487.2564 | 0 | 487.2564 | 0 | 487.2564 | 0 | 487.2564 | 500 | 487.2564 | 0 | 487.2564 | 0 | 487.2564 | 0
2025-08-09 | 5977.0115 | 500 | 498.0843 | 0 | 498.0843 | 0 | 498.0843 | 0 | 498.0843 | 0 | 498.0843 | 0 | 498.0843 | 0 | 498.0843 | 0 | 498.0843 | 0 | 498.0843 | 500 | 498.0843 | 0 | 498.0843 | 0 | 498.0843 | 0
2025-08-10 | 6106.9465 | 500 | 508.9122 | 0 | 508.9122 | 0 | 508.9122 | 0 | 508.9122 | 0 | 508.9122 | 0 | 508.9122 | 0 | 508.9122 | 0 | 508.9122 | 0 | 508.9122 | 500 | 508.9122 | 0 | 508.9122 | 0 | 508.9122 | 0
2025-08-11 | 6236.8816 | 500 | 519.7401 | 0 | 519.7401 | 0 | 519.7401 | 0 | 519.7401 | 0 | 519.7401 | 0 | 519.7401 | 0 | 519.7401 | 0 | 519.7401 | 0 | 519.7401 | 500 | 519.7401 | 0 | 519.7401 | 0 | 519.7401 | 0
2025-08-12 | 6366.8166 | 500 | 530.568 | 0 | 530.568 | 0 | 530.568 | 0 | 530.568 | 0 | 530.568 | 0 | 530.568 | 0 | 530.568 | 0 | 530.568 | 0 | 530.568 | 500 | 530.568 | 0 | 530.568 | 0 | 530.568 | 0
2025-08-13 | 6496.7516 | 500 | 541.396 | 0 | 541.396 | 0 | 541.396 | 0 | 541.396 | 0 | 541.396 | 0 | 541.396 | 0 | 541.396 | 0 | 541.396 | 0 | 541.396 | 500 | 541.396 | 0 | 541.396 | 0 | 541.396 | 0
2025-08-14 | 6626.6867 | 500 | 552.2239 | 0 | 552.2239 | 0 | 552.2239 | 0 | 552.2239 | 0 | 552.2239 | 0 | 552.2239 | 0 | 552.2239 | 0 | 552.2239 | 0 | 552.2239 | 500 | 552.2239 | 0 | 552.2239 | 0 | 552.2239 | 0
2025-08-15 | 6756.6217 | 500 | 563.0518 | 0 | 563.0518 | 0 | 563.0518 | 0 | 563.0518 | 0 | 563.0518 | 0 | 563.0518 | 0 | 563.0518 | 0 | 563.0518 | 0 | 563.0518 | 500 | 563.0518 | 0 | 563.0518 | 0 | 563.0518 | 0
2025-08-16 | 6886.5567 | 500 | 573.8797 | 0 | 573.8797 | 0 | 573.8797 | 0 | 573.8797 | 0 | 573.8797 | 0 | 573.8797 | 0 | 573.8797 | 0 | 573.8797 | 0 | 573.8797 | 500 | 573.8797 | 0 | 573.8797 | 0 | 573.8797 | 0
2025-08-17 | 7016.4918 | 500 | 584.7076 | 0 | 584.7076 | 0 | 584.7076 | 0 | 584.7076 | 0 | 584.7076 | 0 | 584.7076 | 0 | 584.7076 | 0 | 584.7076 | 0 | 584.7076 | 500 | 584.7076 | 0 | 584.7076 | 0 | 584.7076 | 0
2025-08-18 | 7146.4268 | 500 | 595.5356 | 0 | 595.5356 | 0 | 595.5356 | 0 | 595.5356 | 0 | 595.5356 | 0 | 595.5356 | 0 | 595.5356 | 0 | 595.5356 | 0 | 595.5356 | 500 | 595.5356 | 0 | 595.5356 | 0 | 595.5356 | 0
2025-08-19 | 7276.3618 | 500 | 606.3635 | 0 | 606.3635 | 0 | 606.3635 | 0 | 606.3635 | 0 | 606.3635 | 0 | 606.3635 | 0 | 606.3635 | 0 | 606.3635 | 0 | 606.3635 | 500 | 606.3635 | 0 | 606.3635 | 0 | 606.3635 | 0
2025-08-20 | 7406.2969 | 500 | 617.1914 | 0 | 617.1914 | 0 | 617.1914 | 0 | 617.1914 | 0 | 617.1914 | 0 | 617.1914 | 0 | 617.1914 | 0 | 617.1914 | 0 | 617.1914 | 500 | 617.1914 | 0 | 617.1914 | 0 | 617.1914 | 0
2025-08-21 | 7536.2319 | 500 | 628.0193 | 0 | 628.0193 | 0 | 628.0193 | 0 | 628.0193 | 0 | 628.0193 | 0 | 628.0193 | 0 | 628.0193 | 0 | 628.0193 | 0 | 628.0193 | 500 | 628.0193 | 0 | 628.0193 | 0 | 628.0193 | 0
2025-08-22 | 7666.1669 | 500 | 638.8472 | 0 | 638.8472 | 0 | 638.8472 | 0 | 638.8472 | 0 | 638.8472 | 0 | 638.8472 | 0 | 638.8472 | 0 | 638.8472 | 0 | 638.8472 | 500 | 638.8472 | 0 | 638.8472 | 0 | 638.8472 | 0
2025-08-23 | 7796.1019 | 500 | 649.6752 | 0 | 649.6752 | 0 | 649.6752 | 0 | 649.6752 | 0 | 649.6752 | 0 | 649.6752 | 0 | 649.6752 | 0 | 649.6752 | 0 | 649.6752 | 500 | 649.6752 | 0 | 649.6752 | 0 | 649.6752 | 0
2025-08-24 | 7926.037 | 500 | 660.5031 | 0 | 660.5031 | 0 | 660.5031 | 0 | 660.5031 | 0 | 660.5031 | 0 | 660.5031 | 0 | 660.5031 | 0 | 660.5031 | 0 | 660.5031 | 500 | 660.5031 | 0 | 660.5031 | 0 | 660.5031 | 0
2025-08-25 | 8055.972 | 515 | 671.331 | 0 | 671.331 | 0 | 671.331 | 0 | 671.331 | 0 | 671.331 | 0 | 671.331 | 0 | 671.331 | 0 | 671.331 | 15 | 671.331 | 500 | 671.331 | 0 | 671.331 | 0 | 671.331 | 0
2025-08-26 | 8185.907 | 3265 | 682.1589 | 0 | 682.1589 | 0 | 682.1589 | 0 | 682.1589 | 0 | 682.1589 | 0 | 682.1589 | 0 | 682.1589 | 0 | 682.1589 | 2765 | 682.1589 | 500 | 682.1589 | 0 | 682.1589 | 0 | 682.1589 | 0
2025-08-27 | 8315.8421 | 3265 | 692.9868 | 0 | 692.9868 | 0 | 692.9868 | 0 | 692.9868 | 0 | 692.9868 | 0 | 692.9868 | 0 | 692.9868 | 0 | 692.9868 | 2765 | 692.9868 | 500 | 692.9868 | 0 | 692.9868 | 0 | 692.9868 | 0
2025-08-28 | 8445.7771 | 3265 | 703.8148 | 0 | 703.8148 | 0 | 703.8148 | 0 | 703.8148 | 0 | 703.8148 | 0 | 703.8148 | 0 | 703.8148 | 0 | 703.8148 | 2765 | 703.8148 | 500 | 703.8148 | 0 | 703.8148 | 0 | 703.8148 | 0
2025-08-29 | 8575.7121 | 3265 | 714.6427 | 0 | 714.6427 | 0 | 714.6427 | 0 | 714.6427 | 0 | 714.6427 | 0 | 714.6427 | 0 | 714.6427 | 0 | 714.6427 | 2765 | 714.6427 | 500 | 714.6427 | 0 | 714.6427 | 0 | 714.6427 | 0
2025-08-30 | 8705.6472 | 3265 | 725.4706 | 0 | 725.4706 | 0 | 725.4706 | 0 | 725.4706 | 0 | 725.4706 | 0 | 725.4706 | 0 | 725.4706 | 0 | 725.4706 | 2765 | 725.4706 | 500 | 725.4706 | 0 | 725.4706 | 0 | 725.4706 | 0
2025-08-31 | 8835.5822 | 3265 | 736.2985 | 0 | 736.2985 | 0 | 736.2985 | 0 | 736.2985 | 0 | 736.2985 | 0 | 736.2985 | 0 | 736.2985 | 0 | 736.2985 | 2765 | 736.2985 | 500 | 736.2985 | 0 | 736.2985 | 0 | 736.2985 | 0
2025-09-01 | 8965.5172 | 3265 | 747.1264 | 0 | 747.1264 | 0 | 747.1264 | 0 | 747.1264 | 0 | 747.1264 | 0 | 747.1264 | 0 | 747.1264 | 0 | 747.1264 | 2765 | 747.1264 | 500 | 747.1264 | 0 | 747.1264 | 0 | 747.1264 | 0
2025-09-02 | 9095.4523 | 3265 | 757.9544 | 0 | 757.9544 | 0 | 757.9544 | 0 | 757.9544 | 0 | 757.9544 | 0 | 757.9544 | 0 | 757.9544 | 0 | 757.9544 | 2765 | 757.9544 | 500 | 757.9544 | 0 | 757.9544 | 0 | 757.9544 | 0
2025-09-03 | 9225.3873 | 3265 | 768.7823 | 0 | 768.7823 | 0 | 768.7823 | 0 | 768.7823 | 0 | 768.7823 | 0 | 768.7823 | 0 | 768.7823 | 0 | 768.7823 | 2765 | 768.7823 | 500 | 768.7823 | 0 | 768.7823 | 0 | 768.7823 | 0
2025-09-04 | 9355.3223 | 3951.7 | 779.6102 | 0 | 779.6102 | 0 | 779.6102 | 0 | 779.6102 | 0 | 779.6102 | 686.7 | 779.6102 | 0 | 779.6102 | 0 | 779.6102 | 2765 | 779.6102 | 500 | 779.6102 | 0 | 779.6102 | 0 | 779.6102 | 0
2025-09-05 | 9485.2574 | 3951.7 | 790.4381 | 0 | 790.4381 | 0 | 790.4381 | 0 | 790.4381 | 0 | 790.4381 | 686.7 | 790.4381 | 0 | 790.4381 | 0 | 790.4381 | 2765 | 790.4381 | 500 | 790.4381 | 0 | 790.4381 | 0 | 790.4381 | 0
2025-09-06 | 9615.1924 | 3951.7 | 801.266 | 0 | 801.266 | 0 | 801.266 | 0 | 801.266 | 0 | 801.266 | 686.7 | 801.266 | 0 | 801.266 | 0 | 801.266 | 2765 | 801.266 | 500 | 801.266 | 0 | 801.266 | 0 | 801.266 | 0
2025-09-07 | 9745.1274 | 3951.7 | 812.094 | 0 | 812.094 | 0 | 812.094 | 0 | 812.094 | 0 | 812.094 | 686.7 | 812.094 | 0 | 812.094 | 0 | 812.094 | 2765 | 812.094 | 500 | 812.094 | 0 | 812.094 | 0 | 812.094 | 0
2025-09-08 | 9875.0625 | 3951.7 | 822.9219 | 0 | 822.9219 | 0 | 822.9219 | 0 | 822.9219 | 0 | 822.9219 | 686.7 | 822.9219 | 0 | 822.9219 | 0 | 822.9219 | 2765 | 822.9219 | 500 | 822.9219 | 0 | 822.9219 | 0 | 822.9219 | 0
2025-09-09 | 10004.9975 | 3951.7 | 833.7498 | 0 | 833.7498 | 0 | 833.7498 | 0 | 833.7498 | 0 | 833.7498 | 686.7 | 833.7498 | 0 | 833.7498 | 0 | 833.7498 | 2765 | 833.7498 | 500 | 833.7498 | 0 | 833.7498 | 0 | 833.7498 | 0
2025-09-10 | 10134.9325 | 3951.7 | 844.5777 | 0 | 844.5777 | 0 | 844.5777 | 0 | 844.5777 | 0 | 844.5777 | 686.7 | 844.5777 | 0 | 844.5777 | 0 | 844.5777 | 2765 | 844.5777 | 500 | 844.5777 | 0 | 844.5777 | 0 | 844.5777 | 0
2025-09-11 | 10264.8676 | 3951.7 | 855.4056 | 0 | 855.4056 | 0 | 855.4056 | 0 | 855.4056 | 0 | 855.4056 | 686.7 | 855.4056 | 0 | 855.4056 | 0 | 855.4056 | 2765 | 855.4056 | 500 | 855.4056 | 0 | 855.4056 | 0 | 855.4056 | 0
2025-09-12 | 10394.8026 | 18066.7 | 866.2335 | 14115 | 866.2335 | 0 | 866.2335 | 0 | 866.2335 | 0 | 866.2335 | 686.7 | 866.2335 | 0 | 866.2335 | 0 | 866.2335 | 2765 | 866.2335 | 500 | 866.2335 | 0 | 866.2335 | 0 | 866.2335 | 0
2025-09-13 | 10524.7376 | 18066.7 | 877.0615 | 14115 | 877.0615 | 0 | 877.0615 | 0 | 877.0615 | 0 | 877.0615 | 686.7 | 877.0615 | 0 | 877.0615 | 0 | 877.0615 | 2765 | 877.0615 | 500 | 877.0615 | 0 | 877.0615 | 0 | 877.0615 | 0
2025-09-14 | 10654.6727 | 18066.7 | 887.8894 | 14115 | 887.8894 | 0 | 887.8894 | 0 | 887.8894 | 0 | 887.8894 | 686.7 | 887.8894 | 0 | 887.8894 | 0 | 887.8894 | 2765 | 887.8894 | 500 | 887.8894 | 0 | 887.8894 | 0 | 887.8894 | 0
2025-09-15 | 10784.6077 | 18066.7 | 898.7173 | 14115 | 898.7173 | 0 | 898.7173 | 0 | 898.7173 | 0 | 898.7173 | 686.7 | 898.7173 | 0 | 898.7173 | 0 | 898.7173 | 2765 | 898.7173 | 500 | 898.7173 | 0 | 898.7173 | 0 | 898.7173 | 0
2025-09-16 | 10914.5427 | 18066.7 | 909.5452 | 14115 | 909.5452 | 0 | 909.5452 | 0 | 909.5452 | 0 | 909.5452 | 686.7 | 909.5452 | 0 | 909.5452 | 0 | 909.5452 | 2765 | 909.5452 | 500 | 909.5452 | 0 | 909.5452 | 0 | 909.5452 | 0
2025-09-17 | 11044.4778 | 18066.7 | 920.3731 | 14115 | 920.3731 | 0 | 920.3731 | 0 | 920.3731 | 0 | 920.3731 | 686.7 | 920.3731 | 0 | 920.3731 | 0 | 920.3731 | 2765 | 920.3731 | 500 | 920.3731 | 0 | 920.3731 | 0 | 920.3731 | 0
2025-09-18 | 11174.4128 | 18066.7 | 931.2011 | 14115 | 931.2011 | 0 | 931.2011 | 0 | 931.2011 | 0 | 931.2011 | 686.7 | 931.2011 | 0 | 931.2011 | 0 | 931.2011 | 2765 | 931.2011 | 500 | 931.2011 | 0 | 931.2011 | 0 | 931.2011 | 0
2025-09-19 | 11304.3478 | 18066.7 | 942.029 | 14115 | 942.029 | 0 | 942.029 | 0 | 942.029 | 0 | 942.029 | 686.7 | 942.029 | 0 | 942.029 | 0 | 942.029 | 2765 | 942.029 | 500 | 942.029 | 0 | 942.029 | 0 | 942.029 | 0
2025-09-20 | 11304.3478 | 18066.7 | 942.029 | 14115 | 942.029 | 0 | 942.029 | 0 | 942.029 | 0 | 942.029 | 686.7 | 942.029 | 0 | 942.029 | 0 | 942.029 | 2765 | 942.029 | 500 | 942.029 | 0 | 942.029 | 0 | 942.029 | 0
2025-09-21 | 11304.3478 | 18066.7 | 942.029 | 14115 | 942.029 | 0 | 942.029 | 0 | 942.029 | 0 | 942.029 | 686.7 | 942.029 | 0 | 942.029 | 0 | 942.029 | 2765 | 942.029 | 500 | 942.029 | 0 | 942.029 | 0 | 942.029 | 0
2025-09-22 | 11322.2506 | 20014.2 | 943.5209 | 14115 | 943.5209 | 0 | 943.5209 | 0 | 943.5209 | 0 | 943.5209 | 1184.2 | 943.5209 | 0 | 943.5209 | 0 | 943.5209 | 4215 | 943.5209 | 500 | 943.5209 | 0 | 943.5209 | 0 | 943.5209 | 0
2025-09-23 | 11340.1535 | 21151.72 | 945.0128 | 14262.52 | 945.0128 | 0 | 945.0128 | 0 | 945.0128 | 0 | 945.0128 | 1184.2 | 945.0128 | 990 | 945.0128 | 0 | 945.0128 | 4215 | 945.0128 | 500 | 945.0128 | 0 | 945.0128 | 0 | 945.0128 | 0
2025-09-24 | 11358.0563 | 31325.53 | 946.5047 | 24436.33 | 946.5047 | 0 | 946.5047 | 0 | 946.5047 | 0 | 946.5047 | 1184.2 | 946.5047 | 990 | 946.5047 | 0 | 946.5047 | 4215 | 946.5047 | 500 | 946.5047 | 0 | 946.5047 | 0 | 946.5047 | 0
2025-09-25 | 11375.9591 | 31325.53 | 947.9966 | 24436.33 | 947.9966 | 0 | 947.9966 | 0 | 947.9966 | 0 | 947.9966 | 1184.2 | 947.9966 | 990 | 947.9966 | 0 | 947.9966 | 4215 | 947.9966 | 500 | 947.9966 | 0 | 947.9966 | 0 | 947.9966 | 0
2025-09-26 | 11393.8619 | 31325.53 | 949.4885 | 24436.33 | 949.4885 | 0 | 949.4885 | 0 | 949.4885 | 0 | 949.4885 | 1184.2 | 949.4885 | 990 | 949.4885 | 0 | 949.4885 | 4215 | 949.4885 | 500 | 949.4885 | 0 | 949.4885 | 0 | 949.4885 | 0
2025-09-27 | 11411.7647 | 31325.53 | 950.9804 | 24436.33 | 950.9804 | 0 | 950.9804 | 0 | 950.9804 | 0 | 950.9804 | 1184.2 | 950.9804 | 990 | 950.9804 | 0 | 950.9804 | 4215 | 950.9804 | 500 | 950.9804 | 0 | 950.9804 | 0 | 950.9804 | 0
2025-09-28 | 11429.6675 | 31325.53 | 952.4723 | 24436.33 | 952.4723 | 0 | 952.4723 | 0 | 952.4723 | 0 | 952.4723 | 1184.2 | 952.4723 | 990 | 952.4723 | 0 | 952.4723 | 4215 | 952.4723 | 500 | 952.4723 | 0 | 952.4723 | 0 | 952.4723 | 0
2025-09-29 | 11447.5703 | 31325.53 | 953.9642 | 24436.33 | 953.9642 | 0 | 953.9642 | 0 | 953.9642 | 0 | 953.9642 | 1184.2 | 953.9642 | 990 | 953.9642 | 0 | 953.9642 | 4215 | 953.9642 | 500 | 953.9642 | 0 | 953.9642 | 0 | 953.9642 | 0
2025-09-30 | 11465.4731 | 31325.53 | 955.4561 | 24436.33 | 955.4561 | 0 | 955.4561 | 0 | 955.4561 | 0 | 955.4561 | 1184.2 | 955.4561 | 990 | 955.4561 | 0 | 955.4561 | 4215 | 955.4561 | 500 | 955.4561 | 0 | 955.4561 | 0 | 955.4561 | 0
2025-10-01 | 11483.376 | 31325.53 | 956.948 | 24436.33 | 956.948 | 0 | 956.948 | 0 | 956.948 | 0 | 956.948 | 1184.2 | 956.948 | 990 | 956.948 | 0 | 956.948 | 4215 | 956.948 | 500 | 956.948 | 0 | 956.948 | 0 | 956.948 | 0
2025-10-02 | 11501.2788 | 31325.53 | 958.4399 | 24436.33 | 958.4399 | 0 | 958.4399 | 0 | 958.4399 | 0 | 958.4399 | 1184.2 | 958.4399 | 990 | 958.4399 | 0 | 958.4399 | 4215 | 958.4399 | 500 | 958.4399 | 0 | 958.4399 | 0 | 958.4399 | 0
2025-10-03 | 11519.1816 | 31325.53 | 959.9318 | 24436.33 | 959.9318 | 0 | 959.9318 | 0 | 959.9318 | 0 | 959.9318 | 1184.2 | 959.9318 | 990 | 959.9318 | 0 | 959.9318 | 4215 | 959.9318 | 500 | 959.9318 | 0 | 959.9318 | 0 | 959.9318 | 0
2025-10-04 | 11537.0844 | 31325.53 | 961.4237 | 24436.33 | 961.4237 | 0 | 961.4237 | 0 | 961.4237 | 0 | 961.4237 | 1184.2 | 961.4237 | 990 | 961.4237 | 0 | 961.4237 | 4215 | 961.4237 | 500 | 961.4237 | 0 | 961.4237 | 0 | 961.4237 | 0
2025-10-05 | 11554.9872 | 31325.53 | 962.9156 | 24436.33 | 962.9156 | 0 | 962.9156 | 0 | 962.9156 | 0 | 962.9156 | 1184.2 | 962.9156 | 990 | 962.9156 | 0 | 962.9156 | 4215 | 962.9156 | 500 | 962.9156 | 0 | 962.9156 | 0 | 962.9156 | 0
2025-10-06 | 11572.89 | 31325.53 | 964.4075 | 24436.33 | 964.4075 | 0 | 964.4075 | 0 | 964.4075 | 0 | 964.4075 | 1184.2 | 964.4075 | 990 | 964.4075 | 0 | 964.4075 | 4215 | 964.4075 | 500 | 964.4075 | 0 | 964.4075 | 0 | 964.4075 | 0
2025-10-07 | 11590.7928 | 31325.53 | 965.8994 | 24436.33 | 965.8994 | 0 | 965.8994 | 0 | 965.8994 | 0 | 965.8994 | 1184.2 | 965.8994 | 990 | 965.8994 | 0 | 965.8994 | 4215 | 965.8994 | 500 | 965.8994 | 0 | 965.8994 | 0 | 965.8994 | 0
2025-10-08 | 11608.6957 | 31325.53 | 967.3913 | 24436.33 | 967.3913 | 0 | 967.3913 | 0 | 967.3913 | 0 | 967.3913 | 1184.2 | 967.3913 | 990 | 967.3913 | 0 | 967.3913 | 4215 | 967.3913 | 500 | 967.3913 | 0 | 967.3913 | 0 | 967.3913 | 0
2025-10-09 | 11626.5985 | 31325.53 | 968.8832 | 24436.33 | 968.8832 | 0 | 968.8832 | 0 | 968.8832 | 0 | 968.8832 | 1184.2 | 968.8832 | 990 | 968.8832 | 0 | 968.8832 | 4215 | 968.8832 | 500 | 968.8832 | 0 | 968.8832 | 0 | 968.8832 | 0
2025-10-10 | 11644.5013 | 31325.53 | 970.3751 | 24436.33 | 970.3751 | 0 | 970.3751 | 0 | 970.3751 | 0 | 970.3751 | 1184.2 | 970.3751 | 990 | 970.3751 | 0 | 970.3751 | 4215 | 970.3751 | 500 | 970.3751 | 0 | 970.3751 | 0 | 970.3751 | 0
2025-10-11 | 11662.4041 | 31325.53 | 971.867 | 24436.33 | 971.867 | 0 | 971.867 | 0 | 971.867 | 0 | 971.867 | 1184.2 | 971.867 | 990 | 971.867 | 0 | 971.867 | 4215 | 971.867 | 500 | 971.867 | 0 | 971.867 | 0 | 971.867 | 0
2025-10-12 | 11680.3069 | 31325.53 | 973.3589 | 24436.33 | 973.3589 | 0 | 973.3589 | 0 | 973.3589 | 0 | 973.3589 | 1184.2 | 973.3589 | 990 | 973.3589 | 0 | 973.3589 | 4215 | 973.3589 | 500 | 973.3589 | 0 | 973.3589 | 0 | 973.3589 | 0
2025-10-13 | 11698.2097 |  | 974.8508 |  | 974.8508 |  | 974.8508 |  | 974.8508 |  | 974.8508 |  | 974.8508 |  | 974.8508 |  | 974.8508 |  | 974.8508 |  | 974.8508 |  | 974.8508 |  | 974.8508
2025-10-14 | 11716.1125 |  | 976.3427 |  | 976.3427 |  | 976.3427 |  | 976.3427 |  | 976.3427 |  | 976.3427 |  | 976.3427 |  | 976.3427 |  | 976.3427 |  | 976.3427 |  | 976.3427 |  | 976.3427
2025-10-15 | 11734.0153 |  | 977.8346 |  | 977.8346 |  | 977.8346 |  | 977.8346 |  | 977.8346 |  | 977.8346 |  | 977.8346 |  | 977.8346 |  | 977.8346 |  | 977.8346 |  | 977.8346 |  | 977.8346
2025-10-16 | 11751.9182 |  | 979.3265 |  | 979.3265 |  | 979.3265 |  | 979.3265 |  | 979.3265 |  | 979.3265 |  | 979.3265 |  | 979.3265 |  | 979.3265 |  | 979.3265 |  | 979.3265 |  | 979.3265
2025-10-17 | 11769.821 |  | 980.8184 |  | 980.8184 |  | 980.8184 |  | 980.8184 |  | 980.8184 |  | 980.8184 |  | 980.8184 |  | 980.8184 |  | 980.8184 |  | 980.8184 |  | 980.8184 |  | 980.8184
2025-10-18 | 11787.7238 |  | 982.3103 |  | 982.3103 |  | 982.3103 |  | 982.3103 |  | 982.3103 |  | 982.3103 |  | 982.3103 |  | 982.3103 |  | 982.3103 |  | 982.3103 |  | 982.3103 |  | 982.3103
2025-10-19 | 11805.6266 |  | 983.8022 |  | 983.8022 |  | 983.8022 |  | 983.8022 |  | 983.8022 |  | 983.8022 |  | 983.8022 |  | 983.8022 |  | 983.8022 |  | 983.8022 |  | 983.8022 |  | 983.8022
2025-10-20 | 11823.5294 |  | 985.2941 |  | 985.2941 |  | 985.2941 |  | 985.2941 |  | 985.2941 |  | 985.2941 |  | 985.2941 |  | 985.2941 |  | 985.2941 |  | 985.2941 |  | 985.2941 |  | 985.2941
2025-10-21 | 11841.4322 |  | 986.786 |  | 986.786 |  | 986.786 |  | 986.786 |  | 986.786 |  | 986.786 |  | 986.786 |  | 986.786 |  | 986.786 |  | 986.786 |  | 986.786 |  | 986.786
2025-10-22 | 11859.335 |  | 988.2779 |  | 988.2779 |  | 988.2779 |  | 988.2779 |  | 988.2779 |  | 988.2779 |  | 988.2779 |  | 988.2779 |  | 988.2779 |  | 988.2779 |  | 988.2779 |  | 988.2779
2025-10-23 | 11877.2379 |  | 989.7698 |  | 989.7698 |  | 989.7698 |  | 989.7698 |  | 989.7698 |  | 989.7698 |  | 989.7698 |  | 989.7698 |  | 989.7698 |  | 989.7698 |  | 989.7698 |  | 989.7698
2025-10-24 | 11895.1407 |  | 991.2617 |  | 991.2617 |  | 991.2617 |  | 991.2617 |  | 991.2617 |  | 991.2617 |  | 991.2617 |  | 991.2617 |  | 991.2617 |  | 991.2617 |  | 991.2617 |  | 991.2617
2025-10-25 | 11913.0435 |  | 992.7536 |  | 992.7536 |  | 992.7536 |  | 992.7536 |  | 992.7536 |  | 992.7536 |  | 992.7536 |  | 992.7536 |  | 992.7536 |  | 992.7536 |  | 992.7536 |  | 992.7536
2025-10-26 | 11930.9463 |  | 994.2455 |  | 994.2455 |  | 994.2455 |  | 994.2455 |  | 994.2455 |  | 994.2455 |  | 994.2455 |  | 994.2455 |  | 994.2455 |  | 994.2455 |  | 994.2455 |  | 994.2455
2025-10-27 | 11948.8491 |  | 995.7374 |  | 995.7374 |  | 995.7374 |  | 995.7374 |  | 995.7374 |  | 995.7374 |  | 995.7374 |  | 995.7374 |  | 995.7374 |  | 995.7374 |  | 995.7374 |  | 995.7374
2025-10-28 | 11966.7519 |  | 997.2293 |  | 997.2293 |  | 997.2293 |  | 997.2293 |  | 997.2293 |  | 997.2293 |  | 997.2293 |  | 997.2293 |  | 997.2293 |  | 997.2293 |  | 997.2293 |  | 997.2293
2025-10-29 | 11984.6547 |  | 998.7212 |  | 998.7212 |  | 998.7212 |  | 998.7212 |  | 998.7212 |  | 998.7212 |  | 998.7212 |  | 998.7212 |  | 998.7212 |  | 998.7212 |  | 998.7212 |  | 998.7212
2025-10-30 | 12002.5575 |  | 1000.2131 |  | 1000.2131 |  | 1000.2131 |  | 1000.2131 |  | 1000.2131 |  | 1000.2131 |  | 1000.2131 |  | 1000.2131 |  | 1000.2131 |  | 1000.2131 |  | 1000.2131 |  | 1000.2131
2025-10-31 | 12020.4604 |  | 1001.705 |  | 1001.705 |  | 1001.705 |  | 1001.705 |  | 1001.705 |  | 1001.705 |  | 1001.705 |  | 1001.705 |  | 1001.705 |  | 1001.705 |  | 1001.705 |  | 1001.705
2025-11-01 | 12038.3632 |  | 1003.1969 |  | 1003.1969 |  | 1003.1969 |  | 1003.1969 |  | 1003.1969 |  | 1003.1969 |  | 1003.1969 |  | 1003.1969 |  | 1003.1969 |  | 1003.1969 |  | 1003.1969 |  | 1003.1969
2025-11-02 | 12056.266 |  | 1004.6888 |  | 1004.6888 |  | 1004.6888 |  | 1004.6888 |  | 1004.6888 |  | 1004.6888 |  | 1004.6888 |  | 1004.6888 |  | 1004.6888 |  | 1004.6888 |  | 1004.6888 |  | 1004.6888
2025-11-03 | 12074.1688 |  | 1006.1807 |  | 1006.1807 |  | 1006.1807 |  | 1006.1807 |  | 1006.1807 |  | 1006.1807 |  | 1006.1807 |  | 1006.1807 |  | 1006.1807 |  | 1006.1807 |  | 1006.1807 |  | 1006.1807
2025-11-04 | 12092.0716 |  | 1007.6726 |  | 1007.6726 |  | 1007.6726 |  | 1007.6726 |  | 1007.6726 |  | 1007.6726 |  | 1007.6726 |  | 1007.6726 |  | 1007.6726 |  | 1007.6726 |  | 1007.6726 |  | 1007.6726
2025-11-05 | 12109.9744 |  | 1009.1645 |  | 1009.1645 |  | 1009.1645 |  | 1009.1645 |  | 1009.1645 |  | 1009.1645 |  | 1009.1645 |  | 1009.1645 |  | 1009.1645 |  | 1009.1645 |  | 1009.1645 |  | 1009.1645
2025-11-06 | 12127.8772 |  | 1010.6564 |  | 1010.6564 |  | 1010.6564 |  | 1010.6564 |  | 1010.6564 |  | 1010.6564 |  | 1010.6564 |  | 1010.6564 |  | 1010.6564 |  | 1010.6564 |  | 1010.6564 |  | 1010.6564
2025-11-07 | 12145.7801 |  | 1012.1483 |  | 1012.1483 |  | 1012.1483 |  | 1012.1483 |  | 1012.1483 |  | 1012.1483 |  | 1012.1483 |  | 1012.1483 |  | 1012.1483 |  | 1012.1483 |  | 1012.1483 |  | 1012.1483
2025-11-08 | 12163.6829 |  | 1013.6402 |  | 1013.6402 |  | 1013.6402 |  | 1013.6402 |  | 1013.6402 |  | 1013.6402 |  | 1013.6402 |  | 1013.6402 |  | 1013.6402 |  | 1013.6402 |  | 1013.6402 |  | 1013.6402
2025-11-09 | 12181.5857 |  | 1015.1321 |  | 1015.1321 |  | 1015.1321 |  | 1015.1321 |  | 1015.1321 |  | 1015.1321 |  | 1015.1321 |  | 1015.1321 |  | 1015.1321 |  | 1015.1321 |  | 1015.1321 |  | 1015.1321
2025-11-10 | 12199.4885 |  | 1016.624 |  | 1016.624 |  | 1016.624 |  | 1016.624 |  | 1016.624 |  | 1016.624 |  | 1016.624 |  | 1016.624 |  | 1016.624 |  | 1016.624 |  | 1016.624 |  | 1016.624
2025-11-11 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-12 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-13 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-14 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-15 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-16 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-17 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-18 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-19 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-20 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-21 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-22 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-23 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-24 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-25 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-26 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-27 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-28 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-29 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-11-30 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-01 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-02 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-03 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-04 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-05 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-06 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-07 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-08 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-09 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-10 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-11 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-12 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-13 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-14 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-15 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-16 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-17 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-18 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-19 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-20 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-21 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-22 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-23 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-24 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-25 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-26 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-27 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-28 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-29 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-30 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2025-12-31 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-01 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-02 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-03 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-04 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-05 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-06 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-07 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-08 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-09 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-10 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-11 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-12 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-13 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-14 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-15 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-16 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-17 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-18 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-19 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-20 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-21 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-22 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-23 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-24 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-25 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-26 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-27 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-28 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-29 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-30 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-01-31 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-01 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-02 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-03 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-04 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-05 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-06 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-07 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-08 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-09 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-10 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-11 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-12 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-13 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-14 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-15 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-16 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-17 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-18 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-19 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-20 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-21 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-22 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-23 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-24 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-25 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-26 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-27 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-02-28 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-01 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-02 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-03 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-04 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-05 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-06 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-07 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-08 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-09 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-10 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-11 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-12 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-13 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-14 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-15 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-16 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-17 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-18 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-19 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-20 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-21 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-22 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-23 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-24 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-25 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-26 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-27 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-28 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-29 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-30 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-03-31 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-01 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-02 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-03 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-04 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-05 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-06 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-07 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-08 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-09 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-10 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-11 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-12 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-13 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-14 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-15 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-16 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-17 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-18 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-19 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-20 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-21 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-22 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-23 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-24 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-25 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-26 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-27 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-28 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-29 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-04-30 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-01 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-02 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-03 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-04 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-05 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-06 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-07 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-08 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-09 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-10 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-11 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-12 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-13 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-14 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-15 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-16 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-17 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-18 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-19 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-20 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-21 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-22 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-23 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-24 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-25 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-26 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-27 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-28 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-29 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-30 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-05-31 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-01 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-02 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-03 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-04 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-05 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-06 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-07 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-08 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-09 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-10 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-11 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-12 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-13 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-14 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-15 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-16 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-17 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-18 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-19 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-20 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-21 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-22 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-23 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-24 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-25 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-26 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-27 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-28 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-29 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-06-30 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-01 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-02 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-03 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-04 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-05 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-06 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-07 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-08 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-09 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-10 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-11 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-12 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-13 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-14 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-15 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-16 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-17 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-18 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-19 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-20 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-21 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-22 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-23 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-24 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-25 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-26 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-27 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-28 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-29 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-30 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-07-31 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-01 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-02 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-03 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-04 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-05 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-06 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-07 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-08 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-09 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-10 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-11 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-12 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-13 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-14 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-15 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-16 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-17 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-18 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-19 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-20 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-21 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-22 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-23 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-24 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-25 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-26 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-27 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-28 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-29 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-30 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-08-31 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-01 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-02 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-03 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-04 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-05 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-06 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-07 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-08 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-09 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-10 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-11 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-12 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-13 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-14 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159
2026-09-15 | 12217.3913 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159 |  | 1018.1159

## Equipment Cost
Date | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Planned 1805 · Equipment - Forklift (Cumulative) | Actual 1805 · Equipment - Forklift (Cumulative) | Planned 1818 · Equipment - BCU (Cumulative) | Actual 1818 · Equipment - BCU (Cumulative) | Planned 1819 · Equipment - TPMB (Cumulative) | Actual 1819 · Equipment - TPMB (Cumulative) | Planned 1820 · Equipment & Tools (Cumulative) | Actual 1820 · Equipment & Tools (Cumulative) | Planned 1821 · Equipment - C3 (Cumulative) | Actual 1821 · Equipment - C3 (Cumulative) | Planned 1822 · Equipment - C2 (Cumulative) | Actual 1822 · Equipment - C2 (Cumulative) | Planned 1823 · Equipment - TCU Basic (Cumulative) | Actual 1823 · Equipment - TCU Basic (Cumulative) | Planned 1824 · Equipment - TCU PLC (Cumulative) | Actual 1824 · Equipment - TCU PLC (Cumulative) | Planned 1825 · Equipment - Blower Skids (Cumulative) | Actual 1825 · Equipment - Blower Skids (Cumulative) | Planned 1826 · Equipment - Well Heads (Cumulative) | Actual 1826 · Equipment - Well Heads (Cumulative) | Planned 1827 · Equipment - Thermal Wells (Cumulative) | Actual 1827 · Equipment - Thermal Wells (Cumulative) | Planned 1829 · Equipment - Water Treatment Sys (Cumulative) | Actual 1829 · Equipment - Water Treatment Sys (Cumulative) | Planned 1830 · Equipment - Vapor Extraction (Cumulative) | Actual 1830 · Equipment - Vapor Extraction (Cumulative) | Planned 1831 · Equipment - GTR/C3 Components (Cumulative) | Actual 1831 · Equipment - GTR/C3 Components (Cumulative) | Planned 1832 · Equip - Control/Dist panels (Cumulative) | Actual 1832 · Equip - Control/Dist panels (Cumulative) | Planned 1833 · Equipment - Office & computer (Cumulative) | Actual 1833 · Equipment - Office & computer (Cumulative) | Planned 5113 · Repairs & maint (Direct) (Cumulative) | Actual 5113 · Repairs & maint (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 969.4138 | 5000 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 5000 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0 | 57.0243 | 0
2025-06-26 | 1938.8276 | 5000 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 5000 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0 | 114.0487 | 0
2025-06-27 | 2908.2414 | 5000 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0 | 171.073 | 5000 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0 | 171.073 | 0
2025-06-28 | 3877.6552 | 5000 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 5000 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0 | 228.0974 | 0
2025-06-29 | 4847.069 | 5000 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 5000 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0 | 285.1217 | 0
2025-06-30 | 5816.4828 | 5000 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0 | 342.146 | 5000 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0 | 342.146 | 0
2025-07-01 | 6785.8966 | 5000 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 5000 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0 | 399.1704 | 0
2025-07-02 | 7755.3103 | 5000 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 5000 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0 | 456.1947 | 0
2025-07-03 | 8724.7241 | 5000 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 5000 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0 | 513.2191 | 0
2025-07-04 | 9694.1379 | 5000 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 5000 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0 | 570.2434 | 0
2025-07-05 | 10663.5517 | 5000 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 5000 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0 | 627.2677 | 0
2025-07-06 | 11632.9655 | 5000 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 5000 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0 | 684.2921 | 0
2025-07-07 | 12602.3793 | 5000 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 5000 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0 | 741.3164 | 0
2025-07-08 | 13571.7931 | 5000 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 5000 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0 | 798.3408 | 0
2025-07-09 | 14541.2069 | 5000 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 5000 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0 | 855.3651 | 0
2025-07-10 | 15510.6207 | 5000 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 5000 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0 | 912.3895 | 0
2025-07-11 | 16480.0345 | 5000 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 5000 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0 | 969.4138 | 0
2025-07-12 | 17449.4483 | 5000 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 5000 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0 | 1026.4381 | 0
2025-07-13 | 18418.8621 | 5000 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 5000 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0 | 1083.4625 | 0
2025-07-14 | 19388.2759 | 5000 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 5000 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0 | 1140.4868 | 0
2025-07-15 | 20357.6897 | 5000 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 5000 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0 | 1197.5112 | 0
2025-07-16 | 21327.1034 | 5000 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 5000 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0 | 1254.5355 | 0
2025-07-17 | 22296.5172 | 5000 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 5000 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0 | 1311.5598 | 0
2025-07-18 | 23265.931 | 5000 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 5000 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0 | 1368.5842 | 0
2025-07-19 | 24235.3448 | 5000 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 5000 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0 | 1425.6085 | 0
2025-07-20 | 25204.7586 | 5000 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 5000 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0 | 1482.6329 | 0
2025-07-21 | 26174.1724 | 5000 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 5000 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0 | 1539.6572 | 0
2025-07-22 | 27143.5862 | 5000 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 5000 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0 | 1596.6815 | 0
2025-07-23 | 28113 | 5000 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 5000 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0
2025-07-24 | 29082.4138 | 5000 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 5000 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0 | 1710.7302 | 0
2025-07-25 | 30051.8276 | 5000 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 5000 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0 | 1767.7546 | 0
2025-07-26 | 31021.2414 | 5000 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 5000 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0 | 1824.7789 | 0
2025-07-27 | 31990.6552 | 5000 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 5000 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0 | 1881.8032 | 0
2025-07-28 | 32960.069 | 5000 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 5000 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0 | 1938.8276 | 0
2025-07-29 | 33929.4828 | 5000 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 5000 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0 | 1995.8519 | 0
2025-07-30 | 34898.8966 | 5000 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 5000 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0 | 2052.8763 | 0
2025-07-31 | 35868.3103 | 5000 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 5000 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0 | 2109.9006 | 0
2025-08-01 | 36837.7241 | 5000 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 5000 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0 | 2166.9249 | 0
2025-08-02 | 37807.1379 | 5000 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 5000 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0 | 2223.9493 | 0
2025-08-03 | 38776.5517 | 5000 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 5000 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0 | 2280.9736 | 0
2025-08-04 | 39745.9655 | 5000 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 5000 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0 | 2337.998 | 0
2025-08-05 | 40715.3793 | 5000 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 5000 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0 | 2395.0223 | 0
2025-08-06 | 41684.7931 | 5000 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 5000 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0 | 2452.0467 | 0
2025-08-07 | 42654.2069 | 5000 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 5000 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0 | 2509.071 | 0
2025-08-08 | 43623.6207 | 5000 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 5000 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0 | 2566.0953 | 0
2025-08-09 | 44593.0345 | 5000 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 5000 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0 | 2623.1197 | 0
2025-08-10 | 45562.4483 | 5000 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 5000 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0 | 2680.144 | 0
2025-08-11 | 46531.8621 | 5000 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 5000 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0 | 2737.1684 | 0
2025-08-12 | 47501.2759 | 5000 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 5000 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0 | 2794.1927 | 0
2025-08-13 | 48470.6897 | 5000 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 5000 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0 | 2851.217 | 0
2025-08-14 | 49440.1034 | 5000 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 5000 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0 | 2908.2414 | 0
2025-08-15 | 50409.5172 | 5000 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 5000 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0 | 2965.2657 | 0
2025-08-16 | 51378.931 | 5000 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 5000 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0 | 3022.2901 | 0
2025-08-17 | 52348.3448 | 5000 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 5000 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0 | 3079.3144 | 0
2025-08-18 | 53317.7586 | 5000 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 5000 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0 | 3136.3387 | 0
2025-08-19 | 54287.1724 | 5000 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 5000 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0 | 3193.3631 | 0
2025-08-20 | 55256.5862 | 5000 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 5000 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0 | 3250.3874 | 0
2025-08-21 | 56226 | 5000 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 5000 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0
2025-08-22 | 57195.4138 | 5000 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 5000 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0 | 3364.4361 | 0
2025-08-23 | 58164.8276 | 5000 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 5000 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0 | 3421.4604 | 0
2025-08-24 | 59134.2414 | 5000 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 5000 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0 | 3478.4848 | 0
2025-08-25 | 60103.6552 | 5000 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 5000 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0 | 3535.5091 | 0
2025-08-26 | 61073.069 | 5000 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 5000 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0 | 3592.5335 | 0
2025-08-27 | 62042.4828 | 5000 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 5000 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0 | 3649.5578 | 0
2025-08-28 | 63011.8966 | 5000 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 5000 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0 | 3706.5822 | 0
2025-08-29 | 63981.3103 | 5000 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 5000 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0 | 3763.6065 | 0
2025-08-30 | 64950.7241 | 5000 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 5000 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0 | 3820.6308 | 0
2025-08-31 | 65920.1379 | 5000 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 5000 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0 | 3877.6552 | 0
2025-09-01 | 66889.5517 | 5000 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 5000 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0 | 3934.6795 | 0
2025-09-02 | 67858.9655 | 5000 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 5000 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0 | 3991.7039 | 0
2025-09-03 | 68828.3793 | 5000 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 5000 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0 | 4048.7282 | 0
2025-09-04 | 69797.7931 | 5000 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 5000 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0 | 4105.7525 | 0
2025-09-05 | 70767.2069 | 5000 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 5000 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0 | 4162.7769 | 0
2025-09-06 | 71736.6207 | 5000 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 5000 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0 | 4219.8012 | 0
2025-09-07 | 72706.0345 | 5000 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 5000 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0 | 4276.8256 | 0
2025-09-08 | 73675.4483 | 5000 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 5000 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0 | 4333.8499 | 0
2025-09-09 | 74644.8621 | 5000 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 5000 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0 | 4390.8742 | 0
2025-09-10 | 75614.2759 | 5000 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 5000 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0 | 4447.8986 | 0
2025-09-11 | 76583.6897 | 5000 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 5000 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0 | 4504.9229 | 0
2025-09-12 | 77553.1034 | 5000 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 5000 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0 | 4561.9473 | 0
2025-09-13 | 78522.5172 | 5000 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 5000 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0 | 4618.9716 | 0
2025-09-14 | 79491.931 | 5000 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 5000 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0 | 4675.9959 | 0
2025-09-15 | 80461.3448 | 5000 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 5000 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0 | 4733.0203 | 0
2025-09-16 | 81430.7586 | 5000 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 5000 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0 | 4790.0446 | 0
2025-09-17 | 82400.1724 | 5000 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 5000 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0 | 4847.069 | 0
2025-09-18 | 83369.5862 | 5000 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 5000 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0 | 4904.0933 | 0
2025-09-19 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-20 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-21 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-22 | 84580.2617 | 5000 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 5000 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0
2025-09-23 | 84821.5234 | 5000 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 5000 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0
2025-09-24 | 85062.7852 | 5000 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 5000 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0
2025-09-25 | 85304.0469 | 5000 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 5000 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0
2025-09-26 | 85545.3086 | 5000 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 5000 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0
2025-09-27 | 85786.5703 | 5000 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 5000 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0
2025-09-28 | 86027.8321 | 5000 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 5000 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0
2025-09-29 | 86269.0938 | 5000 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 5000 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0
2025-09-30 | 86510.3555 | 5000 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 5000 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0
2025-10-01 | 86751.6172 | 5000 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 5000 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0
2025-10-02 | 86992.8789 | 5000 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 5000 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0
2025-10-03 | 87234.1407 | 5000 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 5000 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0
2025-10-04 | 87475.4024 | 5000 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 5000 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0
2025-10-05 | 87716.6641 | 5000 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 5000 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0
2025-10-06 | 87957.9258 | 5000 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 5000 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0
2025-10-07 | 88199.1876 | 5000 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 5000 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0
2025-10-08 | 88440.4493 | 5000 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 5000 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0
2025-10-09 | 88681.711 | 5000 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 5000 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0
2025-10-10 | 88922.9727 | 5000 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 5000 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0
2025-10-11 | 89164.2344 | 5000 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 5000 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0
2025-10-12 | 89405.4962 | 5000 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 5000 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0
2025-10-13 | 89646.7579 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387 |  | 5273.3387
2025-10-14 | 89888.0196 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306 |  | 5287.5306
2025-10-15 | 90129.2813 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224 |  | 5301.7224
2025-10-16 | 90370.5431 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143 |  | 5315.9143
2025-10-17 | 90611.8048 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062 |  | 5330.1062
2025-10-18 | 90853.0665 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298 |  | 5344.298
2025-10-19 | 91094.3282 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899 |  | 5358.4899
2025-10-20 | 91335.5899 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818
2025-10-21 | 91576.8517 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736
2025-10-22 | 91818.1134 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655
2025-10-23 | 92059.3751 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574
2025-10-24 | 92300.6368 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492
2025-10-25 | 92541.8986 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411
2025-10-26 | 92783.1603 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833
2025-10-27 | 93024.422 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248
2025-10-28 | 93265.6837 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167
2025-10-29 | 93506.9454 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086
2025-10-30 | 93748.2072 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004
2025-10-31 | 93989.4689 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923
2025-11-01 | 94230.7306 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842
2025-11-02 | 94471.9923 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176
2025-11-03 | 94713.254 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679
2025-11-04 | 94954.5158 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598
2025-11-05 | 95195.7775 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516
2025-11-06 | 95437.0392 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435
2025-11-07 | 95678.3009 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353
2025-11-08 | 95919.5627 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272
2025-11-09 | 96160.8244 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191
2025-11-10 | 96402.0861 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109
2025-11-11 | 96643.3478 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028
2025-11-12 | 97143.3478 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146
2025-11-13 | 97643.3478 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263
2025-11-14 | 98143.3478 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381
2025-11-15 | 98643.3478 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499
2025-11-16 | 99143.3478 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616
2025-11-17 | 99643.3478 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734
2025-11-18 | 100143.3478 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852
2025-11-19 | 100643.3478 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969
2025-11-20 | 101143.3478 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087
2025-11-21 | 101643.3478 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205
2025-11-22 | 102143.3478 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322
2025-11-23 | 102643.3478 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844
2025-11-24 | 103143.3478 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558
2025-11-25 | 103643.3478 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675
2025-11-26 | 104143.3478 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793
2025-11-27 | 104643.3478 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491
2025-11-28 | 105143.3478 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028
2025-11-29 | 105643.3478 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146
2025-11-30 | 106143.3478 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263
2025-12-01 | 106643.3478 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381
2025-12-02 | 107143.3478 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499
2025-12-03 | 107643.3478 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616
2025-12-04 | 108143.3478 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734
2025-12-05 | 108643.3478 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852
2025-12-06 | 109143.3478 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969
2025-12-07 | 109643.3478 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087
2025-12-08 | 110143.3478 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205
2025-12-09 | 110643.3478 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322
2025-12-10 | 111143.3478 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844
2025-12-11 | 111643.3478 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558
2025-12-12 | 112143.3478 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675
2025-12-13 | 112643.3478 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793
2025-12-14 | 113143.3478 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491
2025-12-15 | 113643.3478 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028
2025-12-16 | 114143.3478 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146
2025-12-17 | 114643.3478 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263
2025-12-18 | 115143.3478 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381
2025-12-19 | 115643.3478 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499
2025-12-20 | 116143.3478 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616
2025-12-21 | 116643.3478 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734
2025-12-22 | 117143.3478 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852
2025-12-23 | 117643.3478 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969
2025-12-24 | 118143.3478 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087
2025-12-25 | 118643.3478 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205
2025-12-26 | 119143.3478 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322
2025-12-27 | 119643.3478 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844
2025-12-28 | 120143.3478 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558
2025-12-29 | 120643.3478 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675
2025-12-30 | 121143.3478 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793
2025-12-31 | 121643.3478 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491
2026-01-01 | 122143.3478 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028
2026-01-02 | 122643.3478 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146
2026-01-03 | 123143.3478 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263
2026-01-04 | 123643.3478 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381
2026-01-05 | 124143.3478 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499
2026-01-06 | 124643.3478 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616
2026-01-07 | 125143.3478 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734
2026-01-08 | 125643.3478 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852
2026-01-09 | 126143.3478 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969
2026-01-10 | 126643.3478 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087
2026-01-11 | 127143.3478 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205
2026-01-12 | 127643.3478 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322
2026-01-13 | 128143.3478 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844
2026-01-14 | 128643.3478 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558
2026-01-15 | 129143.3478 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675
2026-01-16 | 129643.3478 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793
2026-01-17 | 130143.3478 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491
2026-01-18 | 130643.3478 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028
2026-01-19 | 131143.3478 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146
2026-01-20 | 131643.3478 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263
2026-01-21 | 132143.3478 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381
2026-01-22 | 132643.3478 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499
2026-01-23 | 133143.3478 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616
2026-01-24 | 133643.3478 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734
2026-01-25 | 134143.3478 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852
2026-01-26 | 134643.3478 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969
2026-01-27 | 135143.3478 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087
2026-01-28 | 135643.3478 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205
2026-01-29 | 136143.3478 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322
2026-01-30 | 136643.3478 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844
2026-01-31 | 137143.3478 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558
2026-02-01 | 137643.3478 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675
2026-02-02 | 138143.3478 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793
2026-02-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491

## Labor Days
Month | Actual Geo Total (Monthly) | Actual On Site Personal (Monthly) | Actual Remote Personal (Monthly) | Planned GEO total personal (Monthly) | Planned on site personal (Monthly) | Planned remote personal (Monthly) | Planned Technician I (Monthly) | Actual Technician I (Monthly) | Planned Technician II (Monthly) | Actual Technician II (Monthly) | Planned Welder (Monthly) | Actual Welder (Monthly) | Planned Engineer/supervisor (Monthly) | Actual Engineer/supervisor (Monthly) | Planned Manager/senior Engineer (Monthly) | Actual Manager/senior Engineer (Monthly) | Planned Remote mid engineer (Monthly) | Actual Remote mid engineer (Monthly) | Planned Remote senior (Monthly) | Actual Remote senior (Monthly)
April 25 | 14.5 | 0 | 14.5 | 46.9 | 0 | 46.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.25 | 46.9 | 6.25
May 25 | 0 | 0 | 0 | 49.1333 | 0 | 49.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.1333 | 0
June 25 | 13.125 | 0 | 13.125 | 39.3 | 1.3333 | 37.9667 | 0 | 0 | 0.88889 | 0 | 0 | 0 | 0.44444 | 0 | 0 | 0 | 0 | 10.625 | 37.9667 | 2.5
July 25 | 14.5 | 0 | 14.5 | 7.6667 | 7.6667 | 0 | 0 | 0 | 5.1111 | 0 | 0 | 0 | 2.5556 | 0 | 0 | 0 | 0 | 14.5 | 0 | 0
August 25 | 18.5 | 0 | 18.5 | 7 | 7 | 0 | 0 | 0 | 4.6667 | 0 | 0 | 0 | 2.3333 | 0 | 0 | 0 | 0 | 13.5 | 0 | 5
September 25 | 52 | 23 | 29 | 64.8074 | 60.2669 | 4.5405 | 0 | 0 | 41.5732 | 23 | 11.3514 | 0 | 1.6667 | 0 | 5.6757 | 0 | 0 | 14.875 | 4.5405 | 14.125
October 25 | 15.625 | 10 | 5.625 | 196.5101 | 181.5912 | 14.9189 | 0 | 0 | 125.6453 | 10 | 37.2973 | 0 | 0 | 0 | 18.6486 | 0 | 0 | 0.375 | 14.9189 | 5.25
November 25 | 0 | 0 | 0 | 124.8598 | 108.1955 | 16.6644 | 4.5238 | 0 | 48.8708 | 0 | 29.4466 | 0 | 8.369 | 0 | 16.9852 | 0 | 0 | 0 | 16.6644 | 0
December 25 | 0 | 0 | 0 | 106.1381 | 86.3571 | 19.781 | 7.381 | 0 | 17.3452 | 0 | 29.5238 | 0 | 13.6548 | 0 | 18.4524 | 0 | 0 | 0 | 19.781 | 0
January 26 | 0 | 0 | 0 | 106.1381 | 86.3571 | 19.781 | 7.381 | 0 | 17.3452 | 0 | 29.5238 | 0 | 13.6548 | 0 | 18.4524 | 0 | 0 | 0 | 19.781 | 0
February 26 | 0 | 0 | 0 | 59.242 | 33.5042 | 25.7378 | 25.8613 | 0 | 1.6786 | 0 | 2.8571 | 0 | 1.3214 | 0 | 1.7857 | 0 | 0 | 0 | 25.7378 | 0
March 26 | 0 | 0 | 0 | 59.8529 | 30.7353 | 29.1176 | 30.7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.1176 | 0
April 26 | 0 | 0 | 0 | 59.8529 | 30.7353 | 29.1176 | 30.7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.1176 | 0
May 26 | 0 | 0 | 0 | 57.1324 | 29.3382 | 27.7941 | 29.3382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7941 | 0
June 26 | 0 | 0 | 0 | 59.8529 | 30.7353 | 29.1176 | 30.7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.1176 | 0
July 26 | 0 | 0 | 0 | 62.5735 | 32.1324 | 30.4412 | 32.1324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.4412 | 0
August 26 | 0 | 0 | 0 | 74.9564 | 49.0931 | 25.8632 | 18.7598 | 0 | 7.5833 | 0 | 15.1667 | 0 | 7.5833 | 0 | 0 | 0 | 0 | 0 | 25.8632 | 0
September 26 | 0 | 0 | 0 | 45.0083 | 32.0833 | 12.925 | 6.4167 | 0 | 6.4167 | 0 | 12.8333 | 0 | 6.4167 | 0 | 0 | 0 | 0 | 0 | 12.925 | 0

## Deleted Duplicates
Date | Account | Amount | Type | Num | Memo | Split | Source_File | Category
No duplicates found