## Summary
Task ID | Task Name | Duration | Start Date | End Date | Invoice | Income Received | Income % | Planned Spend | Planned Labor Days | Status | Actual Duration | Actual Spend | Actual Labor Days | Duration % | Spent Cost % | Applied Labor % | Profit %
200 | Design Activities | 60 | 2025-04-02 | 2025-06-24 | 96480 | 96480 |  | 80400 | 134 | Completed | 60 | 22480.19 | 29.5167 | 100% | 28% | 22% | 77%
300 | Pre-Mobilization, Procurement and Manufacturing | 63 | 2025-06-25 | 2025-09-21 | 412231.3668 | 14785 |  | 199649.043 | 21 | Completed | 63 | 101687.1 | 96.5375 | 100% | 51% | 460% | 75%
400 | Drilling and Subsurface Installation | 38 | 2025-09-23 | 2025-11-13 | 371216.5516 | 665464.25 |  | 284958.9561 | 316.125 | Completed | 38 | 169749.23 | 114.0458 | 100% | 60% | 36% | 54%
500 | Field Construction | 109 | 2025-11-14 | 2026-03-02 | 361680.2306 | 235099.81 |  | 280440.1921 | 287.6 | Completed | 77 | 167239.37 | 164.6655 | 71% | 60% | 57% | 54%
600 | Operation | 190 | 2026-03-03 | 2026-11-23 | 376851.0145 | 115891.65 |  | 313382.9288 | 370 | In Progress | 13 | 10450.45 | 13.2137 | 7% | 3% | 4% | 97%
700 | Demobilization | 24 | 2026-11-24 | 2026-12-25 | 78952.6325 | 0 |  | 64960.5271 | 98.2 | Future |  | 0 | 0
TOTAL | PROJECT TOTAL | 484 | 2025-04-02 | 2026-12-25 | 1697411.796 | 1127720.71 | 66.44% | 1223791.647 | 1226.925 |  | 251 | 462494.33 | 417.9792 | 51.86% | 37.79% | 34.07% | 143.8%

## Invoice Sum
Date | Planned Income (Cumulative) | Actual Income (Daily) | Actual Income (Cumulative) | Planned Labor Sum (Cumulative) | Planned Travel&perdiem (Direct Cost) Sum (Cumulative) | Planned Parts&materials (Direct Cost) Sum (Cumulative) | Planned Outsource (Direct Cost) Sum (Cumulative) | Planned Equipment (Cumulative) | Planned 1805 · EQUIPMENT - FORKLIFT (Cumulative) | Planned 1818 · EQUIPMENT - BCU (Cumulative) | Planned 1819 · EQUIPMENT - TPMB (Cumulative) | Planned 1820 · EQUIPMENT & TOOLS (Cumulative) | Planned 1821 · EQUIPMENT - C3 (Cumulative) | Planned 1822 · EQUIPMENT - C2 (Cumulative) | Planned 1823 · EQUIPMENT - TCU BASIC (Cumulative) | Planned 1824 · EQUIPMENT - TCU PLC (Cumulative) | Planned 1825 · EQUIPMENT - BLOWER SKIDS (Cumulative) | Planned 1826 · EQUIPMENT - WELL HEADS (Cumulative) | Planned 1827 · EQUIPMENT - THERMAL WELLS (Cumulative) | Planned 1829 · EQUIPMENT - WATER TREATMENT SYS (Cumulative) | Planned 1830 · EQUIPMENT - VAPOR EXTRACTION (Cumulative) | Planned 1831 · EQUIPMENT - GTR/C3 COMPONENTS (Cumulative) | Planned 1832 · EQUIP - CONTROL/DIST PANELS (Cumulative) | Planned 1833 · EQUIPMENT - OFFICE & COMPUTER (Cumulative) | Planned 5004 · GTR COST OF SALES - PARTS (Cumulative) | Planned 5006 · DRILLING EXPENSE (Cumulative) | Planned 5101 · SALARY AND WAGES (DIRECT) (Cumulative) | Planned 5102 · PAYROLL TAXES (DIRECT) (Cumulative) | Planned 5105 · TRAVEL - AIRFARE (DIRECT) (Cumulative) | Planned 5106 · TRAVEL - HOTEL (DIRECT) (Cumulative) | Planned 5107 · TRAVEL - OTHER (DIRECT) (Cumulative) | Planned 5108 · MEALS & ENTERTAINMENT (DIRECT) (Cumulative) | Planned 5110 · TEMPORARY LABOR (DIRECT) (Cumulative) | Planned 5111 · PARTS & MATERIAL COSTS (DIRECT) (Cumulative) | Planned 5112 · CARBON & LAB SAMPLIES (DRIECT) (Cumulative) | Planned 5113 · REPAIRS & MAINT (DIRECT) (Cumulative) | Planned 5114 · RENT - BUILDING (DIRECT) (Cumulative) | Planned 5115 · RENT - EQUIPMENT (DIRECT) (Cumulative) | Planned 5116 · Rent - Storage (Direct) (Cumulative) | Planned 5120 · OUTSIDE SERVICES (DIRECT) (Cumulative) | Planned 5121 · FREIGHT & SHIPPING (DIRECT) (Cumulative) | Planned 5122 · MOTOR VEHICLE EXP (DIRECT) (Cumulative) | Planned 5123 · AUTO FUEL (DIRECT) (Cumulative) | Planned 5124 · LICENSE AND PERMITS (DIRECT) (Cumulative) | Planned 5128 · HEALTH & SAFETY EQUIP (DIRECT) (Cumulative) | Planned 5129 · MISC EXPENSES (DIRECT) (Cumulative) | Planned 5132 · INTERNET FEE (DIRECT) (Cumulative) | Planned 6999 · UNCATEGORIZED EXPENSES (Cumulative)
2025-04-02 | 1148.5714 | 0 | 0 | 1148.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 2297.1429 | 0 | 0 | 2297.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2297.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 3445.7143 | 0 | 0 | 3445.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3445.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 4594.2857 | 0 | 0 | 4594.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4594.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 5742.8571 | 0 | 0 | 5742.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5742.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 6891.4286 | 0 | 0 | 6891.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6891.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 8040 | 0 | 0 | 8040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 9188.5714 | 51408 | 51408 | 9188.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9188.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 10337.1429 | 0 | 51408 | 10337.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10337.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 11485.7143 | 0 | 51408 | 11485.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11485.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 12634.2857 | 0 | 51408 | 12634.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12634.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 13782.8571 | 0 | 51408 | 13782.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13782.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 14931.4286 | 0 | 51408 | 14931.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14931.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 16080 | 0 | 51408 | 16080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 17228.5714 | 0 | 51408 | 17228.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17228.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 18377.1429 | 0 | 51408 | 18377.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18377.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 19525.7143 | 0 | 51408 | 19525.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19525.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 20674.2857 | 0 | 51408 | 20674.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20674.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 21822.8571 | 0 | 51408 | 21822.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21822.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 22971.4286 | 0 | 51408 | 22971.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22971.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 24120 | 0 | 51408 | 24120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 25268.5714 | 0 | 51408 | 25268.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25268.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 26417.1429 | 0 | 51408 | 26417.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26417.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 27565.7143 | 0 | 51408 | 27565.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27565.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 28714.2857 | 0 | 51408 | 28714.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28714.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 29862.8571 | 0 | 51408 | 29862.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29862.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 31011.4286 | 0 | 51408 | 31011.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31011.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 32160 | 0 | 51408 | 32160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 33308.5714 | 0 | 51408 | 33308.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33308.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 34457.1429 | 0 | 51408 | 34457.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34457.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 35605.7143 | 0 | 51408 | 35605.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35605.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 36754.2857 | 0 | 51408 | 36754.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36754.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 37902.8571 | 0 | 51408 | 37902.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37902.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 39051.4286 | 0 | 51408 | 39051.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39051.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 40200 | 0 | 51408 | 40200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 41348.5714 | 0 | 51408 | 41348.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41348.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 42497.1429 | 0 | 51408 | 42497.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42497.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 43645.7143 | 0 | 51408 | 43645.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43645.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 44794.2857 | 0 | 51408 | 44794.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44794.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 45942.8571 | 0 | 51408 | 45942.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45942.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 47091.4286 | 0 | 51408 | 47091.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47091.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 48240 | 0 | 51408 | 48240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 49388.5714 | 0 | 51408 | 49388.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49388.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 50537.1429 | 0 | 51408 | 50537.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50537.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 51685.7143 | 0 | 51408 | 51685.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51685.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 52834.2857 | 0 | 51408 | 52834.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52834.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 53982.8571 | 0 | 51408 | 53982.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53982.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 55131.4286 | 0 | 51408 | 55131.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55131.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 56280 | 0 | 51408 | 56280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 57428.5714 | 0 | 51408 | 57428.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57428.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 58577.1429 | 0 | 51408 | 58577.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58577.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 59725.7143 | 0 | 51408 | 59725.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59725.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 60874.2857 | 0 | 51408 | 60874.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60874.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 62022.8571 | 0 | 51408 | 62022.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62022.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 63171.4286 | 0 | 51408 | 63171.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63171.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 64320 | 0 | 51408 | 64320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 65468.5714 | 45072 | 96480 | 65468.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65468.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 66617.1429 | 0 | 96480 | 66617.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66617.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 67765.7143 | 0 | 96480 | 67765.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67765.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 68914.2857 | 0 | 96480 | 68914.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68914.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 70062.8571 | 0 | 96480 | 70062.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70062.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 71211.4286 | 0 | 96480 | 71211.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71211.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 72360 | 0 | 96480 | 72360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 73508.5714 | 0 | 96480 | 73508.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73508.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 74657.1429 | 0 | 96480 | 74657.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74657.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 75805.7143 | 0 | 96480 | 75805.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75805.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 76954.2857 | 0 | 96480 | 76954.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76954.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 78102.8571 | 0 | 96480 | 78102.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78102.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 79251.4286 | 0 | 96480 | 79251.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79251.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 80400 | 0 | 96480 | 80400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 81548.5714 | 0 | 96480 | 81548.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81548.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 82697.1429 | 0 | 96480 | 82697.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82697.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 83845.7143 | 0 | 96480 | 83845.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83845.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 84994.2857 | 0 | 96480 | 84994.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84994.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 86142.8571 | 0 | 96480 | 86142.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86142.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 87291.4286 | 0 | 96480 | 87291.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87291.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 88440 | 0 | 96480 | 88440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 89588.5714 | 0 | 96480 | 89588.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89588.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 90737.1429 | 0 | 96480 | 90737.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90737.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 91885.7143 | 0 | 96480 | 91885.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91885.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 93034.2857 | 0 | 96480 | 93034.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93034.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 94182.8571 | 0 | 96480 | 94182.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94182.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 95331.4286 | 0 | 96480 | 95331.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95331.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 96480 | 0 | 96480 | 96480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 101111.8131 | 0 | 96480 | 96707.2708 | 162.3119 | 1462.3349 | 424.7191 | 2355.1764 | 0 | 0 | 63.627 | 0 | 0 | 1872.5843 | 105.1685 | 0 | 0 | 49.0787 | 0 | 0 | 111.3472 | 153.3708 | 0 | 0 | 0 | 0 | 96707.2708 | 0 | 62.8737 | 65.7303 | 3.3708 | 8.427 | 0 | 1462.3349 | 0 | 0 | 1.1236 | 29.2135 | 73.0337 | 146.0674 | 146.0674 | 21.9101 | 0 | 0 | 0 | 0 | 29.2135 | 0
2025-06-26 | 105743.6262 | 0 | 96480 | 96934.5415 | 324.6238 | 2924.6699 | 849.4382 | 4710.3528 | 0 | 0 | 127.2539 | 0 | 0 | 3745.1685 | 210.3371 | 0 | 0 | 98.1573 | 0 | 0 | 222.6944 | 306.7416 | 0 | 0 | 0 | 0 | 96934.5415 | 0 | 125.7474 | 131.4607 | 6.7416 | 16.8539 | 0 | 2924.6699 | 0 | 0 | 2.2472 | 58.427 | 146.0674 | 292.1348 | 292.1348 | 43.8202 | 0 | 0 | 0 | 0 | 58.427 | 0
2025-06-27 | 110375.4393 | 0 | 96480 | 97161.8123 | 486.9357 | 4387.0048 | 1274.1573 | 7065.5292 | 0 | 0 | 190.8809 | 0 | 0 | 5617.7528 | 315.5056 | 0 | 0 | 147.236 | 0 | 0 | 334.0416 | 460.1124 | 0 | 0 | 0 | 0 | 97161.8123 | 0 | 188.6211 | 197.191 | 10.1124 | 25.2809 | 0 | 4387.0048 | 0 | 0 | 3.3708 | 87.6404 | 219.1011 | 438.2022 | 438.2022 | 65.7303 | 0 | 0 | 0 | 0 | 87.6404 | 0
2025-06-28 | 115007.2524 | 0 | 96480 | 97389.083 | 649.2476 | 5849.3398 | 1698.8764 | 9420.7056 | 0 | 0 | 254.5079 | 0 | 0 | 7490.3371 | 420.6742 | 0 | 0 | 196.3146 | 0 | 0 | 445.3888 | 613.4831 | 0 | 0 | 0 | 0 | 97389.083 | 0 | 251.4948 | 262.9213 | 13.4831 | 33.7079 | 0 | 5849.3398 | 0 | 0 | 4.4944 | 116.8539 | 292.1348 | 584.2697 | 584.2697 | 87.6404 | 0 | 0 | 0 | 0 | 116.8539 | 0
2025-06-29 | 119639.0655 | 0 | 96480 | 97616.3538 | 811.5596 | 7311.6747 | 2123.5955 | 11775.882 | 0 | 0 | 318.1348 | 0 | 0 | 9362.9213 | 525.8427 | 0 | 0 | 245.3933 | 0 | 0 | 556.736 | 766.8539 | 0 | 0 | 0 | 0 | 97616.3538 | 0 | 314.3685 | 328.6517 | 16.8539 | 42.1348 | 0 | 7311.6747 | 0 | 0 | 5.618 | 146.0674 | 365.1685 | 730.3371 | 730.3371 | 109.5506 | 0 | 0 | 0 | 0 | 146.0674 | 0
2025-06-30 | 124270.8787 | 0 | 96480 | 97843.6245 | 973.8715 | 8774.0097 | 2548.3146 | 14131.0584 | 0 | 0 | 381.7618 | 0 | 0 | 11235.5056 | 631.0112 | 0 | 0 | 294.4719 | 0 | 0 | 668.0831 | 920.2247 | 0 | 0 | 0 | 0 | 97843.6245 | 0 | 377.2422 | 394.382 | 20.2247 | 50.5618 | 0 | 8774.0097 | 0 | 0 | 6.7416 | 175.2809 | 438.2022 | 876.4045 | 876.4045 | 131.4607 | 0 | 0 | 0 | 0 | 175.2809 | 0
2025-07-01 | 128902.6918 | 0 | 96480 | 98070.8953 | 1136.1834 | 10236.3446 | 2973.0337 | 16486.2348 | 0 | 0 | 445.3888 | 0 | 0 | 13108.0899 | 736.1798 | 0 | 0 | 343.5506 | 0 | 0 | 779.4303 | 1073.5955 | 0 | 0 | 0 | 0 | 98070.8953 | 0 | 440.116 | 460.1124 | 23.5955 | 58.9888 | 0 | 10236.3446 | 0 | 0 | 7.8652 | 204.4944 | 511.236 | 1022.4719 | 1022.4719 | 153.3708 | 0 | 0 | 0 | 0 | 204.4944 | 0
2025-07-02 | 133534.5049 | 0 | 96480 | 98298.166 | 1298.4953 | 11698.6796 | 3397.7528 | 18841.4112 | 0 | 0 | 509.0157 | 0 | 0 | 14980.6742 | 841.3483 | 0 | 0 | 392.6292 | 0 | 0 | 890.7775 | 1226.9663 | 0 | 0 | 0 | 0 | 98298.166 | 0 | 502.9897 | 525.8427 | 26.9663 | 67.4157 | 0 | 11698.6796 | 0 | 0 | 8.9888 | 233.7079 | 584.2697 | 1168.5393 | 1168.5393 | 175.2809 | 0 | 0 | 0 | 0 | 233.7079 | 0
2025-07-03 | 138166.318 | 0 | 96480 | 98525.4368 | 1460.8072 | 13161.0145 | 3822.4719 | 21196.5876 | 0 | 0 | 572.6427 | 0 | 0 | 16853.2584 | 946.5169 | 0 | 0 | 441.7079 | 0 | 0 | 1002.1247 | 1380.3371 | 0 | 0 | 0 | 0 | 98525.4368 | 0 | 565.8634 | 591.573 | 30.3371 | 75.8427 | 0 | 13161.0145 | 0 | 0 | 10.1124 | 262.9213 | 657.3034 | 1314.6067 | 1314.6067 | 197.191 | 0 | 0 | 0 | 0 | 262.9213 | 0
2025-07-04 | 142798.1311 | 0 | 96480 | 98752.7075 | 1623.1191 | 14623.3494 | 4247.191 | 23551.764 | 0 | 0 | 636.2697 | 0 | 0 | 18725.8427 | 1051.6854 | 0 | 0 | 490.7865 | 0 | 0 | 1113.4719 | 1533.7079 | 0 | 0 | 0 | 0 | 98752.7075 | 0 | 628.7371 | 657.3034 | 33.7079 | 84.2697 | 0 | 14623.3494 | 0 | 0 | 11.236 | 292.1348 | 730.3371 | 1460.6742 | 1460.6742 | 219.1011 | 0 | 0 | 0 | 0 | 292.1348 | 0
2025-07-05 | 147429.9442 | 0 | 96480 | 98979.9783 | 1785.431 | 16085.6844 | 4671.9101 | 25906.9404 | 0 | 0 | 699.8966 | 0 | 0 | 20598.427 | 1156.8539 | 0 | 0 | 539.8652 | 0 | 0 | 1224.8191 | 1687.0787 | 0 | 0 | 0 | 0 | 98979.9783 | 0 | 691.6108 | 723.0337 | 37.0787 | 92.6966 | 0 | 16085.6844 | 0 | 0 | 12.3596 | 321.3483 | 803.3708 | 1606.7416 | 1606.7416 | 241.0112 | 0 | 0 | 0 | 0 | 321.3483 | 0
2025-07-06 | 152061.7573 | 0 | 96480 | 99207.249 | 1947.7429 | 17548.0193 | 5096.6292 | 28262.1169 | 0 | 0 | 763.5236 | 0 | 0 | 22471.0112 | 1262.0225 | 0 | 0 | 588.9438 | 0 | 0 | 1336.1663 | 1840.4494 | 0 | 0 | 0 | 0 | 99207.249 | 0 | 754.4845 | 788.764 | 40.4494 | 101.1236 | 0 | 17548.0193 | 0 | 0 | 13.4831 | 350.5618 | 876.4045 | 1752.809 | 1752.809 | 262.9213 | 0 | 0 | 0 | 0 | 350.5618 | 0
2025-07-07 | 156693.5704 | 0 | 96480 | 99434.5198 | 2110.0548 | 19010.3543 | 5521.3483 | 30617.2933 | 0 | 0 | 827.1506 | 0 | 0 | 24343.5955 | 1367.191 | 0 | 0 | 638.0225 | 0 | 0 | 1447.5135 | 1993.8202 | 0 | 0 | 0 | 0 | 99434.5198 | 0 | 817.3582 | 854.4944 | 43.8202 | 109.5506 | 0 | 19010.3543 | 0 | 0 | 14.6067 | 379.7753 | 949.4382 | 1898.8764 | 1898.8764 | 284.8315 | 0 | 0 | 0 | 0 | 379.7753 | 0
2025-07-08 | 161325.3835 | 0 | 96480 | 99661.7905 | 2272.3667 | 20472.6892 | 5946.0674 | 32972.4697 | 0 | 0 | 890.7775 | 0 | 0 | 26216.1798 | 1472.3596 | 0 | 0 | 687.1011 | 0 | 0 | 1558.8607 | 2147.191 | 0 | 0 | 0 | 0 | 99661.7905 | 0 | 880.2319 | 920.2247 | 47.191 | 117.9775 | 0 | 20472.6892 | 0 | 0 | 15.7303 | 408.9888 | 1022.4719 | 2044.9438 | 2044.9438 | 306.7416 | 0 | 0 | 0 | 0 | 408.9888 | 0
2025-07-09 | 165957.1966 | 0 | 96480 | 99889.0613 | 2434.6787 | 21935.0242 | 6370.7865 | 35327.6461 | 0 | 0 | 954.4045 | 0 | 0 | 28088.764 | 1577.5281 | 0 | 0 | 736.1798 | 0 | 0 | 1670.2079 | 2300.5618 | 0 | 0 | 0 | 0 | 99889.0613 | 0 | 943.1056 | 985.9551 | 50.5618 | 126.4045 | 0 | 21935.0242 | 0 | 0 | 16.8539 | 438.2022 | 1095.5056 | 2191.0112 | 2191.0112 | 328.6517 | 0 | 0 | 0 | 0 | 438.2022 | 0
2025-07-10 | 170589.0098 | 0 | 96480 | 100116.332 | 2596.9906 | 23397.3591 | 6795.5056 | 37682.8225 | 0 | 0 | 1018.0315 | 0 | 0 | 29961.3483 | 1682.6966 | 0 | 0 | 785.2584 | 0 | 0 | 1781.5551 | 2453.9326 | 0 | 0 | 0 | 0 | 100116.332 | 0 | 1005.9793 | 1051.6854 | 53.9326 | 134.8315 | 0 | 23397.3591 | 0 | 0 | 17.9775 | 467.4157 | 1168.5393 | 2337.0787 | 2337.0787 | 350.5618 | 0 | 0 | 0 | 0 | 467.4157 | 0
2025-07-11 | 175220.8229 | 0 | 96480 | 100343.6028 | 2759.3025 | 24859.694 | 7220.2247 | 40037.9989 | 0 | 0 | 1081.6584 | 0 | 0 | 31833.9326 | 1787.8652 | 0 | 0 | 834.3371 | 0 | 0 | 1892.9022 | 2607.3034 | 0 | 0 | 0 | 0 | 100343.6028 | 0 | 1068.853 | 1117.4157 | 57.3034 | 143.2584 | 0 | 24859.694 | 0 | 0 | 19.1011 | 496.6292 | 1241.573 | 2483.1461 | 2483.1461 | 372.4719 | 0 | 0 | 0 | 0 | 496.6292 | 0
2025-07-12 | 179852.636 | 0 | 96480 | 100570.8735 | 2921.6144 | 26322.029 | 7644.9438 | 42393.1753 | 0 | 0 | 1145.2854 | 0 | 0 | 33706.5169 | 1893.0337 | 0 | 0 | 883.4157 | 0 | 0 | 2004.2494 | 2760.6742 | 0 | 0 | 0 | 0 | 100570.8735 | 0 | 1131.7267 | 1183.1461 | 60.6742 | 151.6854 | 0 | 26322.029 | 0 | 0 | 20.2247 | 525.8427 | 1314.6067 | 2629.2135 | 2629.2135 | 394.382 | 0 | 0 | 0 | 0 | 525.8427 | 0
2025-07-13 | 184484.4491 | 0 | 96480 | 100798.1443 | 3083.9263 | 27784.3639 | 8069.6629 | 44748.3517 | 0 | 0 | 1208.9124 | 0 | 0 | 35579.1011 | 1998.2022 | 0 | 0 | 932.4944 | 0 | 0 | 2115.5966 | 2914.0449 | 0 | 0 | 0 | 0 | 100798.1443 | 0 | 1194.6004 | 1248.8764 | 64.0449 | 160.1124 | 0 | 27784.3639 | 0 | 0 | 21.3483 | 555.0562 | 1387.6404 | 2775.2809 | 2775.2809 | 416.2921 | 0 | 0 | 0 | 0 | 555.0562 | 0
2025-07-14 | 189116.2622 | 0 | 96480 | 101025.415 | 3246.2382 | 29246.6989 | 8494.382 | 47103.5281 | 0 | 0 | 1272.5393 | 0 | 0 | 37451.6854 | 2103.3708 | 0 | 0 | 981.573 | 0 | 0 | 2226.9438 | 3067.4157 | 0 | 0 | 0 | 0 | 101025.415 | 0 | 1257.4742 | 1314.6067 | 67.4157 | 168.5393 | 0 | 29246.6989 | 0 | 0 | 22.4719 | 584.2697 | 1460.6742 | 2921.3483 | 2921.3483 | 438.2022 | 0 | 0 | 0 | 0 | 584.2697 | 0
2025-07-15 | 193748.0753 | 0 | 96480 | 101252.6858 | 3408.5501 | 30709.0338 | 8919.1011 | 49458.7045 | 0 | 0 | 1336.1663 | 0 | 0 | 39324.2697 | 2208.5393 | 0 | 0 | 1030.6517 | 0 | 0 | 2338.291 | 3220.7865 | 0 | 0 | 0 | 0 | 101252.6858 | 0 | 1320.3479 | 1380.3371 | 70.7865 | 176.9663 | 0 | 30709.0338 | 0 | 0 | 23.5955 | 613.4831 | 1533.7079 | 3067.4157 | 3067.4157 | 460.1124 | 0 | 0 | 0 | 0 | 613.4831 | 0
2025-07-16 | 198379.8884 | 0 | 96480 | 101479.9565 | 3570.862 | 32171.3688 | 9343.8202 | 51813.8809 | 0 | 0 | 1399.7933 | 0 | 0 | 41196.8539 | 2313.7079 | 0 | 0 | 1079.7303 | 0 | 0 | 2449.6382 | 3374.1573 | 0 | 0 | 0 | 0 | 101479.9565 | 0 | 1383.2216 | 1446.0674 | 74.1573 | 185.3933 | 0 | 32171.3688 | 0 | 0 | 24.7191 | 642.6966 | 1606.7416 | 3213.4831 | 3213.4831 | 482.0225 | 0 | 0 | 0 | 0 | 642.6966 | 0
2025-07-17 | 203011.7015 | 0 | 96480 | 101707.2273 | 3733.1739 | 33633.7037 | 9768.5393 | 54169.0573 | 0 | 0 | 1463.4202 | 0 | 0 | 43069.4382 | 2418.8764 | 0 | 0 | 1128.809 | 0 | 0 | 2560.9854 | 3527.5281 | 0 | 0 | 0 | 0 | 101707.2273 | 0 | 1446.0953 | 1511.7978 | 77.5281 | 193.8202 | 0 | 33633.7037 | 0 | 0 | 25.8427 | 671.9101 | 1679.7753 | 3359.5506 | 3359.5506 | 503.9326 | 0 | 0 | 0 | 0 | 671.9101 | 0
2025-07-18 | 207643.5146 | 0 | 96480 | 101934.498 | 3895.4858 | 35096.0387 | 10193.2584 | 56524.2337 | 0 | 0 | 1527.0472 | 0 | 0 | 44942.0225 | 2524.0449 | 0 | 0 | 1177.8876 | 0 | 0 | 2672.3326 | 3680.8989 | 0 | 0 | 0 | 0 | 101934.498 | 0 | 1508.969 | 1577.5281 | 80.8989 | 202.2472 | 0 | 35096.0387 | 0 | 0 | 26.9663 | 701.1236 | 1752.809 | 3505.618 | 3505.618 | 525.8427 | 0 | 0 | 0 | 0 | 701.1236 | 0
2025-07-19 | 212275.3277 | 0 | 96480 | 102161.7688 | 4057.7978 | 36558.3736 | 10617.9775 | 58879.4101 | 0 | 0 | 1590.6742 | 0 | 0 | 46814.6067 | 2629.2135 | 0 | 0 | 1226.9663 | 0 | 0 | 2783.6798 | 3834.2697 | 0 | 0 | 0 | 0 | 102161.7688 | 0 | 1571.8427 | 1643.2584 | 84.2697 | 210.6742 | 0 | 36558.3736 | 0 | 0 | 28.0899 | 730.3371 | 1825.8427 | 3651.6854 | 3651.6854 | 547.7528 | 0 | 0 | 0 | 0 | 730.3371 | 0
2025-07-20 | 216907.1409 | 0 | 96480 | 102389.0395 | 4220.1097 | 38020.7085 | 11042.6966 | 61234.5865 | 0 | 0 | 1654.3011 | 0 | 0 | 48687.191 | 2734.382 | 0 | 0 | 1276.0449 | 0 | 0 | 2895.027 | 3987.6404 | 0 | 0 | 0 | 0 | 102389.0395 | 0 | 1634.7164 | 1708.9888 | 87.6404 | 219.1011 | 0 | 38020.7085 | 0 | 0 | 29.2135 | 759.5506 | 1898.8764 | 3797.7528 | 3797.7528 | 569.6629 | 0 | 0 | 0 | 0 | 759.5506 | 0
2025-07-21 | 221538.954 | 0 | 96480 | 102616.3103 | 4382.4216 | 39483.0435 | 11467.4157 | 63589.7629 | 0 | 0 | 1717.9281 | 0 | 0 | 50559.7753 | 2839.5506 | 0 | 0 | 1325.1236 | 0 | 0 | 3006.3742 | 4141.0112 | 0 | 0 | 0 | 0 | 102616.3103 | 0 | 1697.5901 | 1774.7191 | 91.0112 | 227.5281 | 0 | 39483.0435 | 0 | 0 | 30.3371 | 788.764 | 1971.9101 | 3943.8202 | 3943.8202 | 591.573 | 0 | 0 | 0 | 0 | 788.764 | 0
2025-07-22 | 226170.7671 | 0 | 96480 | 102843.581 | 4544.7335 | 40945.3784 | 11892.1348 | 65944.9393 | 0 | 0 | 1781.5551 | 0 | 0 | 52432.3596 | 2944.7191 | 0 | 0 | 1374.2022 | 0 | 0 | 3117.7213 | 4294.382 | 0 | 0 | 0 | 0 | 102843.581 | 0 | 1760.4638 | 1840.4494 | 94.382 | 235.9551 | 0 | 40945.3784 | 0 | 0 | 31.4607 | 817.9775 | 2044.9438 | 4089.8876 | 4089.8876 | 613.4831 | 0 | 0 | 0 | 0 | 817.9775 | 0
2025-07-23 | 230802.5802 | 0 | 96480 | 103070.8518 | 4707.0454 | 42407.7134 | 12316.8539 | 68300.1157 | 0 | 0 | 1845.182 | 0 | 0 | 54304.9438 | 3049.8876 | 0 | 0 | 1423.2809 | 0 | 0 | 3229.0685 | 4447.7528 | 0 | 0 | 0 | 0 | 103070.8518 | 0 | 1823.3375 | 1906.1798 | 97.7528 | 244.382 | 0 | 42407.7134 | 0 | 0 | 32.5843 | 847.191 | 2117.9775 | 4235.9551 | 4235.9551 | 635.3933 | 0 | 0 | 0 | 0 | 847.191 | 0
2025-07-24 | 235434.3933 | 0 | 96480 | 103298.1225 | 4869.3573 | 43870.0483 | 12741.573 | 70655.2921 | 0 | 0 | 1908.809 | 0 | 0 | 56177.5281 | 3155.0562 | 0 | 0 | 1472.3596 | 0 | 0 | 3340.4157 | 4601.1236 | 0 | 0 | 0 | 0 | 103298.1225 | 0 | 1886.2112 | 1971.9101 | 101.1236 | 252.809 | 0 | 43870.0483 | 0 | 0 | 33.7079 | 876.4045 | 2191.0112 | 4382.0225 | 4382.0225 | 657.3034 | 0 | 0 | 0 | 0 | 876.4045 | 0
2025-07-25 | 240066.2064 | 0 | 96480 | 103525.3933 | 5031.6692 | 45332.3833 | 13166.2921 | 73010.4685 | 0 | 0 | 1972.436 | 0 | 0 | 58050.1124 | 3260.2247 | 0 | 0 | 1521.4382 | 0 | 0 | 3451.7629 | 4754.4944 | 0 | 0 | 0 | 0 | 103525.3933 | 0 | 1949.0849 | 2037.6404 | 104.4944 | 261.236 | 0 | 45332.3833 | 0 | 0 | 34.8315 | 905.618 | 2264.0449 | 4528.0899 | 4528.0899 | 679.2135 | 0 | 0 | 0 | 0 | 905.618 | 0
2025-07-26 | 244698.0195 | 0 | 96480 | 103752.664 | 5193.9811 | 46794.7182 | 13591.0112 | 75365.6449 | 0 | 0 | 2036.0629 | 0 | 0 | 59922.6966 | 3365.3933 | 0 | 0 | 1570.5169 | 0 | 0 | 3563.1101 | 4907.8652 | 0 | 0 | 0 | 0 | 103752.664 | 0 | 2011.9587 | 2103.3708 | 107.8652 | 269.6629 | 0 | 46794.7182 | 0 | 0 | 35.9551 | 934.8315 | 2337.0787 | 4674.1573 | 4674.1573 | 701.1236 | 0 | 0 | 0 | 0 | 934.8315 | 0
2025-07-27 | 249329.8326 | 0 | 96480 | 103979.9348 | 5356.293 | 48257.0531 | 14015.7303 | 77720.8213 | 0 | 0 | 2099.6899 | 0 | 0 | 61795.2809 | 3470.5618 | 0 | 0 | 1619.5955 | 0 | 0 | 3674.4573 | 5061.236 | 0 | 0 | 0 | 0 | 103979.9348 | 0 | 2074.8324 | 2169.1011 | 111.236 | 278.0899 | 0 | 48257.0531 | 0 | 0 | 37.0787 | 964.0449 | 2410.1124 | 4820.2247 | 4820.2247 | 723.0337 | 0 | 0 | 0 | 0 | 964.0449 | 0
2025-07-28 | 253961.6457 | 0 | 96480 | 104207.2055 | 5518.6049 | 49719.3881 | 14440.4494 | 80075.9978 | 0 | 0 | 2163.3169 | 0 | 0 | 63667.8652 | 3575.7303 | 0 | 0 | 1668.6742 | 0 | 0 | 3785.8045 | 5214.6067 | 0 | 0 | 0 | 0 | 104207.2055 | 0 | 2137.7061 | 2234.8315 | 114.6067 | 286.5169 | 0 | 49719.3881 | 0 | 0 | 38.2022 | 993.2584 | 2483.1461 | 4966.2921 | 4966.2921 | 744.9438 | 0 | 0 | 0 | 0 | 993.2584 | 0
2025-07-29 | 258593.4588 | 0 | 96480 | 104434.4763 | 5680.9169 | 51181.723 | 14865.1685 | 82431.1742 | 0 | 0 | 2226.9438 | 0 | 0 | 65540.4494 | 3680.8989 | 0 | 0 | 1717.7528 | 0 | 0 | 3897.1517 | 5367.9775 | 0 | 0 | 0 | 0 | 104434.4763 | 0 | 2200.5798 | 2300.5618 | 117.9775 | 294.9438 | 0 | 51181.723 | 0 | 0 | 39.3258 | 1022.4719 | 2556.1798 | 5112.3596 | 5112.3596 | 766.8539 | 0 | 0 | 0 | 0 | 1022.4719 | 0
2025-07-30 | 263225.272 | 0 | 96480 | 104661.747 | 5843.2288 | 52644.058 | 15289.8876 | 84786.3506 | 0 | 0 | 2290.5708 | 0 | 0 | 67413.0337 | 3786.0674 | 0 | 0 | 1766.8315 | 0 | 0 | 4008.4989 | 5521.3483 | 0 | 0 | 0 | 0 | 104661.747 | 0 | 2263.4535 | 2366.2921 | 121.3483 | 303.3708 | 0 | 52644.058 | 0 | 0 | 40.4494 | 1051.6854 | 2629.2135 | 5258.427 | 5258.427 | 788.764 | 0 | 0 | 0 | 0 | 1051.6854 | 0
2025-07-31 | 267857.0851 | 0 | 96480 | 104889.0178 | 6005.5407 | 54106.3929 | 15714.6067 | 87141.527 | 0 | 0 | 2354.1978 | 0 | 0 | 69285.618 | 3891.236 | 0 | 0 | 1815.9101 | 0 | 0 | 4119.8461 | 5674.7191 | 0 | 0 | 0 | 0 | 104889.0178 | 0 | 2326.3272 | 2432.0225 | 124.7191 | 311.7978 | 0 | 54106.3929 | 0 | 0 | 41.573 | 1080.8989 | 2702.2472 | 5404.4944 | 5404.4944 | 810.6742 | 0 | 0 | 0 | 0 | 1080.8989 | 0
2025-08-01 | 272488.8982 | 0 | 96480 | 105116.2885 | 6167.8526 | 55568.7279 | 16139.3258 | 89496.7034 | 0 | 0 | 2417.8247 | 0 | 0 | 71158.2022 | 3996.4045 | 0 | 0 | 1864.9888 | 0 | 0 | 4231.1933 | 5828.0899 | 0 | 0 | 0 | 0 | 105116.2885 | 0 | 2389.2009 | 2497.7528 | 128.0899 | 320.2247 | 0 | 55568.7279 | 0 | 0 | 42.6966 | 1110.1124 | 2775.2809 | 5550.5618 | 5550.5618 | 832.5843 | 0 | 0 | 0 | 0 | 1110.1124 | 0
2025-08-02 | 277120.7113 | 0 | 96480 | 105343.5593 | 6330.1645 | 57031.0628 | 16564.0449 | 91851.8798 | 0 | 0 | 2481.4517 | 0 | 0 | 73030.7865 | 4101.573 | 0 | 0 | 1914.0674 | 0 | 0 | 4342.5404 | 5981.4607 | 0 | 0 | 0 | 0 | 105343.5593 | 0 | 2452.0746 | 2563.4831 | 131.4607 | 328.6517 | 0 | 57031.0628 | 0 | 0 | 43.8202 | 1139.3258 | 2848.3146 | 5696.6292 | 5696.6292 | 854.4944 | 0 | 0 | 0 | 0 | 1139.3258 | 0
2025-08-03 | 281752.5244 | 0 | 96480 | 105570.83 | 6492.4764 | 58493.3978 | 16988.764 | 94207.0562 | 0 | 0 | 2545.0787 | 0 | 0 | 74903.3708 | 4206.7416 | 0 | 0 | 1963.1461 | 0 | 0 | 4453.8876 | 6134.8315 | 0 | 0 | 0 | 0 | 105570.83 | 0 | 2514.9483 | 2629.2135 | 134.8315 | 337.0787 | 0 | 58493.3978 | 0 | 0 | 44.9438 | 1168.5393 | 2921.3483 | 5842.6966 | 5842.6966 | 876.4045 | 0 | 0 | 0 | 0 | 1168.5393 | 0
2025-08-04 | 286384.3375 | 0 | 96480 | 105798.1008 | 6654.7883 | 59955.7327 | 17413.4831 | 96562.2326 | 0 | 0 | 2608.7056 | 0 | 0 | 76775.9551 | 4311.9101 | 0 | 0 | 2012.2247 | 0 | 0 | 4565.2348 | 6288.2022 | 0 | 0 | 0 | 0 | 105798.1008 | 0 | 2577.822 | 2694.9438 | 138.2022 | 345.5056 | 0 | 59955.7327 | 0 | 0 | 46.0674 | 1197.7528 | 2994.382 | 5988.764 | 5988.764 | 898.3146 | 0 | 0 | 0 | 0 | 1197.7528 | 0
2025-08-05 | 291016.1506 | 0 | 96480 | 106025.3715 | 6817.1002 | 61418.0676 | 17838.2022 | 98917.409 | 0 | 0 | 2672.3326 | 0 | 0 | 78648.5393 | 4417.0787 | 0 | 0 | 2061.3034 | 0 | 0 | 4676.582 | 6441.573 | 0 | 0 | 0 | 0 | 106025.3715 | 0 | 2640.6957 | 2760.6742 | 141.573 | 353.9326 | 0 | 61418.0676 | 0 | 0 | 47.191 | 1226.9663 | 3067.4157 | 6134.8315 | 6134.8315 | 920.2247 | 0 | 0 | 0 | 0 | 1226.9663 | 0
2025-08-06 | 295647.9637 | 0 | 96480 | 106252.6423 | 6979.4121 | 62880.4026 | 18262.9213 | 101272.5854 | 0 | 0 | 2735.9596 | 0 | 0 | 80521.1236 | 4522.2472 | 0 | 0 | 2110.382 | 0 | 0 | 4787.9292 | 6594.9438 | 0 | 0 | 0 | 0 | 106252.6423 | 0 | 2703.5694 | 2826.4045 | 144.9438 | 362.3596 | 0 | 62880.4026 | 0 | 0 | 48.3146 | 1256.1798 | 3140.4494 | 6280.8989 | 6280.8989 | 942.1348 | 0 | 0 | 0 | 0 | 1256.1798 | 0
2025-08-07 | 300279.7768 | 0 | 96480 | 106479.913 | 7141.724 | 64342.7375 | 18687.6404 | 103627.7618 | 0 | 0 | 2799.5865 | 0 | 0 | 82393.7079 | 4627.4157 | 0 | 0 | 2159.4607 | 0 | 0 | 4899.2764 | 6748.3146 | 0 | 0 | 0 | 0 | 106479.913 | 0 | 2766.4431 | 2892.1348 | 148.3146 | 370.7865 | 0 | 64342.7375 | 0 | 0 | 49.4382 | 1285.3933 | 3213.4831 | 6426.9663 | 6426.9663 | 964.0449 | 0 | 0 | 0 | 0 | 1285.3933 | 0
2025-08-08 | 304911.5899 | 0 | 96480 | 106707.1838 | 7304.036 | 65805.0725 | 19112.3596 | 105982.9382 | 0 | 0 | 2863.2135 | 0 | 0 | 84266.2921 | 4732.5843 | 0 | 0 | 2208.5393 | 0 | 0 | 5010.6236 | 6901.6854 | 0 | 0 | 0 | 0 | 106707.1838 | 0 | 2829.3169 | 2957.8652 | 151.6854 | 379.2135 | 0 | 65805.0725 | 0 | 0 | 50.5618 | 1314.6067 | 3286.5169 | 6573.0337 | 6573.0337 | 985.9551 | 0 | 0 | 0 | 0 | 1314.6067 | 0
2025-08-09 | 309543.4031 | 0 | 96480 | 106934.4545 | 7466.3479 | 67267.4074 | 19537.0787 | 108338.1146 | 0 | 0 | 2926.8404 | 0 | 0 | 86138.8764 | 4837.7528 | 0 | 0 | 2257.618 | 0 | 0 | 5121.9708 | 7055.0562 | 0 | 0 | 0 | 0 | 106934.4545 | 0 | 2892.1906 | 3023.5955 | 155.0562 | 387.6404 | 0 | 67267.4074 | 0 | 0 | 51.6854 | 1343.8202 | 3359.5506 | 6719.1011 | 6719.1011 | 1007.8652 | 0 | 0 | 0 | 0 | 1343.8202 | 0
2025-08-10 | 314175.2162 | 0 | 96480 | 107161.7253 | 7628.6598 | 68729.7424 | 19961.7978 | 110693.291 | 0 | 0 | 2990.4674 | 0 | 0 | 88011.4607 | 4942.9213 | 0 | 0 | 2306.6966 | 0 | 0 | 5233.318 | 7208.427 | 0 | 0 | 0 | 0 | 107161.7253 | 0 | 2955.0643 | 3089.3258 | 158.427 | 396.0674 | 0 | 68729.7424 | 0 | 0 | 52.809 | 1373.0337 | 3432.5843 | 6865.1685 | 6865.1685 | 1029.7753 | 0 | 0 | 0 | 0 | 1373.0337 | 0
2025-08-11 | 318807.0293 | 0 | 96480 | 107388.996 | 7790.9717 | 70192.0773 | 20386.5169 | 113048.4674 | 0 | 0 | 3054.0944 | 0 | 0 | 89884.0449 | 5048.0899 | 0 | 0 | 2355.7753 | 0 | 0 | 5344.6652 | 7361.7978 | 0 | 0 | 0 | 0 | 107388.996 | 0 | 3017.938 | 3155.0562 | 161.7978 | 404.4944 | 0 | 70192.0773 | 0 | 0 | 53.9326 | 1402.2472 | 3505.618 | 7011.236 | 7011.236 | 1051.6854 | 0 | 0 | 0 | 0 | 1402.2472 | 0
2025-08-12 | 323438.8424 | 0 | 96480 | 107616.2668 | 7953.2836 | 71654.4122 | 20811.236 | 115403.6438 | 0 | 0 | 3117.7213 | 0 | 0 | 91756.6292 | 5153.2584 | 0 | 0 | 2404.8539 | 0 | 0 | 5456.0124 | 7515.1685 | 0 | 0 | 0 | 0 | 107616.2668 | 0 | 3080.8117 | 3220.7865 | 165.1685 | 412.9213 | 0 | 71654.4122 | 0 | 0 | 55.0562 | 1431.4607 | 3578.6517 | 7157.3034 | 7157.3034 | 1073.5955 | 0 | 0 | 0 | 0 | 1431.4607 | 0
2025-08-13 | 328070.6555 | 0 | 96480 | 107843.5375 | 8115.5955 | 73116.7472 | 21235.9551 | 117758.8202 | 0 | 0 | 3181.3483 | 0 | 0 | 93629.2135 | 5258.427 | 0 | 0 | 2453.9326 | 0 | 0 | 5567.3596 | 7668.5393 | 0 | 0 | 0 | 0 | 107843.5375 | 0 | 3143.6854 | 3286.5169 | 168.5393 | 421.3483 | 0 | 73116.7472 | 0 | 0 | 56.1798 | 1460.6742 | 3651.6854 | 7303.3708 | 7303.3708 | 1095.5056 | 0 | 0 | 0 | 0 | 1460.6742 | 0
2025-08-14 | 332702.4686 | 0 | 96480 | 108070.8083 | 8277.9074 | 74579.0821 | 21660.6742 | 120113.9966 | 0 | 0 | 3244.9753 | 0 | 0 | 95501.7978 | 5363.5955 | 0 | 0 | 2503.0112 | 0 | 0 | 5678.7067 | 7821.9101 | 0 | 0 | 0 | 0 | 108070.8083 | 0 | 3206.5591 | 3352.2472 | 171.9101 | 429.7753 | 0 | 74579.0821 | 0 | 0 | 57.3034 | 1489.8876 | 3724.7191 | 7449.4382 | 7449.4382 | 1117.4157 | 0 | 0 | 0 | 0 | 1489.8876 | 0
2025-08-15 | 337334.2817 | 0 | 96480 | 108298.079 | 8440.2193 | 76041.4171 | 22085.3933 | 122469.173 | 0 | 0 | 3308.6022 | 0 | 0 | 97374.382 | 5468.764 | 0 | 0 | 2552.0899 | 0 | 0 | 5790.0539 | 7975.2809 | 0 | 0 | 0 | 0 | 108298.079 | 0 | 3269.4328 | 3417.9775 | 175.2809 | 438.2022 | 0 | 76041.4171 | 0 | 0 | 58.427 | 1519.1011 | 3797.7528 | 7595.5056 | 7595.5056 | 1139.3258 | 0 | 0 | 0 | 0 | 1519.1011 | 0
2025-08-16 | 341966.0948 | 0 | 96480 | 108525.3498 | 8602.5312 | 77503.752 | 22510.1124 | 124824.3494 | 0 | 0 | 3372.2292 | 0 | 0 | 99246.9663 | 5573.9326 | 0 | 0 | 2601.1685 | 0 | 0 | 5901.4011 | 8128.6517 | 0 | 0 | 0 | 0 | 108525.3498 | 0 | 3332.3065 | 3483.7079 | 178.6517 | 446.6292 | 0 | 77503.752 | 0 | 0 | 59.5506 | 1548.3146 | 3870.7865 | 7741.573 | 7741.573 | 1161.236 | 0 | 0 | 0 | 0 | 1548.3146 | 0
2025-08-17 | 346597.9079 | 0 | 96480 | 108752.6205 | 8764.8431 | 78966.087 | 22934.8315 | 127179.5258 | 0 | 0 | 3435.8562 | 0 | 0 | 101119.5506 | 5679.1011 | 0 | 0 | 2650.2472 | 0 | 0 | 6012.7483 | 8282.0225 | 0 | 0 | 0 | 0 | 108752.6205 | 0 | 3395.1802 | 3549.4382 | 182.0225 | 455.0562 | 0 | 78966.087 | 0 | 0 | 60.6742 | 1577.5281 | 3943.8202 | 7887.6404 | 7887.6404 | 1183.1461 | 0 | 0 | 0 | 0 | 1577.5281 | 0
2025-08-18 | 351229.721 | 0 | 96480 | 108979.8913 | 8927.1551 | 80428.4219 | 23359.5506 | 129534.7022 | 0 | 0 | 3499.4831 | 0 | 0 | 102992.1348 | 5784.2697 | 0 | 0 | 2699.3258 | 0 | 0 | 6124.0955 | 8435.3933 | 0 | 0 | 0 | 0 | 108979.8913 | 0 | 3458.0539 | 3615.1685 | 185.3933 | 463.4831 | 0 | 80428.4219 | 0 | 0 | 61.7978 | 1606.7416 | 4016.8539 | 8033.7079 | 8033.7079 | 1205.0562 | 0 | 0 | 0 | 0 | 1606.7416 | 0
2025-08-19 | 355861.5342 | 0 | 96480 | 109207.162 | 9089.467 | 81890.7569 | 23784.2697 | 131889.8787 | 0 | 0 | 3563.1101 | 0 | 0 | 104864.7191 | 5889.4382 | 0 | 0 | 2748.4045 | 0 | 0 | 6235.4427 | 8588.764 | 0 | 0 | 0 | 0 | 109207.162 | 0 | 3520.9276 | 3680.8989 | 188.764 | 471.9101 | 0 | 81890.7569 | 0 | 0 | 62.9213 | 1635.9551 | 4089.8876 | 8179.7753 | 8179.7753 | 1226.9663 | 0 | 0 | 0 | 0 | 1635.9551 | 0
2025-08-20 | 360493.3473 | 0 | 96480 | 109434.4328 | 9251.7789 | 83353.0918 | 24208.9888 | 134245.0551 | 0 | 0 | 3626.7371 | 0 | 0 | 106737.3034 | 5994.6067 | 0 | 0 | 2797.4831 | 0 | 0 | 6346.7899 | 8742.1348 | 0 | 0 | 0 | 0 | 109434.4328 | 0 | 3583.8013 | 3746.6292 | 192.1348 | 480.3371 | 0 | 83353.0918 | 0 | 0 | 64.0449 | 1665.1685 | 4162.9213 | 8325.8427 | 8325.8427 | 1248.8764 | 0 | 0 | 0 | 0 | 1665.1685 | 0
2025-08-21 | 365125.1604 | 0 | 96480 | 109661.7035 | 9414.0908 | 84815.4267 | 24633.7079 | 136600.2315 | 0 | 0 | 3690.364 | 0 | 0 | 108609.8876 | 6099.7753 | 0 | 0 | 2846.5618 | 0 | 0 | 6458.1371 | 8895.5056 | 0 | 0 | 0 | 0 | 109661.7035 | 0 | 3646.6751 | 3812.3596 | 195.5056 | 488.764 | 0 | 84815.4267 | 0 | 0 | 65.1685 | 1694.382 | 4235.9551 | 8471.9101 | 8471.9101 | 1270.7865 | 0 | 0 | 0 | 0 | 1694.382 | 0
2025-08-22 | 369756.9735 | 0 | 96480 | 109888.9743 | 9576.4027 | 86277.7617 | 25058.427 | 138955.4079 | 0 | 0 | 3753.991 | 0 | 0 | 110482.4719 | 6204.9438 | 0 | 0 | 2895.6404 | 0 | 0 | 6569.4843 | 9048.8764 | 0 | 0 | 0 | 0 | 109888.9743 | 0 | 3709.5488 | 3878.0899 | 198.8764 | 497.191 | 0 | 86277.7617 | 0 | 0 | 66.2921 | 1723.5955 | 4308.9888 | 8617.9775 | 8617.9775 | 1292.6966 | 0 | 0 | 0 | 0 | 1723.5955 | 0
2025-08-23 | 374388.7866 | 0 | 96480 | 110116.245 | 9738.7146 | 87740.0966 | 25483.1461 | 141310.5843 | 0 | 0 | 3817.618 | 0 | 0 | 112355.0562 | 6310.1124 | 0 | 0 | 2944.7191 | 0 | 0 | 6680.8315 | 9202.2472 | 0 | 0 | 0 | 0 | 110116.245 | 0 | 3772.4225 | 3943.8202 | 202.2472 | 505.618 | 0 | 87740.0966 | 0 | 0 | 67.4157 | 1752.809 | 4382.0225 | 8764.0449 | 8764.0449 | 1314.6067 | 0 | 0 | 0 | 0 | 1752.809 | 0
2025-08-24 | 379020.5997 | 0 | 96480 | 110343.5158 | 9901.0265 | 89202.4316 | 25907.8652 | 143665.7607 | 0 | 0 | 3881.2449 | 0 | 0 | 114227.6404 | 6415.2809 | 0 | 0 | 2993.7978 | 0 | 0 | 6792.1787 | 9355.618 | 0 | 0 | 0 | 0 | 110343.5158 | 0 | 3835.2962 | 4009.5506 | 205.618 | 514.0449 | 0 | 89202.4316 | 0 | 0 | 68.5393 | 1782.0225 | 4455.0562 | 8910.1124 | 8910.1124 | 1336.5169 | 0 | 0 | 0 | 0 | 1782.0225 | 0
2025-08-25 | 383652.4128 | 0 | 96480 | 110570.7865 | 10063.3384 | 90664.7665 | 26332.5843 | 146020.9371 | 0 | 0 | 3944.8719 | 0 | 0 | 116100.2247 | 6520.4494 | 0 | 0 | 3042.8764 | 0 | 0 | 6903.5258 | 9508.9888 | 0 | 0 | 0 | 0 | 110570.7865 | 0 | 3898.1699 | 4075.2809 | 208.9888 | 522.4719 | 0 | 90664.7665 | 0 | 0 | 69.6629 | 1811.236 | 4528.0899 | 9056.1798 | 9056.1798 | 1358.427 | 0 | 0 | 0 | 0 | 1811.236 | 0
2025-08-26 | 388284.2259 | 0 | 96480 | 110798.0573 | 10225.6503 | 92127.1015 | 26757.3034 | 148376.1135 | 0 | 0 | 4008.4989 | 0 | 0 | 117972.809 | 6625.618 | 0 | 0 | 3091.9551 | 0 | 0 | 7014.873 | 9662.3596 | 0 | 0 | 0 | 0 | 110798.0573 | 0 | 3961.0436 | 4141.0112 | 212.3596 | 530.8989 | 0 | 92127.1015 | 0 | 0 | 70.7865 | 1840.4494 | 4601.1236 | 9202.2472 | 9202.2472 | 1380.3371 | 0 | 0 | 0 | 0 | 1840.4494 | 0
2025-08-27 | 392916.039 | 0 | 96480 | 111025.328 | 10387.9622 | 93589.4364 | 27182.0225 | 150731.2899 | 0 | 0 | 4072.1258 | 0 | 0 | 119845.3933 | 6730.7865 | 0 | 0 | 3141.0337 | 0 | 0 | 7126.2202 | 9815.7303 | 0 | 0 | 0 | 0 | 111025.328 | 0 | 4023.9173 | 4206.7416 | 215.7303 | 539.3258 | 0 | 93589.4364 | 0 | 0 | 71.9101 | 1869.6629 | 4674.1573 | 9348.3146 | 9348.3146 | 1402.2472 | 0 | 0 | 0 | 0 | 1869.6629 | 0
2025-08-28 | 397547.8521 | 0 | 96480 | 111252.5988 | 10550.2742 | 95051.7713 | 27606.7416 | 153086.4663 | 0 | 0 | 4135.7528 | 0 | 0 | 121717.9775 | 6835.9551 | 0 | 0 | 3190.1124 | 0 | 0 | 7237.5674 | 9969.1011 | 0 | 0 | 0 | 0 | 111252.5988 | 0 | 4086.791 | 4272.4719 | 219.1011 | 547.7528 | 0 | 95051.7713 | 0 | 0 | 73.0337 | 1898.8764 | 4747.191 | 9494.382 | 9494.382 | 1424.1573 | 0 | 0 | 0 | 0 | 1898.8764 | 0
2025-08-29 | 402179.6652 | 0 | 96480 | 111479.8695 | 10712.5861 | 96514.1063 | 28031.4607 | 155441.6427 | 0 | 0 | 4199.3798 | 0 | 0 | 123590.5618 | 6941.1236 | 0 | 0 | 3239.191 | 0 | 0 | 7348.9146 | 10122.4719 | 0 | 0 | 0 | 0 | 111479.8695 | 0 | 4149.6647 | 4338.2022 | 222.4719 | 556.1798 | 0 | 96514.1063 | 0 | 0 | 74.1573 | 1928.0899 | 4820.2247 | 9640.4494 | 9640.4494 | 1446.0674 | 0 | 0 | 0 | 0 | 1928.0899 | 0
2025-08-30 | 406811.4784 | 0 | 96480 | 111707.1403 | 10874.898 | 97976.4412 | 28456.1798 | 157796.8191 | 0 | 0 | 4263.0067 | 0 | 0 | 125463.1461 | 7046.2921 | 0 | 0 | 3288.2697 | 0 | 0 | 7460.2618 | 10275.8427 | 0 | 0 | 0 | 0 | 111707.1403 | 0 | 4212.5384 | 4403.9326 | 225.8427 | 564.6067 | 0 | 97976.4412 | 0 | 0 | 75.2809 | 1957.3034 | 4893.2584 | 9786.5169 | 9786.5169 | 1467.9775 | 0 | 0 | 0 | 0 | 1957.3034 | 0
2025-08-31 | 411443.2915 | 0 | 96480 | 111934.411 | 11037.2099 | 99438.7762 | 28880.8989 | 160151.9955 | 0 | 0 | 4326.6337 | 0 | 0 | 127335.7303 | 7151.4607 | 0 | 0 | 3337.3483 | 0 | 0 | 7571.609 | 10429.2135 | 0 | 0 | 0 | 0 | 111934.411 | 0 | 4275.4121 | 4469.6629 | 229.2135 | 573.0337 | 0 | 99438.7762 | 0 | 0 | 76.4045 | 1986.5169 | 4966.2921 | 9932.5843 | 9932.5843 | 1489.8876 | 0 | 0 | 0 | 0 | 1986.5169 | 0
2025-09-01 | 416075.1046 | 0 | 96480 | 112161.6818 | 11199.5218 | 100901.1111 | 29305.618 | 162507.1719 | 0 | 0 | 4390.2607 | 0 | 0 | 129208.3146 | 7256.6292 | 0 | 0 | 3386.427 | 0 | 0 | 7682.9562 | 10582.5843 | 0 | 0 | 0 | 0 | 112161.6818 | 0 | 4338.2858 | 4535.3933 | 232.5843 | 581.4607 | 0 | 100901.1111 | 0 | 0 | 77.5281 | 2015.7303 | 5039.3258 | 10078.6517 | 10078.6517 | 1511.7978 | 0 | 0 | 0 | 0 | 2015.7303 | 0
2025-09-02 | 420706.9177 | 0 | 96480 | 112388.9525 | 11361.8337 | 102363.4461 | 29730.3371 | 164862.3483 | 0 | 0 | 4453.8876 | 0 | 0 | 131080.8989 | 7361.7978 | 0 | 0 | 3435.5056 | 0 | 0 | 7794.3034 | 10735.9551 | 0 | 0 | 0 | 0 | 112388.9525 | 0 | 4401.1596 | 4601.1236 | 235.9551 | 589.8876 | 0 | 102363.4461 | 0 | 0 | 78.6517 | 2044.9438 | 5112.3596 | 10224.7191 | 10224.7191 | 1533.7079 | 0 | 0 | 0 | 0 | 2044.9438 | 0
2025-09-03 | 425338.7308 | 0 | 96480 | 112616.2233 | 11524.1456 | 103825.781 | 30155.0562 | 167217.5247 | 0 | 0 | 4517.5146 | 0 | 0 | 132953.4831 | 7466.9663 | 0 | 0 | 3484.5843 | 0 | 0 | 7905.6506 | 10889.3258 | 0 | 0 | 0 | 0 | 112616.2233 | 0 | 4464.0333 | 4666.8539 | 239.3258 | 598.3146 | 0 | 103825.781 | 0 | 0 | 79.7753 | 2074.1573 | 5185.3933 | 10370.7865 | 10370.7865 | 1555.618 | 0 | 0 | 0 | 0 | 2074.1573 | 0
2025-09-04 | 429970.5439 | 0 | 96480 | 112843.494 | 11686.4575 | 105288.116 | 30579.7753 | 169572.7011 | 0 | 0 | 4581.1416 | 0 | 0 | 134826.0674 | 7572.1348 | 0 | 0 | 3533.6629 | 0 | 0 | 8016.9978 | 11042.6966 | 0 | 0 | 0 | 0 | 112843.494 | 0 | 4526.907 | 4732.5843 | 242.6966 | 606.7416 | 0 | 105288.116 | 0 | 0 | 80.8989 | 2103.3708 | 5258.427 | 10516.8539 | 10516.8539 | 1577.5281 | 0 | 0 | 0 | 0 | 2103.3708 | 0
2025-09-05 | 434602.357 | 0 | 96480 | 113070.7648 | 11848.7694 | 106750.4509 | 31004.4944 | 171927.8775 | 0 | 0 | 4644.7685 | 0 | 0 | 136698.6517 | 7677.3034 | 0 | 0 | 3582.7416 | 0 | 0 | 8128.3449 | 11196.0674 | 0 | 0 | 0 | 0 | 113070.7648 | 0 | 4589.7807 | 4798.3146 | 246.0674 | 615.1685 | 0 | 106750.4509 | 0 | 0 | 82.0225 | 2132.5843 | 5331.4607 | 10662.9213 | 10662.9213 | 1599.4382 | 0 | 0 | 0 | 0 | 2132.5843 | 0
2025-09-06 | 439234.1701 | 0 | 96480 | 113298.0355 | 12011.0813 | 108212.7858 | 31429.2135 | 174283.0539 | 0 | 0 | 4708.3955 | 0 | 0 | 138571.236 | 7782.4719 | 0 | 0 | 3631.8202 | 0 | 0 | 8239.6921 | 11349.4382 | 0 | 0 | 0 | 0 | 113298.0355 | 0 | 4652.6544 | 4864.0449 | 249.4382 | 623.5955 | 0 | 108212.7858 | 0 | 0 | 83.1461 | 2161.7978 | 5404.4944 | 10808.9888 | 10808.9888 | 1621.3483 | 0 | 0 | 0 | 0 | 2161.7978 | 0
2025-09-07 | 443865.9832 | 0 | 96480 | 113525.3063 | 12173.3933 | 109675.1208 | 31853.9326 | 176638.2303 | 0 | 0 | 4772.0225 | 0 | 0 | 140443.8202 | 7887.6404 | 0 | 0 | 3680.8989 | 0 | 0 | 8351.0393 | 11502.809 | 0 | 0 | 0 | 0 | 113525.3063 | 0 | 4715.5281 | 4929.7753 | 252.809 | 632.0225 | 0 | 109675.1208 | 0 | 0 | 84.2697 | 2191.0112 | 5477.5281 | 10955.0562 | 10955.0562 | 1643.2584 | 0 | 0 | 0 | 0 | 2191.0112 | 0
2025-09-08 | 448497.7963 | 0 | 96480 | 113752.577 | 12335.7052 | 111137.4557 | 32278.6517 | 178993.4067 | 0 | 0 | 4835.6494 | 0 | 0 | 142316.4045 | 7992.809 | 0 | 0 | 3729.9775 | 0 | 0 | 8462.3865 | 11656.1798 | 0 | 0 | 0 | 0 | 113752.577 | 0 | 4778.4018 | 4995.5056 | 256.1798 | 640.4494 | 0 | 111137.4557 | 0 | 0 | 85.3933 | 2220.2247 | 5550.5618 | 11101.1236 | 11101.1236 | 1665.1685 | 0 | 0 | 0 | 0 | 2220.2247 | 0
2025-09-09 | 453129.6095 | 0 | 96480 | 113979.8478 | 12498.0171 | 112599.7907 | 32703.3708 | 181348.5831 | 0 | 0 | 4899.2764 | 0 | 0 | 144188.9888 | 8097.9775 | 0 | 0 | 3779.0562 | 0 | 0 | 8573.7337 | 11809.5506 | 0 | 0 | 0 | 0 | 113979.8478 | 0 | 4841.2755 | 5061.236 | 259.5506 | 648.8764 | 0 | 112599.7907 | 0 | 0 | 86.5169 | 2249.4382 | 5623.5955 | 11247.191 | 11247.191 | 1687.0787 | 0 | 0 | 0 | 0 | 2249.4382 | 0
2025-09-10 | 457761.4226 | 0 | 96480 | 114207.1185 | 12660.329 | 114062.1256 | 33128.0899 | 183703.7596 | 0 | 0 | 4962.9034 | 0 | 0 | 146061.573 | 8203.1461 | 0 | 0 | 3828.1348 | 0 | 0 | 8685.0809 | 11962.9213 | 0 | 0 | 0 | 0 | 114207.1185 | 0 | 4904.1492 | 5126.9663 | 262.9213 | 657.3034 | 0 | 114062.1256 | 0 | 0 | 87.6404 | 2278.6517 | 5696.6292 | 11393.2584 | 11393.2584 | 1708.9888 | 0 | 0 | 0 | 0 | 2278.6517 | 0
2025-09-11 | 462393.2357 | 0 | 96480 | 114434.3893 | 12822.6409 | 115524.4606 | 33552.809 | 186058.936 | 0 | 0 | 5026.5303 | 0 | 0 | 147934.1573 | 8308.3146 | 0 | 0 | 3877.2135 | 0 | 0 | 8796.4281 | 12116.2921 | 0 | 0 | 0 | 0 | 114434.3893 | 0 | 4967.0229 | 5192.6966 | 266.2921 | 665.7303 | 0 | 115524.4606 | 0 | 0 | 88.764 | 2307.8652 | 5769.6629 | 11539.3258 | 11539.3258 | 1730.8989 | 0 | 0 | 0 | 0 | 2307.8652 | 0
2025-09-12 | 467025.0488 | 0 | 96480 | 114661.66 | 12984.9528 | 116986.7955 | 33977.5281 | 188414.1124 | 0 | 0 | 5090.1573 | 0 | 0 | 149806.7416 | 8413.4831 | 0 | 0 | 3926.2921 | 0 | 0 | 8907.7753 | 12269.6629 | 0 | 0 | 0 | 0 | 114661.66 | 0 | 5029.8966 | 5258.427 | 269.6629 | 674.1573 | 0 | 116986.7955 | 0 | 0 | 89.8876 | 2337.0787 | 5842.6966 | 11685.3933 | 11685.3933 | 1752.809 | 0 | 0 | 0 | 0 | 2337.0787 | 0
2025-09-13 | 471656.8619 | 0 | 96480 | 114888.9308 | 13147.2647 | 118449.1304 | 34402.2472 | 190769.2888 | 0 | 0 | 5153.7843 | 0 | 0 | 151679.3258 | 8518.6517 | 0 | 0 | 3975.3708 | 0 | 0 | 9019.1225 | 12423.0337 | 0 | 0 | 0 | 0 | 114888.9308 | 0 | 5092.7703 | 5324.1573 | 273.0337 | 682.5843 | 0 | 118449.1304 | 0 | 0 | 91.0112 | 2366.2921 | 5915.7303 | 11831.4607 | 11831.4607 | 1774.7191 | 0 | 0 | 0 | 0 | 2366.2921 | 0
2025-09-14 | 476288.675 | 0 | 96480 | 115116.2015 | 13309.5766 | 119911.4654 | 34826.9663 | 193124.4652 | 0 | 0 | 5217.4112 | 0 | 0 | 153551.9101 | 8623.8202 | 0 | 0 | 4024.4494 | 0 | 0 | 9130.4697 | 12576.4045 | 0 | 0 | 0 | 0 | 115116.2015 | 0 | 5155.644 | 5389.8876 | 276.4045 | 691.0112 | 0 | 119911.4654 | 0 | 0 | 92.1348 | 2395.5056 | 5988.764 | 11977.5281 | 11977.5281 | 1796.6292 | 0 | 0 | 0 | 0 | 2395.5056 | 0
2025-09-15 | 480920.4881 | 0 | 96480 | 115343.4723 | 13471.8885 | 121373.8003 | 35251.6854 | 195479.6416 | 0 | 0 | 5281.0382 | 0 | 0 | 155424.4944 | 8728.9888 | 0 | 0 | 4073.5281 | 0 | 0 | 9241.8169 | 12729.7753 | 0 | 0 | 0 | 0 | 115343.4723 | 0 | 5218.5178 | 5455.618 | 279.7753 | 699.4382 | 0 | 121373.8003 | 0 | 0 | 93.2584 | 2424.7191 | 6061.7978 | 12123.5955 | 12123.5955 | 1818.5393 | 0 | 0 | 0 | 0 | 2424.7191 | 0
2025-09-16 | 485552.3012 | 0 | 96480 | 115570.743 | 13634.2004 | 122836.1353 | 35676.4045 | 197834.818 | 0 | 0 | 5344.6652 | 0 | 0 | 157297.0787 | 8834.1573 | 0 | 0 | 4122.6067 | 0 | 0 | 9353.164 | 12883.1461 | 0 | 0 | 0 | 0 | 115570.743 | 0 | 5281.3915 | 5521.3483 | 283.1461 | 707.8652 | 0 | 122836.1353 | 0 | 0 | 94.382 | 2453.9326 | 6134.8315 | 12269.6629 | 12269.6629 | 1840.4494 | 0 | 0 | 0 | 0 | 2453.9326 | 0
2025-09-17 | 490184.1143 | 0 | 96480 | 115798.0138 | 13796.5124 | 124298.4702 | 36101.1236 | 200189.9944 | 0 | 0 | 5408.2921 | 0 | 0 | 159169.6629 | 8939.3258 | 0 | 0 | 4171.6854 | 0 | 0 | 9464.5112 | 13036.5169 | 0 | 0 | 0 | 0 | 115798.0138 | 0 | 5344.2652 | 5587.0787 | 286.5169 | 716.2921 | 0 | 124298.4702 | 0 | 0 | 95.5056 | 2483.1461 | 6207.8652 | 12415.7303 | 12415.7303 | 1862.3596 | 0 | 0 | 0 | 0 | 2483.1461 | 0
2025-09-18 | 494815.9274 | 0 | 96480 | 116025.2845 | 13958.8243 | 125760.8052 | 36525.8427 | 202545.1708 | 0 | 0 | 5471.9191 | 0 | 0 | 161042.2472 | 9044.4944 | 0 | 0 | 4220.764 | 0 | 0 | 9575.8584 | 13189.8876 | 0 | 0 | 0 | 0 | 116025.2845 | 0 | 5407.1389 | 5652.809 | 289.8876 | 724.7191 | 0 | 125760.8052 | 0 | 0 | 96.6292 | 2512.3596 | 6280.8989 | 12561.7978 | 12561.7978 | 1884.2697 | 0 | 0 | 0 | 0 | 2512.3596 | 0
2025-09-19 | 499447.7406 | 0 | 96480 | 116252.5553 | 14121.1362 | 127223.1401 | 36950.5618 | 204900.3472 | 0 | 0 | 5535.5461 | 0 | 0 | 162914.8315 | 9149.6629 | 0 | 0 | 4269.8427 | 0 | 0 | 9687.2056 | 13343.2584 | 0 | 0 | 0 | 0 | 116252.5553 | 0 | 5470.0126 | 5718.5393 | 293.2584 | 733.1461 | 0 | 127223.1401 | 0 | 0 | 97.7528 | 2541.573 | 6353.9326 | 12707.8652 | 12707.8652 | 1906.1798 | 0 | 0 | 0 | 0 | 2541.573 | 0
2025-09-20 | 504079.5537 | 0 | 96480 | 116479.826 | 14283.4481 | 128685.4751 | 37375.2809 | 207255.5236 | 0 | 0 | 5599.173 | 0 | 0 | 164787.4157 | 9254.8315 | 0 | 0 | 4318.9213 | 0 | 0 | 9798.5528 | 13496.6292 | 0 | 0 | 0 | 0 | 116479.826 | 0 | 5532.8863 | 5784.2697 | 296.6292 | 741.573 | 0 | 128685.4751 | 0 | 0 | 98.8764 | 2570.7865 | 6426.9663 | 12853.9326 | 12853.9326 | 1928.0899 | 0 | 0 | 0 | 0 | 2570.7865 | 0
2025-09-21 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-22 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-23 | 515850.1466 | 0 | 96480 | 121148.6247 | 15629.6542 | 131133.2446 | 38055.8077 | 209882.8154 | 272.1154 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 546.6846 | 121148.6247 | 0 | 5635.76 | 6379.6154 | 360 | 900 | 0 | 130586.56 | 0 | 0 | 100 | 2792.3462 | 6500 | 13020.1923 | 13043.2692 | 2267.3077 | 86.9712 | 0 | 0 | 0 | 2600 | 0
2025-09-24 | 522988.9265 | 0 | 96480 | 125590.1526 | 16813.5485 | 132118.6792 | 38311.6154 | 210154.9308 | 544.2308 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 1093.3692 | 125590.1526 | 0 | 5675.76 | 6909.2308 | 420 | 1050 | 0 | 131025.31 | 0 | 0 | 100 | 2984.6923 | 6500 | 13040.3846 | 13086.5385 | 2584.6154 | 173.9423 | 0 | 0 | 0 | 2600 | 0
2025-09-25 | 530127.7063 | 0 | 96480 | 130031.6805 | 17997.4427 | 133104.1138 | 38567.4231 | 210427.0462 | 816.3462 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 1640.0538 | 130031.6805 | 0 | 5715.76 | 7438.8462 | 480 | 1200 | 0 | 131464.06 | 0 | 0 | 100 | 3177.0385 | 6500 | 13060.5769 | 13129.8077 | 2901.9231 | 260.9135 | 0 | 0 | 0 | 2600 | 0
2025-09-26 | 537266.4861 | 0 | 96480 | 134473.2084 | 19181.3369 | 134089.5485 | 38823.2308 | 210699.1615 | 1088.4615 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 2186.7385 | 134473.2084 | 0 | 5755.76 | 7968.4615 | 540 | 1350 | 0 | 131902.81 | 0 | 0 | 100 | 3369.3846 | 6500 | 13080.7692 | 13173.0769 | 3219.2308 | 347.8846 | 0 | 0 | 0 | 2600 | 0
2025-09-27 | 544405.266 | 0 | 96480 | 138914.7364 | 20365.2312 | 135074.9831 | 39079.0385 | 210971.2769 | 1360.5769 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 2733.4231 | 138914.7364 | 0 | 5795.76 | 8498.0769 | 600 | 1500 | 0 | 132341.56 | 0 | 0 | 100 | 3561.7308 | 6500 | 13100.9615 | 13216.3462 | 3536.5385 | 434.8558 | 0 | 0 | 0 | 2600 | 0
2025-09-28 | 551544.0458 | 0 | 96480 | 143356.2643 | 21549.1254 | 136060.4177 | 39334.8462 | 211243.3923 | 1632.6923 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 3280.1077 | 143356.2643 | 0 | 5835.76 | 9027.6923 | 660 | 1650 | 0 | 132780.31 | 0 | 0 | 100 | 3754.0769 | 6500 | 13121.1538 | 13259.6154 | 3853.8462 | 521.8269 | 0 | 0 | 0 | 2600 | 0
2025-09-29 | 558682.8256 | 0 | 96480 | 147797.7922 | 22733.0196 | 137045.8523 | 39590.6538 | 211515.5077 | 1904.8077 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 3826.7923 | 147797.7922 | 0 | 5875.76 | 9557.3077 | 720 | 1800 | 0 | 133219.06 | 0 | 0 | 100 | 3946.4231 | 6500 | 13141.3462 | 13302.8846 | 4171.1538 | 608.7981 | 0 | 0 | 0 | 2600 | 0
2025-09-30 | 565821.6055 | 358685.61 | 455165.61 | 152239.3201 | 23916.9138 | 138031.2869 | 39846.4615 | 211787.6231 | 2176.9231 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 4373.4769 | 152239.3201 | 0 | 5915.76 | 10086.9231 | 780 | 1950 | 0 | 133657.81 | 0 | 0 | 100 | 4138.7692 | 6500 | 13161.5385 | 13346.1538 | 4488.4615 | 695.7692 | 0 | 0 | 0 | 2600 | 0
2025-10-01 | 572960.3853 | 0 | 455165.61 | 156680.848 | 25100.8081 | 139016.7215 | 40102.2692 | 212059.7385 | 2449.0385 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 4920.1615 | 156680.848 | 0 | 5955.76 | 10616.5385 | 840 | 2100 | 0 | 134096.56 | 0 | 0 | 100 | 4331.1154 | 6500 | 13181.7308 | 13389.4231 | 4805.7692 | 782.7404 | 0 | 0 | 0 | 2600 | 0
2025-10-02 | 580099.1652 | 0 | 455165.61 | 161122.3759 | 26284.7023 | 140002.1562 | 40358.0769 | 212331.8538 | 2721.1538 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 5466.8462 | 161122.3759 | 0 | 5995.76 | 11146.1538 | 900 | 2250 | 0 | 134535.31 | 0 | 0 | 100 | 4523.4615 | 6500 | 13201.9231 | 13432.6923 | 5123.0769 | 869.7115 | 0 | 0 | 0 | 2600 | 0
2025-10-03 | 587237.945 | 0 | 455165.61 | 165563.9038 | 27468.5965 | 140987.5908 | 40613.8846 | 212603.9692 | 2993.2692 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 6013.5308 | 165563.9038 | 0 | 6035.76 | 11675.7692 | 960 | 2400 | 0 | 134974.06 | 0 | 0 | 100 | 4715.8077 | 6500 | 13222.1154 | 13475.9615 | 5440.3846 | 956.6827 | 0 | 0 | 0 | 2600 | 0
2025-10-04 | 594376.7248 | 0 | 455165.61 | 170005.4318 | 28652.4908 | 141973.0254 | 40869.6923 | 212876.0846 | 3265.3846 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 6560.2154 | 170005.4318 | 0 | 6075.76 | 12205.3846 | 1020 | 2550 | 0 | 135412.81 | 0 | 0 | 100 | 4908.1538 | 6500 | 13242.3077 | 13519.2308 | 5757.6923 | 1043.6538 | 0 | 0 | 0 | 2600 | 0
2025-10-05 | 601515.5047 | 0 | 455165.61 | 174446.9597 | 29836.385 | 142958.46 | 41125.5 | 213148.2 | 3537.5 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 7106.9 | 174446.9597 | 0 | 6115.76 | 12735 | 1080 | 2700 | 0 | 135851.56 | 0 | 0 | 100 | 5100.5 | 6500 | 13262.5 | 13562.5 | 6075 | 1130.625 | 0 | 0 | 0 | 2600 | 0
2025-10-06 | 608654.2845 | 0 | 455165.61 | 178888.4876 | 31020.2792 | 143943.8946 | 41381.3077 | 213420.3154 | 3809.6154 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 7653.5846 | 178888.4876 | 0 | 6155.76 | 13264.6154 | 1140 | 2850 | 0 | 136290.31 | 0 | 0 | 100 | 5292.8462 | 6500 | 13282.6923 | 13605.7692 | 6392.3077 | 1217.5962 | 0 | 0 | 0 | 2600 | 0
2025-10-07 | 615793.0644 | 0 | 455165.61 | 183330.0155 | 32204.1735 | 144929.3292 | 41637.1154 | 213692.4308 | 4081.7308 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 8200.2692 | 183330.0155 | 0 | 6195.76 | 13794.2308 | 1200 | 3000 | 0 | 136729.06 | 0 | 0 | 100 | 5485.1923 | 6500 | 13302.8846 | 13649.0385 | 6709.6154 | 1304.5673 | 0 | 0 | 0 | 2600 | 0
2025-10-08 | 622931.8442 | 0 | 455165.61 | 187771.5434 | 33388.0677 | 145914.7638 | 41892.9231 | 213964.5462 | 4353.8462 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 8746.9538 | 187771.5434 | 0 | 6235.76 | 14323.8462 | 1260 | 3150 | 0 | 137167.81 | 0 | 0 | 100 | 5677.5385 | 6500 | 13323.0769 | 13692.3077 | 7026.9231 | 1391.5385 | 0 | 0 | 0 | 2600 | 0
2025-10-09 | 630070.624 | 0 | 455165.61 | 192213.0713 | 34571.9619 | 146900.1985 | 42148.7308 | 214236.6615 | 4625.9615 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 9293.6385 | 192213.0713 | 0 | 6275.76 | 14853.4615 | 1320 | 3300 | 0 | 137606.56 | 0 | 0 | 100 | 5869.8846 | 6500 | 13343.2692 | 13735.5769 | 7344.2308 | 1478.5096 | 0 | 0 | 0 | 2600 | 0
2025-10-10 | 637209.4039 | 0 | 455165.61 | 196654.5993 | 35755.8562 | 147885.6331 | 42404.5385 | 214508.7769 | 4898.0769 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 9840.3231 | 196654.5993 | 0 | 6315.76 | 15383.0769 | 1380 | 3450 | 0 | 138045.31 | 0 | 0 | 100 | 6062.2308 | 6500 | 13363.4615 | 13778.8462 | 7661.5385 | 1565.4808 | 0 | 0 | 0 | 2600 | 0
2025-10-11 | 644348.1837 | 0 | 455165.61 | 201096.1272 | 36939.7504 | 148871.0677 | 42660.3462 | 214780.8923 | 5170.1923 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 10387.0077 | 201096.1272 | 0 | 6355.76 | 15912.6923 | 1440 | 3600 | 0 | 138484.06 | 0 | 0 | 100 | 6254.5769 | 6500 | 13383.6538 | 13822.1154 | 7978.8462 | 1652.4519 | 0 | 0 | 0 | 2600 | 0
2025-10-12 | 651486.9635 | 0 | 455165.61 | 205537.6551 | 38123.6446 | 149856.5023 | 42916.1538 | 215053.0077 | 5442.3077 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 10933.6923 | 205537.6551 | 0 | 6395.76 | 16442.3077 | 1500 | 3750 | 0 | 138922.81 | 0 | 0 | 100 | 6446.9231 | 6500 | 13403.8462 | 13865.3846 | 8296.1538 | 1739.4231 | 0 | 0 | 0 | 2600 | 0
2025-10-13 | 658625.7434 | 0 | 455165.61 | 209979.183 | 39307.5388 | 150841.9369 | 43171.9615 | 215325.1231 | 5714.4231 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 11480.3769 | 209979.183 | 0 | 6435.76 | 16971.9231 | 1560 | 3900 | 0 | 139361.56 | 0 | 0 | 100 | 6639.2692 | 6500 | 13424.0385 | 13908.6538 | 8613.4615 | 1826.3942 | 0 | 0 | 0 | 2600 | 0
2025-10-14 | 665764.5232 | 0 | 455165.61 | 214420.7109 | 40491.4331 | 151827.3715 | 43427.7692 | 215597.2385 | 5986.5385 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 12027.0615 | 214420.7109 | 0 | 6475.76 | 17501.5385 | 1620 | 4050 | 0 | 139800.31 | 0 | 0 | 100 | 6831.6154 | 6500 | 13444.2308 | 13951.9231 | 8930.7692 | 1913.3654 | 0 | 0 | 0 | 2600 | 0
2025-10-15 | 672903.3031 | 0 | 455165.61 | 218862.2388 | 41675.3273 | 152812.8062 | 43683.5769 | 215869.3538 | 6258.6538 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 12573.7462 | 218862.2388 | 0 | 6515.76 | 18031.1538 | 1680 | 4200 | 0 | 140239.06 | 0 | 0 | 100 | 7023.9615 | 6500 | 13464.4231 | 13995.1923 | 9248.0769 | 2000.3365 | 0 | 0 | 0 | 2600 | 0
2025-10-16 | 680042.0829 | 0 | 455165.61 | 223303.7667 | 42859.2215 | 153798.2408 | 43939.3846 | 216141.4692 | 6530.7692 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 13120.4308 | 223303.7667 | 0 | 6555.76 | 18560.7692 | 1740 | 4350 | 0 | 140677.81 | 0 | 0 | 100 | 7216.3077 | 6500 | 13484.6154 | 14038.4615 | 9565.3846 | 2087.3077 | 0 | 0 | 0 | 2600 | 0
2025-10-17 | 687180.8627 | 0 | 455165.61 | 227745.2947 | 44043.1158 | 154783.6754 | 44195.1923 | 216413.5846 | 6802.8846 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 13667.1154 | 227745.2947 | 0 | 6595.76 | 19090.3846 | 1800 | 4500 | 0 | 141116.56 | 0 | 0 | 100 | 7408.6538 | 6500 | 13504.8077 | 14081.7308 | 9882.6923 | 2174.2788 | 0 | 0 | 0 | 2600 | 0
2025-10-18 | 694319.6426 | 0 | 455165.61 | 232186.8226 | 45227.01 | 155769.11 | 44451 | 216685.7 | 7075 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 14213.8 | 232186.8226 | 0 | 6635.76 | 19620 | 1860 | 4650 | 0 | 141555.31 | 0 | 0 | 100 | 7601 | 6500 | 13525 | 14125 | 10200 | 2261.25 | 0 | 0 | 0 | 2600 | 0
2025-10-19 | 701458.4224 | 0 | 455165.61 | 236628.3505 | 46410.9042 | 156754.5446 | 44706.8077 | 216957.8154 | 7347.1154 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 14760.4846 | 236628.3505 | 0 | 6675.76 | 20149.6154 | 1920 | 4800 | 0 | 141994.06 | 0 | 0 | 100 | 7793.3462 | 6500 | 13545.1923 | 14168.2692 | 10517.3077 | 2348.2212 | 0 | 0 | 0 | 2600 | 0
2025-10-20 | 708597.2023 | 0 | 455165.61 | 241069.8784 | 47594.7985 | 157739.9792 | 44962.6154 | 217229.9308 | 7619.2308 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 15307.1692 | 241069.8784 | 0 | 6715.76 | 20679.2308 | 1980 | 4950 | 0 | 142432.81 | 0 | 0 | 100 | 7985.6923 | 6500 | 13565.3846 | 14211.5385 | 10834.6154 | 2435.1923 | 0 | 0 | 0 | 2600 | 0
2025-10-21 | 715735.9821 | 0 | 455165.61 | 245511.4063 | 48778.6927 | 158725.4138 | 45218.4231 | 217502.0462 | 7891.3462 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 15853.8538 | 245511.4063 | 0 | 6755.76 | 21208.8462 | 2040 | 5100 | 0 | 142871.56 | 0 | 0 | 100 | 8178.0385 | 6500 | 13585.5769 | 14254.8077 | 11151.9231 | 2522.1635 | 0 | 0 | 0 | 2600 | 0
2025-10-22 | 722874.7619 | 0 | 455165.61 | 249952.9342 | 49962.5869 | 159710.8485 | 45474.2308 | 217774.1615 | 8163.4615 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 16400.5385 | 249952.9342 | 0 | 6795.76 | 21738.4615 | 2100 | 5250 | 0 | 143310.31 | 0 | 0 | 100 | 8370.3846 | 6500 | 13605.7692 | 14298.0769 | 11469.2308 | 2609.1346 | 0 | 0 | 0 | 2600 | 0
2025-10-23 | 730013.5418 | 0 | 455165.61 | 254394.4622 | 51146.4812 | 160696.2831 | 45730.0385 | 218046.2769 | 8435.5769 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 16947.2231 | 254394.4622 | 0 | 6835.76 | 22268.0769 | 2160 | 5400 | 0 | 143749.06 | 0 | 0 | 100 | 8562.7308 | 6500 | 13625.9615 | 14341.3462 | 11786.5385 | 2696.1058 | 0 | 0 | 0 | 2600 | 0
2025-10-24 | 737152.3216 | 0 | 455165.61 | 258835.9901 | 52330.3754 | 161681.7177 | 45985.8462 | 218318.3923 | 8707.6923 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 17493.9077 | 258835.9901 | 0 | 6875.76 | 22797.6923 | 2220 | 5550 | 0 | 144187.81 | 0 | 0 | 100 | 8755.0769 | 6500 | 13646.1538 | 14384.6154 | 12103.8462 | 2783.0769 | 0 | 0 | 0 | 2600 | 0
2025-10-25 | 744291.1015 | 0 | 455165.61 | 263277.518 | 53514.2696 | 162667.1523 | 46241.6538 | 218590.5077 | 8979.8077 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 18040.5923 | 263277.518 | 0 | 6915.76 | 23327.3077 | 2280 | 5700 | 0 | 144626.56 | 0 | 0 | 100 | 8947.4231 | 6500 | 13666.3462 | 14427.8846 | 12421.1538 | 2870.0481 | 0 | 0 | 0 | 2600 | 0
2025-10-26 | 751429.8813 | 0 | 455165.61 | 267719.0459 | 54698.1638 | 163652.5869 | 46497.4615 | 218862.6231 | 9251.9231 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 18587.2769 | 267719.0459 | 0 | 6955.76 | 23856.9231 | 2340 | 5850 | 0 | 145065.31 | 0 | 0 | 100 | 9139.7692 | 6500 | 13686.5385 | 14471.1538 | 12738.4615 | 2957.0192 | 0 | 0 | 0 | 2600 | 0
2025-10-27 | 758568.6611 | 0 | 455165.61 | 272160.5738 | 55882.0581 | 164638.0215 | 46753.2692 | 219134.7385 | 9524.0385 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 19133.9615 | 272160.5738 | 0 | 6995.76 | 24386.5385 | 2400 | 6000 | 0 | 145504.06 | 0 | 0 | 100 | 9332.1154 | 6500 | 13706.7308 | 14514.4231 | 13055.7692 | 3043.9904 | 0 | 0 | 0 | 2600 | 0
2025-10-28 | 765707.441 | 321563.64 | 776729.25 | 276602.1017 | 57065.9523 | 165623.4562 | 47009.0769 | 219406.8538 | 9796.1538 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 19680.6462 | 276602.1017 | 0 | 7035.76 | 24916.1538 | 2460 | 6150 | 0 | 145942.81 | 0 | 0 | 100 | 9524.4615 | 6500 | 13726.9231 | 14557.6923 | 13373.0769 | 3130.9615 | 0 | 0 | 0 | 2600 | 0
2025-10-29 | 772846.2208 | 0 | 776729.25 | 281043.6297 | 58249.8465 | 166608.8908 | 47264.8846 | 219678.9692 | 10068.2692 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 20227.3308 | 281043.6297 | 0 | 7075.76 | 25445.7692 | 2520 | 6300 | 0 | 146381.56 | 0 | 0 | 100 | 9716.8077 | 6500 | 13747.1154 | 14600.9615 | 13690.3846 | 3217.9327 | 0 | 0 | 0 | 2600 | 0
2025-10-30 | 779985.0006 | 0 | 776729.25 | 285485.1576 | 59433.7408 | 167594.3254 | 47520.6923 | 219951.0846 | 10340.3846 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 20774.0154 | 285485.1576 | 0 | 7115.76 | 25975.3846 | 2580 | 6450 | 0 | 146820.31 | 0 | 0 | 100 | 9909.1538 | 6500 | 13767.3077 | 14644.2308 | 14007.6923 | 3304.9038 | 0 | 0 | 0 | 2600 | 0
2025-10-31 | 787123.7805 | 0 | 776729.25 | 289926.6855 | 60617.635 | 168579.76 | 47776.5 | 220223.2 | 10612.5 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 21320.7 | 289926.6855 | 0 | 7155.76 | 26505 | 2640 | 6600 | 0 | 147259.06 | 0 | 0 | 100 | 10101.5 | 6500 | 13787.5 | 14687.5 | 14325 | 3391.875 | 0 | 0 | 0 | 2600 | 0
2025-11-01 | 794262.5603 | 0 | 776729.25 | 294368.2134 | 61801.5292 | 169565.1946 | 48032.3077 | 220495.3154 | 10884.6154 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 21867.3846 | 294368.2134 | 0 | 7195.76 | 27034.6154 | 2700 | 6750 | 0 | 147697.81 | 0 | 0 | 100 | 10293.8462 | 6500 | 13807.6923 | 14730.7692 | 14642.3077 | 3478.8462 | 0 | 0 | 0 | 2600 | 0
2025-11-02 | 801401.3402 | 0 | 776729.25 | 298809.7413 | 62985.4235 | 170550.6292 | 48288.1154 | 220767.4308 | 11156.7308 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 22414.0692 | 298809.7413 | 0 | 7235.76 | 27564.2308 | 2760 | 6900 | 0 | 148136.56 | 0 | 0 | 100 | 10486.1923 | 6500 | 13827.8846 | 14774.0385 | 14959.6154 | 3565.8173 | 0 | 0 | 0 | 2600 | 0
2025-11-03 | 808540.12 | 0 | 776729.25 | 303251.2692 | 64169.3177 | 171536.0638 | 48543.9231 | 221039.5462 | 11428.8462 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 22960.7538 | 303251.2692 | 0 | 7275.76 | 28093.8462 | 2820 | 7050 | 0 | 148575.31 | 0 | 0 | 100 | 10678.5385 | 6500 | 13848.0769 | 14817.3077 | 15276.9231 | 3652.7885 | 0 | 0 | 0 | 2600 | 0
2025-11-04 | 815678.8998 | 0 | 776729.25 | 307692.7971 | 65353.2119 | 172521.4985 | 48799.7308 | 221311.6615 | 11700.9615 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 23507.4385 | 307692.7971 | 0 | 7315.76 | 28623.4615 | 2880 | 7200 | 0 | 149014.06 | 0 | 0 | 100 | 10870.8846 | 6500 | 13868.2692 | 14860.5769 | 15594.2308 | 3739.7596 | 0 | 0 | 0 | 2600 | 0
2025-11-05 | 822817.6797 | 0 | 776729.25 | 312134.3251 | 66537.1062 | 173506.9331 | 49055.5385 | 221583.7769 | 11973.0769 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 24054.1231 | 312134.3251 | 0 | 7355.76 | 29153.0769 | 2940 | 7350 | 0 | 149452.81 | 0 | 0 | 100 | 11063.2308 | 6500 | 13888.4615 | 14903.8462 | 15911.5385 | 3826.7308 | 0 | 0 | 0 | 2600 | 0
2025-11-06 | 829956.4595 | 0 | 776729.25 | 316575.853 | 67721.0004 | 174492.3677 | 49311.3462 | 221855.8923 | 12245.1923 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 24600.8077 | 316575.853 | 0 | 7395.76 | 29682.6923 | 3000 | 7500 | 0 | 149891.56 | 0 | 0 | 100 | 11255.5769 | 6500 | 13908.6538 | 14947.1154 | 16228.8462 | 3913.7019 | 0 | 0 | 0 | 2600 | 0
2025-11-07 | 837095.2394 | 0 | 776729.25 | 321017.3809 | 68904.8946 | 175477.8023 | 49567.1538 | 222128.0077 | 12517.3077 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 25147.4923 | 321017.3809 | 0 | 7435.76 | 30212.3077 | 3060 | 7650 | 0 | 150330.31 | 0 | 0 | 100 | 11447.9231 | 6500 | 13928.8462 | 14990.3846 | 16546.1538 | 4000.6731 | 0 | 0 | 0 | 2600 | 0
2025-11-08 | 844234.0192 | 0 | 776729.25 | 325458.9088 | 70088.7888 | 176463.2369 | 49822.9615 | 222400.1231 | 12789.4231 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 25694.1769 | 325458.9088 | 0 | 7475.76 | 30741.9231 | 3120 | 7800 | 0 | 150769.06 | 0 | 0 | 100 | 11640.2692 | 6500 | 13949.0385 | 15033.6538 | 16863.4615 | 4087.6442 | 0 | 0 | 0 | 2600 | 0
2025-11-09 | 851372.799 | 0 | 776729.25 | 329900.4367 | 71272.6831 | 177448.6715 | 50078.7692 | 222672.2385 | 13061.5385 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 26240.8615 | 329900.4367 | 0 | 7515.76 | 31271.5385 | 3180 | 7950 | 0 | 151207.81 | 0 | 0 | 100 | 11832.6154 | 6500 | 13969.2308 | 15076.9231 | 17180.7692 | 4174.6154 | 0 | 0 | 0 | 2600 | 0
2025-11-10 | 858511.5789 | 0 | 776729.25 | 334341.9646 | 72456.5773 | 178434.1062 | 50334.5769 | 222944.3538 | 13333.6538 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 26787.5462 | 334341.9646 | 0 | 7555.76 | 31801.1538 | 3240 | 8100 | 0 | 151646.56 | 0 | 0 | 100 | 12024.9615 | 6500 | 13989.4231 | 15120.1923 | 17498.0769 | 4261.5865 | 0 | 0 | 0 | 2600 | 0
2025-11-11 | 865650.3587 | 0 | 776729.25 | 338783.4926 | 73640.4715 | 179419.5408 | 50590.3846 | 223216.4692 | 13605.7692 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 27334.2308 | 338783.4926 | 0 | 7595.76 | 32330.7692 | 3300 | 8250 | 0 | 152085.31 | 0 | 0 | 100 | 12217.3077 | 6500 | 14009.6154 | 15163.4615 | 17815.3846 | 4348.5577 | 0 | 0 | 0 | 2600 | 0
2025-11-12 | 872789.1385 | 0 | 776729.25 | 343225.0205 | 74824.3658 | 180404.9754 | 50846.1923 | 223488.5846 | 13877.8846 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 27880.9154 | 343225.0205 | 0 | 7635.76 | 32860.3846 | 3360 | 8400 | 0 | 152524.06 | 0 | 0 | 100 | 12409.6538 | 6500 | 14029.8077 | 15206.7308 | 18132.6923 | 4435.5288 | 0 | 0 | 0 | 2600 | 0
2025-11-13 | 879927.9184 | 0 | 776729.25 | 347666.5484 | 76008.26 | 181390.41 | 51102 | 223760.7 | 14150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 28427.6 | 347666.5484 | 0 | 7675.76 | 33390 | 3420 | 8550 | 0 | 152962.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-14 | 883246.0856 | 0 | 776729.25 | 349099.2478 | 76565.1407 | 182078.8137 | 51102 | 224400.8835 | 14388.5321 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 401.6514 | 0 | 0 | 28427.6 | 349099.2478 | 0 | 7709.705 | 33729.9083 | 3472.2936 | 8680.7339 | 0 | 153651.2137 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-15 | 886564.2529 | 0 | 776729.25 | 350531.9471 | 77122.0215 | 182767.2173 | 51102 | 225041.067 | 14627.0642 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 803.3028 | 0 | 0 | 28427.6 | 350531.9471 | 0 | 7743.6499 | 34069.8165 | 3524.5872 | 8811.4679 | 0 | 154339.6173 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-16 | 889882.4201 | 0 | 776729.25 | 351964.6465 | 77678.9022 | 183455.621 | 51102 | 225681.2505 | 14865.5963 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 1204.9541 | 0 | 0 | 28427.6 | 351964.6465 | 0 | 7777.5949 | 34409.7248 | 3576.8807 | 8942.2018 | 0 | 155028.021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-17 | 893200.5874 | 0 | 776729.25 | 353397.3458 | 78235.7829 | 184144.0247 | 51102 | 226321.4339 | 15104.1284 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 1606.6055 | 0 | 0 | 28427.6 | 353397.3458 | 0 | 7811.5398 | 34749.633 | 3629.1743 | 9072.9358 | 0 | 155716.4247 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-18 | 896518.7547 | 0 | 776729.25 | 354830.0452 | 78792.6637 | 184832.4283 | 51102 | 226961.6174 | 15342.6606 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 2008.2569 | 0 | 0 | 28427.6 | 354830.0452 | 0 | 7845.4848 | 35089.5413 | 3681.4679 | 9203.6697 | 0 | 156404.8283 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-19 | 899836.9219 | 0 | 776729.25 | 356262.7446 | 79349.5444 | 185520.832 | 51102 | 227601.8009 | 15581.1927 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 2409.9083 | 0 | 0 | 28427.6 | 356262.7446 | 0 | 7879.4297 | 35429.4495 | 3733.7615 | 9334.4037 | 0 | 157093.232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-20 | 903155.0892 | 0 | 776729.25 | 357695.4439 | 79906.4251 | 186209.2357 | 51102 | 228241.9844 | 15819.7248 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 2811.5596 | 0 | 0 | 28427.6 | 357695.4439 | 0 | 7913.3747 | 35769.3578 | 3786.055 | 9465.1376 | 0 | 157781.6357 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-21 | 906473.2564 | 0 | 776729.25 | 359128.1433 | 80463.3059 | 186897.6394 | 51102 | 228882.1679 | 16058.2569 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 3213.211 | 0 | 0 | 28427.6 | 359128.1433 | 0 | 7947.3196 | 36109.2661 | 3838.3486 | 9595.8716 | 0 | 158470.0394 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-22 | 909791.4237 | 0 | 776729.25 | 360560.8427 | 81020.1866 | 187586.043 | 51102 | 229522.3514 | 16296.789 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 3614.8624 | 0 | 0 | 28427.6 | 360560.8427 | 0 | 7981.2646 | 36449.1743 | 3890.6422 | 9726.6055 | 0 | 159158.443 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-23 | 913109.5909 | 0 | 776729.25 | 361993.542 | 81577.0673 | 188274.4467 | 51102 | 230162.5349 | 16535.3211 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 4016.5138 | 0 | 0 | 28427.6 | 361993.542 | 0 | 8015.2095 | 36789.0826 | 3942.9358 | 9857.3394 | 0 | 159846.8467 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-24 | 916427.7582 | 0 | 776729.25 | 363426.2414 | 82133.9481 | 188962.8504 | 51102 | 230802.7183 | 16773.8532 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 4418.1651 | 0 | 0 | 28427.6 | 363426.2414 | 0 | 8049.1545 | 37128.9908 | 3995.2294 | 9988.0734 | 0 | 160535.2504 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-25 | 919745.9254 | 0 | 776729.25 | 364858.9407 | 82690.8288 | 189651.254 | 51102 | 231442.9018 | 17012.3853 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 4819.8165 | 0 | 0 | 28427.6 | 364858.9407 | 0 | 8083.0994 | 37468.8991 | 4047.5229 | 10118.8073 | 0 | 161223.654 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-26 | 923064.0927 | 0 | 776729.25 | 366291.6401 | 83247.7095 | 190339.6577 | 51102 | 232083.0853 | 17250.9174 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 5221.4679 | 0 | 0 | 28427.6 | 366291.6401 | 0 | 8117.0444 | 37808.8073 | 4099.8165 | 10249.5413 | 0 | 161912.0577 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-27 | 926382.2599 | 0 | 776729.25 | 367724.3395 | 83804.5903 | 191028.0614 | 51102 | 232723.2688 | 17489.4495 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 5623.1193 | 0 | 0 | 28427.6 | 367724.3395 | 0 | 8150.9894 | 38148.7156 | 4152.1101 | 10380.2752 | 0 | 162600.4614 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-28 | 929700.4272 | 0 | 776729.25 | 369157.0388 | 84361.471 | 191716.465 | 51102 | 233363.4523 | 17727.9817 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 6024.7706 | 0 | 0 | 28427.6 | 369157.0388 | 0 | 8184.9343 | 38488.6239 | 4204.4037 | 10511.0092 | 0 | 163288.865 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-29 | 933018.5944 | 0 | 776729.25 | 370589.7382 | 84918.3517 | 192404.8687 | 51102 | 234003.6358 | 17966.5138 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 6426.422 | 0 | 0 | 28427.6 | 370589.7382 | 0 | 8218.8793 | 38828.5321 | 4256.6972 | 10641.7431 | 0 | 163977.2687 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-30 | 936336.7617 | 52562.17 | 829291.42 | 372022.4376 | 85475.2325 | 193093.2724 | 51102 | 234643.8193 | 18205.0459 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 6828.0734 | 0 | 0 | 28427.6 | 372022.4376 | 0 | 8252.8242 | 39168.4404 | 4308.9908 | 10772.4771 | 0 | 164665.6724 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-01 | 939654.9289 | 0 | 829291.42 | 373455.1369 | 86032.1132 | 193781.6761 | 51102 | 235284.0028 | 18443.578 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 7229.7248 | 0 | 0 | 28427.6 | 373455.1369 | 0 | 8286.7692 | 39508.3486 | 4361.2844 | 10903.211 | 0 | 165354.0761 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-02 | 942973.0962 | 0 | 829291.42 | 374887.8363 | 86588.9939 | 194470.0797 | 51102 | 235924.1862 | 18682.1101 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 7631.3761 | 0 | 0 | 28427.6 | 374887.8363 | 0 | 8320.7141 | 39848.2569 | 4413.578 | 11033.945 | 0 | 166042.4797 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-03 | 946291.2634 | 0 | 829291.42 | 376320.5356 | 87145.8747 | 195158.4834 | 51102 | 236564.3697 | 18920.6422 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 8033.0275 | 0 | 0 | 28427.6 | 376320.5356 | 0 | 8354.6591 | 40188.1651 | 4465.8716 | 11164.6789 | 0 | 166730.8834 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-04 | 949609.4307 | 0 | 829291.42 | 377753.235 | 87702.7554 | 195846.8871 | 51102 | 237204.5532 | 19159.1743 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 8434.6789 | 0 | 0 | 28427.6 | 377753.235 | 0 | 8388.604 | 40528.0734 | 4518.1651 | 11295.4128 | 0 | 167419.2871 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-05 | 952927.598 | 0 | 829291.42 | 379185.9344 | 88259.6361 | 196535.2907 | 51102 | 237844.7367 | 19397.7064 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 8836.3303 | 0 | 0 | 28427.6 | 379185.9344 | 0 | 8422.549 | 40867.9817 | 4570.4587 | 11426.1468 | 0 | 168107.6907 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-06 | 956245.7652 | 0 | 829291.42 | 380618.6337 | 88816.5169 | 197223.6944 | 51102 | 238484.9202 | 19636.2385 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 9237.9817 | 0 | 0 | 28427.6 | 380618.6337 | 0 | 8456.4939 | 41207.8899 | 4622.7523 | 11556.8807 | 0 | 168796.0944 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-07 | 959563.9325 | 0 | 829291.42 | 382051.3331 | 89373.3976 | 197912.0981 | 51102 | 239125.1037 | 19874.7706 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 9639.633 | 0 | 0 | 28427.6 | 382051.3331 | 0 | 8490.4389 | 41547.7982 | 4675.0459 | 11687.6147 | 0 | 169484.4981 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-08 | 962882.0997 | 0 | 829291.42 | 383484.0325 | 89930.2783 | 198600.5017 | 51102 | 239765.2872 | 20113.3028 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 10041.2844 | 0 | 0 | 28427.6 | 383484.0325 | 0 | 8524.3839 | 41887.7064 | 4727.3394 | 11818.3486 | 0 | 170172.9017 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-09 | 966200.267 | 0 | 829291.42 | 384916.7318 | 90487.1591 | 199288.9054 | 51102 | 240405.4706 | 20351.8349 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 10442.9358 | 0 | 0 | 28427.6 | 384916.7318 | 0 | 8558.3288 | 42227.6147 | 4779.633 | 11949.0826 | 0 | 170861.3054 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-10 | 969518.4342 | 0 | 829291.42 | 386349.4312 | 91044.0398 | 199977.3091 | 51102 | 241045.6541 | 20590.367 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 10844.5872 | 0 | 0 | 28427.6 | 386349.4312 | 0 | 8592.2738 | 42567.5229 | 4831.9266 | 12079.8165 | 0 | 171549.7091 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-11 | 972836.6015 | 0 | 829291.42 | 387782.1306 | 91600.9206 | 200665.7128 | 51102 | 241685.8376 | 20828.8991 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 11246.2385 | 0 | 0 | 28427.6 | 387782.1306 | 0 | 8626.2187 | 42907.4312 | 4884.2202 | 12210.5505 | 0 | 172238.1128 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-12 | 976154.7687 | 0 | 829291.42 | 389214.8299 | 92157.8013 | 201354.1164 | 51102 | 242326.0211 | 21067.4312 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 11647.8899 | 0 | 0 | 28427.6 | 389214.8299 | 0 | 8660.1637 | 43247.3394 | 4936.5138 | 12341.2844 | 0 | 172926.5164 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-13 | 979472.936 | 0 | 829291.42 | 390647.5293 | 92714.682 | 202042.5201 | 51102 | 242966.2046 | 21305.9633 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 12049.5413 | 0 | 0 | 28427.6 | 390647.5293 | 0 | 8694.1086 | 43587.2477 | 4988.8073 | 12472.0183 | 0 | 173614.9201 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-14 | 982791.1032 | 0 | 829291.42 | 392080.2286 | 93271.5628 | 202730.9238 | 51102 | 243606.3881 | 21544.4954 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 12451.1927 | 0 | 0 | 28427.6 | 392080.2286 | 0 | 8728.0536 | 43927.156 | 5041.1009 | 12602.7523 | 0 | 174303.3238 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-15 | 986109.2705 | 0 | 829291.42 | 393512.928 | 93828.4435 | 203419.3274 | 51102 | 244246.5716 | 21783.0275 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 12852.844 | 0 | 0 | 28427.6 | 393512.928 | 0 | 8761.9985 | 44267.0642 | 5093.3945 | 12733.4862 | 0 | 174991.7274 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-16 | 989427.4377 | 0 | 829291.42 | 394945.6274 | 94385.3242 | 204107.7311 | 51102 | 244886.755 | 22021.5596 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 13254.4954 | 0 | 0 | 28427.6 | 394945.6274 | 0 | 8795.9435 | 44606.9725 | 5145.6881 | 12864.2202 | 0 | 175680.1311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-17 | 992745.605 | 0 | 829291.42 | 396378.3267 | 94942.205 | 204796.1348 | 51102 | 245526.9385 | 22260.0917 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 13656.1468 | 0 | 0 | 28427.6 | 396378.3267 | 0 | 8829.8884 | 44946.8807 | 5197.9817 | 12994.9541 | 0 | 176368.5348 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-18 | 996063.7722 | 0 | 829291.42 | 397811.0261 | 95499.0857 | 205484.5384 | 51102 | 246167.122 | 22498.6239 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 14057.7982 | 0 | 0 | 28427.6 | 397811.0261 | 0 | 8863.8334 | 45286.789 | 5250.2752 | 13125.6881 | 0 | 177056.9384 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-19 | 999381.9395 | 0 | 829291.42 | 399243.7255 | 96055.9664 | 206172.9421 | 51102 | 246807.3055 | 22737.156 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 14459.4495 | 0 | 0 | 28427.6 | 399243.7255 | 0 | 8897.7783 | 45626.6972 | 5302.5688 | 13256.422 | 0 | 177745.3421 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-20 | 1002700.1067 | 0 | 829291.42 | 400676.4248 | 96612.8472 | 206861.3458 | 51102 | 247447.489 | 22975.6881 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 14861.1009 | 0 | 0 | 28427.6 | 400676.4248 | 0 | 8931.7233 | 45966.6055 | 5354.8624 | 13387.156 | 0 | 178433.7458 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-21 | 1006018.274 | 0 | 829291.42 | 402109.1242 | 97169.7279 | 207549.7494 | 51102 | 248087.6725 | 23214.2202 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 15262.7523 | 0 | 0 | 28427.6 | 402109.1242 | 0 | 8965.6683 | 46306.5138 | 5407.156 | 13517.8899 | 0 | 179122.1494 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-22 | 1009336.4413 | 0 | 829291.42 | 403541.8235 | 97726.6086 | 208238.1531 | 51102 | 248727.856 | 23452.7523 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 15664.4037 | 0 | 0 | 28427.6 | 403541.8235 | 0 | 8999.6132 | 46646.422 | 5459.4495 | 13648.6239 | 0 | 179810.5531 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-23 | 1012654.6085 | 0 | 829291.42 | 404974.5229 | 98283.4894 | 208926.5568 | 51102 | 249368.0394 | 23691.2844 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 16066.055 | 0 | 0 | 28427.6 | 404974.5229 | 0 | 9033.5582 | 46986.3303 | 5511.7431 | 13779.3578 | 0 | 180498.9568 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-24 | 1015972.7758 | 0 | 829291.42 | 406407.2223 | 98840.3701 | 209614.9605 | 51102 | 250008.2229 | 23929.8165 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 16467.7064 | 0 | 0 | 28427.6 | 406407.2223 | 0 | 9067.5031 | 47326.2385 | 5564.0367 | 13910.0917 | 0 | 181187.3605 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-25 | 1019290.943 | 0 | 829291.42 | 407839.9216 | 99397.2508 | 210303.3641 | 51102 | 250648.4064 | 24168.3486 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 16869.3578 | 0 | 0 | 28427.6 | 407839.9216 | 0 | 9101.4481 | 47666.1468 | 5616.3303 | 14040.8257 | 0 | 181875.7641 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-26 | 1022609.1103 | 0 | 829291.42 | 409272.621 | 99954.1316 | 210991.7678 | 51102 | 251288.5899 | 24406.8807 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 17271.0092 | 0 | 0 | 28427.6 | 409272.621 | 0 | 9135.393 | 48006.055 | 5668.6239 | 14171.5596 | 0 | 182564.1678 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-27 | 1025927.2775 | 0 | 829291.42 | 410705.3204 | 100511.0123 | 211680.1715 | 51102 | 251928.7734 | 24645.4128 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 17672.6606 | 0 | 0 | 28427.6 | 410705.3204 | 0 | 9169.338 | 48345.9633 | 5720.9174 | 14302.2936 | 0 | 183252.5715 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-28 | 1029245.4448 | 0 | 829291.42 | 412138.0197 | 101067.893 | 212368.5751 | 51102 | 252568.9569 | 24883.945 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 18074.3119 | 0 | 0 | 28427.6 | 412138.0197 | 0 | 9203.2829 | 48685.8716 | 5773.211 | 14433.0275 | 0 | 183940.9751 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-29 | 1032563.612 | 0 | 829291.42 | 413570.7191 | 101624.7738 | 213056.9788 | 51102 | 253209.1404 | 25122.4771 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 18475.9633 | 0 | 0 | 28427.6 | 413570.7191 | 0 | 9237.2279 | 49025.7798 | 5825.5046 | 14563.7615 | 0 | 184629.3788 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-30 | 1035881.7793 | 0 | 829291.42 | 415003.4184 | 102181.6545 | 213745.3825 | 51102 | 253849.3239 | 25361.0092 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 18877.6147 | 0 | 0 | 28427.6 | 415003.4184 | 0 | 9271.1728 | 49365.6881 | 5877.7982 | 14694.4954 | 0 | 185317.7825 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-31 | 1039199.9465 | 66009.82 | 895301.24 | 416436.1178 | 102738.5352 | 214433.7861 | 51102 | 254489.5073 | 25599.5413 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 19279.2661 | 0 | 0 | 28427.6 | 416436.1178 | 0 | 9305.1178 | 49705.5963 | 5930.0917 | 14825.2294 | 0 | 186006.1861 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-01 | 1042518.1138 | 0 | 895301.24 | 417868.8172 | 103295.416 | 215122.1898 | 51102 | 255129.6908 | 25838.0734 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 19680.9174 | 0 | 0 | 28427.6 | 417868.8172 | 0 | 9339.0628 | 50045.5046 | 5982.3853 | 14955.9633 | 0 | 186694.5898 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-02 | 1045836.281 | 0 | 895301.24 | 419301.5165 | 103852.2967 | 215810.5935 | 51102 | 255769.8743 | 26076.6055 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 20082.5688 | 0 | 0 | 28427.6 | 419301.5165 | 0 | 9373.0077 | 50385.4128 | 6034.6789 | 15086.6972 | 0 | 187382.9935 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-03 | 1049154.4483 | 0 | 895301.24 | 420734.2159 | 104409.1774 | 216498.9972 | 51102 | 256410.0578 | 26315.1376 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 20484.2202 | 0 | 0 | 28427.6 | 420734.2159 | 0 | 9406.9527 | 50725.3211 | 6086.9725 | 15217.4312 | 0 | 188071.3972 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-04 | 1052472.6155 | 0 | 895301.24 | 422166.9153 | 104966.0582 | 217187.4008 | 51102 | 257050.2413 | 26553.6697 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 20885.8716 | 0 | 0 | 28427.6 | 422166.9153 | 0 | 9440.8976 | 51065.2294 | 6139.2661 | 15348.1651 | 0 | 188759.8008 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-05 | 1055790.7828 | 0 | 895301.24 | 423599.6146 | 105522.9389 | 217875.8045 | 51102 | 257690.4248 | 26792.2018 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 21287.5229 | 0 | 0 | 28427.6 | 423599.6146 | 0 | 9474.8426 | 51405.1376 | 6191.5596 | 15478.8991 | 0 | 189448.2045 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-06 | 1059108.95 | 0 | 895301.24 | 425032.314 | 106079.8196 | 218564.2082 | 51102 | 258330.6083 | 27030.7339 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 21689.1743 | 0 | 0 | 28427.6 | 425032.314 | 0 | 9508.7875 | 51745.0459 | 6243.8532 | 15609.633 | 0 | 190136.6082 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-07 | 1062427.1173 | 0 | 895301.24 | 426465.0134 | 106636.7004 | 219252.6118 | 51102 | 258970.7917 | 27269.2661 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 22090.8257 | 0 | 0 | 28427.6 | 426465.0134 | 0 | 9542.7325 | 52084.9541 | 6296.1468 | 15740.367 | 0 | 190825.0118 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-08 | 1065745.2845 | 0 | 895301.24 | 427897.7127 | 107193.5811 | 219941.0155 | 51102 | 259610.9752 | 27507.7982 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 22492.4771 | 0 | 0 | 28427.6 | 427897.7127 | 0 | 9576.6774 | 52424.8624 | 6348.4404 | 15871.1009 | 0 | 191513.4155 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-09 | 1069063.4518 | 0 | 895301.24 | 429330.4121 | 107750.4618 | 220629.4192 | 51102 | 260251.1587 | 27746.3303 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 22894.1284 | 0 | 0 | 28427.6 | 429330.4121 | 0 | 9610.6224 | 52764.7706 | 6400.7339 | 16001.8349 | 0 | 192201.8192 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-10 | 1072381.6191 | 0 | 895301.24 | 430763.1114 | 108307.3426 | 221317.8228 | 51102 | 260891.3422 | 27984.8624 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 23295.7798 | 0 | 0 | 28427.6 | 430763.1114 | 0 | 9644.5673 | 53104.6789 | 6453.0275 | 16132.5688 | 0 | 192890.2228 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-11 | 1075699.7863 | 0 | 895301.24 | 432195.8108 | 108864.2233 | 222006.2265 | 51102 | 261531.5257 | 28223.3945 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 23697.4312 | 0 | 0 | 28427.6 | 432195.8108 | 0 | 9678.5123 | 53444.5872 | 6505.3211 | 16263.3028 | 0 | 193578.6265 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-12 | 1079017.9536 | 0 | 895301.24 | 433628.5102 | 109421.104 | 222694.6302 | 51102 | 262171.7092 | 28461.9266 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 24099.0826 | 0 | 0 | 28427.6 | 433628.5102 | 0 | 9712.4572 | 53784.4954 | 6557.6147 | 16394.0367 | 0 | 194267.0302 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-13 | 1082336.1208 | 0 | 895301.24 | 435061.2095 | 109977.9848 | 223383.0339 | 51102 | 262811.8927 | 28700.4587 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 24500.7339 | 0 | 0 | 28427.6 | 435061.2095 | 0 | 9746.4022 | 54124.4037 | 6609.9083 | 16524.7706 | 0 | 194955.4339 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-14 | 1085654.2881 | 0 | 895301.24 | 436493.9089 | 110534.8655 | 224071.4375 | 51102 | 263452.0761 | 28938.9908 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 24902.3853 | 0 | 0 | 28427.6 | 436493.9089 | 0 | 9780.3472 | 54464.3119 | 6662.2018 | 16655.5046 | 0 | 195643.8375 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-15 | 1088972.4553 | 0 | 895301.24 | 437926.6083 | 111091.7462 | 224759.8412 | 51102 | 264092.2596 | 29177.5229 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 25304.0367 | 0 | 0 | 28427.6 | 437926.6083 | 0 | 9814.2921 | 54804.2202 | 6714.4954 | 16786.2385 | 0 | 196332.2412 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-16 | 1092290.6226 | 0 | 895301.24 | 439359.3076 | 111648.627 | 225448.2449 | 51102 | 264732.4431 | 29416.055 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 25705.6881 | 0 | 0 | 28427.6 | 439359.3076 | 0 | 9848.2371 | 55144.1284 | 6766.789 | 16916.9725 | 0 | 197020.6449 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-17 | 1095608.7898 | 0 | 895301.24 | 440792.007 | 112205.5077 | 226136.6485 | 51102 | 265372.6266 | 29654.5872 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 26107.3394 | 0 | 0 | 28427.6 | 440792.007 | 0 | 9882.182 | 55484.0367 | 6819.0826 | 17047.7064 | 0 | 197709.0485 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-18 | 1098926.9571 | 0 | 895301.24 | 442224.7063 | 112762.3884 | 226825.0522 | 51102 | 266012.8101 | 29893.1193 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 26508.9908 | 0 | 0 | 28427.6 | 442224.7063 | 0 | 9916.127 | 55823.945 | 6871.3761 | 17178.4404 | 0 | 198397.4522 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-19 | 1102245.1243 | 0 | 895301.24 | 443657.4057 | 113319.2692 | 227513.4559 | 51102 | 266652.9936 | 30131.6514 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 26910.6422 | 0 | 0 | 28427.6 | 443657.4057 | 0 | 9950.0719 | 56163.8532 | 6923.6697 | 17309.1743 | 0 | 199085.8559 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-20 | 1105563.2916 | 0 | 895301.24 | 445090.1051 | 113876.1499 | 228201.8595 | 51102 | 267293.1771 | 30370.1835 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 27312.2936 | 0 | 0 | 28427.6 | 445090.1051 | 0 | 9984.0169 | 56503.7615 | 6975.9633 | 17439.9083 | 0 | 199774.2595 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-21 | 1108881.4588 | 0 | 895301.24 | 446522.8044 | 114433.0306 | 228890.2632 | 51102 | 267933.3606 | 30608.7156 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 27713.945 | 0 | 0 | 28427.6 | 446522.8044 | 0 | 10017.9618 | 56843.6697 | 7028.2569 | 17570.6422 | 0 | 200462.6632 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-22 | 1112199.6261 | 0 | 895301.24 | 447955.5038 | 114989.9114 | 229578.6669 | 51102 | 268573.544 | 30847.2477 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 28115.5963 | 0 | 0 | 28427.6 | 447955.5038 | 0 | 10051.9068 | 57183.578 | 7080.5505 | 17701.3761 | 0 | 201151.0669 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-23 | 1115517.7933 | 0 | 895301.24 | 449388.2032 | 115546.7921 | 230267.0706 | 51102 | 269213.7275 | 31085.7798 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 28517.2477 | 0 | 0 | 28427.6 | 449388.2032 | 0 | 10085.8517 | 57523.4862 | 7132.844 | 17832.1101 | 0 | 201839.4706 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-24 | 1118835.9606 | 0 | 895301.24 | 450820.9025 | 116103.6728 | 230955.4742 | 51102 | 269853.911 | 31324.3119 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 28918.8991 | 0 | 0 | 28427.6 | 450820.9025 | 0 | 10119.7967 | 57863.3945 | 7185.1376 | 17962.844 | 0 | 202527.8742 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-25 | 1122154.1278 | 0 | 895301.24 | 452253.6019 | 116660.5536 | 231643.8779 | 51102 | 270494.0945 | 31562.844 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 29320.5505 | 0 | 0 | 28427.6 | 452253.6019 | 0 | 10153.7417 | 58203.3028 | 7237.4312 | 18093.578 | 0 | 203216.2779 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-26 | 1125472.2951 | 0 | 895301.24 | 453686.3012 | 117217.4343 | 232332.2816 | 51102 | 271134.278 | 31801.3761 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 29722.2018 | 0 | 0 | 28427.6 | 453686.3012 | 0 | 10187.6866 | 58543.211 | 7289.7248 | 18224.3119 | 0 | 203904.6816 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-27 | 1128790.4624 | 0 | 895301.24 | 455119.0006 | 117774.315 | 233020.6852 | 51102 | 271774.4615 | 32039.9083 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 30123.8532 | 0 | 0 | 28427.6 | 455119.0006 | 0 | 10221.6316 | 58883.1193 | 7342.0183 | 18355.0459 | 0 | 204593.0852 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-28 | 1132108.6296 | 0 | 895301.24 | 456551.7 | 118331.1958 | 233709.0889 | 51102 | 272414.645 | 32278.4404 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 30525.5046 | 0 | 0 | 28427.6 | 456551.7 | 0 | 10255.5765 | 59223.0275 | 7394.3119 | 18485.7798 | 0 | 205281.4889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-29 | 1135426.7969 | 0 | 895301.24 | 457984.3993 | 118888.0765 | 234397.4926 | 51102 | 273054.8284 | 32516.9725 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 30927.156 | 0 | 0 | 28427.6 | 457984.3993 | 0 | 10289.5215 | 59562.9358 | 7446.6055 | 18616.5138 | 0 | 205969.8926 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-30 | 1138744.9641 | 0 | 895301.24 | 459417.0987 | 119444.9572 | 235085.8962 | 51102 | 273695.0119 | 32755.5046 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 31328.8073 | 0 | 0 | 28427.6 | 459417.0987 | 0 | 10323.4664 | 59902.844 | 7498.8991 | 18747.2477 | 0 | 206658.2962 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-31 | 1142063.1314 | 0 | 895301.24 | 460849.7981 | 120001.838 | 235774.2999 | 51102 | 274335.1954 | 32994.0367 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 31730.4587 | 0 | 0 | 28427.6 | 460849.7981 | 0 | 10357.4114 | 60242.7523 | 7551.1927 | 18877.9817 | 0 | 207346.6999 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-01 | 1145381.2986 | 0 | 895301.24 | 462282.4974 | 120558.7187 | 236462.7036 | 51102 | 274975.3789 | 33232.5688 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 32132.1101 | 0 | 0 | 28427.6 | 462282.4974 | 0 | 10391.3563 | 60582.6606 | 7603.4862 | 19008.7156 | 0 | 208035.1036 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-02 | 1148699.4659 | 0 | 895301.24 | 463715.1968 | 121115.5994 | 237151.1072 | 51102 | 275615.5624 | 33471.1009 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 32533.7615 | 0 | 0 | 28427.6 | 463715.1968 | 0 | 10425.3013 | 60922.5688 | 7655.7798 | 19139.4495 | 0 | 208723.5072 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-03 | 1152017.6331 | 116527.82 | 1011829.06 | 465147.8962 | 121672.4802 | 237839.5109 | 51102 | 276255.7459 | 33709.633 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 32935.4128 | 0 | 0 | 28427.6 | 465147.8962 | 0 | 10459.2462 | 61262.4771 | 7708.0734 | 19270.1835 | 0 | 209411.9109 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-04 | 1155335.8004 | 0 | 1011829.06 | 466580.5955 | 122229.3609 | 238527.9146 | 51102 | 276895.9294 | 33948.1651 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 33337.0642 | 0 | 0 | 28427.6 | 466580.5955 | 0 | 10493.1912 | 61602.3853 | 7760.367 | 19400.9174 | 0 | 210100.3146 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-05 | 1158653.9676 | 0 | 1011829.06 | 468013.2949 | 122786.2417 | 239216.3183 | 51102 | 277536.1128 | 34186.6972 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 33738.7156 | 0 | 0 | 28427.6 | 468013.2949 | 0 | 10527.1361 | 61942.2936 | 7812.6606 | 19531.6514 | 0 | 210788.7183 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-06 | 1161972.1349 | 0 | 1011829.06 | 469445.9942 | 123343.1224 | 239904.7219 | 51102 | 278176.2963 | 34425.2294 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 34140.367 | 0 | 0 | 28427.6 | 469445.9942 | 0 | 10561.0811 | 62282.2018 | 7864.9541 | 19662.3853 | 0 | 211477.1219 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-07 | 1165290.3021 | 0 | 1011829.06 | 470878.6936 | 123900.0031 | 240593.1256 | 51102 | 278816.4798 | 34663.7615 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 34542.0183 | 0 | 0 | 28427.6 | 470878.6936 | 0 | 10595.0261 | 62622.1101 | 7917.2477 | 19793.1193 | 0 | 212165.5256 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-08 | 1168608.4694 | 0 | 1011829.06 | 472311.393 | 124456.8839 | 241281.5293 | 51102 | 279456.6633 | 34902.2936 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 34943.6697 | 0 | 0 | 28427.6 | 472311.393 | 0 | 10628.971 | 62962.0183 | 7969.5413 | 19923.8532 | 0 | 212853.9293 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-09 | 1171926.6366 | 0 | 1011829.06 | 473744.0923 | 125013.7646 | 241969.9329 | 51102 | 280096.8468 | 35140.8257 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 35345.3211 | 0 | 0 | 28427.6 | 473744.0923 | 0 | 10662.916 | 63301.9266 | 8021.8349 | 20054.5872 | 0 | 213542.3329 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-10 | 1175244.8039 | 0 | 1011829.06 | 475176.7917 | 125570.6453 | 242658.3366 | 51102 | 280737.0303 | 35379.3578 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 35746.9725 | 0 | 0 | 28427.6 | 475176.7917 | 0 | 10696.8609 | 63641.8349 | 8074.1284 | 20185.3211 | 0 | 214230.7366 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-11 | 1178562.9711 | 0 | 1011829.06 | 476609.4911 | 126127.5261 | 243346.7403 | 51102 | 281377.2138 | 35617.8899 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 36148.6239 | 0 | 0 | 28427.6 | 476609.4911 | 0 | 10730.8059 | 63981.7431 | 8126.422 | 20316.055 | 0 | 214919.1403 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-12 | 1181881.1384 | 0 | 1011829.06 | 478042.1904 | 126684.4068 | 244035.1439 | 51102 | 282017.3972 | 35856.422 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 36550.2752 | 0 | 0 | 28427.6 | 478042.1904 | 0 | 10764.7508 | 64321.6514 | 8178.7156 | 20446.789 | 0 | 215607.5439 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-13 | 1185199.3057 | 0 | 1011829.06 | 479474.8898 | 127241.2875 | 244723.5476 | 51102 | 282657.5807 | 36094.9541 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 36951.9266 | 0 | 0 | 28427.6 | 479474.8898 | 0 | 10798.6958 | 64661.5596 | 8231.0092 | 20577.5229 | 0 | 216295.9476 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-14 | 1188517.4729 | 0 | 1011829.06 | 480907.5891 | 127798.1683 | 245411.9513 | 51102 | 283297.7642 | 36333.4862 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 37353.578 | 0 | 0 | 28427.6 | 480907.5891 | 0 | 10832.6407 | 65001.4679 | 8283.3028 | 20708.2569 | 0 | 216984.3513 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-15 | 1191835.6402 | 0 | 1011829.06 | 482340.2885 | 128355.049 | 246100.355 | 51102 | 283937.9477 | 36572.0183 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 37755.2294 | 0 | 0 | 28427.6 | 482340.2885 | 0 | 10866.5857 | 65341.3761 | 8335.5963 | 20838.9908 | 0 | 217672.755 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-16 | 1195153.8074 | 0 | 1011829.06 | 483772.9879 | 128911.9297 | 246788.7586 | 51102 | 284578.1312 | 36810.5505 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 38156.8807 | 0 | 0 | 28427.6 | 483772.9879 | 0 | 10900.5306 | 65681.2844 | 8387.8899 | 20969.7248 | 0 | 218361.1586 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-17 | 1198471.9747 | 0 | 1011829.06 | 485205.6872 | 129468.8105 | 247477.1623 | 51102 | 285218.3147 | 37049.0826 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 38558.5321 | 0 | 0 | 28427.6 | 485205.6872 | 0 | 10934.4756 | 66021.1927 | 8440.1835 | 21100.4587 | 0 | 219049.5623 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-18 | 1201790.1419 | 0 | 1011829.06 | 486638.3866 | 130025.6912 | 248165.566 | 51102 | 285858.4982 | 37287.6147 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 38960.1835 | 0 | 0 | 28427.6 | 486638.3866 | 0 | 10968.4206 | 66361.1009 | 8492.4771 | 21231.1927 | 0 | 219737.966 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-19 | 1205108.3092 | 0 | 1011829.06 | 488071.086 | 130582.5719 | 248853.9696 | 51102 | 286498.6817 | 37526.1468 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 39361.8349 | 0 | 0 | 28427.6 | 488071.086 | 0 | 11002.3655 | 66701.0092 | 8544.7706 | 21361.9266 | 0 | 220426.3696 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-20 | 1208426.4764 | 0 | 1011829.06 | 489503.7853 | 131139.4527 | 249542.3733 | 51102 | 287138.8651 | 37764.6789 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 39763.4862 | 0 | 0 | 28427.6 | 489503.7853 | 0 | 11036.3105 | 67040.9174 | 8597.0642 | 21492.6606 | 0 | 221114.7733 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-21 | 1211744.6437 | 0 | 1011829.06 | 490936.4847 | 131696.3334 | 250230.777 | 51102 | 287779.0486 | 38003.211 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 40165.1376 | 0 | 0 | 28427.6 | 490936.4847 | 0 | 11070.2554 | 67380.8257 | 8649.3578 | 21623.3945 | 0 | 221803.177 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-22 | 1215062.8109 | 0 | 1011829.06 | 492369.184 | 132253.2141 | 250919.1806 | 51102 | 288419.2321 | 38241.7431 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 40566.789 | 0 | 0 | 28427.6 | 492369.184 | 0 | 11104.2004 | 67720.7339 | 8701.6514 | 21754.1284 | 0 | 222491.5806 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-23 | 1218380.9782 | 0 | 1011829.06 | 493801.8834 | 132810.0949 | 251607.5843 | 51102 | 289059.4156 | 38480.2752 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 40968.4404 | 0 | 0 | 28427.6 | 493801.8834 | 0 | 11138.1453 | 68060.6422 | 8753.945 | 21884.8624 | 0 | 223179.9843 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-24 | 1221699.1454 | 0 | 1011829.06 | 495234.5828 | 133366.9756 | 252295.988 | 51102 | 289699.5991 | 38718.8073 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 41370.0917 | 0 | 0 | 28427.6 | 495234.5828 | 0 | 11172.0903 | 68400.5505 | 8806.2385 | 22015.5963 | 0 | 223868.388 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-25 | 1225017.3127 | 0 | 1011829.06 | 496667.2821 | 133923.8563 | 252984.3917 | 51102 | 290339.7826 | 38957.3394 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 41771.7431 | 0 | 0 | 28427.6 | 496667.2821 | 0 | 11206.0352 | 68740.4587 | 8858.5321 | 22146.3303 | 0 | 224556.7917 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-26 | 1228335.4799 | 0 | 1011829.06 | 498099.9815 | 134480.7371 | 253672.7953 | 51102 | 290979.9661 | 39195.8716 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 42173.3945 | 0 | 0 | 28427.6 | 498099.9815 | 0 | 11239.9802 | 69080.367 | 8910.8257 | 22277.0642 | 0 | 225245.1953 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-27 | 1231653.6472 | 0 | 1011829.06 | 499532.6809 | 135037.6178 | 254361.199 | 51102 | 291620.1495 | 39434.4037 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 42575.0459 | 0 | 0 | 28427.6 | 499532.6809 | 0 | 11273.9251 | 69420.2752 | 8963.1193 | 22407.7982 | 0 | 225933.599 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-28 | 1234971.8144 | 0 | 1011829.06 | 500965.3802 | 135594.4985 | 255049.6027 | 51102 | 292260.333 | 39672.9358 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 42976.6972 | 0 | 0 | 28427.6 | 500965.3802 | 0 | 11307.8701 | 69760.1835 | 9015.4128 | 22538.5321 | 0 | 226622.0027 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-01 | 1238289.9817 | 0 | 1011829.06 | 502398.0796 | 136151.3793 | 255738.0063 | 51102 | 292900.5165 | 39911.4679 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43378.3486 | 0 | 0 | 28427.6 | 502398.0796 | 0 | 11341.815 | 70100.0917 | 9067.7064 | 22669.2661 | 0 | 227310.4063 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-02 | 1241608.149 | 0 | 1011829.06 | 503830.779 | 136708.26 | 256426.41 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 503830.779 | 0 | 11375.76 | 70440 | 9120 | 22800 | 0 | 227998.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-03 | 1243024.8821 | 0 | 1011829.06 | 504934.8448 | 136982.245 | 256465.0923 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 504934.8448 | 0 | 11385.8352 | 70611.5414 | 9146.391 | 22865.9774 | 0 | 228037.4923 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-04 | 1244441.6152 | 115891.65 | 1127720.71 | 506038.9106 | 137256.2299 | 256503.7747 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 506038.9106 | 0 | 11395.9104 | 70783.0827 | 9172.782 | 22931.9549 | 0 | 228076.1747 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-05 | 1245858.3484 | 0 | 1127720.71 | 507142.9765 | 137530.2149 | 256542.457 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 507142.9765 | 0 | 11405.9856 | 70954.6241 | 9199.1729 | 22997.9323 | 0 | 228114.857 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-06 | 1247275.0815 | 0 | 1127720.71 | 508247.0423 | 137804.1998 | 256581.1393 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 508247.0423 | 0 | 11416.0608 | 71126.1654 | 9225.5639 | 23063.9098 | 0 | 228153.5393 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-07 | 1248691.8146 | 0 | 1127720.71 | 509351.1082 | 138078.1848 | 256619.8217 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 509351.1082 | 0 | 11426.1359 | 71297.7068 | 9251.9549 | 23129.8872 | 0 | 228192.2217 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-08 | 1250108.5478 | 0 | 1127720.71 | 510455.174 | 138352.1698 | 256658.504 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 510455.174 | 0 | 11436.2111 | 71469.2481 | 9278.3459 | 23195.8647 | 0 | 228230.904 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-09 | 1251525.2809 | 0 | 1127720.71 | 511559.2399 | 138626.1547 | 256697.1863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 511559.2399 | 0 | 11446.2863 | 71640.7895 | 9304.7368 | 23261.8421 | 0 | 228269.5863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-10 | 1252942.0141 | 0 | 1127720.71 | 512663.3057 | 138900.1397 | 256735.8686 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 512663.3057 | 0 | 11456.3615 | 71812.3308 | 9331.1278 | 23327.8195 | 0 | 228308.2686 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-11 | 1254358.7472 | 0 | 1127720.71 | 513767.3716 | 139174.1247 | 256774.551 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 513767.3716 | 0 | 11466.4367 | 71983.8722 | 9357.5188 | 23393.797 | 0 | 228346.951 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-12 | 1255775.4803 | 0 | 1127720.71 | 514871.4374 | 139448.1096 | 256813.2333 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 514871.4374 | 0 | 11476.5119 | 72155.4135 | 9383.9098 | 23459.7744 | 0 | 228385.6333 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-13 | 1257192.2135 | 0 | 1127720.71 | 515975.5032 | 139722.0946 | 256851.9156 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 515975.5032 | 0 | 11486.5871 | 72326.9549 | 9410.3008 | 23525.7519 | 0 | 228424.3156 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-14 | 1258608.9466 | 0 | 1127720.71 | 517079.5691 | 139996.0795 | 256890.598 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 517079.5691 | 0 | 11496.6623 | 72498.4962 | 9436.6917 | 23591.7293 | 0 | 228462.998 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-15 | 1260025.6797 | 0 | 1127720.71 | 518183.6349 | 140270.0645 | 256929.2803 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 518183.6349 | 0 | 11506.7374 | 72670.0376 | 9463.0827 | 23657.7068 | 0 | 228501.6803 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-16 | 1261442.4129 | 0 | 1127720.71 | 519287.7008 | 140544.0495 | 256967.9626 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 519287.7008 | 0 | 11516.8126 | 72841.5789 | 9489.4737 | 23723.6842 | 0 | 228540.3626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-17 | 1262859.146 | 0 | 1127720.71 | 520391.7666 | 140818.0344 | 257006.645 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 520391.7666 | 0 | 11526.8878 | 73013.1203 | 9515.8647 | 23789.6617 | 0 | 228579.045 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-18 | 1264275.8792 | 0 | 1127720.71 | 521495.8325 | 141092.0194 | 257045.3273 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 521495.8325 | 0 | 11536.963 | 73184.6617 | 9542.2556 | 23855.6391 | 0 | 228617.7273 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-19 | 1265692.6123 | 0 | 1127720.71 | 522599.8983 | 141366.0044 | 257084.0096 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 522599.8983 | 0 | 11547.0382 | 73356.203 | 9568.6466 | 23921.6165 | 0 | 228656.4096 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-20 | 1267109.3454 | 0 | 1127720.71 | 523703.9641 | 141639.9893 | 257122.692 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 523703.9641 | 0 | 11557.1134 | 73527.7444 | 9595.0376 | 23987.594 | 0 | 228695.092 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-21 | 1268526.0786 | 0 | 1127720.71 | 524808.03 | 141913.9743 | 257161.3743 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 524808.03 | 0 | 11567.1886 | 73699.2857 | 9621.4286 | 24053.5714 | 0 | 228733.7743 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-22 | 1269942.8117 | 0 | 1127720.71 | 525912.0958 | 142187.9592 | 257200.0566 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 525912.0958 | 0 | 11577.2638 | 73870.8271 | 9647.8195 | 24119.5489 | 0 | 228772.4566 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-23 | 1271359.5448 |  |  | 527016.1617 | 142461.9442 | 257238.7389 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 527016.1617 | 0 | 11587.3389 | 74042.3684 | 9674.2105 | 24185.5263 | 0 | 228811.1389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-24 | 1272776.278 |  |  | 528120.2275 | 142735.9292 | 257277.4213 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 528120.2275 | 0 | 11597.4141 | 74213.9098 | 9700.6015 | 24251.5038 | 0 | 228849.8213 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-25 | 1274193.0111 |  |  | 529224.2934 | 143009.9141 | 257316.1036 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 529224.2934 | 0 | 11607.4893 | 74385.4511 | 9726.9925 | 24317.4812 | 0 | 228888.5036 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-26 | 1275609.7443 |  |  | 530328.3592 | 143283.8991 | 257354.7859 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 530328.3592 | 0 | 11617.5645 | 74556.9925 | 9753.3835 | 24383.4586 | 0 | 228927.1859 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-27 | 1277026.4774 |  |  | 531432.4251 | 143557.8841 | 257393.4683 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 531432.4251 | 0 | 11627.6397 | 74728.5338 | 9779.7744 | 24449.4361 | 0 | 228965.8683 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-28 | 1278443.2105 |  |  | 532536.4909 | 143831.869 | 257432.1506 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 532536.4909 | 0 | 11637.7149 | 74900.0752 | 9806.1654 | 24515.4135 | 0 | 229004.5506 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-29 | 1279859.9437 |  |  | 533640.5567 | 144105.854 | 257470.8329 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 533640.5567 | 0 | 11647.7901 | 75071.6165 | 9832.5564 | 24581.391 | 0 | 229043.2329 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-30 | 1281276.6768 |  |  | 534744.6226 | 144379.8389 | 257509.5153 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 534744.6226 | 0 | 11657.8653 | 75243.1579 | 9858.9474 | 24647.3684 | 0 | 229081.9153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-31 | 1282693.4099 |  |  | 535848.6884 | 144653.8239 | 257548.1976 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 535848.6884 | 0 | 11667.9405 | 75414.6992 | 9885.3383 | 24713.3459 | 0 | 229120.5976 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-01 | 1284110.1431 |  |  | 536952.7543 | 144927.8089 | 257586.8799 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 536952.7543 | 0 | 11678.0156 | 75586.2406 | 9911.7293 | 24779.3233 | 0 | 229159.2799 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-02 | 1285526.8762 |  |  | 538056.8201 | 145201.7938 | 257625.5623 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 538056.8201 | 0 | 11688.0908 | 75757.782 | 9938.1203 | 24845.3008 | 0 | 229197.9623 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-03 | 1286943.6093 |  |  | 539160.886 | 145475.7788 | 257664.2446 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 539160.886 | 0 | 11698.166 | 75929.3233 | 9964.5113 | 24911.2782 | 0 | 229236.6446 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-04 | 1288360.3425 |  |  | 540264.9518 | 145749.7638 | 257702.9269 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 540264.9518 | 0 | 11708.2412 | 76100.8647 | 9990.9023 | 24977.2556 | 0 | 229275.3269 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-05 | 1289777.0756 |  |  | 541369.0177 | 146023.7487 | 257741.6092 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 541369.0177 | 0 | 11718.3164 | 76272.406 | 10017.2932 | 25043.2331 | 0 | 229314.0092 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-06 | 1291193.8088 |  |  | 542473.0835 | 146297.7337 | 257780.2916 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 542473.0835 | 0 | 11728.3916 | 76443.9474 | 10043.6842 | 25109.2105 | 0 | 229352.6916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-07 | 1292610.5419 |  |  | 543577.1493 | 146571.7186 | 257818.9739 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 543577.1493 | 0 | 11738.4668 | 76615.4887 | 10070.0752 | 25175.188 | 0 | 229391.3739 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-08 | 1294027.275 |  |  | 544681.2152 | 146845.7036 | 257857.6562 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 544681.2152 | 0 | 11748.542 | 76787.0301 | 10096.4662 | 25241.1654 | 0 | 229430.0562 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-09 | 1295444.0082 |  |  | 545785.281 | 147119.6886 | 257896.3386 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 545785.281 | 0 | 11758.6171 | 76958.5714 | 10122.8571 | 25307.1429 | 0 | 229468.7386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-10 | 1296860.7413 |  |  | 546889.3469 | 147393.6735 | 257935.0209 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 546889.3469 | 0 | 11768.6923 | 77130.1128 | 10149.2481 | 25373.1203 | 0 | 229507.4209 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-11 | 1298277.4744 |  |  | 547993.4127 | 147667.6585 | 257973.7032 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 547993.4127 | 0 | 11778.7675 | 77301.6541 | 10175.6391 | 25439.0977 | 0 | 229546.1032 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-12 | 1299694.2076 |  |  | 549097.4786 | 147941.6435 | 258012.3856 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 549097.4786 | 0 | 11788.8427 | 77473.1955 | 10202.0301 | 25505.0752 | 0 | 229584.7856 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-13 | 1301110.9407 |  |  | 550201.5444 | 148215.6284 | 258051.0679 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 550201.5444 | 0 | 11798.9179 | 77644.7368 | 10228.4211 | 25571.0526 | 0 | 229623.4679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-14 | 1302527.6739 |  |  | 551305.6103 | 148489.6134 | 258089.7502 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 551305.6103 | 0 | 11808.9931 | 77816.2782 | 10254.812 | 25637.0301 | 0 | 229662.1502 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-15 | 1303944.407 |  |  | 552409.6761 | 148763.5983 | 258128.4326 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 552409.6761 | 0 | 11819.0683 | 77987.8195 | 10281.203 | 25703.0075 | 0 | 229700.8326 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-16 | 1305361.1401 |  |  | 553513.7419 | 149037.5833 | 258167.1149 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 553513.7419 | 0 | 11829.1435 | 78159.3609 | 10307.594 | 25768.985 | 0 | 229739.5149 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-17 | 1306777.8733 |  |  | 554617.8078 | 149311.5683 | 258205.7972 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 554617.8078 | 0 | 11839.2186 | 78330.9023 | 10333.985 | 25834.9624 | 0 | 229778.1972 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-18 | 1308194.6064 |  |  | 555721.8736 | 149585.5532 | 258244.4795 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 555721.8736 | 0 | 11849.2938 | 78502.4436 | 10360.3759 | 25900.9398 | 0 | 229816.8795 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-19 | 1309611.3395 |  |  | 556825.9395 | 149859.5382 | 258283.1619 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 556825.9395 | 0 | 11859.369 | 78673.985 | 10386.7669 | 25966.9173 | 0 | 229855.5619 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-20 | 1311028.0727 |  |  | 557930.0053 | 150133.5232 | 258321.8442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 557930.0053 | 0 | 11869.4442 | 78845.5263 | 10413.1579 | 26032.8947 | 0 | 229894.2442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-21 | 1312444.8058 |  |  | 559034.0712 | 150407.5081 | 258360.5265 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 559034.0712 | 0 | 11879.5194 | 79017.0677 | 10439.5489 | 26098.8722 | 0 | 229932.9265 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-22 | 1313861.539 |  |  | 560138.137 | 150681.4931 | 258399.2089 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 560138.137 | 0 | 11889.5946 | 79188.609 | 10465.9398 | 26164.8496 | 0 | 229971.6089 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-23 | 1315278.2721 |  |  | 561242.2028 | 150955.478 | 258437.8912 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 561242.2028 | 0 | 11899.6698 | 79360.1504 | 10492.3308 | 26230.8271 | 0 | 230010.2912 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-24 | 1316695.0052 |  |  | 562346.2687 | 151229.463 | 258476.5735 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 562346.2687 | 0 | 11909.745 | 79531.6917 | 10518.7218 | 26296.8045 | 0 | 230048.9735 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-25 | 1318111.7384 |  |  | 563450.3345 | 151503.448 | 258515.2559 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 563450.3345 | 0 | 11919.8202 | 79703.2331 | 10545.1128 | 26362.782 | 0 | 230087.6559 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-26 | 1319528.4715 |  |  | 564554.4004 | 151777.4329 | 258553.9382 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 564554.4004 | 0 | 11929.8953 | 79874.7744 | 10571.5038 | 26428.7594 | 0 | 230126.3382 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-27 | 1320945.2046 |  |  | 565658.4662 | 152051.4179 | 258592.6205 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 565658.4662 | 0 | 11939.9705 | 80046.3158 | 10597.8947 | 26494.7368 | 0 | 230165.0205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-28 | 1322361.9378 |  |  | 566762.5321 | 152325.4029 | 258631.3029 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 566762.5321 | 0 | 11950.0457 | 80217.8571 | 10624.2857 | 26560.7143 | 0 | 230203.7029 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-29 | 1323778.6709 |  |  | 567866.5979 | 152599.3878 | 258669.9852 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 567866.5979 | 0 | 11960.1209 | 80389.3985 | 10650.6767 | 26626.6917 | 0 | 230242.3852 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-30 | 1325195.4041 |  |  | 568970.6638 | 152873.3728 | 258708.6675 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 568970.6638 | 0 | 11970.1961 | 80560.9398 | 10677.0677 | 26692.6692 | 0 | 230281.0675 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-01 | 1326612.1372 |  |  | 570074.7296 | 153147.3577 | 258747.3498 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 570074.7296 | 0 | 11980.2713 | 80732.4812 | 10703.4586 | 26758.6466 | 0 | 230319.7498 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-02 | 1328028.8703 |  |  | 571178.7954 | 153421.3427 | 258786.0322 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 571178.7954 | 0 | 11990.3465 | 80904.0226 | 10729.8496 | 26824.6241 | 0 | 230358.4322 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-03 | 1329445.6035 |  |  | 572282.8613 | 153695.3277 | 258824.7145 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 572282.8613 | 0 | 12000.4217 | 81075.5639 | 10756.2406 | 26890.6015 | 0 | 230397.1145 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-04 | 1330862.3366 |  |  | 573386.9271 | 153969.3126 | 258863.3968 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 573386.9271 | 0 | 12010.4968 | 81247.1053 | 10782.6316 | 26956.5789 | 0 | 230435.7968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-05 | 1332279.0697 |  |  | 574490.993 | 154243.2976 | 258902.0792 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 574490.993 | 0 | 12020.572 | 81418.6466 | 10809.0226 | 27022.5564 | 0 | 230474.4792 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-06 | 1333695.8029 |  |  | 575595.0588 | 154517.2826 | 258940.7615 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 575595.0588 | 0 | 12030.6472 | 81590.188 | 10835.4135 | 27088.5338 | 0 | 230513.1615 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-07 | 1335112.536 |  |  | 576699.1247 | 154791.2675 | 258979.4438 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 576699.1247 | 0 | 12040.7224 | 81761.7293 | 10861.8045 | 27154.5113 | 0 | 230551.8438 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-08 | 1336529.2692 |  |  | 577803.1905 | 155065.2525 | 259018.1262 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 577803.1905 | 0 | 12050.7976 | 81933.2707 | 10888.1955 | 27220.4887 | 0 | 230590.5262 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-09 | 1337946.0023 |  |  | 578907.2564 | 155339.2374 | 259056.8085 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 578907.2564 | 0 | 12060.8728 | 82104.812 | 10914.5865 | 27286.4662 | 0 | 230629.2085 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-10 | 1339362.7354 |  |  | 580011.3222 | 155613.2224 | 259095.4908 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 580011.3222 | 0 | 12070.948 | 82276.3534 | 10940.9774 | 27352.4436 | 0 | 230667.8908 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-11 | 1340779.4686 |  |  | 581115.388 | 155887.2074 | 259134.1732 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 581115.388 | 0 | 12081.0232 | 82447.8947 | 10967.3684 | 27418.4211 | 0 | 230706.5732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-12 | 1342196.2017 |  |  | 582219.4539 | 156161.1923 | 259172.8555 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 582219.4539 | 0 | 12091.0983 | 82619.4361 | 10993.7594 | 27484.3985 | 0 | 230745.2555 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-13 | 1343612.9348 |  |  | 583323.5197 | 156435.1773 | 259211.5378 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 583323.5197 | 0 | 12101.1735 | 82790.9774 | 11020.1504 | 27550.3759 | 0 | 230783.9378 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-14 | 1345029.668 |  |  | 584427.5856 | 156709.1623 | 259250.2202 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 584427.5856 | 0 | 12111.2487 | 82962.5188 | 11046.5414 | 27616.3534 | 0 | 230822.6202 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-15 | 1346446.4011 |  |  | 585531.6514 | 156983.1472 | 259288.9025 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 585531.6514 | 0 | 12121.3239 | 83134.0602 | 11072.9323 | 27682.3308 | 0 | 230861.3025 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-16 | 1347863.1343 |  |  | 586635.7173 | 157257.1322 | 259327.5848 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 586635.7173 | 0 | 12131.3991 | 83305.6015 | 11099.3233 | 27748.3083 | 0 | 230899.9848 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-17 | 1349279.8674 |  |  | 587739.7831 | 157531.1171 | 259366.2671 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 587739.7831 | 0 | 12141.4743 | 83477.1429 | 11125.7143 | 27814.2857 | 0 | 230938.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-18 | 1350696.6005 |  |  | 588843.849 | 157805.1021 | 259404.9495 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 588843.849 | 0 | 12151.5495 | 83648.6842 | 11152.1053 | 27880.2632 | 0 | 230977.3495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-19 | 1352113.3337 |  |  | 589947.9148 | 158079.0871 | 259443.6318 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 589947.9148 | 0 | 12161.6247 | 83820.2256 | 11178.4962 | 27946.2406 | 0 | 231016.0318 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-20 | 1353530.0668 |  |  | 591051.9806 | 158353.072 | 259482.3141 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 591051.9806 | 0 | 12171.6998 | 83991.7669 | 11204.8872 | 28012.218 | 0 | 231054.7141 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-21 | 1354946.7999 |  |  | 592156.0465 | 158627.057 | 259520.9965 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 592156.0465 | 0 | 12181.775 | 84163.3083 | 11231.2782 | 28078.1955 | 0 | 231093.3965 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-22 | 1356363.5331 |  |  | 593260.1123 | 158901.042 | 259559.6788 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 593260.1123 | 0 | 12191.8502 | 84334.8496 | 11257.6692 | 28144.1729 | 0 | 231132.0788 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-23 | 1357780.2662 |  |  | 594364.1782 | 159175.0269 | 259598.3611 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 594364.1782 | 0 | 12201.9254 | 84506.391 | 11284.0602 | 28210.1504 | 0 | 231170.7611 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-24 | 1359196.9994 |  |  | 595468.244 | 159449.0119 | 259637.0435 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 595468.244 | 0 | 12212.0006 | 84677.9323 | 11310.4511 | 28276.1278 | 0 | 231209.4435 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-25 | 1360613.7325 |  |  | 596572.3099 | 159722.9968 | 259675.7258 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 596572.3099 | 0 | 12222.0758 | 84849.4737 | 11336.8421 | 28342.1053 | 0 | 231248.1258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-26 | 1362030.4656 |  |  | 597676.3757 | 159996.9818 | 259714.4081 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 597676.3757 | 0 | 12232.151 | 85021.015 | 11363.2331 | 28408.0827 | 0 | 231286.8081 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-27 | 1363447.1988 |  |  | 598780.4415 | 160270.9668 | 259753.0905 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 598780.4415 | 0 | 12242.2262 | 85192.5564 | 11389.6241 | 28474.0602 | 0 | 231325.4905 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-28 | 1364863.9319 |  |  | 599884.5074 | 160544.9517 | 259791.7728 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 599884.5074 | 0 | 12252.3014 | 85364.0977 | 11416.015 | 28540.0376 | 0 | 231364.1728 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-29 | 1366280.665 |  |  | 600988.5732 | 160818.9367 | 259830.4551 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 600988.5732 | 0 | 12262.3765 | 85535.6391 | 11442.406 | 28606.015 | 0 | 231402.8551 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-30 | 1367697.3982 |  |  | 602092.6391 | 161092.9217 | 259869.1374 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 602092.6391 | 0 | 12272.4517 | 85707.1805 | 11468.797 | 28671.9925 | 0 | 231441.5374 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-31 | 1369114.1313 |  |  | 603196.7049 | 161366.9066 | 259907.8198 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 603196.7049 | 0 | 12282.5269 | 85878.7218 | 11495.188 | 28737.9699 | 0 | 231480.2198 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-01 | 1370530.8645 |  |  | 604300.7708 | 161640.8916 | 259946.5021 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 604300.7708 | 0 | 12292.6021 | 86050.2632 | 11521.5789 | 28803.9474 | 0 | 231518.9021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-02 | 1371947.5976 |  |  | 605404.8366 | 161914.8765 | 259985.1844 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 605404.8366 | 0 | 12302.6773 | 86221.8045 | 11547.9699 | 28869.9248 | 0 | 231557.5844 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-03 | 1373364.3307 |  |  | 606508.9025 | 162188.8615 | 260023.8668 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 606508.9025 | 0 | 12312.7525 | 86393.3459 | 11574.3609 | 28935.9023 | 0 | 231596.2668 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-04 | 1374781.0639 |  |  | 607612.9683 | 162462.8465 | 260062.5491 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 607612.9683 | 0 | 12322.8277 | 86564.8872 | 11600.7519 | 29001.8797 | 0 | 231634.9491 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-05 | 1376197.797 |  |  | 608717.0341 | 162736.8314 | 260101.2314 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 608717.0341 | 0 | 12332.9029 | 86736.4286 | 11627.1429 | 29067.8571 | 0 | 231673.6314 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-06 | 1377614.5301 |  |  | 609821.1 | 163010.8164 | 260139.9138 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 609821.1 | 0 | 12342.978 | 86907.9699 | 11653.5338 | 29133.8346 | 0 | 231712.3138 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-07 | 1379031.2633 |  |  | 610925.1658 | 163284.8014 | 260178.5961 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 610925.1658 | 0 | 12353.0532 | 87079.5113 | 11679.9248 | 29199.812 | 0 | 231750.9961 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-08 | 1380447.9964 |  |  | 612029.2317 | 163558.7863 | 260217.2784 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 612029.2317 | 0 | 12363.1284 | 87251.0526 | 11706.3158 | 29265.7895 | 0 | 231789.6784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-09 | 1381864.7296 |  |  | 613133.2975 | 163832.7713 | 260255.9608 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 613133.2975 | 0 | 12373.2036 | 87422.594 | 11732.7068 | 29331.7669 | 0 | 231828.3608 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-10 | 1383281.4627 |  |  | 614237.3634 | 164106.7562 | 260294.6431 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 614237.3634 | 0 | 12383.2788 | 87594.1353 | 11759.0977 | 29397.7444 | 0 | 231867.0431 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-11 | 1384698.1958 |  |  | 615341.4292 | 164380.7412 | 260333.3254 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 615341.4292 | 0 | 12393.354 | 87765.6767 | 11785.4887 | 29463.7218 | 0 | 231905.7254 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-12 | 1386114.929 |  |  | 616445.4951 | 164654.7262 | 260372.0077 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 616445.4951 | 0 | 12403.4292 | 87937.218 | 11811.8797 | 29529.6992 | 0 | 231944.4077 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-13 | 1387531.6621 |  |  | 617549.5609 | 164928.7111 | 260410.6901 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 617549.5609 | 0 | 12413.5044 | 88108.7594 | 11838.2707 | 29595.6767 | 0 | 231983.0901 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-14 | 1388948.3952 |  |  | 618653.6267 | 165202.6961 | 260449.3724 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 618653.6267 | 0 | 12423.5795 | 88280.3008 | 11864.6617 | 29661.6541 | 0 | 232021.7724 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-15 | 1390365.1284 |  |  | 619757.6926 | 165476.6811 | 260488.0547 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 619757.6926 | 0 | 12433.6547 | 88451.8421 | 11891.0526 | 29727.6316 | 0 | 232060.4547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-16 | 1391781.8615 |  |  | 620861.7584 | 165750.666 | 260526.7371 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 620861.7584 | 0 | 12443.7299 | 88623.3835 | 11917.4436 | 29793.609 | 0 | 232099.1371 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-17 | 1393198.5947 |  |  | 621965.8243 | 166024.651 | 260565.4194 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 621965.8243 | 0 | 12453.8051 | 88794.9248 | 11943.8346 | 29859.5865 | 0 | 232137.8194 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-18 | 1394615.3278 |  |  | 623069.8901 | 166298.6359 | 260604.1017 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 623069.8901 | 0 | 12463.8803 | 88966.4662 | 11970.2256 | 29925.5639 | 0 | 232176.5017 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-19 | 1396032.0609 |  |  | 624173.956 | 166572.6209 | 260642.7841 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 624173.956 | 0 | 12473.9555 | 89138.0075 | 11996.6165 | 29991.5414 | 0 | 232215.1841 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-20 | 1397448.7941 |  |  | 625278.0218 | 166846.6059 | 260681.4664 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 625278.0218 | 0 | 12484.0307 | 89309.5489 | 12023.0075 | 30057.5188 | 0 | 232253.8664 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-21 | 1398865.5272 |  |  | 626382.0877 | 167120.5908 | 260720.1487 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 626382.0877 | 0 | 12494.1059 | 89481.0902 | 12049.3985 | 30123.4962 | 0 | 232292.5487 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-22 | 1400282.2603 |  |  | 627486.1535 | 167394.5758 | 260758.8311 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 627486.1535 | 0 | 12504.1811 | 89652.6316 | 12075.7895 | 30189.4737 | 0 | 232331.2311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-23 | 1401698.9935 |  |  | 628590.2193 | 167668.5608 | 260797.5134 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 628590.2193 | 0 | 12514.2562 | 89824.1729 | 12102.1805 | 30255.4511 | 0 | 232369.9134 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-24 | 1403115.7266 |  |  | 629694.2852 | 167942.5457 | 260836.1957 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 629694.2852 | 0 | 12524.3314 | 89995.7143 | 12128.5714 | 30321.4286 | 0 | 232408.5957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-25 | 1404532.4598 |  |  | 630798.351 | 168216.5307 | 260874.878 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 630798.351 | 0 | 12534.4066 | 90167.2556 | 12154.9624 | 30387.406 | 0 | 232447.278 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-26 | 1405949.1929 |  |  | 631902.4169 | 168490.5156 | 260913.5604 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 631902.4169 | 0 | 12544.4818 | 90338.797 | 12181.3534 | 30453.3835 | 0 | 232485.9604 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-27 | 1407365.926 |  |  | 633006.4827 | 168764.5006 | 260952.2427 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 633006.4827 | 0 | 12554.557 | 90510.3383 | 12207.7444 | 30519.3609 | 0 | 232524.6427 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-28 | 1408782.6592 |  |  | 634110.5486 | 169038.4856 | 260990.925 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 634110.5486 | 0 | 12564.6322 | 90681.8797 | 12234.1353 | 30585.3383 | 0 | 232563.325 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-29 | 1410199.3923 |  |  | 635214.6144 | 169312.4705 | 261029.6074 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 635214.6144 | 0 | 12574.7074 | 90853.4211 | 12260.5263 | 30651.3158 | 0 | 232602.0074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-30 | 1411616.1254 |  |  | 636318.6803 | 169586.4555 | 261068.2897 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 636318.6803 | 0 | 12584.7826 | 91024.9624 | 12286.9173 | 30717.2932 | 0 | 232640.6897 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-01 | 1413032.8586 |  |  | 637422.7461 | 169860.4405 | 261106.972 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 637422.7461 | 0 | 12594.8577 | 91196.5038 | 12313.3083 | 30783.2707 | 0 | 232679.372 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-02 | 1414449.5917 |  |  | 638526.8119 | 170134.4254 | 261145.6544 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 638526.8119 | 0 | 12604.9329 | 91368.0451 | 12339.6992 | 30849.2481 | 0 | 232718.0544 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-03 | 1415866.3249 |  |  | 639630.8778 | 170408.4104 | 261184.3367 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 639630.8778 | 0 | 12615.0081 | 91539.5865 | 12366.0902 | 30915.2256 | 0 | 232756.7367 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-04 | 1417283.058 |  |  | 640734.9436 | 170682.3953 | 261223.019 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 640734.9436 | 0 | 12625.0833 | 91711.1278 | 12392.4812 | 30981.203 | 0 | 232795.419 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-05 | 1418699.7911 |  |  | 641839.0095 | 170956.3803 | 261261.7014 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 641839.0095 | 0 | 12635.1585 | 91882.6692 | 12418.8722 | 31047.1805 | 0 | 232834.1014 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-06 | 1420116.5243 |  |  | 642943.0753 | 171230.3653 | 261300.3837 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 642943.0753 | 0 | 12645.2337 | 92054.2105 | 12445.2632 | 31113.1579 | 0 | 232872.7837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-07 | 1421533.2574 |  |  | 644047.1412 | 171504.3502 | 261339.066 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 644047.1412 | 0 | 12655.3089 | 92225.7519 | 12471.6541 | 31179.1353 | 0 | 232911.466 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-08 | 1422949.9905 |  |  | 645151.207 | 171778.3352 | 261377.7483 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 645151.207 | 0 | 12665.3841 | 92397.2932 | 12498.0451 | 31245.1128 | 0 | 232950.1483 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-09 | 1424366.7237 |  |  | 646255.2728 | 172052.3202 | 261416.4307 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 646255.2728 | 0 | 12675.4592 | 92568.8346 | 12524.4361 | 31311.0902 | 0 | 232988.8307 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-10 | 1425783.4568 |  |  | 647359.3387 | 172326.3051 | 261455.113 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 647359.3387 | 0 | 12685.5344 | 92740.3759 | 12550.8271 | 31377.0677 | 0 | 233027.513 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-11 | 1427200.1899 |  |  | 648463.4045 | 172600.2901 | 261493.7953 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 648463.4045 | 0 | 12695.6096 | 92911.9173 | 12577.218 | 31443.0451 | 0 | 233066.1953 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-12 | 1428616.9231 |  |  | 649567.4704 | 172874.275 | 261532.4777 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 649567.4704 | 0 | 12705.6848 | 93083.4586 | 12603.609 | 31509.0226 | 0 | 233104.8777 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-13 | 1430033.6562 |  |  | 650671.5362 | 173148.26 | 261571.16 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 650671.5362 | 0 | 12715.76 | 93255 | 12630 | 31575 | 0 | 233143.56 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-14 | 1431450.3894 |  |  | 651775.6021 | 173422.245 | 261609.8423 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 651775.6021 | 0 | 12725.8352 | 93426.5414 | 12656.391 | 31640.9774 | 0 | 233182.2423 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-15 | 1432867.1225 |  |  | 652879.6679 | 173696.2299 | 261648.5247 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 652879.6679 | 0 | 12735.9104 | 93598.0827 | 12682.782 | 31706.9549 | 0 | 233220.9247 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-16 | 1434283.8556 |  |  | 653983.7338 | 173970.2149 | 261687.207 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 653983.7338 | 0 | 12745.9856 | 93769.6241 | 12709.1729 | 31772.9323 | 0 | 233259.607 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-17 | 1435700.5888 |  |  | 655087.7996 | 174244.1998 | 261725.8893 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 655087.7996 | 0 | 12756.0608 | 93941.1654 | 12735.5639 | 31838.9098 | 0 | 233298.2893 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-18 | 1437117.3219 |  |  | 656191.8654 | 174518.1848 | 261764.5717 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 656191.8654 | 0 | 12766.1359 | 94112.7068 | 12761.9549 | 31904.8872 | 0 | 233336.9717 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-19 | 1438534.055 |  |  | 657295.9313 | 174792.1698 | 261803.254 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 657295.9313 | 0 | 12776.2111 | 94284.2481 | 12788.3459 | 31970.8647 | 0 | 233375.654 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-20 | 1439950.7882 |  |  | 658399.9971 | 175066.1547 | 261841.9363 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 658399.9971 | 0 | 12786.2863 | 94455.7895 | 12814.7368 | 32036.8421 | 0 | 233414.3363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-21 | 1441367.5213 |  |  | 659504.063 | 175340.1397 | 261880.6186 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 659504.063 | 0 | 12796.3615 | 94627.3308 | 12841.1278 | 32102.8195 | 0 | 233453.0186 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-22 | 1442784.2545 |  |  | 660608.1288 | 175614.1247 | 261919.301 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 660608.1288 | 0 | 12806.4367 | 94798.8722 | 12867.5188 | 32168.797 | 0 | 233491.701 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-23 | 1444200.9876 |  |  | 661712.1947 | 175888.1096 | 261957.9833 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 661712.1947 | 0 | 12816.5119 | 94970.4135 | 12893.9098 | 32234.7744 | 0 | 233530.3833 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-24 | 1445617.7207 |  |  | 662816.2605 | 176162.0946 | 261996.6656 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 662816.2605 | 0 | 12826.5871 | 95141.9549 | 12920.3008 | 32300.7519 | 0 | 233569.0656 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-25 | 1447034.4539 |  |  | 663920.3264 | 176436.0795 | 262035.348 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 663920.3264 | 0 | 12836.6623 | 95313.4962 | 12946.6917 | 32366.7293 | 0 | 233607.748 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-26 | 1448451.187 |  |  | 665024.3922 | 176710.0645 | 262074.0303 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 665024.3922 | 0 | 12846.7374 | 95485.0376 | 12973.0827 | 32432.7068 | 0 | 233646.4303 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-27 | 1449867.9201 |  |  | 666128.458 | 176984.0495 | 262112.7126 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 666128.458 | 0 | 12856.8126 | 95656.5789 | 12999.4737 | 32498.6842 | 0 | 233685.1126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-28 | 1451284.6533 |  |  | 667232.5239 | 177258.0344 | 262151.395 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 667232.5239 | 0 | 12866.8878 | 95828.1203 | 13025.8647 | 32564.6617 | 0 | 233723.795 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-29 | 1452701.3864 |  |  | 668336.5897 | 177532.0194 | 262190.0773 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 668336.5897 | 0 | 12876.963 | 95999.6617 | 13052.2556 | 32630.6391 | 0 | 233762.4773 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-30 | 1454118.1196 |  |  | 669440.6556 | 177806.0044 | 262228.7596 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 669440.6556 | 0 | 12887.0382 | 96171.203 | 13078.6466 | 32696.6165 | 0 | 233801.1596 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-31 | 1455534.8527 |  |  | 670544.7214 | 178079.9893 | 262267.442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 670544.7214 | 0 | 12897.1134 | 96342.7444 | 13105.0376 | 32762.594 | 0 | 233839.842 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-01 | 1456951.5858 |  |  | 671648.7873 | 178353.9743 | 262306.1243 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 671648.7873 | 0 | 12907.1886 | 96514.2857 | 13131.4286 | 32828.5714 | 0 | 233878.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-02 | 1458368.319 |  |  | 672752.8531 | 178627.9592 | 262344.8066 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 672752.8531 | 0 | 12917.2638 | 96685.8271 | 13157.8195 | 32894.5489 | 0 | 233917.2066 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-03 | 1459785.0521 |  |  | 673856.919 | 178901.9442 | 262383.4889 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 673856.919 | 0 | 12927.3389 | 96857.3684 | 13184.2105 | 32960.5263 | 0 | 233955.8889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-04 | 1461201.7852 |  |  | 674960.9848 | 179175.9292 | 262422.1713 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 674960.9848 | 0 | 12937.4141 | 97028.9098 | 13210.6015 | 33026.5038 | 0 | 233994.5713 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-05 | 1462618.5184 |  |  | 676065.0506 | 179449.9141 | 262460.8536 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 676065.0506 | 0 | 12947.4893 | 97200.4511 | 13236.9925 | 33092.4812 | 0 | 234033.2536 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-06 | 1464035.2515 |  |  | 677169.1165 | 179723.8991 | 262499.5359 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 677169.1165 | 0 | 12957.5645 | 97371.9925 | 13263.3835 | 33158.4586 | 0 | 234071.9359 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-07 | 1465451.9847 |  |  | 678273.1823 | 179997.8841 | 262538.2183 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 678273.1823 | 0 | 12967.6397 | 97543.5338 | 13289.7744 | 33224.4361 | 0 | 234110.6183 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-08 | 1466868.7178 |  |  | 679377.2482 | 180271.869 | 262576.9006 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 679377.2482 | 0 | 12977.7149 | 97715.0752 | 13316.1654 | 33290.4135 | 0 | 234149.3006 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-09 | 1468285.4509 |  |  | 680481.314 | 180545.854 | 262615.5829 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 680481.314 | 0 | 12987.7901 | 97886.6165 | 13342.5564 | 33356.391 | 0 | 234187.9829 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-10 | 1469702.1841 |  |  | 681585.3799 | 180819.8389 | 262654.2653 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 681585.3799 | 0 | 12997.8653 | 98058.1579 | 13368.9474 | 33422.3684 | 0 | 234226.6653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-11 | 1471118.9172 |  |  | 682689.4457 | 181093.8239 | 262692.9476 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 682689.4457 | 0 | 13007.9405 | 98229.6992 | 13395.3383 | 33488.3459 | 0 | 234265.3476 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-12 | 1472535.6503 |  |  | 683793.5115 | 181367.8089 | 262731.6299 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 683793.5115 | 0 | 13018.0156 | 98401.2406 | 13421.7293 | 33554.3233 | 0 | 234304.0299 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-13 | 1473952.3835 |  |  | 684897.5774 | 181641.7938 | 262770.3123 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 684897.5774 | 0 | 13028.0908 | 98572.782 | 13448.1203 | 33620.3008 | 0 | 234342.7123 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-14 | 1475369.1166 |  |  | 686001.6432 | 181915.7788 | 262808.9946 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 686001.6432 | 0 | 13038.166 | 98744.3233 | 13474.5113 | 33686.2782 | 0 | 234381.3946 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-15 | 1476785.8498 |  |  | 687105.7091 | 182189.7638 | 262847.6769 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 687105.7091 | 0 | 13048.2412 | 98915.8647 | 13500.9023 | 33752.2556 | 0 | 234420.0769 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-16 | 1478202.5829 |  |  | 688209.7749 | 182463.7487 | 262886.3592 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 688209.7749 | 0 | 13058.3164 | 99087.406 | 13527.2932 | 33818.2331 | 0 | 234458.7592 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-17 | 1479619.316 |  |  | 689313.8408 | 182737.7337 | 262925.0416 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 689313.8408 | 0 | 13068.3916 | 99258.9474 | 13553.6842 | 33884.2105 | 0 | 234497.4416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-18 | 1481036.0492 |  |  | 690417.9066 | 183011.7186 | 262963.7239 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 690417.9066 | 0 | 13078.4668 | 99430.4887 | 13580.0752 | 33950.188 | 0 | 234536.1239 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-19 | 1482452.7823 |  |  | 691521.9725 | 183285.7036 | 263002.4062 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 691521.9725 | 0 | 13088.542 | 99602.0301 | 13606.4662 | 34016.1654 | 0 | 234574.8062 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-20 | 1483869.5154 |  |  | 692626.0383 | 183559.6886 | 263041.0886 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 692626.0383 | 0 | 13098.6171 | 99773.5714 | 13632.8571 | 34082.1429 | 0 | 234613.4886 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-21 | 1485286.2486 |  |  | 693730.1041 | 183833.6735 | 263079.7709 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 693730.1041 | 0 | 13108.6923 | 99945.1128 | 13659.2481 | 34148.1203 | 0 | 234652.1709 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-22 | 1486702.9817 |  |  | 694834.17 | 184107.6585 | 263118.4532 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 694834.17 | 0 | 13118.7675 | 100116.6541 | 13685.6391 | 34214.0977 | 0 | 234690.8532 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-23 | 1488119.7149 |  |  | 695938.2358 | 184381.6435 | 263157.1356 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 695938.2358 | 0 | 13128.8427 | 100288.1955 | 13712.0301 | 34280.0752 | 0 | 234729.5356 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-24 | 1489536.448 |  |  | 697042.3017 | 184655.6284 | 263195.8179 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 697042.3017 | 0 | 13138.9179 | 100459.7368 | 13738.4211 | 34346.0526 | 0 | 234768.2179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-25 | 1490953.1811 |  |  | 698146.3675 | 184929.6134 | 263234.5002 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 698146.3675 | 0 | 13148.9931 | 100631.2782 | 13764.812 | 34412.0301 | 0 | 234806.9002 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-26 | 1492369.9143 |  |  | 699250.4334 | 185203.5983 | 263273.1826 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 699250.4334 | 0 | 13159.0683 | 100802.8195 | 13791.203 | 34478.0075 | 0 | 234845.5826 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-27 | 1493786.6474 |  |  | 700354.4992 | 185477.5833 | 263311.8649 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 700354.4992 | 0 | 13169.1435 | 100974.3609 | 13817.594 | 34543.985 | 0 | 234884.2649 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-28 | 1495203.3805 |  |  | 701458.5651 | 185751.5683 | 263350.5472 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 701458.5651 | 0 | 13179.2186 | 101145.9023 | 13843.985 | 34609.9624 | 0 | 234922.9472 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-29 | 1496620.1137 |  |  | 702562.6309 | 186025.5532 | 263389.2295 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 702562.6309 | 0 | 13189.2938 | 101317.4436 | 13870.3759 | 34675.9398 | 0 | 234961.6295 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-30 | 1498036.8468 |  |  | 703666.6967 | 186299.5382 | 263427.9119 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 703666.6967 | 0 | 13199.369 | 101488.985 | 13896.7669 | 34741.9173 | 0 | 235000.3119 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-31 | 1499453.58 |  |  | 704770.7626 | 186573.5232 | 263466.5942 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 704770.7626 | 0 | 13209.4442 | 101660.5263 | 13923.1579 | 34807.8947 | 0 | 235038.9942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-01 | 1500870.3131 |  |  | 705874.8284 | 186847.5081 | 263505.2765 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 705874.8284 | 0 | 13219.5194 | 101832.0677 | 13949.5489 | 34873.8722 | 0 | 235077.6765 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-02 | 1502287.0462 |  |  | 706978.8943 | 187121.4931 | 263543.9589 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 706978.8943 | 0 | 13229.5946 | 102003.609 | 13975.9398 | 34939.8496 | 0 | 235116.3589 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-03 | 1503703.7794 |  |  | 708082.9601 | 187395.478 | 263582.6412 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 708082.9601 | 0 | 13239.6698 | 102175.1504 | 14002.3308 | 35005.8271 | 0 | 235155.0412 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-04 | 1505120.5125 |  |  | 709187.026 | 187669.463 | 263621.3235 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 709187.026 | 0 | 13249.745 | 102346.6917 | 14028.7218 | 35071.8045 | 0 | 235193.7235 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-05 | 1506537.2456 |  |  | 710291.0918 | 187943.448 | 263660.0059 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 710291.0918 | 0 | 13259.8202 | 102518.2331 | 14055.1128 | 35137.782 | 0 | 235232.4059 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-06 | 1507953.9788 |  |  | 711395.1577 | 188217.4329 | 263698.6882 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 711395.1577 | 0 | 13269.8953 | 102689.7744 | 14081.5038 | 35203.7594 | 0 | 235271.0882 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-07 | 1509370.7119 |  |  | 712499.2235 | 188491.4179 | 263737.3705 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 712499.2235 | 0 | 13279.9705 | 102861.3158 | 14107.8947 | 35269.7368 | 0 | 235309.7705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-08 | 1510787.4451 |  |  | 713603.2893 | 188765.4029 | 263776.0529 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 713603.2893 | 0 | 13290.0457 | 103032.8571 | 14134.2857 | 35335.7143 | 0 | 235348.4529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-09 | 1512204.1782 |  |  | 714707.3552 | 189039.3878 | 263814.7352 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 714707.3552 | 0 | 13300.1209 | 103204.3985 | 14160.6767 | 35401.6917 | 0 | 235387.1352 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-10 | 1513620.9113 |  |  | 715811.421 | 189313.3728 | 263853.4175 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 715811.421 | 0 | 13310.1961 | 103375.9398 | 14187.0677 | 35467.6692 | 0 | 235425.8175 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-11 | 1515037.6445 |  |  | 716915.4869 | 189587.3577 | 263892.0998 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 716915.4869 | 0 | 13320.2713 | 103547.4812 | 14213.4586 | 35533.6466 | 0 | 235464.4998 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-12 | 1516454.3776 |  |  | 718019.5527 | 189861.3427 | 263930.7822 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 718019.5527 | 0 | 13330.3465 | 103719.0226 | 14239.8496 | 35599.6241 | 0 | 235503.1822 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-13 | 1517871.1107 |  |  | 719123.6186 | 190135.3277 | 263969.4645 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 719123.6186 | 0 | 13340.4217 | 103890.5639 | 14266.2406 | 35665.6015 | 0 | 235541.8645 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-14 | 1519287.8439 |  |  | 720227.6844 | 190409.3126 | 264008.1468 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 720227.6844 | 0 | 13350.4968 | 104062.1053 | 14292.6316 | 35731.5789 | 0 | 235580.5468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-15 | 1520704.577 |  |  | 721331.7502 | 190683.2976 | 264046.8292 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 721331.7502 | 0 | 13360.572 | 104233.6466 | 14319.0226 | 35797.5564 | 0 | 235619.2292 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-16 | 1522121.3102 |  |  | 722435.8161 | 190957.2826 | 264085.5115 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 722435.8161 | 0 | 13370.6472 | 104405.188 | 14345.4135 | 35863.5338 | 0 | 235657.9115 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-17 | 1523538.0433 |  |  | 723539.8819 | 191231.2675 | 264124.1938 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 723539.8819 | 0 | 13380.7224 | 104576.7293 | 14371.8045 | 35929.5113 | 0 | 235696.5938 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-18 | 1524954.7764 |  |  | 724643.9478 | 191505.2525 | 264162.8762 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 724643.9478 | 0 | 13390.7976 | 104748.2707 | 14398.1955 | 35995.4887 | 0 | 235735.2762 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-19 | 1526371.5096 |  |  | 725748.0136 | 191779.2374 | 264201.5585 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 725748.0136 | 0 | 13400.8728 | 104919.812 | 14424.5865 | 36061.4662 | 0 | 235773.9585 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-20 | 1527788.2427 |  |  | 726852.0795 | 192053.2224 | 264240.2408 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 726852.0795 | 0 | 13410.948 | 105091.3534 | 14450.9774 | 36127.4436 | 0 | 235812.6408 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-21 | 1529204.9758 |  |  | 727956.1453 | 192327.2074 | 264278.9232 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 727956.1453 | 0 | 13421.0232 | 105262.8947 | 14477.3684 | 36193.4211 | 0 | 235851.3232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-22 | 1530621.709 |  |  | 729060.2112 | 192601.1923 | 264317.6055 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 729060.2112 | 0 | 13431.0983 | 105434.4361 | 14503.7594 | 36259.3985 | 0 | 235890.0055 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-23 | 1532038.4421 |  |  | 730164.277 | 192875.1773 | 264356.2878 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 730164.277 | 0 | 13441.1735 | 105605.9774 | 14530.1504 | 36325.3759 | 0 | 235928.6878 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-24 | 1533455.1753 |  |  | 731268.3428 | 193149.1623 | 264394.9702 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 731268.3428 | 0 | 13451.2487 | 105777.5188 | 14556.5414 | 36391.3534 | 0 | 235967.3702 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-25 | 1534871.9084 |  |  | 732372.4087 | 193423.1472 | 264433.6525 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 732372.4087 | 0 | 13461.3239 | 105949.0602 | 14582.9323 | 36457.3308 | 0 | 236006.0525 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-26 | 1536288.6415 |  |  | 733476.4745 | 193697.1322 | 264472.3348 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 733476.4745 | 0 | 13471.3991 | 106120.6015 | 14609.3233 | 36523.3083 | 0 | 236044.7348 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-27 | 1537705.3747 |  |  | 734580.5404 | 193971.1171 | 264511.0171 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 734580.5404 | 0 | 13481.4743 | 106292.1429 | 14635.7143 | 36589.2857 | 0 | 236083.4171 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-28 | 1539122.1078 |  |  | 735684.6062 | 194245.1021 | 264549.6995 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 735684.6062 | 0 | 13491.5495 | 106463.6842 | 14662.1053 | 36655.2632 | 0 | 236122.0995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-29 | 1540538.8409 |  |  | 736788.6721 | 194519.0871 | 264588.3818 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 736788.6721 | 0 | 13501.6247 | 106635.2256 | 14688.4962 | 36721.2406 | 0 | 236160.7818 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-30 | 1541955.5741 |  |  | 737892.7379 | 194793.072 | 264627.0641 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 737892.7379 | 0 | 13511.6998 | 106806.7669 | 14714.8872 | 36787.218 | 0 | 236199.4641 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-01 | 1543372.3072 |  |  | 738996.8038 | 195067.057 | 264665.7465 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 738996.8038 | 0 | 13521.775 | 106978.3083 | 14741.2782 | 36853.1955 | 0 | 236238.1465 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-02 | 1544789.0404 |  |  | 740100.8696 | 195341.042 | 264704.4288 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 740100.8696 | 0 | 13531.8502 | 107149.8496 | 14767.6692 | 36919.1729 | 0 | 236276.8288 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-03 | 1546205.7735 |  |  | 741204.9354 | 195615.0269 | 264743.1111 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 741204.9354 | 0 | 13541.9254 | 107321.391 | 14794.0602 | 36985.1504 | 0 | 236315.5111 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-04 | 1547622.5066 |  |  | 742309.0013 | 195889.0119 | 264781.7935 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 742309.0013 | 0 | 13552.0006 | 107492.9323 | 14820.4511 | 37051.1278 | 0 | 236354.1935 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-05 | 1549039.2398 |  |  | 743413.0671 | 196162.9968 | 264820.4758 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 743413.0671 | 0 | 13562.0758 | 107664.4737 | 14846.8421 | 37117.1053 | 0 | 236392.8758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-06 | 1550455.9729 |  |  | 744517.133 | 196436.9818 | 264859.1581 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 744517.133 | 0 | 13572.151 | 107836.015 | 14873.2331 | 37183.0827 | 0 | 236431.5581 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-07 | 1551872.706 |  |  | 745621.1988 | 196710.9668 | 264897.8405 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 745621.1988 | 0 | 13582.2262 | 108007.5564 | 14899.6241 | 37249.0602 | 0 | 236470.2405 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-08 | 1553289.4392 |  |  | 746725.2647 | 196984.9517 | 264936.5228 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 746725.2647 | 0 | 13592.3014 | 108179.0977 | 14926.015 | 37315.0376 | 0 | 236508.9228 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-09 | 1554706.1723 |  |  | 747829.3305 | 197258.9367 | 264975.2051 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 747829.3305 | 0 | 13602.3765 | 108350.6391 | 14952.406 | 37381.015 | 0 | 236547.6051 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-10 | 1556122.9055 |  |  | 748933.3964 | 197532.9217 | 265013.8874 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 748933.3964 | 0 | 13612.4517 | 108522.1805 | 14978.797 | 37446.9925 | 0 | 236586.2874 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-11 | 1557539.6386 |  |  | 750037.4622 | 197806.9066 | 265052.5698 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 750037.4622 | 0 | 13622.5269 | 108693.7218 | 15005.188 | 37512.9699 | 0 | 236624.9698 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-12 | 1558956.3717 |  |  | 751141.528 | 198080.8916 | 265091.2521 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 751141.528 | 0 | 13632.6021 | 108865.2632 | 15031.5789 | 37578.9474 | 0 | 236663.6521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-13 | 1560373.1049 |  |  | 752245.5939 | 198354.8765 | 265129.9344 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 752245.5939 | 0 | 13642.6773 | 109036.8045 | 15057.9699 | 37644.9248 | 0 | 236702.3344 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-14 | 1561789.838 |  |  | 753349.6597 | 198628.8615 | 265168.6168 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 753349.6597 | 0 | 13652.7525 | 109208.3459 | 15084.3609 | 37710.9023 | 0 | 236741.0168 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-15 | 1563206.5711 |  |  | 754453.7256 | 198902.8465 | 265207.2991 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 754453.7256 | 0 | 13662.8277 | 109379.8872 | 15110.7519 | 37776.8797 | 0 | 236779.6991 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-16 | 1564623.3043 |  |  | 755557.7914 | 199176.8314 | 265245.9814 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 755557.7914 | 0 | 13672.9029 | 109551.4286 | 15137.1429 | 37842.8571 | 0 | 236818.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-17 | 1566040.0374 |  |  | 756661.8573 | 199450.8164 | 265284.6638 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 756661.8573 | 0 | 13682.978 | 109722.9699 | 15163.5338 | 37908.8346 | 0 | 236857.0638 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-18 | 1567456.7705 |  |  | 757765.9231 | 199724.8014 | 265323.3461 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 757765.9231 | 0 | 13693.0532 | 109894.5113 | 15189.9248 | 37974.812 | 0 | 236895.7461 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-19 | 1568873.5037 |  |  | 758869.989 | 199998.7863 | 265362.0284 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 758869.989 | 0 | 13703.1284 | 110066.0526 | 15216.3158 | 38040.7895 | 0 | 236934.4284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-20 | 1570290.2368 |  |  | 759974.0548 | 200272.7713 | 265400.7108 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 759974.0548 | 0 | 13713.2036 | 110237.594 | 15242.7068 | 38106.7669 | 0 | 236973.1108 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-21 | 1571706.97 |  |  | 761078.1206 | 200546.7562 | 265439.3931 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 761078.1206 | 0 | 13723.2788 | 110409.1353 | 15269.0977 | 38172.7444 | 0 | 237011.7931 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-22 | 1573123.7031 |  |  | 762182.1865 | 200820.7412 | 265478.0754 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 762182.1865 | 0 | 13733.354 | 110580.6767 | 15295.4887 | 38238.7218 | 0 | 237050.4754 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-23 | 1574540.4362 |  |  | 763286.2523 | 201094.7262 | 265516.7577 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 763286.2523 | 0 | 13743.4292 | 110752.218 | 15321.8797 | 38304.6992 | 0 | 237089.1577 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-24 | 1575957.1694 |  |  | 764390.3182 | 201368.7111 | 265555.4401 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 764390.3182 | 0 | 13753.5044 | 110923.7594 | 15348.2707 | 38370.6767 | 0 | 237127.8401 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-25 | 1577373.9025 |  |  | 765494.384 | 201642.6961 | 265594.1224 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 765494.384 | 0 | 13763.5795 | 111095.3008 | 15374.6617 | 38436.6541 | 0 | 237166.5224 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-26 | 1578790.6356 |  |  | 766598.4499 | 201916.6811 | 265632.8047 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 766598.4499 | 0 | 13773.6547 | 111266.8421 | 15401.0526 | 38502.6316 | 0 | 237205.2047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-27 | 1580207.3688 |  |  | 767702.5157 | 202190.666 | 265671.4871 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 767702.5157 | 0 | 13783.7299 | 111438.3835 | 15427.4436 | 38568.609 | 0 | 237243.8871 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-28 | 1581624.1019 |  |  | 768806.5815 | 202464.651 | 265710.1694 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 768806.5815 | 0 | 13793.8051 | 111609.9248 | 15453.8346 | 38634.5865 | 0 | 237282.5694 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-29 | 1583040.8351 |  |  | 769910.6474 | 202738.6359 | 265748.8517 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 769910.6474 | 0 | 13803.8803 | 111781.4662 | 15480.2256 | 38700.5639 | 0 | 237321.2517 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-30 | 1584457.5682 |  |  | 771014.7132 | 203012.6209 | 265787.5341 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 771014.7132 | 0 | 13813.9555 | 111953.0075 | 15506.6165 | 38766.5414 | 0 | 237359.9341 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-10-31 | 1585874.3013 |  |  | 772118.7791 | 203286.6059 | 265826.2164 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 772118.7791 | 0 | 13824.0307 | 112124.5489 | 15533.0075 | 38832.5188 | 0 | 237398.6164 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-01 | 1587291.0345 |  |  | 773222.8449 | 203560.5908 | 265864.8987 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 773222.8449 | 0 | 13834.1059 | 112296.0902 | 15559.3985 | 38898.4962 | 0 | 237437.2987 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-02 | 1588707.7676 |  |  | 774326.9108 | 203834.5758 | 265903.5811 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 774326.9108 | 0 | 13844.1811 | 112467.6316 | 15585.7895 | 38964.4737 | 0 | 237475.9811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-03 | 1590124.5007 |  |  | 775430.9766 | 204108.5608 | 265942.2634 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 775430.9766 | 0 | 13854.2562 | 112639.1729 | 15612.1805 | 39030.4511 | 0 | 237514.6634 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-04 | 1591541.2339 |  |  | 776535.0425 | 204382.5457 | 265980.9457 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 776535.0425 | 0 | 13864.3314 | 112810.7143 | 15638.5714 | 39096.4286 | 0 | 237553.3457 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-05 | 1592957.967 |  |  | 777639.1083 | 204656.5307 | 266019.628 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 777639.1083 | 0 | 13874.4066 | 112982.2556 | 15664.9624 | 39162.406 | 0 | 237592.028 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-06 | 1594374.7002 |  |  | 778743.1741 | 204930.5156 | 266058.3104 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 778743.1741 | 0 | 13884.4818 | 113153.797 | 15691.3534 | 39228.3835 | 0 | 237630.7104 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-07 | 1595791.4333 |  |  | 779847.24 | 205204.5006 | 266096.9927 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 779847.24 | 0 | 13894.557 | 113325.3383 | 15717.7444 | 39294.3609 | 0 | 237669.3927 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-08 | 1597208.1664 |  |  | 780951.3058 | 205478.4856 | 266135.675 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 780951.3058 | 0 | 13904.6322 | 113496.8797 | 15744.1353 | 39360.3383 | 0 | 237708.075 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-09 | 1598624.8996 |  |  | 782055.3717 | 205752.4705 | 266174.3574 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 782055.3717 | 0 | 13914.7074 | 113668.4211 | 15770.5263 | 39426.3158 | 0 | 237746.7574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-10 | 1600041.6327 |  |  | 783159.4375 | 206026.4555 | 266213.0397 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 783159.4375 | 0 | 13924.7826 | 113839.9624 | 15796.9173 | 39492.2932 | 0 | 237785.4397 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-11 | 1601458.3658 |  |  | 784263.5034 | 206300.4405 | 266251.722 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 784263.5034 | 0 | 13934.8577 | 114011.5038 | 15823.3083 | 39558.2707 | 0 | 237824.122 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-12 | 1602875.099 |  |  | 785367.5692 | 206574.4254 | 266290.4044 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 785367.5692 | 0 | 13944.9329 | 114183.0451 | 15849.6992 | 39624.2481 | 0 | 237862.8044 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-13 | 1604291.8321 |  |  | 786471.6351 | 206848.4104 | 266329.0867 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 786471.6351 | 0 | 13955.0081 | 114354.5865 | 15876.0902 | 39690.2256 | 0 | 237901.4867 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-14 | 1605708.5653 |  |  | 787575.7009 | 207122.3953 | 266367.769 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 787575.7009 | 0 | 13965.0833 | 114526.1278 | 15902.4812 | 39756.203 | 0 | 237940.169 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-15 | 1607125.2984 |  |  | 788679.7667 | 207396.3803 | 266406.4514 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 788679.7667 | 0 | 13975.1585 | 114697.6692 | 15928.8722 | 39822.1805 | 0 | 237978.8514 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-16 | 1608542.0315 |  |  | 789783.8326 | 207670.3653 | 266445.1337 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 789783.8326 | 0 | 13985.2337 | 114869.2105 | 15955.2632 | 39888.1579 | 0 | 238017.5337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-17 | 1609958.7647 |  |  | 790887.8984 | 207944.3502 | 266483.816 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 790887.8984 | 0 | 13995.3089 | 115040.7519 | 15981.6541 | 39954.1353 | 0 | 238056.216 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-18 | 1611375.4978 |  |  | 791991.9643 | 208218.3352 | 266522.4983 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 791991.9643 | 0 | 14005.3841 | 115212.2932 | 16008.0451 | 40020.1128 | 0 | 238094.8983 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-19 | 1612792.2309 |  |  | 793096.0301 | 208492.3202 | 266561.1807 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 793096.0301 | 0 | 14015.4592 | 115383.8346 | 16034.4361 | 40086.0902 | 0 | 238133.5807 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-20 | 1614208.9641 |  |  | 794200.096 | 208766.3051 | 266599.863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 794200.096 | 0 | 14025.5344 | 115555.3759 | 16060.8271 | 40152.0677 | 0 | 238172.263 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-21 | 1615625.6972 |  |  | 795304.1618 | 209040.2901 | 266638.5453 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 795304.1618 | 0 | 14035.6096 | 115726.9173 | 16087.218 | 40218.0451 | 0 | 238210.9453 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-22 | 1617042.4304 |  |  | 796408.2277 | 209314.275 | 266677.2277 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 796408.2277 | 0 | 14045.6848 | 115898.4586 | 16113.609 | 40284.0226 | 0 | 238249.6277 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-23 | 1618459.1635 |  |  | 797512.2935 | 209588.26 | 266715.91 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 797512.2935 | 0 | 14055.76 | 116070 | 16140 | 40350 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-24 | 1620926.4333 |  |  | 799017.6883 | 210143.885 | 266715.91 | 51508.25 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 799017.6883 | 0 | 14086.385 | 116411.25 | 16192.5 | 40481.25 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15656.25 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-25 | 1623393.703 |  |  | 800523.083 | 210699.51 | 266715.91 | 51914.5 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 800523.083 | 0 | 14117.01 | 116752.5 | 16245 | 40612.5 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16062.5 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-26 | 1625860.9728 |  |  | 802028.4778 | 211255.135 | 266715.91 | 52320.75 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 802028.4778 | 0 | 14147.635 | 117093.75 | 16297.5 | 40743.75 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16468.75 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-27 | 1628328.2426 |  |  | 803533.8726 | 211810.76 | 266715.91 | 52727 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 803533.8726 | 0 | 14178.26 | 117435 | 16350 | 40875 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16875 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-28 | 1630795.5123 |  |  | 805039.2673 | 212366.385 | 266715.91 | 53133.25 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 805039.2673 | 0 | 14208.885 | 117776.25 | 16402.5 | 41006.25 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 17281.25 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-29 | 1633262.7821 |  |  | 806544.6621 | 212922.01 | 266715.91 | 53539.5 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 806544.6621 | 0 | 14239.51 | 118117.5 | 16455 | 41137.5 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 17687.5 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-11-30 | 1635730.0518 |  |  | 808050.0568 | 213477.635 | 266715.91 | 53945.75 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 808050.0568 | 0 | 14270.135 | 118458.75 | 16507.5 | 41268.75 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 18093.75 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-01 | 1638197.3216 |  |  | 809555.4516 | 214033.26 | 266715.91 | 54352 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 809555.4516 | 0 | 14300.76 | 118800 | 16560 | 41400 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 18500 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-02 | 1640664.5914 |  |  | 811060.8464 | 214588.885 | 266715.91 | 54758.25 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 811060.8464 | 0 | 14331.385 | 119141.25 | 16612.5 | 41531.25 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 18906.25 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-03 | 1643131.8611 |  |  | 812566.2411 | 215144.51 | 266715.91 | 55164.5 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 812566.2411 | 0 | 14362.01 | 119482.5 | 16665 | 41662.5 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 19312.5 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-04 | 1645599.1309 |  |  | 814071.6359 | 215700.135 | 266715.91 | 55570.75 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 814071.6359 | 0 | 14392.635 | 119823.75 | 16717.5 | 41793.75 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 19718.75 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-05 | 1648066.4007 |  |  | 815577.0307 | 216255.76 | 266715.91 | 55977 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 815577.0307 | 0 | 14423.26 | 120165 | 16770 | 41925 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 20125 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-06 | 1650533.6704 |  |  | 817082.4254 | 216811.385 | 266715.91 | 56383.25 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 817082.4254 | 0 | 14453.885 | 120506.25 | 16822.5 | 42056.25 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 20531.25 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-07 | 1653000.9402 |  |  | 818587.8202 | 217367.01 | 266715.91 | 56789.5 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 818587.8202 | 0 | 14484.51 | 120847.5 | 16875 | 42187.5 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 20937.5 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-08 | 1655468.21 |  |  | 820093.215 | 217922.635 | 266715.91 | 57195.75 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 820093.215 | 0 | 14515.135 | 121188.75 | 16927.5 | 42318.75 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 21343.75 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-09 | 1657935.4797 |  |  | 821598.6097 | 218478.26 | 266715.91 | 57602 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 821598.6097 | 0 | 14545.76 | 121530 | 16980 | 42450 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 21750 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-10 | 1660402.7495 |  |  | 823104.0045 | 219033.885 | 266715.91 | 58008.25 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 823104.0045 | 0 | 14576.385 | 121871.25 | 17032.5 | 42581.25 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 22156.25 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-11 | 1662870.0193 |  |  | 824609.3993 | 219589.51 | 266715.91 | 58414.5 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 824609.3993 | 0 | 14607.01 | 122212.5 | 17085 | 42712.5 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 22562.5 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-12 | 1665337.289 |  |  | 826114.794 | 220145.135 | 266715.91 | 58820.75 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 826114.794 | 0 | 14637.635 | 122553.75 | 17137.5 | 42843.75 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 22968.75 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-13 | 1667804.5588 |  |  | 827620.1888 | 220700.76 | 266715.91 | 59227 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 827620.1888 | 0 | 14668.26 | 122895 | 17190 | 42975 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 23375 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-14 | 1670271.8286 |  |  | 829125.5836 | 221256.385 | 266715.91 | 59633.25 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 829125.5836 | 0 | 14698.885 | 123236.25 | 17242.5 | 43106.25 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 23781.25 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-15 | 1672739.0983 |  |  | 830630.9783 | 221812.01 | 266715.91 | 60039.5 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 830630.9783 | 0 | 14729.51 | 123577.5 | 17295 | 43237.5 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 24187.5 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-16 | 1675206.3681 |  |  | 832136.3731 | 222367.635 | 266715.91 | 60445.75 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 832136.3731 | 0 | 14760.135 | 123918.75 | 17347.5 | 43368.75 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 24593.75 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-17 | 1677673.6378 |  |  | 833641.7678 | 222923.26 | 266715.91 | 60852 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 833641.7678 | 0 | 14790.76 | 124260 | 17400 | 43500 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25000 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-18 | 1680140.9076 |  |  | 835147.1626 | 223478.885 | 266715.91 | 61258.25 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 835147.1626 | 0 | 14821.385 | 124601.25 | 17452.5 | 43631.25 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25406.25 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-19 | 1682608.1774 |  |  | 836652.5574 | 224034.51 | 266715.91 | 61664.5 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 836652.5574 | 0 | 14852.01 | 124942.5 | 17505 | 43762.5 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25812.5 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-20 | 1685075.4471 |  |  | 838157.9521 | 224590.135 | 266715.91 | 62070.75 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 838157.9521 | 0 | 14882.635 | 125283.75 | 17557.5 | 43893.75 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 26218.75 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-21 | 1687542.7169 |  |  | 839663.3469 | 225145.76 | 266715.91 | 62477 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 839663.3469 | 0 | 14913.26 | 125625 | 17610 | 44025 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 26625 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-22 | 1690009.9867 |  |  | 841168.7417 | 225701.385 | 266715.91 | 62883.25 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 841168.7417 | 0 | 14943.885 | 125966.25 | 17662.5 | 44156.25 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27031.25 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-23 | 1692477.2564 |  |  | 842674.1364 | 226257.01 | 266715.91 | 63289.5 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 842674.1364 | 0 | 14974.51 | 126307.5 | 17715 | 44287.5 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27437.5 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-24 | 1694944.5262 |  |  | 844179.5312 | 226812.635 | 266715.91 | 63695.75 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 844179.5312 | 0 | 15005.135 | 126648.75 | 17767.5 | 44418.75 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27843.75 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-12-25 | 1697411.796 |  |  | 845684.926 | 227368.26 | 266715.91 | 64102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 845684.926 | 0 | 15035.76 | 126990 | 17820 | 44550 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 28250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0

## Cost Sum
Date | Planned Total Cost (Cumulative) | Actual Total Cost (Cumulative) | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Planned Total Cost (Daily) | Actual Total Cost (Daily) | Planned Labor (Daily) | Actual Labor (Daily) | Planned Travel&perdiem (Daily) | Actual Travel&perdiem (Daily) | Planned Parts&materials (Daily) | Actual Parts&materials (Daily) | Planned Outsource (Daily) | Actual Outsource (Daily) | Planned Equipment (Daily) | Actual Equipment (Daily)
2025-04-02 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 1914.2857 | 5000 | 1914.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 5000 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
2025-04-04 | 2871.4286 | 5000 | 2871.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 3828.5714 | 5000 | 3828.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 4785.7143 | 5000 | 4785.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 5742.8571 | 6126.6 | 5742.8571 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1126.6 | 957.1429 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 6700 | 7253.2 | 6700 | 2253.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1126.6 | 957.1429 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 7657.1429 | 8379.8 | 7657.1429 | 3379.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1126.6 | 957.1429 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 8614.2857 | 9716.32 | 8614.2857 | 4506.4 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1336.52 | 957.1429 | 1126.6 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 9571.4286 | 10879.95 | 9571.4286 | 5633 | 0 | 209.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 1163.63 | 957.1429 | 1126.6 | 0 | 0 | 0 | 37.03 | 0 | 0 | 0 | 0
2025-04-12 | 10528.5714 | 10897.95 | 10528.5714 | 5633 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 18 | 957.1429 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 11485.7143 | 10897.95 | 11485.7143 | 5633 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 12442.8571 | 11112.35 | 12442.8571 | 5847.4 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 13400 | 11326.75 | 13400 | 6061.8 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 14357.1429 | 11541.15 | 14357.1429 | 6276.2 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 15314.2857 | 11755.55 | 15314.2857 | 6490.6 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 16271.4286 | 11969.95 | 16271.4286 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 17228.5714 | 11969.95 | 17228.5714 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 18185.7143 | 11969.95 | 18185.7143 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 19142.8571 | 12352.1 | 19142.8571 | 7087.15 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 20100 | 12734.25 | 20100 | 7469.3 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 21057.1429 | 13116.4 | 21057.1429 | 7851.45 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 22014.2857 | 13498.55 | 22014.2857 | 8233.6 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 22971.4286 | 13880.7 | 22971.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 23928.5714 | 13880.7 | 23928.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 24885.7143 | 13880.7 | 24885.7143 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 25842.8571 | 13880.7 | 25842.8571 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 26800 | 13880.7 | 26800 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 27757.1429 | 13880.7 | 27757.1429 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 28714.2857 | 13880.7 | 28714.2857 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 29671.4286 | 13880.7 | 29671.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 30628.5714 | 13880.7 | 30628.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 31585.7143 | 13880.7 | 31585.7143 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 32542.8571 | 13880.7 | 32542.8571 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 33500 | 13880.7 | 33500 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 34457.1429 | 13880.7 | 34457.1429 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 35414.2857 | 13880.7 | 35414.2857 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 36371.4286 | 13880.7 | 36371.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 37328.5714 | 13880.7 | 37328.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 38285.7143 | 13880.7 | 38285.7143 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 39242.8571 | 13880.7 | 39242.8571 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 40200 | 13880.7 | 40200 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 41157.1429 | 13880.7 | 41157.1429 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 42114.2857 | 13880.7 | 42114.2857 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 43071.4286 | 13880.7 | 43071.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 44028.5714 | 13880.7 | 44028.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 44985.7143 | 14644.31 | 44985.7143 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 763.61 | 957.1429 | 0 | 0 | 0 | 0 | 763.61 | 0 | 0 | 0 | 0
2025-05-19 | 45942.8571 | 14644.31 | 45942.8571 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 46900 | 14644.31 | 46900 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 47857.1429 | 14644.31 | 47857.1429 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 48814.2857 | 14644.31 | 48814.2857 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 49771.4286 | 14823.29 | 49771.4286 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 178.98 | 957.1429 | 0 | 0 | 0 | 0 | 178.98 | 0 | 0 | 0 | 0
2025-05-24 | 50728.5714 | 14823.29 | 50728.5714 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 51685.7143 | 14823.29 | 51685.7143 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 52642.8571 | 14823.29 | 52642.8571 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 53600 | 14823.29 | 53600 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 54557.1429 | 14823.29 | 54557.1429 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 55514.2857 | 14823.29 | 55514.2857 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 56471.4286 | 14823.29 | 56471.4286 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 57428.5714 | 14823.29 | 57428.5714 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 58385.7143 | 14823.29 | 58385.7143 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 59342.8571 | 15419.84 | 59342.8571 | 9212.3 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 596.55 | 957.1429 | 596.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 60300 | 16016.39 | 60300 | 9808.85 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 596.55 | 957.1429 | 596.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 61257.1429 | 16612.94 | 61257.1429 | 10405.4 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 596.55 | 957.1429 | 596.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 62214.2857 | 17209.49 | 62214.2857 | 11001.95 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 596.55 | 957.1429 | 596.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 63171.4286 | 17806.04 | 63171.4286 | 11598.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 596.55 | 957.1429 | 596.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 64128.5714 | 17806.04 | 64128.5714 | 11598.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 65085.7143 | 17806.04 | 65085.7143 | 11598.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 66042.8571 | 18080.99 | 66042.8571 | 11873.45 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 274.95 | 957.1429 | 274.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 67000 | 18355.94 | 67000 | 12148.4 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 274.95 | 957.1429 | 274.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 67957.1429 | 18630.89 | 67957.1429 | 12423.35 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 274.95 | 957.1429 | 274.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 68914.2857 | 18905.84 | 68914.2857 | 12698.3 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 274.95 | 957.1429 | 274.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 69871.4286 | 19180.79 | 69871.4286 | 12973.25 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 274.95 | 957.1429 | 274.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 70828.5714 | 19180.79 | 70828.5714 | 12973.25 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 71785.7143 | 19180.79 | 71785.7143 | 12973.25 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 72742.8571 | 19730.69 | 72742.8571 | 13523.15 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 549.9 | 957.1429 | 549.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 73700 | 20280.59 | 73700 | 14073.05 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 549.9 | 957.1429 | 549.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 74657.1429 | 20830.49 | 74657.1429 | 14622.95 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 549.9 | 957.1429 | 549.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 75614.2857 | 21380.39 | 75614.2857 | 15172.85 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 549.9 | 957.1429 | 549.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 76571.4286 | 21930.29 | 76571.4286 | 15722.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 549.9 | 957.1429 | 549.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 77528.5714 | 21930.29 | 77528.5714 | 15722.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 78485.7143 | 21930.29 | 78485.7143 | 15722.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 79442.8571 | 22205.24 | 79442.8571 | 15997.7 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 274.95 | 957.1429 | 274.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 80400 | 22480.19 | 80400 | 16272.65 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 274.95 | 957.1429 | 274.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 82643.2477 | 22755.14 | 80520.2088 | 16547.6 | 139.8381 | 227.92 | 713.6371 | 979.62 | 321.9345 | 0 | 947.6292 | 5000 | 2243.2477 | 274.95 | 120.2088 | 274.95 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-06-26 | 84886.4953 | 23030.09 | 80640.4175 | 16822.55 | 279.6761 | 227.92 | 1427.2742 | 979.62 | 643.8691 | 0 | 1895.2584 | 5000 | 2243.2477 | 274.95 | 120.2088 | 274.95 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-06-27 | 87129.743 | 23305.04 | 80760.6263 | 17097.5 | 419.5142 | 227.92 | 2140.9112 | 979.62 | 965.8036 | 0 | 2842.8876 | 5000 | 2243.2477 | 274.95 | 120.2088 | 274.95 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-06-28 | 89372.9907 | 23305.04 | 80880.8351 | 17097.5 | 559.3523 | 227.92 | 2854.5483 | 979.62 | 1287.7382 | 0 | 3790.5169 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-06-29 | 91616.2384 | 23305.04 | 81001.0439 | 17097.5 | 699.1904 | 227.92 | 3568.1854 | 979.62 | 1609.6727 | 0 | 4738.1461 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-06-30 | 93859.486 | 23921.94 | 81121.2526 | 17714.4 | 839.0284 | 227.92 | 4281.8225 | 979.62 | 1931.6072 | 0 | 5685.7753 | 5000 | 2243.2477 | 616.9 | 120.2088 | 616.9 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-01 | 96102.7337 | 24538.84 | 81241.4614 | 18331.3 | 978.8665 | 227.92 | 4995.4596 | 979.62 | 2253.5418 | 0 | 6633.4045 | 5000 | 2243.2477 | 616.9 | 120.2088 | 616.9 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-02 | 98345.9814 | 25155.74 | 81361.6702 | 18948.2 | 1118.7046 | 227.92 | 5709.0966 | 979.62 | 2575.4763 | 0 | 7581.0337 | 5000 | 2243.2477 | 616.9 | 120.2088 | 616.9 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-03 | 100589.2291 | 25772.64 | 81481.8789 | 19565.1 | 1258.5426 | 227.92 | 6422.7337 | 979.62 | 2897.4108 | 0 | 8528.6629 | 5000 | 2243.2477 | 616.9 | 120.2088 | 616.9 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-04 | 102832.4767 | 26389.54 | 81602.0877 | 20182 | 1398.3807 | 227.92 | 7136.3708 | 979.62 | 3219.3454 | 0 | 9476.2921 | 5000 | 2243.2477 | 616.9 | 120.2088 | 616.9 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-05 | 105075.7244 | 26389.54 | 81722.2965 | 20182 | 1538.2188 | 227.92 | 7850.0079 | 979.62 | 3541.2799 | 0 | 10423.9213 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-06 | 107318.9721 | 26389.54 | 81842.5053 | 20182 | 1678.0569 | 227.92 | 8563.6449 | 979.62 | 3863.2145 | 0 | 11371.5506 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-07 | 109562.2198 | 27043.165 | 81962.714 | 20835.625 | 1817.8949 | 227.92 | 9277.282 | 979.62 | 4185.149 | 0 | 12319.1798 | 5000 | 2243.2477 | 653.625 | 120.2088 | 653.625 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-08 | 111805.4674 | 27696.79 | 82082.9228 | 21489.25 | 1957.733 | 227.92 | 9990.9191 | 979.62 | 4507.0835 | 0 | 13266.809 | 5000 | 2243.2477 | 653.625 | 120.2088 | 653.625 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-09 | 114048.7151 | 28350.415 | 82203.1316 | 22142.875 | 2097.5711 | 227.92 | 10704.5562 | 979.62 | 4829.0181 | 0 | 14214.4382 | 5000 | 2243.2477 | 653.625 | 120.2088 | 653.625 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-10 | 116291.9628 | 29004.04 | 82323.3403 | 22796.5 | 2237.4092 | 227.92 | 11418.1933 | 979.62 | 5150.9526 | 0 | 15162.0674 | 5000 | 2243.2477 | 653.625 | 120.2088 | 653.625 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-11 | 118535.2105 | 29657.665 | 82443.5491 | 23450.125 | 2377.2472 | 227.92 | 12131.8303 | 979.62 | 5472.8872 | 0 | 16109.6966 | 5000 | 2243.2477 | 653.625 | 120.2088 | 653.625 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-12 | 120778.4581 | 29657.665 | 82563.7579 | 23450.125 | 2517.0853 | 227.92 | 12845.4674 | 979.62 | 5794.8217 | 0 | 17057.3258 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-13 | 123021.7058 | 29657.665 | 82683.9667 | 23450.125 | 2656.9234 | 227.92 | 13559.1045 | 979.62 | 6116.7562 | 0 | 18004.9551 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-14 | 125264.9535 | 31960.39 | 82804.1754 | 24210.95 | 2796.7614 | 1769.82 | 14272.7416 | 979.62 | 6438.6908 | 0 | 18952.5843 | 5000 | 2243.2477 | 2302.725 | 120.2088 | 760.825 | 139.8381 | 1541.9 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-15 | 127508.2011 | 32721.215 | 82924.3842 | 24971.775 | 2936.5995 | 1769.82 | 14986.3787 | 979.62 | 6760.6253 | 0 | 19900.2135 | 5000 | 2243.2477 | 760.825 | 120.2088 | 760.825 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-16 | 129751.4488 | 33482.04 | 83044.593 | 25732.6 | 3076.4376 | 1769.82 | 15700.0157 | 979.62 | 7082.5598 | 0 | 20847.8427 | 5000 | 2243.2477 | 760.825 | 120.2088 | 760.825 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-17 | 131994.6965 | 34307.315 | 83164.8017 | 26493.425 | 3216.2757 | 1834.27 | 16413.6528 | 979.62 | 7404.4944 | 0 | 21795.4719 | 5000 | 2243.2477 | 825.275 | 120.2088 | 760.825 | 139.8381 | 64.45 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-18 | 134237.9442 | 35095.28 | 83285.0105 | 27254.25 | 3356.1137 | 1861.41 | 17127.2899 | 979.62 | 7726.4289 | 0 | 22743.1011 | 5000 | 2243.2477 | 787.965 | 120.2088 | 760.825 | 139.8381 | 27.14 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-19 | 136481.1918 | 35125.28 | 83405.2193 | 27254.25 | 3495.9518 | 1891.41 | 17840.927 | 979.62 | 8048.3635 | 0 | 23690.7303 | 5000 | 2243.2477 | 30 | 120.2088 | 0 | 139.8381 | 30 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-20 | 138724.4395 | 35125.28 | 83525.4281 | 27254.25 | 3635.7899 | 1891.41 | 18554.564 | 979.62 | 8370.298 | 0 | 24638.3596 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-21 | 140967.6872 | 35778.905 | 83645.6368 | 27907.875 | 3775.6279 | 1891.41 | 19268.2011 | 979.62 | 8692.2325 | 0 | 25585.9888 | 5000 | 2243.2477 | 653.625 | 120.2088 | 653.625 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-22 | 143210.9349 | 36932.53 | 83765.8456 | 28561.5 | 3915.466 | 1891.41 | 19981.8382 | 979.62 | 9014.1671 | 500 | 26533.618 | 5000 | 2243.2477 | 1153.625 | 120.2088 | 653.625 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 500 | 947.6292 | 0
2025-07-23 | 145454.1825 | 37586.155 | 83886.0544 | 29215.125 | 4055.3041 | 1891.41 | 20695.4753 | 979.62 | 9336.1016 | 500 | 27481.2472 | 5000 | 2243.2477 | 653.625 | 120.2088 | 653.625 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-24 | 147697.4302 | 38239.78 | 84006.2631 | 29868.75 | 4195.1422 | 1891.41 | 21409.1124 | 979.62 | 9658.0362 | 500 | 28428.8764 | 5000 | 2243.2477 | 653.625 | 120.2088 | 653.625 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-25 | 149940.6779 | 38893.405 | 84126.4719 | 30522.375 | 4334.9802 | 1891.41 | 22122.7494 | 979.62 | 9979.9707 | 500 | 29376.5056 | 5000 | 2243.2477 | 653.625 | 120.2088 | 653.625 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-26 | 152183.9256 | 38893.405 | 84246.6807 | 30522.375 | 4474.8183 | 1891.41 | 22836.3865 | 979.62 | 10301.9052 | 500 | 30324.1348 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-27 | 154427.1732 | 38893.405 | 84366.8895 | 30522.375 | 4614.6564 | 1891.41 | 23550.0236 | 979.62 | 10623.8398 | 500 | 31271.764 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-28 | 156670.4209 | 39493.43 | 84487.0982 | 31122.4 | 4754.4944 | 1891.41 | 24263.6607 | 979.62 | 10945.7743 | 500 | 32219.3933 | 5000 | 2243.2477 | 600.025 | 120.2088 | 600.025 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-29 | 158913.6686 | 40093.455 | 84607.307 | 31722.425 | 4894.3325 | 1891.41 | 24977.2978 | 979.62 | 11267.7088 | 500 | 33167.0225 | 5000 | 2243.2477 | 600.025 | 120.2088 | 600.025 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-30 | 161156.9163 | 40693.48 | 84727.5158 | 32322.45 | 5034.1706 | 1891.41 | 25690.9348 | 979.62 | 11589.6434 | 500 | 34114.6517 | 5000 | 2243.2477 | 600.025 | 120.2088 | 600.025 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-31 | 163400.1639 | 41293.505 | 84847.7245 | 32922.475 | 5174.0087 | 1891.41 | 26404.5719 | 979.62 | 11911.5779 | 500 | 35062.2809 | 5000 | 2243.2477 | 600.025 | 120.2088 | 600.025 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-01 | 165643.4116 | 45631.46 | 84967.9333 | 33522.5 | 5313.8467 | 3774.04 | 27118.209 | 2806.92 | 12233.5125 | 528 | 36009.9101 | 5000 | 2243.2477 | 4337.955 | 120.2088 | 600.025 | 139.8381 | 1882.63 | 713.6371 | 1827.3 | 321.9345 | 28 | 947.6292 | 0
2025-08-02 | 167886.6593 | 45631.46 | 85088.1421 | 33522.5 | 5453.6848 | 3774.04 | 27831.8461 | 2806.92 | 12555.447 | 528 | 36957.5393 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-03 | 170129.907 | 45631.46 | 85208.3509 | 33522.5 | 5593.5229 | 3774.04 | 28545.4831 | 2806.92 | 12877.3815 | 528 | 37905.1685 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-04 | 172373.1546 | 47604.11 | 85328.5596 | 34126 | 5733.361 | 3774.04 | 29259.1202 | 4176.07 | 13199.3161 | 528 | 38852.7978 | 5000 | 2243.2477 | 1972.65 | 120.2088 | 603.5 | 139.8381 | 0 | 713.6371 | 1369.15 | 321.9345 | 0 | 947.6292 | 0
2025-08-05 | 174616.4023 | 48207.61 | 85448.7684 | 34729.5 | 5873.199 | 3774.04 | 29972.7573 | 4176.07 | 13521.2506 | 528 | 39800.427 | 5000 | 2243.2477 | 603.5 | 120.2088 | 603.5 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-06 | 176859.65 | 48811.11 | 85568.9772 | 35333 | 6013.0371 | 3774.04 | 30686.3944 | 4176.07 | 13843.1851 | 528 | 40748.0562 | 5000 | 2243.2477 | 603.5 | 120.2088 | 603.5 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-07 | 179102.8976 | 50365.48 | 85689.1859 | 35936.5 | 6152.8752 | 3774.04 | 31400.0315 | 5126.94 | 14165.1197 | 528 | 41695.6854 | 5000 | 2243.2477 | 1554.37 | 120.2088 | 603.5 | 139.8381 | 0 | 713.6371 | 950.87 | 321.9345 | 0 | 947.6292 | 0
2025-08-08 | 181346.1453 | 50968.98 | 85809.3947 | 36540 | 6292.7132 | 3774.04 | 32113.6685 | 5126.94 | 14487.0542 | 528 | 42643.3146 | 5000 | 2243.2477 | 603.5 | 120.2088 | 603.5 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-09 | 183589.393 | 50968.98 | 85929.6035 | 36540 | 6432.5513 | 3774.04 | 32827.3056 | 5126.94 | 14808.9888 | 528 | 43590.9438 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-10 | 185832.6407 | 50968.98 | 86049.8123 | 36540 | 6572.3894 | 3774.04 | 33540.9427 | 5126.94 | 15130.9233 | 528 | 44538.573 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-11 | 188075.8883 | 51735.85 | 86170.021 | 37089.9 | 6712.2275 | 3774.04 | 34254.5798 | 5343.91 | 15452.8578 | 528 | 45486.2022 | 5000 | 2243.2477 | 766.87 | 120.2088 | 549.9 | 139.8381 | 0 | 713.6371 | 216.97 | 321.9345 | 0 | 947.6292 | 0
2025-08-12 | 190319.136 | 52285.75 | 86290.2298 | 37639.8 | 6852.0655 | 3774.04 | 34968.2169 | 5343.91 | 15774.7924 | 528 | 46433.8315 | 5000 | 2243.2477 | 549.9 | 120.2088 | 549.9 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-13 | 192562.3837 | 52835.65 | 86410.4386 | 38189.7 | 6991.9036 | 3774.04 | 35681.8539 | 5343.91 | 16096.7269 | 528 | 47381.4607 | 5000 | 2243.2477 | 549.9 | 120.2088 | 549.9 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-14 | 194805.6314 | 53385.55 | 86530.6473 | 38739.6 | 7131.7417 | 3774.04 | 36395.491 | 5343.91 | 16418.6615 | 528 | 48329.0899 | 5000 | 2243.2477 | 549.9 | 120.2088 | 549.9 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-15 | 197048.879 | 53935.45 | 86650.8561 | 39289.5 | 7271.5797 | 3774.04 | 37109.1281 | 5343.91 | 16740.596 | 528 | 49276.7191 | 5000 | 2243.2477 | 549.9 | 120.2088 | 549.9 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-16 | 199292.1267 | 53935.45 | 86771.0649 | 39289.5 | 7411.4178 | 3774.04 | 37822.7652 | 5343.91 | 17062.5305 | 528 | 50224.3483 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-17 | 201535.3744 | 53935.45 | 86891.2736 | 39289.5 | 7551.2559 | 3774.04 | 38536.4022 | 5343.91 | 17384.4651 | 528 | 51171.9775 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-18 | 203778.6221 | 54639.2 | 87011.4824 | 39993.25 | 7691.094 | 3774.04 | 39250.0393 | 5343.91 | 17706.3996 | 528 | 52119.6067 | 5000 | 2243.2477 | 703.75 | 120.2088 | 703.75 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-19 | 206021.8697 | 67852.31 | 87131.6912 | 40697 | 7830.932 | 3774.04 | 39963.6764 | 17853.27 | 18028.3341 | 528 | 53067.236 | 5000 | 2243.2477 | 13213.11 | 120.2088 | 703.75 | 139.8381 | 0 | 713.6371 | 12509.36 | 321.9345 | 0 | 947.6292 | 0
2025-08-20 | 208265.1174 | 69008.83 | 87251.9 | 41400.75 | 7970.7701 | 4226.81 | 40677.3135 | 17853.27 | 18350.2687 | 528 | 54014.8652 | 5000 | 2243.2477 | 1156.52 | 120.2088 | 703.75 | 139.8381 | 452.77 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-21 | 210508.3651 | 69712.58 | 87372.1087 | 42104.5 | 8110.6082 | 4226.81 | 41390.9506 | 17853.27 | 18672.2032 | 528 | 54962.4944 | 5000 | 2243.2477 | 703.75 | 120.2088 | 703.75 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-22 | 212751.6128 | 70516.33 | 87492.3175 | 42808.25 | 8250.4462 | 4326.81 | 42104.5876 | 17853.27 | 18994.1378 | 528 | 55910.1236 | 5000 | 2243.2477 | 803.75 | 120.2088 | 703.75 | 139.8381 | 100 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-23 | 214994.8604 | 70516.33 | 87612.5263 | 42808.25 | 8390.2843 | 4326.81 | 42818.2247 | 17853.27 | 19316.0723 | 528 | 56857.7528 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-24 | 217238.1081 | 70516.33 | 87732.735 | 42808.25 | 8530.1224 | 4326.81 | 43531.8618 | 17853.27 | 19638.0068 | 528 | 57805.382 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-25 | 219481.3558 | 71931.515 | 87852.9438 | 43488.675 | 8669.9605 | 4326.81 | 44245.4989 | 18573.03 | 19959.9414 | 543 | 58753.0112 | 5000 | 2243.2477 | 1415.185 | 120.2088 | 680.425 | 139.8381 | 0 | 713.6371 | 719.76 | 321.9345 | 15 | 947.6292 | 0
2025-08-26 | 221724.6034 | 75361.94 | 87973.1526 | 44169.1 | 8809.7985 | 4326.81 | 44959.136 | 18573.03 | 20281.8759 | 3293 | 59700.6404 | 5000 | 2243.2477 | 3430.425 | 120.2088 | 680.425 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 2750 | 947.6292 | 0
2025-08-27 | 223967.8511 | 76042.365 | 88093.3614 | 44849.525 | 8949.6366 | 4326.81 | 45672.773 | 18573.03 | 20603.8105 | 3293 | 60648.2697 | 5000 | 2243.2477 | 680.425 | 120.2088 | 680.425 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-28 | 226211.0988 | 76722.79 | 88213.5701 | 45529.95 | 9089.4747 | 4326.81 | 46386.4101 | 18573.03 | 20925.745 | 3293 | 61595.8989 | 5000 | 2243.2477 | 680.425 | 120.2088 | 680.425 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-29 | 228454.3465 | 77403.215 | 88333.7789 | 46210.375 | 9229.3128 | 4326.81 | 47100.0472 | 18573.03 | 21247.6795 | 3293 | 62543.5281 | 5000 | 2243.2477 | 680.425 | 120.2088 | 680.425 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-30 | 230697.5941 | 77403.215 | 88453.9877 | 46210.375 | 9369.1508 | 4326.81 | 47813.6843 | 18573.03 | 21569.6141 | 3293 | 63491.1573 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-31 | 232940.8418 | 77403.215 | 88574.1964 | 46210.375 | 9508.9889 | 4326.81 | 48527.3213 | 18573.03 | 21891.5486 | 3293 | 64438.7865 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-01 | 235184.0895 | 78566.54 | 88694.4052 | 47373.7 | 9648.827 | 4326.81 | 49240.9584 | 18573.03 | 22213.4831 | 3293 | 65386.4157 | 5000 | 2243.2477 | 1163.325 | 120.2088 | 1163.325 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-02 | 237427.3372 | 82854.665 | 88814.614 | 48537.025 | 9788.665 | 4326.81 | 49954.5955 | 21697.83 | 22535.4177 | 3293 | 66334.0449 | 5000 | 2243.2477 | 4288.125 | 120.2088 | 1163.325 | 139.8381 | 0 | 713.6371 | 3124.8 | 321.9345 | 0 | 947.6292 | 0
2025-09-03 | 239670.5848 | 84612.45 | 88934.8228 | 49700.35 | 9928.5031 | 4921.27 | 50668.2326 | 21697.83 | 22857.3522 | 3293 | 67281.6742 | 5000 | 2243.2477 | 1757.785 | 120.2088 | 1163.325 | 139.8381 | 594.46 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-04 | 241913.8325 | 86517.505 | 89055.0315 | 50863.675 | 10068.3412 | 4976.3 | 51381.8697 | 21697.83 | 23179.2868 | 3979.7 | 68229.3034 | 5000 | 2243.2477 | 1905.055 | 120.2088 | 1163.325 | 139.8381 | 55.03 | 713.6371 | 0 | 321.9345 | 686.7 | 947.6292 | 0
2025-09-05 | 244157.0802 | 88824.12 | 89175.2403 | 52027 | 10208.1793 | 5948.88 | 52095.5067 | 21868.54 | 23501.2213 | 3979.7 | 69176.9326 | 5000 | 2243.2477 | 2306.615 | 120.2088 | 1163.325 | 139.8381 | 972.58 | 713.6371 | 170.71 | 321.9345 | 0 | 947.6292 | 0
2025-09-06 | 246400.3279 | 88824.12 | 89295.4491 | 52027 | 10348.0173 | 5948.88 | 52809.1438 | 21868.54 | 23823.1558 | 3979.7 | 70124.5618 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-07 | 248643.5755 | 88824.12 | 89415.6578 | 52027 | 10487.8554 | 5948.88 | 53522.7809 | 21868.54 | 24145.0904 | 3979.7 | 71072.191 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-08 | 250886.8232 | 89578.495 | 89535.8666 | 52781.375 | 10627.6935 | 5948.88 | 54236.418 | 21868.54 | 24467.0249 | 3979.7 | 72019.8202 | 5000 | 2243.2477 | 754.375 | 120.2088 | 754.375 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-09 | 253130.0709 | 90913.88 | 89656.0754 | 53535.75 | 10767.5315 | 5948.88 | 54950.0551 | 22449.55 | 24788.9595 | 3979.7 | 72967.4494 | 5000 | 2243.2477 | 1335.385 | 120.2088 | 754.375 | 139.8381 | 0 | 713.6371 | 581.01 | 321.9345 | 0 | 947.6292 | 0
2025-09-10 | 255373.3186 | 91905.115 | 89776.2842 | 54290.125 | 10907.3696 | 6185.74 | 55663.6921 | 22449.55 | 25110.894 | 3979.7 | 73915.0787 | 5000 | 2243.2477 | 991.235 | 120.2088 | 754.375 | 139.8381 | 236.86 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-11 | 257616.5662 | 92866.11 | 89896.4929 | 55044.5 | 11047.2077 | 6185.74 | 56377.3292 | 22656.17 | 25432.8285 | 3979.7 | 74862.7079 | 5000 | 2243.2477 | 960.995 | 120.2088 | 754.375 | 139.8381 | 0 | 713.6371 | 206.62 | 321.9345 | 0 | 947.6292 | 0
2025-09-12 | 259859.8139 | 108610.085 | 90016.7017 | 55798.875 | 11187.0458 | 6296.68 | 57090.9663 | 23419.83 | 25754.7631 | 18094.7 | 75810.3371 | 5000 | 2243.2477 | 15743.975 | 120.2088 | 754.375 | 139.8381 | 110.94 | 713.6371 | 763.66 | 321.9345 | 14115 | 947.6292 | 0
2025-09-13 | 262103.0616 | 108762.505 | 90136.9105 | 55798.875 | 11326.8838 | 6296.68 | 57804.6034 | 23469.34 | 26076.6976 | 18197.61 | 76757.9663 | 5000 | 2243.2477 | 152.42 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 49.51 | 321.9345 | 102.91 | 947.6292 | 0
2025-09-14 | 264346.3092 | 108762.505 | 90257.1192 | 55798.875 | 11466.7219 | 6296.68 | 58518.2404 | 23469.34 | 26398.6321 | 18197.61 | 77705.5955 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-15 | 266589.5569 | 110838.88 | 90377.328 | 57425.25 | 11606.56 | 6746.68 | 59231.8775 | 23469.34 | 26720.5667 | 18197.61 | 78653.2247 | 5000 | 2243.2477 | 2076.375 | 120.2088 | 1626.375 | 139.8381 | 450 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-16 | 268832.8046 | 115928.295 | 90497.5368 | 59051.625 | 11746.398 | 10209.72 | 59945.5146 | 23469.34 | 27042.5012 | 18197.61 | 79600.8539 | 5000 | 2243.2477 | 5089.415 | 120.2088 | 1626.375 | 139.8381 | 3463.04 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-17 | 271076.0523 | 117709.64 | 90617.7456 | 60678 | 11886.2361 | 10209.72 | 60659.1517 | 23624.31 | 27364.4358 | 18197.61 | 80548.4831 | 5000 | 2243.2477 | 1781.345 | 120.2088 | 1626.375 | 139.8381 | 0 | 713.6371 | 154.97 | 321.9345 | 0 | 947.6292 | 0
2025-09-18 | 273319.2999 | 120281.575 | 90737.9543 | 62304.375 | 12026.0742 | 11155.28 | 61372.7888 | 23624.31 | 27686.3703 | 18197.61 | 81496.1124 | 5000 | 2243.2477 | 2571.935 | 120.2088 | 1626.375 | 139.8381 | 945.56 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-19 | 275562.5476 | 122037.09 | 90858.1631 | 63930.75 | 12165.9123 | 11155.28 | 62086.4258 | 23753.45 | 28008.3048 | 18197.61 | 82443.7416 | 5000 | 2243.2477 | 1755.515 | 120.2088 | 1626.375 | 139.8381 | 0 | 713.6371 | 129.14 | 321.9345 | 0 | 947.6292 | 0
2025-09-20 | 277805.7953 | 122611.58 | 90978.3719 | 63930.75 | 12305.7503 | 11155.28 | 62800.0629 | 24327.94 | 28330.2394 | 18197.61 | 83391.3708 | 5000 | 2243.2477 | 574.49 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 574.49 | 321.9345 | 0 | 947.6292 | 0
2025-09-21 | 280049.043 | 122611.58 | 91098.5806 | 63930.75 | 12445.5884 | 11155.28 | 63513.7 | 24327.94 | 28652.1739 | 18197.61 | 84339 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-22 | 280049.043 | 126870.395 | 91098.5806 | 65705.925 | 12445.5884 | 11620.8 | 63513.7 | 24398.56 | 28652.1739 | 20145.11 | 84339 | 5000 | 0 | 4258.815 | 0 | 1775.175 | 0 | 465.52 | 0 | 70.62 | 0 | 1947.5 | 0 | 0
2025-09-23 | 285529.0229 | 129928.8 | 94337.9597 | 67481.1 | 13451.8732 | 11766.51 | 64326.5779 | 24398.56 | 28836.99 | 21282.63 | 84575.6221 | 5000 | 5479.9799 | 3058.405 | 3239.379 | 1775.175 | 1006.2848 | 145.71 | 812.8779 | 0 | 184.8161 | 1137.52 | 236.6221 | 0
2025-09-24 | 291009.0028 | 139225.045 | 97577.3387 | 69256.275 | 14458.1581 | 12020.36 | 65139.4559 | 27354.47 | 29021.806 | 25593.94 | 84812.2441 | 5000 | 5479.9799 | 9296.245 | 3239.379 | 1775.175 | 1006.2848 | 253.85 | 812.8779 | 2955.91 | 184.8161 | 4311.31 | 236.6221 | 0
2025-09-25 | 296488.9827 | 144836.61 | 100816.7177 | 71031.45 | 15464.4429 | 12061.95 | 65952.3338 | 30373.02 | 29206.6221 | 26370.19 | 85048.8662 | 5000 | 5479.9799 | 5611.565 | 3239.379 | 1775.175 | 1006.2848 | 41.59 | 812.8779 | 3018.55 | 184.8161 | 776.25 | 236.6221 | 0
2025-09-26 | 301968.9627 | 146921.235 | 104056.0968 | 72806.625 | 16470.7278 | 12061.95 | 66765.2117 | 30682.47 | 29391.4381 | 26370.19 | 85285.4883 | 5000 | 5479.9799 | 2084.625 | 3239.379 | 1775.175 | 1006.2848 | 0 | 812.8779 | 309.45 | 184.8161 | 0 | 236.6221 | 0
2025-09-27 | 307448.9426 | 147436.225 | 107295.4758 | 72806.625 | 17477.0126 | 12061.95 | 67578.0896 | 31197.46 | 29576.2542 | 26370.19 | 85522.1104 | 5000 | 5479.9799 | 514.99 | 3239.379 | 0 | 1006.2848 | 0 | 812.8779 | 514.99 | 184.8161 | 0 | 236.6221 | 0
2025-09-28 | 312928.9225 | 147894.905 | 110534.8548 | 72806.625 | 18483.2974 | 12197.85 | 68390.9676 | 31520.24 | 29761.0702 | 26370.19 | 85758.7324 | 5000 | 5479.9799 | 458.68 | 3239.379 | 0 | 1006.2848 | 135.9 | 812.8779 | 322.78 | 184.8161 | 0 | 236.6221 | 0
2025-09-29 | 318408.9024 | 157676.72 | 113774.2339 | 74913.85 | 19489.5823 | 12547.85 | 69203.8455 | 38844.83 | 29945.8863 | 26370.19 | 85995.3545 | 5000 | 5479.9799 | 9781.815 | 3239.379 | 2107.225 | 1006.2848 | 350 | 812.8779 | 7324.59 | 184.8161 | 0 | 236.6221 | 0
2025-09-30 | 323888.8824 | 172783.945 | 117013.6129 | 77021.075 | 20495.8671 | 12547.85 | 70016.7234 | 38844.83 | 30130.7023 | 39370.19 | 86231.9766 | 5000 | 5479.9799 | 15107.225 | 3239.379 | 2107.225 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 13000 | 236.6221 | 0
2025-10-01 | 329368.8623 | 175654.42 | 120252.9919 | 79128.3 | 21502.152 | 13248.82 | 70829.6013 | 38907.11 | 30315.5184 | 39370.19 | 86468.5987 | 5000 | 5479.9799 | 2870.475 | 3239.379 | 2107.225 | 1006.2848 | 700.97 | 812.8779 | 62.28 | 184.8161 | 0 | 236.6221 | 0
2025-10-02 | 334848.8422 | 178576.865 | 123492.371 | 81235.525 | 22508.4368 | 13928.74 | 71642.4793 | 38907.11 | 30500.3344 | 39505.49 | 86705.2207 | 5000 | 5479.9799 | 2922.445 | 3239.379 | 2107.225 | 1006.2848 | 679.92 | 812.8779 | 0 | 184.8161 | 135.3 | 236.6221 | 0
2025-10-03 | 340328.8221 | 181389.86 | 126731.75 | 83342.75 | 23514.7216 | 14634.51 | 72455.3572 | 38907.11 | 30685.1505 | 39505.49 | 86941.8428 | 5000 | 5479.9799 | 2812.995 | 3239.379 | 2107.225 | 1006.2848 | 705.77 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-04 | 345808.8021 | 181464.86 | 129971.129 | 83342.75 | 24521.0065 | 14709.51 | 73268.2351 | 38907.11 | 30869.9666 | 39505.49 | 87178.4649 | 5000 | 5479.9799 | 75 | 3239.379 | 0 | 1006.2848 | 75 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-05 | 351288.782 | 181464.86 | 133210.5081 | 83342.75 | 25527.2913 | 14709.51 | 74081.113 | 38907.11 | 31054.7826 | 39505.49 | 87415.087 | 5000 | 5479.9799 | 0 | 3239.379 | 0 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-06 | 356768.7619 | 183211.985 | 136449.8871 | 85089.875 | 26533.5761 | 14709.51 | 74893.991 | 38907.11 | 31239.5987 | 39505.49 | 87651.709 | 5000 | 5479.9799 | 1747.125 | 3239.379 | 1747.125 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-07 | 362248.7418 | 185114.88 | 139689.2661 | 86837 | 27539.861 | 14865.28 | 75706.8689 | 38907.11 | 31424.4147 | 39505.49 | 87888.3311 | 5000 | 5479.9799 | 1902.895 | 3239.379 | 1747.125 | 1006.2848 | 155.77 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-08 | 367728.7217 | 196758.935 | 142928.6452 | 88584.125 | 28546.1458 | 14865.28 | 76519.7468 | 38907.11 | 31609.2308 | 49402.42 | 88124.9532 | 5000 | 5479.9799 | 11644.055 | 3239.379 | 1747.125 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 9896.93 | 236.6221 | 0
2025-10-09 | 373208.7017 | 198570.43 | 146168.0242 | 90331.25 | 29552.4307 | 14929.65 | 77332.6247 | 38907.11 | 31794.0468 | 49402.42 | 88361.5753 | 5000 | 5479.9799 | 1811.495 | 3239.379 | 1747.125 | 1006.2848 | 64.37 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-10 | 378688.6816 | 200415.715 | 149407.4032 | 92078.375 | 30558.7155 | 14959.65 | 78145.5027 | 38975.27 | 31978.8629 | 49402.42 | 88598.1973 | 5000 | 5479.9799 | 1845.285 | 3239.379 | 1747.125 | 1006.2848 | 30 | 812.8779 | 68.16 | 184.8161 | 0 | 236.6221 | 0
2025-10-11 | 384168.6615 | 202050.145 | 152646.7823 | 92078.375 | 31565.0003 | 14959.65 | 78958.3806 | 39009.7 | 32163.6789 | 51002.42 | 88834.8194 | 5000 | 5479.9799 | 1634.43 | 3239.379 | 0 | 1006.2848 | 0 | 812.8779 | 34.43 | 184.8161 | 1600 | 236.6221 | 0
2025-10-12 | 389648.6414 | 202088.945 | 155886.1613 | 92078.375 | 32571.2852 | 14984.65 | 79771.2585 | 39023.5 | 32348.495 | 51002.42 | 89071.4415 | 5000 | 5479.9799 | 38.8 | 3239.379 | 0 | 1006.2848 | 25 | 812.8779 | 13.8 | 184.8161 | 0 | 236.6221 | 0
2025-10-13 | 395128.6214 | 203859.395 | 159125.5403 | 93848.825 | 33577.57 | 14984.65 | 80584.1365 | 39023.5 | 32533.311 | 51002.42 | 89308.0635 | 5000 | 5479.9799 | 1770.45 | 3239.379 | 1770.45 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-14 | 400608.6013 | 206665.575 | 162364.9194 | 95619.275 | 34583.8548 | 15868.99 | 81397.0144 | 39174.89 | 32718.1271 | 51002.42 | 89544.6856 | 5000 | 5479.9799 | 2806.18 | 3239.379 | 1770.45 | 1006.2848 | 884.34 | 812.8779 | 151.39 | 184.8161 | 0 | 236.6221 | 0
2025-10-15 | 406088.5812 | 210518.585 | 165604.2984 | 97389.725 | 35590.1397 | 17951.55 | 82209.8923 | 39174.89 | 32902.9431 | 51002.42 | 89781.3077 | 5000 | 5479.9799 | 3853.01 | 3239.379 | 1770.45 | 1006.2848 | 2082.56 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-16 | 411568.5611 | 212352.675 | 168843.6774 | 99160.175 | 36596.4245 | 18015.19 | 83022.7702 | 39174.89 | 33087.7592 | 51002.42 | 90017.9298 | 5000 | 5479.9799 | 1834.09 | 3239.379 | 1770.45 | 1006.2848 | 63.64 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-17 | 417048.5411 | 215294.875 | 172083.0565 | 100930.625 | 37602.7094 | 19157.15 | 83835.6482 | 39204.68 | 33272.5753 | 51002.42 | 90254.5518 | 5000 | 5479.9799 | 2942.2 | 3239.379 | 1770.45 | 1006.2848 | 1141.96 | 812.8779 | 29.79 | 184.8161 | 0 | 236.6221 | 0
2025-10-18 | 422528.521 | 215294.875 | 175322.4355 | 100930.625 | 38608.9942 | 19157.15 | 84648.5261 | 39204.68 | 33457.3913 | 51002.42 | 90491.1739 | 5000 | 5479.9799 | 0 | 3239.379 | 0 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-19 | 428008.5009 | 215294.875 | 178561.8145 | 100930.625 | 39615.279 | 19157.15 | 85461.404 | 39204.68 | 33642.2074 | 51002.42 | 90727.796 | 5000 | 5479.9799 | 0 | 3239.379 | 0 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-20 | 433488.4808 | 217810.88 | 181801.1935 | 103046.55 | 40621.5639 | 19455.45 | 86274.2819 | 39306.46 | 33827.0234 | 51002.42 | 90964.4181 | 5000 | 5479.9799 | 2516.005 | 3239.379 | 2115.925 | 1006.2848 | 298.3 | 812.8779 | 101.78 | 184.8161 | 0 | 236.6221 | 0
2025-10-21 | 438968.4608 | 220006.155 | 185040.5726 | 105162.475 | 41627.8487 | 19455.45 | 87087.1599 | 39385.81 | 34011.8395 | 51002.42 | 91201.0401 | 5000 | 5479.9799 | 2195.275 | 3239.379 | 2115.925 | 1006.2848 | 0 | 812.8779 | 79.35 | 184.8161 | 0 | 236.6221 | 0
2025-10-22 | 444448.4407 | 230888.51 | 188279.9516 | 107278.4 | 42634.1336 | 19521.88 | 87900.0378 | 39385.81 | 34196.6555 | 59702.42 | 91437.6622 | 5000 | 5479.9799 | 10882.355 | 3239.379 | 2115.925 | 1006.2848 | 66.43 | 812.8779 | 0 | 184.8161 | 8700 | 236.6221 | 0
2025-10-23 | 449928.4206 | 233140.835 | 191519.3306 | 109394.325 | 43640.4184 | 19658.28 | 88712.9157 | 39385.81 | 34381.4716 | 59702.42 | 91674.2843 | 5000 | 5479.9799 | 2252.325 | 3239.379 | 2115.925 | 1006.2848 | 136.4 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-24 | 455408.4005 | 238645.59 | 194758.7097 | 111510.25 | 44646.7032 | 22793.36 | 89525.7936 | 39639.56 | 34566.2876 | 59702.42 | 91910.9064 | 5000 | 5479.9799 | 5504.755 | 3239.379 | 2115.925 | 1006.2848 | 3135.08 | 812.8779 | 253.75 | 184.8161 | 0 | 236.6221 | 0
2025-10-25 | 460888.3805 | 238670.59 | 197998.0887 | 111510.25 | 45652.9881 | 22818.36 | 90338.6716 | 39639.56 | 34751.1037 | 59702.42 | 92147.5284 | 5000 | 5479.9799 | 25 | 3239.379 | 0 | 1006.2848 | 25 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-26 | 466368.3604 | 238854.93 | 201237.4677 | 111510.25 | 46659.2729 | 23002.7 | 91151.5495 | 39639.56 | 34935.9197 | 59702.42 | 92384.1505 | 5000 | 5479.9799 | 184.34 | 3239.379 | 0 | 1006.2848 | 184.34 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-27 | 471848.3403 | 241266.39 | 204476.8468 | 113280.75 | 47665.5577 | 23643.66 | 91964.4274 | 39639.56 | 35120.7358 | 59702.42 | 92620.7726 | 5000 | 5479.9799 | 2411.46 | 3239.379 | 1770.5 | 1006.2848 | 640.96 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-28 | 477328.3202 | 244212.72 | 207716.2258 | 115051.25 | 48671.8426 | 23688.24 | 92777.3054 | 40754.18 | 35305.5518 | 59719.05 | 92857.3946 | 5000 | 5479.9799 | 2946.33 | 3239.379 | 1770.5 | 1006.2848 | 44.58 | 812.8779 | 1114.62 | 184.8161 | 16.63 | 236.6221 | 0
2025-10-29 | 482808.3002 | 251946.78 | 210955.6048 | 116821.75 | 49678.1274 | 23713.24 | 93590.1833 | 40892.74 | 35490.3679 | 65519.05 | 93094.0167 | 5000 | 5479.9799 | 7734.06 | 3239.379 | 1770.5 | 1006.2848 | 25 | 812.8779 | 138.56 | 184.8161 | 5800 | 236.6221 | 0
2025-10-30 | 488288.2801 | 254017.43 | 214194.9839 | 118592.25 | 50684.4123 | 23798.03 | 94403.0612 | 40972.8 | 35675.1839 | 65654.35 | 93330.6388 | 5000 | 5479.9799 | 2070.65 | 3239.379 | 1770.5 | 1006.2848 | 84.79 | 812.8779 | 80.06 | 184.8161 | 135.3 | 236.6221 | 0
2025-10-31 | 493768.26 | 257434.04 | 217434.3629 | 120362.75 | 51690.6971 | 25444.14 | 95215.9391 | 40972.8 | 35860 | 65654.35 | 93567.2609 | 5000 | 5479.9799 | 3416.61 | 3239.379 | 1770.5 | 1006.2848 | 1646.11 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-11-01 | 499248.2399 | 257674.14 | 220673.7419 | 120362.75 | 52696.9819 | 25684.24 | 96028.8171 | 40972.8 | 36044.8161 | 65654.35 | 93803.8829 | 5000 | 5479.9799 | 240.1 | 3239.379 | 0 | 1006.2848 | 240.1 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-11-02 | 504728.2199 | 257674.14 | 223913.121 | 120362.75 | 53703.2668 | 25684.24 | 96841.695 | 40972.8 | 36229.6321 | 65654.35 | 94040.505 | 5000 | 5479.9799 | 0 | 3239.379 | 0 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-11-03 | 510208.1998 | 259345.44 | 227152.5 | 122034.05 | 54709.5516 | 25684.24 | 97654.5729 | 40972.8 | 36414.4482 | 65654.35 | 94277.1271 | 5000 | 5479.9799 | 1671.3 | 3239.379 | 1671.3 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-11-04 | 515688.1797 | 261553.65 | 230391.879 | 123705.35 | 55715.8365 | 26221.15 | 98467.4508 | 40972.8 | 36599.2642 | 65654.35 | 94513.7492 | 5000 | 5479.9799 | 2208.21 | 3239.379 | 1671.3 | 1006.2848 | 536.91 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-11-05 | 521168.1596 | 265878.78 | 233631.2581 | 125376.65 | 56722.1213 | 28874.98 | 99280.3288 | 40972.8 | 36784.0803 | 65654.35 | 94750.3712 | 5000 | 5479.9799 | 4325.13 | 3239.379 | 1671.3 | 1006.2848 | 2653.83 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-11-06 | 526648.1395 | 269178.21 | 236870.6371 | 127047.95 | 57728.4061 | 28929.76 | 100093.2067 | 41196.15 | 36968.8963 | 67004.35 | 94986.9933 | 5000 | 5479.9799 | 3299.43 | 3239.379 | 1671.3 | 1006.2848 | 54.78 | 812.8779 | 223.35 | 184.8161 | 1350 | 236.6221 | 0
2025-11-07 | 532128.1195 | 272249.29 | 240110.0161 | 128719.25 | 58734.691 | 30042.48 | 100906.0846 | 41483.21 | 37153.7124 | 67004.35 | 95223.6154 | 5000 | 5479.9799 | 3071.08 | 3239.379 | 1671.3 | 1006.2848 | 1112.72 | 812.8779 | 287.06 | 184.8161 | 0 | 236.6221 | 0
2025-11-08 | 537608.0994 | 272270 | 243349.3952 | 128719.25 | 59740.9758 | 30063.19 | 101718.9625 | 41483.21 | 37338.5284 | 67004.35 | 95460.2375 | 5000 | 5479.9799 | 20.71 | 3239.379 | 0 | 1006.2848 | 20.71 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-11-09 | 543088.0793 | 272270 | 246588.7742 | 128719.25 | 60747.2606 | 30063.19 | 102531.8405 | 41483.21 | 37523.3445 | 67004.35 | 95696.8595 | 5000 | 5479.9799 | 0 | 3239.379 | 0 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-11-10 | 548568.0592 | 273916.365 | 249828.1532 | 130337.625 | 61753.5455 | 30091.18 | 103344.7184 | 41483.21 | 37708.1605 | 67004.35 | 95933.4816 | 5000 | 5479.9799 | 1646.365 | 3239.379 | 1618.375 | 1006.2848 | 27.99 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-11-11 | 554048.0392 | 275659.34 | 253067.5323 | 131956 | 62759.8303 | 30133.05 | 104157.5963 | 41565.94 | 37892.9766 | 67004.35 | 96170.1037 | 5000 | 5479.9799 | 1742.975 | 3239.379 | 1618.375 | 1006.2848 | 41.87 | 812.8779 | 82.73 | 184.8161 | 0 | 236.6221 | 0
2025-11-12 | 559528.0191 | 277277.715 | 256306.9113 | 133574.375 | 63766.1152 | 30133.05 | 104970.4742 | 41565.94 | 38077.7926 | 67004.35 | 96406.7258 | 5000 | 5479.9799 | 1618.375 | 3239.379 | 1618.375 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-11-13 | 565007.999 | 284018.87 | 259546.2903 | 135192.75 | 64772.4 | 30133.05 | 105783.3522 | 41565.94 | 38262.6087 | 72127.13 | 96643.3478 | 5000 | 5479.9799 | 6741.155 | 3239.379 | 1618.375 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 5122.78 | 236.6221 | 0
2025-11-14 | 567580.8448 | 286139.145 | 260740.2065 | 136811.125 | 65236.4673 | 30634.95 | 106312.8935 | 41565.94 | 38262.6087 | 72127.13 | 97028.6689 | 5000 | 2572.8458 | 2120.275 | 1193.9161 | 1618.375 | 464.0673 | 501.9 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-15 | 570153.6906 | 288239.785 | 261934.1226 | 136811.125 | 65700.5346 | 32679.7 | 106842.4347 | 41621.83 | 38262.6087 | 72127.13 | 97413.99 | 5000 | 2572.8458 | 2100.64 | 1193.9161 | 0 | 464.0673 | 2044.75 | 529.5413 | 55.89 | 0 | 0 | 385.3211 | 0
2025-11-16 | 572726.5364 | 288239.785 | 263128.0387 | 136811.125 | 66164.6018 | 32679.7 | 107371.976 | 41621.83 | 38262.6087 | 72127.13 | 97799.3111 | 5000 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-17 | 575299.3822 | 288944.085 | 264321.9549 | 137515.425 | 66628.6691 | 32679.7 | 107901.5173 | 41621.83 | 38262.6087 | 72127.13 | 98184.6322 | 5000 | 2572.8458 | 704.3 | 1193.9161 | 704.3 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-18 | 577872.228 | 295580.995 | 265515.871 | 138219.725 | 67092.7364 | 32679.7 | 108431.0586 | 41621.83 | 38262.6087 | 78059.74 | 98569.9533 | 5000 | 2572.8458 | 6636.91 | 1193.9161 | 704.3 | 464.0673 | 0 | 529.5413 | 0 | 0 | 5932.61 | 385.3211 | 0
2025-11-19 | 580445.0738 | 296420.595 | 266709.7871 | 138924.025 | 67556.8037 | 32679.7 | 108960.5999 | 41621.83 | 38262.6087 | 78195.04 | 98955.2744 | 5000 | 2572.8458 | 839.6 | 1193.9161 | 704.3 | 464.0673 | 0 | 529.5413 | 0 | 0 | 135.3 | 385.3211 | 0
2025-11-20 | 583017.9196 | 297124.895 | 267903.7033 | 139628.325 | 68020.8709 | 32679.7 | 109490.1412 | 41621.83 | 38262.6087 | 78195.04 | 99340.5955 | 5000 | 2572.8458 | 704.3 | 1193.9161 | 704.3 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-21 | 585590.7654 | 297829.195 | 269097.6194 | 140332.625 | 68484.9382 | 32679.7 | 110019.6824 | 41621.83 | 38262.6087 | 78195.04 | 99725.9166 | 5000 | 2572.8458 | 704.3 | 1193.9161 | 704.3 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-22 | 588163.6112 | 297829.195 | 270291.5355 | 140332.625 | 68949.0055 | 32679.7 | 110549.2237 | 41621.83 | 38262.6087 | 78195.04 | 100111.2377 | 5000 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-23 | 590736.457 | 297829.195 | 271485.4517 | 140332.625 | 69413.0728 | 32679.7 | 111078.765 | 41621.83 | 38262.6087 | 78195.04 | 100496.5588 | 5000 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-24 | 593309.3028 | 298641.42 | 272679.3678 | 141144.85 | 69877.1401 | 32679.7 | 111608.3063 | 41621.83 | 38262.6087 | 78195.04 | 100881.8799 | 5000 | 2572.8458 | 812.225 | 1193.9161 | 812.225 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-25 | 595882.1486 | 299453.645 | 273873.284 | 141957.075 | 70341.2073 | 32679.7 | 112137.8476 | 41621.83 | 38262.6087 | 78195.04 | 101267.201 | 5000 | 2572.8458 | 812.225 | 1193.9161 | 812.225 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-26 | 598454.9944 | 300265.87 | 275067.2001 | 142769.3 | 70805.2746 | 32679.7 | 112667.3889 | 41621.83 | 38262.6087 | 78195.04 | 101652.5221 | 5000 | 2572.8458 | 812.225 | 1193.9161 | 812.225 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-27 | 601027.8402 | 301078.095 | 276261.1162 | 143581.525 | 71269.3419 | 32679.7 | 113196.9302 | 41621.83 | 38262.6087 | 78195.04 | 102037.8432 | 5000 | 2572.8458 | 812.225 | 1193.9161 | 812.225 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-28 | 603600.686 | 301890.32 | 277455.0324 | 144393.75 | 71733.4092 | 32679.7 | 113726.4714 | 41621.83 | 38262.6087 | 78195.04 | 102423.1643 | 5000 | 2572.8458 | 812.225 | 1193.9161 | 812.225 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-29 | 606173.5318 | 301890.32 | 278648.9485 | 144393.75 | 72197.4765 | 32679.7 | 114256.0127 | 41621.83 | 38262.6087 | 78195.04 | 102808.4854 | 5000 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-11-30 | 608746.3776 | 301959.33 | 279842.8646 | 144393.75 | 72661.5437 | 32748.71 | 114785.554 | 41621.83 | 38262.6087 | 78195.04 | 103193.8065 | 5000 | 2572.8458 | 69.01 | 1193.9161 | 0 | 464.0673 | 69.01 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-01 | 611319.2234 | 303269.54 | 281036.7808 | 145486.9 | 73125.611 | 32748.71 | 115315.0953 | 41621.83 | 38262.6087 | 78195.04 | 103579.1276 | 5217.06 | 2572.8458 | 1310.21 | 1193.9161 | 1093.15 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 217.06
2025-12-02 | 613892.0692 | 304546.37 | 282230.6969 | 146580.05 | 73589.6783 | 32748.71 | 115844.6366 | 41805.51 | 38262.6087 | 78195.04 | 103964.4487 | 5217.06 | 2572.8458 | 1276.83 | 1193.9161 | 1093.15 | 464.0673 | 0 | 529.5413 | 183.68 | 0 | 0 | 385.3211 | 0
2025-12-03 | 616464.915 | 305639.52 | 283424.613 | 147673.2 | 74053.7456 | 32748.71 | 116374.1779 | 41805.51 | 38262.6087 | 78195.04 | 104349.7698 | 5217.06 | 2572.8458 | 1093.15 | 1193.9161 | 1093.15 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-04 | 619037.7608 | 306732.67 | 284618.5292 | 148766.35 | 74517.8128 | 32748.71 | 116903.7191 | 41805.51 | 38262.6087 | 78195.04 | 104735.0909 | 5217.06 | 2572.8458 | 1093.15 | 1193.9161 | 1093.15 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-05 | 621610.6066 | 308657.1 | 285812.4453 | 149859.5 | 74981.8801 | 33248.71 | 117433.2604 | 42136.79 | 38262.6087 | 78195.04 | 105120.412 | 5217.06 | 2572.8458 | 1924.43 | 1193.9161 | 1093.15 | 464.0673 | 500 | 529.5413 | 331.28 | 0 | 0 | 385.3211 | 0
2025-12-06 | 624183.4524 | 308657.1 | 287006.3614 | 149859.5 | 75445.9474 | 33248.71 | 117962.8017 | 42136.79 | 38262.6087 | 78195.04 | 105505.7331 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-07 | 626756.2982 | 308657.1 | 288200.2776 | 149859.5 | 75910.0147 | 33248.71 | 118492.343 | 42136.79 | 38262.6087 | 78195.04 | 105891.0542 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-08 | 629329.144 | 309820.725 | 289394.1937 | 151023.125 | 76374.082 | 33248.71 | 119021.8843 | 42136.79 | 38262.6087 | 78195.04 | 106276.3753 | 5217.06 | 2572.8458 | 1163.625 | 1193.9161 | 1163.625 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-09 | 631901.9898 | 311479.66 | 290588.1099 | 152186.75 | 76838.1492 | 33248.71 | 119551.4256 | 42136.79 | 38262.6087 | 78690.35 | 106661.6964 | 5217.06 | 2572.8458 | 1658.935 | 1193.9161 | 1163.625 | 464.0673 | 0 | 529.5413 | 0 | 0 | 495.31 | 385.3211 | 0
2025-12-10 | 634474.8356 | 313943.285 | 291782.026 | 153350.375 | 77302.2165 | 33248.71 | 120080.9669 | 42136.79 | 38262.6087 | 79990.35 | 107047.0176 | 5217.06 | 2572.8458 | 2463.625 | 1193.9161 | 1163.625 | 464.0673 | 0 | 529.5413 | 0 | 0 | 1300 | 385.3211 | 0
2025-12-11 | 637047.6814 | 315938.88 | 292975.9421 | 154514 | 77766.2838 | 33248.71 | 120610.5081 | 42136.79 | 38262.6087 | 80822.32 | 107432.3387 | 5217.06 | 2572.8458 | 1995.595 | 1193.9161 | 1163.625 | 464.0673 | 0 | 529.5413 | 0 | 0 | 831.97 | 385.3211 | 0
2025-12-12 | 639620.5272 | 318956.995 | 294169.8583 | 155677.625 | 78230.3511 | 33948.71 | 121140.0494 | 42459.31 | 38262.6087 | 81654.29 | 107817.6598 | 5217.06 | 2572.8458 | 3018.115 | 1193.9161 | 1163.625 | 464.0673 | 700 | 529.5413 | 322.52 | 0 | 831.97 | 385.3211 | 0
2025-12-13 | 642193.373 | 318956.995 | 295363.7744 | 155677.625 | 78694.4183 | 33948.71 | 121669.5907 | 42459.31 | 38262.6087 | 81654.29 | 108202.9809 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-14 | 644766.2188 | 318956.995 | 296557.6905 | 155677.625 | 79158.4856 | 33948.71 | 122199.132 | 42459.31 | 38262.6087 | 81654.29 | 108588.302 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-15 | 647339.0646 | 320120.62 | 297751.6067 | 156841.25 | 79622.5529 | 33948.71 | 122728.6733 | 42459.31 | 38262.6087 | 81654.29 | 108973.6231 | 5217.06 | 2572.8458 | 1163.625 | 1193.9161 | 1163.625 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-16 | 649911.9104 | 321284.245 | 298945.5228 | 158004.875 | 80086.6202 | 33948.71 | 123258.2146 | 42459.31 | 38262.6087 | 81654.29 | 109358.9442 | 5217.06 | 2572.8458 | 1163.625 | 1193.9161 | 1163.625 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-17 | 652484.7562 | 322447.87 | 300139.4389 | 159168.5 | 80550.6875 | 33948.71 | 123787.7558 | 42459.31 | 38262.6087 | 81654.29 | 109744.2653 | 5217.06 | 2572.8458 | 1163.625 | 1193.9161 | 1163.625 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-18 | 655057.602 | 323611.495 | 301333.3551 | 160332.125 | 81014.7547 | 33948.71 | 124317.2971 | 42459.31 | 38262.6087 | 81654.29 | 110129.5864 | 5217.06 | 2572.8458 | 1163.625 | 1193.9161 | 1163.625 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-19 | 657630.4478 | 326807.92 | 302527.2712 | 161495.75 | 81478.822 | 35981.51 | 124846.8384 | 42459.31 | 38262.6087 | 81654.29 | 110514.9075 | 5217.06 | 2572.8458 | 3196.425 | 1193.9161 | 1163.625 | 464.0673 | 2032.8 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-20 | 660203.2936 | 327011.2 | 303721.1873 | 161495.75 | 81942.8893 | 36184.79 | 125376.3797 | 42459.31 | 38262.6087 | 81654.29 | 110900.2286 | 5217.06 | 2572.8458 | 203.28 | 1193.9161 | 0 | 464.0673 | 203.28 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-21 | 662776.1394 | 327011.2 | 304915.1035 | 161495.75 | 82406.9566 | 36184.79 | 125905.921 | 42459.31 | 38262.6087 | 81654.29 | 111285.5497 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-22 | 665348.9852 | 327102.9 | 306109.0196 | 161495.75 | 82871.0239 | 36184.79 | 126435.4623 | 42551.01 | 38262.6087 | 81654.29 | 111670.8708 | 5217.06 | 2572.8458 | 91.7 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 91.7 | 0 | 0 | 385.3211 | 0
2025-12-23 | 667921.831 | 331628.28 | 307302.9358 | 161495.75 | 83335.0911 | 36184.79 | 126965.0036 | 42551.01 | 38262.6087 | 86179.67 | 112056.1919 | 5217.06 | 2572.8458 | 4525.38 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 4525.38 | 385.3211 | 0
2025-12-24 | 670494.6768 | 331628.28 | 308496.8519 | 161495.75 | 83799.1584 | 36184.79 | 127494.5448 | 42551.01 | 38262.6087 | 86179.67 | 112441.513 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-25 | 673067.5226 | 331763.58 | 309690.768 | 161495.75 | 84263.2257 | 36184.79 | 128024.0861 | 42551.01 | 38262.6087 | 86314.97 | 112826.8341 | 5217.06 | 2572.8458 | 135.3 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 135.3 | 385.3211 | 0
2025-12-26 | 675640.3684 | 331763.58 | 310884.6842 | 161495.75 | 84727.293 | 36184.79 | 128553.6274 | 42551.01 | 38262.6087 | 86314.97 | 113212.1552 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-27 | 678213.2142 | 331763.58 | 312078.6003 | 161495.75 | 85191.3602 | 36184.79 | 129083.1687 | 42551.01 | 38262.6087 | 86314.97 | 113597.4763 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-28 | 680786.06 | 331763.58 | 313272.5164 | 161495.75 | 85655.4275 | 36184.79 | 129612.71 | 42551.01 | 38262.6087 | 86314.97 | 113982.7974 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2025-12-29 | 683358.9058 | 333787.27 | 314466.4326 | 162393.1 | 86119.4948 | 36184.79 | 130142.2513 | 43677.35 | 38262.6087 | 86314.97 | 114368.1185 | 5217.06 | 2572.8458 | 2023.69 | 1193.9161 | 897.35 | 464.0673 | 0 | 529.5413 | 1126.34 | 0 | 0 | 385.3211 | 0
2025-12-30 | 685931.7516 | 335184.62 | 315660.3487 | 163290.45 | 86583.5621 | 36184.79 | 130671.7925 | 43677.35 | 38262.6087 | 86814.97 | 114753.4396 | 5217.06 | 2572.8458 | 1397.35 | 1193.9161 | 897.35 | 464.0673 | 0 | 529.5413 | 0 | 0 | 500 | 385.3211 | 0
2025-12-31 | 688504.5974 | 336081.97 | 316854.2648 | 164187.8 | 87047.6294 | 36184.79 | 131201.3338 | 43677.35 | 38262.6087 | 86814.97 | 115138.7607 | 5217.06 | 2572.8458 | 897.35 | 1193.9161 | 897.35 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-01 | 691077.4432 | 336979.32 | 318048.181 | 165085.15 | 87511.6966 | 36184.79 | 131730.8751 | 43677.35 | 38262.6087 | 86814.97 | 115524.0818 | 5217.06 | 2572.8458 | 897.35 | 1193.9161 | 897.35 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-02 | 693650.289 | 337876.67 | 319242.0971 | 165982.5 | 87975.7639 | 36184.79 | 132260.4164 | 43677.35 | 38262.6087 | 86814.97 | 115909.4029 | 5217.06 | 2572.8458 | 897.35 | 1193.9161 | 897.35 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-03 | 696223.1348 | 337876.67 | 320436.0132 | 165982.5 | 88439.8312 | 36184.79 | 132789.9577 | 43677.35 | 38262.6087 | 86814.97 | 116294.724 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-04 | 698795.9806 | 337876.67 | 321629.9294 | 165982.5 | 88903.8985 | 36184.79 | 133319.499 | 43677.35 | 38262.6087 | 86814.97 | 116680.0451 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-05 | 701368.8264 | 338949.095 | 322823.8455 | 167054.925 | 89367.9657 | 36184.79 | 133849.0402 | 43677.35 | 38262.6087 | 86814.97 | 117065.3662 | 5217.06 | 2572.8458 | 1072.425 | 1193.9161 | 1072.425 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-06 | 703941.6722 | 352722 | 324017.7617 | 168127.35 | 89832.033 | 37260.27 | 134378.5815 | 43677.35 | 38262.6087 | 98439.97 | 117450.6873 | 5217.06 | 2572.8458 | 13772.905 | 1193.9161 | 1072.425 | 464.0673 | 1075.48 | 529.5413 | 0 | 0 | 11625 | 385.3211 | 0
2026-01-07 | 706514.518 | 355957.165 | 325211.6778 | 169199.775 | 90296.1003 | 37260.27 | 134908.1228 | 45840.09 | 38262.6087 | 98439.97 | 117836.0084 | 5217.06 | 2572.8458 | 3235.165 | 1193.9161 | 1072.425 | 464.0673 | 0 | 529.5413 | 2162.74 | 0 | 0 | 385.3211 | 0
2026-01-08 | 709087.3638 | 357029.59 | 326405.5939 | 170272.2 | 90760.1676 | 37260.27 | 135437.6641 | 45840.09 | 38262.6087 | 98439.97 | 118221.3295 | 5217.06 | 2572.8458 | 1072.425 | 1193.9161 | 1072.425 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-09 | 711660.2096 | 360134.815 | 327599.5101 | 171344.625 | 91224.2349 | 39293.07 | 135967.2054 | 45840.09 | 38262.6087 | 98439.97 | 118606.6506 | 5217.06 | 2572.8458 | 3105.225 | 1193.9161 | 1072.425 | 464.0673 | 2032.8 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-10 | 714233.0554 | 360134.815 | 328793.4262 | 171344.625 | 91688.3021 | 39293.07 | 136496.7467 | 45840.09 | 38262.6087 | 98439.97 | 118991.9717 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-11 | 716805.9012 | 360134.815 | 329987.3423 | 171344.625 | 92152.3694 | 39293.07 | 137026.288 | 45840.09 | 38262.6087 | 98439.97 | 119377.2928 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-12 | 719378.747 | 360835.115 | 331181.2585 | 172044.925 | 92616.4367 | 39293.07 | 137555.8292 | 45840.09 | 38262.6087 | 98439.97 | 119762.6139 | 5217.06 | 2572.8458 | 700.3 | 1193.9161 | 700.3 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-13 | 721951.5928 | 362348.535 | 332375.1746 | 172745.225 | 93080.504 | 40106.19 | 138085.3705 | 45840.09 | 38262.6087 | 98439.97 | 120147.935 | 5217.06 | 2572.8458 | 1513.42 | 1193.9161 | 700.3 | 464.0673 | 813.12 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-14 | 724524.4386 | 364066.835 | 333569.0907 | 173445.525 | 93544.5713 | 40831.79 | 138614.9118 | 46132.49 | 38262.6087 | 98439.97 | 120533.2561 | 5217.06 | 2572.8458 | 1718.3 | 1193.9161 | 700.3 | 464.0673 | 725.6 | 529.5413 | 292.4 | 0 | 0 | 385.3211 | 0
2026-01-15 | 727097.2844 | 364767.135 | 334763.0069 | 174145.825 | 94008.6385 | 40831.79 | 139144.4531 | 46132.49 | 38262.6087 | 98439.97 | 120918.5772 | 5217.06 | 2572.8458 | 700.3 | 1193.9161 | 700.3 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-16 | 729670.1302 | 372033.805 | 335956.923 | 174846.125 | 94472.7058 | 41881.79 | 139673.9944 | 46132.49 | 38262.6087 | 103956.34 | 121303.8983 | 5217.06 | 2572.8458 | 7266.67 | 1193.9161 | 700.3 | 464.0673 | 1050 | 529.5413 | 0 | 0 | 5516.37 | 385.3211 | 0
2026-01-17 | 732242.976 | 372033.805 | 337150.8392 | 174846.125 | 94936.7731 | 41881.79 | 140203.5357 | 46132.49 | 38262.6087 | 103956.34 | 121689.2194 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-18 | 734815.8218 | 372033.805 | 338344.7553 | 174846.125 | 95400.8404 | 41881.79 | 140733.0769 | 46132.49 | 38262.6087 | 103956.34 | 122074.5405 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-19 | 737388.6676 | 374147.875 | 339538.6714 | 175873.425 | 95864.9076 | 41881.79 | 141262.6182 | 47202.82 | 38262.6087 | 103972.78 | 122459.8616 | 5217.06 | 2572.8458 | 2114.07 | 1193.9161 | 1027.3 | 464.0673 | 0 | 529.5413 | 1070.33 | 0 | 16.44 | 385.3211 | 0
2026-01-20 | 739961.5134 | 375175.175 | 340732.5876 | 176900.725 | 96328.9749 | 41881.79 | 141792.1595 | 47202.82 | 38262.6087 | 103972.78 | 122845.1827 | 5217.06 | 2572.8458 | 1027.3 | 1193.9161 | 1027.3 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-21 | 742534.3592 | 376202.475 | 341926.5037 | 177928.025 | 96793.0422 | 41881.79 | 142321.7008 | 47202.82 | 38262.6087 | 103972.78 | 123230.5038 | 5217.06 | 2572.8458 | 1027.3 | 1193.9161 | 1027.3 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-22 | 745107.205 | 379292.875 | 343120.4198 | 178955.325 | 97257.1095 | 42257.27 | 142851.2421 | 48609.68 | 38262.6087 | 104253.54 | 123615.8249 | 5217.06 | 2572.8458 | 3090.4 | 1193.9161 | 1027.3 | 464.0673 | 375.48 | 529.5413 | 1406.86 | 0 | 280.76 | 385.3211 | 0
2026-01-23 | 747680.0508 | 381120.175 | 344314.336 | 179982.625 | 97721.1768 | 43057.27 | 143380.7834 | 48609.68 | 38262.6087 | 104253.54 | 124001.146 | 5217.06 | 2572.8458 | 1827.3 | 1193.9161 | 1027.3 | 464.0673 | 800 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-24 | 750252.8966 | 381120.175 | 345508.2521 | 179982.625 | 98185.244 | 43057.27 | 143910.3247 | 48609.68 | 38262.6087 | 104253.54 | 124386.4671 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-25 | 752825.7424 | 381120.175 | 346702.1682 | 179982.625 | 98649.3113 | 43057.27 | 144439.8659 | 48609.68 | 38262.6087 | 104253.54 | 124771.7882 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-26 | 755398.5882 | 385085.79 | 347896.0844 | 181735.85 | 99113.3786 | 43057.27 | 144969.4072 | 50822.07 | 38262.6087 | 104253.54 | 125157.1093 | 5217.06 | 2572.8458 | 3965.615 | 1193.9161 | 1753.225 | 464.0673 | 0 | 529.5413 | 2212.39 | 0 | 0 | 385.3211 | 0
2026-01-27 | 757971.434 | 386839.015 | 349090.0005 | 183489.075 | 99577.4459 | 43057.27 | 145498.9485 | 50822.07 | 38262.6087 | 104253.54 | 125542.4304 | 5217.06 | 2572.8458 | 1753.225 | 1193.9161 | 1753.225 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-28 | 760544.2798 | 389645.36 | 350283.9166 | 185242.3 | 100041.5131 | 44110.39 | 146028.4898 | 50822.07 | 38262.6087 | 104253.54 | 125927.7515 | 5217.06 | 2572.8458 | 2806.345 | 1193.9161 | 1753.225 | 464.0673 | 1053.12 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-01-29 | 763117.1256 | 391990.475 | 351477.8328 | 186995.525 | 100505.5804 | 44110.39 | 146558.0311 | 51413.96 | 38262.6087 | 104253.54 | 126313.0726 | 5217.06 | 2572.8458 | 2345.115 | 1193.9161 | 1753.225 | 464.0673 | 0 | 529.5413 | 591.89 | 0 | 0 | 385.3211 | 0
2026-01-30 | 765689.9714 | 397172.24 | 352671.7489 | 188748.75 | 100969.6477 | 45613.93 | 147087.5724 | 53338.96 | 38262.6087 | 104253.54 | 126698.3937 | 5217.06 | 2572.8458 | 5181.765 | 1193.9161 | 1753.225 | 464.0673 | 1503.54 | 529.5413 | 1925 | 0 | 0 | 385.3211 | 0
2026-01-31 | 768262.8172 | 397172.24 | 353865.6651 | 188748.75 | 101433.715 | 45613.93 | 147617.1136 | 53338.96 | 38262.6087 | 104253.54 | 127083.7148 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-01 | 770835.663 | 397172.24 | 355059.5812 | 188748.75 | 101897.7823 | 45613.93 | 148146.6549 | 53338.96 | 38262.6087 | 104253.54 | 127469.0359 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-02 | 773408.5088 | 398951.99 | 356253.4973 | 189828.5 | 102361.8495 | 46313.93 | 148676.1962 | 53338.96 | 38262.6087 | 104253.54 | 127854.357 | 5217.06 | 2572.8458 | 1779.75 | 1193.9161 | 1079.75 | 464.0673 | 700 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-03 | 775981.3546 | 401908.54 | 357447.4135 | 190908.25 | 102825.9168 | 47794.75 | 149205.7375 | 53734.94 | 38262.6087 | 104253.54 | 128239.6781 | 5217.06 | 2572.8458 | 2956.55 | 1193.9161 | 1079.75 | 464.0673 | 1480.82 | 529.5413 | 395.98 | 0 | 0 | 385.3211 | 0
2026-02-04 | 778554.2004 | 406800.18 | 358641.3296 | 191988 | 103289.9841 | 47794.75 | 149735.2788 | 54596.83 | 38262.6087 | 107203.54 | 128624.9992 | 5217.06 | 2572.8458 | 4891.64 | 1193.9161 | 1079.75 | 464.0673 | 0 | 529.5413 | 861.89 | 0 | 2950 | 385.3211 | 0
2026-02-05 | 781127.0462 | 409148.98 | 359835.2457 | 193067.75 | 103754.0514 | 48920.45 | 150264.8201 | 54740.18 | 38262.6087 | 107203.54 | 129010.3203 | 5217.06 | 2572.8458 | 2348.8 | 1193.9161 | 1079.75 | 464.0673 | 1125.7 | 529.5413 | 143.35 | 0 | 0 | 385.3211 | 0
2026-02-06 | 783699.892 | 412384.17 | 361029.1619 | 194147.5 | 104218.1187 | 49782.09 | 150794.3613 | 56033.98 | 38262.6087 | 107203.54 | 129395.6414 | 5217.06 | 2572.8458 | 3235.19 | 1193.9161 | 1079.75 | 464.0673 | 861.64 | 529.5413 | 1293.8 | 0 | 0 | 385.3211 | 0
2026-02-07 | 786272.7378 | 412384.17 | 362223.078 | 194147.5 | 104682.1859 | 49782.09 | 151323.9026 | 56033.98 | 38262.6087 | 107203.54 | 129780.9625 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-08 | 788845.5836 | 412384.17 | 363416.9941 | 194147.5 | 105146.2532 | 49782.09 | 151853.4439 | 56033.98 | 38262.6087 | 107203.54 | 130166.2836 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-09 | 791418.4294 | 413793.24 | 364610.9103 | 195428.55 | 105610.3205 | 49782.09 | 152382.9852 | 56162 | 38262.6087 | 107203.54 | 130551.6047 | 5217.06 | 2572.8458 | 1409.07 | 1193.9161 | 1281.05 | 464.0673 | 0 | 529.5413 | 128.02 | 0 | 0 | 385.3211 | 0
2026-02-10 | 793991.2752 | 417705.47 | 365804.8264 | 196709.6 | 106074.3878 | 51113.27 | 152912.5265 | 56162 | 38262.6087 | 108503.54 | 130936.9258 | 5217.06 | 2572.8458 | 3912.23 | 1193.9161 | 1281.05 | 464.0673 | 1331.18 | 529.5413 | 0 | 0 | 1300 | 385.3211 | 0
2026-02-11 | 796564.121 | 429786.76 | 366998.7425 | 197990.65 | 106538.455 | 52176.91 | 153442.0678 | 56448.1 | 38262.6087 | 117954.04 | 131322.2469 | 5217.06 | 2572.8458 | 12081.29 | 1193.9161 | 1281.05 | 464.0673 | 1063.64 | 529.5413 | 286.1 | 0 | 9450.5 | 385.3211 | 0
2026-02-12 | 799136.9668 | 431767.81 | 368192.6587 | 199271.7 | 107002.5223 | 52876.91 | 153971.6091 | 56448.1 | 38262.6087 | 117954.04 | 131707.568 | 5217.06 | 2572.8458 | 1981.05 | 1193.9161 | 1281.05 | 464.0673 | 700 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-13 | 801709.8126 | 433048.86 | 369386.5748 | 200552.75 | 107466.5896 | 52876.91 | 154501.1503 | 56448.1 | 38262.6087 | 117954.04 | 132092.8891 | 5217.06 | 2572.8458 | 1281.05 | 1193.9161 | 1281.05 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-14 | 804282.6584 | 433048.86 | 370580.491 | 200552.75 | 107930.6569 | 52876.91 | 155030.6916 | 56448.1 | 38262.6087 | 117954.04 | 132478.2102 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-15 | 806855.5042 | 433048.86 | 371774.4071 | 200552.75 | 108394.7242 | 52876.91 | 155560.2329 | 56448.1 | 38262.6087 | 117954.04 | 132863.5313 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-16 | 809428.35 | 434175.56 | 372968.3232 | 201679.45 | 108858.7914 | 52876.91 | 156089.7742 | 56448.1 | 38262.6087 | 117954.04 | 133248.8524 | 5217.06 | 2572.8458 | 1126.7 | 1193.9161 | 1126.7 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-17 | 812001.1958 | 435302.26 | 374162.2394 | 202806.15 | 109322.8587 | 52876.91 | 156619.3155 | 56448.1 | 38262.6087 | 117954.04 | 133634.1735 | 5217.06 | 2572.8458 | 1126.7 | 1193.9161 | 1126.7 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-18 | 814574.0416 | 436428.96 | 375356.1555 | 203932.85 | 109786.926 | 52876.91 | 157148.8568 | 56448.1 | 38262.6087 | 117954.04 | 134019.4946 | 5217.06 | 2572.8458 | 1126.7 | 1193.9161 | 1126.7 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-19 | 817146.8874 | 437691.32 | 376550.0716 | 205059.55 | 110250.9933 | 52876.91 | 157678.398 | 56448.1 | 38262.6087 | 118089.7 | 134404.8157 | 5217.06 | 2572.8458 | 1262.36 | 1193.9161 | 1126.7 | 464.0673 | 0 | 529.5413 | 0 | 0 | 135.66 | 385.3211 | 0
2026-02-20 | 819719.7332 | 442681.44 | 377743.9878 | 206186.25 | 110715.0606 | 55667.27 | 158207.9393 | 57469.49 | 38262.6087 | 118141.37 | 134790.1368 | 5217.06 | 2572.8458 | 4990.12 | 1193.9161 | 1126.7 | 464.0673 | 2790.36 | 529.5413 | 1021.39 | 0 | 51.67 | 385.3211 | 0
2026-02-21 | 822292.579 | 442681.44 | 378937.9039 | 206186.25 | 111179.1278 | 55667.27 | 158737.4806 | 57469.49 | 38262.6087 | 118141.37 | 135175.4579 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-22 | 824865.4248 | 442681.44 | 380131.82 | 206186.25 | 111643.1951 | 55667.27 | 159267.0219 | 57469.49 | 38262.6087 | 118141.37 | 135560.779 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-23 | 827438.2706 | 443761.19 | 381325.7362 | 207266 | 112107.2624 | 55667.27 | 159796.5632 | 57469.49 | 38262.6087 | 118141.37 | 135946.1001 | 5217.06 | 2572.8458 | 1079.75 | 1193.9161 | 1079.75 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-24 | 830011.1164 | 444963.44 | 382519.6523 | 208345.75 | 112571.3297 | 55667.27 | 160326.1045 | 57469.49 | 38262.6087 | 118263.87 | 136331.4212 | 5217.06 | 2572.8458 | 1202.25 | 1193.9161 | 1079.75 | 464.0673 | 0 | 529.5413 | 0 | 0 | 122.5 | 385.3211 | 0
2026-02-25 | 832583.9622 | 446043.19 | 383713.5684 | 209425.5 | 113035.3969 | 55667.27 | 160855.6458 | 57469.49 | 38262.6087 | 118263.87 | 136716.7423 | 5217.06 | 2572.8458 | 1079.75 | 1193.9161 | 1079.75 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-26 | 835156.808 | 448304.3 | 384907.4846 | 210505.25 | 113499.4642 | 55667.27 | 161385.187 | 58650.85 | 38262.6087 | 118263.87 | 137102.0634 | 5217.06 | 2572.8458 | 2261.11 | 1193.9161 | 1079.75 | 464.0673 | 0 | 529.5413 | 1181.36 | 0 | 0 | 385.3211 | 0
2026-02-27 | 837729.6538 | 449911.65 | 386101.4007 | 211585 | 113963.5315 | 56194.87 | 161914.7283 | 58650.85 | 38262.6087 | 118263.87 | 137487.3845 | 5217.06 | 2572.8458 | 1607.35 | 1193.9161 | 1079.75 | 464.0673 | 527.6 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-02-28 | 840302.4996 | 451648.13 | 387295.3169 | 211585 | 114427.5988 | 57931.35 | 162444.2696 | 58650.85 | 38262.6087 | 118263.87 | 137872.7056 | 5217.06 | 2572.8458 | 1736.48 | 1193.9161 | 0 | 464.0673 | 1736.48 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-03-01 | 842875.3454 | 451648.13 | 388489.233 | 211585 | 114891.6661 | 57931.35 | 162973.8109 | 58650.85 | 38262.6087 | 118263.87 | 138258.0267 | 5217.06 | 2572.8458 | 0 | 1193.9161 | 0 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-03-02 | 845448.1912 | 452043.88 | 389683.1491 | 211980.75 | 115355.7333 | 57931.35 | 163503.3522 | 58650.85 | 38262.6087 | 118263.87 | 138643.3478 | 5217.06 | 2572.8458 | 395.75 | 1193.9161 | 395.75 | 464.0673 | 0 | 529.5413 | 0 | 0 | 0 | 385.3211 | 0
2026-03-03 | 846626.3225 | 452439.63 | 390603.204 | 212376.5 | 115584.0541 | 57931.35 | 163533.1078 | 58650.85 | 38262.6087 | 118263.87 | 138643.3478 | 5217.06 | 1178.1313 | 395.75 | 920.0549 | 395.75 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-04 | 847804.4538 | 452928.89 | 391523.2589 | 212772.25 | 115812.3749 | 58024.86 | 163562.8635 | 58650.85 | 38262.6087 | 118263.87 | 138643.3478 | 5217.06 | 1178.1313 | 489.26 | 920.0549 | 395.75 | 228.3208 | 93.51 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-05 | 848982.5851 | 453324.64 | 392443.3137 | 213168 | 116040.6957 | 58024.86 | 163592.6191 | 58650.85 | 38262.6087 | 118263.87 | 138643.3478 | 5217.06 | 1178.1313 | 395.75 | 920.0549 | 395.75 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-06 | 850160.7164 | 453720.39 | 393363.3686 | 213563.75 | 116269.0165 | 58024.86 | 163622.3747 | 58650.85 | 38262.6087 | 118263.87 | 138643.3478 | 5217.06 | 1178.1313 | 395.75 | 920.0549 | 395.75 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-07 | 851338.8477 | 453720.39 | 394283.4235 | 213563.75 | 116497.3373 | 58024.86 | 163652.1304 | 58650.85 | 38262.6087 | 118263.87 | 138643.3478 | 5217.06 | 1178.1313 | 0 | 920.0549 | 0 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-08 | 852516.979 | 453720.39 | 395203.4783 | 213563.75 | 116725.6581 | 58024.86 | 163681.886 | 58650.85 | 38262.6087 | 118263.87 | 138643.3478 | 5217.06 | 1178.1313 | 0 | 920.0549 | 0 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-09 | 853695.1103 | 453918.265 | 396123.5332 | 213761.625 | 116953.9789 | 58024.86 | 163711.6416 | 58650.85 | 38262.6087 | 118263.87 | 138643.3478 | 5217.06 | 1178.1313 | 197.875 | 920.0549 | 197.875 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-10 | 854873.2416 | 454116.14 | 397043.5881 | 213959.5 | 117182.2997 | 58024.86 | 163741.3973 | 58650.85 | 38262.6087 | 118263.87 | 138643.3478 | 5217.06 | 1178.1313 | 197.875 | 920.0549 | 197.875 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-11 | 856051.373 | 454314.015 | 397963.643 | 214157.375 | 117410.6206 | 58024.86 | 163771.1529 | 58650.85 | 38262.6087 | 118263.87 | 138643.3478 | 5217.06 | 1178.1313 | 197.875 | 920.0549 | 197.875 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-12 | 857229.5043 | 455517.33 | 398883.6978 | 214355.25 | 117638.9414 | 58024.86 | 163800.9086 | 59656.29 | 38262.6087 | 118263.87 | 138643.3478 | 5217.06 | 1178.1313 | 1203.315 | 920.0549 | 197.875 | 228.3208 | 0 | 29.7556 | 1005.44 | 0 | 0 | 0 | 0
2026-03-13 | 858407.6356 | 458215.205 | 399803.7527 | 214553.125 | 117867.2622 | 58024.86 | 163830.6642 | 59656.29 | 38262.6087 | 120763.87 | 138643.3478 | 5217.06 | 1178.1313 | 2697.875 | 920.0549 | 197.875 | 228.3208 | 0 | 29.7556 | 0 | 0 | 2500 | 0 | 0
2026-03-14 | 859585.7669 | 458215.205 | 400723.8076 | 214553.125 | 118095.583 | 58024.86 | 163860.4198 | 59656.29 | 38262.6087 | 120763.87 | 138643.3478 | 5217.06 | 1178.1313 | 0 | 920.0549 | 0 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-15 | 860763.8982 | 458215.205 | 401643.8624 | 214553.125 | 118323.9038 | 58024.86 | 163890.1755 | 59656.29 | 38262.6087 | 120763.87 | 138643.3478 | 5217.06 | 1178.1313 | 0 | 920.0549 | 0 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-16 | 861942.0295 | 459071.03 | 402563.9173 | 215408.95 | 118552.2246 | 58024.86 | 163919.9311 | 59656.29 | 38262.6087 | 120763.87 | 138643.3478 | 5217.06 | 1178.1313 | 855.825 | 920.0549 | 855.825 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-17 | 863120.1608 | 459926.855 | 403483.9722 | 216264.775 | 118780.5454 | 58024.86 | 163949.6868 | 59656.29 | 38262.6087 | 120763.87 | 138643.3478 | 5217.06 | 1178.1313 | 855.825 | 920.0549 | 855.825 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-18 | 864298.2921 | 460782.68 | 404404.027 | 217120.6 | 119008.8662 | 58024.86 | 163979.4424 | 59656.29 | 38262.6087 | 120763.87 | 138643.3478 | 5217.06 | 1178.1313 | 855.825 | 920.0549 | 855.825 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-19 | 865476.4234 | 461638.505 | 405324.0819 | 217976.425 | 119237.187 | 58024.86 | 164009.198 | 59656.29 | 38262.6087 | 120763.87 | 138643.3478 | 5217.06 | 1178.1313 | 855.825 | 920.0549 | 855.825 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-20 | 866654.5548 | 462494.33 | 406244.1368 | 218832.25 | 119465.5078 | 58024.86 | 164038.9537 | 59656.29 | 38262.6087 | 120763.87 | 138643.3478 | 5217.06 | 1178.1313 | 855.825 | 920.0549 | 855.825 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-21 | 867832.6861 | 462494.33 | 407164.1917 | 218832.25 | 119693.8286 | 58024.86 | 164068.7093 | 59656.29 | 38262.6087 | 120763.87 | 138643.3478 | 5217.06 | 1178.1313 | 0 | 920.0549 | 0 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-22 | 869010.8174 | 462494.33 | 408084.2465 | 218832.25 | 119922.1494 | 57021.06 | 164098.465 | 59656.29 | 38262.6087 | 83163.87 | 138643.3478 | 5217.06 | 1178.1313 | 0 | 920.0549 | 0 | 228.3208 | 0 | 29.7556 | 0 | 0 | 0 | 0 | 0
2026-03-23 | 870188.9487 |  | 409004.3014 |  | 120150.4702 |  | 164128.2206 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-03-24 | 871367.08 |  | 409924.3563 |  | 120378.791 |  | 164157.9762 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-03-25 | 872545.2113 |  | 410844.4111 |  | 120607.1118 |  | 164187.7319 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-03-26 | 873723.3426 |  | 411764.466 |  | 120835.4326 |  | 164217.4875 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-03-27 | 874901.4739 |  | 412684.5209 |  | 121063.7534 |  | 164247.2432 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-03-28 | 876079.6052 |  | 413604.5758 |  | 121292.0742 |  | 164276.9988 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-03-29 | 877257.7366 |  | 414524.6306 |  | 121520.395 |  | 164306.7544 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-03-30 | 878435.8679 |  | 415444.6855 |  | 121748.7158 |  | 164336.5101 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-03-31 | 879613.9992 |  | 416364.7404 |  | 121977.0366 |  | 164366.2657 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-01 | 880792.1305 |  | 417284.7952 |  | 122205.3574 |  | 164396.0213 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-02 | 881970.2618 |  | 418204.8501 |  | 122433.6782 |  | 164425.777 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-03 | 883148.3931 |  | 419124.905 |  | 122661.999 |  | 164455.5326 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-04 | 884326.5244 |  | 420044.9598 |  | 122890.3198 |  | 164485.2883 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-05 | 885504.6557 |  | 420965.0147 |  | 123118.6406 |  | 164515.0439 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-06 | 886682.787 |  | 421885.0696 |  | 123346.9614 |  | 164544.7995 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-07 | 887860.9184 |  | 422805.1245 |  | 123575.2822 |  | 164574.5552 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-08 | 889039.0497 |  | 423725.1793 |  | 123803.603 |  | 164604.3108 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-09 | 890217.181 |  | 424645.2342 |  | 124031.9238 |  | 164634.0665 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-10 | 891395.3123 |  | 425565.2891 |  | 124260.2446 |  | 164663.8221 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-11 | 892573.4436 |  | 426485.3439 |  | 124488.5654 |  | 164693.5777 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-12 | 893751.5749 |  | 427405.3988 |  | 124716.8862 |  | 164723.3334 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-13 | 894929.7062 |  | 428325.4537 |  | 124945.207 |  | 164753.089 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-14 | 896107.8375 |  | 429245.5085 |  | 125173.5278 |  | 164782.8447 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-15 | 897285.9689 |  | 430165.5634 |  | 125401.8486 |  | 164812.6003 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-16 | 898464.1002 |  | 431085.6183 |  | 125630.1694 |  | 164842.3559 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-17 | 899642.2315 |  | 432005.6732 |  | 125858.4902 |  | 164872.1116 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-18 | 900820.3628 |  | 432925.728 |  | 126086.811 |  | 164901.8672 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-19 | 901998.4941 |  | 433845.7829 |  | 126315.1318 |  | 164931.6229 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-20 | 903176.6254 |  | 434765.8378 |  | 126543.4526 |  | 164961.3785 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-21 | 904354.7567 |  | 435685.8926 |  | 126771.7734 |  | 164991.1341 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-22 | 905532.888 |  | 436605.9475 |  | 127000.0942 |  | 165020.8898 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-23 | 906711.0193 |  | 437526.0024 |  | 127228.415 |  | 165050.6454 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-24 | 907889.1507 |  | 438446.0572 |  | 127456.7358 |  | 165080.401 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-25 | 909067.282 |  | 439366.1121 |  | 127685.0566 |  | 165110.1567 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-26 | 910245.4133 |  | 440286.167 |  | 127913.3774 |  | 165139.9123 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-27 | 911423.5446 |  | 441206.2219 |  | 128141.6982 |  | 165169.668 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-28 | 912601.6759 |  | 442126.2767 |  | 128370.019 |  | 165199.4236 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-29 | 913779.8072 |  | 443046.3316 |  | 128598.3398 |  | 165229.1792 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-04-30 | 914957.9385 |  | 443966.3865 |  | 128826.6607 |  | 165258.9349 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-01 | 916136.0698 |  | 444886.4413 |  | 129054.9815 |  | 165288.6905 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-02 | 917314.2011 |  | 445806.4962 |  | 129283.3023 |  | 165318.4462 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-03 | 918492.3325 |  | 446726.5511 |  | 129511.6231 |  | 165348.2018 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-04 | 919670.4638 |  | 447646.6059 |  | 129739.9439 |  | 165377.9574 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-05 | 920848.5951 |  | 448566.6608 |  | 129968.2647 |  | 165407.7131 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-06 | 922026.7264 |  | 449486.7157 |  | 130196.5855 |  | 165437.4687 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-07 | 923204.8577 |  | 450406.7706 |  | 130424.9063 |  | 165467.2244 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-08 | 924382.989 |  | 451326.8254 |  | 130653.2271 |  | 165496.98 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-09 | 925561.1203 |  | 452246.8803 |  | 130881.5479 |  | 165526.7356 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-10 | 926739.2516 |  | 453166.9352 |  | 131109.8687 |  | 165556.4913 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-11 | 927917.3829 |  | 454086.99 |  | 131338.1895 |  | 165586.2469 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-12 | 929095.5143 |  | 455007.0449 |  | 131566.5103 |  | 165616.0025 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-13 | 930273.6456 |  | 455927.0998 |  | 131794.8311 |  | 165645.7582 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-14 | 931451.7769 |  | 456847.1546 |  | 132023.1519 |  | 165675.5138 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-15 | 932629.9082 |  | 457767.2095 |  | 132251.4727 |  | 165705.2695 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-16 | 933808.0395 |  | 458687.2644 |  | 132479.7935 |  | 165735.0251 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-17 | 934986.1708 |  | 459607.3193 |  | 132708.1143 |  | 165764.7807 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-18 | 936164.3021 |  | 460527.3741 |  | 132936.4351 |  | 165794.5364 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-19 | 937342.4334 |  | 461447.429 |  | 133164.7559 |  | 165824.292 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-20 | 938520.5647 |  | 462367.4839 |  | 133393.0767 |  | 165854.0477 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-21 | 939698.6961 |  | 463287.5387 |  | 133621.3975 |  | 165883.8033 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-22 | 940876.8274 |  | 464207.5936 |  | 133849.7183 |  | 165913.5589 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-23 | 942054.9587 |  | 465127.6485 |  | 134078.0391 |  | 165943.3146 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-24 | 943233.09 |  | 466047.7033 |  | 134306.3599 |  | 165973.0702 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-25 | 944411.2213 |  | 466967.7582 |  | 134534.6807 |  | 166002.8259 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-26 | 945589.3526 |  | 467887.8131 |  | 134763.0015 |  | 166032.5815 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-27 | 946767.4839 |  | 468807.868 |  | 134991.3223 |  | 166062.3371 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-28 | 947945.6152 |  | 469727.9228 |  | 135219.6431 |  | 166092.0928 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-29 | 949123.7465 |  | 470647.9777 |  | 135447.9639 |  | 166121.8484 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-30 | 950301.8779 |  | 471568.0326 |  | 135676.2847 |  | 166151.6041 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-05-31 | 951480.0092 |  | 472488.0874 |  | 135904.6055 |  | 166181.3597 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-01 | 952658.1405 |  | 473408.1423 |  | 136132.9263 |  | 166211.1153 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-02 | 953836.2718 |  | 474328.1972 |  | 136361.2471 |  | 166240.871 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-03 | 955014.4031 |  | 475248.252 |  | 136589.5679 |  | 166270.6266 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-04 | 956192.5344 |  | 476168.3069 |  | 136817.8887 |  | 166300.3822 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-05 | 957370.6657 |  | 477088.3618 |  | 137046.2095 |  | 166330.1379 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-06 | 958548.797 |  | 478008.4167 |  | 137274.5303 |  | 166359.8935 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-07 | 959726.9283 |  | 478928.4715 |  | 137502.8511 |  | 166389.6492 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-08 | 960905.0597 |  | 479848.5264 |  | 137731.1719 |  | 166419.4048 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-09 | 962083.191 |  | 480768.5813 |  | 137959.4927 |  | 166449.1604 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-10 | 963261.3223 |  | 481688.6361 |  | 138187.8135 |  | 166478.9161 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-11 | 964439.4536 |  | 482608.691 |  | 138416.1343 |  | 166508.6717 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-12 | 965617.5849 |  | 483528.7459 |  | 138644.4551 |  | 166538.4274 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-13 | 966795.7162 |  | 484448.8007 |  | 138872.7759 |  | 166568.183 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-14 | 967973.8475 |  | 485368.8556 |  | 139101.0967 |  | 166597.9386 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-15 | 969151.9788 |  | 486288.9105 |  | 139329.4175 |  | 166627.6943 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-16 | 970330.1101 |  | 487208.9654 |  | 139557.7383 |  | 166657.4499 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-17 | 971508.2415 |  | 488129.0202 |  | 139786.0591 |  | 166687.2056 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-18 | 972686.3728 |  | 489049.0751 |  | 140014.3799 |  | 166716.9612 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-19 | 973864.5041 |  | 489969.13 |  | 140242.7008 |  | 166746.7168 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-20 | 975042.6354 |  | 490889.1848 |  | 140471.0216 |  | 166776.4725 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-21 | 976220.7667 |  | 491809.2397 |  | 140699.3424 |  | 166806.2281 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-22 | 977398.898 |  | 492729.2946 |  | 140927.6632 |  | 166835.9838 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-23 | 978577.0293 |  | 493649.3495 |  | 141155.984 |  | 166865.7394 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-24 | 979755.1606 |  | 494569.4043 |  | 141384.3048 |  | 166895.495 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-25 | 980933.2919 |  | 495489.4592 |  | 141612.6256 |  | 166925.2507 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-26 | 982111.4233 |  | 496409.5141 |  | 141840.9464 |  | 166955.0063 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-27 | 983289.5546 |  | 497329.5689 |  | 142069.2672 |  | 166984.7619 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-28 | 984467.6859 |  | 498249.6238 |  | 142297.588 |  | 167014.5176 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-29 | 985645.8172 |  | 499169.6787 |  | 142525.9088 |  | 167044.2732 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-06-30 | 986823.9485 |  | 500089.7335 |  | 142754.2296 |  | 167074.0289 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-01 | 988002.0798 |  | 501009.7884 |  | 142982.5504 |  | 167103.7845 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-02 | 989180.2111 |  | 501929.8433 |  | 143210.8712 |  | 167133.5401 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-03 | 990358.3424 |  | 502849.8982 |  | 143439.192 |  | 167163.2958 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-04 | 991536.4737 |  | 503769.953 |  | 143667.5128 |  | 167193.0514 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-05 | 992714.6051 |  | 504690.0079 |  | 143895.8336 |  | 167222.8071 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-06 | 993892.7364 |  | 505610.0628 |  | 144124.1544 |  | 167252.5627 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-07 | 995070.8677 |  | 506530.1176 |  | 144352.4752 |  | 167282.3183 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-08 | 996248.999 |  | 507450.1725 |  | 144580.796 |  | 167312.074 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-09 | 997427.1303 |  | 508370.2274 |  | 144809.1168 |  | 167341.8296 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-10 | 998605.2616 |  | 509290.2822 |  | 145037.4376 |  | 167371.5853 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-11 | 999783.3929 |  | 510210.3371 |  | 145265.7584 |  | 167401.3409 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-12 | 1000961.5242 |  | 511130.392 |  | 145494.0792 |  | 167431.0965 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-13 | 1002139.6555 |  | 512050.4469 |  | 145722.4 |  | 167460.8522 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-14 | 1003317.7869 |  | 512970.5017 |  | 145950.7208 |  | 167490.6078 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-15 | 1004495.9182 |  | 513890.5566 |  | 146179.0416 |  | 167520.3635 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-16 | 1005674.0495 |  | 514810.6115 |  | 146407.3624 |  | 167550.1191 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-17 | 1006852.1808 |  | 515730.6663 |  | 146635.6832 |  | 167579.8747 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-18 | 1008030.3121 |  | 516650.7212 |  | 146864.004 |  | 167609.6304 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-19 | 1009208.4434 |  | 517570.7761 |  | 147092.3248 |  | 167639.386 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-20 | 1010386.5747 |  | 518490.8309 |  | 147320.6456 |  | 167669.1416 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-21 | 1011564.706 |  | 519410.8858 |  | 147548.9664 |  | 167698.8973 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-22 | 1012742.8374 |  | 520330.9407 |  | 147777.2872 |  | 167728.6529 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-23 | 1013920.9687 |  | 521250.9956 |  | 148005.608 |  | 167758.4086 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-24 | 1015099.1 |  | 522171.0504 |  | 148233.9288 |  | 167788.1642 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-25 | 1016277.2313 |  | 523091.1053 |  | 148462.2496 |  | 167817.9198 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-26 | 1017455.3626 |  | 524011.1602 |  | 148690.5704 |  | 167847.6755 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-27 | 1018633.4939 |  | 524931.215 |  | 148918.8912 |  | 167877.4311 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-28 | 1019811.6252 |  | 525851.2699 |  | 149147.212 |  | 167907.1868 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-29 | 1020989.7565 |  | 526771.3248 |  | 149375.5328 |  | 167936.9424 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-30 | 1022167.8878 |  | 527691.3796 |  | 149603.8536 |  | 167966.698 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-07-31 | 1023346.0192 |  | 528611.4345 |  | 149832.1744 |  | 167996.4537 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-01 | 1024524.1505 |  | 529531.4894 |  | 150060.4952 |  | 168026.2093 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-02 | 1025702.2818 |  | 530451.5443 |  | 150288.816 |  | 168055.965 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-03 | 1026880.4131 |  | 531371.5991 |  | 150517.1368 |  | 168085.7206 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-04 | 1028058.5444 |  | 532291.654 |  | 150745.4576 |  | 168115.4762 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-05 | 1029236.6757 |  | 533211.7089 |  | 150973.7784 |  | 168145.2319 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-06 | 1030414.807 |  | 534131.7637 |  | 151202.0992 |  | 168174.9875 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-07 | 1031592.9383 |  | 535051.8186 |  | 151430.4201 |  | 168204.7432 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-08 | 1032771.0696 |  | 535971.8735 |  | 151658.7409 |  | 168234.4988 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-09 | 1033949.201 |  | 536891.9283 |  | 151887.0617 |  | 168264.2544 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-10 | 1035127.3323 |  | 537811.9832 |  | 152115.3825 |  | 168294.0101 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-11 | 1036305.4636 |  | 538732.0381 |  | 152343.7033 |  | 168323.7657 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-12 | 1037483.5949 |  | 539652.093 |  | 152572.0241 |  | 168353.5213 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-13 | 1038661.7262 |  | 540572.1478 |  | 152800.3449 |  | 168383.277 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-14 | 1039839.8575 |  | 541492.2027 |  | 153028.6657 |  | 168413.0326 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-15 | 1041017.9888 |  | 542412.2576 |  | 153256.9865 |  | 168442.7883 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-16 | 1042196.1201 |  | 543332.3124 |  | 153485.3073 |  | 168472.5439 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-17 | 1043374.2514 |  | 544252.3673 |  | 153713.6281 |  | 168502.2995 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-18 | 1044552.3828 |  | 545172.4222 |  | 153941.9489 |  | 168532.0552 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-19 | 1045730.5141 |  | 546092.477 |  | 154170.2697 |  | 168561.8108 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-20 | 1046908.6454 |  | 547012.5319 |  | 154398.5905 |  | 168591.5665 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-21 | 1048086.7767 |  | 547932.5868 |  | 154626.9113 |  | 168621.3221 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-22 | 1049264.908 |  | 548852.6417 |  | 154855.2321 |  | 168651.0777 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-23 | 1050443.0393 |  | 549772.6965 |  | 155083.5529 |  | 168680.8334 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-24 | 1051621.1706 |  | 550692.7514 |  | 155311.8737 |  | 168710.589 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-25 | 1052799.3019 |  | 551612.8063 |  | 155540.1945 |  | 168740.3447 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-26 | 1053977.4332 |  | 552532.8611 |  | 155768.5153 |  | 168770.1003 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-27 | 1055155.5646 |  | 553452.916 |  | 155996.8361 |  | 168799.8559 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-28 | 1056333.6959 |  | 554372.9709 |  | 156225.1569 |  | 168829.6116 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-29 | 1057511.8272 |  | 555293.0257 |  | 156453.4777 |  | 168859.3672 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-30 | 1058689.9585 |  | 556213.0806 |  | 156681.7985 |  | 168889.1229 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-08-31 | 1059868.0898 |  | 557133.1355 |  | 156910.1193 |  | 168918.8785 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-01 | 1061046.2211 |  | 558053.1904 |  | 157138.4401 |  | 168948.6341 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-02 | 1062224.3524 |  | 558973.2452 |  | 157366.7609 |  | 168978.3898 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-03 | 1063402.4837 |  | 559893.3001 |  | 157595.0817 |  | 169008.1454 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-04 | 1064580.615 |  | 560813.355 |  | 157823.4025 |  | 169037.901 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-05 | 1065758.7464 |  | 561733.4098 |  | 158051.7233 |  | 169067.6567 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-06 | 1066936.8777 |  | 562653.4647 |  | 158280.0441 |  | 169097.4123 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-07 | 1068115.009 |  | 563573.5196 |  | 158508.3649 |  | 169127.168 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-08 | 1069293.1403 |  | 564493.5745 |  | 158736.6857 |  | 169156.9236 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-09 | 1070471.2716 |  | 565413.6293 |  | 158965.0065 |  | 169186.6792 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-10 | 1071649.4029 |  | 566333.6842 |  | 159193.3273 |  | 169216.4349 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-11 | 1072827.5342 |  | 567253.7391 |  | 159421.6481 |  | 169246.1905 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-12 | 1074005.6655 |  | 568173.7939 |  | 159649.9689 |  | 169275.9462 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-13 | 1075183.7968 |  | 569093.8488 |  | 159878.2897 |  | 169305.7018 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-14 | 1076361.9282 |  | 570013.9037 |  | 160106.6105 |  | 169335.4574 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-15 | 1077540.0595 |  | 570933.9585 |  | 160334.9313 |  | 169365.2131 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-16 | 1078718.1908 |  | 571854.0134 |  | 160563.2521 |  | 169394.9687 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-17 | 1079896.3221 |  | 572774.0683 |  | 160791.5729 |  | 169424.7244 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-18 | 1081074.4534 |  | 573694.1232 |  | 161019.8937 |  | 169454.48 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-19 | 1082252.5847 |  | 574614.178 |  | 161248.2145 |  | 169484.2356 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-20 | 1083430.716 |  | 575534.2329 |  | 161476.5353 |  | 169513.9913 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-21 | 1084608.8473 |  | 576454.2878 |  | 161704.8561 |  | 169543.7469 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-22 | 1085786.9786 |  | 577374.3426 |  | 161933.1769 |  | 169573.5025 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-23 | 1086965.11 |  | 578294.3975 |  | 162161.4977 |  | 169603.2582 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-24 | 1088143.2413 |  | 579214.4524 |  | 162389.8185 |  | 169633.0138 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-25 | 1089321.3726 |  | 580134.5072 |  | 162618.1393 |  | 169662.7695 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-26 | 1090499.5039 |  | 581054.5621 |  | 162846.4602 |  | 169692.5251 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-27 | 1091677.6352 |  | 581974.617 |  | 163074.781 |  | 169722.2807 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-28 | 1092855.7665 |  | 582894.6719 |  | 163303.1018 |  | 169752.0364 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-29 | 1094033.8978 |  | 583814.7267 |  | 163531.4226 |  | 169781.792 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-09-30 | 1095212.0291 |  | 584734.7816 |  | 163759.7434 |  | 169811.5477 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-01 | 1096390.1604 |  | 585654.8365 |  | 163988.0642 |  | 169841.3033 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-02 | 1097568.2918 |  | 586574.8913 |  | 164216.385 |  | 169871.0589 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-03 | 1098746.4231 |  | 587494.9462 |  | 164444.7058 |  | 169900.8146 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-04 | 1099924.5544 |  | 588415.0011 |  | 164673.0266 |  | 169930.5702 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-05 | 1101102.6857 |  | 589335.0559 |  | 164901.3474 |  | 169960.3259 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-06 | 1102280.817 |  | 590255.1108 |  | 165129.6682 |  | 169990.0815 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-07 | 1103458.9483 |  | 591175.1657 |  | 165357.989 |  | 170019.8371 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-08 | 1104637.0796 |  | 592095.2206 |  | 165586.3098 |  | 170049.5928 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-09 | 1105815.2109 |  | 593015.2754 |  | 165814.6306 |  | 170079.3484 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-10 | 1106993.3422 |  | 593935.3303 |  | 166042.9514 |  | 170109.1041 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-11 | 1108171.4736 |  | 594855.3852 |  | 166271.2722 |  | 170138.8597 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-12 | 1109349.6049 |  | 595775.44 |  | 166499.593 |  | 170168.6153 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-13 | 1110527.7362 |  | 596695.4949 |  | 166727.9138 |  | 170198.371 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-14 | 1111705.8675 |  | 597615.5498 |  | 166956.2346 |  | 170228.1266 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-15 | 1112883.9988 |  | 598535.6046 |  | 167184.5554 |  | 170257.8822 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-16 | 1114062.1301 |  | 599455.6595 |  | 167412.8762 |  | 170287.6379 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-17 | 1115240.2614 |  | 600375.7144 |  | 167641.197 |  | 170317.3935 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-18 | 1116418.3927 |  | 601295.7693 |  | 167869.5178 |  | 170347.1492 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-19 | 1117596.524 |  | 602215.8241 |  | 168097.8386 |  | 170376.9048 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-20 | 1118774.6554 |  | 603135.879 |  | 168326.1594 |  | 170406.6604 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-21 | 1119952.7867 |  | 604055.9339 |  | 168554.4802 |  | 170436.4161 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-22 | 1121130.918 |  | 604975.9887 |  | 168782.801 |  | 170466.1717 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-23 | 1122309.0493 |  | 605896.0436 |  | 169011.1218 |  | 170495.9274 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-24 | 1123487.1806 |  | 606816.0985 |  | 169239.4426 |  | 170525.683 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-25 | 1124665.3119 |  | 607736.1533 |  | 169467.7634 |  | 170555.4386 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-26 | 1125843.4432 |  | 608656.2082 |  | 169696.0842 |  | 170585.1943 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-27 | 1127021.5745 |  | 609576.2631 |  | 169924.405 |  | 170614.9499 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-28 | 1128199.7059 |  | 610496.318 |  | 170152.7258 |  | 170644.7056 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-29 | 1129377.8372 |  | 611416.3728 |  | 170381.0466 |  | 170674.4612 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-30 | 1130555.9685 |  | 612336.4277 |  | 170609.3674 |  | 170704.2168 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-10-31 | 1131734.0998 |  | 613256.4826 |  | 170837.6882 |  | 170733.9725 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-01 | 1132912.2311 |  | 614176.5374 |  | 171066.009 |  | 170763.7281 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-02 | 1134090.3624 |  | 615096.5923 |  | 171294.3298 |  | 170793.4838 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-03 | 1135268.4937 |  | 616016.6472 |  | 171522.6506 |  | 170823.2394 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-04 | 1136446.625 |  | 616936.702 |  | 171750.9714 |  | 170852.995 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-05 | 1137624.7563 |  | 617856.7569 |  | 171979.2922 |  | 170882.7507 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-06 | 1138802.8877 |  | 618776.8118 |  | 172207.613 |  | 170912.5063 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-07 | 1139981.019 |  | 619696.8667 |  | 172435.9338 |  | 170942.2619 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-08 | 1141159.1503 |  | 620616.9215 |  | 172664.2546 |  | 170972.0176 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-09 | 1142337.2816 |  | 621536.9764 |  | 172892.5754 |  | 171001.7732 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-10 | 1143515.4129 |  | 622457.0313 |  | 173120.8962 |  | 171031.5289 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-11 | 1144693.5442 |  | 623377.0861 |  | 173349.217 |  | 171061.2845 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-12 | 1145871.6755 |  | 624297.141 |  | 173577.5378 |  | 171091.0401 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-13 | 1147049.8068 |  | 625217.1959 |  | 173805.8586 |  | 171120.7958 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-14 | 1148227.9381 |  | 626137.2507 |  | 174034.1794 |  | 171150.5514 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-15 | 1149406.0695 |  | 627057.3056 |  | 174262.5003 |  | 171180.3071 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-16 | 1150584.2008 |  | 627977.3605 |  | 174490.8211 |  | 171210.0627 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-17 | 1151762.3321 |  | 628897.4154 |  | 174719.1419 |  | 171239.8183 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-18 | 1152940.4634 |  | 629817.4702 |  | 174947.4627 |  | 171269.574 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-19 | 1154118.5947 |  | 630737.5251 |  | 175175.7835 |  | 171299.3296 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-20 | 1155296.726 |  | 631657.58 |  | 175404.1043 |  | 171329.0853 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-21 | 1156474.8573 |  | 632577.6348 |  | 175632.4251 |  | 171358.8409 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-22 | 1157652.9886 |  | 633497.6897 |  | 175860.7459 |  | 171388.5965 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-23 | 1158831.1199 |  | 634417.7446 |  | 176089.0667 |  | 171418.3522 |  | 38262.6087 |  | 138643.3478 |  | 1178.1313 |  | 920.0549 |  | 228.3208 |  | 29.7556 |  | 0 |  | 0
2026-11-24 | 1160861.1364 |  | 635672.2402 |  | 176552.0875 |  | 171418.3522 |  | 38575.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-11-25 | 1162891.1529 |  | 636926.7359 |  | 177015.1083 |  | 171418.3522 |  | 38887.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-11-26 | 1164921.1694 |  | 638181.2315 |  | 177478.1292 |  | 171418.3522 |  | 39200.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-11-27 | 1166951.1858 |  | 639435.7271 |  | 177941.15 |  | 171418.3522 |  | 39512.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-11-28 | 1168981.2023 |  | 640690.2228 |  | 178404.1708 |  | 171418.3522 |  | 39825.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-11-29 | 1171011.2188 |  | 641944.7184 |  | 178867.1917 |  | 171418.3522 |  | 40137.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-11-30 | 1173041.2352 |  | 643199.214 |  | 179330.2125 |  | 171418.3522 |  | 40450.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-01 | 1175071.2517 |  | 644453.7097 |  | 179793.2333 |  | 171418.3522 |  | 40762.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-02 | 1177101.2682 |  | 645708.2053 |  | 180256.2542 |  | 171418.3522 |  | 41075.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-03 | 1179131.2846 |  | 646962.701 |  | 180719.275 |  | 171418.3522 |  | 41387.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-04 | 1181161.3011 |  | 648217.1966 |  | 181182.2958 |  | 171418.3522 |  | 41700.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-05 | 1183191.3176 |  | 649471.6922 |  | 181645.3167 |  | 171418.3522 |  | 42012.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-06 | 1185221.3341 |  | 650726.1879 |  | 182108.3375 |  | 171418.3522 |  | 42325.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-07 | 1187251.3505 |  | 651980.6835 |  | 182571.3583 |  | 171418.3522 |  | 42637.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-08 | 1189281.367 |  | 653235.1791 |  | 183034.3792 |  | 171418.3522 |  | 42950.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-09 | 1191311.3835 |  | 654489.6748 |  | 183497.4 |  | 171418.3522 |  | 43262.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-10 | 1193341.3999 |  | 655744.1704 |  | 183960.4208 |  | 171418.3522 |  | 43575.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-11 | 1195371.4164 |  | 656998.666 |  | 184423.4417 |  | 171418.3522 |  | 43887.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-12 | 1197401.4329 |  | 658253.1617 |  | 184886.4625 |  | 171418.3522 |  | 44200.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-13 | 1199431.4494 |  | 659507.6573 |  | 185349.4833 |  | 171418.3522 |  | 44512.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-14 | 1201461.4658 |  | 660762.153 |  | 185812.5042 |  | 171418.3522 |  | 44825.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-15 | 1203491.4823 |  | 662016.6486 |  | 186275.525 |  | 171418.3522 |  | 45137.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-16 | 1205521.4988 |  | 663271.1442 |  | 186738.5458 |  | 171418.3522 |  | 45450.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-17 | 1207551.5152 |  | 664525.6399 |  | 187201.5667 |  | 171418.3522 |  | 45762.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-18 | 1209581.5317 |  | 665780.1355 |  | 187664.5875 |  | 171418.3522 |  | 46075.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-19 | 1211611.5482 |  | 667034.6311 |  | 188127.6083 |  | 171418.3522 |  | 46387.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-20 | 1213641.5646 |  | 668289.1268 |  | 188590.6292 |  | 171418.3522 |  | 46700.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-21 | 1215671.5811 |  | 669543.6224 |  | 189053.65 |  | 171418.3522 |  | 47012.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-22 | 1217701.5976 |  | 670798.1181 |  | 189516.6708 |  | 171418.3522 |  | 47325.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-23 | 1219731.6141 |  | 672052.6137 |  | 189979.6917 |  | 171418.3522 |  | 47637.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-24 | 1221761.6305 |  | 673307.1093 |  | 190442.7125 |  | 171418.3522 |  | 47950.1087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0
2026-12-25 | 1223791.647 |  | 674561.605 |  | 190905.7333 |  | 171418.3522 |  | 48262.6087 |  | 138643.3478 |  | 2030.0165 |  | 1254.4956 |  | 463.0208 |  | 0 |  | 312.5 |  | 0

## Labor Cost
Date | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned 5101 · Salary and wages (Direct) (Cumulative) | Actual 5101 · Salary and wages (Direct) (Cumulative) | Planned 5102 · Payroll taxes (Direct) (Cumulative) | Actual 5102 · Payroll taxes (Direct) (Cumulative)
2025-04-02 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0
2025-04-03 | 1914.2857 | 0 | 1914.2857 | 0 | 0 | 0
2025-04-04 | 2871.4286 | 0 | 2871.4286 | 0 | 0 | 0
2025-04-05 | 3828.5714 | 0 | 3828.5714 | 0 | 0 | 0
2025-04-06 | 4785.7143 | 0 | 4785.7143 | 0 | 0 | 0
2025-04-07 | 5742.8571 | 1126.6 | 5742.8571 | 1126.6 | 0 | 1126.6
2025-04-08 | 6700 | 2253.2 | 6700 | 2253.2 | 0 | 2253.2
2025-04-09 | 7657.1429 | 3379.8 | 7657.1429 | 3379.8 | 0 | 3379.8
2025-04-10 | 8614.2857 | 4506.4 | 8614.2857 | 4506.4 | 0 | 4506.4
2025-04-11 | 9571.4286 | 5633 | 9571.4286 | 5633 | 0 | 5633
2025-04-12 | 10528.5714 | 5633 | 10528.5714 | 5633 | 0 | 5633
2025-04-13 | 11485.7143 | 5633 | 11485.7143 | 5633 | 0 | 5633
2025-04-14 | 12442.8571 | 5847.4 | 12442.8571 | 5847.4 | 0 | 5847.4
2025-04-15 | 13400 | 6061.8 | 13400 | 6061.8 | 0 | 6061.8
2025-04-16 | 14357.1429 | 6276.2 | 14357.1429 | 6276.2 | 0 | 6276.2
2025-04-17 | 15314.2857 | 6490.6 | 15314.2857 | 6490.6 | 0 | 6490.6
2025-04-18 | 16271.4286 | 6705 | 16271.4286 | 6705 | 0 | 6705
2025-04-19 | 17228.5714 | 6705 | 17228.5714 | 6705 | 0 | 6705
2025-04-20 | 18185.7143 | 6705 | 18185.7143 | 6705 | 0 | 6705
2025-04-21 | 19142.8571 | 7087.15 | 19142.8571 | 7087.15 | 0 | 7087.15
2025-04-22 | 20100 | 7469.3 | 20100 | 7469.3 | 0 | 7469.3
2025-04-23 | 21057.1429 | 7851.45 | 21057.1429 | 7851.45 | 0 | 7851.45
2025-04-24 | 22014.2857 | 8233.6 | 22014.2857 | 8233.6 | 0 | 8233.6
2025-04-25 | 22971.4286 | 8615.75 | 22971.4286 | 8615.75 | 0 | 8615.75
2025-04-26 | 23928.5714 | 8615.75 | 23928.5714 | 8615.75 | 0 | 8615.75
2025-04-27 | 24885.7143 | 8615.75 | 24885.7143 | 8615.75 | 0 | 8615.75
2025-04-28 | 25842.8571 | 8615.75 | 25842.8571 | 8615.75 | 0 | 8615.75
2025-04-29 | 26800 | 8615.75 | 26800 | 8615.75 | 0 | 8615.75
2025-04-30 | 27757.1429 | 8615.75 | 27757.1429 | 8615.75 | 0 | 8615.75
2025-05-01 | 28714.2857 | 8615.75 | 28714.2857 | 8615.75 | 0 | 8615.75
2025-05-02 | 29671.4286 | 8615.75 | 29671.4286 | 8615.75 | 0 | 8615.75
2025-05-03 | 30628.5714 | 8615.75 | 30628.5714 | 8615.75 | 0 | 8615.75
2025-05-04 | 31585.7143 | 8615.75 | 31585.7143 | 8615.75 | 0 | 8615.75
2025-05-05 | 32542.8571 | 8615.75 | 32542.8571 | 8615.75 | 0 | 8615.75
2025-05-06 | 33500 | 8615.75 | 33500 | 8615.75 | 0 | 8615.75
2025-05-07 | 34457.1429 | 8615.75 | 34457.1429 | 8615.75 | 0 | 8615.75
2025-05-08 | 35414.2857 | 8615.75 | 35414.2857 | 8615.75 | 0 | 8615.75
2025-05-09 | 36371.4286 | 8615.75 | 36371.4286 | 8615.75 | 0 | 8615.75
2025-05-10 | 37328.5714 | 8615.75 | 37328.5714 | 8615.75 | 0 | 8615.75
2025-05-11 | 38285.7143 | 8615.75 | 38285.7143 | 8615.75 | 0 | 8615.75
2025-05-12 | 39242.8571 | 8615.75 | 39242.8571 | 8615.75 | 0 | 8615.75
2025-05-13 | 40200 | 8615.75 | 40200 | 8615.75 | 0 | 8615.75
2025-05-14 | 41157.1429 | 8615.75 | 41157.1429 | 8615.75 | 0 | 8615.75
2025-05-15 | 42114.2857 | 8615.75 | 42114.2857 | 8615.75 | 0 | 8615.75
2025-05-16 | 43071.4286 | 8615.75 | 43071.4286 | 8615.75 | 0 | 8615.75
2025-05-17 | 44028.5714 | 8615.75 | 44028.5714 | 8615.75 | 0 | 8615.75
2025-05-18 | 44985.7143 | 8615.75 | 44985.7143 | 8615.75 | 0 | 8615.75
2025-05-19 | 45942.8571 | 8615.75 | 45942.8571 | 8615.75 | 0 | 8615.75
2025-05-20 | 46900 | 8615.75 | 46900 | 8615.75 | 0 | 8615.75
2025-05-21 | 47857.1429 | 8615.75 | 47857.1429 | 8615.75 | 0 | 8615.75
2025-05-22 | 48814.2857 | 8615.75 | 48814.2857 | 8615.75 | 0 | 8615.75
2025-05-23 | 49771.4286 | 8615.75 | 49771.4286 | 8615.75 | 0 | 8615.75
2025-05-24 | 50728.5714 | 8615.75 | 50728.5714 | 8615.75 | 0 | 8615.75
2025-05-25 | 51685.7143 | 8615.75 | 51685.7143 | 8615.75 | 0 | 8615.75
2025-05-26 | 52642.8571 | 8615.75 | 52642.8571 | 8615.75 | 0 | 8615.75
2025-05-27 | 53600 | 8615.75 | 53600 | 8615.75 | 0 | 8615.75
2025-05-28 | 54557.1429 | 8615.75 | 54557.1429 | 8615.75 | 0 | 8615.75
2025-05-29 | 55514.2857 | 8615.75 | 55514.2857 | 8615.75 | 0 | 8615.75
2025-05-30 | 56471.4286 | 8615.75 | 56471.4286 | 8615.75 | 0 | 8615.75
2025-05-31 | 57428.5714 | 8615.75 | 57428.5714 | 8615.75 | 0 | 8615.75
2025-06-01 | 58385.7143 | 8615.75 | 58385.7143 | 8615.75 | 0 | 8615.75
2025-06-02 | 59342.8571 | 9212.3 | 59342.8571 | 9212.3 | 0 | 9212.3
2025-06-03 | 60300 | 9808.85 | 60300 | 9808.85 | 0 | 9808.85
2025-06-04 | 61257.1429 | 10405.4 | 61257.1429 | 10405.4 | 0 | 10405.4
2025-06-05 | 62214.2857 | 11001.95 | 62214.2857 | 11001.95 | 0 | 11001.95
2025-06-06 | 63171.4286 | 11598.5 | 63171.4286 | 11598.5 | 0 | 11598.5
2025-06-07 | 64128.5714 | 11598.5 | 64128.5714 | 11598.5 | 0 | 11598.5
2025-06-08 | 65085.7143 | 11598.5 | 65085.7143 | 11598.5 | 0 | 11598.5
2025-06-09 | 66042.8571 | 11873.45 | 66042.8571 | 11873.45 | 0 | 11873.45
2025-06-10 | 67000 | 12148.4 | 67000 | 12148.4 | 0 | 12148.4
2025-06-11 | 67957.1429 | 12423.35 | 67957.1429 | 12423.35 | 0 | 12423.35
2025-06-12 | 68914.2857 | 12698.3 | 68914.2857 | 12698.3 | 0 | 12698.3
2025-06-13 | 69871.4286 | 12973.25 | 69871.4286 | 12973.25 | 0 | 12973.25
2025-06-14 | 70828.5714 | 12973.25 | 70828.5714 | 12973.25 | 0 | 12973.25
2025-06-15 | 71785.7143 | 12973.25 | 71785.7143 | 12973.25 | 0 | 12973.25
2025-06-16 | 72742.8571 | 13523.15 | 72742.8571 | 13523.15 | 0 | 13523.15
2025-06-17 | 73700 | 14073.05 | 73700 | 14073.05 | 0 | 14073.05
2025-06-18 | 74657.1429 | 14622.95 | 74657.1429 | 14622.95 | 0 | 14622.95
2025-06-19 | 75614.2857 | 15172.85 | 75614.2857 | 15172.85 | 0 | 15172.85
2025-06-20 | 76571.4286 | 15722.75 | 76571.4286 | 15722.75 | 0 | 15722.75
2025-06-21 | 77528.5714 | 15722.75 | 77528.5714 | 15722.75 | 0 | 15722.75
2025-06-22 | 78485.7143 | 15722.75 | 78485.7143 | 15722.75 | 0 | 15722.75
2025-06-23 | 79442.8571 | 15997.7 | 79442.8571 | 15997.7 | 0 | 15997.7
2025-06-24 | 80400 | 16272.65 | 80400 | 16272.65 | 0 | 16272.65
2025-06-25 | 80520.2088 | 16547.6 | 80520.2088 | 16547.6 | 0 | 16547.6
2025-06-26 | 80640.4175 | 16822.55 | 80640.4175 | 16822.55 | 0 | 16822.55
2025-06-27 | 80760.6263 | 17097.5 | 80760.6263 | 17097.5 | 0 | 17097.5
2025-06-28 | 80880.8351 | 17097.5 | 80880.8351 | 17097.5 | 0 | 17097.5
2025-06-29 | 81001.0439 | 17097.5 | 81001.0439 | 17097.5 | 0 | 17097.5
2025-06-30 | 81121.2526 | 17714.4 | 81121.2526 | 17714.4 | 0 | 17714.4
2025-07-01 | 81241.4614 | 18331.3 | 81241.4614 | 18331.3 | 0 | 18331.3
2025-07-02 | 81361.6702 | 18948.2 | 81361.6702 | 18948.2 | 0 | 18948.2
2025-07-03 | 81481.8789 | 19565.1 | 81481.8789 | 19565.1 | 0 | 19565.1
2025-07-04 | 81602.0877 | 20182 | 81602.0877 | 20182 | 0 | 20182
2025-07-05 | 81722.2965 | 20182 | 81722.2965 | 20182 | 0 | 20182
2025-07-06 | 81842.5053 | 20182 | 81842.5053 | 20182 | 0 | 20182
2025-07-07 | 81962.714 | 20835.625 | 81962.714 | 20835.625 | 0 | 20835.625
2025-07-08 | 82082.9228 | 21489.25 | 82082.9228 | 21489.25 | 0 | 21489.25
2025-07-09 | 82203.1316 | 22142.875 | 82203.1316 | 22142.875 | 0 | 22142.875
2025-07-10 | 82323.3403 | 22796.5 | 82323.3403 | 22796.5 | 0 | 22796.5
2025-07-11 | 82443.5491 | 23450.125 | 82443.5491 | 23450.125 | 0 | 23450.125
2025-07-12 | 82563.7579 | 23450.125 | 82563.7579 | 23450.125 | 0 | 23450.125
2025-07-13 | 82683.9667 | 23450.125 | 82683.9667 | 23450.125 | 0 | 23450.125
2025-07-14 | 82804.1754 | 24210.95 | 82804.1754 | 24210.95 | 0 | 24210.95
2025-07-15 | 82924.3842 | 24971.775 | 82924.3842 | 24971.775 | 0 | 24971.775
2025-07-16 | 83044.593 | 25732.6 | 83044.593 | 25732.6 | 0 | 25732.6
2025-07-17 | 83164.8017 | 26493.425 | 83164.8017 | 26493.425 | 0 | 26493.425
2025-07-18 | 83285.0105 | 27254.25 | 83285.0105 | 27254.25 | 0 | 27254.25
2025-07-19 | 83405.2193 | 27254.25 | 83405.2193 | 27254.25 | 0 | 27254.25
2025-07-20 | 83525.4281 | 27254.25 | 83525.4281 | 27254.25 | 0 | 27254.25
2025-07-21 | 83645.6368 | 27907.875 | 83645.6368 | 27907.875 | 0 | 27907.875
2025-07-22 | 83765.8456 | 28561.5 | 83765.8456 | 28561.5 | 0 | 28561.5
2025-07-23 | 83886.0544 | 29215.125 | 83886.0544 | 29215.125 | 0 | 29215.125
2025-07-24 | 84006.2631 | 29868.75 | 84006.2631 | 29868.75 | 0 | 29868.75
2025-07-25 | 84126.4719 | 30522.375 | 84126.4719 | 30522.375 | 0 | 30522.375
2025-07-26 | 84246.6807 | 30522.375 | 84246.6807 | 30522.375 | 0 | 30522.375
2025-07-27 | 84366.8895 | 30522.375 | 84366.8895 | 30522.375 | 0 | 30522.375
2025-07-28 | 84487.0982 | 31122.4 | 84487.0982 | 31122.4 | 0 | 31122.4
2025-07-29 | 84607.307 | 31722.425 | 84607.307 | 31722.425 | 0 | 31722.425
2025-07-30 | 84727.5158 | 32322.45 | 84727.5158 | 32322.45 | 0 | 32322.45
2025-07-31 | 84847.7245 | 32922.475 | 84847.7245 | 32922.475 | 0 | 32922.475
2025-08-01 | 84967.9333 | 33522.5 | 84967.9333 | 33522.5 | 0 | 33522.5
2025-08-02 | 85088.1421 | 33522.5 | 85088.1421 | 33522.5 | 0 | 33522.5
2025-08-03 | 85208.3509 | 33522.5 | 85208.3509 | 33522.5 | 0 | 33522.5
2025-08-04 | 85328.5596 | 34126 | 85328.5596 | 34126 | 0 | 34126
2025-08-05 | 85448.7684 | 34729.5 | 85448.7684 | 34729.5 | 0 | 34729.5
2025-08-06 | 85568.9772 | 35333 | 85568.9772 | 35333 | 0 | 35333
2025-08-07 | 85689.1859 | 35936.5 | 85689.1859 | 35936.5 | 0 | 35936.5
2025-08-08 | 85809.3947 | 36540 | 85809.3947 | 36540 | 0 | 36540
2025-08-09 | 85929.6035 | 36540 | 85929.6035 | 36540 | 0 | 36540
2025-08-10 | 86049.8123 | 36540 | 86049.8123 | 36540 | 0 | 36540
2025-08-11 | 86170.021 | 37089.9 | 86170.021 | 37089.9 | 0 | 37089.9
2025-08-12 | 86290.2298 | 37639.8 | 86290.2298 | 37639.8 | 0 | 37639.8
2025-08-13 | 86410.4386 | 38189.7 | 86410.4386 | 38189.7 | 0 | 38189.7
2025-08-14 | 86530.6473 | 38739.6 | 86530.6473 | 38739.6 | 0 | 38739.6
2025-08-15 | 86650.8561 | 39289.5 | 86650.8561 | 39289.5 | 0 | 39289.5
2025-08-16 | 86771.0649 | 39289.5 | 86771.0649 | 39289.5 | 0 | 39289.5
2025-08-17 | 86891.2736 | 39289.5 | 86891.2736 | 39289.5 | 0 | 39289.5
2025-08-18 | 87011.4824 | 39993.25 | 87011.4824 | 39993.25 | 0 | 39993.25
2025-08-19 | 87131.6912 | 40697 | 87131.6912 | 40697 | 0 | 40697
2025-08-20 | 87251.9 | 41400.75 | 87251.9 | 41400.75 | 0 | 41400.75
2025-08-21 | 87372.1087 | 42104.5 | 87372.1087 | 42104.5 | 0 | 42104.5
2025-08-22 | 87492.3175 | 42808.25 | 87492.3175 | 42808.25 | 0 | 42808.25
2025-08-23 | 87612.5263 | 42808.25 | 87612.5263 | 42808.25 | 0 | 42808.25
2025-08-24 | 87732.735 | 42808.25 | 87732.735 | 42808.25 | 0 | 42808.25
2025-08-25 | 87852.9438 | 43488.675 | 87852.9438 | 43488.675 | 0 | 43488.675
2025-08-26 | 87973.1526 | 44169.1 | 87973.1526 | 44169.1 | 0 | 44169.1
2025-08-27 | 88093.3614 | 44849.525 | 88093.3614 | 44849.525 | 0 | 44849.525
2025-08-28 | 88213.5701 | 45529.95 | 88213.5701 | 45529.95 | 0 | 45529.95
2025-08-29 | 88333.7789 | 46210.375 | 88333.7789 | 46210.375 | 0 | 46210.375
2025-08-30 | 88453.9877 | 46210.375 | 88453.9877 | 46210.375 | 0 | 46210.375
2025-08-31 | 88574.1964 | 46210.375 | 88574.1964 | 46210.375 | 0 | 46210.375
2025-09-01 | 88694.4052 | 47373.7 | 88694.4052 | 47373.7 | 0 | 47373.7
2025-09-02 | 88814.614 | 48537.025 | 88814.614 | 48537.025 | 0 | 48537.025
2025-09-03 | 88934.8228 | 49700.35 | 88934.8228 | 49700.35 | 0 | 49700.35
2025-09-04 | 89055.0315 | 50863.675 | 89055.0315 | 50863.675 | 0 | 50863.675
2025-09-05 | 89175.2403 | 52027 | 89175.2403 | 52027 | 0 | 52027
2025-09-06 | 89295.4491 | 52027 | 89295.4491 | 52027 | 0 | 52027
2025-09-07 | 89415.6578 | 52027 | 89415.6578 | 52027 | 0 | 52027
2025-09-08 | 89535.8666 | 52781.375 | 89535.8666 | 52781.375 | 0 | 52781.375
2025-09-09 | 89656.0754 | 53535.75 | 89656.0754 | 53535.75 | 0 | 53535.75
2025-09-10 | 89776.2842 | 54290.125 | 89776.2842 | 54290.125 | 0 | 54290.125
2025-09-11 | 89896.4929 | 55044.5 | 89896.4929 | 55044.5 | 0 | 55044.5
2025-09-12 | 90016.7017 | 55798.875 | 90016.7017 | 55798.875 | 0 | 55798.875
2025-09-13 | 90136.9105 | 55798.875 | 90136.9105 | 55798.875 | 0 | 55798.875
2025-09-14 | 90257.1192 | 55798.875 | 90257.1192 | 55798.875 | 0 | 55798.875
2025-09-15 | 90377.328 | 57425.25 | 90377.328 | 57425.25 | 0 | 57425.25
2025-09-16 | 90497.5368 | 59051.625 | 90497.5368 | 59051.625 | 0 | 59051.625
2025-09-17 | 90617.7456 | 60678 | 90617.7456 | 60678 | 0 | 60678
2025-09-18 | 90737.9543 | 62304.375 | 90737.9543 | 62304.375 | 0 | 62304.375
2025-09-19 | 90858.1631 | 63930.75 | 90858.1631 | 63930.75 | 0 | 63930.75
2025-09-20 | 90978.3719 | 63930.75 | 90978.3719 | 63930.75 | 0 | 63930.75
2025-09-21 | 91098.5806 | 63930.75 | 91098.5806 | 63930.75 | 0 | 63930.75
2025-09-22 | 91098.5806 | 65705.925 | 91098.5806 | 65705.925 | 0 | 65705.925
2025-09-23 | 94337.9597 | 67481.1 | 94337.9597 | 67481.1 | 0 | 67481.1
2025-09-24 | 97577.3387 | 69256.275 | 97577.3387 | 69256.275 | 0 | 69256.275
2025-09-25 | 100816.7177 | 71031.45 | 100816.7177 | 71031.45 | 0 | 71031.45
2025-09-26 | 104056.0968 | 72806.625 | 104056.0968 | 72806.625 | 0 | 72806.625
2025-09-27 | 107295.4758 | 72806.625 | 107295.4758 | 72806.625 | 0 | 72806.625
2025-09-28 | 110534.8548 | 72806.625 | 110534.8548 | 72806.625 | 0 | 72806.625
2025-09-29 | 113774.2339 | 74913.85 | 113774.2339 | 74913.85 | 0 | 74913.85
2025-09-30 | 117013.6129 | 77021.075 | 117013.6129 | 77021.075 | 0 | 77021.075
2025-10-01 | 120252.9919 | 79128.3 | 120252.9919 | 79128.3 | 0 | 79128.3
2025-10-02 | 123492.371 | 81235.525 | 123492.371 | 81235.525 | 0 | 81235.525
2025-10-03 | 126731.75 | 83342.75 | 126731.75 | 83342.75 | 0 | 83342.75
2025-10-04 | 129971.129 | 83342.75 | 129971.129 | 83342.75 | 0 | 83342.75
2025-10-05 | 133210.5081 | 83342.75 | 133210.5081 | 83342.75 | 0 | 83342.75
2025-10-06 | 136449.8871 | 85089.875 | 136449.8871 | 85089.875 | 0 | 85089.875
2025-10-07 | 139689.2661 | 86837 | 139689.2661 | 86837 | 0 | 86837
2025-10-08 | 142928.6452 | 88584.125 | 142928.6452 | 88584.125 | 0 | 88584.125
2025-10-09 | 146168.0242 | 90331.25 | 146168.0242 | 90331.25 | 0 | 90331.25
2025-10-10 | 149407.4032 | 92078.375 | 149407.4032 | 92078.375 | 0 | 92078.375
2025-10-11 | 152646.7823 | 92078.375 | 152646.7823 | 92078.375 | 0 | 92078.375
2025-10-12 | 155886.1613 | 92078.375 | 155886.1613 | 92078.375 | 0 | 92078.375
2025-10-13 | 159125.5403 | 93848.825 | 159125.5403 | 93848.825 | 0 | 93848.825
2025-10-14 | 162364.9194 | 95619.275 | 162364.9194 | 95619.275 | 0 | 95619.275
2025-10-15 | 165604.2984 | 97389.725 | 165604.2984 | 97389.725 | 0 | 97389.725
2025-10-16 | 168843.6774 | 99160.175 | 168843.6774 | 99160.175 | 0 | 99160.175
2025-10-17 | 172083.0565 | 100930.625 | 172083.0565 | 100930.625 | 0 | 100930.625
2025-10-18 | 175322.4355 | 100930.625 | 175322.4355 | 100930.625 | 0 | 100930.625
2025-10-19 | 178561.8145 | 100930.625 | 178561.8145 | 100930.625 | 0 | 100930.625
2025-10-20 | 181801.1935 | 103046.55 | 181801.1935 | 103046.55 | 0 | 103046.55
2025-10-21 | 185040.5726 | 105162.475 | 185040.5726 | 105162.475 | 0 | 105162.475
2025-10-22 | 188279.9516 | 107278.4 | 188279.9516 | 107278.4 | 0 | 107278.4
2025-10-23 | 191519.3306 | 109394.325 | 191519.3306 | 109394.325 | 0 | 109394.325
2025-10-24 | 194758.7097 | 111510.25 | 194758.7097 | 111510.25 | 0 | 111510.25
2025-10-25 | 197998.0887 | 111510.25 | 197998.0887 | 111510.25 | 0 | 111510.25
2025-10-26 | 201237.4677 | 111510.25 | 201237.4677 | 111510.25 | 0 | 111510.25
2025-10-27 | 204476.8468 | 113280.75 | 204476.8468 | 113280.75 | 0 | 113280.75
2025-10-28 | 207716.2258 | 115051.25 | 207716.2258 | 115051.25 | 0 | 115051.25
2025-10-29 | 210955.6048 | 116821.75 | 210955.6048 | 116821.75 | 0 | 116821.75
2025-10-30 | 214194.9839 | 118592.25 | 214194.9839 | 118592.25 | 0 | 118592.25
2025-10-31 | 217434.3629 | 120362.75 | 217434.3629 | 120362.75 | 0 | 120362.75
2025-11-01 | 220673.7419 | 120362.75 | 220673.7419 | 120362.75 | 0 | 120362.75
2025-11-02 | 223913.121 | 120362.75 | 223913.121 | 120362.75 | 0 | 120362.75
2025-11-03 | 227152.5 | 122034.05 | 227152.5 | 122034.05 | 0 | 122034.05
2025-11-04 | 230391.879 | 123705.35 | 230391.879 | 123705.35 | 0 | 123705.35
2025-11-05 | 233631.2581 | 125376.65 | 233631.2581 | 125376.65 | 0 | 125376.65
2025-11-06 | 236870.6371 | 127047.95 | 236870.6371 | 127047.95 | 0 | 127047.95
2025-11-07 | 240110.0161 | 128719.25 | 240110.0161 | 128719.25 | 0 | 128719.25
2025-11-08 | 243349.3952 | 128719.25 | 243349.3952 | 128719.25 | 0 | 128719.25
2025-11-09 | 246588.7742 | 128719.25 | 246588.7742 | 128719.25 | 0 | 128719.25
2025-11-10 | 249828.1532 | 130337.625 | 249828.1532 | 130337.625 | 0 | 130337.625
2025-11-11 | 253067.5323 | 131956 | 253067.5323 | 131956 | 0 | 131956
2025-11-12 | 256306.9113 | 133574.375 | 256306.9113 | 133574.375 | 0 | 133574.375
2025-11-13 | 259546.2903 | 135192.75 | 259546.2903 | 135192.75 | 0 | 135192.75
2025-11-14 | 260740.2065 | 136811.125 | 260740.2065 | 136811.125 | 0 | 136811.125
2025-11-15 | 261934.1226 | 136811.125 | 261934.1226 | 136811.125 | 0 | 136811.125
2025-11-16 | 263128.0387 | 136811.125 | 263128.0387 | 136811.125 | 0 | 136811.125
2025-11-17 | 264321.9549 | 137515.425 | 264321.9549 | 137515.425 | 0 | 137515.425
2025-11-18 | 265515.871 | 138219.725 | 265515.871 | 138219.725 | 0 | 138219.725
2025-11-19 | 266709.7871 | 138924.025 | 266709.7871 | 138924.025 | 0 | 138924.025
2025-11-20 | 267903.7033 | 139628.325 | 267903.7033 | 139628.325 | 0 | 139628.325
2025-11-21 | 269097.6194 | 140332.625 | 269097.6194 | 140332.625 | 0 | 140332.625
2025-11-22 | 270291.5355 | 140332.625 | 270291.5355 | 140332.625 | 0 | 140332.625
2025-11-23 | 271485.4517 | 140332.625 | 271485.4517 | 140332.625 | 0 | 140332.625
2025-11-24 | 272679.3678 | 141144.85 | 272679.3678 | 141144.85 | 0 | 141144.85
2025-11-25 | 273873.284 | 141957.075 | 273873.284 | 141957.075 | 0 | 141957.075
2025-11-26 | 275067.2001 | 142769.3 | 275067.2001 | 142769.3 | 0 | 142769.3
2025-11-27 | 276261.1162 | 143581.525 | 276261.1162 | 143581.525 | 0 | 143581.525
2025-11-28 | 277455.0324 | 144393.75 | 277455.0324 | 144393.75 | 0 | 144393.75
2025-11-29 | 278648.9485 | 144393.75 | 278648.9485 | 144393.75 | 0 | 144393.75
2025-11-30 | 279842.8646 | 144393.75 | 279842.8646 | 144393.75 | 0 | 144393.75
2025-12-01 | 281036.7808 | 145486.9 | 281036.7808 | 145486.9 | 0 | 145486.9
2025-12-02 | 282230.6969 | 146580.05 | 282230.6969 | 146580.05 | 0 | 146580.05
2025-12-03 | 283424.613 | 147673.2 | 283424.613 | 147673.2 | 0 | 147673.2
2025-12-04 | 284618.5292 | 148766.35 | 284618.5292 | 148766.35 | 0 | 148766.35
2025-12-05 | 285812.4453 | 149859.5 | 285812.4453 | 149859.5 | 0 | 149859.5
2025-12-06 | 287006.3614 | 149859.5 | 287006.3614 | 149859.5 | 0 | 149859.5
2025-12-07 | 288200.2776 | 149859.5 | 288200.2776 | 149859.5 | 0 | 149859.5
2025-12-08 | 289394.1937 | 151023.125 | 289394.1937 | 151023.125 | 0 | 151023.125
2025-12-09 | 290588.1099 | 152186.75 | 290588.1099 | 152186.75 | 0 | 152186.75
2025-12-10 | 291782.026 | 153350.375 | 291782.026 | 153350.375 | 0 | 153350.375
2025-12-11 | 292975.9421 | 154514 | 292975.9421 | 154514 | 0 | 154514
2025-12-12 | 294169.8583 | 155677.625 | 294169.8583 | 155677.625 | 0 | 155677.625
2025-12-13 | 295363.7744 | 155677.625 | 295363.7744 | 155677.625 | 0 | 155677.625
2025-12-14 | 296557.6905 | 155677.625 | 296557.6905 | 155677.625 | 0 | 155677.625
2025-12-15 | 297751.6067 | 156841.25 | 297751.6067 | 156841.25 | 0 | 156841.25
2025-12-16 | 298945.5228 | 158004.875 | 298945.5228 | 158004.875 | 0 | 158004.875
2025-12-17 | 300139.4389 | 159168.5 | 300139.4389 | 159168.5 | 0 | 159168.5
2025-12-18 | 301333.3551 | 160332.125 | 301333.3551 | 160332.125 | 0 | 160332.125
2025-12-19 | 302527.2712 | 161495.75 | 302527.2712 | 161495.75 | 0 | 161495.75
2025-12-20 | 303721.1873 | 161495.75 | 303721.1873 | 161495.75 | 0 | 161495.75
2025-12-21 | 304915.1035 | 161495.75 | 304915.1035 | 161495.75 | 0 | 161495.75
2025-12-22 | 306109.0196 | 161495.75 | 306109.0196 | 161495.75 | 0 | 161495.75
2025-12-23 | 307302.9358 | 161495.75 | 307302.9358 | 161495.75 | 0 | 161495.75
2025-12-24 | 308496.8519 | 161495.75 | 308496.8519 | 161495.75 | 0 | 161495.75
2025-12-25 | 309690.768 | 161495.75 | 309690.768 | 161495.75 | 0 | 161495.75
2025-12-26 | 310884.6842 | 161495.75 | 310884.6842 | 161495.75 | 0 | 161495.75
2025-12-27 | 312078.6003 | 161495.75 | 312078.6003 | 161495.75 | 0 | 161495.75
2025-12-28 | 313272.5164 | 161495.75 | 313272.5164 | 161495.75 | 0 | 161495.75
2025-12-29 | 314466.4326 | 162393.1 | 314466.4326 | 162393.1 | 0 | 162393.1
2025-12-30 | 315660.3487 | 163290.45 | 315660.3487 | 163290.45 | 0 | 163290.45
2025-12-31 | 316854.2648 | 164187.8 | 316854.2648 | 164187.8 | 0 | 164187.8
2026-01-01 | 318048.181 | 165085.15 | 318048.181 | 165085.15 | 0 | 165085.15
2026-01-02 | 319242.0971 | 165982.5 | 319242.0971 | 165982.5 | 0 | 165982.5
2026-01-03 | 320436.0132 | 165982.5 | 320436.0132 | 165982.5 | 0 | 165982.5
2026-01-04 | 321629.9294 | 165982.5 | 321629.9294 | 165982.5 | 0 | 165982.5
2026-01-05 | 322823.8455 | 167054.925 | 322823.8455 | 167054.925 | 0 | 167054.925
2026-01-06 | 324017.7617 | 168127.35 | 324017.7617 | 168127.35 | 0 | 168127.35
2026-01-07 | 325211.6778 | 169199.775 | 325211.6778 | 169199.775 | 0 | 169199.775
2026-01-08 | 326405.5939 | 170272.2 | 326405.5939 | 170272.2 | 0 | 170272.2
2026-01-09 | 327599.5101 | 171344.625 | 327599.5101 | 171344.625 | 0 | 171344.625
2026-01-10 | 328793.4262 | 171344.625 | 328793.4262 | 171344.625 | 0 | 171344.625
2026-01-11 | 329987.3423 | 171344.625 | 329987.3423 | 171344.625 | 0 | 171344.625
2026-01-12 | 331181.2585 | 172044.925 | 331181.2585 | 172044.925 | 0 | 172044.925
2026-01-13 | 332375.1746 | 172745.225 | 332375.1746 | 172745.225 | 0 | 172745.225
2026-01-14 | 333569.0907 | 173445.525 | 333569.0907 | 173445.525 | 0 | 173445.525
2026-01-15 | 334763.0069 | 174145.825 | 334763.0069 | 174145.825 | 0 | 174145.825
2026-01-16 | 335956.923 | 174846.125 | 335956.923 | 174846.125 | 0 | 174846.125
2026-01-17 | 337150.8392 | 174846.125 | 337150.8392 | 174846.125 | 0 | 174846.125
2026-01-18 | 338344.7553 | 174846.125 | 338344.7553 | 174846.125 | 0 | 174846.125
2026-01-19 | 339538.6714 | 175873.425 | 339538.6714 | 175873.425 | 0 | 175873.425
2026-01-20 | 340732.5876 | 176900.725 | 340732.5876 | 176900.725 | 0 | 176900.725
2026-01-21 | 341926.5037 | 177928.025 | 341926.5037 | 177928.025 | 0 | 177928.025
2026-01-22 | 343120.4198 | 178955.325 | 343120.4198 | 178955.325 | 0 | 178955.325
2026-01-23 | 344314.336 | 179982.625 | 344314.336 | 179982.625 | 0 | 179982.625
2026-01-24 | 345508.2521 | 179982.625 | 345508.2521 | 179982.625 | 0 | 179982.625
2026-01-25 | 346702.1682 | 179982.625 | 346702.1682 | 179982.625 | 0 | 179982.625
2026-01-26 | 347896.0844 | 181735.85 | 347896.0844 | 181735.85 | 0 | 181735.85
2026-01-27 | 349090.0005 | 183489.075 | 349090.0005 | 183489.075 | 0 | 183489.075
2026-01-28 | 350283.9166 | 185242.3 | 350283.9166 | 185242.3 | 0 | 185242.3
2026-01-29 | 351477.8328 | 186995.525 | 351477.8328 | 186995.525 | 0 | 186995.525
2026-01-30 | 352671.7489 | 188748.75 | 352671.7489 | 188748.75 | 0 | 188748.75
2026-01-31 | 353865.6651 | 188748.75 | 353865.6651 | 188748.75 | 0 | 188748.75
2026-02-01 | 355059.5812 | 188748.75 | 355059.5812 | 188748.75 | 0 | 188748.75
2026-02-02 | 356253.4973 | 189828.5 | 356253.4973 | 189828.5 | 0 | 189828.5
2026-02-03 | 357447.4135 | 190908.25 | 357447.4135 | 190908.25 | 0 | 190908.25
2026-02-04 | 358641.3296 | 191988 | 358641.3296 | 191988 | 0 | 191988
2026-02-05 | 359835.2457 | 193067.75 | 359835.2457 | 193067.75 | 0 | 193067.75
2026-02-06 | 361029.1619 | 194147.5 | 361029.1619 | 194147.5 | 0 | 194147.5
2026-02-07 | 362223.078 | 194147.5 | 362223.078 | 194147.5 | 0 | 194147.5
2026-02-08 | 363416.9941 | 194147.5 | 363416.9941 | 194147.5 | 0 | 194147.5
2026-02-09 | 364610.9103 | 195428.55 | 364610.9103 | 195428.55 | 0 | 195428.55
2026-02-10 | 365804.8264 | 196709.6 | 365804.8264 | 196709.6 | 0 | 196709.6
2026-02-11 | 366998.7425 | 197990.65 | 366998.7425 | 197990.65 | 0 | 197990.65
2026-02-12 | 368192.6587 | 199271.7 | 368192.6587 | 199271.7 | 0 | 199271.7
2026-02-13 | 369386.5748 | 200552.75 | 369386.5748 | 200552.75 | 0 | 200552.75
2026-02-14 | 370580.491 | 200552.75 | 370580.491 | 200552.75 | 0 | 200552.75
2026-02-15 | 371774.4071 | 200552.75 | 371774.4071 | 200552.75 | 0 | 200552.75
2026-02-16 | 372968.3232 | 201679.45 | 372968.3232 | 201679.45 | 0 | 201679.45
2026-02-17 | 374162.2394 | 202806.15 | 374162.2394 | 202806.15 | 0 | 202806.15
2026-02-18 | 375356.1555 | 203932.85 | 375356.1555 | 203932.85 | 0 | 203932.85
2026-02-19 | 376550.0716 | 205059.55 | 376550.0716 | 205059.55 | 0 | 205059.55
2026-02-20 | 377743.9878 | 206186.25 | 377743.9878 | 206186.25 | 0 | 206186.25
2026-02-21 | 378937.9039 | 206186.25 | 378937.9039 | 206186.25 | 0 | 206186.25
2026-02-22 | 380131.82 | 206186.25 | 380131.82 | 206186.25 | 0 | 206186.25
2026-02-23 | 381325.7362 | 207266 | 381325.7362 | 207266 | 0 | 207266
2026-02-24 | 382519.6523 | 208345.75 | 382519.6523 | 208345.75 | 0 | 208345.75
2026-02-25 | 383713.5684 | 209425.5 | 383713.5684 | 209425.5 | 0 | 209425.5
2026-02-26 | 384907.4846 | 210505.25 | 384907.4846 | 210505.25 | 0 | 210505.25
2026-02-27 | 386101.4007 | 211585 | 386101.4007 | 211585 | 0 | 211585
2026-02-28 | 387295.3169 | 211585 | 387295.3169 | 211585 | 0 | 211585
2026-03-01 | 388489.233 | 211585 | 388489.233 | 211585 | 0 | 211585
2026-03-02 | 389683.1491 | 211980.75 | 389683.1491 | 211980.75 | 0 | 211980.75
2026-03-03 | 390603.204 | 212376.5 | 390603.204 | 212376.5 | 0 | 212376.5
2026-03-04 | 391523.2589 | 212772.25 | 391523.2589 | 212772.25 | 0 | 212772.25
2026-03-05 | 392443.3137 | 213168 | 392443.3137 | 213168 | 0 | 213168
2026-03-06 | 393363.3686 | 213563.75 | 393363.3686 | 213563.75 | 0 | 213563.75
2026-03-07 | 394283.4235 | 213563.75 | 394283.4235 | 213563.75 | 0 | 213563.75
2026-03-08 | 395203.4783 | 213563.75 | 395203.4783 | 213563.75 | 0 | 213563.75
2026-03-09 | 396123.5332 | 213761.625 | 396123.5332 | 213761.625 | 0 | 213761.625
2026-03-10 | 397043.5881 | 213959.5 | 397043.5881 | 213959.5 | 0 | 213959.5
2026-03-11 | 397963.643 | 214157.375 | 397963.643 | 214157.375 | 0 | 214157.375
2026-03-12 | 398883.6978 | 214355.25 | 398883.6978 | 214355.25 | 0 | 214355.25
2026-03-13 | 399803.7527 | 214553.125 | 399803.7527 | 214553.125 | 0 | 214553.125
2026-03-14 | 400723.8076 | 214553.125 | 400723.8076 | 214553.125 | 0 | 214553.125
2026-03-15 | 401643.8624 | 214553.125 | 401643.8624 | 214553.125 | 0 | 214553.125
2026-03-16 | 402563.9173 | 215408.95 | 402563.9173 | 215408.95 | 0 | 215408.95
2026-03-17 | 403483.9722 | 216264.775 | 403483.9722 | 216264.775 | 0 | 216264.775
2026-03-18 | 404404.027 | 217120.6 | 404404.027 | 217120.6 | 0 | 217120.6
2026-03-19 | 405324.0819 | 217976.425 | 405324.0819 | 217976.425 | 0 | 217976.425
2026-03-20 | 406244.1368 | 218832.25 | 406244.1368 | 218832.25 | 0 | 218832.25
2026-03-21 | 407164.1917 | 218832.25 | 407164.1917 | 218832.25 | 0 | 218832.25
2026-03-22 | 408084.2465 | 218832.25 | 408084.2465 | 218832.25 | 0 | 218832.25
2026-03-23 | 409004.3014 |  | 409004.3014 |  | 0
2026-03-24 | 409924.3563 |  | 409924.3563 |  | 0
2026-03-25 | 410844.4111 |  | 410844.4111 |  | 0
2026-03-26 | 411764.466 |  | 411764.466 |  | 0
2026-03-27 | 412684.5209 |  | 412684.5209 |  | 0
2026-03-28 | 413604.5758 |  | 413604.5758 |  | 0
2026-03-29 | 414524.6306 |  | 414524.6306 |  | 0
2026-03-30 | 415444.6855 |  | 415444.6855 |  | 0
2026-03-31 | 416364.7404 |  | 416364.7404 |  | 0
2026-04-01 | 417284.7952 |  | 417284.7952 |  | 0
2026-04-02 | 418204.8501 |  | 418204.8501 |  | 0
2026-04-03 | 419124.905 |  | 419124.905 |  | 0
2026-04-04 | 420044.9598 |  | 420044.9598 |  | 0
2026-04-05 | 420965.0147 |  | 420965.0147 |  | 0
2026-04-06 | 421885.0696 |  | 421885.0696 |  | 0
2026-04-07 | 422805.1245 |  | 422805.1245 |  | 0
2026-04-08 | 423725.1793 |  | 423725.1793 |  | 0
2026-04-09 | 424645.2342 |  | 424645.2342 |  | 0
2026-04-10 | 425565.2891 |  | 425565.2891 |  | 0
2026-04-11 | 426485.3439 |  | 426485.3439 |  | 0
2026-04-12 | 427405.3988 |  | 427405.3988 |  | 0
2026-04-13 | 428325.4537 |  | 428325.4537 |  | 0
2026-04-14 | 429245.5085 |  | 429245.5085 |  | 0
2026-04-15 | 430165.5634 |  | 430165.5634 |  | 0
2026-04-16 | 431085.6183 |  | 431085.6183 |  | 0
2026-04-17 | 432005.6732 |  | 432005.6732 |  | 0
2026-04-18 | 432925.728 |  | 432925.728 |  | 0
2026-04-19 | 433845.7829 |  | 433845.7829 |  | 0
2026-04-20 | 434765.8378 |  | 434765.8378 |  | 0
2026-04-21 | 435685.8926 |  | 435685.8926 |  | 0
2026-04-22 | 436605.9475 |  | 436605.9475 |  | 0
2026-04-23 | 437526.0024 |  | 437526.0024 |  | 0
2026-04-24 | 438446.0572 |  | 438446.0572 |  | 0
2026-04-25 | 439366.1121 |  | 439366.1121 |  | 0
2026-04-26 | 440286.167 |  | 440286.167 |  | 0
2026-04-27 | 441206.2219 |  | 441206.2219 |  | 0
2026-04-28 | 442126.2767 |  | 442126.2767 |  | 0
2026-04-29 | 443046.3316 |  | 443046.3316 |  | 0
2026-04-30 | 443966.3865 |  | 443966.3865 |  | 0
2026-05-01 | 444886.4413 |  | 444886.4413 |  | 0
2026-05-02 | 445806.4962 |  | 445806.4962 |  | 0
2026-05-03 | 446726.5511 |  | 446726.5511 |  | 0
2026-05-04 | 447646.6059 |  | 447646.6059 |  | 0
2026-05-05 | 448566.6608 |  | 448566.6608 |  | 0
2026-05-06 | 449486.7157 |  | 449486.7157 |  | 0
2026-05-07 | 450406.7706 |  | 450406.7706 |  | 0
2026-05-08 | 451326.8254 |  | 451326.8254 |  | 0
2026-05-09 | 452246.8803 |  | 452246.8803 |  | 0
2026-05-10 | 453166.9352 |  | 453166.9352 |  | 0
2026-05-11 | 454086.99 |  | 454086.99 |  | 0
2026-05-12 | 455007.0449 |  | 455007.0449 |  | 0
2026-05-13 | 455927.0998 |  | 455927.0998 |  | 0
2026-05-14 | 456847.1546 |  | 456847.1546 |  | 0
2026-05-15 | 457767.2095 |  | 457767.2095 |  | 0
2026-05-16 | 458687.2644 |  | 458687.2644 |  | 0
2026-05-17 | 459607.3193 |  | 459607.3193 |  | 0
2026-05-18 | 460527.3741 |  | 460527.3741 |  | 0
2026-05-19 | 461447.429 |  | 461447.429 |  | 0
2026-05-20 | 462367.4839 |  | 462367.4839 |  | 0
2026-05-21 | 463287.5387 |  | 463287.5387 |  | 0
2026-05-22 | 464207.5936 |  | 464207.5936 |  | 0
2026-05-23 | 465127.6485 |  | 465127.6485 |  | 0
2026-05-24 | 466047.7033 |  | 466047.7033 |  | 0
2026-05-25 | 466967.7582 |  | 466967.7582 |  | 0
2026-05-26 | 467887.8131 |  | 467887.8131 |  | 0
2026-05-27 | 468807.868 |  | 468807.868 |  | 0
2026-05-28 | 469727.9228 |  | 469727.9228 |  | 0
2026-05-29 | 470647.9777 |  | 470647.9777 |  | 0
2026-05-30 | 471568.0326 |  | 471568.0326 |  | 0
2026-05-31 | 472488.0874 |  | 472488.0874 |  | 0
2026-06-01 | 473408.1423 |  | 473408.1423 |  | 0
2026-06-02 | 474328.1972 |  | 474328.1972 |  | 0
2026-06-03 | 475248.252 |  | 475248.252 |  | 0
2026-06-04 | 476168.3069 |  | 476168.3069 |  | 0
2026-06-05 | 477088.3618 |  | 477088.3618 |  | 0
2026-06-06 | 478008.4167 |  | 478008.4167 |  | 0
2026-06-07 | 478928.4715 |  | 478928.4715 |  | 0
2026-06-08 | 479848.5264 |  | 479848.5264 |  | 0
2026-06-09 | 480768.5813 |  | 480768.5813 |  | 0
2026-06-10 | 481688.6361 |  | 481688.6361 |  | 0
2026-06-11 | 482608.691 |  | 482608.691 |  | 0
2026-06-12 | 483528.7459 |  | 483528.7459 |  | 0
2026-06-13 | 484448.8007 |  | 484448.8007 |  | 0
2026-06-14 | 485368.8556 |  | 485368.8556 |  | 0
2026-06-15 | 486288.9105 |  | 486288.9105 |  | 0
2026-06-16 | 487208.9654 |  | 487208.9654 |  | 0
2026-06-17 | 488129.0202 |  | 488129.0202 |  | 0
2026-06-18 | 489049.0751 |  | 489049.0751 |  | 0
2026-06-19 | 489969.13 |  | 489969.13 |  | 0
2026-06-20 | 490889.1848 |  | 490889.1848 |  | 0
2026-06-21 | 491809.2397 |  | 491809.2397 |  | 0
2026-06-22 | 492729.2946 |  | 492729.2946 |  | 0
2026-06-23 | 493649.3495 |  | 493649.3495 |  | 0
2026-06-24 | 494569.4043 |  | 494569.4043 |  | 0
2026-06-25 | 495489.4592 |  | 495489.4592 |  | 0
2026-06-26 | 496409.5141 |  | 496409.5141 |  | 0
2026-06-27 | 497329.5689 |  | 497329.5689 |  | 0
2026-06-28 | 498249.6238 |  | 498249.6238 |  | 0
2026-06-29 | 499169.6787 |  | 499169.6787 |  | 0
2026-06-30 | 500089.7335 |  | 500089.7335 |  | 0
2026-07-01 | 501009.7884 |  | 501009.7884 |  | 0
2026-07-02 | 501929.8433 |  | 501929.8433 |  | 0
2026-07-03 | 502849.8982 |  | 502849.8982 |  | 0
2026-07-04 | 503769.953 |  | 503769.953 |  | 0
2026-07-05 | 504690.0079 |  | 504690.0079 |  | 0
2026-07-06 | 505610.0628 |  | 505610.0628 |  | 0
2026-07-07 | 506530.1176 |  | 506530.1176 |  | 0
2026-07-08 | 507450.1725 |  | 507450.1725 |  | 0
2026-07-09 | 508370.2274 |  | 508370.2274 |  | 0
2026-07-10 | 509290.2822 |  | 509290.2822 |  | 0
2026-07-11 | 510210.3371 |  | 510210.3371 |  | 0
2026-07-12 | 511130.392 |  | 511130.392 |  | 0
2026-07-13 | 512050.4469 |  | 512050.4469 |  | 0
2026-07-14 | 512970.5017 |  | 512970.5017 |  | 0
2026-07-15 | 513890.5566 |  | 513890.5566 |  | 0
2026-07-16 | 514810.6115 |  | 514810.6115 |  | 0
2026-07-17 | 515730.6663 |  | 515730.6663 |  | 0
2026-07-18 | 516650.7212 |  | 516650.7212 |  | 0
2026-07-19 | 517570.7761 |  | 517570.7761 |  | 0
2026-07-20 | 518490.8309 |  | 518490.8309 |  | 0
2026-07-21 | 519410.8858 |  | 519410.8858 |  | 0
2026-07-22 | 520330.9407 |  | 520330.9407 |  | 0
2026-07-23 | 521250.9956 |  | 521250.9956 |  | 0
2026-07-24 | 522171.0504 |  | 522171.0504 |  | 0
2026-07-25 | 523091.1053 |  | 523091.1053 |  | 0
2026-07-26 | 524011.1602 |  | 524011.1602 |  | 0
2026-07-27 | 524931.215 |  | 524931.215 |  | 0
2026-07-28 | 525851.2699 |  | 525851.2699 |  | 0
2026-07-29 | 526771.3248 |  | 526771.3248 |  | 0
2026-07-30 | 527691.3796 |  | 527691.3796 |  | 0
2026-07-31 | 528611.4345 |  | 528611.4345 |  | 0
2026-08-01 | 529531.4894 |  | 529531.4894 |  | 0
2026-08-02 | 530451.5443 |  | 530451.5443 |  | 0
2026-08-03 | 531371.5991 |  | 531371.5991 |  | 0
2026-08-04 | 532291.654 |  | 532291.654 |  | 0
2026-08-05 | 533211.7089 |  | 533211.7089 |  | 0
2026-08-06 | 534131.7637 |  | 534131.7637 |  | 0
2026-08-07 | 535051.8186 |  | 535051.8186 |  | 0
2026-08-08 | 535971.8735 |  | 535971.8735 |  | 0
2026-08-09 | 536891.9283 |  | 536891.9283 |  | 0
2026-08-10 | 537811.9832 |  | 537811.9832 |  | 0
2026-08-11 | 538732.0381 |  | 538732.0381 |  | 0
2026-08-12 | 539652.093 |  | 539652.093 |  | 0
2026-08-13 | 540572.1478 |  | 540572.1478 |  | 0
2026-08-14 | 541492.2027 |  | 541492.2027 |  | 0
2026-08-15 | 542412.2576 |  | 542412.2576 |  | 0
2026-08-16 | 543332.3124 |  | 543332.3124 |  | 0
2026-08-17 | 544252.3673 |  | 544252.3673 |  | 0
2026-08-18 | 545172.4222 |  | 545172.4222 |  | 0
2026-08-19 | 546092.477 |  | 546092.477 |  | 0
2026-08-20 | 547012.5319 |  | 547012.5319 |  | 0
2026-08-21 | 547932.5868 |  | 547932.5868 |  | 0
2026-08-22 | 548852.6417 |  | 548852.6417 |  | 0
2026-08-23 | 549772.6965 |  | 549772.6965 |  | 0
2026-08-24 | 550692.7514 |  | 550692.7514 |  | 0
2026-08-25 | 551612.8063 |  | 551612.8063 |  | 0
2026-08-26 | 552532.8611 |  | 552532.8611 |  | 0
2026-08-27 | 553452.916 |  | 553452.916 |  | 0
2026-08-28 | 554372.9709 |  | 554372.9709 |  | 0
2026-08-29 | 555293.0257 |  | 555293.0257 |  | 0
2026-08-30 | 556213.0806 |  | 556213.0806 |  | 0
2026-08-31 | 557133.1355 |  | 557133.1355 |  | 0
2026-09-01 | 558053.1904 |  | 558053.1904 |  | 0
2026-09-02 | 558973.2452 |  | 558973.2452 |  | 0
2026-09-03 | 559893.3001 |  | 559893.3001 |  | 0
2026-09-04 | 560813.355 |  | 560813.355 |  | 0
2026-09-05 | 561733.4098 |  | 561733.4098 |  | 0
2026-09-06 | 562653.4647 |  | 562653.4647 |  | 0
2026-09-07 | 563573.5196 |  | 563573.5196 |  | 0
2026-09-08 | 564493.5745 |  | 564493.5745 |  | 0
2026-09-09 | 565413.6293 |  | 565413.6293 |  | 0
2026-09-10 | 566333.6842 |  | 566333.6842 |  | 0
2026-09-11 | 567253.7391 |  | 567253.7391 |  | 0
2026-09-12 | 568173.7939 |  | 568173.7939 |  | 0
2026-09-13 | 569093.8488 |  | 569093.8488 |  | 0
2026-09-14 | 570013.9037 |  | 570013.9037 |  | 0
2026-09-15 | 570933.9585 |  | 570933.9585 |  | 0
2026-09-16 | 571854.0134 |  | 571854.0134 |  | 0
2026-09-17 | 572774.0683 |  | 572774.0683 |  | 0
2026-09-18 | 573694.1232 |  | 573694.1232 |  | 0
2026-09-19 | 574614.178 |  | 574614.178 |  | 0
2026-09-20 | 575534.2329 |  | 575534.2329 |  | 0
2026-09-21 | 576454.2878 |  | 576454.2878 |  | 0
2026-09-22 | 577374.3426 |  | 577374.3426 |  | 0
2026-09-23 | 578294.3975 |  | 578294.3975 |  | 0
2026-09-24 | 579214.4524 |  | 579214.4524 |  | 0
2026-09-25 | 580134.5072 |  | 580134.5072 |  | 0
2026-09-26 | 581054.5621 |  | 581054.5621 |  | 0
2026-09-27 | 581974.617 |  | 581974.617 |  | 0
2026-09-28 | 582894.6719 |  | 582894.6719 |  | 0
2026-09-29 | 583814.7267 |  | 583814.7267 |  | 0
2026-09-30 | 584734.7816 |  | 584734.7816 |  | 0
2026-10-01 | 585654.8365 |  | 585654.8365 |  | 0
2026-10-02 | 586574.8913 |  | 586574.8913 |  | 0
2026-10-03 | 587494.9462 |  | 587494.9462 |  | 0
2026-10-04 | 588415.0011 |  | 588415.0011 |  | 0
2026-10-05 | 589335.0559 |  | 589335.0559 |  | 0
2026-10-06 | 590255.1108 |  | 590255.1108 |  | 0
2026-10-07 | 591175.1657 |  | 591175.1657 |  | 0
2026-10-08 | 592095.2206 |  | 592095.2206 |  | 0
2026-10-09 | 593015.2754 |  | 593015.2754 |  | 0
2026-10-10 | 593935.3303 |  | 593935.3303 |  | 0
2026-10-11 | 594855.3852 |  | 594855.3852 |  | 0
2026-10-12 | 595775.44 |  | 595775.44 |  | 0
2026-10-13 | 596695.4949 |  | 596695.4949 |  | 0
2026-10-14 | 597615.5498 |  | 597615.5498 |  | 0
2026-10-15 | 598535.6046 |  | 598535.6046 |  | 0
2026-10-16 | 599455.6595 |  | 599455.6595 |  | 0
2026-10-17 | 600375.7144 |  | 600375.7144 |  | 0
2026-10-18 | 601295.7693 |  | 601295.7693 |  | 0
2026-10-19 | 602215.8241 |  | 602215.8241 |  | 0
2026-10-20 | 603135.879 |  | 603135.879 |  | 0
2026-10-21 | 604055.9339 |  | 604055.9339 |  | 0
2026-10-22 | 604975.9887 |  | 604975.9887 |  | 0
2026-10-23 | 605896.0436 |  | 605896.0436 |  | 0
2026-10-24 | 606816.0985 |  | 606816.0985 |  | 0
2026-10-25 | 607736.1533 |  | 607736.1533 |  | 0
2026-10-26 | 608656.2082 |  | 608656.2082 |  | 0
2026-10-27 | 609576.2631 |  | 609576.2631 |  | 0
2026-10-28 | 610496.318 |  | 610496.318 |  | 0
2026-10-29 | 611416.3728 |  | 611416.3728 |  | 0
2026-10-30 | 612336.4277 |  | 612336.4277 |  | 0
2026-10-31 | 613256.4826 |  | 613256.4826 |  | 0
2026-11-01 | 614176.5374 |  | 614176.5374 |  | 0
2026-11-02 | 615096.5923 |  | 615096.5923 |  | 0
2026-11-03 | 616016.6472 |  | 616016.6472 |  | 0
2026-11-04 | 616936.702 |  | 616936.702 |  | 0
2026-11-05 | 617856.7569 |  | 617856.7569 |  | 0
2026-11-06 | 618776.8118 |  | 618776.8118 |  | 0
2026-11-07 | 619696.8667 |  | 619696.8667 |  | 0
2026-11-08 | 620616.9215 |  | 620616.9215 |  | 0
2026-11-09 | 621536.9764 |  | 621536.9764 |  | 0
2026-11-10 | 622457.0313 |  | 622457.0313 |  | 0
2026-11-11 | 623377.0861 |  | 623377.0861 |  | 0
2026-11-12 | 624297.141 |  | 624297.141 |  | 0
2026-11-13 | 625217.1959 |  | 625217.1959 |  | 0
2026-11-14 | 626137.2507 |  | 626137.2507 |  | 0
2026-11-15 | 627057.3056 |  | 627057.3056 |  | 0
2026-11-16 | 627977.3605 |  | 627977.3605 |  | 0
2026-11-17 | 628897.4154 |  | 628897.4154 |  | 0
2026-11-18 | 629817.4702 |  | 629817.4702 |  | 0
2026-11-19 | 630737.5251 |  | 630737.5251 |  | 0
2026-11-20 | 631657.58 |  | 631657.58 |  | 0
2026-11-21 | 632577.6348 |  | 632577.6348 |  | 0
2026-11-22 | 633497.6897 |  | 633497.6897 |  | 0
2026-11-23 | 634417.7446 |  | 634417.7446 |  | 0
2026-11-24 | 635672.2402 |  | 635672.2402 |  | 0
2026-11-25 | 636926.7359 |  | 636926.7359 |  | 0
2026-11-26 | 638181.2315 |  | 638181.2315 |  | 0
2026-11-27 | 639435.7271 |  | 639435.7271 |  | 0
2026-11-28 | 640690.2228 |  | 640690.2228 |  | 0
2026-11-29 | 641944.7184 |  | 641944.7184 |  | 0
2026-11-30 | 643199.214 |  | 643199.214 |  | 0
2026-12-01 | 644453.7097 |  | 644453.7097 |  | 0
2026-12-02 | 645708.2053 |  | 645708.2053 |  | 0
2026-12-03 | 646962.701 |  | 646962.701 |  | 0
2026-12-04 | 648217.1966 |  | 648217.1966 |  | 0
2026-12-05 | 649471.6922 |  | 649471.6922 |  | 0
2026-12-06 | 650726.1879 |  | 650726.1879 |  | 0
2026-12-07 | 651980.6835 |  | 651980.6835 |  | 0
2026-12-08 | 653235.1791 |  | 653235.1791 |  | 0
2026-12-09 | 654489.6748 |  | 654489.6748 |  | 0
2026-12-10 | 655744.1704 |  | 655744.1704 |  | 0
2026-12-11 | 656998.666 |  | 656998.666 |  | 0
2026-12-12 | 658253.1617 |  | 658253.1617 |  | 0
2026-12-13 | 659507.6573 |  | 659507.6573 |  | 0
2026-12-14 | 660762.153 |  | 660762.153 |  | 0
2026-12-15 | 662016.6486 |  | 662016.6486 |  | 0
2026-12-16 | 663271.1442 |  | 663271.1442 |  | 0
2026-12-17 | 664525.6399 |  | 664525.6399 |  | 0
2026-12-18 | 665780.1355 |  | 665780.1355 |  | 0
2026-12-19 | 667034.6311 |  | 667034.6311 |  | 0
2026-12-20 | 668289.1268 |  | 668289.1268 |  | 0
2026-12-21 | 669543.6224 |  | 669543.6224 |  | 0
2026-12-22 | 670798.1181 |  | 670798.1181 |  | 0
2026-12-23 | 672052.6137 |  | 672052.6137 |  | 0
2026-12-24 | 673307.1093 |  | 673307.1093 |  | 0
2026-12-25 | 674561.605 |  | 674561.605 |  | 0

## Travel&perdiem (Direct Cost)
Date | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Actual Labor (Cumulative) | Planned 5105 · Travel - Airfare (Direct) (Cumulative) | Actual 5105 · Travel - Airfare (Direct) (Cumulative) | Planned 5106 · Travel - Hotel (Direct) (Cumulative) | Actual 5106 · Travel - Hotel (Direct) (Cumulative) | Planned 5107 · Travel - Other (Direct) (Cumulative) | Actual 5107 · Travel - Other (Direct) (Cumulative) | Planned 5107.1 (Cumulative) | Actual 5107.1 (Cumulative) | Planned 5108 · Meals & entertainment (Direct) (Cumulative) | Actual 5108 · Meals & entertainment (Direct) (Cumulative) | Planned 5122 · Motor vehicle exp (Direct) (Cumulative) | Actual 5122 · Motor vehicle exp (Direct) (Cumulative) | Planned 5123 · Auto fuel (Direct) (Cumulative) | Actual 5123 · Auto fuel (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 2253.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 3379.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 209.92 | 4506.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 209.92 | 5633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 227.92 | 5633 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 227.92 | 5633 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 227.92 | 5847.4 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 227.92 | 6061.8 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 227.92 | 6276.2 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 227.92 | 6490.6 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 227.92 | 6705 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 227.92 | 6705 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 227.92 | 6705 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 227.92 | 7087.15 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 227.92 | 7469.3 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 227.92 | 7851.45 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 227.92 | 8233.6 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 227.92 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 227.92 | 9212.3 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 227.92 | 9808.85 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 227.92 | 10405.4 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 227.92 | 11001.95 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 227.92 | 11598.5 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 227.92 | 11598.5 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 227.92 | 11598.5 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 227.92 | 11873.45 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 227.92 | 12148.4 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 227.92 | 12423.35 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 227.92 | 12698.3 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 227.92 | 12973.25 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 227.92 | 12973.25 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 227.92 | 12973.25 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 227.92 | 13523.15 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 227.92 | 14073.05 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 227.92 | 14622.95 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 227.92 | 15172.85 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 227.92 | 15722.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 227.92 | 15722.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 227.92 | 15722.75 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 227.92 | 15997.7 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 227.92 | 16272.65 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 139.8381 | 227.92 | 16547.6 | 19.9769 | 0 | 19.9769 | 0 | 19.9769 | 18 | 19.9769 | 209.92 | 19.9769 | 0 | 19.9769 | 0 | 19.9769 | 0
2025-06-26 | 279.6761 | 227.92 | 16822.55 | 39.9537 | 0 | 39.9537 | 0 | 39.9537 | 18 | 39.9537 | 209.92 | 39.9537 | 0 | 39.9537 | 0 | 39.9537 | 0
2025-06-27 | 419.5142 | 227.92 | 17097.5 | 59.9306 | 0 | 59.9306 | 0 | 59.9306 | 18 | 59.9306 | 209.92 | 59.9306 | 0 | 59.9306 | 0 | 59.9306 | 0
2025-06-28 | 559.3523 | 227.92 | 17097.5 | 79.9075 | 0 | 79.9075 | 0 | 79.9075 | 18 | 79.9075 | 209.92 | 79.9075 | 0 | 79.9075 | 0 | 79.9075 | 0
2025-06-29 | 699.1904 | 227.92 | 17097.5 | 99.8843 | 0 | 99.8843 | 0 | 99.8843 | 18 | 99.8843 | 209.92 | 99.8843 | 0 | 99.8843 | 0 | 99.8843 | 0
2025-06-30 | 839.0284 | 227.92 | 17714.4 | 119.8612 | 0 | 119.8612 | 0 | 119.8612 | 18 | 119.8612 | 209.92 | 119.8612 | 0 | 119.8612 | 0 | 119.8612 | 0
2025-07-01 | 978.8665 | 227.92 | 18331.3 | 139.8381 | 0 | 139.8381 | 0 | 139.8381 | 18 | 139.8381 | 209.92 | 139.8381 | 0 | 139.8381 | 0 | 139.8381 | 0
2025-07-02 | 1118.7046 | 227.92 | 18948.2 | 159.8149 | 0 | 159.8149 | 0 | 159.8149 | 18 | 159.8149 | 209.92 | 159.8149 | 0 | 159.8149 | 0 | 159.8149 | 0
2025-07-03 | 1258.5426 | 227.92 | 19565.1 | 179.7918 | 0 | 179.7918 | 0 | 179.7918 | 18 | 179.7918 | 209.92 | 179.7918 | 0 | 179.7918 | 0 | 179.7918 | 0
2025-07-04 | 1398.3807 | 227.92 | 20182 | 199.7687 | 0 | 199.7687 | 0 | 199.7687 | 18 | 199.7687 | 209.92 | 199.7687 | 0 | 199.7687 | 0 | 199.7687 | 0
2025-07-05 | 1538.2188 | 227.92 | 20182 | 219.7455 | 0 | 219.7455 | 0 | 219.7455 | 18 | 219.7455 | 209.92 | 219.7455 | 0 | 219.7455 | 0 | 219.7455 | 0
2025-07-06 | 1678.0569 | 227.92 | 20182 | 239.7224 | 0 | 239.7224 | 0 | 239.7224 | 18 | 239.7224 | 209.92 | 239.7224 | 0 | 239.7224 | 0 | 239.7224 | 0
2025-07-07 | 1817.8949 | 227.92 | 20835.625 | 259.6993 | 0 | 259.6993 | 0 | 259.6993 | 18 | 259.6993 | 209.92 | 259.6993 | 0 | 259.6993 | 0 | 259.6993 | 0
2025-07-08 | 1957.733 | 227.92 | 21489.25 | 279.6761 | 0 | 279.6761 | 0 | 279.6761 | 18 | 279.6761 | 209.92 | 279.6761 | 0 | 279.6761 | 0 | 279.6761 | 0
2025-07-09 | 2097.5711 | 227.92 | 22142.875 | 299.653 | 0 | 299.653 | 0 | 299.653 | 18 | 299.653 | 209.92 | 299.653 | 0 | 299.653 | 0 | 299.653 | 0
2025-07-10 | 2237.4092 | 227.92 | 22796.5 | 319.6299 | 0 | 319.6299 | 0 | 319.6299 | 18 | 319.6299 | 209.92 | 319.6299 | 0 | 319.6299 | 0 | 319.6299 | 0
2025-07-11 | 2377.2472 | 227.92 | 23450.125 | 339.6067 | 0 | 339.6067 | 0 | 339.6067 | 18 | 339.6067 | 209.92 | 339.6067 | 0 | 339.6067 | 0 | 339.6067 | 0
2025-07-12 | 2517.0853 | 227.92 | 23450.125 | 359.5836 | 0 | 359.5836 | 0 | 359.5836 | 18 | 359.5836 | 209.92 | 359.5836 | 0 | 359.5836 | 0 | 359.5836 | 0
2025-07-13 | 2656.9234 | 227.92 | 23450.125 | 379.5605 | 0 | 379.5605 | 0 | 379.5605 | 18 | 379.5605 | 209.92 | 379.5605 | 0 | 379.5605 | 0 | 379.5605 | 0
2025-07-14 | 2796.7614 | 1769.82 | 24210.95 | 399.5373 | 1541.9 | 399.5373 | 0 | 399.5373 | 18 | 399.5373 | 209.92 | 399.5373 | 0 | 399.5373 | 0 | 399.5373 | 0
2025-07-15 | 2936.5995 | 1769.82 | 24971.775 | 419.5142 | 1541.9 | 419.5142 | 0 | 419.5142 | 18 | 419.5142 | 209.92 | 419.5142 | 0 | 419.5142 | 0 | 419.5142 | 0
2025-07-16 | 3076.4376 | 1769.82 | 25732.6 | 439.4911 | 1541.9 | 439.4911 | 0 | 439.4911 | 18 | 439.4911 | 209.92 | 439.4911 | 0 | 439.4911 | 0 | 439.4911 | 0
2025-07-17 | 3216.2757 | 1834.27 | 26493.425 | 459.468 | 1541.9 | 459.468 | 0 | 459.468 | 18 | 459.468 | 274.37 | 459.468 | 0 | 459.468 | 0 | 459.468 | 0
2025-07-18 | 3356.1137 | 1861.41 | 27254.25 | 479.4448 | 1569.04 | 479.4448 | 0 | 479.4448 | 18 | 479.4448 | 274.37 | 479.4448 | 0 | 479.4448 | 0 | 479.4448 | 0
2025-07-19 | 3495.9518 | 1891.41 | 27254.25 | 499.4217 | 1569.04 | 499.4217 | 0 | 499.4217 | 48 | 499.4217 | 274.37 | 499.4217 | 0 | 499.4217 | 0 | 499.4217 | 0
2025-07-20 | 3635.7899 | 1891.41 | 27254.25 | 519.3986 | 1569.04 | 519.3986 | 0 | 519.3986 | 48 | 519.3986 | 274.37 | 519.3986 | 0 | 519.3986 | 0 | 519.3986 | 0
2025-07-21 | 3775.6279 | 1891.41 | 27907.875 | 539.3754 | 1569.04 | 539.3754 | 0 | 539.3754 | 48 | 539.3754 | 274.37 | 539.3754 | 0 | 539.3754 | 0 | 539.3754 | 0
2025-07-22 | 3915.466 | 1891.41 | 28561.5 | 559.3523 | 1569.04 | 559.3523 | 0 | 559.3523 | 48 | 559.3523 | 274.37 | 559.3523 | 0 | 559.3523 | 0 | 559.3523 | 0
2025-07-23 | 4055.3041 | 1891.41 | 29215.125 | 579.3292 | 1569.04 | 579.3292 | 0 | 579.3292 | 48 | 579.3292 | 274.37 | 579.3292 | 0 | 579.3292 | 0 | 579.3292 | 0
2025-07-24 | 4195.1422 | 1891.41 | 29868.75 | 599.306 | 1569.04 | 599.306 | 0 | 599.306 | 48 | 599.306 | 274.37 | 599.306 | 0 | 599.306 | 0 | 599.306 | 0
2025-07-25 | 4334.9802 | 1891.41 | 30522.375 | 619.2829 | 1569.04 | 619.2829 | 0 | 619.2829 | 48 | 619.2829 | 274.37 | 619.2829 | 0 | 619.2829 | 0 | 619.2829 | 0
2025-07-26 | 4474.8183 | 1891.41 | 30522.375 | 639.2598 | 1569.04 | 639.2598 | 0 | 639.2598 | 48 | 639.2598 | 274.37 | 639.2598 | 0 | 639.2598 | 0 | 639.2598 | 0
2025-07-27 | 4614.6564 | 1891.41 | 30522.375 | 659.2366 | 1569.04 | 659.2366 | 0 | 659.2366 | 48 | 659.2366 | 274.37 | 659.2366 | 0 | 659.2366 | 0 | 659.2366 | 0
2025-07-28 | 4754.4944 | 1891.41 | 31122.4 | 679.2135 | 1569.04 | 679.2135 | 0 | 679.2135 | 48 | 679.2135 | 274.37 | 679.2135 | 0 | 679.2135 | 0 | 679.2135 | 0
2025-07-29 | 4894.3325 | 1891.41 | 31722.425 | 699.1904 | 1569.04 | 699.1904 | 0 | 699.1904 | 48 | 699.1904 | 274.37 | 699.1904 | 0 | 699.1904 | 0 | 699.1904 | 0
2025-07-30 | 5034.1706 | 1891.41 | 32322.45 | 719.1672 | 1569.04 | 719.1672 | 0 | 719.1672 | 48 | 719.1672 | 274.37 | 719.1672 | 0 | 719.1672 | 0 | 719.1672 | 0
2025-07-31 | 5174.0087 | 1891.41 | 32922.475 | 739.1441 | 1569.04 | 739.1441 | 0 | 739.1441 | 48 | 739.1441 | 274.37 | 739.1441 | 0 | 739.1441 | 0 | 739.1441 | 0
2025-08-01 | 5313.8467 | 3774.04 | 33522.5 | 759.121 | 3200.96 | 759.121 | 0 | 759.121 | 116.71 | 759.121 | 274.37 | 759.121 | 0 | 759.121 | 0 | 759.121 | 182
2025-08-02 | 5453.6848 | 3774.04 | 33522.5 | 779.0978 | 3200.96 | 779.0978 | 0 | 779.0978 | 116.71 | 779.0978 | 274.37 | 779.0978 | 0 | 779.0978 | 0 | 779.0978 | 182
2025-08-03 | 5593.5229 | 3774.04 | 33522.5 | 799.0747 | 3200.96 | 799.0747 | 0 | 799.0747 | 116.71 | 799.0747 | 274.37 | 799.0747 | 0 | 799.0747 | 0 | 799.0747 | 182
2025-08-04 | 5733.361 | 3774.04 | 34126 | 819.0516 | 3200.96 | 819.0516 | 0 | 819.0516 | 116.71 | 819.0516 | 274.37 | 819.0516 | 0 | 819.0516 | 0 | 819.0516 | 182
2025-08-05 | 5873.199 | 3774.04 | 34729.5 | 839.0284 | 3200.96 | 839.0284 | 0 | 839.0284 | 116.71 | 839.0284 | 274.37 | 839.0284 | 0 | 839.0284 | 0 | 839.0284 | 182
2025-08-06 | 6013.0371 | 3774.04 | 35333 | 859.0053 | 3200.96 | 859.0053 | 0 | 859.0053 | 116.71 | 859.0053 | 274.37 | 859.0053 | 0 | 859.0053 | 0 | 859.0053 | 182
2025-08-07 | 6152.8752 | 3774.04 | 35936.5 | 878.9822 | 3200.96 | 878.9822 | 0 | 878.9822 | 116.71 | 878.9822 | 274.37 | 878.9822 | 0 | 878.9822 | 0 | 878.9822 | 182
2025-08-08 | 6292.7132 | 3774.04 | 36540 | 898.959 | 3200.96 | 898.959 | 0 | 898.959 | 116.71 | 898.959 | 274.37 | 898.959 | 0 | 898.959 | 0 | 898.959 | 182
2025-08-09 | 6432.5513 | 3774.04 | 36540 | 918.9359 | 3200.96 | 918.9359 | 0 | 918.9359 | 116.71 | 918.9359 | 274.37 | 918.9359 | 0 | 918.9359 | 0 | 918.9359 | 182
2025-08-10 | 6572.3894 | 3774.04 | 36540 | 938.9128 | 3200.96 | 938.9128 | 0 | 938.9128 | 116.71 | 938.9128 | 274.37 | 938.9128 | 0 | 938.9128 | 0 | 938.9128 | 182
2025-08-11 | 6712.2275 | 3774.04 | 37089.9 | 958.8896 | 3200.96 | 958.8896 | 0 | 958.8896 | 116.71 | 958.8896 | 274.37 | 958.8896 | 0 | 958.8896 | 0 | 958.8896 | 182
2025-08-12 | 6852.0655 | 3774.04 | 37639.8 | 978.8665 | 3200.96 | 978.8665 | 0 | 978.8665 | 116.71 | 978.8665 | 274.37 | 978.8665 | 0 | 978.8665 | 0 | 978.8665 | 182
2025-08-13 | 6991.9036 | 3774.04 | 38189.7 | 998.8434 | 3200.96 | 998.8434 | 0 | 998.8434 | 116.71 | 998.8434 | 274.37 | 998.8434 | 0 | 998.8434 | 0 | 998.8434 | 182
2025-08-14 | 7131.7417 | 3774.04 | 38739.6 | 1018.8202 | 3200.96 | 1018.8202 | 0 | 1018.8202 | 116.71 | 1018.8202 | 274.37 | 1018.8202 | 0 | 1018.8202 | 0 | 1018.8202 | 182
2025-08-15 | 7271.5797 | 3774.04 | 39289.5 | 1038.7971 | 3200.96 | 1038.7971 | 0 | 1038.7971 | 116.71 | 1038.7971 | 274.37 | 1038.7971 | 0 | 1038.7971 | 0 | 1038.7971 | 182
2025-08-16 | 7411.4178 | 3774.04 | 39289.5 | 1058.774 | 3200.96 | 1058.774 | 0 | 1058.774 | 116.71 | 1058.774 | 274.37 | 1058.774 | 0 | 1058.774 | 0 | 1058.774 | 182
2025-08-17 | 7551.2559 | 3774.04 | 39289.5 | 1078.7508 | 3200.96 | 1078.7508 | 0 | 1078.7508 | 116.71 | 1078.7508 | 274.37 | 1078.7508 | 0 | 1078.7508 | 0 | 1078.7508 | 182
2025-08-18 | 7691.094 | 3774.04 | 39993.25 | 1098.7277 | 3200.96 | 1098.7277 | 0 | 1098.7277 | 116.71 | 1098.7277 | 274.37 | 1098.7277 | 0 | 1098.7277 | 0 | 1098.7277 | 182
2025-08-19 | 7830.932 | 3774.04 | 40697 | 1118.7046 | 3200.96 | 1118.7046 | 0 | 1118.7046 | 116.71 | 1118.7046 | 274.37 | 1118.7046 | 0 | 1118.7046 | 0 | 1118.7046 | 182
2025-08-20 | 7970.7701 | 4226.81 | 41400.75 | 1138.6814 | 3200.96 | 1138.6814 | 313.96 | 1138.6814 | 116.71 | 1138.6814 | 413.18 | 1138.6814 | 0 | 1138.6814 | 0 | 1138.6814 | 182
2025-08-21 | 8110.6082 | 4226.81 | 42104.5 | 1158.6583 | 3200.96 | 1158.6583 | 313.96 | 1158.6583 | 116.71 | 1158.6583 | 413.18 | 1158.6583 | 0 | 1158.6583 | 0 | 1158.6583 | 182
2025-08-22 | 8250.4462 | 4326.81 | 42808.25 | 1178.6352 | 3200.96 | 1178.6352 | 313.96 | 1178.6352 | 116.71 | 1178.6352 | 413.18 | 1178.6352 | 100 | 1178.6352 | 0 | 1178.6352 | 182
2025-08-23 | 8390.2843 | 4326.81 | 42808.25 | 1198.612 | 3200.96 | 1198.612 | 313.96 | 1198.612 | 116.71 | 1198.612 | 413.18 | 1198.612 | 100 | 1198.612 | 0 | 1198.612 | 182
2025-08-24 | 8530.1224 | 4326.81 | 42808.25 | 1218.5889 | 3200.96 | 1218.5889 | 313.96 | 1218.5889 | 116.71 | 1218.5889 | 413.18 | 1218.5889 | 100 | 1218.5889 | 0 | 1218.5889 | 182
2025-08-25 | 8669.9605 | 4326.81 | 43488.675 | 1238.5658 | 3200.96 | 1238.5658 | 313.96 | 1238.5658 | 116.71 | 1238.5658 | 413.18 | 1238.5658 | 100 | 1238.5658 | 0 | 1238.5658 | 182
2025-08-26 | 8809.7985 | 4326.81 | 44169.1 | 1258.5426 | 3200.96 | 1258.5426 | 313.96 | 1258.5426 | 116.71 | 1258.5426 | 413.18 | 1258.5426 | 100 | 1258.5426 | 0 | 1258.5426 | 182
2025-08-27 | 8949.6366 | 4326.81 | 44849.525 | 1278.5195 | 3200.96 | 1278.5195 | 313.96 | 1278.5195 | 116.71 | 1278.5195 | 413.18 | 1278.5195 | 100 | 1278.5195 | 0 | 1278.5195 | 182
2025-08-28 | 9089.4747 | 4326.81 | 45529.95 | 1298.4964 | 3200.96 | 1298.4964 | 313.96 | 1298.4964 | 116.71 | 1298.4964 | 413.18 | 1298.4964 | 100 | 1298.4964 | 0 | 1298.4964 | 182
2025-08-29 | 9229.3128 | 4326.81 | 46210.375 | 1318.4733 | 3200.96 | 1318.4733 | 313.96 | 1318.4733 | 116.71 | 1318.4733 | 413.18 | 1318.4733 | 100 | 1318.4733 | 0 | 1318.4733 | 182
2025-08-30 | 9369.1508 | 4326.81 | 46210.375 | 1338.4501 | 3200.96 | 1338.4501 | 313.96 | 1338.4501 | 116.71 | 1338.4501 | 413.18 | 1338.4501 | 100 | 1338.4501 | 0 | 1338.4501 | 182
2025-08-31 | 9508.9889 | 4326.81 | 46210.375 | 1358.427 | 3200.96 | 1358.427 | 313.96 | 1358.427 | 116.71 | 1358.427 | 413.18 | 1358.427 | 100 | 1358.427 | 0 | 1358.427 | 182
2025-09-01 | 9648.827 | 4326.81 | 47373.7 | 1378.4039 | 3200.96 | 1378.4039 | 313.96 | 1378.4039 | 116.71 | 1378.4039 | 413.18 | 1378.4039 | 100 | 1378.4039 | 0 | 1378.4039 | 182
2025-09-02 | 9788.665 | 4326.81 | 48537.025 | 1398.3807 | 3200.96 | 1398.3807 | 313.96 | 1398.3807 | 116.71 | 1398.3807 | 413.18 | 1398.3807 | 100 | 1398.3807 | 0 | 1398.3807 | 182
2025-09-03 | 9928.5031 | 4921.27 | 49700.35 | 1418.3576 | 3200.96 | 1418.3576 | 879.12 | 1418.3576 | 116.71 | 1418.3576 | 413.18 | 1418.3576 | 129.3 | 1418.3576 | 0 | 1418.3576 | 182
2025-09-04 | 10068.3412 | 4976.3 | 50863.675 | 1438.3345 | 3200.96 | 1438.3345 | 879.12 | 1438.3345 | 116.71 | 1438.3345 | 413.18 | 1438.3345 | 184.33 | 1438.3345 | 0 | 1438.3345 | 182
2025-09-05 | 10208.1793 | 5948.88 | 52027 | 1458.3113 | 4151.92 | 1458.3113 | 879.12 | 1458.3113 | 116.71 | 1458.3113 | 413.18 | 1458.3113 | 205.95 | 1458.3113 | 0 | 1458.3113 | 182
2025-09-06 | 10348.0173 | 5948.88 | 52027 | 1478.2882 | 4151.92 | 1478.2882 | 879.12 | 1478.2882 | 116.71 | 1478.2882 | 413.18 | 1478.2882 | 205.95 | 1478.2882 | 0 | 1478.2882 | 182
2025-09-07 | 10487.8554 | 5948.88 | 52027 | 1498.2651 | 4151.92 | 1498.2651 | 879.12 | 1498.2651 | 116.71 | 1498.2651 | 413.18 | 1498.2651 | 205.95 | 1498.2651 | 0 | 1498.2651 | 182
2025-09-08 | 10627.6935 | 5948.88 | 52781.375 | 1518.2419 | 4151.92 | 1518.2419 | 879.12 | 1518.2419 | 116.71 | 1518.2419 | 413.18 | 1518.2419 | 205.95 | 1518.2419 | 0 | 1518.2419 | 182
2025-09-09 | 10767.5315 | 5948.88 | 53535.75 | 1538.2188 | 4151.92 | 1538.2188 | 879.12 | 1538.2188 | 116.71 | 1538.2188 | 413.18 | 1538.2188 | 205.95 | 1538.2188 | 0 | 1538.2188 | 182
2025-09-10 | 10907.3696 | 6185.74 | 54290.125 | 1558.1957 | 4151.92 | 1558.1957 | 879.12 | 1558.1957 | 116.71 | 1558.1957 | 650.04 | 1558.1957 | 205.95 | 1558.1957 | 0 | 1558.1957 | 182
2025-09-11 | 11047.2077 | 6185.74 | 55044.5 | 1578.1725 | 4151.92 | 1578.1725 | 879.12 | 1578.1725 | 116.71 | 1578.1725 | 650.04 | 1578.1725 | 205.95 | 1578.1725 | 0 | 1578.1725 | 182
2025-09-12 | 11187.0458 | 6296.68 | 55798.875 | 1598.1494 | 4151.92 | 1598.1494 | 879.12 | 1598.1494 | 227.65 | 1598.1494 | 650.04 | 1598.1494 | 205.95 | 1598.1494 | 0 | 1598.1494 | 182
2025-09-13 | 11326.8838 | 6296.68 | 55798.875 | 1618.1263 | 4151.92 | 1618.1263 | 879.12 | 1618.1263 | 227.65 | 1618.1263 | 650.04 | 1618.1263 | 205.95 | 1618.1263 | 0 | 1618.1263 | 182
2025-09-14 | 11466.7219 | 6296.68 | 55798.875 | 1638.1031 | 4151.92 | 1638.1031 | 879.12 | 1638.1031 | 227.65 | 1638.1031 | 650.04 | 1638.1031 | 205.95 | 1638.1031 | 0 | 1638.1031 | 182
2025-09-15 | 11606.56 | 6746.68 | 57425.25 | 1658.08 | 4151.92 | 1658.08 | 879.12 | 1658.08 | 227.65 | 1658.08 | 650.04 | 1658.08 | 655.95 | 1658.08 | 0 | 1658.08 | 182
2025-09-16 | 11746.398 | 10209.72 | 59051.625 | 1678.0569 | 7614.96 | 1678.0569 | 879.12 | 1678.0569 | 227.65 | 1678.0569 | 650.04 | 1678.0569 | 655.95 | 1678.0569 | 0 | 1678.0569 | 182
2025-09-17 | 11886.2361 | 10209.72 | 60678 | 1698.0337 | 7614.96 | 1698.0337 | 879.12 | 1698.0337 | 227.65 | 1698.0337 | 650.04 | 1698.0337 | 655.95 | 1698.0337 | 0 | 1698.0337 | 182
2025-09-18 | 12026.0742 | 11155.28 | 62304.375 | 1718.0106 | 8560.52 | 1718.0106 | 879.12 | 1718.0106 | 227.65 | 1718.0106 | 650.04 | 1718.0106 | 655.95 | 1718.0106 | 0 | 1718.0106 | 182
2025-09-19 | 12165.9123 | 11155.28 | 63930.75 | 1737.9875 | 8560.52 | 1737.9875 | 879.12 | 1737.9875 | 227.65 | 1737.9875 | 650.04 | 1737.9875 | 655.95 | 1737.9875 | 0 | 1737.9875 | 182
2025-09-20 | 12305.7503 | 11155.28 | 63930.75 | 1757.9643 | 8560.52 | 1757.9643 | 879.12 | 1757.9643 | 227.65 | 1757.9643 | 650.04 | 1757.9643 | 655.95 | 1757.9643 | 0 | 1757.9643 | 182
2025-09-21 | 12445.5884 | 11155.28 | 63930.75 | 1777.9412 | 8560.52 | 1777.9412 | 879.12 | 1777.9412 | 227.65 | 1777.9412 | 650.04 | 1777.9412 | 655.95 | 1777.9412 | 0 | 1777.9412 | 182
2025-09-22 | 12445.5884 | 11620.8 | 65705.925 | 1777.9412 | 8560.52 | 1777.9412 | 879.12 | 1777.9412 | 227.65 | 1777.9412 | 650.04 | 1777.9412 | 955.95 | 1777.9412 | 0 | 1777.9412 | 347.52
2025-09-23 | 13451.8732 | 11766.51 | 67481.1 | 1921.6962 | 8560.52 | 1921.6962 | 879.12 | 1921.6962 | 227.65 | 1921.6962 | 650.04 | 1921.6962 | 955.95 | 1921.6962 | 0 | 1921.6962 | 493.23
2025-09-24 | 14458.1581 | 12020.36 | 69256.275 | 2065.4512 | 8560.52 | 2065.4512 | 879.12 | 2065.4512 | 227.65 | 2065.4512 | 650.04 | 2065.4512 | 955.95 | 2065.4512 | 148.58 | 2065.4512 | 598.5
2025-09-25 | 15464.4429 | 12061.95 | 71031.45 | 2209.2061 | 8560.52 | 2209.2061 | 879.12 | 2209.2061 | 227.65 | 2209.2061 | 650.04 | 2209.2061 | 955.95 | 2209.2061 | 148.58 | 2209.2061 | 640.09
2025-09-26 | 16470.7278 | 12061.95 | 72806.625 | 2352.9611 | 8560.52 | 2352.9611 | 879.12 | 2352.9611 | 227.65 | 2352.9611 | 650.04 | 2352.9611 | 955.95 | 2352.9611 | 148.58 | 2352.9611 | 640.09
2025-09-27 | 17477.0126 | 12061.95 | 72806.625 | 2496.7161 | 8560.52 | 2496.7161 | 879.12 | 2496.7161 | 227.65 | 2496.7161 | 650.04 | 2496.7161 | 955.95 | 2496.7161 | 148.58 | 2496.7161 | 640.09
2025-09-28 | 18483.2974 | 12197.85 | 72806.625 | 2640.4711 | 8560.52 | 2640.4711 | 879.12 | 2640.4711 | 244.02 | 2640.4711 | 650.04 | 2640.4711 | 955.95 | 2640.4711 | 148.58 | 2640.4711 | 759.62
2025-09-29 | 19489.5823 | 12547.85 | 74913.85 | 2784.226 | 8560.52 | 2784.226 | 879.12 | 2784.226 | 244.02 | 2784.226 | 650.04 | 2784.226 | 1305.95 | 2784.226 | 148.58 | 2784.226 | 759.62
2025-09-30 | 20495.8671 | 12547.85 | 77021.075 | 2927.981 | 8560.52 | 2927.981 | 879.12 | 2927.981 | 244.02 | 2927.981 | 650.04 | 2927.981 | 1305.95 | 2927.981 | 148.58 | 2927.981 | 759.62
2025-10-01 | 21502.152 | 13248.82 | 79128.3 | 3071.736 | 9236.49 | 3071.736 | 879.12 | 3071.736 | 269.02 | 3071.736 | 650.04 | 3071.736 | 1305.95 | 3071.736 | 148.58 | 3071.736 | 759.62
2025-10-02 | 22508.4368 | 13928.74 | 81235.525 | 3215.491 | 9236.49 | 3215.491 | 879.12 | 3215.491 | 817.38 | 3215.491 | 650.04 | 3215.491 | 1305.95 | 3215.491 | 148.58 | 3215.491 | 891.18
2025-10-03 | 23514.7216 | 14634.51 | 83342.75 | 3359.2459 | 9254.09 | 3359.2459 | 1026.41 | 3359.2459 | 817.38 | 3359.2459 | 650.04 | 3359.2459 | 1805.95 | 3359.2459 | 148.58 | 3359.2459 | 932.06
2025-10-04 | 24521.0065 | 14709.51 | 83342.75 | 3503.0009 | 9254.09 | 3503.0009 | 1026.41 | 3503.0009 | 852.38 | 3503.0009 | 650.04 | 3503.0009 | 1805.95 | 3503.0009 | 148.58 | 3503.0009 | 972.06
2025-10-05 | 25527.2913 | 14709.51 | 83342.75 | 3646.7559 | 9254.09 | 3646.7559 | 1026.41 | 3646.7559 | 852.38 | 3646.7559 | 650.04 | 3646.7559 | 1805.95 | 3646.7559 | 148.58 | 3646.7559 | 972.06
2025-10-06 | 26533.5761 | 14709.51 | 85089.875 | 3790.5109 | 9254.09 | 3790.5109 | 1026.41 | 3790.5109 | 852.38 | 3790.5109 | 650.04 | 3790.5109 | 1805.95 | 3790.5109 | 148.58 | 3790.5109 | 972.06
2025-10-07 | 27539.861 | 14865.28 | 86837 | 3934.2659 | 9344.08 | 3934.2659 | 1026.41 | 3934.2659 | 852.38 | 3934.2659 | 650.04 | 3934.2659 | 1805.95 | 3934.2659 | 148.58 | 3934.2659 | 1037.84
2025-10-08 | 28546.1458 | 14865.28 | 88584.125 | 4078.0208 | 9344.08 | 4078.0208 | 1026.41 | 4078.0208 | 852.38 | 4078.0208 | 650.04 | 4078.0208 | 1805.95 | 4078.0208 | 148.58 | 4078.0208 | 1037.84
2025-10-09 | 29552.4307 | 14929.65 | 90331.25 | 4221.7758 | 9344.08 | 4221.7758 | 1026.41 | 4221.7758 | 859.39 | 4221.7758 | 650.04 | 4221.7758 | 1805.95 | 4221.7758 | 148.58 | 4221.7758 | 1095.2
2025-10-10 | 30558.7155 | 14959.65 | 92078.375 | 4365.5308 | 9344.08 | 4365.5308 | 1026.41 | 4365.5308 | 889.39 | 4365.5308 | 650.04 | 4365.5308 | 1805.95 | 4365.5308 | 148.58 | 4365.5308 | 1095.2
2025-10-11 | 31565.0003 | 14959.65 | 92078.375 | 4509.2858 | 9344.08 | 4509.2858 | 1026.41 | 4509.2858 | 889.39 | 4509.2858 | 650.04 | 4509.2858 | 1805.95 | 4509.2858 | 148.58 | 4509.2858 | 1095.2
2025-10-12 | 32571.2852 | 14984.65 | 92078.375 | 4653.0407 | 9344.08 | 4653.0407 | 1026.41 | 4653.0407 | 889.39 | 4653.0407 | 650.04 | 4653.0407 | 1805.95 | 4653.0407 | 148.58 | 4653.0407 | 1120.2
2025-10-13 | 33577.57 | 14984.65 | 93848.825 | 4796.7957 | 9344.08 | 4796.7957 | 1026.41 | 4796.7957 | 889.39 | 4796.7957 | 650.04 | 4796.7957 | 1805.95 | 4796.7957 | 148.58 | 4796.7957 | 1120.2
2025-10-14 | 34583.8548 | 15868.99 | 95619.275 | 4940.5507 | 9344.08 | 4940.5507 | 1026.41 | 4940.5507 | 889.39 | 4940.5507 | 650.04 | 4940.5507 | 2505.95 | 4940.5507 | 148.58 | 4940.5507 | 1304.54
2025-10-15 | 35590.1397 | 17951.55 | 97389.725 | 5084.3057 | 9344.08 | 5084.3057 | 3061.49 | 5084.3057 | 889.39 | 5084.3057 | 650.04 | 5084.3057 | 2505.95 | 5084.3057 | 148.58 | 5084.3057 | 1352.02
2025-10-16 | 36596.4245 | 18015.19 | 99160.175 | 5228.0606 | 9344.08 | 5228.0606 | 3061.49 | 5228.0606 | 889.39 | 5228.0606 | 650.04 | 5228.0606 | 2505.95 | 5228.0606 | 148.58 | 5228.0606 | 1415.66
2025-10-17 | 37602.7094 | 19157.15 | 100930.625 | 5371.8156 | 9786.04 | 5371.8156 | 3061.49 | 5371.8156 | 889.39 | 5371.8156 | 650.04 | 5371.8156 | 3205.95 | 5371.8156 | 148.58 | 5371.8156 | 1415.66
2025-10-18 | 38608.9942 | 19157.15 | 100930.625 | 5515.5706 | 9786.04 | 5515.5706 | 3061.49 | 5515.5706 | 889.39 | 5515.5706 | 650.04 | 5515.5706 | 3205.95 | 5515.5706 | 148.58 | 5515.5706 | 1415.66
2025-10-19 | 39615.279 | 19157.15 | 100930.625 | 5659.3256 | 9786.04 | 5659.3256 | 3061.49 | 5659.3256 | 889.39 | 5659.3256 | 650.04 | 5659.3256 | 3205.95 | 5659.3256 | 148.58 | 5659.3256 | 1415.66
2025-10-20 | 40621.5639 | 19455.45 | 103046.55 | 5803.0806 | 10084.34 | 5803.0806 | 3061.49 | 5803.0806 | 889.39 | 5803.0806 | 650.04 | 5803.0806 | 3205.95 | 5803.0806 | 148.58 | 5803.0806 | 1415.66
2025-10-21 | 41627.8487 | 19455.45 | 105162.475 | 5946.8355 | 10084.34 | 5946.8355 | 3061.49 | 5946.8355 | 889.39 | 5946.8355 | 650.04 | 5946.8355 | 3205.95 | 5946.8355 | 148.58 | 5946.8355 | 1415.66
2025-10-22 | 42634.1336 | 19521.88 | 107278.4 | 6090.5905 | 10084.34 | 6090.5905 | 3061.49 | 6090.5905 | 889.39 | 6090.5905 | 650.04 | 6090.5905 | 3205.95 | 6090.5905 | 148.58 | 6090.5905 | 1482.09
2025-10-23 | 43640.4184 | 19658.28 | 109394.325 | 6234.3455 | 10084.34 | 6234.3455 | 3061.49 | 6234.3455 | 889.39 | 6234.3455 | 650.04 | 6234.3455 | 3205.95 | 6234.3455 | 148.58 | 6234.3455 | 1618.49
2025-10-24 | 44646.7032 | 22793.36 | 111510.25 | 6378.1005 | 10084.34 | 6378.1005 | 5096.57 | 6378.1005 | 889.39 | 6378.1005 | 650.04 | 6378.1005 | 4305.95 | 6378.1005 | 148.58 | 6378.1005 | 1618.49
2025-10-25 | 45652.9881 | 22818.36 | 111510.25 | 6521.8554 | 10084.34 | 6521.8554 | 5096.57 | 6521.8554 | 889.39 | 6521.8554 | 650.04 | 6521.8554 | 4305.95 | 6521.8554 | 148.58 | 6521.8554 | 1643.49
2025-10-26 | 46659.2729 | 23002.7 | 111510.25 | 6665.6104 | 10084.34 | 6665.6104 | 5096.57 | 6665.6104 | 889.39 | 6665.6104 | 650.04 | 6665.6104 | 4305.95 | 6665.6104 | 148.58 | 6665.6104 | 1827.83
2025-10-27 | 47665.5577 | 23643.66 | 113280.75 | 6809.3654 | 10725.3 | 6809.3654 | 5096.57 | 6809.3654 | 889.39 | 6809.3654 | 650.04 | 6809.3654 | 4305.95 | 6809.3654 | 148.58 | 6809.3654 | 1827.83
2025-10-28 | 48671.8426 | 23688.24 | 115051.25 | 6953.1204 | 10725.3 | 6953.1204 | 5096.57 | 6953.1204 | 889.39 | 6953.1204 | 650.04 | 6953.1204 | 4305.95 | 6953.1204 | 148.58 | 6953.1204 | 1872.41
2025-10-29 | 49678.1274 | 23713.24 | 116821.75 | 7096.8753 | 10725.3 | 7096.8753 | 5096.57 | 7096.8753 | 889.39 | 7096.8753 | 650.04 | 7096.8753 | 4305.95 | 7096.8753 | 148.58 | 7096.8753 | 1897.41
2025-10-30 | 50684.4123 | 23798.03 | 118592.25 | 7240.6303 | 10725.3 | 7240.6303 | 5096.57 | 7240.6303 | 889.39 | 7240.6303 | 650.04 | 7240.6303 | 4305.95 | 7240.6303 | 148.58 | 7240.6303 | 1982.2
2025-10-31 | 51690.6971 | 25444.14 | 120362.75 | 7384.3853 | 10805.3 | 7384.3853 | 5909.69 | 7384.3853 | 918.31 | 7384.3853 | 650.04 | 7384.3853 | 4905.95 | 7384.3853 | 148.58 | 7384.3853 | 2106.27
2025-11-01 | 52696.9819 | 25684.24 | 120362.75 | 7528.1403 | 10805.3 | 7528.1403 | 5909.69 | 7528.1403 | 918.31 | 7528.1403 | 650.04 | 7528.1403 | 4905.95 | 7528.1403 | 148.58 | 7528.1403 | 2346.37
2025-11-02 | 53703.2668 | 25684.24 | 120362.75 | 7671.8953 | 10805.3 | 7671.8953 | 5909.69 | 7671.8953 | 918.31 | 7671.8953 | 650.04 | 7671.8953 | 4905.95 | 7671.8953 | 148.58 | 7671.8953 | 2346.37
2025-11-03 | 54709.5516 | 25684.24 | 122034.05 | 7815.6502 | 10805.3 | 7815.6502 | 5909.69 | 7815.6502 | 918.31 | 7815.6502 | 650.04 | 7815.6502 | 4905.95 | 7815.6502 | 148.58 | 7815.6502 | 2346.37
2025-11-04 | 55715.8365 | 26221.15 | 123705.35 | 7959.4052 | 10805.3 | 7959.4052 | 5909.69 | 7959.4052 | 918.31 | 7959.4052 | 650.04 | 7959.4052 | 4905.95 | 7959.4052 | 559.58 | 7959.4052 | 2472.28
2025-11-05 | 56722.1213 | 28874.98 | 125376.65 | 8103.1602 | 10840.3 | 8103.1602 | 8257.57 | 8103.1602 | 1006.72 | 8103.1602 | 650.04 | 8103.1602 | 4905.95 | 8103.1602 | 559.58 | 8103.1602 | 2654.82
2025-11-06 | 57728.4061 | 28929.76 | 127047.95 | 8246.9152 | 10840.3 | 8246.9152 | 8257.57 | 8246.9152 | 1036.72 | 8246.9152 | 650.04 | 8246.9152 | 4905.95 | 8246.9152 | 559.58 | 8246.9152 | 2679.6
2025-11-07 | 58734.691 | 30042.48 | 128719.25 | 8390.6701 | 10840.3 | 8390.6701 | 8257.57 | 8390.6701 | 1036.72 | 8390.6701 | 650.04 | 8390.6701 | 5955.95 | 8390.6701 | 559.58 | 8390.6701 | 2742.32
2025-11-08 | 59740.9758 | 30063.19 | 128719.25 | 8534.4251 | 10840.3 | 8534.4251 | 8257.57 | 8534.4251 | 1036.72 | 8534.4251 | 650.04 | 8534.4251 | 5955.95 | 8534.4251 | 559.58 | 8534.4251 | 2763.03
2025-11-09 | 60747.2606 | 30063.19 | 128719.25 | 8678.1801 | 10840.3 | 8678.1801 | 8257.57 | 8678.1801 | 1036.72 | 8678.1801 | 650.04 | 8678.1801 | 5955.95 | 8678.1801 | 559.58 | 8678.1801 | 2763.03
2025-11-10 | 61753.5455 | 30091.18 | 130337.625 | 8821.9351 | 10840.3 | 8821.9351 | 8257.57 | 8821.9351 | 1036.72 | 8821.9351 | 650.04 | 8821.9351 | 5955.95 | 8821.9351 | 587.57 | 8821.9351 | 2763.03
2025-11-11 | 62759.8303 | 30133.05 | 131956 | 8965.69 | 10840.3 | 8965.69 | 8257.57 | 8965.69 | 1036.72 | 8965.69 | 650.04 | 8965.69 | 5955.95 | 8965.69 | 587.57 | 8965.69 | 2804.9
2025-11-12 | 63766.1152 | 30133.05 | 133574.375 | 9109.445 | 10840.3 | 9109.445 | 8257.57 | 9109.445 | 1036.72 | 9109.445 | 650.04 | 9109.445 | 5955.95 | 9109.445 | 587.57 | 9109.445 | 2804.9
2025-11-13 | 64772.4 | 30133.05 | 135192.75 | 9253.2 | 10840.3 | 9253.2 | 8257.57 | 9253.2 | 1036.72 | 9253.2 | 650.04 | 9253.2 | 5955.95 | 9253.2 | 587.57 | 9253.2 | 2804.9
2025-11-14 | 65236.4673 | 29631.15 | 136811.125 | 9319.4953 | 10840.3 | 9319.4953 | 8257.57 | 9319.4953 | 1036.72 | 9319.4953 | 650.04 | 9319.4953 | 5405.95 | 9319.4953 | 635.67 | 9319.4953 | 2804.9
2025-11-15 | 65700.5346 | 31675.9 | 136811.125 | 9385.7907 | 10840.3 | 9385.7907 | 10137.57 | 9385.7907 | 1036.72 | 9385.7907 | 650.04 | 9385.7907 | 5405.95 | 9385.7907 | 635.67 | 9385.7907 | 2969.65
2025-11-16 | 66164.6018 | 31675.9 | 136811.125 | 9452.086 | 10840.3 | 9452.086 | 10137.57 | 9452.086 | 1036.72 | 9452.086 | 650.04 | 9452.086 | 5405.95 | 9452.086 | 635.67 | 9452.086 | 2969.65
2025-11-17 | 66628.6691 | 31675.9 | 137515.425 | 9518.3813 | 10840.3 | 9518.3813 | 10137.57 | 9518.3813 | 1036.72 | 9518.3813 | 650.04 | 9518.3813 | 5405.95 | 9518.3813 | 635.67 | 9518.3813 | 2969.65
2025-11-18 | 67092.7364 | 31675.9 | 138219.725 | 9584.6766 | 10840.3 | 9584.6766 | 10137.57 | 9584.6766 | 1036.72 | 9584.6766 | 650.04 | 9584.6766 | 5405.95 | 9584.6766 | 635.67 | 9584.6766 | 2969.65
2025-11-19 | 67556.8037 | 31675.9 | 138924.025 | 9650.972 | 10840.3 | 9650.972 | 10137.57 | 9650.972 | 1036.72 | 9650.972 | 650.04 | 9650.972 | 5405.95 | 9650.972 | 635.67 | 9650.972 | 2969.65
2025-11-20 | 68020.8709 | 31675.9 | 139628.325 | 9717.2673 | 10840.3 | 9717.2673 | 10137.57 | 9717.2673 | 1036.72 | 9717.2673 | 650.04 | 9717.2673 | 5405.95 | 9717.2673 | 635.67 | 9717.2673 | 2969.65
2025-11-21 | 68484.9382 | 31675.9 | 140332.625 | 9783.5626 | 10840.3 | 9783.5626 | 10137.57 | 9783.5626 | 1036.72 | 9783.5626 | 650.04 | 9783.5626 | 5405.95 | 9783.5626 | 635.67 | 9783.5626 | 2969.65
2025-11-22 | 68949.0055 | 31675.9 | 140332.625 | 9849.8579 | 10840.3 | 9849.8579 | 10137.57 | 9849.8579 | 1036.72 | 9849.8579 | 650.04 | 9849.8579 | 5405.95 | 9849.8579 | 635.67 | 9849.8579 | 2969.65
2025-11-23 | 69413.0728 | 31675.9 | 140332.625 | 9916.1533 | 10840.3 | 9916.1533 | 10137.57 | 9916.1533 | 1036.72 | 9916.1533 | 650.04 | 9916.1533 | 5405.95 | 9916.1533 | 635.67 | 9916.1533 | 2969.65
2025-11-24 | 69877.1401 | 31675.9 | 141144.85 | 9982.4486 | 10840.3 | 9982.4486 | 10137.57 | 9982.4486 | 1036.72 | 9982.4486 | 650.04 | 9982.4486 | 5405.95 | 9982.4486 | 635.67 | 9982.4486 | 2969.65
2025-11-25 | 70341.2073 | 31675.9 | 141957.075 | 10048.7439 | 10840.3 | 10048.7439 | 10137.57 | 10048.7439 | 1036.72 | 10048.7439 | 650.04 | 10048.7439 | 5405.95 | 10048.7439 | 635.67 | 10048.7439 | 2969.65
2025-11-26 | 70805.2746 | 31675.9 | 142769.3 | 10115.0392 | 10840.3 | 10115.0392 | 10137.57 | 10115.0392 | 1036.72 | 10115.0392 | 650.04 | 10115.0392 | 5405.95 | 10115.0392 | 635.67 | 10115.0392 | 2969.65
2025-11-27 | 71269.3419 | 31675.9 | 143581.525 | 10181.3346 | 10840.3 | 10181.3346 | 10137.57 | 10181.3346 | 1036.72 | 10181.3346 | 650.04 | 10181.3346 | 5405.95 | 10181.3346 | 635.67 | 10181.3346 | 2969.65
2025-11-28 | 71733.4092 | 31675.9 | 144393.75 | 10247.6299 | 10840.3 | 10247.6299 | 10137.57 | 10247.6299 | 1036.72 | 10247.6299 | 650.04 | 10247.6299 | 5405.95 | 10247.6299 | 635.67 | 10247.6299 | 2969.65
2025-11-29 | 72197.4765 | 31675.9 | 144393.75 | 10313.9252 | 10840.3 | 10313.9252 | 10137.57 | 10313.9252 | 1036.72 | 10313.9252 | 650.04 | 10313.9252 | 5405.95 | 10313.9252 | 635.67 | 10313.9252 | 2969.65
2025-11-30 | 72661.5437 | 31744.91 | 144393.75 | 10380.2205 | 10840.3 | 10380.2205 | 10137.57 | 10380.2205 | 1036.72 | 10380.2205 | 650.04 | 10380.2205 | 5405.95 | 10380.2205 | 635.67 | 10380.2205 | 3038.66
2025-12-01 | 73125.611 | 31744.91 | 145486.9 | 10446.5159 | 10840.3 | 10446.5159 | 10137.57 | 10446.5159 | 1036.72 | 10446.5159 | 650.04 | 10446.5159 | 5405.95 | 10446.5159 | 635.67 | 10446.5159 | 3038.66
2025-12-02 | 73589.6783 | 31744.91 | 146580.05 | 10512.8112 | 10840.3 | 10512.8112 | 10137.57 | 10512.8112 | 1036.72 | 10512.8112 | 650.04 | 10512.8112 | 5405.95 | 10512.8112 | 635.67 | 10512.8112 | 3038.66
2025-12-03 | 74053.7456 | 31744.91 | 147673.2 | 10579.1065 | 10840.3 | 10579.1065 | 10137.57 | 10579.1065 | 1036.72 | 10579.1065 | 650.04 | 10579.1065 | 5405.95 | 10579.1065 | 635.67 | 10579.1065 | 3038.66
2025-12-04 | 74517.8128 | 31744.91 | 148766.35 | 10645.4018 | 10840.3 | 10645.4018 | 10137.57 | 10645.4018 | 1036.72 | 10645.4018 | 650.04 | 10645.4018 | 5405.95 | 10645.4018 | 635.67 | 10645.4018 | 3038.66
2025-12-05 | 74981.8801 | 32244.91 | 149859.5 | 10711.6972 | 10840.3 | 10711.6972 | 10137.57 | 10711.6972 | 1036.72 | 10711.6972 | 650.04 | 10711.6972 | 5905.95 | 10711.6972 | 635.67 | 10711.6972 | 3038.66
2025-12-06 | 75445.9474 | 32244.91 | 149859.5 | 10777.9925 | 10840.3 | 10777.9925 | 10137.57 | 10777.9925 | 1036.72 | 10777.9925 | 650.04 | 10777.9925 | 5905.95 | 10777.9925 | 635.67 | 10777.9925 | 3038.66
2025-12-07 | 75910.0147 | 32244.91 | 149859.5 | 10844.2878 | 10840.3 | 10844.2878 | 10137.57 | 10844.2878 | 1036.72 | 10844.2878 | 650.04 | 10844.2878 | 5905.95 | 10844.2878 | 635.67 | 10844.2878 | 3038.66
2025-12-08 | 76374.082 | 32244.91 | 151023.125 | 10910.5831 | 10840.3 | 10910.5831 | 10137.57 | 10910.5831 | 1036.72 | 10910.5831 | 650.04 | 10910.5831 | 5905.95 | 10910.5831 | 635.67 | 10910.5831 | 3038.66
2025-12-09 | 76838.1492 | 32244.91 | 152186.75 | 10976.8785 | 10840.3 | 10976.8785 | 10137.57 | 10976.8785 | 1036.72 | 10976.8785 | 650.04 | 10976.8785 | 5905.95 | 10976.8785 | 635.67 | 10976.8785 | 3038.66
2025-12-10 | 77302.2165 | 32244.91 | 153350.375 | 11043.1738 | 10840.3 | 11043.1738 | 10137.57 | 11043.1738 | 1036.72 | 11043.1738 | 650.04 | 11043.1738 | 5905.95 | 11043.1738 | 635.67 | 11043.1738 | 3038.66
2025-12-11 | 77766.2838 | 32244.91 | 154514 | 11109.4691 | 10840.3 | 11109.4691 | 10137.57 | 11109.4691 | 1036.72 | 11109.4691 | 650.04 | 11109.4691 | 5905.95 | 11109.4691 | 635.67 | 11109.4691 | 3038.66
2025-12-12 | 78230.3511 | 32944.91 | 155677.625 | 11175.7644 | 10840.3 | 11175.7644 | 10137.57 | 11175.7644 | 1036.72 | 11175.7644 | 650.04 | 11175.7644 | 6605.95 | 11175.7644 | 635.67 | 11175.7644 | 3038.66
2025-12-13 | 78694.4183 | 32944.91 | 155677.625 | 11242.0598 | 10840.3 | 11242.0598 | 10137.57 | 11242.0598 | 1036.72 | 11242.0598 | 650.04 | 11242.0598 | 6605.95 | 11242.0598 | 635.67 | 11242.0598 | 3038.66
2025-12-14 | 79158.4856 | 32944.91 | 155677.625 | 11308.3551 | 10840.3 | 11308.3551 | 10137.57 | 11308.3551 | 1036.72 | 11308.3551 | 650.04 | 11308.3551 | 6605.95 | 11308.3551 | 635.67 | 11308.3551 | 3038.66
2025-12-15 | 79622.5529 | 32944.91 | 156841.25 | 11374.6504 | 10840.3 | 11374.6504 | 10137.57 | 11374.6504 | 1036.72 | 11374.6504 | 650.04 | 11374.6504 | 6605.95 | 11374.6504 | 635.67 | 11374.6504 | 3038.66
2025-12-16 | 80086.6202 | 32944.91 | 158004.875 | 11440.9457 | 10840.3 | 11440.9457 | 10137.57 | 11440.9457 | 1036.72 | 11440.9457 | 650.04 | 11440.9457 | 6605.95 | 11440.9457 | 635.67 | 11440.9457 | 3038.66
2025-12-17 | 80550.6875 | 32944.91 | 159168.5 | 11507.2411 | 10840.3 | 11507.2411 | 10137.57 | 11507.2411 | 1036.72 | 11507.2411 | 650.04 | 11507.2411 | 6605.95 | 11507.2411 | 635.67 | 11507.2411 | 3038.66
2025-12-18 | 81014.7547 | 32944.91 | 160332.125 | 11573.5364 | 10840.3 | 11573.5364 | 10137.57 | 11573.5364 | 1036.72 | 11573.5364 | 650.04 | 11573.5364 | 6605.95 | 11573.5364 | 635.67 | 11573.5364 | 3038.66
2025-12-19 | 81478.822 | 34977.71 | 161495.75 | 11639.8317 | 10840.3 | 11639.8317 | 12170.37 | 11639.8317 | 1036.72 | 11639.8317 | 650.04 | 11639.8317 | 6605.95 | 11639.8317 | 635.67 | 11639.8317 | 3038.66
2025-12-20 | 81942.8893 | 35180.99 | 161495.75 | 11706.127 | 10840.3 | 11706.127 | 12373.65 | 11706.127 | 1036.72 | 11706.127 | 650.04 | 11706.127 | 6605.95 | 11706.127 | 635.67 | 11706.127 | 3038.66
2025-12-21 | 82406.9566 | 35180.99 | 161495.75 | 11772.4224 | 10840.3 | 11772.4224 | 12373.65 | 11772.4224 | 1036.72 | 11772.4224 | 650.04 | 11772.4224 | 6605.95 | 11772.4224 | 635.67 | 11772.4224 | 3038.66
2025-12-22 | 82871.0239 | 35180.99 | 161495.75 | 11838.7177 | 10840.3 | 11838.7177 | 12373.65 | 11838.7177 | 1036.72 | 11838.7177 | 650.04 | 11838.7177 | 6605.95 | 11838.7177 | 635.67 | 11838.7177 | 3038.66
2025-12-23 | 83335.0911 | 35180.99 | 161495.75 | 11905.013 | 10840.3 | 11905.013 | 12373.65 | 11905.013 | 1036.72 | 11905.013 | 650.04 | 11905.013 | 6605.95 | 11905.013 | 635.67 | 11905.013 | 3038.66
2025-12-24 | 83799.1584 | 35180.99 | 161495.75 | 11971.3083 | 10840.3 | 11971.3083 | 12373.65 | 11971.3083 | 1036.72 | 11971.3083 | 650.04 | 11971.3083 | 6605.95 | 11971.3083 | 635.67 | 11971.3083 | 3038.66
2025-12-25 | 84263.2257 | 35180.99 | 161495.75 | 12037.6037 | 10840.3 | 12037.6037 | 12373.65 | 12037.6037 | 1036.72 | 12037.6037 | 650.04 | 12037.6037 | 6605.95 | 12037.6037 | 635.67 | 12037.6037 | 3038.66
2025-12-26 | 84727.293 | 35180.99 | 161495.75 | 12103.899 | 10840.3 | 12103.899 | 12373.65 | 12103.899 | 1036.72 | 12103.899 | 650.04 | 12103.899 | 6605.95 | 12103.899 | 635.67 | 12103.899 | 3038.66
2025-12-27 | 85191.3602 | 35180.99 | 161495.75 | 12170.1943 | 10840.3 | 12170.1943 | 12373.65 | 12170.1943 | 1036.72 | 12170.1943 | 650.04 | 12170.1943 | 6605.95 | 12170.1943 | 635.67 | 12170.1943 | 3038.66
2025-12-28 | 85655.4275 | 35180.99 | 161495.75 | 12236.4896 | 10840.3 | 12236.4896 | 12373.65 | 12236.4896 | 1036.72 | 12236.4896 | 650.04 | 12236.4896 | 6605.95 | 12236.4896 | 635.67 | 12236.4896 | 3038.66
2025-12-29 | 86119.4948 | 35180.99 | 162393.1 | 12302.785 | 10840.3 | 12302.785 | 12373.65 | 12302.785 | 1036.72 | 12302.785 | 650.04 | 12302.785 | 6605.95 | 12302.785 | 635.67 | 12302.785 | 3038.66
2025-12-30 | 86583.5621 | 35180.99 | 163290.45 | 12369.0803 | 10840.3 | 12369.0803 | 12373.65 | 12369.0803 | 1036.72 | 12369.0803 | 650.04 | 12369.0803 | 6605.95 | 12369.0803 | 635.67 | 12369.0803 | 3038.66
2025-12-31 | 87047.6294 | 35180.99 | 164187.8 | 12435.3756 | 10840.3 | 12435.3756 | 12373.65 | 12435.3756 | 1036.72 | 12435.3756 | 650.04 | 12435.3756 | 6605.95 | 12435.3756 | 635.67 | 12435.3756 | 3038.66
2026-01-01 | 87511.6966 | 35180.99 | 165085.15 | 12501.6709 | 10840.3 | 12501.6709 | 12373.65 | 12501.6709 | 1036.72 | 12501.6709 | 650.04 | 12501.6709 | 6605.95 | 12501.6709 | 635.67 | 12501.6709 | 3038.66
2026-01-02 | 87975.7639 | 35180.99 | 165982.5 | 12567.9663 | 10840.3 | 12567.9663 | 12373.65 | 12567.9663 | 1036.72 | 12567.9663 | 650.04 | 12567.9663 | 6605.95 | 12567.9663 | 635.67 | 12567.9663 | 3038.66
2026-01-03 | 88439.8312 | 35180.99 | 165982.5 | 12634.2616 | 10840.3 | 12634.2616 | 12373.65 | 12634.2616 | 1036.72 | 12634.2616 | 650.04 | 12634.2616 | 6605.95 | 12634.2616 | 635.67 | 12634.2616 | 3038.66
2026-01-04 | 88903.8985 | 35180.99 | 165982.5 | 12700.5569 | 10840.3 | 12700.5569 | 12373.65 | 12700.5569 | 1036.72 | 12700.5569 | 650.04 | 12700.5569 | 6605.95 | 12700.5569 | 635.67 | 12700.5569 | 3038.66
2026-01-05 | 89367.9657 | 35180.99 | 167054.925 | 12766.8522 | 10840.3 | 12766.8522 | 12373.65 | 12766.8522 | 1036.72 | 12766.8522 | 650.04 | 12766.8522 | 6605.95 | 12766.8522 | 635.67 | 12766.8522 | 3038.66
2026-01-06 | 89832.033 | 36256.47 | 168127.35 | 12833.1476 | 11215.78 | 12833.1476 | 12373.65 | 12833.1476 | 1036.72 | 12833.1476 | 650.04 | 12833.1476 | 7305.95 | 12833.1476 | 635.67 | 12833.1476 | 3038.66
2026-01-07 | 90296.1003 | 36256.47 | 169199.775 | 12899.4429 | 11215.78 | 12899.4429 | 12373.65 | 12899.4429 | 1036.72 | 12899.4429 | 650.04 | 12899.4429 | 7305.95 | 12899.4429 | 635.67 | 12899.4429 | 3038.66
2026-01-08 | 90760.1676 | 36256.47 | 170272.2 | 12965.7382 | 11215.78 | 12965.7382 | 12373.65 | 12965.7382 | 1036.72 | 12965.7382 | 650.04 | 12965.7382 | 7305.95 | 12965.7382 | 635.67 | 12965.7382 | 3038.66
2026-01-09 | 91224.2349 | 38289.27 | 171344.625 | 13032.0336 | 11215.78 | 13032.0336 | 14406.45 | 13032.0336 | 1036.72 | 13032.0336 | 650.04 | 13032.0336 | 7305.95 | 13032.0336 | 635.67 | 13032.0336 | 3038.66
2026-01-10 | 91688.3021 | 38289.27 | 171344.625 | 13098.3289 | 11215.78 | 13098.3289 | 14406.45 | 13098.3289 | 1036.72 | 13098.3289 | 650.04 | 13098.3289 | 7305.95 | 13098.3289 | 635.67 | 13098.3289 | 3038.66
2026-01-11 | 92152.3694 | 38289.27 | 171344.625 | 13164.6242 | 11215.78 | 13164.6242 | 14406.45 | 13164.6242 | 1036.72 | 13164.6242 | 650.04 | 13164.6242 | 7305.95 | 13164.6242 | 635.67 | 13164.6242 | 3038.66
2026-01-12 | 92616.4367 | 38289.27 | 172044.925 | 13230.9195 | 11215.78 | 13230.9195 | 14406.45 | 13230.9195 | 1036.72 | 13230.9195 | 650.04 | 13230.9195 | 7305.95 | 13230.9195 | 635.67 | 13230.9195 | 3038.66
2026-01-13 | 93080.504 | 39102.39 | 172745.225 | 13297.2149 | 11215.78 | 13297.2149 | 15219.57 | 13297.2149 | 1036.72 | 13297.2149 | 650.04 | 13297.2149 | 7305.95 | 13297.2149 | 635.67 | 13297.2149 | 3038.66
2026-01-14 | 93544.5713 | 39827.99 | 173445.525 | 13363.5102 | 11215.78 | 13363.5102 | 15219.57 | 13363.5102 | 1762.32 | 13363.5102 | 650.04 | 13363.5102 | 7305.95 | 13363.5102 | 635.67 | 13363.5102 | 3038.66
2026-01-15 | 94008.6385 | 39827.99 | 174145.825 | 13429.8055 | 11215.78 | 13429.8055 | 15219.57 | 13429.8055 | 1762.32 | 13429.8055 | 650.04 | 13429.8055 | 7305.95 | 13429.8055 | 635.67 | 13429.8055 | 3038.66
2026-01-16 | 94472.7058 | 40877.99 | 174846.125 | 13496.1008 | 11215.78 | 13496.1008 | 15219.57 | 13496.1008 | 1762.32 | 13496.1008 | 650.04 | 13496.1008 | 8355.95 | 13496.1008 | 635.67 | 13496.1008 | 3038.66
2026-01-17 | 94936.7731 | 40877.99 | 174846.125 | 13562.3962 | 11215.78 | 13562.3962 | 15219.57 | 13562.3962 | 1762.32 | 13562.3962 | 650.04 | 13562.3962 | 8355.95 | 13562.3962 | 635.67 | 13562.3962 | 3038.66
2026-01-18 | 95400.8404 | 40877.99 | 174846.125 | 13628.6915 | 11215.78 | 13628.6915 | 15219.57 | 13628.6915 | 1762.32 | 13628.6915 | 650.04 | 13628.6915 | 8355.95 | 13628.6915 | 635.67 | 13628.6915 | 3038.66
2026-01-19 | 95864.9076 | 40877.99 | 175873.425 | 13694.9868 | 11215.78 | 13694.9868 | 15219.57 | 13694.9868 | 1762.32 | 13694.9868 | 650.04 | 13694.9868 | 8355.95 | 13694.9868 | 635.67 | 13694.9868 | 3038.66
2026-01-20 | 96328.9749 | 40877.99 | 176900.725 | 13761.2821 | 11215.78 | 13761.2821 | 15219.57 | 13761.2821 | 1762.32 | 13761.2821 | 650.04 | 13761.2821 | 8355.95 | 13761.2821 | 635.67 | 13761.2821 | 3038.66
2026-01-21 | 96793.0422 | 40877.99 | 177928.025 | 13827.5775 | 11215.78 | 13827.5775 | 15219.57 | 13827.5775 | 1762.32 | 13827.5775 | 650.04 | 13827.5775 | 8355.95 | 13827.5775 | 635.67 | 13827.5775 | 3038.66
2026-01-22 | 97257.1095 | 41253.47 | 178955.325 | 13893.8728 | 11591.26 | 13893.8728 | 15219.57 | 13893.8728 | 1762.32 | 13893.8728 | 650.04 | 13893.8728 | 8355.95 | 13893.8728 | 635.67 | 13893.8728 | 3038.66
2026-01-23 | 97721.1768 | 42053.47 | 179982.625 | 13960.1681 | 11591.26 | 13960.1681 | 15219.57 | 13960.1681 | 1762.32 | 13960.1681 | 650.04 | 13960.1681 | 9155.95 | 13960.1681 | 635.67 | 13960.1681 | 3038.66
2026-01-24 | 98185.244 | 42053.47 | 179982.625 | 14026.4634 | 11591.26 | 14026.4634 | 15219.57 | 14026.4634 | 1762.32 | 14026.4634 | 650.04 | 14026.4634 | 9155.95 | 14026.4634 | 635.67 | 14026.4634 | 3038.66
2026-01-25 | 98649.3113 | 42053.47 | 179982.625 | 14092.7588 | 11591.26 | 14092.7588 | 15219.57 | 14092.7588 | 1762.32 | 14092.7588 | 650.04 | 14092.7588 | 9155.95 | 14092.7588 | 635.67 | 14092.7588 | 3038.66
2026-01-26 | 99113.3786 | 42053.47 | 181735.85 | 14159.0541 | 11591.26 | 14159.0541 | 15219.57 | 14159.0541 | 1762.32 | 14159.0541 | 650.04 | 14159.0541 | 9155.95 | 14159.0541 | 635.67 | 14159.0541 | 3038.66
2026-01-27 | 99577.4459 | 42053.47 | 183489.075 | 14225.3494 | 11591.26 | 14225.3494 | 15219.57 | 14225.3494 | 1762.32 | 14225.3494 | 650.04 | 14225.3494 | 9155.95 | 14225.3494 | 635.67 | 14225.3494 | 3038.66
2026-01-28 | 100041.5131 | 43106.59 | 185242.3 | 14291.6447 | 11591.26 | 14291.6447 | 16272.69 | 14291.6447 | 1762.32 | 14291.6447 | 650.04 | 14291.6447 | 9155.95 | 14291.6447 | 635.67 | 14291.6447 | 3038.66
2026-01-29 | 100505.5804 | 43106.59 | 186995.525 | 14357.9401 | 11591.26 | 14357.9401 | 16272.69 | 14357.9401 | 1762.32 | 14357.9401 | 650.04 | 14357.9401 | 9155.95 | 14357.9401 | 635.67 | 14357.9401 | 3038.66
2026-01-30 | 100969.6477 | 44610.13 | 188748.75 | 14424.2354 | 11591.26 | 14424.2354 | 17325.73 | 14424.2354 | 2212.82 | 14424.2354 | 650.04 | 14424.2354 | 9155.95 | 14424.2354 | 635.67 | 14424.2354 | 3038.66
2026-01-31 | 101433.715 | 44610.13 | 188748.75 | 14490.5307 | 11591.26 | 14490.5307 | 17325.73 | 14490.5307 | 2212.82 | 14490.5307 | 650.04 | 14490.5307 | 9155.95 | 14490.5307 | 635.67 | 14490.5307 | 3038.66
2026-02-01 | 101897.7823 | 44610.13 | 188748.75 | 14556.826 | 11591.26 | 14556.826 | 17325.73 | 14556.826 | 2212.82 | 14556.826 | 650.04 | 14556.826 | 9155.95 | 14556.826 | 635.67 | 14556.826 | 3038.66
2026-02-02 | 102361.8495 | 45310.13 | 189828.5 | 14623.1214 | 11591.26 | 14623.1214 | 17325.73 | 14623.1214 | 2212.82 | 14623.1214 | 650.04 | 14623.1214 | 9855.95 | 14623.1214 | 635.67 | 14623.1214 | 3038.66
2026-02-03 | 102825.9168 | 46790.95 | 190908.25 | 14689.4167 | 11591.26 | 14689.4167 | 18806.55 | 14689.4167 | 2212.82 | 14689.4167 | 650.04 | 14689.4167 | 9855.95 | 14689.4167 | 635.67 | 14689.4167 | 3038.66
2026-02-04 | 103289.9841 | 46790.95 | 191988 | 14755.712 | 11591.26 | 14755.712 | 18806.55 | 14755.712 | 2212.82 | 14755.712 | 650.04 | 14755.712 | 9855.95 | 14755.712 | 635.67 | 14755.712 | 3038.66
2026-02-05 | 103754.0514 | 47916.65 | 193067.75 | 14822.0073 | 11591.26 | 14822.0073 | 19859.67 | 14822.0073 | 2285.4 | 14822.0073 | 650.04 | 14822.0073 | 9855.95 | 14822.0073 | 635.67 | 14822.0073 | 3038.66
2026-02-06 | 104218.1187 | 48778.29 | 194147.5 | 14888.3027 | 11591.26 | 14888.3027 | 20021.31 | 14888.3027 | 2285.4 | 14888.3027 | 650.04 | 14888.3027 | 10555.95 | 14888.3027 | 635.67 | 14888.3027 | 3038.66
2026-02-07 | 104682.1859 | 48778.29 | 194147.5 | 14954.598 | 11591.26 | 14954.598 | 20021.31 | 14954.598 | 2285.4 | 14954.598 | 650.04 | 14954.598 | 10555.95 | 14954.598 | 635.67 | 14954.598 | 3038.66
2026-02-08 | 105146.2532 | 48778.29 | 194147.5 | 15020.8933 | 11591.26 | 15020.8933 | 20021.31 | 15020.8933 | 2285.4 | 15020.8933 | 650.04 | 15020.8933 | 10555.95 | 15020.8933 | 635.67 | 15020.8933 | 3038.66
2026-02-09 | 105610.3205 | 48778.29 | 195428.55 | 15087.1886 | 11591.26 | 15087.1886 | 20021.31 | 15087.1886 | 2285.4 | 15087.1886 | 650.04 | 15087.1886 | 10555.95 | 15087.1886 | 635.67 | 15087.1886 | 3038.66
2026-02-10 | 106074.3878 | 50109.47 | 196709.6 | 15153.484 | 11591.26 | 15153.484 | 21352.49 | 15153.484 | 2285.4 | 15153.484 | 650.04 | 15153.484 | 10555.95 | 15153.484 | 635.67 | 15153.484 | 3038.66
2026-02-11 | 106538.455 | 51173.11 | 197990.65 | 15219.7793 | 11591.26 | 15219.7793 | 22416.13 | 15219.7793 | 2285.4 | 15219.7793 | 650.04 | 15219.7793 | 10555.95 | 15219.7793 | 635.67 | 15219.7793 | 3038.66
2026-02-12 | 107002.5223 | 51873.11 | 199271.7 | 15286.0746 | 11591.26 | 15286.0746 | 22416.13 | 15286.0746 | 2285.4 | 15286.0746 | 650.04 | 15286.0746 | 11255.95 | 15286.0746 | 635.67 | 15286.0746 | 3038.66
2026-02-13 | 107466.5896 | 51873.11 | 200552.75 | 15352.3699 | 11591.26 | 15352.3699 | 22416.13 | 15352.3699 | 2285.4 | 15352.3699 | 650.04 | 15352.3699 | 11255.95 | 15352.3699 | 635.67 | 15352.3699 | 3038.66
2026-02-14 | 107930.6569 | 51873.11 | 200552.75 | 15418.6653 | 11591.26 | 15418.6653 | 22416.13 | 15418.6653 | 2285.4 | 15418.6653 | 650.04 | 15418.6653 | 11255.95 | 15418.6653 | 635.67 | 15418.6653 | 3038.66
2026-02-15 | 108394.7242 | 51873.11 | 200552.75 | 15484.9606 | 11591.26 | 15484.9606 | 22416.13 | 15484.9606 | 2285.4 | 15484.9606 | 650.04 | 15484.9606 | 11255.95 | 15484.9606 | 635.67 | 15484.9606 | 3038.66
2026-02-16 | 108858.7914 | 51873.11 | 201679.45 | 15551.2559 | 11591.26 | 15551.2559 | 22416.13 | 15551.2559 | 2285.4 | 15551.2559 | 650.04 | 15551.2559 | 11255.95 | 15551.2559 | 635.67 | 15551.2559 | 3038.66
2026-02-17 | 109322.8587 | 51873.11 | 202806.15 | 15617.5512 | 11591.26 | 15617.5512 | 22416.13 | 15617.5512 | 2285.4 | 15617.5512 | 650.04 | 15617.5512 | 11255.95 | 15617.5512 | 635.67 | 15617.5512 | 3038.66
2026-02-18 | 109786.926 | 51873.11 | 203932.85 | 15683.8466 | 11591.26 | 15683.8466 | 22416.13 | 15683.8466 | 2285.4 | 15683.8466 | 650.04 | 15683.8466 | 11255.95 | 15683.8466 | 635.67 | 15683.8466 | 3038.66
2026-02-19 | 110250.9933 | 51873.11 | 205059.55 | 15750.1419 | 11591.26 | 15750.1419 | 22416.13 | 15750.1419 | 2285.4 | 15750.1419 | 650.04 | 15750.1419 | 11255.95 | 15750.1419 | 635.67 | 15750.1419 | 3038.66
2026-02-20 | 110715.0606 | 54663.47 | 206186.25 | 15816.4372 | 11591.26 | 15816.4372 | 24506.49 | 15816.4372 | 2285.4 | 15816.4372 | 650.04 | 15816.4372 | 11955.95 | 15816.4372 | 635.67 | 15816.4372 | 3038.66
2026-02-21 | 111179.1278 | 54663.47 | 206186.25 | 15882.7325 | 11591.26 | 15882.7325 | 24506.49 | 15882.7325 | 2285.4 | 15882.7325 | 650.04 | 15882.7325 | 11955.95 | 15882.7325 | 635.67 | 15882.7325 | 3038.66
2026-02-22 | 111643.1951 | 54663.47 | 206186.25 | 15949.0279 | 11591.26 | 15949.0279 | 24506.49 | 15949.0279 | 2285.4 | 15949.0279 | 650.04 | 15949.0279 | 11955.95 | 15949.0279 | 635.67 | 15949.0279 | 3038.66
2026-02-23 | 112107.2624 | 54663.47 | 207266 | 16015.3232 | 11591.26 | 16015.3232 | 24506.49 | 16015.3232 | 2285.4 | 16015.3232 | 650.04 | 16015.3232 | 11955.95 | 16015.3232 | 635.67 | 16015.3232 | 3038.66
2026-02-24 | 112571.3297 | 54663.47 | 208345.75 | 16081.6185 | 11591.26 | 16081.6185 | 24506.49 | 16081.6185 | 2285.4 | 16081.6185 | 650.04 | 16081.6185 | 11955.95 | 16081.6185 | 635.67 | 16081.6185 | 3038.66
2026-02-25 | 113035.3969 | 54663.47 | 209425.5 | 16147.9138 | 11591.26 | 16147.9138 | 24506.49 | 16147.9138 | 2285.4 | 16147.9138 | 650.04 | 16147.9138 | 11955.95 | 16147.9138 | 635.67 | 16147.9138 | 3038.66
2026-02-26 | 113499.4642 | 54663.47 | 210505.25 | 16214.2092 | 11591.26 | 16214.2092 | 24506.49 | 16214.2092 | 2285.4 | 16214.2092 | 650.04 | 16214.2092 | 11955.95 | 16214.2092 | 635.67 | 16214.2092 | 3038.66
2026-02-27 | 113963.5315 | 55191.07 | 211585 | 16280.5045 | 12118.86 | 16280.5045 | 24506.49 | 16280.5045 | 2285.4 | 16280.5045 | 650.04 | 16280.5045 | 11955.95 | 16280.5045 | 635.67 | 16280.5045 | 3038.66
2026-02-28 | 114427.5988 | 56927.55 | 211585 | 16346.7998 | 12118.86 | 16346.7998 | 26242.97 | 16346.7998 | 2285.4 | 16346.7998 | 650.04 | 16346.7998 | 11955.95 | 16346.7998 | 635.67 | 16346.7998 | 3038.66
2026-03-01 | 114891.6661 | 56927.55 | 211585 | 16413.0952 | 12118.86 | 16413.0952 | 26242.97 | 16413.0952 | 2285.4 | 16413.0952 | 650.04 | 16413.0952 | 11955.95 | 16413.0952 | 635.67 | 16413.0952 | 3038.66
2026-03-02 | 115355.7333 | 56927.55 | 211980.75 | 16479.3905 | 12118.86 | 16479.3905 | 26242.97 | 16479.3905 | 2285.4 | 16479.3905 | 650.04 | 16479.3905 | 11955.95 | 16479.3905 | 635.67 | 16479.3905 | 3038.66
2026-03-03 | 115584.0541 | 56927.55 | 212376.5 | 16512.0077 | 12118.86 | 16512.0077 | 26242.97 | 16512.0077 | 2285.4 | 16512.0077 | 650.04 | 16512.0077 | 11955.95 | 16512.0077 | 635.67 | 16512.0077 | 3038.66
2026-03-04 | 115812.3749 | 57021.06 | 212772.25 | 16544.625 | 12118.86 | 16544.625 | 26242.97 | 16544.625 | 2285.4 | 16544.625 | 743.55 | 16544.625 | 11955.95 | 16544.625 | 635.67 | 16544.625 | 3038.66
2026-03-05 | 116040.6957 | 57021.06 | 213168 | 16577.2422 | 12118.86 | 16577.2422 | 26242.97 | 16577.2422 | 2285.4 | 16577.2422 | 743.55 | 16577.2422 | 11955.95 | 16577.2422 | 635.67 | 16577.2422 | 3038.66
2026-03-06 | 116269.0165 | 57021.06 | 213563.75 | 16609.8595 | 12118.86 | 16609.8595 | 26242.97 | 16609.8595 | 2285.4 | 16609.8595 | 743.55 | 16609.8595 | 11955.95 | 16609.8595 | 635.67 | 16609.8595 | 3038.66
2026-03-07 | 116497.3373 | 57021.06 | 213563.75 | 16642.4768 | 12118.86 | 16642.4768 | 26242.97 | 16642.4768 | 2285.4 | 16642.4768 | 743.55 | 16642.4768 | 11955.95 | 16642.4768 | 635.67 | 16642.4768 | 3038.66
2026-03-08 | 116725.6581 | 57021.06 | 213563.75 | 16675.094 | 12118.86 | 16675.094 | 26242.97 | 16675.094 | 2285.4 | 16675.094 | 743.55 | 16675.094 | 11955.95 | 16675.094 | 635.67 | 16675.094 | 3038.66
2026-03-09 | 116953.9789 | 57021.06 | 213761.625 | 16707.7113 | 12118.86 | 16707.7113 | 26242.97 | 16707.7113 | 2285.4 | 16707.7113 | 743.55 | 16707.7113 | 11955.95 | 16707.7113 | 635.67 | 16707.7113 | 3038.66
2026-03-10 | 117182.2997 | 57021.06 | 213959.5 | 16740.3285 | 12118.86 | 16740.3285 | 26242.97 | 16740.3285 | 2285.4 | 16740.3285 | 743.55 | 16740.3285 | 11955.95 | 16740.3285 | 635.67 | 16740.3285 | 3038.66
2026-03-11 | 117410.6206 | 57021.06 | 214157.375 | 16772.9458 | 12118.86 | 16772.9458 | 26242.97 | 16772.9458 | 2285.4 | 16772.9458 | 743.55 | 16772.9458 | 11955.95 | 16772.9458 | 635.67 | 16772.9458 | 3038.66
2026-03-12 | 117638.9414 | 57021.06 | 214355.25 | 16805.5631 | 12118.86 | 16805.5631 | 26242.97 | 16805.5631 | 2285.4 | 16805.5631 | 743.55 | 16805.5631 | 11955.95 | 16805.5631 | 635.67 | 16805.5631 | 3038.66
2026-03-13 | 117867.2622 | 57021.06 | 214553.125 | 16838.1803 | 12118.86 | 16838.1803 | 26242.97 | 16838.1803 | 2285.4 | 16838.1803 | 743.55 | 16838.1803 | 11955.95 | 16838.1803 | 635.67 | 16838.1803 | 3038.66
2026-03-14 | 118095.583 | 57021.06 | 214553.125 | 16870.7976 | 12118.86 | 16870.7976 | 26242.97 | 16870.7976 | 2285.4 | 16870.7976 | 743.55 | 16870.7976 | 11955.95 | 16870.7976 | 635.67 | 16870.7976 | 3038.66
2026-03-15 | 118323.9038 | 57021.06 | 214553.125 | 16903.4148 | 12118.86 | 16903.4148 | 26242.97 | 16903.4148 | 2285.4 | 16903.4148 | 743.55 | 16903.4148 | 11955.95 | 16903.4148 | 635.67 | 16903.4148 | 3038.66
2026-03-16 | 118552.2246 | 57021.06 | 215408.95 | 16936.0321 | 12118.86 | 16936.0321 | 26242.97 | 16936.0321 | 2285.4 | 16936.0321 | 743.55 | 16936.0321 | 11955.95 | 16936.0321 | 635.67 | 16936.0321 | 3038.66
2026-03-17 | 118780.5454 | 57021.06 | 216264.775 | 16968.6493 | 12118.86 | 16968.6493 | 26242.97 | 16968.6493 | 2285.4 | 16968.6493 | 743.55 | 16968.6493 | 11955.95 | 16968.6493 | 635.67 | 16968.6493 | 3038.66
2026-03-18 | 119008.8662 | 57021.06 | 217120.6 | 17001.2666 | 12118.86 | 17001.2666 | 26242.97 | 17001.2666 | 2285.4 | 17001.2666 | 743.55 | 17001.2666 | 11955.95 | 17001.2666 | 635.67 | 17001.2666 | 3038.66
2026-03-19 | 119237.187 | 57021.06 | 217976.425 | 17033.8839 | 12118.86 | 17033.8839 | 26242.97 | 17033.8839 | 2285.4 | 17033.8839 | 743.55 | 17033.8839 | 11955.95 | 17033.8839 | 635.67 | 17033.8839 | 3038.66
2026-03-20 | 119465.5078 | 57021.06 | 218832.25 | 17066.5011 | 12118.86 | 17066.5011 | 26242.97 | 17066.5011 | 2285.4 | 17066.5011 | 743.55 | 17066.5011 | 11955.95 | 17066.5011 | 635.67 | 17066.5011 | 3038.66
2026-03-21 | 119693.8286 | 57021.06 | 218832.25 | 17099.1184 | 12118.86 | 17099.1184 | 26242.97 | 17099.1184 | 2285.4 | 17099.1184 | 743.55 | 17099.1184 | 11955.95 | 17099.1184 | 635.67 | 17099.1184 | 3038.66
2026-03-22 | 119922.1494 | 57021.06 | 218832.25 | 17131.7356 | 12118.86 | 17131.7356 | 26242.97 | 17131.7356 | 2285.4 | 17131.7356 | 743.55 | 17131.7356 | 11955.95 | 17131.7356 | 635.67 | 17131.7356 | 3038.66
2026-03-23 | 120150.4702 |  |  | 17164.3529 |  | 17164.3529 |  | 17164.3529 |  | 17164.3529 |  | 17164.3529 |  | 17164.3529 |  | 17164.3529
2026-03-24 | 120378.791 |  |  | 17196.9701 |  | 17196.9701 |  | 17196.9701 |  | 17196.9701 |  | 17196.9701 |  | 17196.9701 |  | 17196.9701
2026-03-25 | 120607.1118 |  |  | 17229.5874 |  | 17229.5874 |  | 17229.5874 |  | 17229.5874 |  | 17229.5874 |  | 17229.5874 |  | 17229.5874
2026-03-26 | 120835.4326 |  |  | 17262.2047 |  | 17262.2047 |  | 17262.2047 |  | 17262.2047 |  | 17262.2047 |  | 17262.2047 |  | 17262.2047
2026-03-27 | 121063.7534 |  |  | 17294.8219 |  | 17294.8219 |  | 17294.8219 |  | 17294.8219 |  | 17294.8219 |  | 17294.8219 |  | 17294.8219
2026-03-28 | 121292.0742 |  |  | 17327.4392 |  | 17327.4392 |  | 17327.4392 |  | 17327.4392 |  | 17327.4392 |  | 17327.4392 |  | 17327.4392
2026-03-29 | 121520.395 |  |  | 17360.0564 |  | 17360.0564 |  | 17360.0564 |  | 17360.0564 |  | 17360.0564 |  | 17360.0564 |  | 17360.0564
2026-03-30 | 121748.7158 |  |  | 17392.6737 |  | 17392.6737 |  | 17392.6737 |  | 17392.6737 |  | 17392.6737 |  | 17392.6737 |  | 17392.6737
2026-03-31 | 121977.0366 |  |  | 17425.2909 |  | 17425.2909 |  | 17425.2909 |  | 17425.2909 |  | 17425.2909 |  | 17425.2909 |  | 17425.2909
2026-04-01 | 122205.3574 |  |  | 17457.9082 |  | 17457.9082 |  | 17457.9082 |  | 17457.9082 |  | 17457.9082 |  | 17457.9082 |  | 17457.9082
2026-04-02 | 122433.6782 |  |  | 17490.5255 |  | 17490.5255 |  | 17490.5255 |  | 17490.5255 |  | 17490.5255 |  | 17490.5255 |  | 17490.5255
2026-04-03 | 122661.999 |  |  | 17523.1427 |  | 17523.1427 |  | 17523.1427 |  | 17523.1427 |  | 17523.1427 |  | 17523.1427 |  | 17523.1427
2026-04-04 | 122890.3198 |  |  | 17555.76 |  | 17555.76 |  | 17555.76 |  | 17555.76 |  | 17555.76 |  | 17555.76 |  | 17555.76
2026-04-05 | 123118.6406 |  |  | 17588.3772 |  | 17588.3772 |  | 17588.3772 |  | 17588.3772 |  | 17588.3772 |  | 17588.3772 |  | 17588.3772
2026-04-06 | 123346.9614 |  |  | 17620.9945 |  | 17620.9945 |  | 17620.9945 |  | 17620.9945 |  | 17620.9945 |  | 17620.9945 |  | 17620.9945
2026-04-07 | 123575.2822 |  |  | 17653.6117 |  | 17653.6117 |  | 17653.6117 |  | 17653.6117 |  | 17653.6117 |  | 17653.6117 |  | 17653.6117
2026-04-08 | 123803.603 |  |  | 17686.229 |  | 17686.229 |  | 17686.229 |  | 17686.229 |  | 17686.229 |  | 17686.229 |  | 17686.229
2026-04-09 | 124031.9238 |  |  | 17718.8463 |  | 17718.8463 |  | 17718.8463 |  | 17718.8463 |  | 17718.8463 |  | 17718.8463 |  | 17718.8463
2026-04-10 | 124260.2446 |  |  | 17751.4635 |  | 17751.4635 |  | 17751.4635 |  | 17751.4635 |  | 17751.4635 |  | 17751.4635 |  | 17751.4635
2026-04-11 | 124488.5654 |  |  | 17784.0808 |  | 17784.0808 |  | 17784.0808 |  | 17784.0808 |  | 17784.0808 |  | 17784.0808 |  | 17784.0808
2026-04-12 | 124716.8862 |  |  | 17816.698 |  | 17816.698 |  | 17816.698 |  | 17816.698 |  | 17816.698 |  | 17816.698 |  | 17816.698
2026-04-13 | 124945.207 |  |  | 17849.3153 |  | 17849.3153 |  | 17849.3153 |  | 17849.3153 |  | 17849.3153 |  | 17849.3153 |  | 17849.3153
2026-04-14 | 125173.5278 |  |  | 17881.9325 |  | 17881.9325 |  | 17881.9325 |  | 17881.9325 |  | 17881.9325 |  | 17881.9325 |  | 17881.9325
2026-04-15 | 125401.8486 |  |  | 17914.5498 |  | 17914.5498 |  | 17914.5498 |  | 17914.5498 |  | 17914.5498 |  | 17914.5498 |  | 17914.5498
2026-04-16 | 125630.1694 |  |  | 17947.1671 |  | 17947.1671 |  | 17947.1671 |  | 17947.1671 |  | 17947.1671 |  | 17947.1671 |  | 17947.1671
2026-04-17 | 125858.4902 |  |  | 17979.7843 |  | 17979.7843 |  | 17979.7843 |  | 17979.7843 |  | 17979.7843 |  | 17979.7843 |  | 17979.7843
2026-04-18 | 126086.811 |  |  | 18012.4016 |  | 18012.4016 |  | 18012.4016 |  | 18012.4016 |  | 18012.4016 |  | 18012.4016 |  | 18012.4016
2026-04-19 | 126315.1318 |  |  | 18045.0188 |  | 18045.0188 |  | 18045.0188 |  | 18045.0188 |  | 18045.0188 |  | 18045.0188 |  | 18045.0188
2026-04-20 | 126543.4526 |  |  | 18077.6361 |  | 18077.6361 |  | 18077.6361 |  | 18077.6361 |  | 18077.6361 |  | 18077.6361 |  | 18077.6361
2026-04-21 | 126771.7734 |  |  | 18110.2533 |  | 18110.2533 |  | 18110.2533 |  | 18110.2533 |  | 18110.2533 |  | 18110.2533 |  | 18110.2533
2026-04-22 | 127000.0942 |  |  | 18142.8706 |  | 18142.8706 |  | 18142.8706 |  | 18142.8706 |  | 18142.8706 |  | 18142.8706 |  | 18142.8706
2026-04-23 | 127228.415 |  |  | 18175.4879 |  | 18175.4879 |  | 18175.4879 |  | 18175.4879 |  | 18175.4879 |  | 18175.4879 |  | 18175.4879
2026-04-24 | 127456.7358 |  |  | 18208.1051 |  | 18208.1051 |  | 18208.1051 |  | 18208.1051 |  | 18208.1051 |  | 18208.1051 |  | 18208.1051
2026-04-25 | 127685.0566 |  |  | 18240.7224 |  | 18240.7224 |  | 18240.7224 |  | 18240.7224 |  | 18240.7224 |  | 18240.7224 |  | 18240.7224
2026-04-26 | 127913.3774 |  |  | 18273.3396 |  | 18273.3396 |  | 18273.3396 |  | 18273.3396 |  | 18273.3396 |  | 18273.3396 |  | 18273.3396
2026-04-27 | 128141.6982 |  |  | 18305.9569 |  | 18305.9569 |  | 18305.9569 |  | 18305.9569 |  | 18305.9569 |  | 18305.9569 |  | 18305.9569
2026-04-28 | 128370.019 |  |  | 18338.5741 |  | 18338.5741 |  | 18338.5741 |  | 18338.5741 |  | 18338.5741 |  | 18338.5741 |  | 18338.5741
2026-04-29 | 128598.3398 |  |  | 18371.1914 |  | 18371.1914 |  | 18371.1914 |  | 18371.1914 |  | 18371.1914 |  | 18371.1914 |  | 18371.1914
2026-04-30 | 128826.6607 |  |  | 18403.8087 |  | 18403.8087 |  | 18403.8087 |  | 18403.8087 |  | 18403.8087 |  | 18403.8087 |  | 18403.8087
2026-05-01 | 129054.9815 |  |  | 18436.4259 |  | 18436.4259 |  | 18436.4259 |  | 18436.4259 |  | 18436.4259 |  | 18436.4259 |  | 18436.4259
2026-05-02 | 129283.3023 |  |  | 18469.0432 |  | 18469.0432 |  | 18469.0432 |  | 18469.0432 |  | 18469.0432 |  | 18469.0432 |  | 18469.0432
2026-05-03 | 129511.6231 |  |  | 18501.6604 |  | 18501.6604 |  | 18501.6604 |  | 18501.6604 |  | 18501.6604 |  | 18501.6604 |  | 18501.6604
2026-05-04 | 129739.9439 |  |  | 18534.2777 |  | 18534.2777 |  | 18534.2777 |  | 18534.2777 |  | 18534.2777 |  | 18534.2777 |  | 18534.2777
2026-05-05 | 129968.2647 |  |  | 18566.895 |  | 18566.895 |  | 18566.895 |  | 18566.895 |  | 18566.895 |  | 18566.895 |  | 18566.895
2026-05-06 | 130196.5855 |  |  | 18599.5122 |  | 18599.5122 |  | 18599.5122 |  | 18599.5122 |  | 18599.5122 |  | 18599.5122 |  | 18599.5122
2026-05-07 | 130424.9063 |  |  | 18632.1295 |  | 18632.1295 |  | 18632.1295 |  | 18632.1295 |  | 18632.1295 |  | 18632.1295 |  | 18632.1295
2026-05-08 | 130653.2271 |  |  | 18664.7467 |  | 18664.7467 |  | 18664.7467 |  | 18664.7467 |  | 18664.7467 |  | 18664.7467 |  | 18664.7467
2026-05-09 | 130881.5479 |  |  | 18697.364 |  | 18697.364 |  | 18697.364 |  | 18697.364 |  | 18697.364 |  | 18697.364 |  | 18697.364
2026-05-10 | 131109.8687 |  |  | 18729.9812 |  | 18729.9812 |  | 18729.9812 |  | 18729.9812 |  | 18729.9812 |  | 18729.9812 |  | 18729.9812
2026-05-11 | 131338.1895 |  |  | 18762.5985 |  | 18762.5985 |  | 18762.5985 |  | 18762.5985 |  | 18762.5985 |  | 18762.5985 |  | 18762.5985
2026-05-12 | 131566.5103 |  |  | 18795.2158 |  | 18795.2158 |  | 18795.2158 |  | 18795.2158 |  | 18795.2158 |  | 18795.2158 |  | 18795.2158
2026-05-13 | 131794.8311 |  |  | 18827.833 |  | 18827.833 |  | 18827.833 |  | 18827.833 |  | 18827.833 |  | 18827.833 |  | 18827.833
2026-05-14 | 132023.1519 |  |  | 18860.4503 |  | 18860.4503 |  | 18860.4503 |  | 18860.4503 |  | 18860.4503 |  | 18860.4503 |  | 18860.4503
2026-05-15 | 132251.4727 |  |  | 18893.0675 |  | 18893.0675 |  | 18893.0675 |  | 18893.0675 |  | 18893.0675 |  | 18893.0675 |  | 18893.0675
2026-05-16 | 132479.7935 |  |  | 18925.6848 |  | 18925.6848 |  | 18925.6848 |  | 18925.6848 |  | 18925.6848 |  | 18925.6848 |  | 18925.6848
2026-05-17 | 132708.1143 |  |  | 18958.302 |  | 18958.302 |  | 18958.302 |  | 18958.302 |  | 18958.302 |  | 18958.302 |  | 18958.302
2026-05-18 | 132936.4351 |  |  | 18990.9193 |  | 18990.9193 |  | 18990.9193 |  | 18990.9193 |  | 18990.9193 |  | 18990.9193 |  | 18990.9193
2026-05-19 | 133164.7559 |  |  | 19023.5366 |  | 19023.5366 |  | 19023.5366 |  | 19023.5366 |  | 19023.5366 |  | 19023.5366 |  | 19023.5366
2026-05-20 | 133393.0767 |  |  | 19056.1538 |  | 19056.1538 |  | 19056.1538 |  | 19056.1538 |  | 19056.1538 |  | 19056.1538 |  | 19056.1538
2026-05-21 | 133621.3975 |  |  | 19088.7711 |  | 19088.7711 |  | 19088.7711 |  | 19088.7711 |  | 19088.7711 |  | 19088.7711 |  | 19088.7711
2026-05-22 | 133849.7183 |  |  | 19121.3883 |  | 19121.3883 |  | 19121.3883 |  | 19121.3883 |  | 19121.3883 |  | 19121.3883 |  | 19121.3883
2026-05-23 | 134078.0391 |  |  | 19154.0056 |  | 19154.0056 |  | 19154.0056 |  | 19154.0056 |  | 19154.0056 |  | 19154.0056 |  | 19154.0056
2026-05-24 | 134306.3599 |  |  | 19186.6228 |  | 19186.6228 |  | 19186.6228 |  | 19186.6228 |  | 19186.6228 |  | 19186.6228 |  | 19186.6228
2026-05-25 | 134534.6807 |  |  | 19219.2401 |  | 19219.2401 |  | 19219.2401 |  | 19219.2401 |  | 19219.2401 |  | 19219.2401 |  | 19219.2401
2026-05-26 | 134763.0015 |  |  | 19251.8574 |  | 19251.8574 |  | 19251.8574 |  | 19251.8574 |  | 19251.8574 |  | 19251.8574 |  | 19251.8574
2026-05-27 | 134991.3223 |  |  | 19284.4746 |  | 19284.4746 |  | 19284.4746 |  | 19284.4746 |  | 19284.4746 |  | 19284.4746 |  | 19284.4746
2026-05-28 | 135219.6431 |  |  | 19317.0919 |  | 19317.0919 |  | 19317.0919 |  | 19317.0919 |  | 19317.0919 |  | 19317.0919 |  | 19317.0919
2026-05-29 | 135447.9639 |  |  | 19349.7091 |  | 19349.7091 |  | 19349.7091 |  | 19349.7091 |  | 19349.7091 |  | 19349.7091 |  | 19349.7091
2026-05-30 | 135676.2847 |  |  | 19382.3264 |  | 19382.3264 |  | 19382.3264 |  | 19382.3264 |  | 19382.3264 |  | 19382.3264 |  | 19382.3264
2026-05-31 | 135904.6055 |  |  | 19414.9436 |  | 19414.9436 |  | 19414.9436 |  | 19414.9436 |  | 19414.9436 |  | 19414.9436 |  | 19414.9436
2026-06-01 | 136132.9263 |  |  | 19447.5609 |  | 19447.5609 |  | 19447.5609 |  | 19447.5609 |  | 19447.5609 |  | 19447.5609 |  | 19447.5609
2026-06-02 | 136361.2471 |  |  | 19480.1782 |  | 19480.1782 |  | 19480.1782 |  | 19480.1782 |  | 19480.1782 |  | 19480.1782 |  | 19480.1782
2026-06-03 | 136589.5679 |  |  | 19512.7954 |  | 19512.7954 |  | 19512.7954 |  | 19512.7954 |  | 19512.7954 |  | 19512.7954 |  | 19512.7954
2026-06-04 | 136817.8887 |  |  | 19545.4127 |  | 19545.4127 |  | 19545.4127 |  | 19545.4127 |  | 19545.4127 |  | 19545.4127 |  | 19545.4127
2026-06-05 | 137046.2095 |  |  | 19578.0299 |  | 19578.0299 |  | 19578.0299 |  | 19578.0299 |  | 19578.0299 |  | 19578.0299 |  | 19578.0299
2026-06-06 | 137274.5303 |  |  | 19610.6472 |  | 19610.6472 |  | 19610.6472 |  | 19610.6472 |  | 19610.6472 |  | 19610.6472 |  | 19610.6472
2026-06-07 | 137502.8511 |  |  | 19643.2644 |  | 19643.2644 |  | 19643.2644 |  | 19643.2644 |  | 19643.2644 |  | 19643.2644 |  | 19643.2644
2026-06-08 | 137731.1719 |  |  | 19675.8817 |  | 19675.8817 |  | 19675.8817 |  | 19675.8817 |  | 19675.8817 |  | 19675.8817 |  | 19675.8817
2026-06-09 | 137959.4927 |  |  | 19708.499 |  | 19708.499 |  | 19708.499 |  | 19708.499 |  | 19708.499 |  | 19708.499 |  | 19708.499
2026-06-10 | 138187.8135 |  |  | 19741.1162 |  | 19741.1162 |  | 19741.1162 |  | 19741.1162 |  | 19741.1162 |  | 19741.1162 |  | 19741.1162
2026-06-11 | 138416.1343 |  |  | 19773.7335 |  | 19773.7335 |  | 19773.7335 |  | 19773.7335 |  | 19773.7335 |  | 19773.7335 |  | 19773.7335
2026-06-12 | 138644.4551 |  |  | 19806.3507 |  | 19806.3507 |  | 19806.3507 |  | 19806.3507 |  | 19806.3507 |  | 19806.3507 |  | 19806.3507
2026-06-13 | 138872.7759 |  |  | 19838.968 |  | 19838.968 |  | 19838.968 |  | 19838.968 |  | 19838.968 |  | 19838.968 |  | 19838.968
2026-06-14 | 139101.0967 |  |  | 19871.5852 |  | 19871.5852 |  | 19871.5852 |  | 19871.5852 |  | 19871.5852 |  | 19871.5852 |  | 19871.5852
2026-06-15 | 139329.4175 |  |  | 19904.2025 |  | 19904.2025 |  | 19904.2025 |  | 19904.2025 |  | 19904.2025 |  | 19904.2025 |  | 19904.2025
2026-06-16 | 139557.7383 |  |  | 19936.8198 |  | 19936.8198 |  | 19936.8198 |  | 19936.8198 |  | 19936.8198 |  | 19936.8198 |  | 19936.8198
2026-06-17 | 139786.0591 |  |  | 19969.437 |  | 19969.437 |  | 19969.437 |  | 19969.437 |  | 19969.437 |  | 19969.437 |  | 19969.437
2026-06-18 | 140014.3799 |  |  | 20002.0543 |  | 20002.0543 |  | 20002.0543 |  | 20002.0543 |  | 20002.0543 |  | 20002.0543 |  | 20002.0543
2026-06-19 | 140242.7008 |  |  | 20034.6715 |  | 20034.6715 |  | 20034.6715 |  | 20034.6715 |  | 20034.6715 |  | 20034.6715 |  | 20034.6715
2026-06-20 | 140471.0216 |  |  | 20067.2888 |  | 20067.2888 |  | 20067.2888 |  | 20067.2888 |  | 20067.2888 |  | 20067.2888 |  | 20067.2888
2026-06-21 | 140699.3424 |  |  | 20099.9061 |  | 20099.9061 |  | 20099.9061 |  | 20099.9061 |  | 20099.9061 |  | 20099.9061 |  | 20099.9061
2026-06-22 | 140927.6632 |  |  | 20132.5233 |  | 20132.5233 |  | 20132.5233 |  | 20132.5233 |  | 20132.5233 |  | 20132.5233 |  | 20132.5233
2026-06-23 | 141155.984 |  |  | 20165.1406 |  | 20165.1406 |  | 20165.1406 |  | 20165.1406 |  | 20165.1406 |  | 20165.1406 |  | 20165.1406
2026-06-24 | 141384.3048 |  |  | 20197.7578 |  | 20197.7578 |  | 20197.7578 |  | 20197.7578 |  | 20197.7578 |  | 20197.7578 |  | 20197.7578
2026-06-25 | 141612.6256 |  |  | 20230.3751 |  | 20230.3751 |  | 20230.3751 |  | 20230.3751 |  | 20230.3751 |  | 20230.3751 |  | 20230.3751
2026-06-26 | 141840.9464 |  |  | 20262.9923 |  | 20262.9923 |  | 20262.9923 |  | 20262.9923 |  | 20262.9923 |  | 20262.9923 |  | 20262.9923
2026-06-27 | 142069.2672 |  |  | 20295.6096 |  | 20295.6096 |  | 20295.6096 |  | 20295.6096 |  | 20295.6096 |  | 20295.6096 |  | 20295.6096
2026-06-28 | 142297.588 |  |  | 20328.2269 |  | 20328.2269 |  | 20328.2269 |  | 20328.2269 |  | 20328.2269 |  | 20328.2269 |  | 20328.2269
2026-06-29 | 142525.9088 |  |  | 20360.8441 |  | 20360.8441 |  | 20360.8441 |  | 20360.8441 |  | 20360.8441 |  | 20360.8441 |  | 20360.8441
2026-06-30 | 142754.2296 |  |  | 20393.4614 |  | 20393.4614 |  | 20393.4614 |  | 20393.4614 |  | 20393.4614 |  | 20393.4614 |  | 20393.4614
2026-07-01 | 142982.5504 |  |  | 20426.0786 |  | 20426.0786 |  | 20426.0786 |  | 20426.0786 |  | 20426.0786 |  | 20426.0786 |  | 20426.0786
2026-07-02 | 143210.8712 |  |  | 20458.6959 |  | 20458.6959 |  | 20458.6959 |  | 20458.6959 |  | 20458.6959 |  | 20458.6959 |  | 20458.6959
2026-07-03 | 143439.192 |  |  | 20491.3131 |  | 20491.3131 |  | 20491.3131 |  | 20491.3131 |  | 20491.3131 |  | 20491.3131 |  | 20491.3131
2026-07-04 | 143667.5128 |  |  | 20523.9304 |  | 20523.9304 |  | 20523.9304 |  | 20523.9304 |  | 20523.9304 |  | 20523.9304 |  | 20523.9304
2026-07-05 | 143895.8336 |  |  | 20556.5477 |  | 20556.5477 |  | 20556.5477 |  | 20556.5477 |  | 20556.5477 |  | 20556.5477 |  | 20556.5477
2026-07-06 | 144124.1544 |  |  | 20589.1649 |  | 20589.1649 |  | 20589.1649 |  | 20589.1649 |  | 20589.1649 |  | 20589.1649 |  | 20589.1649
2026-07-07 | 144352.4752 |  |  | 20621.7822 |  | 20621.7822 |  | 20621.7822 |  | 20621.7822 |  | 20621.7822 |  | 20621.7822 |  | 20621.7822
2026-07-08 | 144580.796 |  |  | 20654.3994 |  | 20654.3994 |  | 20654.3994 |  | 20654.3994 |  | 20654.3994 |  | 20654.3994 |  | 20654.3994
2026-07-09 | 144809.1168 |  |  | 20687.0167 |  | 20687.0167 |  | 20687.0167 |  | 20687.0167 |  | 20687.0167 |  | 20687.0167 |  | 20687.0167
2026-07-10 | 145037.4376 |  |  | 20719.6339 |  | 20719.6339 |  | 20719.6339 |  | 20719.6339 |  | 20719.6339 |  | 20719.6339 |  | 20719.6339
2026-07-11 | 145265.7584 |  |  | 20752.2512 |  | 20752.2512 |  | 20752.2512 |  | 20752.2512 |  | 20752.2512 |  | 20752.2512 |  | 20752.2512
2026-07-12 | 145494.0792 |  |  | 20784.8685 |  | 20784.8685 |  | 20784.8685 |  | 20784.8685 |  | 20784.8685 |  | 20784.8685 |  | 20784.8685
2026-07-13 | 145722.4 |  |  | 20817.4857 |  | 20817.4857 |  | 20817.4857 |  | 20817.4857 |  | 20817.4857 |  | 20817.4857 |  | 20817.4857
2026-07-14 | 145950.7208 |  |  | 20850.103 |  | 20850.103 |  | 20850.103 |  | 20850.103 |  | 20850.103 |  | 20850.103 |  | 20850.103
2026-07-15 | 146179.0416 |  |  | 20882.7202 |  | 20882.7202 |  | 20882.7202 |  | 20882.7202 |  | 20882.7202 |  | 20882.7202 |  | 20882.7202
2026-07-16 | 146407.3624 |  |  | 20915.3375 |  | 20915.3375 |  | 20915.3375 |  | 20915.3375 |  | 20915.3375 |  | 20915.3375 |  | 20915.3375
2026-07-17 | 146635.6832 |  |  | 20947.9547 |  | 20947.9547 |  | 20947.9547 |  | 20947.9547 |  | 20947.9547 |  | 20947.9547 |  | 20947.9547
2026-07-18 | 146864.004 |  |  | 20980.572 |  | 20980.572 |  | 20980.572 |  | 20980.572 |  | 20980.572 |  | 20980.572 |  | 20980.572
2026-07-19 | 147092.3248 |  |  | 21013.1893 |  | 21013.1893 |  | 21013.1893 |  | 21013.1893 |  | 21013.1893 |  | 21013.1893 |  | 21013.1893
2026-07-20 | 147320.6456 |  |  | 21045.8065 |  | 21045.8065 |  | 21045.8065 |  | 21045.8065 |  | 21045.8065 |  | 21045.8065 |  | 21045.8065
2026-07-21 | 147548.9664 |  |  | 21078.4238 |  | 21078.4238 |  | 21078.4238 |  | 21078.4238 |  | 21078.4238 |  | 21078.4238 |  | 21078.4238
2026-07-22 | 147777.2872 |  |  | 21111.041 |  | 21111.041 |  | 21111.041 |  | 21111.041 |  | 21111.041 |  | 21111.041 |  | 21111.041
2026-07-23 | 148005.608 |  |  | 21143.6583 |  | 21143.6583 |  | 21143.6583 |  | 21143.6583 |  | 21143.6583 |  | 21143.6583 |  | 21143.6583
2026-07-24 | 148233.9288 |  |  | 21176.2755 |  | 21176.2755 |  | 21176.2755 |  | 21176.2755 |  | 21176.2755 |  | 21176.2755 |  | 21176.2755
2026-07-25 | 148462.2496 |  |  | 21208.8928 |  | 21208.8928 |  | 21208.8928 |  | 21208.8928 |  | 21208.8928 |  | 21208.8928 |  | 21208.8928
2026-07-26 | 148690.5704 |  |  | 21241.5101 |  | 21241.5101 |  | 21241.5101 |  | 21241.5101 |  | 21241.5101 |  | 21241.5101 |  | 21241.5101
2026-07-27 | 148918.8912 |  |  | 21274.1273 |  | 21274.1273 |  | 21274.1273 |  | 21274.1273 |  | 21274.1273 |  | 21274.1273 |  | 21274.1273
2026-07-28 | 149147.212 |  |  | 21306.7446 |  | 21306.7446 |  | 21306.7446 |  | 21306.7446 |  | 21306.7446 |  | 21306.7446 |  | 21306.7446
2026-07-29 | 149375.5328 |  |  | 21339.3618 |  | 21339.3618 |  | 21339.3618 |  | 21339.3618 |  | 21339.3618 |  | 21339.3618 |  | 21339.3618
2026-07-30 | 149603.8536 |  |  | 21371.9791 |  | 21371.9791 |  | 21371.9791 |  | 21371.9791 |  | 21371.9791 |  | 21371.9791 |  | 21371.9791
2026-07-31 | 149832.1744 |  |  | 21404.5963 |  | 21404.5963 |  | 21404.5963 |  | 21404.5963 |  | 21404.5963 |  | 21404.5963 |  | 21404.5963
2026-08-01 | 150060.4952 |  |  | 21437.2136 |  | 21437.2136 |  | 21437.2136 |  | 21437.2136 |  | 21437.2136 |  | 21437.2136 |  | 21437.2136
2026-08-02 | 150288.816 |  |  | 21469.8309 |  | 21469.8309 |  | 21469.8309 |  | 21469.8309 |  | 21469.8309 |  | 21469.8309 |  | 21469.8309
2026-08-03 | 150517.1368 |  |  | 21502.4481 |  | 21502.4481 |  | 21502.4481 |  | 21502.4481 |  | 21502.4481 |  | 21502.4481 |  | 21502.4481
2026-08-04 | 150745.4576 |  |  | 21535.0654 |  | 21535.0654 |  | 21535.0654 |  | 21535.0654 |  | 21535.0654 |  | 21535.0654 |  | 21535.0654
2026-08-05 | 150973.7784 |  |  | 21567.6826 |  | 21567.6826 |  | 21567.6826 |  | 21567.6826 |  | 21567.6826 |  | 21567.6826 |  | 21567.6826
2026-08-06 | 151202.0992 |  |  | 21600.2999 |  | 21600.2999 |  | 21600.2999 |  | 21600.2999 |  | 21600.2999 |  | 21600.2999 |  | 21600.2999
2026-08-07 | 151430.4201 |  |  | 21632.9172 |  | 21632.9172 |  | 21632.9172 |  | 21632.9172 |  | 21632.9172 |  | 21632.9172 |  | 21632.9172
2026-08-08 | 151658.7409 |  |  | 21665.5344 |  | 21665.5344 |  | 21665.5344 |  | 21665.5344 |  | 21665.5344 |  | 21665.5344 |  | 21665.5344
2026-08-09 | 151887.0617 |  |  | 21698.1517 |  | 21698.1517 |  | 21698.1517 |  | 21698.1517 |  | 21698.1517 |  | 21698.1517 |  | 21698.1517
2026-08-10 | 152115.3825 |  |  | 21730.7689 |  | 21730.7689 |  | 21730.7689 |  | 21730.7689 |  | 21730.7689 |  | 21730.7689 |  | 21730.7689
2026-08-11 | 152343.7033 |  |  | 21763.3862 |  | 21763.3862 |  | 21763.3862 |  | 21763.3862 |  | 21763.3862 |  | 21763.3862 |  | 21763.3862
2026-08-12 | 152572.0241 |  |  | 21796.0034 |  | 21796.0034 |  | 21796.0034 |  | 21796.0034 |  | 21796.0034 |  | 21796.0034 |  | 21796.0034
2026-08-13 | 152800.3449 |  |  | 21828.6207 |  | 21828.6207 |  | 21828.6207 |  | 21828.6207 |  | 21828.6207 |  | 21828.6207 |  | 21828.6207
2026-08-14 | 153028.6657 |  |  | 21861.238 |  | 21861.238 |  | 21861.238 |  | 21861.238 |  | 21861.238 |  | 21861.238 |  | 21861.238
2026-08-15 | 153256.9865 |  |  | 21893.8552 |  | 21893.8552 |  | 21893.8552 |  | 21893.8552 |  | 21893.8552 |  | 21893.8552 |  | 21893.8552
2026-08-16 | 153485.3073 |  |  | 21926.4725 |  | 21926.4725 |  | 21926.4725 |  | 21926.4725 |  | 21926.4725 |  | 21926.4725 |  | 21926.4725
2026-08-17 | 153713.6281 |  |  | 21959.0897 |  | 21959.0897 |  | 21959.0897 |  | 21959.0897 |  | 21959.0897 |  | 21959.0897 |  | 21959.0897
2026-08-18 | 153941.9489 |  |  | 21991.707 |  | 21991.707 |  | 21991.707 |  | 21991.707 |  | 21991.707 |  | 21991.707 |  | 21991.707
2026-08-19 | 154170.2697 |  |  | 22024.3242 |  | 22024.3242 |  | 22024.3242 |  | 22024.3242 |  | 22024.3242 |  | 22024.3242 |  | 22024.3242
2026-08-20 | 154398.5905 |  |  | 22056.9415 |  | 22056.9415 |  | 22056.9415 |  | 22056.9415 |  | 22056.9415 |  | 22056.9415 |  | 22056.9415
2026-08-21 | 154626.9113 |  |  | 22089.5588 |  | 22089.5588 |  | 22089.5588 |  | 22089.5588 |  | 22089.5588 |  | 22089.5588 |  | 22089.5588
2026-08-22 | 154855.2321 |  |  | 22122.176 |  | 22122.176 |  | 22122.176 |  | 22122.176 |  | 22122.176 |  | 22122.176 |  | 22122.176
2026-08-23 | 155083.5529 |  |  | 22154.7933 |  | 22154.7933 |  | 22154.7933 |  | 22154.7933 |  | 22154.7933 |  | 22154.7933 |  | 22154.7933
2026-08-24 | 155311.8737 |  |  | 22187.4105 |  | 22187.4105 |  | 22187.4105 |  | 22187.4105 |  | 22187.4105 |  | 22187.4105 |  | 22187.4105
2026-08-25 | 155540.1945 |  |  | 22220.0278 |  | 22220.0278 |  | 22220.0278 |  | 22220.0278 |  | 22220.0278 |  | 22220.0278 |  | 22220.0278
2026-08-26 | 155768.5153 |  |  | 22252.645 |  | 22252.645 |  | 22252.645 |  | 22252.645 |  | 22252.645 |  | 22252.645 |  | 22252.645
2026-08-27 | 155996.8361 |  |  | 22285.2623 |  | 22285.2623 |  | 22285.2623 |  | 22285.2623 |  | 22285.2623 |  | 22285.2623 |  | 22285.2623
2026-08-28 | 156225.1569 |  |  | 22317.8796 |  | 22317.8796 |  | 22317.8796 |  | 22317.8796 |  | 22317.8796 |  | 22317.8796 |  | 22317.8796
2026-08-29 | 156453.4777 |  |  | 22350.4968 |  | 22350.4968 |  | 22350.4968 |  | 22350.4968 |  | 22350.4968 |  | 22350.4968 |  | 22350.4968
2026-08-30 | 156681.7985 |  |  | 22383.1141 |  | 22383.1141 |  | 22383.1141 |  | 22383.1141 |  | 22383.1141 |  | 22383.1141 |  | 22383.1141
2026-08-31 | 156910.1193 |  |  | 22415.7313 |  | 22415.7313 |  | 22415.7313 |  | 22415.7313 |  | 22415.7313 |  | 22415.7313 |  | 22415.7313
2026-09-01 | 157138.4401 |  |  | 22448.3486 |  | 22448.3486 |  | 22448.3486 |  | 22448.3486 |  | 22448.3486 |  | 22448.3486 |  | 22448.3486
2026-09-02 | 157366.7609 |  |  | 22480.9658 |  | 22480.9658 |  | 22480.9658 |  | 22480.9658 |  | 22480.9658 |  | 22480.9658 |  | 22480.9658
2026-09-03 | 157595.0817 |  |  | 22513.5831 |  | 22513.5831 |  | 22513.5831 |  | 22513.5831 |  | 22513.5831 |  | 22513.5831 |  | 22513.5831
2026-09-04 | 157823.4025 |  |  | 22546.2004 |  | 22546.2004 |  | 22546.2004 |  | 22546.2004 |  | 22546.2004 |  | 22546.2004 |  | 22546.2004
2026-09-05 | 158051.7233 |  |  | 22578.8176 |  | 22578.8176 |  | 22578.8176 |  | 22578.8176 |  | 22578.8176 |  | 22578.8176 |  | 22578.8176
2026-09-06 | 158280.0441 |  |  | 22611.4349 |  | 22611.4349 |  | 22611.4349 |  | 22611.4349 |  | 22611.4349 |  | 22611.4349 |  | 22611.4349
2026-09-07 | 158508.3649 |  |  | 22644.0521 |  | 22644.0521 |  | 22644.0521 |  | 22644.0521 |  | 22644.0521 |  | 22644.0521 |  | 22644.0521
2026-09-08 | 158736.6857 |  |  | 22676.6694 |  | 22676.6694 |  | 22676.6694 |  | 22676.6694 |  | 22676.6694 |  | 22676.6694 |  | 22676.6694
2026-09-09 | 158965.0065 |  |  | 22709.2866 |  | 22709.2866 |  | 22709.2866 |  | 22709.2866 |  | 22709.2866 |  | 22709.2866 |  | 22709.2866
2026-09-10 | 159193.3273 |  |  | 22741.9039 |  | 22741.9039 |  | 22741.9039 |  | 22741.9039 |  | 22741.9039 |  | 22741.9039 |  | 22741.9039
2026-09-11 | 159421.6481 |  |  | 22774.5212 |  | 22774.5212 |  | 22774.5212 |  | 22774.5212 |  | 22774.5212 |  | 22774.5212 |  | 22774.5212
2026-09-12 | 159649.9689 |  |  | 22807.1384 |  | 22807.1384 |  | 22807.1384 |  | 22807.1384 |  | 22807.1384 |  | 22807.1384 |  | 22807.1384
2026-09-13 | 159878.2897 |  |  | 22839.7557 |  | 22839.7557 |  | 22839.7557 |  | 22839.7557 |  | 22839.7557 |  | 22839.7557 |  | 22839.7557
2026-09-14 | 160106.6105 |  |  | 22872.3729 |  | 22872.3729 |  | 22872.3729 |  | 22872.3729 |  | 22872.3729 |  | 22872.3729 |  | 22872.3729
2026-09-15 | 160334.9313 |  |  | 22904.9902 |  | 22904.9902 |  | 22904.9902 |  | 22904.9902 |  | 22904.9902 |  | 22904.9902 |  | 22904.9902
2026-09-16 | 160563.2521 |  |  | 22937.6074 |  | 22937.6074 |  | 22937.6074 |  | 22937.6074 |  | 22937.6074 |  | 22937.6074 |  | 22937.6074
2026-09-17 | 160791.5729 |  |  | 22970.2247 |  | 22970.2247 |  | 22970.2247 |  | 22970.2247 |  | 22970.2247 |  | 22970.2247 |  | 22970.2247
2026-09-18 | 161019.8937 |  |  | 23002.842 |  | 23002.842 |  | 23002.842 |  | 23002.842 |  | 23002.842 |  | 23002.842 |  | 23002.842
2026-09-19 | 161248.2145 |  |  | 23035.4592 |  | 23035.4592 |  | 23035.4592 |  | 23035.4592 |  | 23035.4592 |  | 23035.4592 |  | 23035.4592
2026-09-20 | 161476.5353 |  |  | 23068.0765 |  | 23068.0765 |  | 23068.0765 |  | 23068.0765 |  | 23068.0765 |  | 23068.0765 |  | 23068.0765
2026-09-21 | 161704.8561 |  |  | 23100.6937 |  | 23100.6937 |  | 23100.6937 |  | 23100.6937 |  | 23100.6937 |  | 23100.6937 |  | 23100.6937
2026-09-22 | 161933.1769 |  |  | 23133.311 |  | 23133.311 |  | 23133.311 |  | 23133.311 |  | 23133.311 |  | 23133.311 |  | 23133.311
2026-09-23 | 162161.4977 |  |  | 23165.9282 |  | 23165.9282 |  | 23165.9282 |  | 23165.9282 |  | 23165.9282 |  | 23165.9282 |  | 23165.9282
2026-09-24 | 162389.8185 |  |  | 23198.5455 |  | 23198.5455 |  | 23198.5455 |  | 23198.5455 |  | 23198.5455 |  | 23198.5455 |  | 23198.5455
2026-09-25 | 162618.1393 |  |  | 23231.1628 |  | 23231.1628 |  | 23231.1628 |  | 23231.1628 |  | 23231.1628 |  | 23231.1628 |  | 23231.1628
2026-09-26 | 162846.4602 |  |  | 23263.78 |  | 23263.78 |  | 23263.78 |  | 23263.78 |  | 23263.78 |  | 23263.78 |  | 23263.78
2026-09-27 | 163074.781 |  |  | 23296.3973 |  | 23296.3973 |  | 23296.3973 |  | 23296.3973 |  | 23296.3973 |  | 23296.3973 |  | 23296.3973
2026-09-28 | 163303.1018 |  |  | 23329.0145 |  | 23329.0145 |  | 23329.0145 |  | 23329.0145 |  | 23329.0145 |  | 23329.0145 |  | 23329.0145
2026-09-29 | 163531.4226 |  |  | 23361.6318 |  | 23361.6318 |  | 23361.6318 |  | 23361.6318 |  | 23361.6318 |  | 23361.6318 |  | 23361.6318
2026-09-30 | 163759.7434 |  |  | 23394.2491 |  | 23394.2491 |  | 23394.2491 |  | 23394.2491 |  | 23394.2491 |  | 23394.2491 |  | 23394.2491
2026-10-01 | 163988.0642 |  |  | 23426.8663 |  | 23426.8663 |  | 23426.8663 |  | 23426.8663 |  | 23426.8663 |  | 23426.8663 |  | 23426.8663
2026-10-02 | 164216.385 |  |  | 23459.4836 |  | 23459.4836 |  | 23459.4836 |  | 23459.4836 |  | 23459.4836 |  | 23459.4836 |  | 23459.4836
2026-10-03 | 164444.7058 |  |  | 23492.1008 |  | 23492.1008 |  | 23492.1008 |  | 23492.1008 |  | 23492.1008 |  | 23492.1008 |  | 23492.1008
2026-10-04 | 164673.0266 |  |  | 23524.7181 |  | 23524.7181 |  | 23524.7181 |  | 23524.7181 |  | 23524.7181 |  | 23524.7181 |  | 23524.7181
2026-10-05 | 164901.3474 |  |  | 23557.3353 |  | 23557.3353 |  | 23557.3353 |  | 23557.3353 |  | 23557.3353 |  | 23557.3353 |  | 23557.3353
2026-10-06 | 165129.6682 |  |  | 23589.9526 |  | 23589.9526 |  | 23589.9526 |  | 23589.9526 |  | 23589.9526 |  | 23589.9526 |  | 23589.9526
2026-10-07 | 165357.989 |  |  | 23622.5699 |  | 23622.5699 |  | 23622.5699 |  | 23622.5699 |  | 23622.5699 |  | 23622.5699 |  | 23622.5699
2026-10-08 | 165586.3098 |  |  | 23655.1871 |  | 23655.1871 |  | 23655.1871 |  | 23655.1871 |  | 23655.1871 |  | 23655.1871 |  | 23655.1871
2026-10-09 | 165814.6306 |  |  | 23687.8044 |  | 23687.8044 |  | 23687.8044 |  | 23687.8044 |  | 23687.8044 |  | 23687.8044 |  | 23687.8044
2026-10-10 | 166042.9514 |  |  | 23720.4216 |  | 23720.4216 |  | 23720.4216 |  | 23720.4216 |  | 23720.4216 |  | 23720.4216 |  | 23720.4216
2026-10-11 | 166271.2722 |  |  | 23753.0389 |  | 23753.0389 |  | 23753.0389 |  | 23753.0389 |  | 23753.0389 |  | 23753.0389 |  | 23753.0389
2026-10-12 | 166499.593 |  |  | 23785.6561 |  | 23785.6561 |  | 23785.6561 |  | 23785.6561 |  | 23785.6561 |  | 23785.6561 |  | 23785.6561
2026-10-13 | 166727.9138 |  |  | 23818.2734 |  | 23818.2734 |  | 23818.2734 |  | 23818.2734 |  | 23818.2734 |  | 23818.2734 |  | 23818.2734
2026-10-14 | 166956.2346 |  |  | 23850.8907 |  | 23850.8907 |  | 23850.8907 |  | 23850.8907 |  | 23850.8907 |  | 23850.8907 |  | 23850.8907
2026-10-15 | 167184.5554 |  |  | 23883.5079 |  | 23883.5079 |  | 23883.5079 |  | 23883.5079 |  | 23883.5079 |  | 23883.5079 |  | 23883.5079
2026-10-16 | 167412.8762 |  |  | 23916.1252 |  | 23916.1252 |  | 23916.1252 |  | 23916.1252 |  | 23916.1252 |  | 23916.1252 |  | 23916.1252
2026-10-17 | 167641.197 |  |  | 23948.7424 |  | 23948.7424 |  | 23948.7424 |  | 23948.7424 |  | 23948.7424 |  | 23948.7424 |  | 23948.7424
2026-10-18 | 167869.5178 |  |  | 23981.3597 |  | 23981.3597 |  | 23981.3597 |  | 23981.3597 |  | 23981.3597 |  | 23981.3597 |  | 23981.3597
2026-10-19 | 168097.8386 |  |  | 24013.9769 |  | 24013.9769 |  | 24013.9769 |  | 24013.9769 |  | 24013.9769 |  | 24013.9769 |  | 24013.9769
2026-10-20 | 168326.1594 |  |  | 24046.5942 |  | 24046.5942 |  | 24046.5942 |  | 24046.5942 |  | 24046.5942 |  | 24046.5942 |  | 24046.5942
2026-10-21 | 168554.4802 |  |  | 24079.2115 |  | 24079.2115 |  | 24079.2115 |  | 24079.2115 |  | 24079.2115 |  | 24079.2115 |  | 24079.2115
2026-10-22 | 168782.801 |  |  | 24111.8287 |  | 24111.8287 |  | 24111.8287 |  | 24111.8287 |  | 24111.8287 |  | 24111.8287 |  | 24111.8287
2026-10-23 | 169011.1218 |  |  | 24144.446 |  | 24144.446 |  | 24144.446 |  | 24144.446 |  | 24144.446 |  | 24144.446 |  | 24144.446
2026-10-24 | 169239.4426 |  |  | 24177.0632 |  | 24177.0632 |  | 24177.0632 |  | 24177.0632 |  | 24177.0632 |  | 24177.0632 |  | 24177.0632
2026-10-25 | 169467.7634 |  |  | 24209.6805 |  | 24209.6805 |  | 24209.6805 |  | 24209.6805 |  | 24209.6805 |  | 24209.6805 |  | 24209.6805
2026-10-26 | 169696.0842 |  |  | 24242.2977 |  | 24242.2977 |  | 24242.2977 |  | 24242.2977 |  | 24242.2977 |  | 24242.2977 |  | 24242.2977
2026-10-27 | 169924.405 |  |  | 24274.915 |  | 24274.915 |  | 24274.915 |  | 24274.915 |  | 24274.915 |  | 24274.915 |  | 24274.915
2026-10-28 | 170152.7258 |  |  | 24307.5323 |  | 24307.5323 |  | 24307.5323 |  | 24307.5323 |  | 24307.5323 |  | 24307.5323 |  | 24307.5323
2026-10-29 | 170381.0466 |  |  | 24340.1495 |  | 24340.1495 |  | 24340.1495 |  | 24340.1495 |  | 24340.1495 |  | 24340.1495 |  | 24340.1495
2026-10-30 | 170609.3674 |  |  | 24372.7668 |  | 24372.7668 |  | 24372.7668 |  | 24372.7668 |  | 24372.7668 |  | 24372.7668 |  | 24372.7668
2026-10-31 | 170837.6882 |  |  | 24405.384 |  | 24405.384 |  | 24405.384 |  | 24405.384 |  | 24405.384 |  | 24405.384 |  | 24405.384
2026-11-01 | 171066.009 |  |  | 24438.0013 |  | 24438.0013 |  | 24438.0013 |  | 24438.0013 |  | 24438.0013 |  | 24438.0013 |  | 24438.0013
2026-11-02 | 171294.3298 |  |  | 24470.6185 |  | 24470.6185 |  | 24470.6185 |  | 24470.6185 |  | 24470.6185 |  | 24470.6185 |  | 24470.6185
2026-11-03 | 171522.6506 |  |  | 24503.2358 |  | 24503.2358 |  | 24503.2358 |  | 24503.2358 |  | 24503.2358 |  | 24503.2358 |  | 24503.2358
2026-11-04 | 171750.9714 |  |  | 24535.8531 |  | 24535.8531 |  | 24535.8531 |  | 24535.8531 |  | 24535.8531 |  | 24535.8531 |  | 24535.8531
2026-11-05 | 171979.2922 |  |  | 24568.4703 |  | 24568.4703 |  | 24568.4703 |  | 24568.4703 |  | 24568.4703 |  | 24568.4703 |  | 24568.4703
2026-11-06 | 172207.613 |  |  | 24601.0876 |  | 24601.0876 |  | 24601.0876 |  | 24601.0876 |  | 24601.0876 |  | 24601.0876 |  | 24601.0876
2026-11-07 | 172435.9338 |  |  | 24633.7048 |  | 24633.7048 |  | 24633.7048 |  | 24633.7048 |  | 24633.7048 |  | 24633.7048 |  | 24633.7048
2026-11-08 | 172664.2546 |  |  | 24666.3221 |  | 24666.3221 |  | 24666.3221 |  | 24666.3221 |  | 24666.3221 |  | 24666.3221 |  | 24666.3221
2026-11-09 | 172892.5754 |  |  | 24698.9393 |  | 24698.9393 |  | 24698.9393 |  | 24698.9393 |  | 24698.9393 |  | 24698.9393 |  | 24698.9393
2026-11-10 | 173120.8962 |  |  | 24731.5566 |  | 24731.5566 |  | 24731.5566 |  | 24731.5566 |  | 24731.5566 |  | 24731.5566 |  | 24731.5566
2026-11-11 | 173349.217 |  |  | 24764.1739 |  | 24764.1739 |  | 24764.1739 |  | 24764.1739 |  | 24764.1739 |  | 24764.1739 |  | 24764.1739
2026-11-12 | 173577.5378 |  |  | 24796.7911 |  | 24796.7911 |  | 24796.7911 |  | 24796.7911 |  | 24796.7911 |  | 24796.7911 |  | 24796.7911
2026-11-13 | 173805.8586 |  |  | 24829.4084 |  | 24829.4084 |  | 24829.4084 |  | 24829.4084 |  | 24829.4084 |  | 24829.4084 |  | 24829.4084
2026-11-14 | 174034.1794 |  |  | 24862.0256 |  | 24862.0256 |  | 24862.0256 |  | 24862.0256 |  | 24862.0256 |  | 24862.0256 |  | 24862.0256
2026-11-15 | 174262.5003 |  |  | 24894.6429 |  | 24894.6429 |  | 24894.6429 |  | 24894.6429 |  | 24894.6429 |  | 24894.6429 |  | 24894.6429
2026-11-16 | 174490.8211 |  |  | 24927.2602 |  | 24927.2602 |  | 24927.2602 |  | 24927.2602 |  | 24927.2602 |  | 24927.2602 |  | 24927.2602
2026-11-17 | 174719.1419 |  |  | 24959.8774 |  | 24959.8774 |  | 24959.8774 |  | 24959.8774 |  | 24959.8774 |  | 24959.8774 |  | 24959.8774
2026-11-18 | 174947.4627 |  |  | 24992.4947 |  | 24992.4947 |  | 24992.4947 |  | 24992.4947 |  | 24992.4947 |  | 24992.4947 |  | 24992.4947
2026-11-19 | 175175.7835 |  |  | 25025.1119 |  | 25025.1119 |  | 25025.1119 |  | 25025.1119 |  | 25025.1119 |  | 25025.1119 |  | 25025.1119
2026-11-20 | 175404.1043 |  |  | 25057.7292 |  | 25057.7292 |  | 25057.7292 |  | 25057.7292 |  | 25057.7292 |  | 25057.7292 |  | 25057.7292
2026-11-21 | 175632.4251 |  |  | 25090.3464 |  | 25090.3464 |  | 25090.3464 |  | 25090.3464 |  | 25090.3464 |  | 25090.3464 |  | 25090.3464
2026-11-22 | 175860.7459 |  |  | 25122.9637 |  | 25122.9637 |  | 25122.9637 |  | 25122.9637 |  | 25122.9637 |  | 25122.9637 |  | 25122.9637
2026-11-23 | 176089.0667 |  |  | 25155.581 |  | 25155.581 |  | 25155.581 |  | 25155.581 |  | 25155.581 |  | 25155.581 |  | 25155.581
2026-11-24 | 176552.0875 |  |  | 25221.7268 |  | 25221.7268 |  | 25221.7268 |  | 25221.7268 |  | 25221.7268 |  | 25221.7268 |  | 25221.7268
2026-11-25 | 177015.1083 |  |  | 25287.8726 |  | 25287.8726 |  | 25287.8726 |  | 25287.8726 |  | 25287.8726 |  | 25287.8726 |  | 25287.8726
2026-11-26 | 177478.1292 |  |  | 25354.0185 |  | 25354.0185 |  | 25354.0185 |  | 25354.0185 |  | 25354.0185 |  | 25354.0185 |  | 25354.0185
2026-11-27 | 177941.15 |  |  | 25420.1643 |  | 25420.1643 |  | 25420.1643 |  | 25420.1643 |  | 25420.1643 |  | 25420.1643 |  | 25420.1643
2026-11-28 | 178404.1708 |  |  | 25486.3101 |  | 25486.3101 |  | 25486.3101 |  | 25486.3101 |  | 25486.3101 |  | 25486.3101 |  | 25486.3101
2026-11-29 | 178867.1917 |  |  | 25552.456 |  | 25552.456 |  | 25552.456 |  | 25552.456 |  | 25552.456 |  | 25552.456 |  | 25552.456
2026-11-30 | 179330.2125 |  |  | 25618.6018 |  | 25618.6018 |  | 25618.6018 |  | 25618.6018 |  | 25618.6018 |  | 25618.6018 |  | 25618.6018
2026-12-01 | 179793.2333 |  |  | 25684.7476 |  | 25684.7476 |  | 25684.7476 |  | 25684.7476 |  | 25684.7476 |  | 25684.7476 |  | 25684.7476
2026-12-02 | 180256.2542 |  |  | 25750.8935 |  | 25750.8935 |  | 25750.8935 |  | 25750.8935 |  | 25750.8935 |  | 25750.8935 |  | 25750.8935
2026-12-03 | 180719.275 |  |  | 25817.0393 |  | 25817.0393 |  | 25817.0393 |  | 25817.0393 |  | 25817.0393 |  | 25817.0393 |  | 25817.0393
2026-12-04 | 181182.2958 |  |  | 25883.1851 |  | 25883.1851 |  | 25883.1851 |  | 25883.1851 |  | 25883.1851 |  | 25883.1851 |  | 25883.1851
2026-12-05 | 181645.3167 |  |  | 25949.331 |  | 25949.331 |  | 25949.331 |  | 25949.331 |  | 25949.331 |  | 25949.331 |  | 25949.331
2026-12-06 | 182108.3375 |  |  | 26015.4768 |  | 26015.4768 |  | 26015.4768 |  | 26015.4768 |  | 26015.4768 |  | 26015.4768 |  | 26015.4768
2026-12-07 | 182571.3583 |  |  | 26081.6226 |  | 26081.6226 |  | 26081.6226 |  | 26081.6226 |  | 26081.6226 |  | 26081.6226 |  | 26081.6226
2026-12-08 | 183034.3792 |  |  | 26147.7685 |  | 26147.7685 |  | 26147.7685 |  | 26147.7685 |  | 26147.7685 |  | 26147.7685 |  | 26147.7685
2026-12-09 | 183497.4 |  |  | 26213.9143 |  | 26213.9143 |  | 26213.9143 |  | 26213.9143 |  | 26213.9143 |  | 26213.9143 |  | 26213.9143
2026-12-10 | 183960.4208 |  |  | 26280.0601 |  | 26280.0601 |  | 26280.0601 |  | 26280.0601 |  | 26280.0601 |  | 26280.0601 |  | 26280.0601
2026-12-11 | 184423.4417 |  |  | 26346.206 |  | 26346.206 |  | 26346.206 |  | 26346.206 |  | 26346.206 |  | 26346.206 |  | 26346.206
2026-12-12 | 184886.4625 |  |  | 26412.3518 |  | 26412.3518 |  | 26412.3518 |  | 26412.3518 |  | 26412.3518 |  | 26412.3518 |  | 26412.3518
2026-12-13 | 185349.4833 |  |  | 26478.4976 |  | 26478.4976 |  | 26478.4976 |  | 26478.4976 |  | 26478.4976 |  | 26478.4976 |  | 26478.4976
2026-12-14 | 185812.5042 |  |  | 26544.6435 |  | 26544.6435 |  | 26544.6435 |  | 26544.6435 |  | 26544.6435 |  | 26544.6435 |  | 26544.6435
2026-12-15 | 186275.525 |  |  | 26610.7893 |  | 26610.7893 |  | 26610.7893 |  | 26610.7893 |  | 26610.7893 |  | 26610.7893 |  | 26610.7893
2026-12-16 | 186738.5458 |  |  | 26676.9351 |  | 26676.9351 |  | 26676.9351 |  | 26676.9351 |  | 26676.9351 |  | 26676.9351 |  | 26676.9351
2026-12-17 | 187201.5667 |  |  | 26743.081 |  | 26743.081 |  | 26743.081 |  | 26743.081 |  | 26743.081 |  | 26743.081 |  | 26743.081
2026-12-18 | 187664.5875 |  |  | 26809.2268 |  | 26809.2268 |  | 26809.2268 |  | 26809.2268 |  | 26809.2268 |  | 26809.2268 |  | 26809.2268
2026-12-19 | 188127.6083 |  |  | 26875.3726 |  | 26875.3726 |  | 26875.3726 |  | 26875.3726 |  | 26875.3726 |  | 26875.3726 |  | 26875.3726
2026-12-20 | 188590.6292 |  |  | 26941.5185 |  | 26941.5185 |  | 26941.5185 |  | 26941.5185 |  | 26941.5185 |  | 26941.5185 |  | 26941.5185
2026-12-21 | 189053.65 |  |  | 27007.6643 |  | 27007.6643 |  | 27007.6643 |  | 27007.6643 |  | 27007.6643 |  | 27007.6643 |  | 27007.6643
2026-12-22 | 189516.6708 |  |  | 27073.8101 |  | 27073.8101 |  | 27073.8101 |  | 27073.8101 |  | 27073.8101 |  | 27073.8101 |  | 27073.8101
2026-12-23 | 189979.6917 |  |  | 27139.956 |  | 27139.956 |  | 27139.956 |  | 27139.956 |  | 27139.956 |  | 27139.956 |  | 27139.956
2026-12-24 | 190442.7125 |  |  | 27206.1018 |  | 27206.1018 |  | 27206.1018 |  | 27206.1018 |  | 27206.1018 |  | 27206.1018 |  | 27206.1018
2026-12-25 | 190905.7333 |  |  | 27272.2476 |  | 27272.2476 |  | 27272.2476 |  | 27272.2476 |  | 27272.2476 |  | 27272.2476 |  | 27272.2476

## Parts&materials (Direct Cost)
Date | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Actual Labor (Cumulative) | Planned 5004 · GTR Cost of Sales - Parts (Cumulative) | Actual 5004 · GTR Cost of Sales - Parts (Cumulative) | Planned 5111 · Parts & material costs (Direct) (Cumulative) | Actual 5111 · Parts & material costs (Direct) (Cumulative) | Planned 5128 · Health & Safety Equip (Direct) (Cumulative) | Actual 5128 · Health & Safety Equip (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 2253.2 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 3379.8 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 4506.4 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 37.03 | 5633 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-12 | 0 | 37.03 | 5633 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-13 | 0 | 37.03 | 5633 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-14 | 0 | 37.03 | 5847.4 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-15 | 0 | 37.03 | 6061.8 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-16 | 0 | 37.03 | 6276.2 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-17 | 0 | 37.03 | 6490.6 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-18 | 0 | 37.03 | 6705 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-19 | 0 | 37.03 | 6705 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-20 | 0 | 37.03 | 6705 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-21 | 0 | 37.03 | 7087.15 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-22 | 0 | 37.03 | 7469.3 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-23 | 0 | 37.03 | 7851.45 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-24 | 0 | 37.03 | 8233.6 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-25 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-26 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-27 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-28 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-29 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-30 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-01 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-02 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-03 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-04 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-05 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-06 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-07 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-08 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-09 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-10 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-11 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-12 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-13 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-14 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-15 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-16 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-17 | 0 | 37.03 | 8615.75 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-18 | 0 | 800.64 | 8615.75 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-19 | 0 | 800.64 | 8615.75 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-20 | 0 | 800.64 | 8615.75 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-21 | 0 | 800.64 | 8615.75 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-22 | 0 | 800.64 | 8615.75 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-23 | 0 | 979.62 | 8615.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-24 | 0 | 979.62 | 8615.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-25 | 0 | 979.62 | 8615.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-26 | 0 | 979.62 | 8615.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-27 | 0 | 979.62 | 8615.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-28 | 0 | 979.62 | 8615.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-29 | 0 | 979.62 | 8615.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-30 | 0 | 979.62 | 8615.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-31 | 0 | 979.62 | 8615.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-01 | 0 | 979.62 | 8615.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-02 | 0 | 979.62 | 9212.3 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-03 | 0 | 979.62 | 9808.85 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-04 | 0 | 979.62 | 10405.4 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-05 | 0 | 979.62 | 11001.95 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-06 | 0 | 979.62 | 11598.5 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-07 | 0 | 979.62 | 11598.5 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-08 | 0 | 979.62 | 11598.5 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-09 | 0 | 979.62 | 11873.45 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-10 | 0 | 979.62 | 12148.4 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-11 | 0 | 979.62 | 12423.35 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-12 | 0 | 979.62 | 12698.3 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-13 | 0 | 979.62 | 12973.25 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-14 | 0 | 979.62 | 12973.25 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-15 | 0 | 979.62 | 12973.25 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-16 | 0 | 979.62 | 13523.15 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-17 | 0 | 979.62 | 14073.05 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-18 | 0 | 979.62 | 14622.95 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-19 | 0 | 979.62 | 15172.85 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-20 | 0 | 979.62 | 15722.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-21 | 0 | 979.62 | 15722.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-22 | 0 | 979.62 | 15722.75 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-23 | 0 | 979.62 | 15997.7 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-24 | 0 | 979.62 | 16272.65 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-25 | 713.6371 | 979.62 | 16547.6 | 237.879 | 0 | 237.879 | 979.62 | 237.879 | 0
2025-06-26 | 1427.2742 | 979.62 | 16822.55 | 475.7581 | 0 | 475.7581 | 979.62 | 475.7581 | 0
2025-06-27 | 2140.9112 | 979.62 | 17097.5 | 713.6371 | 0 | 713.6371 | 979.62 | 713.6371 | 0
2025-06-28 | 2854.5483 | 979.62 | 17097.5 | 951.5161 | 0 | 951.5161 | 979.62 | 951.5161 | 0
2025-06-29 | 3568.1854 | 979.62 | 17097.5 | 1189.3951 | 0 | 1189.3951 | 979.62 | 1189.3951 | 0
2025-06-30 | 4281.8225 | 979.62 | 17714.4 | 1427.2742 | 0 | 1427.2742 | 979.62 | 1427.2742 | 0
2025-07-01 | 4995.4596 | 979.62 | 18331.3 | 1665.1532 | 0 | 1665.1532 | 979.62 | 1665.1532 | 0
2025-07-02 | 5709.0966 | 979.62 | 18948.2 | 1903.0322 | 0 | 1903.0322 | 979.62 | 1903.0322 | 0
2025-07-03 | 6422.7337 | 979.62 | 19565.1 | 2140.9112 | 0 | 2140.9112 | 979.62 | 2140.9112 | 0
2025-07-04 | 7136.3708 | 979.62 | 20182 | 2378.7903 | 0 | 2378.7903 | 979.62 | 2378.7903 | 0
2025-07-05 | 7850.0079 | 979.62 | 20182 | 2616.6693 | 0 | 2616.6693 | 979.62 | 2616.6693 | 0
2025-07-06 | 8563.6449 | 979.62 | 20182 | 2854.5483 | 0 | 2854.5483 | 979.62 | 2854.5483 | 0
2025-07-07 | 9277.282 | 979.62 | 20835.625 | 3092.4273 | 0 | 3092.4273 | 979.62 | 3092.4273 | 0
2025-07-08 | 9990.9191 | 979.62 | 21489.25 | 3330.3064 | 0 | 3330.3064 | 979.62 | 3330.3064 | 0
2025-07-09 | 10704.5562 | 979.62 | 22142.875 | 3568.1854 | 0 | 3568.1854 | 979.62 | 3568.1854 | 0
2025-07-10 | 11418.1933 | 979.62 | 22796.5 | 3806.0644 | 0 | 3806.0644 | 979.62 | 3806.0644 | 0
2025-07-11 | 12131.8303 | 979.62 | 23450.125 | 4043.9434 | 0 | 4043.9434 | 979.62 | 4043.9434 | 0
2025-07-12 | 12845.4674 | 979.62 | 23450.125 | 4281.8225 | 0 | 4281.8225 | 979.62 | 4281.8225 | 0
2025-07-13 | 13559.1045 | 979.62 | 23450.125 | 4519.7015 | 0 | 4519.7015 | 979.62 | 4519.7015 | 0
2025-07-14 | 14272.7416 | 979.62 | 24210.95 | 4757.5805 | 0 | 4757.5805 | 979.62 | 4757.5805 | 0
2025-07-15 | 14986.3787 | 979.62 | 24971.775 | 4995.4596 | 0 | 4995.4596 | 979.62 | 4995.4596 | 0
2025-07-16 | 15700.0157 | 979.62 | 25732.6 | 5233.3386 | 0 | 5233.3386 | 979.62 | 5233.3386 | 0
2025-07-17 | 16413.6528 | 979.62 | 26493.425 | 5471.2176 | 0 | 5471.2176 | 979.62 | 5471.2176 | 0
2025-07-18 | 17127.2899 | 979.62 | 27254.25 | 5709.0966 | 0 | 5709.0966 | 979.62 | 5709.0966 | 0
2025-07-19 | 17840.927 | 979.62 | 27254.25 | 5946.9757 | 0 | 5946.9757 | 979.62 | 5946.9757 | 0
2025-07-20 | 18554.564 | 979.62 | 27254.25 | 6184.8547 | 0 | 6184.8547 | 979.62 | 6184.8547 | 0
2025-07-21 | 19268.2011 | 979.62 | 27907.875 | 6422.7337 | 0 | 6422.7337 | 979.62 | 6422.7337 | 0
2025-07-22 | 19981.8382 | 979.62 | 28561.5 | 6660.6127 | 0 | 6660.6127 | 979.62 | 6660.6127 | 0
2025-07-23 | 20695.4753 | 979.62 | 29215.125 | 6898.4918 | 0 | 6898.4918 | 979.62 | 6898.4918 | 0
2025-07-24 | 21409.1124 | 979.62 | 29868.75 | 7136.3708 | 0 | 7136.3708 | 979.62 | 7136.3708 | 0
2025-07-25 | 22122.7494 | 979.62 | 30522.375 | 7374.2498 | 0 | 7374.2498 | 979.62 | 7374.2498 | 0
2025-07-26 | 22836.3865 | 979.62 | 30522.375 | 7612.1288 | 0 | 7612.1288 | 979.62 | 7612.1288 | 0
2025-07-27 | 23550.0236 | 979.62 | 30522.375 | 7850.0079 | 0 | 7850.0079 | 979.62 | 7850.0079 | 0
2025-07-28 | 24263.6607 | 979.62 | 31122.4 | 8087.8869 | 0 | 8087.8869 | 979.62 | 8087.8869 | 0
2025-07-29 | 24977.2978 | 979.62 | 31722.425 | 8325.7659 | 0 | 8325.7659 | 979.62 | 8325.7659 | 0
2025-07-30 | 25690.9348 | 979.62 | 32322.45 | 8563.6449 | 0 | 8563.6449 | 979.62 | 8563.6449 | 0
2025-07-31 | 26404.5719 | 979.62 | 32922.475 | 8801.524 | 0 | 8801.524 | 979.62 | 8801.524 | 0
2025-08-01 | 27118.209 | 2806.92 | 33522.5 | 9039.403 | 0 | 9039.403 | 2800.74 | 9039.403 | 6.18
2025-08-02 | 27831.8461 | 2806.92 | 33522.5 | 9277.282 | 0 | 9277.282 | 2800.74 | 9277.282 | 6.18
2025-08-03 | 28545.4831 | 2806.92 | 33522.5 | 9515.161 | 0 | 9515.161 | 2800.74 | 9515.161 | 6.18
2025-08-04 | 29259.1202 | 4176.07 | 34126 | 9753.0401 | 0 | 9753.0401 | 4169.89 | 9753.0401 | 6.18
2025-08-05 | 29972.7573 | 4176.07 | 34729.5 | 9990.9191 | 0 | 9990.9191 | 4169.89 | 9990.9191 | 6.18
2025-08-06 | 30686.3944 | 4176.07 | 35333 | 10228.7981 | 0 | 10228.7981 | 4169.89 | 10228.7981 | 6.18
2025-08-07 | 31400.0315 | 5126.94 | 35936.5 | 10466.6772 | 0 | 10466.6772 | 5120.76 | 10466.6772 | 6.18
2025-08-08 | 32113.6685 | 5126.94 | 36540 | 10704.5562 | 0 | 10704.5562 | 5120.76 | 10704.5562 | 6.18
2025-08-09 | 32827.3056 | 5126.94 | 36540 | 10942.4352 | 0 | 10942.4352 | 5120.76 | 10942.4352 | 6.18
2025-08-10 | 33540.9427 | 5126.94 | 36540 | 11180.3142 | 0 | 11180.3142 | 5120.76 | 11180.3142 | 6.18
2025-08-11 | 34254.5798 | 5343.91 | 37089.9 | 11418.1933 | 0 | 11418.1933 | 5337.73 | 11418.1933 | 6.18
2025-08-12 | 34968.2169 | 5343.91 | 37639.8 | 11656.0723 | 0 | 11656.0723 | 5337.73 | 11656.0723 | 6.18
2025-08-13 | 35681.8539 | 5343.91 | 38189.7 | 11893.9513 | 0 | 11893.9513 | 5337.73 | 11893.9513 | 6.18
2025-08-14 | 36395.491 | 5343.91 | 38739.6 | 12131.8303 | 0 | 12131.8303 | 5337.73 | 12131.8303 | 6.18
2025-08-15 | 37109.1281 | 5343.91 | 39289.5 | 12369.7094 | 0 | 12369.7094 | 5337.73 | 12369.7094 | 6.18
2025-08-16 | 37822.7652 | 5343.91 | 39289.5 | 12607.5884 | 0 | 12607.5884 | 5337.73 | 12607.5884 | 6.18
2025-08-17 | 38536.4022 | 5343.91 | 39289.5 | 12845.4674 | 0 | 12845.4674 | 5337.73 | 12845.4674 | 6.18
2025-08-18 | 39250.0393 | 5343.91 | 39993.25 | 13083.3464 | 0 | 13083.3464 | 5337.73 | 13083.3464 | 6.18
2025-08-19 | 39963.6764 | 17853.27 | 40697 | 13321.2255 | 0 | 13321.2255 | 17847.09 | 13321.2255 | 6.18
2025-08-20 | 40677.3135 | 17853.27 | 41400.75 | 13559.1045 | 0 | 13559.1045 | 17847.09 | 13559.1045 | 6.18
2025-08-21 | 41390.9506 | 17853.27 | 42104.5 | 13796.9835 | 0 | 13796.9835 | 17847.09 | 13796.9835 | 6.18
2025-08-22 | 42104.5876 | 17853.27 | 42808.25 | 14034.8625 | 0 | 14034.8625 | 17847.09 | 14034.8625 | 6.18
2025-08-23 | 42818.2247 | 17853.27 | 42808.25 | 14272.7416 | 0 | 14272.7416 | 17847.09 | 14272.7416 | 6.18
2025-08-24 | 43531.8618 | 17853.27 | 42808.25 | 14510.6206 | 0 | 14510.6206 | 17847.09 | 14510.6206 | 6.18
2025-08-25 | 44245.4989 | 18573.03 | 43488.675 | 14748.4996 | 0 | 14748.4996 | 18566.85 | 14748.4996 | 6.18
2025-08-26 | 44959.136 | 18573.03 | 44169.1 | 14986.3787 | 0 | 14986.3787 | 18566.85 | 14986.3787 | 6.18
2025-08-27 | 45672.773 | 18573.03 | 44849.525 | 15224.2577 | 0 | 15224.2577 | 18566.85 | 15224.2577 | 6.18
2025-08-28 | 46386.4101 | 18573.03 | 45529.95 | 15462.1367 | 0 | 15462.1367 | 18566.85 | 15462.1367 | 6.18
2025-08-29 | 47100.0472 | 18573.03 | 46210.375 | 15700.0157 | 0 | 15700.0157 | 18566.85 | 15700.0157 | 6.18
2025-08-30 | 47813.6843 | 18573.03 | 46210.375 | 15937.8948 | 0 | 15937.8948 | 18566.85 | 15937.8948 | 6.18
2025-08-31 | 48527.3213 | 18573.03 | 46210.375 | 16175.7738 | 0 | 16175.7738 | 18566.85 | 16175.7738 | 6.18
2025-09-01 | 49240.9584 | 18573.03 | 47373.7 | 16413.6528 | 0 | 16413.6528 | 18566.85 | 16413.6528 | 6.18
2025-09-02 | 49954.5955 | 21697.83 | 48537.025 | 16651.5318 | 0 | 16651.5318 | 21691.65 | 16651.5318 | 6.18
2025-09-03 | 50668.2326 | 21697.83 | 49700.35 | 16889.4109 | 0 | 16889.4109 | 21691.65 | 16889.4109 | 6.18
2025-09-04 | 51381.8697 | 21697.83 | 50863.675 | 17127.2899 | 0 | 17127.2899 | 21691.65 | 17127.2899 | 6.18
2025-09-05 | 52095.5067 | 21868.54 | 52027 | 17365.1689 | 0 | 17365.1689 | 21862.36 | 17365.1689 | 6.18
2025-09-06 | 52809.1438 | 21868.54 | 52027 | 17603.0479 | 0 | 17603.0479 | 21862.36 | 17603.0479 | 6.18
2025-09-07 | 53522.7809 | 21868.54 | 52027 | 17840.927 | 0 | 17840.927 | 21862.36 | 17840.927 | 6.18
2025-09-08 | 54236.418 | 21868.54 | 52781.375 | 18078.806 | 0 | 18078.806 | 21862.36 | 18078.806 | 6.18
2025-09-09 | 54950.0551 | 22449.55 | 53535.75 | 18316.685 | 0 | 18316.685 | 22443.37 | 18316.685 | 6.18
2025-09-10 | 55663.6921 | 22449.55 | 54290.125 | 18554.564 | 0 | 18554.564 | 22443.37 | 18554.564 | 6.18
2025-09-11 | 56377.3292 | 22656.17 | 55044.5 | 18792.4431 | 0 | 18792.4431 | 22649.99 | 18792.4431 | 6.18
2025-09-12 | 57090.9663 | 23419.83 | 55798.875 | 19030.3221 | 0 | 19030.3221 | 23413.65 | 19030.3221 | 6.18
2025-09-13 | 57804.6034 | 23469.34 | 55798.875 | 19268.2011 | 0 | 19268.2011 | 23463.16 | 19268.2011 | 6.18
2025-09-14 | 58518.2404 | 23469.34 | 55798.875 | 19506.0801 | 0 | 19506.0801 | 23463.16 | 19506.0801 | 6.18
2025-09-15 | 59231.8775 | 23469.34 | 57425.25 | 19743.9592 | 0 | 19743.9592 | 23463.16 | 19743.9592 | 6.18
2025-09-16 | 59945.5146 | 23469.34 | 59051.625 | 19981.8382 | 0 | 19981.8382 | 23463.16 | 19981.8382 | 6.18
2025-09-17 | 60659.1517 | 23624.31 | 60678 | 20219.7172 | 0 | 20219.7172 | 23618.13 | 20219.7172 | 6.18
2025-09-18 | 61372.7888 | 23624.31 | 62304.375 | 20457.5963 | 0 | 20457.5963 | 23618.13 | 20457.5963 | 6.18
2025-09-19 | 62086.4258 | 23753.45 | 63930.75 | 20695.4753 | 0 | 20695.4753 | 23747.27 | 20695.4753 | 6.18
2025-09-20 | 62800.0629 | 24327.94 | 63930.75 | 20933.3543 | 0 | 20933.3543 | 24321.76 | 20933.3543 | 6.18
2025-09-21 | 63513.7 | 24327.94 | 63930.75 | 21171.2333 | 0 | 21171.2333 | 24321.76 | 21171.2333 | 6.18
2025-09-22 | 63513.7 | 24398.56 | 65705.925 | 21171.2333 | 0 | 21171.2333 | 24321.76 | 21171.2333 | 76.8
2025-09-23 | 64326.5779 | 24398.56 | 67481.1 | 21442.1926 | 0 | 21442.1926 | 24321.76 | 21442.1926 | 76.8
2025-09-24 | 65139.4559 | 27354.47 | 69256.275 | 21713.152 | 0 | 21713.152 | 27277.67 | 21713.152 | 76.8
2025-09-25 | 65952.3338 | 30373.02 | 71031.45 | 21984.1113 | 0 | 21984.1113 | 30005.24 | 21984.1113 | 367.78
2025-09-26 | 66765.2117 | 30682.47 | 72806.625 | 22255.0706 | 0 | 22255.0706 | 30314.69 | 22255.0706 | 367.78
2025-09-27 | 67578.0896 | 31197.46 | 72806.625 | 22526.0299 | 0 | 22526.0299 | 30829.68 | 22526.0299 | 367.78
2025-09-28 | 68390.9676 | 31520.24 | 72806.625 | 22796.9892 | 0 | 22796.9892 | 31152.46 | 22796.9892 | 367.78
2025-09-29 | 69203.8455 | 38844.83 | 74913.85 | 23067.9485 | 0 | 23067.9485 | 38395.03 | 23067.9485 | 449.8
2025-09-30 | 70016.7234 | 38844.83 | 77021.075 | 23338.9078 | 0 | 23338.9078 | 38395.03 | 23338.9078 | 449.8
2025-10-01 | 70829.6013 | 38907.11 | 79128.3 | 23609.8671 | 0 | 23609.8671 | 38442.44 | 23609.8671 | 464.67
2025-10-02 | 71642.4793 | 38907.11 | 81235.525 | 23880.8264 | 0 | 23880.8264 | 38442.44 | 23880.8264 | 464.67
2025-10-03 | 72455.3572 | 38907.11 | 83342.75 | 24151.7857 | 0 | 24151.7857 | 38442.44 | 24151.7857 | 464.67
2025-10-04 | 73268.2351 | 38907.11 | 83342.75 | 24422.745 | 0 | 24422.745 | 38442.44 | 24422.745 | 464.67
2025-10-05 | 74081.113 | 38907.11 | 83342.75 | 24693.7043 | 0 | 24693.7043 | 38442.44 | 24693.7043 | 464.67
2025-10-06 | 74893.991 | 38907.11 | 85089.875 | 24964.6637 | 0 | 24964.6637 | 38442.44 | 24964.6637 | 464.67
2025-10-07 | 75706.8689 | 38907.11 | 86837 | 25235.623 | 0 | 25235.623 | 38442.44 | 25235.623 | 464.67
2025-10-08 | 76519.7468 | 38907.11 | 88584.125 | 25506.5823 | 0 | 25506.5823 | 38442.44 | 25506.5823 | 464.67
2025-10-09 | 77332.6247 | 38907.11 | 90331.25 | 25777.5416 | 0 | 25777.5416 | 38442.44 | 25777.5416 | 464.67
2025-10-10 | 78145.5027 | 38975.27 | 92078.375 | 26048.5009 | 0 | 26048.5009 | 38442.44 | 26048.5009 | 532.83
2025-10-11 | 78958.3806 | 39009.7 | 92078.375 | 26319.4602 | 0 | 26319.4602 | 38442.44 | 26319.4602 | 567.26
2025-10-12 | 79771.2585 | 39023.5 | 92078.375 | 26590.4195 | 0 | 26590.4195 | 38456.24 | 26590.4195 | 567.26
2025-10-13 | 80584.1365 | 39023.5 | 93848.825 | 26861.3788 | 0 | 26861.3788 | 38456.24 | 26861.3788 | 567.26
2025-10-14 | 81397.0144 | 39174.89 | 95619.275 | 27132.3381 | 0 | 27132.3381 | 38607.63 | 27132.3381 | 567.26
2025-10-15 | 82209.8923 | 39174.89 | 97389.725 | 27403.2974 | 0 | 27403.2974 | 38607.63 | 27403.2974 | 567.26
2025-10-16 | 83022.7702 | 39174.89 | 99160.175 | 27674.2567 | 0 | 27674.2567 | 38607.63 | 27674.2567 | 567.26
2025-10-17 | 83835.6482 | 39204.68 | 100930.625 | 27945.2161 | 0 | 27945.2161 | 38607.63 | 27945.2161 | 597.05
2025-10-18 | 84648.5261 | 39204.68 | 100930.625 | 28216.1754 | 0 | 28216.1754 | 38607.63 | 28216.1754 | 597.05
2025-10-19 | 85461.404 | 39204.68 | 100930.625 | 28487.1347 | 0 | 28487.1347 | 38607.63 | 28487.1347 | 597.05
2025-10-20 | 86274.2819 | 39306.46 | 103046.55 | 28758.094 | 0 | 28758.094 | 38709.41 | 28758.094 | 597.05
2025-10-21 | 87087.1599 | 39385.81 | 105162.475 | 29029.0533 | 0 | 29029.0533 | 38788.76 | 29029.0533 | 597.05
2025-10-22 | 87900.0378 | 39385.81 | 107278.4 | 29300.0126 | 0 | 29300.0126 | 38788.76 | 29300.0126 | 597.05
2025-10-23 | 88712.9157 | 39385.81 | 109394.325 | 29570.9719 | 0 | 29570.9719 | 38788.76 | 29570.9719 | 597.05
2025-10-24 | 89525.7936 | 39639.56 | 111510.25 | 29841.9312 | 0 | 29841.9312 | 38788.76 | 29841.9312 | 850.8
2025-10-25 | 90338.6716 | 39639.56 | 111510.25 | 30112.8905 | 0 | 30112.8905 | 38788.76 | 30112.8905 | 850.8
2025-10-26 | 91151.5495 | 39639.56 | 111510.25 | 30383.8498 | 0 | 30383.8498 | 38788.76 | 30383.8498 | 850.8
2025-10-27 | 91964.4274 | 39639.56 | 113280.75 | 30654.8091 | 0 | 30654.8091 | 38788.76 | 30654.8091 | 850.8
2025-10-28 | 92777.3054 | 40754.18 | 115051.25 | 30925.7685 | 0 | 30925.7685 | 39844.18 | 30925.7685 | 910
2025-10-29 | 93590.1833 | 40892.74 | 116821.75 | 31196.7278 | 0 | 31196.7278 | 39982.74 | 31196.7278 | 910
2025-10-30 | 94403.0612 | 40972.8 | 118592.25 | 31467.6871 | 0 | 31467.6871 | 40062.8 | 31467.6871 | 910
2025-10-31 | 95215.9391 | 40972.8 | 120362.75 | 31738.6464 | 0 | 31738.6464 | 40062.8 | 31738.6464 | 910
2025-11-01 | 96028.8171 | 40972.8 | 120362.75 | 32009.6057 | 0 | 32009.6057 | 40062.8 | 32009.6057 | 910
2025-11-02 | 96841.695 | 40972.8 | 120362.75 | 32280.565 | 0 | 32280.565 | 40062.8 | 32280.565 | 910
2025-11-03 | 97654.5729 | 40972.8 | 122034.05 | 32551.5243 | 0 | 32551.5243 | 40062.8 | 32551.5243 | 910
2025-11-04 | 98467.4508 | 40972.8 | 123705.35 | 32822.4836 | 0 | 32822.4836 | 40062.8 | 32822.4836 | 910
2025-11-05 | 99280.3288 | 40972.8 | 125376.65 | 33093.4429 | 0 | 33093.4429 | 40062.8 | 33093.4429 | 910
2025-11-06 | 100093.2067 | 41196.15 | 127047.95 | 33364.4022 | 0 | 33364.4022 | 40286.15 | 33364.4022 | 910
2025-11-07 | 100906.0846 | 41483.21 | 128719.25 | 33635.3615 | 0 | 33635.3615 | 40573.21 | 33635.3615 | 910
2025-11-08 | 101718.9625 | 41483.21 | 128719.25 | 33906.3208 | 0 | 33906.3208 | 40573.21 | 33906.3208 | 910
2025-11-09 | 102531.8405 | 41483.21 | 128719.25 | 34177.2802 | 0 | 34177.2802 | 40573.21 | 34177.2802 | 910
2025-11-10 | 103344.7184 | 41483.21 | 130337.625 | 34448.2395 | 0 | 34448.2395 | 40573.21 | 34448.2395 | 910
2025-11-11 | 104157.5963 | 41565.94 | 131956 | 34719.1988 | 0 | 34719.1988 | 40655.94 | 34719.1988 | 910
2025-11-12 | 104970.4742 | 41565.94 | 133574.375 | 34990.1581 | 0 | 34990.1581 | 40655.94 | 34990.1581 | 910
2025-11-13 | 105783.3522 | 41565.94 | 135192.75 | 35261.1174 | 0 | 35261.1174 | 40655.94 | 35261.1174 | 910
2025-11-14 | 106312.8935 | 41565.94 | 136811.125 | 35437.6312 | 0 | 35437.6312 | 40655.94 | 35437.6312 | 910
2025-11-15 | 106842.4347 | 41621.83 | 136811.125 | 35614.1449 | 0 | 35614.1449 | 40711.83 | 35614.1449 | 910
2025-11-16 | 107371.976 | 41621.83 | 136811.125 | 35790.6587 | 0 | 35790.6587 | 40711.83 | 35790.6587 | 910
2025-11-17 | 107901.5173 | 41621.83 | 137515.425 | 35967.1724 | 0 | 35967.1724 | 40711.83 | 35967.1724 | 910
2025-11-18 | 108431.0586 | 41621.83 | 138219.725 | 36143.6862 | 0 | 36143.6862 | 40711.83 | 36143.6862 | 910
2025-11-19 | 108960.5999 | 41621.83 | 138924.025 | 36320.2 | 0 | 36320.2 | 40711.83 | 36320.2 | 910
2025-11-20 | 109490.1412 | 41621.83 | 139628.325 | 36496.7137 | 0 | 36496.7137 | 40711.83 | 36496.7137 | 910
2025-11-21 | 110019.6824 | 41621.83 | 140332.625 | 36673.2275 | 0 | 36673.2275 | 40711.83 | 36673.2275 | 910
2025-11-22 | 110549.2237 | 41621.83 | 140332.625 | 36849.7412 | 0 | 36849.7412 | 40711.83 | 36849.7412 | 910
2025-11-23 | 111078.765 | 41621.83 | 140332.625 | 37026.255 | 0 | 37026.255 | 40711.83 | 37026.255 | 910
2025-11-24 | 111608.3063 | 41621.83 | 141144.85 | 37202.7688 | 0 | 37202.7688 | 40711.83 | 37202.7688 | 910
2025-11-25 | 112137.8476 | 41621.83 | 141957.075 | 37379.2825 | 0 | 37379.2825 | 40711.83 | 37379.2825 | 910
2025-11-26 | 112667.3889 | 41621.83 | 142769.3 | 37555.7963 | 0 | 37555.7963 | 40711.83 | 37555.7963 | 910
2025-11-27 | 113196.9302 | 41621.83 | 143581.525 | 37732.3101 | 0 | 37732.3101 | 40711.83 | 37732.3101 | 910
2025-11-28 | 113726.4714 | 41621.83 | 144393.75 | 37908.8238 | 0 | 37908.8238 | 40711.83 | 37908.8238 | 910
2025-11-29 | 114256.0127 | 41621.83 | 144393.75 | 38085.3376 | 0 | 38085.3376 | 40711.83 | 38085.3376 | 910
2025-11-30 | 114785.554 | 41621.83 | 144393.75 | 38261.8513 | 0 | 38261.8513 | 40711.83 | 38261.8513 | 910
2025-12-01 | 115315.0953 | 41621.83 | 145486.9 | 38438.3651 | 0 | 38438.3651 | 40711.83 | 38438.3651 | 910
2025-12-02 | 115844.6366 | 41805.51 | 146580.05 | 38614.8789 | 0 | 38614.8789 | 40895.51 | 38614.8789 | 910
2025-12-03 | 116374.1779 | 41805.51 | 147673.2 | 38791.3926 | 0 | 38791.3926 | 40895.51 | 38791.3926 | 910
2025-12-04 | 116903.7191 | 41805.51 | 148766.35 | 38967.9064 | 0 | 38967.9064 | 40895.51 | 38967.9064 | 910
2025-12-05 | 117433.2604 | 42136.79 | 149859.5 | 39144.4201 | 0 | 39144.4201 | 41226.79 | 39144.4201 | 910
2025-12-06 | 117962.8017 | 42136.79 | 149859.5 | 39320.9339 | 0 | 39320.9339 | 41226.79 | 39320.9339 | 910
2025-12-07 | 118492.343 | 42136.79 | 149859.5 | 39497.4477 | 0 | 39497.4477 | 41226.79 | 39497.4477 | 910
2025-12-08 | 119021.8843 | 42136.79 | 151023.125 | 39673.9614 | 0 | 39673.9614 | 41226.79 | 39673.9614 | 910
2025-12-09 | 119551.4256 | 42136.79 | 152186.75 | 39850.4752 | 0 | 39850.4752 | 41226.79 | 39850.4752 | 910
2025-12-10 | 120080.9669 | 42136.79 | 153350.375 | 40026.989 | 0 | 40026.989 | 41226.79 | 40026.989 | 910
2025-12-11 | 120610.5081 | 42136.79 | 154514 | 40203.5027 | 0 | 40203.5027 | 41226.79 | 40203.5027 | 910
2025-12-12 | 121140.0494 | 42459.31 | 155677.625 | 40380.0165 | 0 | 40380.0165 | 41549.31 | 40380.0165 | 910
2025-12-13 | 121669.5907 | 42459.31 | 155677.625 | 40556.5302 | 0 | 40556.5302 | 41549.31 | 40556.5302 | 910
2025-12-14 | 122199.132 | 42459.31 | 155677.625 | 40733.044 | 0 | 40733.044 | 41549.31 | 40733.044 | 910
2025-12-15 | 122728.6733 | 42459.31 | 156841.25 | 40909.5578 | 0 | 40909.5578 | 41549.31 | 40909.5578 | 910
2025-12-16 | 123258.2146 | 42459.31 | 158004.875 | 41086.0715 | 0 | 41086.0715 | 41549.31 | 41086.0715 | 910
2025-12-17 | 123787.7558 | 42459.31 | 159168.5 | 41262.5853 | 0 | 41262.5853 | 41549.31 | 41262.5853 | 910
2025-12-18 | 124317.2971 | 42459.31 | 160332.125 | 41439.099 | 0 | 41439.099 | 41549.31 | 41439.099 | 910
2025-12-19 | 124846.8384 | 42459.31 | 161495.75 | 41615.6128 | 0 | 41615.6128 | 41549.31 | 41615.6128 | 910
2025-12-20 | 125376.3797 | 42459.31 | 161495.75 | 41792.1266 | 0 | 41792.1266 | 41549.31 | 41792.1266 | 910
2025-12-21 | 125905.921 | 42459.31 | 161495.75 | 41968.6403 | 0 | 41968.6403 | 41549.31 | 41968.6403 | 910
2025-12-22 | 126435.4623 | 42551.01 | 161495.75 | 42145.1541 | 0 | 42145.1541 | 41641.01 | 42145.1541 | 910
2025-12-23 | 126965.0036 | 42551.01 | 161495.75 | 42321.6679 | 0 | 42321.6679 | 41641.01 | 42321.6679 | 910
2025-12-24 | 127494.5448 | 42551.01 | 161495.75 | 42498.1816 | 0 | 42498.1816 | 41641.01 | 42498.1816 | 910
2025-12-25 | 128024.0861 | 42551.01 | 161495.75 | 42674.6954 | 0 | 42674.6954 | 41641.01 | 42674.6954 | 910
2025-12-26 | 128553.6274 | 42551.01 | 161495.75 | 42851.2091 | 0 | 42851.2091 | 41641.01 | 42851.2091 | 910
2025-12-27 | 129083.1687 | 42551.01 | 161495.75 | 43027.7229 | 0 | 43027.7229 | 41641.01 | 43027.7229 | 910
2025-12-28 | 129612.71 | 42551.01 | 161495.75 | 43204.2367 | 0 | 43204.2367 | 41641.01 | 43204.2367 | 910
2025-12-29 | 130142.2513 | 43677.35 | 162393.1 | 43380.7504 | 0 | 43380.7504 | 42767.35 | 43380.7504 | 910
2025-12-30 | 130671.7925 | 43677.35 | 163290.45 | 43557.2642 | 0 | 43557.2642 | 42767.35 | 43557.2642 | 910
2025-12-31 | 131201.3338 | 43677.35 | 164187.8 | 43733.7779 | 0 | 43733.7779 | 42767.35 | 43733.7779 | 910
2026-01-01 | 131730.8751 | 43677.35 | 165085.15 | 43910.2917 | 0 | 43910.2917 | 42767.35 | 43910.2917 | 910
2026-01-02 | 132260.4164 | 43677.35 | 165982.5 | 44086.8055 | 0 | 44086.8055 | 42767.35 | 44086.8055 | 910
2026-01-03 | 132789.9577 | 43677.35 | 165982.5 | 44263.3192 | 0 | 44263.3192 | 42767.35 | 44263.3192 | 910
2026-01-04 | 133319.499 | 43677.35 | 165982.5 | 44439.833 | 0 | 44439.833 | 42767.35 | 44439.833 | 910
2026-01-05 | 133849.0402 | 43677.35 | 167054.925 | 44616.3467 | 0 | 44616.3467 | 42767.35 | 44616.3467 | 910
2026-01-06 | 134378.5815 | 43677.35 | 168127.35 | 44792.8605 | 0 | 44792.8605 | 42767.35 | 44792.8605 | 910
2026-01-07 | 134908.1228 | 45840.09 | 169199.775 | 44969.3743 | 0 | 44969.3743 | 44930.09 | 44969.3743 | 910
2026-01-08 | 135437.6641 | 45840.09 | 170272.2 | 45145.888 | 0 | 45145.888 | 44930.09 | 45145.888 | 910
2026-01-09 | 135967.2054 | 45840.09 | 171344.625 | 45322.4018 | 0 | 45322.4018 | 44930.09 | 45322.4018 | 910
2026-01-10 | 136496.7467 | 45840.09 | 171344.625 | 45498.9156 | 0 | 45498.9156 | 44930.09 | 45498.9156 | 910
2026-01-11 | 137026.288 | 45840.09 | 171344.625 | 45675.4293 | 0 | 45675.4293 | 44930.09 | 45675.4293 | 910
2026-01-12 | 137555.8292 | 45840.09 | 172044.925 | 45851.9431 | 0 | 45851.9431 | 44930.09 | 45851.9431 | 910
2026-01-13 | 138085.3705 | 45840.09 | 172745.225 | 46028.4568 | 0 | 46028.4568 | 44930.09 | 46028.4568 | 910
2026-01-14 | 138614.9118 | 46132.49 | 173445.525 | 46204.9706 | 0 | 46204.9706 | 45222.49 | 46204.9706 | 910
2026-01-15 | 139144.4531 | 46132.49 | 174145.825 | 46381.4844 | 0 | 46381.4844 | 45222.49 | 46381.4844 | 910
2026-01-16 | 139673.9944 | 46132.49 | 174846.125 | 46557.9981 | 0 | 46557.9981 | 45222.49 | 46557.9981 | 910
2026-01-17 | 140203.5357 | 46132.49 | 174846.125 | 46734.5119 | 0 | 46734.5119 | 45222.49 | 46734.5119 | 910
2026-01-18 | 140733.0769 | 46132.49 | 174846.125 | 46911.0256 | 0 | 46911.0256 | 45222.49 | 46911.0256 | 910
2026-01-19 | 141262.6182 | 47202.82 | 175873.425 | 47087.5394 | 0 | 47087.5394 | 46292.82 | 47087.5394 | 910
2026-01-20 | 141792.1595 | 47202.82 | 176900.725 | 47264.0532 | 0 | 47264.0532 | 46292.82 | 47264.0532 | 910
2026-01-21 | 142321.7008 | 47202.82 | 177928.025 | 47440.5669 | 0 | 47440.5669 | 46292.82 | 47440.5669 | 910
2026-01-22 | 142851.2421 | 48609.68 | 178955.325 | 47617.0807 | 0 | 47617.0807 | 47699.68 | 47617.0807 | 910
2026-01-23 | 143380.7834 | 48609.68 | 179982.625 | 47793.5945 | 0 | 47793.5945 | 47699.68 | 47793.5945 | 910
2026-01-24 | 143910.3247 | 48609.68 | 179982.625 | 47970.1082 | 0 | 47970.1082 | 47699.68 | 47970.1082 | 910
2026-01-25 | 144439.8659 | 48609.68 | 179982.625 | 48146.622 | 0 | 48146.622 | 47699.68 | 48146.622 | 910
2026-01-26 | 144969.4072 | 50822.07 | 181735.85 | 48323.1357 | 0 | 48323.1357 | 49912.07 | 48323.1357 | 910
2026-01-27 | 145498.9485 | 50822.07 | 183489.075 | 48499.6495 | 0 | 48499.6495 | 49912.07 | 48499.6495 | 910
2026-01-28 | 146028.4898 | 50822.07 | 185242.3 | 48676.1633 | 0 | 48676.1633 | 49912.07 | 48676.1633 | 910
2026-01-29 | 146558.0311 | 51413.96 | 186995.525 | 48852.677 | 0 | 48852.677 | 50503.96 | 48852.677 | 910
2026-01-30 | 147087.5724 | 53338.96 | 188748.75 | 49029.1908 | 0 | 49029.1908 | 52428.96 | 49029.1908 | 910
2026-01-31 | 147617.1136 | 53338.96 | 188748.75 | 49205.7045 | 0 | 49205.7045 | 52428.96 | 49205.7045 | 910
2026-02-01 | 148146.6549 | 53338.96 | 188748.75 | 49382.2183 | 0 | 49382.2183 | 52428.96 | 49382.2183 | 910
2026-02-02 | 148676.1962 | 53338.96 | 189828.5 | 49558.7321 | 0 | 49558.7321 | 52428.96 | 49558.7321 | 910
2026-02-03 | 149205.7375 | 53734.94 | 190908.25 | 49735.2458 | 0 | 49735.2458 | 52824.94 | 49735.2458 | 910
2026-02-04 | 149735.2788 | 54596.83 | 191988 | 49911.7596 | 0 | 49911.7596 | 53686.83 | 49911.7596 | 910
2026-02-05 | 150264.8201 | 54740.18 | 193067.75 | 50088.2734 | 0 | 50088.2734 | 53830.18 | 50088.2734 | 910
2026-02-06 | 150794.3613 | 56033.98 | 194147.5 | 50264.7871 | 0 | 50264.7871 | 55123.98 | 50264.7871 | 910
2026-02-07 | 151323.9026 | 56033.98 | 194147.5 | 50441.3009 | 0 | 50441.3009 | 55123.98 | 50441.3009 | 910
2026-02-08 | 151853.4439 | 56033.98 | 194147.5 | 50617.8146 | 0 | 50617.8146 | 55123.98 | 50617.8146 | 910
2026-02-09 | 152382.9852 | 56162 | 195428.55 | 50794.3284 | 0 | 50794.3284 | 55252 | 50794.3284 | 910
2026-02-10 | 152912.5265 | 56162 | 196709.6 | 50970.8422 | 0 | 50970.8422 | 55252 | 50970.8422 | 910
2026-02-11 | 153442.0678 | 56448.1 | 197990.65 | 51147.3559 | 0 | 51147.3559 | 55538.1 | 51147.3559 | 910
2026-02-12 | 153971.6091 | 56448.1 | 199271.7 | 51323.8697 | 0 | 51323.8697 | 55538.1 | 51323.8697 | 910
2026-02-13 | 154501.1503 | 56448.1 | 200552.75 | 51500.3834 | 0 | 51500.3834 | 55538.1 | 51500.3834 | 910
2026-02-14 | 155030.6916 | 56448.1 | 200552.75 | 51676.8972 | 0 | 51676.8972 | 55538.1 | 51676.8972 | 910
2026-02-15 | 155560.2329 | 56448.1 | 200552.75 | 51853.411 | 0 | 51853.411 | 55538.1 | 51853.411 | 910
2026-02-16 | 156089.7742 | 56448.1 | 201679.45 | 52029.9247 | 0 | 52029.9247 | 55538.1 | 52029.9247 | 910
2026-02-17 | 156619.3155 | 56448.1 | 202806.15 | 52206.4385 | 0 | 52206.4385 | 55538.1 | 52206.4385 | 910
2026-02-18 | 157148.8568 | 56448.1 | 203932.85 | 52382.9523 | 0 | 52382.9523 | 55538.1 | 52382.9523 | 910
2026-02-19 | 157678.398 | 56448.1 | 205059.55 | 52559.466 | 0 | 52559.466 | 55538.1 | 52559.466 | 910
2026-02-20 | 158207.9393 | 57469.49 | 206186.25 | 52735.9798 | 0 | 52735.9798 | 56559.49 | 52735.9798 | 910
2026-02-21 | 158737.4806 | 57469.49 | 206186.25 | 52912.4935 | 0 | 52912.4935 | 56559.49 | 52912.4935 | 910
2026-02-22 | 159267.0219 | 57469.49 | 206186.25 | 53089.0073 | 0 | 53089.0073 | 56559.49 | 53089.0073 | 910
2026-02-23 | 159796.5632 | 57469.49 | 207266 | 53265.5211 | 0 | 53265.5211 | 56559.49 | 53265.5211 | 910
2026-02-24 | 160326.1045 | 57469.49 | 208345.75 | 53442.0348 | 0 | 53442.0348 | 56559.49 | 53442.0348 | 910
2026-02-25 | 160855.6458 | 57469.49 | 209425.5 | 53618.5486 | 0 | 53618.5486 | 56559.49 | 53618.5486 | 910
2026-02-26 | 161385.187 | 58650.85 | 210505.25 | 53795.0623 | 0 | 53795.0623 | 57740.85 | 53795.0623 | 910
2026-02-27 | 161914.7283 | 58650.85 | 211585 | 53971.5761 | 0 | 53971.5761 | 57740.85 | 53971.5761 | 910
2026-02-28 | 162444.2696 | 58650.85 | 211585 | 54148.0899 | 0 | 54148.0899 | 57740.85 | 54148.0899 | 910
2026-03-01 | 162973.8109 | 58650.85 | 211585 | 54324.6036 | 0 | 54324.6036 | 57740.85 | 54324.6036 | 910
2026-03-02 | 163503.3522 | 58650.85 | 211980.75 | 54501.1174 | 0 | 54501.1174 | 57740.85 | 54501.1174 | 910
2026-03-03 | 163533.1078 | 58650.85 | 212376.5 | 54511.0359 | 0 | 54511.0359 | 57740.85 | 54511.0359 | 910
2026-03-04 | 163562.8635 | 58650.85 | 212772.25 | 54520.9545 | 0 | 54520.9545 | 57740.85 | 54520.9545 | 910
2026-03-05 | 163592.6191 | 58650.85 | 213168 | 54530.873 | 0 | 54530.873 | 57740.85 | 54530.873 | 910
2026-03-06 | 163622.3747 | 58650.85 | 213563.75 | 54540.7916 | 0 | 54540.7916 | 57740.85 | 54540.7916 | 910
2026-03-07 | 163652.1304 | 58650.85 | 213563.75 | 54550.7101 | 0 | 54550.7101 | 57740.85 | 54550.7101 | 910
2026-03-08 | 163681.886 | 58650.85 | 213563.75 | 54560.6287 | 0 | 54560.6287 | 57740.85 | 54560.6287 | 910
2026-03-09 | 163711.6416 | 58650.85 | 213761.625 | 54570.5472 | 0 | 54570.5472 | 57740.85 | 54570.5472 | 910
2026-03-10 | 163741.3973 | 58650.85 | 213959.5 | 54580.4658 | 0 | 54580.4658 | 57740.85 | 54580.4658 | 910
2026-03-11 | 163771.1529 | 58650.85 | 214157.375 | 54590.3843 | 0 | 54590.3843 | 57740.85 | 54590.3843 | 910
2026-03-12 | 163800.9086 | 59656.29 | 214355.25 | 54600.3029 | 0 | 54600.3029 | 58746.29 | 54600.3029 | 910
2026-03-13 | 163830.6642 | 59656.29 | 214553.125 | 54610.2214 | 0 | 54610.2214 | 58746.29 | 54610.2214 | 910
2026-03-14 | 163860.4198 | 59656.29 | 214553.125 | 54620.1399 | 0 | 54620.1399 | 58746.29 | 54620.1399 | 910
2026-03-15 | 163890.1755 | 59656.29 | 214553.125 | 54630.0585 | 0 | 54630.0585 | 58746.29 | 54630.0585 | 910
2026-03-16 | 163919.9311 | 59656.29 | 215408.95 | 54639.977 | 0 | 54639.977 | 58746.29 | 54639.977 | 910
2026-03-17 | 163949.6868 | 59656.29 | 216264.775 | 54649.8956 | 0 | 54649.8956 | 58746.29 | 54649.8956 | 910
2026-03-18 | 163979.4424 | 59656.29 | 217120.6 | 54659.8141 | 0 | 54659.8141 | 58746.29 | 54659.8141 | 910
2026-03-19 | 164009.198 | 59656.29 | 217976.425 | 54669.7327 | 0 | 54669.7327 | 58746.29 | 54669.7327 | 910
2026-03-20 | 164038.9537 | 59656.29 | 218832.25 | 54679.6512 | 0 | 54679.6512 | 58746.29 | 54679.6512 | 910
2026-03-21 | 164068.7093 | 59656.29 | 218832.25 | 54689.5698 | 0 | 54689.5698 | 58746.29 | 54689.5698 | 910
2026-03-22 | 164098.465 | 59656.29 | 218832.25 | 54699.4883 | 0 | 54699.4883 | 58746.29 | 54699.4883 | 910
2026-03-23 | 164128.2206 |  |  | 54709.4069 |  | 54709.4069 |  | 54709.4069
2026-03-24 | 164157.9762 |  |  | 54719.3254 |  | 54719.3254 |  | 54719.3254
2026-03-25 | 164187.7319 |  |  | 54729.244 |  | 54729.244 |  | 54729.244
2026-03-26 | 164217.4875 |  |  | 54739.1625 |  | 54739.1625 |  | 54739.1625
2026-03-27 | 164247.2432 |  |  | 54749.0811 |  | 54749.0811 |  | 54749.0811
2026-03-28 | 164276.9988 |  |  | 54758.9996 |  | 54758.9996 |  | 54758.9996
2026-03-29 | 164306.7544 |  |  | 54768.9181 |  | 54768.9181 |  | 54768.9181
2026-03-30 | 164336.5101 |  |  | 54778.8367 |  | 54778.8367 |  | 54778.8367
2026-03-31 | 164366.2657 |  |  | 54788.7552 |  | 54788.7552 |  | 54788.7552
2026-04-01 | 164396.0213 |  |  | 54798.6738 |  | 54798.6738 |  | 54798.6738
2026-04-02 | 164425.777 |  |  | 54808.5923 |  | 54808.5923 |  | 54808.5923
2026-04-03 | 164455.5326 |  |  | 54818.5109 |  | 54818.5109 |  | 54818.5109
2026-04-04 | 164485.2883 |  |  | 54828.4294 |  | 54828.4294 |  | 54828.4294
2026-04-05 | 164515.0439 |  |  | 54838.348 |  | 54838.348 |  | 54838.348
2026-04-06 | 164544.7995 |  |  | 54848.2665 |  | 54848.2665 |  | 54848.2665
2026-04-07 | 164574.5552 |  |  | 54858.1851 |  | 54858.1851 |  | 54858.1851
2026-04-08 | 164604.3108 |  |  | 54868.1036 |  | 54868.1036 |  | 54868.1036
2026-04-09 | 164634.0665 |  |  | 54878.0222 |  | 54878.0222 |  | 54878.0222
2026-04-10 | 164663.8221 |  |  | 54887.9407 |  | 54887.9407 |  | 54887.9407
2026-04-11 | 164693.5777 |  |  | 54897.8592 |  | 54897.8592 |  | 54897.8592
2026-04-12 | 164723.3334 |  |  | 54907.7778 |  | 54907.7778 |  | 54907.7778
2026-04-13 | 164753.089 |  |  | 54917.6963 |  | 54917.6963 |  | 54917.6963
2026-04-14 | 164782.8447 |  |  | 54927.6149 |  | 54927.6149 |  | 54927.6149
2026-04-15 | 164812.6003 |  |  | 54937.5334 |  | 54937.5334 |  | 54937.5334
2026-04-16 | 164842.3559 |  |  | 54947.452 |  | 54947.452 |  | 54947.452
2026-04-17 | 164872.1116 |  |  | 54957.3705 |  | 54957.3705 |  | 54957.3705
2026-04-18 | 164901.8672 |  |  | 54967.2891 |  | 54967.2891 |  | 54967.2891
2026-04-19 | 164931.6229 |  |  | 54977.2076 |  | 54977.2076 |  | 54977.2076
2026-04-20 | 164961.3785 |  |  | 54987.1262 |  | 54987.1262 |  | 54987.1262
2026-04-21 | 164991.1341 |  |  | 54997.0447 |  | 54997.0447 |  | 54997.0447
2026-04-22 | 165020.8898 |  |  | 55006.9633 |  | 55006.9633 |  | 55006.9633
2026-04-23 | 165050.6454 |  |  | 55016.8818 |  | 55016.8818 |  | 55016.8818
2026-04-24 | 165080.401 |  |  | 55026.8003 |  | 55026.8003 |  | 55026.8003
2026-04-25 | 165110.1567 |  |  | 55036.7189 |  | 55036.7189 |  | 55036.7189
2026-04-26 | 165139.9123 |  |  | 55046.6374 |  | 55046.6374 |  | 55046.6374
2026-04-27 | 165169.668 |  |  | 55056.556 |  | 55056.556 |  | 55056.556
2026-04-28 | 165199.4236 |  |  | 55066.4745 |  | 55066.4745 |  | 55066.4745
2026-04-29 | 165229.1792 |  |  | 55076.3931 |  | 55076.3931 |  | 55076.3931
2026-04-30 | 165258.9349 |  |  | 55086.3116 |  | 55086.3116 |  | 55086.3116
2026-05-01 | 165288.6905 |  |  | 55096.2302 |  | 55096.2302 |  | 55096.2302
2026-05-02 | 165318.4462 |  |  | 55106.1487 |  | 55106.1487 |  | 55106.1487
2026-05-03 | 165348.2018 |  |  | 55116.0673 |  | 55116.0673 |  | 55116.0673
2026-05-04 | 165377.9574 |  |  | 55125.9858 |  | 55125.9858 |  | 55125.9858
2026-05-05 | 165407.7131 |  |  | 55135.9044 |  | 55135.9044 |  | 55135.9044
2026-05-06 | 165437.4687 |  |  | 55145.8229 |  | 55145.8229 |  | 55145.8229
2026-05-07 | 165467.2244 |  |  | 55155.7415 |  | 55155.7415 |  | 55155.7415
2026-05-08 | 165496.98 |  |  | 55165.66 |  | 55165.66 |  | 55165.66
2026-05-09 | 165526.7356 |  |  | 55175.5785 |  | 55175.5785 |  | 55175.5785
2026-05-10 | 165556.4913 |  |  | 55185.4971 |  | 55185.4971 |  | 55185.4971
2026-05-11 | 165586.2469 |  |  | 55195.4156 |  | 55195.4156 |  | 55195.4156
2026-05-12 | 165616.0025 |  |  | 55205.3342 |  | 55205.3342 |  | 55205.3342
2026-05-13 | 165645.7582 |  |  | 55215.2527 |  | 55215.2527 |  | 55215.2527
2026-05-14 | 165675.5138 |  |  | 55225.1713 |  | 55225.1713 |  | 55225.1713
2026-05-15 | 165705.2695 |  |  | 55235.0898 |  | 55235.0898 |  | 55235.0898
2026-05-16 | 165735.0251 |  |  | 55245.0084 |  | 55245.0084 |  | 55245.0084
2026-05-17 | 165764.7807 |  |  | 55254.9269 |  | 55254.9269 |  | 55254.9269
2026-05-18 | 165794.5364 |  |  | 55264.8455 |  | 55264.8455 |  | 55264.8455
2026-05-19 | 165824.292 |  |  | 55274.764 |  | 55274.764 |  | 55274.764
2026-05-20 | 165854.0477 |  |  | 55284.6826 |  | 55284.6826 |  | 55284.6826
2026-05-21 | 165883.8033 |  |  | 55294.6011 |  | 55294.6011 |  | 55294.6011
2026-05-22 | 165913.5589 |  |  | 55304.5196 |  | 55304.5196 |  | 55304.5196
2026-05-23 | 165943.3146 |  |  | 55314.4382 |  | 55314.4382 |  | 55314.4382
2026-05-24 | 165973.0702 |  |  | 55324.3567 |  | 55324.3567 |  | 55324.3567
2026-05-25 | 166002.8259 |  |  | 55334.2753 |  | 55334.2753 |  | 55334.2753
2026-05-26 | 166032.5815 |  |  | 55344.1938 |  | 55344.1938 |  | 55344.1938
2026-05-27 | 166062.3371 |  |  | 55354.1124 |  | 55354.1124 |  | 55354.1124
2026-05-28 | 166092.0928 |  |  | 55364.0309 |  | 55364.0309 |  | 55364.0309
2026-05-29 | 166121.8484 |  |  | 55373.9495 |  | 55373.9495 |  | 55373.9495
2026-05-30 | 166151.6041 |  |  | 55383.868 |  | 55383.868 |  | 55383.868
2026-05-31 | 166181.3597 |  |  | 55393.7866 |  | 55393.7866 |  | 55393.7866
2026-06-01 | 166211.1153 |  |  | 55403.7051 |  | 55403.7051 |  | 55403.7051
2026-06-02 | 166240.871 |  |  | 55413.6237 |  | 55413.6237 |  | 55413.6237
2026-06-03 | 166270.6266 |  |  | 55423.5422 |  | 55423.5422 |  | 55423.5422
2026-06-04 | 166300.3822 |  |  | 55433.4607 |  | 55433.4607 |  | 55433.4607
2026-06-05 | 166330.1379 |  |  | 55443.3793 |  | 55443.3793 |  | 55443.3793
2026-06-06 | 166359.8935 |  |  | 55453.2978 |  | 55453.2978 |  | 55453.2978
2026-06-07 | 166389.6492 |  |  | 55463.2164 |  | 55463.2164 |  | 55463.2164
2026-06-08 | 166419.4048 |  |  | 55473.1349 |  | 55473.1349 |  | 55473.1349
2026-06-09 | 166449.1604 |  |  | 55483.0535 |  | 55483.0535 |  | 55483.0535
2026-06-10 | 166478.9161 |  |  | 55492.972 |  | 55492.972 |  | 55492.972
2026-06-11 | 166508.6717 |  |  | 55502.8906 |  | 55502.8906 |  | 55502.8906
2026-06-12 | 166538.4274 |  |  | 55512.8091 |  | 55512.8091 |  | 55512.8091
2026-06-13 | 166568.183 |  |  | 55522.7277 |  | 55522.7277 |  | 55522.7277
2026-06-14 | 166597.9386 |  |  | 55532.6462 |  | 55532.6462 |  | 55532.6462
2026-06-15 | 166627.6943 |  |  | 55542.5648 |  | 55542.5648 |  | 55542.5648
2026-06-16 | 166657.4499 |  |  | 55552.4833 |  | 55552.4833 |  | 55552.4833
2026-06-17 | 166687.2056 |  |  | 55562.4019 |  | 55562.4019 |  | 55562.4019
2026-06-18 | 166716.9612 |  |  | 55572.3204 |  | 55572.3204 |  | 55572.3204
2026-06-19 | 166746.7168 |  |  | 55582.2389 |  | 55582.2389 |  | 55582.2389
2026-06-20 | 166776.4725 |  |  | 55592.1575 |  | 55592.1575 |  | 55592.1575
2026-06-21 | 166806.2281 |  |  | 55602.076 |  | 55602.076 |  | 55602.076
2026-06-22 | 166835.9838 |  |  | 55611.9946 |  | 55611.9946 |  | 55611.9946
2026-06-23 | 166865.7394 |  |  | 55621.9131 |  | 55621.9131 |  | 55621.9131
2026-06-24 | 166895.495 |  |  | 55631.8317 |  | 55631.8317 |  | 55631.8317
2026-06-25 | 166925.2507 |  |  | 55641.7502 |  | 55641.7502 |  | 55641.7502
2026-06-26 | 166955.0063 |  |  | 55651.6688 |  | 55651.6688 |  | 55651.6688
2026-06-27 | 166984.7619 |  |  | 55661.5873 |  | 55661.5873 |  | 55661.5873
2026-06-28 | 167014.5176 |  |  | 55671.5059 |  | 55671.5059 |  | 55671.5059
2026-06-29 | 167044.2732 |  |  | 55681.4244 |  | 55681.4244 |  | 55681.4244
2026-06-30 | 167074.0289 |  |  | 55691.343 |  | 55691.343 |  | 55691.343
2026-07-01 | 167103.7845 |  |  | 55701.2615 |  | 55701.2615 |  | 55701.2615
2026-07-02 | 167133.5401 |  |  | 55711.18 |  | 55711.18 |  | 55711.18
2026-07-03 | 167163.2958 |  |  | 55721.0986 |  | 55721.0986 |  | 55721.0986
2026-07-04 | 167193.0514 |  |  | 55731.0171 |  | 55731.0171 |  | 55731.0171
2026-07-05 | 167222.8071 |  |  | 55740.9357 |  | 55740.9357 |  | 55740.9357
2026-07-06 | 167252.5627 |  |  | 55750.8542 |  | 55750.8542 |  | 55750.8542
2026-07-07 | 167282.3183 |  |  | 55760.7728 |  | 55760.7728 |  | 55760.7728
2026-07-08 | 167312.074 |  |  | 55770.6913 |  | 55770.6913 |  | 55770.6913
2026-07-09 | 167341.8296 |  |  | 55780.6099 |  | 55780.6099 |  | 55780.6099
2026-07-10 | 167371.5853 |  |  | 55790.5284 |  | 55790.5284 |  | 55790.5284
2026-07-11 | 167401.3409 |  |  | 55800.447 |  | 55800.447 |  | 55800.447
2026-07-12 | 167431.0965 |  |  | 55810.3655 |  | 55810.3655 |  | 55810.3655
2026-07-13 | 167460.8522 |  |  | 55820.2841 |  | 55820.2841 |  | 55820.2841
2026-07-14 | 167490.6078 |  |  | 55830.2026 |  | 55830.2026 |  | 55830.2026
2026-07-15 | 167520.3635 |  |  | 55840.1212 |  | 55840.1212 |  | 55840.1212
2026-07-16 | 167550.1191 |  |  | 55850.0397 |  | 55850.0397 |  | 55850.0397
2026-07-17 | 167579.8747 |  |  | 55859.9582 |  | 55859.9582 |  | 55859.9582
2026-07-18 | 167609.6304 |  |  | 55869.8768 |  | 55869.8768 |  | 55869.8768
2026-07-19 | 167639.386 |  |  | 55879.7953 |  | 55879.7953 |  | 55879.7953
2026-07-20 | 167669.1416 |  |  | 55889.7139 |  | 55889.7139 |  | 55889.7139
2026-07-21 | 167698.8973 |  |  | 55899.6324 |  | 55899.6324 |  | 55899.6324
2026-07-22 | 167728.6529 |  |  | 55909.551 |  | 55909.551 |  | 55909.551
2026-07-23 | 167758.4086 |  |  | 55919.4695 |  | 55919.4695 |  | 55919.4695
2026-07-24 | 167788.1642 |  |  | 55929.3881 |  | 55929.3881 |  | 55929.3881
2026-07-25 | 167817.9198 |  |  | 55939.3066 |  | 55939.3066 |  | 55939.3066
2026-07-26 | 167847.6755 |  |  | 55949.2252 |  | 55949.2252 |  | 55949.2252
2026-07-27 | 167877.4311 |  |  | 55959.1437 |  | 55959.1437 |  | 55959.1437
2026-07-28 | 167907.1868 |  |  | 55969.0623 |  | 55969.0623 |  | 55969.0623
2026-07-29 | 167936.9424 |  |  | 55978.9808 |  | 55978.9808 |  | 55978.9808
2026-07-30 | 167966.698 |  |  | 55988.8993 |  | 55988.8993 |  | 55988.8993
2026-07-31 | 167996.4537 |  |  | 55998.8179 |  | 55998.8179 |  | 55998.8179
2026-08-01 | 168026.2093 |  |  | 56008.7364 |  | 56008.7364 |  | 56008.7364
2026-08-02 | 168055.965 |  |  | 56018.655 |  | 56018.655 |  | 56018.655
2026-08-03 | 168085.7206 |  |  | 56028.5735 |  | 56028.5735 |  | 56028.5735
2026-08-04 | 168115.4762 |  |  | 56038.4921 |  | 56038.4921 |  | 56038.4921
2026-08-05 | 168145.2319 |  |  | 56048.4106 |  | 56048.4106 |  | 56048.4106
2026-08-06 | 168174.9875 |  |  | 56058.3292 |  | 56058.3292 |  | 56058.3292
2026-08-07 | 168204.7432 |  |  | 56068.2477 |  | 56068.2477 |  | 56068.2477
2026-08-08 | 168234.4988 |  |  | 56078.1663 |  | 56078.1663 |  | 56078.1663
2026-08-09 | 168264.2544 |  |  | 56088.0848 |  | 56088.0848 |  | 56088.0848
2026-08-10 | 168294.0101 |  |  | 56098.0034 |  | 56098.0034 |  | 56098.0034
2026-08-11 | 168323.7657 |  |  | 56107.9219 |  | 56107.9219 |  | 56107.9219
2026-08-12 | 168353.5213 |  |  | 56117.8404 |  | 56117.8404 |  | 56117.8404
2026-08-13 | 168383.277 |  |  | 56127.759 |  | 56127.759 |  | 56127.759
2026-08-14 | 168413.0326 |  |  | 56137.6775 |  | 56137.6775 |  | 56137.6775
2026-08-15 | 168442.7883 |  |  | 56147.5961 |  | 56147.5961 |  | 56147.5961
2026-08-16 | 168472.5439 |  |  | 56157.5146 |  | 56157.5146 |  | 56157.5146
2026-08-17 | 168502.2995 |  |  | 56167.4332 |  | 56167.4332 |  | 56167.4332
2026-08-18 | 168532.0552 |  |  | 56177.3517 |  | 56177.3517 |  | 56177.3517
2026-08-19 | 168561.8108 |  |  | 56187.2703 |  | 56187.2703 |  | 56187.2703
2026-08-20 | 168591.5665 |  |  | 56197.1888 |  | 56197.1888 |  | 56197.1888
2026-08-21 | 168621.3221 |  |  | 56207.1074 |  | 56207.1074 |  | 56207.1074
2026-08-22 | 168651.0777 |  |  | 56217.0259 |  | 56217.0259 |  | 56217.0259
2026-08-23 | 168680.8334 |  |  | 56226.9445 |  | 56226.9445 |  | 56226.9445
2026-08-24 | 168710.589 |  |  | 56236.863 |  | 56236.863 |  | 56236.863
2026-08-25 | 168740.3447 |  |  | 56246.7816 |  | 56246.7816 |  | 56246.7816
2026-08-26 | 168770.1003 |  |  | 56256.7001 |  | 56256.7001 |  | 56256.7001
2026-08-27 | 168799.8559 |  |  | 56266.6186 |  | 56266.6186 |  | 56266.6186
2026-08-28 | 168829.6116 |  |  | 56276.5372 |  | 56276.5372 |  | 56276.5372
2026-08-29 | 168859.3672 |  |  | 56286.4557 |  | 56286.4557 |  | 56286.4557
2026-08-30 | 168889.1229 |  |  | 56296.3743 |  | 56296.3743 |  | 56296.3743
2026-08-31 | 168918.8785 |  |  | 56306.2928 |  | 56306.2928 |  | 56306.2928
2026-09-01 | 168948.6341 |  |  | 56316.2114 |  | 56316.2114 |  | 56316.2114
2026-09-02 | 168978.3898 |  |  | 56326.1299 |  | 56326.1299 |  | 56326.1299
2026-09-03 | 169008.1454 |  |  | 56336.0485 |  | 56336.0485 |  | 56336.0485
2026-09-04 | 169037.901 |  |  | 56345.967 |  | 56345.967 |  | 56345.967
2026-09-05 | 169067.6567 |  |  | 56355.8856 |  | 56355.8856 |  | 56355.8856
2026-09-06 | 169097.4123 |  |  | 56365.8041 |  | 56365.8041 |  | 56365.8041
2026-09-07 | 169127.168 |  |  | 56375.7227 |  | 56375.7227 |  | 56375.7227
2026-09-08 | 169156.9236 |  |  | 56385.6412 |  | 56385.6412 |  | 56385.6412
2026-09-09 | 169186.6792 |  |  | 56395.5597 |  | 56395.5597 |  | 56395.5597
2026-09-10 | 169216.4349 |  |  | 56405.4783 |  | 56405.4783 |  | 56405.4783
2026-09-11 | 169246.1905 |  |  | 56415.3968 |  | 56415.3968 |  | 56415.3968
2026-09-12 | 169275.9462 |  |  | 56425.3154 |  | 56425.3154 |  | 56425.3154
2026-09-13 | 169305.7018 |  |  | 56435.2339 |  | 56435.2339 |  | 56435.2339
2026-09-14 | 169335.4574 |  |  | 56445.1525 |  | 56445.1525 |  | 56445.1525
2026-09-15 | 169365.2131 |  |  | 56455.071 |  | 56455.071 |  | 56455.071
2026-09-16 | 169394.9687 |  |  | 56464.9896 |  | 56464.9896 |  | 56464.9896
2026-09-17 | 169424.7244 |  |  | 56474.9081 |  | 56474.9081 |  | 56474.9081
2026-09-18 | 169454.48 |  |  | 56484.8267 |  | 56484.8267 |  | 56484.8267
2026-09-19 | 169484.2356 |  |  | 56494.7452 |  | 56494.7452 |  | 56494.7452
2026-09-20 | 169513.9913 |  |  | 56504.6638 |  | 56504.6638 |  | 56504.6638
2026-09-21 | 169543.7469 |  |  | 56514.5823 |  | 56514.5823 |  | 56514.5823
2026-09-22 | 169573.5025 |  |  | 56524.5008 |  | 56524.5008 |  | 56524.5008
2026-09-23 | 169603.2582 |  |  | 56534.4194 |  | 56534.4194 |  | 56534.4194
2026-09-24 | 169633.0138 |  |  | 56544.3379 |  | 56544.3379 |  | 56544.3379
2026-09-25 | 169662.7695 |  |  | 56554.2565 |  | 56554.2565 |  | 56554.2565
2026-09-26 | 169692.5251 |  |  | 56564.175 |  | 56564.175 |  | 56564.175
2026-09-27 | 169722.2807 |  |  | 56574.0936 |  | 56574.0936 |  | 56574.0936
2026-09-28 | 169752.0364 |  |  | 56584.0121 |  | 56584.0121 |  | 56584.0121
2026-09-29 | 169781.792 |  |  | 56593.9307 |  | 56593.9307 |  | 56593.9307
2026-09-30 | 169811.5477 |  |  | 56603.8492 |  | 56603.8492 |  | 56603.8492
2026-10-01 | 169841.3033 |  |  | 56613.7678 |  | 56613.7678 |  | 56613.7678
2026-10-02 | 169871.0589 |  |  | 56623.6863 |  | 56623.6863 |  | 56623.6863
2026-10-03 | 169900.8146 |  |  | 56633.6049 |  | 56633.6049 |  | 56633.6049
2026-10-04 | 169930.5702 |  |  | 56643.5234 |  | 56643.5234 |  | 56643.5234
2026-10-05 | 169960.3259 |  |  | 56653.442 |  | 56653.442 |  | 56653.442
2026-10-06 | 169990.0815 |  |  | 56663.3605 |  | 56663.3605 |  | 56663.3605
2026-10-07 | 170019.8371 |  |  | 56673.279 |  | 56673.279 |  | 56673.279
2026-10-08 | 170049.5928 |  |  | 56683.1976 |  | 56683.1976 |  | 56683.1976
2026-10-09 | 170079.3484 |  |  | 56693.1161 |  | 56693.1161 |  | 56693.1161
2026-10-10 | 170109.1041 |  |  | 56703.0347 |  | 56703.0347 |  | 56703.0347
2026-10-11 | 170138.8597 |  |  | 56712.9532 |  | 56712.9532 |  | 56712.9532
2026-10-12 | 170168.6153 |  |  | 56722.8718 |  | 56722.8718 |  | 56722.8718
2026-10-13 | 170198.371 |  |  | 56732.7903 |  | 56732.7903 |  | 56732.7903
2026-10-14 | 170228.1266 |  |  | 56742.7089 |  | 56742.7089 |  | 56742.7089
2026-10-15 | 170257.8822 |  |  | 56752.6274 |  | 56752.6274 |  | 56752.6274
2026-10-16 | 170287.6379 |  |  | 56762.546 |  | 56762.546 |  | 56762.546
2026-10-17 | 170317.3935 |  |  | 56772.4645 |  | 56772.4645 |  | 56772.4645
2026-10-18 | 170347.1492 |  |  | 56782.3831 |  | 56782.3831 |  | 56782.3831
2026-10-19 | 170376.9048 |  |  | 56792.3016 |  | 56792.3016 |  | 56792.3016
2026-10-20 | 170406.6604 |  |  | 56802.2201 |  | 56802.2201 |  | 56802.2201
2026-10-21 | 170436.4161 |  |  | 56812.1387 |  | 56812.1387 |  | 56812.1387
2026-10-22 | 170466.1717 |  |  | 56822.0572 |  | 56822.0572 |  | 56822.0572
2026-10-23 | 170495.9274 |  |  | 56831.9758 |  | 56831.9758 |  | 56831.9758
2026-10-24 | 170525.683 |  |  | 56841.8943 |  | 56841.8943 |  | 56841.8943
2026-10-25 | 170555.4386 |  |  | 56851.8129 |  | 56851.8129 |  | 56851.8129
2026-10-26 | 170585.1943 |  |  | 56861.7314 |  | 56861.7314 |  | 56861.7314
2026-10-27 | 170614.9499 |  |  | 56871.65 |  | 56871.65 |  | 56871.65
2026-10-28 | 170644.7056 |  |  | 56881.5685 |  | 56881.5685 |  | 56881.5685
2026-10-29 | 170674.4612 |  |  | 56891.4871 |  | 56891.4871 |  | 56891.4871
2026-10-30 | 170704.2168 |  |  | 56901.4056 |  | 56901.4056 |  | 56901.4056
2026-10-31 | 170733.9725 |  |  | 56911.3242 |  | 56911.3242 |  | 56911.3242
2026-11-01 | 170763.7281 |  |  | 56921.2427 |  | 56921.2427 |  | 56921.2427
2026-11-02 | 170793.4838 |  |  | 56931.1613 |  | 56931.1613 |  | 56931.1613
2026-11-03 | 170823.2394 |  |  | 56941.0798 |  | 56941.0798 |  | 56941.0798
2026-11-04 | 170852.995 |  |  | 56950.9983 |  | 56950.9983 |  | 56950.9983
2026-11-05 | 170882.7507 |  |  | 56960.9169 |  | 56960.9169 |  | 56960.9169
2026-11-06 | 170912.5063 |  |  | 56970.8354 |  | 56970.8354 |  | 56970.8354
2026-11-07 | 170942.2619 |  |  | 56980.754 |  | 56980.754 |  | 56980.754
2026-11-08 | 170972.0176 |  |  | 56990.6725 |  | 56990.6725 |  | 56990.6725
2026-11-09 | 171001.7732 |  |  | 57000.5911 |  | 57000.5911 |  | 57000.5911
2026-11-10 | 171031.5289 |  |  | 57010.5096 |  | 57010.5096 |  | 57010.5096
2026-11-11 | 171061.2845 |  |  | 57020.4282 |  | 57020.4282 |  | 57020.4282
2026-11-12 | 171091.0401 |  |  | 57030.3467 |  | 57030.3467 |  | 57030.3467
2026-11-13 | 171120.7958 |  |  | 57040.2653 |  | 57040.2653 |  | 57040.2653
2026-11-14 | 171150.5514 |  |  | 57050.1838 |  | 57050.1838 |  | 57050.1838
2026-11-15 | 171180.3071 |  |  | 57060.1024 |  | 57060.1024 |  | 57060.1024
2026-11-16 | 171210.0627 |  |  | 57070.0209 |  | 57070.0209 |  | 57070.0209
2026-11-17 | 171239.8183 |  |  | 57079.9394 |  | 57079.9394 |  | 57079.9394
2026-11-18 | 171269.574 |  |  | 57089.858 |  | 57089.858 |  | 57089.858
2026-11-19 | 171299.3296 |  |  | 57099.7765 |  | 57099.7765 |  | 57099.7765
2026-11-20 | 171329.0853 |  |  | 57109.6951 |  | 57109.6951 |  | 57109.6951
2026-11-21 | 171358.8409 |  |  | 57119.6136 |  | 57119.6136 |  | 57119.6136
2026-11-22 | 171388.5965 |  |  | 57129.5322 |  | 57129.5322 |  | 57129.5322
2026-11-23 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-11-24 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-11-25 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-11-26 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-11-27 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-11-28 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-11-29 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-11-30 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-01 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-02 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-03 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-04 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-05 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-06 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-07 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-08 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-09 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-10 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-11 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-12 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-13 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-14 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-15 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-16 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-17 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-18 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-19 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-20 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-21 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-22 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-23 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-24 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-12-25 | 171418.3522 |  |  | 57139.4507 |  | 57139.4507 |  | 57139.4507

## Outsource (Direct Cost)
Date | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Actual Labor (Cumulative) | Planned 5006 · Drilling Expense (Cumulative) | Actual 5006 · Drilling Expense (Cumulative) | Planned 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Actual 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Planned 5115 · Rent - Equipment (direct) (Cumulative) | Actual 5115 · Rent - Equipment (direct) (Cumulative) | Planned 5116 · Rent - Storage (Direct) (Cumulative) | Actual 5116 · Rent - Storage (Direct) (Cumulative) | Planned 5120 · Outside services (Direct) (Cumulative) | Actual 5120 · Outside services (Direct) (Cumulative) | Planned 5121 · Freight & Shipping (Direct) (Cumulative) | Actual 5121 · Freight & Shipping (Direct) (Cumulative) | Planned 5124 · License and permits (Direct) (Cumulative) | Actual 5124 · License and permits (Direct) (Cumulative) | Planned 5132 · Internet fee (Direct) (Cumulative) | Actual 5132 · Internet fee (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 2253.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 3379.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 4506.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 5633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 5633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 5633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 5847.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 6061.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 6276.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 6490.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 6705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 6705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 6705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 7087.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 7469.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 7851.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 8233.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 0 | 8615.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 0 | 9212.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 0 | 9808.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 0 | 10405.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 0 | 11001.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 0 | 11598.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 0 | 11598.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 0 | 11598.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 0 | 11873.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 0 | 12148.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 0 | 12423.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 0 | 12698.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 0 | 12973.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 0 | 12973.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 0 | 12973.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 0 | 13523.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 0 | 14073.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 0 | 14622.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 0 | 15172.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 0 | 15722.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 0 | 15722.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 0 | 15722.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 0 | 15997.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 0 | 16272.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 321.9345 | 0 | 16547.6 | 40.2418 | 0 | 40.2418 | 0 | 40.2418 | 0 | 40.2418 | 0 | 40.2418 | 0 | 40.2418 | 0 | 40.2418 | 0 | 40.2418 | 0
2025-06-26 | 643.8691 | 0 | 16822.55 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0
2025-06-27 | 965.8036 | 0 | 17097.5 | 120.7255 | 0 | 120.7255 | 0 | 120.7255 | 0 | 120.7255 | 0 | 120.7255 | 0 | 120.7255 | 0 | 120.7255 | 0 | 120.7255 | 0
2025-06-28 | 1287.7382 | 0 | 17097.5 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0
2025-06-29 | 1609.6727 | 0 | 17097.5 | 201.2091 | 0 | 201.2091 | 0 | 201.2091 | 0 | 201.2091 | 0 | 201.2091 | 0 | 201.2091 | 0 | 201.2091 | 0 | 201.2091 | 0
2025-06-30 | 1931.6072 | 0 | 17714.4 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0
2025-07-01 | 2253.5418 | 0 | 18331.3 | 281.6927 | 0 | 281.6927 | 0 | 281.6927 | 0 | 281.6927 | 0 | 281.6927 | 0 | 281.6927 | 0 | 281.6927 | 0 | 281.6927 | 0
2025-07-02 | 2575.4763 | 0 | 18948.2 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0
2025-07-03 | 2897.4108 | 0 | 19565.1 | 362.1764 | 0 | 362.1764 | 0 | 362.1764 | 0 | 362.1764 | 0 | 362.1764 | 0 | 362.1764 | 0 | 362.1764 | 0 | 362.1764 | 0
2025-07-04 | 3219.3454 | 0 | 20182 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0
2025-07-05 | 3541.2799 | 0 | 20182 | 442.66 | 0 | 442.66 | 0 | 442.66 | 0 | 442.66 | 0 | 442.66 | 0 | 442.66 | 0 | 442.66 | 0 | 442.66 | 0
2025-07-06 | 3863.2145 | 0 | 20182 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0
2025-07-07 | 4185.149 | 0 | 20835.625 | 523.1436 | 0 | 523.1436 | 0 | 523.1436 | 0 | 523.1436 | 0 | 523.1436 | 0 | 523.1436 | 0 | 523.1436 | 0 | 523.1436 | 0
2025-07-08 | 4507.0835 | 0 | 21489.25 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0
2025-07-09 | 4829.0181 | 0 | 22142.875 | 603.6273 | 0 | 603.6273 | 0 | 603.6273 | 0 | 603.6273 | 0 | 603.6273 | 0 | 603.6273 | 0 | 603.6273 | 0 | 603.6273 | 0
2025-07-10 | 5150.9526 | 0 | 22796.5 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0
2025-07-11 | 5472.8872 | 0 | 23450.125 | 684.1109 | 0 | 684.1109 | 0 | 684.1109 | 0 | 684.1109 | 0 | 684.1109 | 0 | 684.1109 | 0 | 684.1109 | 0 | 684.1109 | 0
2025-07-12 | 5794.8217 | 0 | 23450.125 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0
2025-07-13 | 6116.7562 | 0 | 23450.125 | 764.5945 | 0 | 764.5945 | 0 | 764.5945 | 0 | 764.5945 | 0 | 764.5945 | 0 | 764.5945 | 0 | 764.5945 | 0 | 764.5945 | 0
2025-07-14 | 6438.6908 | 0 | 24210.95 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0
2025-07-15 | 6760.6253 | 0 | 24971.775 | 845.0782 | 0 | 845.0782 | 0 | 845.0782 | 0 | 845.0782 | 0 | 845.0782 | 0 | 845.0782 | 0 | 845.0782 | 0 | 845.0782 | 0
2025-07-16 | 7082.5598 | 0 | 25732.6 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0
2025-07-17 | 7404.4944 | 0 | 26493.425 | 925.5618 | 0 | 925.5618 | 0 | 925.5618 | 0 | 925.5618 | 0 | 925.5618 | 0 | 925.5618 | 0 | 925.5618 | 0 | 925.5618 | 0
2025-07-18 | 7726.4289 | 0 | 27254.25 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0
2025-07-19 | 8048.3635 | 0 | 27254.25 | 1006.0454 | 0 | 1006.0454 | 0 | 1006.0454 | 0 | 1006.0454 | 0 | 1006.0454 | 0 | 1006.0454 | 0 | 1006.0454 | 0 | 1006.0454 | 0
2025-07-20 | 8370.298 | 0 | 27254.25 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0
2025-07-21 | 8692.2325 | 0 | 27907.875 | 1086.5291 | 0 | 1086.5291 | 0 | 1086.5291 | 0 | 1086.5291 | 0 | 1086.5291 | 0 | 1086.5291 | 0 | 1086.5291 | 0 | 1086.5291 | 0
2025-07-22 | 9014.1671 | 500 | 28561.5 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 500 | 1126.7709 | 0
2025-07-23 | 9336.1016 | 500 | 29215.125 | 1167.0127 | 0 | 1167.0127 | 0 | 1167.0127 | 0 | 1167.0127 | 0 | 1167.0127 | 0 | 1167.0127 | 0 | 1167.0127 | 500 | 1167.0127 | 0
2025-07-24 | 9658.0362 | 500 | 29868.75 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 500 | 1207.2545 | 0
2025-07-25 | 9979.9707 | 500 | 30522.375 | 1247.4963 | 0 | 1247.4963 | 0 | 1247.4963 | 0 | 1247.4963 | 0 | 1247.4963 | 0 | 1247.4963 | 0 | 1247.4963 | 500 | 1247.4963 | 0
2025-07-26 | 10301.9052 | 500 | 30522.375 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 500 | 1287.7382 | 0
2025-07-27 | 10623.8398 | 500 | 30522.375 | 1327.98 | 0 | 1327.98 | 0 | 1327.98 | 0 | 1327.98 | 0 | 1327.98 | 0 | 1327.98 | 0 | 1327.98 | 500 | 1327.98 | 0
2025-07-28 | 10945.7743 | 500 | 31122.4 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 500 | 1368.2218 | 0
2025-07-29 | 11267.7088 | 500 | 31722.425 | 1408.4636 | 0 | 1408.4636 | 0 | 1408.4636 | 0 | 1408.4636 | 0 | 1408.4636 | 0 | 1408.4636 | 0 | 1408.4636 | 500 | 1408.4636 | 0
2025-07-30 | 11589.6434 | 500 | 32322.45 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 500 | 1448.7054 | 0
2025-07-31 | 11911.5779 | 500 | 32922.475 | 1488.9472 | 0 | 1488.9472 | 0 | 1488.9472 | 0 | 1488.9472 | 0 | 1488.9472 | 0 | 1488.9472 | 0 | 1488.9472 | 500 | 1488.9472 | 0
2025-08-01 | 12233.5125 | 528 | 33522.5 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 500 | 1529.1891 | 28
2025-08-02 | 12555.447 | 528 | 33522.5 | 1569.4309 | 0 | 1569.4309 | 0 | 1569.4309 | 0 | 1569.4309 | 0 | 1569.4309 | 0 | 1569.4309 | 0 | 1569.4309 | 500 | 1569.4309 | 28
2025-08-03 | 12877.3815 | 528 | 33522.5 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 500 | 1609.6727 | 28
2025-08-04 | 13199.3161 | 528 | 34126 | 1649.9145 | 0 | 1649.9145 | 0 | 1649.9145 | 0 | 1649.9145 | 0 | 1649.9145 | 0 | 1649.9145 | 0 | 1649.9145 | 500 | 1649.9145 | 28
2025-08-05 | 13521.2506 | 528 | 34729.5 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 500 | 1690.1563 | 28
2025-08-06 | 13843.1851 | 528 | 35333 | 1730.3981 | 0 | 1730.3981 | 0 | 1730.3981 | 0 | 1730.3981 | 0 | 1730.3981 | 0 | 1730.3981 | 0 | 1730.3981 | 500 | 1730.3981 | 28
2025-08-07 | 14165.1197 | 528 | 35936.5 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 500 | 1770.64 | 28
2025-08-08 | 14487.0542 | 528 | 36540 | 1810.8818 | 0 | 1810.8818 | 0 | 1810.8818 | 0 | 1810.8818 | 0 | 1810.8818 | 0 | 1810.8818 | 0 | 1810.8818 | 500 | 1810.8818 | 28
2025-08-09 | 14808.9888 | 528 | 36540 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 500 | 1851.1236 | 28
2025-08-10 | 15130.9233 | 528 | 36540 | 1891.3654 | 0 | 1891.3654 | 0 | 1891.3654 | 0 | 1891.3654 | 0 | 1891.3654 | 0 | 1891.3654 | 0 | 1891.3654 | 500 | 1891.3654 | 28
2025-08-11 | 15452.8578 | 528 | 37089.9 | 1931.6072 | 0 | 1931.6072 | 0 | 1931.6072 | 0 | 1931.6072 | 0 | 1931.6072 | 0 | 1931.6072 | 0 | 1931.6072 | 500 | 1931.6072 | 28
2025-08-12 | 15774.7924 | 528 | 37639.8 | 1971.849 | 0 | 1971.849 | 0 | 1971.849 | 0 | 1971.849 | 0 | 1971.849 | 0 | 1971.849 | 0 | 1971.849 | 500 | 1971.849 | 28
2025-08-13 | 16096.7269 | 528 | 38189.7 | 2012.0909 | 0 | 2012.0909 | 0 | 2012.0909 | 0 | 2012.0909 | 0 | 2012.0909 | 0 | 2012.0909 | 0 | 2012.0909 | 500 | 2012.0909 | 28
2025-08-14 | 16418.6615 | 528 | 38739.6 | 2052.3327 | 0 | 2052.3327 | 0 | 2052.3327 | 0 | 2052.3327 | 0 | 2052.3327 | 0 | 2052.3327 | 0 | 2052.3327 | 500 | 2052.3327 | 28
2025-08-15 | 16740.596 | 528 | 39289.5 | 2092.5745 | 0 | 2092.5745 | 0 | 2092.5745 | 0 | 2092.5745 | 0 | 2092.5745 | 0 | 2092.5745 | 0 | 2092.5745 | 500 | 2092.5745 | 28
2025-08-16 | 17062.5305 | 528 | 39289.5 | 2132.8163 | 0 | 2132.8163 | 0 | 2132.8163 | 0 | 2132.8163 | 0 | 2132.8163 | 0 | 2132.8163 | 0 | 2132.8163 | 500 | 2132.8163 | 28
2025-08-17 | 17384.4651 | 528 | 39289.5 | 2173.0581 | 0 | 2173.0581 | 0 | 2173.0581 | 0 | 2173.0581 | 0 | 2173.0581 | 0 | 2173.0581 | 0 | 2173.0581 | 500 | 2173.0581 | 28
2025-08-18 | 17706.3996 | 528 | 39993.25 | 2213.3 | 0 | 2213.3 | 0 | 2213.3 | 0 | 2213.3 | 0 | 2213.3 | 0 | 2213.3 | 0 | 2213.3 | 500 | 2213.3 | 28
2025-08-19 | 18028.3341 | 528 | 40697 | 2253.5418 | 0 | 2253.5418 | 0 | 2253.5418 | 0 | 2253.5418 | 0 | 2253.5418 | 0 | 2253.5418 | 0 | 2253.5418 | 500 | 2253.5418 | 28
2025-08-20 | 18350.2687 | 528 | 41400.75 | 2293.7836 | 0 | 2293.7836 | 0 | 2293.7836 | 0 | 2293.7836 | 0 | 2293.7836 | 0 | 2293.7836 | 0 | 2293.7836 | 500 | 2293.7836 | 28
2025-08-21 | 18672.2032 | 528 | 42104.5 | 2334.0254 | 0 | 2334.0254 | 0 | 2334.0254 | 0 | 2334.0254 | 0 | 2334.0254 | 0 | 2334.0254 | 0 | 2334.0254 | 500 | 2334.0254 | 28
2025-08-22 | 18994.1378 | 528 | 42808.25 | 2374.2672 | 0 | 2374.2672 | 0 | 2374.2672 | 0 | 2374.2672 | 0 | 2374.2672 | 0 | 2374.2672 | 0 | 2374.2672 | 500 | 2374.2672 | 28
2025-08-23 | 19316.0723 | 528 | 42808.25 | 2414.509 | 0 | 2414.509 | 0 | 2414.509 | 0 | 2414.509 | 0 | 2414.509 | 0 | 2414.509 | 0 | 2414.509 | 500 | 2414.509 | 28
2025-08-24 | 19638.0068 | 528 | 42808.25 | 2454.7509 | 0 | 2454.7509 | 0 | 2454.7509 | 0 | 2454.7509 | 0 | 2454.7509 | 0 | 2454.7509 | 0 | 2454.7509 | 500 | 2454.7509 | 28
2025-08-25 | 19959.9414 | 543 | 43488.675 | 2494.9927 | 0 | 2494.9927 | 0 | 2494.9927 | 0 | 2494.9927 | 0 | 2494.9927 | 0 | 2494.9927 | 15 | 2494.9927 | 500 | 2494.9927 | 28
2025-08-26 | 20281.8759 | 3293 | 44169.1 | 2535.2345 | 0 | 2535.2345 | 0 | 2535.2345 | 0 | 2535.2345 | 0 | 2535.2345 | 0 | 2535.2345 | 2765 | 2535.2345 | 500 | 2535.2345 | 28
2025-08-27 | 20603.8105 | 3293 | 44849.525 | 2575.4763 | 0 | 2575.4763 | 0 | 2575.4763 | 0 | 2575.4763 | 0 | 2575.4763 | 0 | 2575.4763 | 2765 | 2575.4763 | 500 | 2575.4763 | 28
2025-08-28 | 20925.745 | 3293 | 45529.95 | 2615.7181 | 0 | 2615.7181 | 0 | 2615.7181 | 0 | 2615.7181 | 0 | 2615.7181 | 0 | 2615.7181 | 2765 | 2615.7181 | 500 | 2615.7181 | 28
2025-08-29 | 21247.6795 | 3293 | 46210.375 | 2655.9599 | 0 | 2655.9599 | 0 | 2655.9599 | 0 | 2655.9599 | 0 | 2655.9599 | 0 | 2655.9599 | 2765 | 2655.9599 | 500 | 2655.9599 | 28
2025-08-30 | 21569.6141 | 3293 | 46210.375 | 2696.2018 | 0 | 2696.2018 | 0 | 2696.2018 | 0 | 2696.2018 | 0 | 2696.2018 | 0 | 2696.2018 | 2765 | 2696.2018 | 500 | 2696.2018 | 28
2025-08-31 | 21891.5486 | 3293 | 46210.375 | 2736.4436 | 0 | 2736.4436 | 0 | 2736.4436 | 0 | 2736.4436 | 0 | 2736.4436 | 0 | 2736.4436 | 2765 | 2736.4436 | 500 | 2736.4436 | 28
2025-09-01 | 22213.4831 | 3293 | 47373.7 | 2776.6854 | 0 | 2776.6854 | 0 | 2776.6854 | 0 | 2776.6854 | 0 | 2776.6854 | 0 | 2776.6854 | 2765 | 2776.6854 | 500 | 2776.6854 | 28
2025-09-02 | 22535.4177 | 3293 | 48537.025 | 2816.9272 | 0 | 2816.9272 | 0 | 2816.9272 | 0 | 2816.9272 | 0 | 2816.9272 | 0 | 2816.9272 | 2765 | 2816.9272 | 500 | 2816.9272 | 28
2025-09-03 | 22857.3522 | 3293 | 49700.35 | 2857.169 | 0 | 2857.169 | 0 | 2857.169 | 0 | 2857.169 | 0 | 2857.169 | 0 | 2857.169 | 2765 | 2857.169 | 500 | 2857.169 | 28
2025-09-04 | 23179.2868 | 3979.7 | 50863.675 | 2897.4108 | 0 | 2897.4108 | 0 | 2897.4108 | 686.7 | 2897.4108 | 0 | 2897.4108 | 0 | 2897.4108 | 2765 | 2897.4108 | 500 | 2897.4108 | 28
2025-09-05 | 23501.2213 | 3979.7 | 52027 | 2937.6527 | 0 | 2937.6527 | 0 | 2937.6527 | 686.7 | 2937.6527 | 0 | 2937.6527 | 0 | 2937.6527 | 2765 | 2937.6527 | 500 | 2937.6527 | 28
2025-09-06 | 23823.1558 | 3979.7 | 52027 | 2977.8945 | 0 | 2977.8945 | 0 | 2977.8945 | 686.7 | 2977.8945 | 0 | 2977.8945 | 0 | 2977.8945 | 2765 | 2977.8945 | 500 | 2977.8945 | 28
2025-09-07 | 24145.0904 | 3979.7 | 52027 | 3018.1363 | 0 | 3018.1363 | 0 | 3018.1363 | 686.7 | 3018.1363 | 0 | 3018.1363 | 0 | 3018.1363 | 2765 | 3018.1363 | 500 | 3018.1363 | 28
2025-09-08 | 24467.0249 | 3979.7 | 52781.375 | 3058.3781 | 0 | 3058.3781 | 0 | 3058.3781 | 686.7 | 3058.3781 | 0 | 3058.3781 | 0 | 3058.3781 | 2765 | 3058.3781 | 500 | 3058.3781 | 28
2025-09-09 | 24788.9595 | 3979.7 | 53535.75 | 3098.6199 | 0 | 3098.6199 | 0 | 3098.6199 | 686.7 | 3098.6199 | 0 | 3098.6199 | 0 | 3098.6199 | 2765 | 3098.6199 | 500 | 3098.6199 | 28
2025-09-10 | 25110.894 | 3979.7 | 54290.125 | 3138.8617 | 0 | 3138.8617 | 0 | 3138.8617 | 686.7 | 3138.8617 | 0 | 3138.8617 | 0 | 3138.8617 | 2765 | 3138.8617 | 500 | 3138.8617 | 28
2025-09-11 | 25432.8285 | 3979.7 | 55044.5 | 3179.1036 | 0 | 3179.1036 | 0 | 3179.1036 | 686.7 | 3179.1036 | 0 | 3179.1036 | 0 | 3179.1036 | 2765 | 3179.1036 | 500 | 3179.1036 | 28
2025-09-12 | 25754.7631 | 18094.7 | 55798.875 | 3219.3454 | 14115 | 3219.3454 | 0 | 3219.3454 | 686.7 | 3219.3454 | 0 | 3219.3454 | 0 | 3219.3454 | 2765 | 3219.3454 | 500 | 3219.3454 | 28
2025-09-13 | 26076.6976 | 18197.61 | 55798.875 | 3259.5872 | 14115 | 3259.5872 | 0 | 3259.5872 | 686.7 | 3259.5872 | 0 | 3259.5872 | 0 | 3259.5872 | 2765 | 3259.5872 | 602.91 | 3259.5872 | 28
2025-09-14 | 26398.6321 | 18197.61 | 55798.875 | 3299.829 | 14115 | 3299.829 | 0 | 3299.829 | 686.7 | 3299.829 | 0 | 3299.829 | 0 | 3299.829 | 2765 | 3299.829 | 602.91 | 3299.829 | 28
2025-09-15 | 26720.5667 | 18197.61 | 57425.25 | 3340.0708 | 14115 | 3340.0708 | 0 | 3340.0708 | 686.7 | 3340.0708 | 0 | 3340.0708 | 0 | 3340.0708 | 2765 | 3340.0708 | 602.91 | 3340.0708 | 28
2025-09-16 | 27042.5012 | 18197.61 | 59051.625 | 3380.3127 | 14115 | 3380.3127 | 0 | 3380.3127 | 686.7 | 3380.3127 | 0 | 3380.3127 | 0 | 3380.3127 | 2765 | 3380.3127 | 602.91 | 3380.3127 | 28
2025-09-17 | 27364.4358 | 18197.61 | 60678 | 3420.5545 | 14115 | 3420.5545 | 0 | 3420.5545 | 686.7 | 3420.5545 | 0 | 3420.5545 | 0 | 3420.5545 | 2765 | 3420.5545 | 602.91 | 3420.5545 | 28
2025-09-18 | 27686.3703 | 18197.61 | 62304.375 | 3460.7963 | 14115 | 3460.7963 | 0 | 3460.7963 | 686.7 | 3460.7963 | 0 | 3460.7963 | 0 | 3460.7963 | 2765 | 3460.7963 | 602.91 | 3460.7963 | 28
2025-09-19 | 28008.3048 | 18197.61 | 63930.75 | 3501.0381 | 14115 | 3501.0381 | 0 | 3501.0381 | 686.7 | 3501.0381 | 0 | 3501.0381 | 0 | 3501.0381 | 2765 | 3501.0381 | 602.91 | 3501.0381 | 28
2025-09-20 | 28330.2394 | 18197.61 | 63930.75 | 3541.2799 | 14115 | 3541.2799 | 0 | 3541.2799 | 686.7 | 3541.2799 | 0 | 3541.2799 | 0 | 3541.2799 | 2765 | 3541.2799 | 602.91 | 3541.2799 | 28
2025-09-21 | 28652.1739 | 18197.61 | 63930.75 | 3581.5217 | 14115 | 3581.5217 | 0 | 3581.5217 | 686.7 | 3581.5217 | 0 | 3581.5217 | 0 | 3581.5217 | 2765 | 3581.5217 | 602.91 | 3581.5217 | 28
2025-09-22 | 28652.1739 | 20145.11 | 65705.925 | 3581.5217 | 14115 | 3581.5217 | 0 | 3581.5217 | 1184.2 | 3581.5217 | 0 | 3581.5217 | 0 | 3581.5217 | 4215 | 3581.5217 | 602.91 | 3581.5217 | 28
2025-09-23 | 28836.99 | 21282.63 | 67481.1 | 3604.6237 | 14262.52 | 3604.6237 | 0 | 3604.6237 | 1184.2 | 3604.6237 | 990 | 3604.6237 | 0 | 3604.6237 | 4215 | 3604.6237 | 602.91 | 3604.6237 | 28
2025-09-24 | 29021.806 | 25593.94 | 69256.275 | 3627.7258 | 18573.83 | 3627.7258 | 0 | 3627.7258 | 1184.2 | 3627.7258 | 990 | 3627.7258 | 0 | 3627.7258 | 4215 | 3627.7258 | 602.91 | 3627.7258 | 28
2025-09-25 | 29206.6221 | 26370.19 | 71031.45 | 3650.8278 | 18573.83 | 3650.8278 | 0 | 3650.8278 | 1960.45 | 3650.8278 | 990 | 3650.8278 | 0 | 3650.8278 | 4215 | 3650.8278 | 602.91 | 3650.8278 | 28
2025-09-26 | 29391.4381 | 26370.19 | 72806.625 | 3673.9298 | 18573.83 | 3673.9298 | 0 | 3673.9298 | 1960.45 | 3673.9298 | 990 | 3673.9298 | 0 | 3673.9298 | 4215 | 3673.9298 | 602.91 | 3673.9298 | 28
2025-09-27 | 29576.2542 | 26370.19 | 72806.625 | 3697.0318 | 18573.83 | 3697.0318 | 0 | 3697.0318 | 1960.45 | 3697.0318 | 990 | 3697.0318 | 0 | 3697.0318 | 4215 | 3697.0318 | 602.91 | 3697.0318 | 28
2025-09-28 | 29761.0702 | 26370.19 | 72806.625 | 3720.1338 | 18573.83 | 3720.1338 | 0 | 3720.1338 | 1960.45 | 3720.1338 | 990 | 3720.1338 | 0 | 3720.1338 | 4215 | 3720.1338 | 602.91 | 3720.1338 | 28
2025-09-29 | 29945.8863 | 26370.19 | 74913.85 | 3743.2358 | 18573.83 | 3743.2358 | 0 | 3743.2358 | 1960.45 | 3743.2358 | 990 | 3743.2358 | 0 | 3743.2358 | 4215 | 3743.2358 | 602.91 | 3743.2358 | 28
2025-09-30 | 30130.7023 | 13370.19 | 77021.075 | 3766.3378 | 18573.83 | 3766.3378 | 0 | 3766.3378 | 1960.45 | 3766.3378 | 990 | 3766.3378 | 0 | 3766.3378 | -8785 | 3766.3378 | 602.91 | 3766.3378 | 28
2025-10-01 | 30315.5184 | 13370.19 | 79128.3 | 3789.4398 | 18573.83 | 3789.4398 | 0 | 3789.4398 | 1960.45 | 3789.4398 | 990 | 3789.4398 | 0 | 3789.4398 | -8785 | 3789.4398 | 602.91 | 3789.4398 | 28
2025-10-02 | 30500.3344 | 13505.49 | 81235.525 | 3812.5418 | 18573.83 | 3812.5418 | 0 | 3812.5418 | 2095.75 | 3812.5418 | 990 | 3812.5418 | 0 | 3812.5418 | -8785 | 3812.5418 | 602.91 | 3812.5418 | 28
2025-10-03 | 30685.1505 | 13505.49 | 83342.75 | 3835.6438 | 18573.83 | 3835.6438 | 0 | 3835.6438 | 2095.75 | 3835.6438 | 990 | 3835.6438 | 0 | 3835.6438 | -8785 | 3835.6438 | 602.91 | 3835.6438 | 28
2025-10-04 | 30869.9666 | 13505.49 | 83342.75 | 3858.7458 | 18573.83 | 3858.7458 | 0 | 3858.7458 | 2095.75 | 3858.7458 | 990 | 3858.7458 | 0 | 3858.7458 | -8785 | 3858.7458 | 602.91 | 3858.7458 | 28
2025-10-05 | 31054.7826 | 13505.49 | 83342.75 | 3881.8478 | 18573.83 | 3881.8478 | 0 | 3881.8478 | 2095.75 | 3881.8478 | 990 | 3881.8478 | 0 | 3881.8478 | -8785 | 3881.8478 | 602.91 | 3881.8478 | 28
2025-10-06 | 31239.5987 | 13505.49 | 85089.875 | 3904.9498 | 18573.83 | 3904.9498 | 0 | 3904.9498 | 2095.75 | 3904.9498 | 990 | 3904.9498 | 0 | 3904.9498 | -8785 | 3904.9498 | 602.91 | 3904.9498 | 28
2025-10-07 | 31424.4147 | 13505.49 | 86837 | 3928.0518 | 18573.83 | 3928.0518 | 0 | 3928.0518 | 2095.75 | 3928.0518 | 990 | 3928.0518 | 0 | 3928.0518 | -8785 | 3928.0518 | 602.91 | 3928.0518 | 28
2025-10-08 | 31609.2308 | 23402.42 | 88584.125 | 3951.1538 | 18573.83 | 3951.1538 | 0 | 3951.1538 | 11992.68 | 3951.1538 | 990 | 3951.1538 | 0 | 3951.1538 | -8785 | 3951.1538 | 602.91 | 3951.1538 | 28
2025-10-09 | 31794.0468 | 23402.42 | 90331.25 | 3974.2559 | 18573.83 | 3974.2559 | 0 | 3974.2559 | 11992.68 | 3974.2559 | 990 | 3974.2559 | 0 | 3974.2559 | -8785 | 3974.2559 | 602.91 | 3974.2559 | 28
2025-10-10 | 31978.8629 | 23402.42 | 92078.375 | 3997.3579 | 18573.83 | 3997.3579 | 0 | 3997.3579 | 11992.68 | 3997.3579 | 990 | 3997.3579 | 0 | 3997.3579 | -8785 | 3997.3579 | 602.91 | 3997.3579 | 28
2025-10-11 | 32163.6789 | 25002.42 | 92078.375 | 4020.4599 | 20173.83 | 4020.4599 | 0 | 4020.4599 | 11992.68 | 4020.4599 | 990 | 4020.4599 | 0 | 4020.4599 | -8785 | 4020.4599 | 602.91 | 4020.4599 | 28
2025-10-12 | 32348.495 | 25002.42 | 92078.375 | 4043.5619 | 20173.83 | 4043.5619 | 0 | 4043.5619 | 11992.68 | 4043.5619 | 990 | 4043.5619 | 0 | 4043.5619 | -8785 | 4043.5619 | 602.91 | 4043.5619 | 28
2025-10-13 | 32533.311 | 25002.42 | 93848.825 | 4066.6639 | 20173.83 | 4066.6639 | 0 | 4066.6639 | 11992.68 | 4066.6639 | 990 | 4066.6639 | 0 | 4066.6639 | -8785 | 4066.6639 | 602.91 | 4066.6639 | 28
2025-10-14 | 32718.1271 | 25002.42 | 95619.275 | 4089.7659 | 20173.83 | 4089.7659 | 0 | 4089.7659 | 11992.68 | 4089.7659 | 990 | 4089.7659 | 0 | 4089.7659 | -8785 | 4089.7659 | 602.91 | 4089.7659 | 28
2025-10-15 | 32902.9431 | 25002.42 | 97389.725 | 4112.8679 | 20173.83 | 4112.8679 | 0 | 4112.8679 | 11992.68 | 4112.8679 | 990 | 4112.8679 | 0 | 4112.8679 | -8785 | 4112.8679 | 602.91 | 4112.8679 | 28
2025-10-16 | 33087.7592 | 25002.42 | 99160.175 | 4135.9699 | 20173.83 | 4135.9699 | 0 | 4135.9699 | 11992.68 | 4135.9699 | 990 | 4135.9699 | 0 | 4135.9699 | -8785 | 4135.9699 | 602.91 | 4135.9699 | 28
2025-10-17 | 33272.5753 | 25002.42 | 100930.625 | 4159.0719 | 20173.83 | 4159.0719 | 0 | 4159.0719 | 11992.68 | 4159.0719 | 990 | 4159.0719 | 0 | 4159.0719 | -8785 | 4159.0719 | 602.91 | 4159.0719 | 28
2025-10-18 | 33457.3913 | 25002.42 | 100930.625 | 4182.1739 | 20173.83 | 4182.1739 | 0 | 4182.1739 | 11992.68 | 4182.1739 | 990 | 4182.1739 | 0 | 4182.1739 | -8785 | 4182.1739 | 602.91 | 4182.1739 | 28
2025-10-19 | 33642.2074 | 25002.42 | 100930.625 | 4205.2759 | 20173.83 | 4205.2759 | 0 | 4205.2759 | 11992.68 | 4205.2759 | 990 | 4205.2759 | 0 | 4205.2759 | -8785 | 4205.2759 | 602.91 | 4205.2759 | 28
2025-10-20 | 33827.0234 | 25002.42 | 103046.55 | 4228.3779 | 20173.83 | 4228.3779 | 0 | 4228.3779 | 11992.68 | 4228.3779 | 990 | 4228.3779 | 0 | 4228.3779 | -8785 | 4228.3779 | 602.91 | 4228.3779 | 28
2025-10-21 | 34011.8395 | 25002.42 | 105162.475 | 4251.4799 | 20173.83 | 4251.4799 | 0 | 4251.4799 | 11992.68 | 4251.4799 | 990 | 4251.4799 | 0 | 4251.4799 | -8785 | 4251.4799 | 602.91 | 4251.4799 | 28
2025-10-22 | 34196.6555 | 33702.42 | 107278.4 | 4274.5819 | 20173.83 | 4274.5819 | 0 | 4274.5819 | 20692.68 | 4274.5819 | 990 | 4274.5819 | 0 | 4274.5819 | -8785 | 4274.5819 | 602.91 | 4274.5819 | 28
2025-10-23 | 34381.4716 | 33702.42 | 109394.325 | 4297.6839 | 20173.83 | 4297.6839 | 0 | 4297.6839 | 20692.68 | 4297.6839 | 990 | 4297.6839 | 0 | 4297.6839 | -8785 | 4297.6839 | 602.91 | 4297.6839 | 28
2025-10-24 | 34566.2876 | 33702.42 | 111510.25 | 4320.786 | 20173.83 | 4320.786 | 0 | 4320.786 | 20692.68 | 4320.786 | 990 | 4320.786 | 0 | 4320.786 | -8785 | 4320.786 | 602.91 | 4320.786 | 28
2025-10-25 | 34751.1037 | 33702.42 | 111510.25 | 4343.888 | 20173.83 | 4343.888 | 0 | 4343.888 | 20692.68 | 4343.888 | 990 | 4343.888 | 0 | 4343.888 | -8785 | 4343.888 | 602.91 | 4343.888 | 28
2025-10-26 | 34935.9197 | 33702.42 | 111510.25 | 4366.99 | 20173.83 | 4366.99 | 0 | 4366.99 | 20692.68 | 4366.99 | 990 | 4366.99 | 0 | 4366.99 | -8785 | 4366.99 | 602.91 | 4366.99 | 28
2025-10-27 | 35120.7358 | 33702.42 | 113280.75 | 4390.092 | 20173.83 | 4390.092 | 0 | 4390.092 | 20692.68 | 4390.092 | 990 | 4390.092 | 0 | 4390.092 | -8785 | 4390.092 | 602.91 | 4390.092 | 28
2025-10-28 | 35305.5518 | 33719.05 | 115051.25 | 4413.194 | 20173.83 | 4413.194 | 0 | 4413.194 | 20692.68 | 4413.194 | 990 | 4413.194 | 0 | 4413.194 | -8768.37 | 4413.194 | 602.91 | 4413.194 | 28
2025-10-29 | 35490.3679 | 27919.05 | 116821.75 | 4436.296 | 20173.83 | 4436.296 | 0 | 4436.296 | 14892.68 | 4436.296 | 990 | 4436.296 | 0 | 4436.296 | -8768.37 | 4436.296 | 602.91 | 4436.296 | 28
2025-10-30 | 35675.1839 | 28054.35 | 118592.25 | 4459.398 | 20173.83 | 4459.398 | 0 | 4459.398 | 15027.98 | 4459.398 | 990 | 4459.398 | 0 | 4459.398 | -8768.37 | 4459.398 | 602.91 | 4459.398 | 28
2025-10-31 | 35860 | 28054.35 | 120362.75 | 4482.5 | 20173.83 | 4482.5 | 0 | 4482.5 | 15027.98 | 4482.5 | 990 | 4482.5 | 0 | 4482.5 | -8768.37 | 4482.5 | 602.91 | 4482.5 | 28
2025-11-01 | 36044.8161 | 28054.35 | 120362.75 | 4505.602 | 20173.83 | 4505.602 | 0 | 4505.602 | 15027.98 | 4505.602 | 990 | 4505.602 | 0 | 4505.602 | -8768.37 | 4505.602 | 602.91 | 4505.602 | 28
2025-11-02 | 36229.6321 | 28054.35 | 120362.75 | 4528.704 | 20173.83 | 4528.704 | 0 | 4528.704 | 15027.98 | 4528.704 | 990 | 4528.704 | 0 | 4528.704 | -8768.37 | 4528.704 | 602.91 | 4528.704 | 28
2025-11-03 | 36414.4482 | 28054.35 | 122034.05 | 4551.806 | 20173.83 | 4551.806 | 0 | 4551.806 | 15027.98 | 4551.806 | 990 | 4551.806 | 0 | 4551.806 | -8768.37 | 4551.806 | 602.91 | 4551.806 | 28
2025-11-04 | 36599.2642 | 28054.35 | 123705.35 | 4574.908 | 20173.83 | 4574.908 | 0 | 4574.908 | 15027.98 | 4574.908 | 990 | 4574.908 | 0 | 4574.908 | -8768.37 | 4574.908 | 602.91 | 4574.908 | 28
2025-11-05 | 36784.0803 | 28054.35 | 125376.65 | 4598.01 | 20173.83 | 4598.01 | 0 | 4598.01 | 15027.98 | 4598.01 | 990 | 4598.01 | 0 | 4598.01 | -8768.37 | 4598.01 | 602.91 | 4598.01 | 28
2025-11-06 | 36968.8963 | 29404.35 | 127047.95 | 4621.112 | 20173.83 | 4621.112 | 0 | 4621.112 | 16377.98 | 4621.112 | 990 | 4621.112 | 0 | 4621.112 | -8768.37 | 4621.112 | 602.91 | 4621.112 | 28
2025-11-07 | 37153.7124 | 29404.35 | 128719.25 | 4644.214 | 20173.83 | 4644.214 | 0 | 4644.214 | 16377.98 | 4644.214 | 990 | 4644.214 | 0 | 4644.214 | -8768.37 | 4644.214 | 602.91 | 4644.214 | 28
2025-11-08 | 37338.5284 | 29404.35 | 128719.25 | 4667.3161 | 20173.83 | 4667.3161 | 0 | 4667.3161 | 16377.98 | 4667.3161 | 990 | 4667.3161 | 0 | 4667.3161 | -8768.37 | 4667.3161 | 602.91 | 4667.3161 | 28
2025-11-09 | 37523.3445 | 29404.35 | 128719.25 | 4690.4181 | 20173.83 | 4690.4181 | 0 | 4690.4181 | 16377.98 | 4690.4181 | 990 | 4690.4181 | 0 | 4690.4181 | -8768.37 | 4690.4181 | 602.91 | 4690.4181 | 28
2025-11-10 | 37708.1605 | 29404.35 | 130337.625 | 4713.5201 | 20173.83 | 4713.5201 | 0 | 4713.5201 | 16377.98 | 4713.5201 | 990 | 4713.5201 | 0 | 4713.5201 | -8768.37 | 4713.5201 | 602.91 | 4713.5201 | 28
2025-11-11 | 37892.9766 | 29404.35 | 131956 | 4736.6221 | 20173.83 | 4736.6221 | 0 | 4736.6221 | 16377.98 | 4736.6221 | 990 | 4736.6221 | 0 | 4736.6221 | -8768.37 | 4736.6221 | 602.91 | 4736.6221 | 28
2025-11-12 | 38077.7926 | 29404.35 | 133574.375 | 4759.7241 | 20173.83 | 4759.7241 | 0 | 4759.7241 | 16377.98 | 4759.7241 | 990 | 4759.7241 | 0 | 4759.7241 | -8768.37 | 4759.7241 | 602.91 | 4759.7241 | 28
2025-11-13 | 38262.6087 | 34527.13 | 135192.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 20811.76 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-14 | 38262.6087 | 34527.13 | 136811.125 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 20811.76 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-15 | 38262.6087 | 34527.13 | 136811.125 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 20811.76 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-16 | 38262.6087 | 34527.13 | 136811.125 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 20811.76 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-17 | 38262.6087 | 34527.13 | 137515.425 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 20811.76 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-18 | 38262.6087 | 40459.74 | 138219.725 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26744.37 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-19 | 38262.6087 | 40595.04 | 138924.025 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-20 | 38262.6087 | 40595.04 | 139628.325 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-21 | 38262.6087 | 40595.04 | 140332.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-22 | 38262.6087 | 40595.04 | 140332.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-23 | 38262.6087 | 40595.04 | 140332.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-24 | 38262.6087 | 40595.04 | 141144.85 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-25 | 38262.6087 | 40595.04 | 141957.075 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-26 | 38262.6087 | 40595.04 | 142769.3 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-27 | 38262.6087 | 40595.04 | 143581.525 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-28 | 38262.6087 | 40595.04 | 144393.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-29 | 38262.6087 | 40595.04 | 144393.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-11-30 | 38262.6087 | 40595.04 | 144393.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-01 | 38262.6087 | 40595.04 | 145486.9 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-02 | 38262.6087 | 40595.04 | 146580.05 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-03 | 38262.6087 | 40595.04 | 147673.2 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-04 | 38262.6087 | 40595.04 | 148766.35 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-05 | 38262.6087 | 40595.04 | 149859.5 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-06 | 38262.6087 | 40595.04 | 149859.5 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-07 | 38262.6087 | 40595.04 | 149859.5 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-08 | 38262.6087 | 40595.04 | 151023.125 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 26879.67 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-09 | 38262.6087 | 41090.35 | 152186.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 27374.98 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -8768.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-10 | 38262.6087 | 42390.35 | 153350.375 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 27374.98 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-11 | 38262.6087 | 43222.32 | 154514 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 28206.95 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-12 | 38262.6087 | 44054.29 | 155677.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 29038.92 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-13 | 38262.6087 | 44054.29 | 155677.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 29038.92 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-14 | 38262.6087 | 44054.29 | 155677.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 29038.92 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-15 | 38262.6087 | 44054.29 | 156841.25 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 29038.92 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-16 | 38262.6087 | 44054.29 | 158004.875 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 29038.92 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-17 | 38262.6087 | 44054.29 | 159168.5 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 29038.92 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-18 | 38262.6087 | 44054.29 | 160332.125 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 29038.92 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-19 | 38262.6087 | 44054.29 | 161495.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 29038.92 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-20 | 38262.6087 | 44054.29 | 161495.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 29038.92 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-21 | 38262.6087 | 44054.29 | 161495.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 29038.92 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-22 | 38262.6087 | 44054.29 | 161495.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 29038.92 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-23 | 38262.6087 | 48579.67 | 161495.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33564.3 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-24 | 38262.6087 | 48579.67 | 161495.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33564.3 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-25 | 38262.6087 | 48714.97 | 161495.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-26 | 38262.6087 | 48714.97 | 161495.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-27 | 38262.6087 | 48714.97 | 161495.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-28 | 38262.6087 | 48714.97 | 161495.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-29 | 38262.6087 | 48714.97 | 162393.1 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 0 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-30 | 38262.6087 | 49214.97 | 163290.45 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 500 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2025-12-31 | 38262.6087 | 49214.97 | 164187.8 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 500 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-01 | 38262.6087 | 49214.97 | 165085.15 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 500 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-02 | 38262.6087 | 49214.97 | 165982.5 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 500 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-03 | 38262.6087 | 49214.97 | 165982.5 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 500 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-04 | 38262.6087 | 49214.97 | 165982.5 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 500 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-05 | 38262.6087 | 49214.97 | 167054.925 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 500 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-06 | 38262.6087 | 60839.97 | 168127.35 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-07 | 38262.6087 | 60839.97 | 169199.775 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-08 | 38262.6087 | 60839.97 | 170272.2 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-09 | 38262.6087 | 60839.97 | 171344.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-10 | 38262.6087 | 60839.97 | 171344.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-11 | 38262.6087 | 60839.97 | 171344.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-12 | 38262.6087 | 60839.97 | 172044.925 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-13 | 38262.6087 | 60839.97 | 172745.225 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-14 | 38262.6087 | 60839.97 | 173445.525 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-15 | 38262.6087 | 60839.97 | 174145.825 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 33699.6 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-16 | 38262.6087 | 66356.34 | 174846.125 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39215.97 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-17 | 38262.6087 | 66356.34 | 174846.125 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39215.97 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-18 | 38262.6087 | 66356.34 | 174846.125 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39215.97 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7468.37 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-19 | 38262.6087 | 66372.78 | 175873.425 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39215.97 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7451.93 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-20 | 38262.6087 | 66372.78 | 176900.725 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39215.97 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7451.93 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-21 | 38262.6087 | 66372.78 | 177928.025 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39215.97 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7451.93 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-22 | 38262.6087 | 66653.54 | 178955.325 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-23 | 38262.6087 | 66653.54 | 179982.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-24 | 38262.6087 | 66653.54 | 179982.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-25 | 38262.6087 | 66653.54 | 179982.625 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-26 | 38262.6087 | 66653.54 | 181735.85 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-27 | 38262.6087 | 66653.54 | 183489.075 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-28 | 38262.6087 | 66653.54 | 185242.3 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-29 | 38262.6087 | 66653.54 | 186995.525 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-30 | 38262.6087 | 66653.54 | 188748.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-01-31 | 38262.6087 | 66653.54 | 188748.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-01 | 38262.6087 | 66653.54 | 188748.75 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-02 | 38262.6087 | 66653.54 | 189828.5 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-03 | 38262.6087 | 66653.54 | 190908.25 | 4782.8261 | 20173.83 | 4782.8261 | 0 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -7306.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-04 | 38262.6087 | 69603.54 | 191988 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -6956.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-05 | 38262.6087 | 69603.54 | 193067.75 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -6956.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-06 | 38262.6087 | 69603.54 | 194147.5 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -6956.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-07 | 38262.6087 | 69603.54 | 194147.5 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -6956.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-08 | 38262.6087 | 69603.54 | 194147.5 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -6956.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-09 | 38262.6087 | 69603.54 | 195428.55 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -6956.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-10 | 38262.6087 | 70903.54 | 196709.6 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 39351.63 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-11 | 38262.6087 | 80354.04 | 197990.65 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48802.13 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-12 | 38262.6087 | 80354.04 | 199271.7 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48802.13 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-13 | 38262.6087 | 80354.04 | 200552.75 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48802.13 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-14 | 38262.6087 | 80354.04 | 200552.75 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48802.13 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-15 | 38262.6087 | 80354.04 | 200552.75 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48802.13 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-16 | 38262.6087 | 80354.04 | 201679.45 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48802.13 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-17 | 38262.6087 | 80354.04 | 202806.15 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48802.13 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-18 | 38262.6087 | 80354.04 | 203932.85 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48802.13 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-19 | 38262.6087 | 80489.7 | 205059.55 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48937.79 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-20 | 38262.6087 | 80541.37 | 206186.25 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48989.46 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-21 | 38262.6087 | 80541.37 | 206186.25 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48989.46 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-22 | 38262.6087 | 80541.37 | 206186.25 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48989.46 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-23 | 38262.6087 | 80541.37 | 207266 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 48989.46 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-24 | 38262.6087 | 80663.87 | 208345.75 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-25 | 38262.6087 | 80663.87 | 209425.5 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-26 | 38262.6087 | 80663.87 | 210505.25 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-27 | 38262.6087 | 80663.87 | 211585 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-02-28 | 38262.6087 | 80663.87 | 211585 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-01 | 38262.6087 | 80663.87 | 211585 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-02 | 38262.6087 | 80663.87 | 211980.75 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-03 | 38262.6087 | 80663.87 | 212376.5 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-04 | 38262.6087 | 80663.87 | 212772.25 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-05 | 38262.6087 | 80663.87 | 213168 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-06 | 38262.6087 | 80663.87 | 213563.75 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-07 | 38262.6087 | 80663.87 | 213563.75 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-08 | 38262.6087 | 80663.87 | 213563.75 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-09 | 38262.6087 | 80663.87 | 213761.625 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-10 | 38262.6087 | 80663.87 | 213959.5 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-11 | 38262.6087 | 80663.87 | 214157.375 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-12 | 38262.6087 | 80663.87 | 214355.25 | 4782.8261 | 20173.83 | 4782.8261 | 2600 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-13 | 38262.6087 | 83163.87 | 214553.125 | 4782.8261 | 20173.83 | 4782.8261 | 5100 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-14 | 38262.6087 | 83163.87 | 214553.125 | 4782.8261 | 20173.83 | 4782.8261 | 5100 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-15 | 38262.6087 | 83163.87 | 214553.125 | 4782.8261 | 20173.83 | 4782.8261 | 5100 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-16 | 38262.6087 | 83163.87 | 215408.95 | 4782.8261 | 20173.83 | 4782.8261 | 5100 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-17 | 38262.6087 | 83163.87 | 216264.775 | 4782.8261 | 20173.83 | 4782.8261 | 5100 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-18 | 38262.6087 | 83163.87 | 217120.6 | 4782.8261 | 20173.83 | 4782.8261 | 5100 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-19 | 38262.6087 | 83163.87 | 217976.425 | 4782.8261 | 20173.83 | 4782.8261 | 5100 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-20 | 38262.6087 | 83163.87 | 218832.25 | 4782.8261 | 20173.83 | 4782.8261 | 5100 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-21 | 38262.6087 | 83163.87 | 218832.25 | 4782.8261 | 20173.83 | 4782.8261 | 5100 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-22 | 38262.6087 | 83163.87 | 218832.25 | 4782.8261 | 20173.83 | 4782.8261 | 5100 | 4782.8261 | 49111.96 | 4782.8261 | 990 | 4782.8261 | 12125 | 4782.8261 | -5656.83 | 4782.8261 | 1291.91 | 4782.8261 | 28
2026-03-23 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-03-24 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-03-25 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-03-26 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-03-27 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-03-28 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-03-29 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-03-30 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-03-31 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-01 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-02 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-03 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-04 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-05 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-06 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-07 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-08 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-09 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-10 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-11 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-12 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-13 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-14 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-15 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-16 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-17 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-18 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-19 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-20 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-21 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-22 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-23 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-24 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-25 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-26 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-27 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-28 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-29 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-04-30 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-01 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-02 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-03 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-04 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-05 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-06 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-07 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-08 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-09 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-10 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-11 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-12 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-13 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-14 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-15 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-16 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-17 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-18 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-19 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-20 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-21 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-22 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-23 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-24 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-25 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-26 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-27 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-28 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-29 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-30 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-05-31 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-01 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-02 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-03 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-04 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-05 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-06 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-07 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-08 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-09 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-10 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-11 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-12 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-13 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-14 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-15 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-16 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-17 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-18 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-19 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-20 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-21 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-22 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-23 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-24 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-25 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-26 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-27 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-28 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-29 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-06-30 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-01 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-02 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-03 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-04 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-05 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-06 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-07 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-08 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-09 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-10 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-11 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-12 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-13 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-14 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-15 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-16 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-17 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-18 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-19 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-20 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-21 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-22 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-23 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-24 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-25 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-26 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-27 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-28 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-29 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-30 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-07-31 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-01 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-02 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-03 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-04 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-05 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-06 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-07 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-08 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-09 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-10 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-11 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-12 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-13 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-14 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-15 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-16 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-17 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-18 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-19 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-20 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-21 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-22 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-23 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-24 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-25 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-26 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-27 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-28 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-29 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-30 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-08-31 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-01 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-02 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-03 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-04 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-05 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-06 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-07 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-08 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-09 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-10 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-11 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-12 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-13 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-14 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-15 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-16 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-17 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-18 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-19 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-20 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-21 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-22 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-23 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-24 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-25 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-26 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-27 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-28 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-29 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-09-30 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-01 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-02 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-03 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-04 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-05 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-06 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-07 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-08 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-09 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-10 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-11 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-12 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-13 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-14 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-15 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-16 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-17 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-18 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-19 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-20 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-21 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-22 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-23 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-24 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-25 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-26 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-27 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-28 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-29 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-30 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-10-31 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-01 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-02 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-03 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-04 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-05 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-06 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-07 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-08 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-09 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-10 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-11 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-12 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-13 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-14 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-15 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-16 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-17 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-18 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-19 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-20 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-21 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-22 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-23 | 38262.6087 |  |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261 |  | 4782.8261
2026-11-24 | 38575.1087 |  |  | 4821.8886 |  | 4821.8886 |  | 4821.8886 |  | 4821.8886 |  | 4821.8886 |  | 4821.8886 |  | 4821.8886 |  | 4821.8886
2026-11-25 | 38887.6087 |  |  | 4860.9511 |  | 4860.9511 |  | 4860.9511 |  | 4860.9511 |  | 4860.9511 |  | 4860.9511 |  | 4860.9511 |  | 4860.9511
2026-11-26 | 39200.1087 |  |  | 4900.0136 |  | 4900.0136 |  | 4900.0136 |  | 4900.0136 |  | 4900.0136 |  | 4900.0136 |  | 4900.0136 |  | 4900.0136
2026-11-27 | 39512.6087 |  |  | 4939.0761 |  | 4939.0761 |  | 4939.0761 |  | 4939.0761 |  | 4939.0761 |  | 4939.0761 |  | 4939.0761 |  | 4939.0761
2026-11-28 | 39825.1087 |  |  | 4978.1386 |  | 4978.1386 |  | 4978.1386 |  | 4978.1386 |  | 4978.1386 |  | 4978.1386 |  | 4978.1386 |  | 4978.1386
2026-11-29 | 40137.6087 |  |  | 5017.2011 |  | 5017.2011 |  | 5017.2011 |  | 5017.2011 |  | 5017.2011 |  | 5017.2011 |  | 5017.2011 |  | 5017.2011
2026-11-30 | 40450.1087 |  |  | 5056.2636 |  | 5056.2636 |  | 5056.2636 |  | 5056.2636 |  | 5056.2636 |  | 5056.2636 |  | 5056.2636 |  | 5056.2636
2026-12-01 | 40762.6087 |  |  | 5095.3261 |  | 5095.3261 |  | 5095.3261 |  | 5095.3261 |  | 5095.3261 |  | 5095.3261 |  | 5095.3261 |  | 5095.3261
2026-12-02 | 41075.1087 |  |  | 5134.3886 |  | 5134.3886 |  | 5134.3886 |  | 5134.3886 |  | 5134.3886 |  | 5134.3886 |  | 5134.3886 |  | 5134.3886
2026-12-03 | 41387.6087 |  |  | 5173.4511 |  | 5173.4511 |  | 5173.4511 |  | 5173.4511 |  | 5173.4511 |  | 5173.4511 |  | 5173.4511 |  | 5173.4511
2026-12-04 | 41700.1087 |  |  | 5212.5136 |  | 5212.5136 |  | 5212.5136 |  | 5212.5136 |  | 5212.5136 |  | 5212.5136 |  | 5212.5136 |  | 5212.5136
2026-12-05 | 42012.6087 |  |  | 5251.5761 |  | 5251.5761 |  | 5251.5761 |  | 5251.5761 |  | 5251.5761 |  | 5251.5761 |  | 5251.5761 |  | 5251.5761
2026-12-06 | 42325.1087 |  |  | 5290.6386 |  | 5290.6386 |  | 5290.6386 |  | 5290.6386 |  | 5290.6386 |  | 5290.6386 |  | 5290.6386 |  | 5290.6386
2026-12-07 | 42637.6087 |  |  | 5329.7011 |  | 5329.7011 |  | 5329.7011 |  | 5329.7011 |  | 5329.7011 |  | 5329.7011 |  | 5329.7011 |  | 5329.7011
2026-12-08 | 42950.1087 |  |  | 5368.7636 |  | 5368.7636 |  | 5368.7636 |  | 5368.7636 |  | 5368.7636 |  | 5368.7636 |  | 5368.7636 |  | 5368.7636
2026-12-09 | 43262.6087 |  |  | 5407.8261 |  | 5407.8261 |  | 5407.8261 |  | 5407.8261 |  | 5407.8261 |  | 5407.8261 |  | 5407.8261 |  | 5407.8261
2026-12-10 | 43575.1087 |  |  | 5446.8886 |  | 5446.8886 |  | 5446.8886 |  | 5446.8886 |  | 5446.8886 |  | 5446.8886 |  | 5446.8886 |  | 5446.8886
2026-12-11 | 43887.6087 |  |  | 5485.9511 |  | 5485.9511 |  | 5485.9511 |  | 5485.9511 |  | 5485.9511 |  | 5485.9511 |  | 5485.9511 |  | 5485.9511
2026-12-12 | 44200.1087 |  |  | 5525.0136 |  | 5525.0136 |  | 5525.0136 |  | 5525.0136 |  | 5525.0136 |  | 5525.0136 |  | 5525.0136 |  | 5525.0136
2026-12-13 | 44512.6087 |  |  | 5564.0761 |  | 5564.0761 |  | 5564.0761 |  | 5564.0761 |  | 5564.0761 |  | 5564.0761 |  | 5564.0761 |  | 5564.0761
2026-12-14 | 44825.1087 |  |  | 5603.1386 |  | 5603.1386 |  | 5603.1386 |  | 5603.1386 |  | 5603.1386 |  | 5603.1386 |  | 5603.1386 |  | 5603.1386
2026-12-15 | 45137.6087 |  |  | 5642.2011 |  | 5642.2011 |  | 5642.2011 |  | 5642.2011 |  | 5642.2011 |  | 5642.2011 |  | 5642.2011 |  | 5642.2011
2026-12-16 | 45450.1087 |  |  | 5681.2636 |  | 5681.2636 |  | 5681.2636 |  | 5681.2636 |  | 5681.2636 |  | 5681.2636 |  | 5681.2636 |  | 5681.2636
2026-12-17 | 45762.6087 |  |  | 5720.3261 |  | 5720.3261 |  | 5720.3261 |  | 5720.3261 |  | 5720.3261 |  | 5720.3261 |  | 5720.3261 |  | 5720.3261
2026-12-18 | 46075.1087 |  |  | 5759.3886 |  | 5759.3886 |  | 5759.3886 |  | 5759.3886 |  | 5759.3886 |  | 5759.3886 |  | 5759.3886 |  | 5759.3886
2026-12-19 | 46387.6087 |  |  | 5798.4511 |  | 5798.4511 |  | 5798.4511 |  | 5798.4511 |  | 5798.4511 |  | 5798.4511 |  | 5798.4511 |  | 5798.4511
2026-12-20 | 46700.1087 |  |  | 5837.5136 |  | 5837.5136 |  | 5837.5136 |  | 5837.5136 |  | 5837.5136 |  | 5837.5136 |  | 5837.5136 |  | 5837.5136
2026-12-21 | 47012.6087 |  |  | 5876.5761 |  | 5876.5761 |  | 5876.5761 |  | 5876.5761 |  | 5876.5761 |  | 5876.5761 |  | 5876.5761 |  | 5876.5761
2026-12-22 | 47325.1087 |  |  | 5915.6386 |  | 5915.6386 |  | 5915.6386 |  | 5915.6386 |  | 5915.6386 |  | 5915.6386 |  | 5915.6386 |  | 5915.6386
2026-12-23 | 47637.6087 |  |  | 5954.7011 |  | 5954.7011 |  | 5954.7011 |  | 5954.7011 |  | 5954.7011 |  | 5954.7011 |  | 5954.7011 |  | 5954.7011
2026-12-24 | 47950.1087 |  |  | 5993.7636 |  | 5993.7636 |  | 5993.7636 |  | 5993.7636 |  | 5993.7636 |  | 5993.7636 |  | 5993.7636 |  | 5993.7636
2026-12-25 | 48262.6087 |  |  | 6032.8261 |  | 6032.8261 |  | 6032.8261 |  | 6032.8261 |  | 6032.8261 |  | 6032.8261 |  | 6032.8261 |  | 6032.8261

## Equipment Cost
Date | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Actual Labor (Cumulative) | Planned 1820 · Equipment & Tools (Cumulative) | Actual 1820 · Equipment & Tools (Cumulative) | Planned 1823 · Equipment - TCU Basic (Cumulative) | Actual 1823 · Equipment - TCU Basic (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0
2025-04-04 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0
2025-04-05 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0
2025-04-06 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0
2025-04-07 | 0 | 5000 | 1126.6 | 0 | 5000 | 0 | 0
2025-04-08 | 0 | 5000 | 2253.2 | 0 | 5000 | 0 | 0
2025-04-09 | 0 | 5000 | 3379.8 | 0 | 5000 | 0 | 0
2025-04-10 | 0 | 5000 | 4506.4 | 0 | 5000 | 0 | 0
2025-04-11 | 0 | 5000 | 5633 | 0 | 5000 | 0 | 0
2025-04-12 | 0 | 5000 | 5633 | 0 | 5000 | 0 | 0
2025-04-13 | 0 | 5000 | 5633 | 0 | 5000 | 0 | 0
2025-04-14 | 0 | 5000 | 5847.4 | 0 | 5000 | 0 | 0
2025-04-15 | 0 | 5000 | 6061.8 | 0 | 5000 | 0 | 0
2025-04-16 | 0 | 5000 | 6276.2 | 0 | 5000 | 0 | 0
2025-04-17 | 0 | 5000 | 6490.6 | 0 | 5000 | 0 | 0
2025-04-18 | 0 | 5000 | 6705 | 0 | 5000 | 0 | 0
2025-04-19 | 0 | 5000 | 6705 | 0 | 5000 | 0 | 0
2025-04-20 | 0 | 5000 | 6705 | 0 | 5000 | 0 | 0
2025-04-21 | 0 | 5000 | 7087.15 | 0 | 5000 | 0 | 0
2025-04-22 | 0 | 5000 | 7469.3 | 0 | 5000 | 0 | 0
2025-04-23 | 0 | 5000 | 7851.45 | 0 | 5000 | 0 | 0
2025-04-24 | 0 | 5000 | 8233.6 | 0 | 5000 | 0 | 0
2025-04-25 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-04-26 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-04-27 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-04-28 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-04-29 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-04-30 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-01 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-02 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-03 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-04 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-05 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-06 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-07 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-08 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-09 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-10 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-11 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-12 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-13 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-14 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-15 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-16 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-17 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-18 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-19 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-20 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-21 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-22 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-23 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-24 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-25 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-26 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-27 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-28 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-29 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-30 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-05-31 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-06-01 | 0 | 5000 | 8615.75 | 0 | 5000 | 0 | 0
2025-06-02 | 0 | 5000 | 9212.3 | 0 | 5000 | 0 | 0
2025-06-03 | 0 | 5000 | 9808.85 | 0 | 5000 | 0 | 0
2025-06-04 | 0 | 5000 | 10405.4 | 0 | 5000 | 0 | 0
2025-06-05 | 0 | 5000 | 11001.95 | 0 | 5000 | 0 | 0
2025-06-06 | 0 | 5000 | 11598.5 | 0 | 5000 | 0 | 0
2025-06-07 | 0 | 5000 | 11598.5 | 0 | 5000 | 0 | 0
2025-06-08 | 0 | 5000 | 11598.5 | 0 | 5000 | 0 | 0
2025-06-09 | 0 | 5000 | 11873.45 | 0 | 5000 | 0 | 0
2025-06-10 | 0 | 5000 | 12148.4 | 0 | 5000 | 0 | 0
2025-06-11 | 0 | 5000 | 12423.35 | 0 | 5000 | 0 | 0
2025-06-12 | 0 | 5000 | 12698.3 | 0 | 5000 | 0 | 0
2025-06-13 | 0 | 5000 | 12973.25 | 0 | 5000 | 0 | 0
2025-06-14 | 0 | 5000 | 12973.25 | 0 | 5000 | 0 | 0
2025-06-15 | 0 | 5000 | 12973.25 | 0 | 5000 | 0 | 0
2025-06-16 | 0 | 5000 | 13523.15 | 0 | 5000 | 0 | 0
2025-06-17 | 0 | 5000 | 14073.05 | 0 | 5000 | 0 | 0
2025-06-18 | 0 | 5000 | 14622.95 | 0 | 5000 | 0 | 0
2025-06-19 | 0 | 5000 | 15172.85 | 0 | 5000 | 0 | 0
2025-06-20 | 0 | 5000 | 15722.75 | 0 | 5000 | 0 | 0
2025-06-21 | 0 | 5000 | 15722.75 | 0 | 5000 | 0 | 0
2025-06-22 | 0 | 5000 | 15722.75 | 0 | 5000 | 0 | 0
2025-06-23 | 0 | 5000 | 15997.7 | 0 | 5000 | 0 | 0
2025-06-24 | 0 | 5000 | 16272.65 | 0 | 5000 | 0 | 0
2025-06-25 | 947.6292 | 5000 | 16547.6 | 473.8146 | 5000 | 473.8146 | 0
2025-06-26 | 1895.2584 | 5000 | 16822.55 | 947.6292 | 5000 | 947.6292 | 0
2025-06-27 | 2842.8876 | 5000 | 17097.5 | 1421.4438 | 5000 | 1421.4438 | 0
2025-06-28 | 3790.5169 | 5000 | 17097.5 | 1895.2584 | 5000 | 1895.2584 | 0
2025-06-29 | 4738.1461 | 5000 | 17097.5 | 2369.073 | 5000 | 2369.073 | 0
2025-06-30 | 5685.7753 | 5000 | 17714.4 | 2842.8876 | 5000 | 2842.8876 | 0
2025-07-01 | 6633.4045 | 5000 | 18331.3 | 3316.7022 | 5000 | 3316.7022 | 0
2025-07-02 | 7581.0337 | 5000 | 18948.2 | 3790.5169 | 5000 | 3790.5169 | 0
2025-07-03 | 8528.6629 | 5000 | 19565.1 | 4264.3315 | 5000 | 4264.3315 | 0
2025-07-04 | 9476.2921 | 5000 | 20182 | 4738.1461 | 5000 | 4738.1461 | 0
2025-07-05 | 10423.9213 | 5000 | 20182 | 5211.9607 | 5000 | 5211.9607 | 0
2025-07-06 | 11371.5506 | 5000 | 20182 | 5685.7753 | 5000 | 5685.7753 | 0
2025-07-07 | 12319.1798 | 5000 | 20835.625 | 6159.5899 | 5000 | 6159.5899 | 0
2025-07-08 | 13266.809 | 5000 | 21489.25 | 6633.4045 | 5000 | 6633.4045 | 0
2025-07-09 | 14214.4382 | 5000 | 22142.875 | 7107.2191 | 5000 | 7107.2191 | 0
2025-07-10 | 15162.0674 | 5000 | 22796.5 | 7581.0337 | 5000 | 7581.0337 | 0
2025-07-11 | 16109.6966 | 5000 | 23450.125 | 8054.8483 | 5000 | 8054.8483 | 0
2025-07-12 | 17057.3258 | 5000 | 23450.125 | 8528.6629 | 5000 | 8528.6629 | 0
2025-07-13 | 18004.9551 | 5000 | 23450.125 | 9002.4775 | 5000 | 9002.4775 | 0
2025-07-14 | 18952.5843 | 5000 | 24210.95 | 9476.2921 | 5000 | 9476.2921 | 0
2025-07-15 | 19900.2135 | 5000 | 24971.775 | 9950.1067 | 5000 | 9950.1067 | 0
2025-07-16 | 20847.8427 | 5000 | 25732.6 | 10423.9213 | 5000 | 10423.9213 | 0
2025-07-17 | 21795.4719 | 5000 | 26493.425 | 10897.736 | 5000 | 10897.736 | 0
2025-07-18 | 22743.1011 | 5000 | 27254.25 | 11371.5506 | 5000 | 11371.5506 | 0
2025-07-19 | 23690.7303 | 5000 | 27254.25 | 11845.3652 | 5000 | 11845.3652 | 0
2025-07-20 | 24638.3596 | 5000 | 27254.25 | 12319.1798 | 5000 | 12319.1798 | 0
2025-07-21 | 25585.9888 | 5000 | 27907.875 | 12792.9944 | 5000 | 12792.9944 | 0
2025-07-22 | 26533.618 | 5000 | 28561.5 | 13266.809 | 5000 | 13266.809 | 0
2025-07-23 | 27481.2472 | 5000 | 29215.125 | 13740.6236 | 5000 | 13740.6236 | 0
2025-07-24 | 28428.8764 | 5000 | 29868.75 | 14214.4382 | 5000 | 14214.4382 | 0
2025-07-25 | 29376.5056 | 5000 | 30522.375 | 14688.2528 | 5000 | 14688.2528 | 0
2025-07-26 | 30324.1348 | 5000 | 30522.375 | 15162.0674 | 5000 | 15162.0674 | 0
2025-07-27 | 31271.764 | 5000 | 30522.375 | 15635.882 | 5000 | 15635.882 | 0
2025-07-28 | 32219.3933 | 5000 | 31122.4 | 16109.6966 | 5000 | 16109.6966 | 0
2025-07-29 | 33167.0225 | 5000 | 31722.425 | 16583.5112 | 5000 | 16583.5112 | 0
2025-07-30 | 34114.6517 | 5000 | 32322.45 | 17057.3258 | 5000 | 17057.3258 | 0
2025-07-31 | 35062.2809 | 5000 | 32922.475 | 17531.1404 | 5000 | 17531.1404 | 0
2025-08-01 | 36009.9101 | 5000 | 33522.5 | 18004.9551 | 5000 | 18004.9551 | 0
2025-08-02 | 36957.5393 | 5000 | 33522.5 | 18478.7697 | 5000 | 18478.7697 | 0
2025-08-03 | 37905.1685 | 5000 | 33522.5 | 18952.5843 | 5000 | 18952.5843 | 0
2025-08-04 | 38852.7978 | 5000 | 34126 | 19426.3989 | 5000 | 19426.3989 | 0
2025-08-05 | 39800.427 | 5000 | 34729.5 | 19900.2135 | 5000 | 19900.2135 | 0
2025-08-06 | 40748.0562 | 5000 | 35333 | 20374.0281 | 5000 | 20374.0281 | 0
2025-08-07 | 41695.6854 | 5000 | 35936.5 | 20847.8427 | 5000 | 20847.8427 | 0
2025-08-08 | 42643.3146 | 5000 | 36540 | 21321.6573 | 5000 | 21321.6573 | 0
2025-08-09 | 43590.9438 | 5000 | 36540 | 21795.4719 | 5000 | 21795.4719 | 0
2025-08-10 | 44538.573 | 5000 | 36540 | 22269.2865 | 5000 | 22269.2865 | 0
2025-08-11 | 45486.2022 | 5000 | 37089.9 | 22743.1011 | 5000 | 22743.1011 | 0
2025-08-12 | 46433.8315 | 5000 | 37639.8 | 23216.9157 | 5000 | 23216.9157 | 0
2025-08-13 | 47381.4607 | 5000 | 38189.7 | 23690.7303 | 5000 | 23690.7303 | 0
2025-08-14 | 48329.0899 | 5000 | 38739.6 | 24164.5449 | 5000 | 24164.5449 | 0
2025-08-15 | 49276.7191 | 5000 | 39289.5 | 24638.3596 | 5000 | 24638.3596 | 0
2025-08-16 | 50224.3483 | 5000 | 39289.5 | 25112.1742 | 5000 | 25112.1742 | 0
2025-08-17 | 51171.9775 | 5000 | 39289.5 | 25585.9888 | 5000 | 25585.9888 | 0
2025-08-18 | 52119.6067 | 5000 | 39993.25 | 26059.8034 | 5000 | 26059.8034 | 0
2025-08-19 | 53067.236 | 5000 | 40697 | 26533.618 | 5000 | 26533.618 | 0
2025-08-20 | 54014.8652 | 5000 | 41400.75 | 27007.4326 | 5000 | 27007.4326 | 0
2025-08-21 | 54962.4944 | 5000 | 42104.5 | 27481.2472 | 5000 | 27481.2472 | 0
2025-08-22 | 55910.1236 | 5000 | 42808.25 | 27955.0618 | 5000 | 27955.0618 | 0
2025-08-23 | 56857.7528 | 5000 | 42808.25 | 28428.8764 | 5000 | 28428.8764 | 0
2025-08-24 | 57805.382 | 5000 | 42808.25 | 28902.691 | 5000 | 28902.691 | 0
2025-08-25 | 58753.0112 | 5000 | 43488.675 | 29376.5056 | 5000 | 29376.5056 | 0
2025-08-26 | 59700.6404 | 5000 | 44169.1 | 29850.3202 | 5000 | 29850.3202 | 0
2025-08-27 | 60648.2697 | 5000 | 44849.525 | 30324.1348 | 5000 | 30324.1348 | 0
2025-08-28 | 61595.8989 | 5000 | 45529.95 | 30797.9494 | 5000 | 30797.9494 | 0
2025-08-29 | 62543.5281 | 5000 | 46210.375 | 31271.764 | 5000 | 31271.764 | 0
2025-08-30 | 63491.1573 | 5000 | 46210.375 | 31745.5787 | 5000 | 31745.5787 | 0
2025-08-31 | 64438.7865 | 5000 | 46210.375 | 32219.3933 | 5000 | 32219.3933 | 0
2025-09-01 | 65386.4157 | 5000 | 47373.7 | 32693.2079 | 5000 | 32693.2079 | 0
2025-09-02 | 66334.0449 | 5000 | 48537.025 | 33167.0225 | 5000 | 33167.0225 | 0
2025-09-03 | 67281.6742 | 5000 | 49700.35 | 33640.8371 | 5000 | 33640.8371 | 0
2025-09-04 | 68229.3034 | 5000 | 50863.675 | 34114.6517 | 5000 | 34114.6517 | 0
2025-09-05 | 69176.9326 | 5000 | 52027 | 34588.4663 | 5000 | 34588.4663 | 0
2025-09-06 | 70124.5618 | 5000 | 52027 | 35062.2809 | 5000 | 35062.2809 | 0
2025-09-07 | 71072.191 | 5000 | 52027 | 35536.0955 | 5000 | 35536.0955 | 0
2025-09-08 | 72019.8202 | 5000 | 52781.375 | 36009.9101 | 5000 | 36009.9101 | 0
2025-09-09 | 72967.4494 | 5000 | 53535.75 | 36483.7247 | 5000 | 36483.7247 | 0
2025-09-10 | 73915.0787 | 5000 | 54290.125 | 36957.5393 | 5000 | 36957.5393 | 0
2025-09-11 | 74862.7079 | 5000 | 55044.5 | 37431.3539 | 5000 | 37431.3539 | 0
2025-09-12 | 75810.3371 | 5000 | 55798.875 | 37905.1685 | 5000 | 37905.1685 | 0
2025-09-13 | 76757.9663 | 5000 | 55798.875 | 38378.9831 | 5000 | 38378.9831 | 0
2025-09-14 | 77705.5955 | 5000 | 55798.875 | 38852.7978 | 5000 | 38852.7978 | 0
2025-09-15 | 78653.2247 | 5000 | 57425.25 | 39326.6124 | 5000 | 39326.6124 | 0
2025-09-16 | 79600.8539 | 5000 | 59051.625 | 39800.427 | 5000 | 39800.427 | 0
2025-09-17 | 80548.4831 | 5000 | 60678 | 40274.2416 | 5000 | 40274.2416 | 0
2025-09-18 | 81496.1124 | 5000 | 62304.375 | 40748.0562 | 5000 | 40748.0562 | 0
2025-09-19 | 82443.7416 | 5000 | 63930.75 | 41221.8708 | 5000 | 41221.8708 | 0
2025-09-20 | 83391.3708 | 5000 | 63930.75 | 41695.6854 | 5000 | 41695.6854 | 0
2025-09-21 | 84339 | 5000 | 63930.75 | 42169.5 | 5000 | 42169.5 | 0
2025-09-22 | 84339 | 5000 | 65705.925 | 42169.5 | 5000 | 42169.5 | 0
2025-09-23 | 84575.6221 | 5000 | 67481.1 | 42287.811 | 5000 | 42287.811 | 0
2025-09-24 | 84812.2441 | 5000 | 69256.275 | 42406.1221 | 5000 | 42406.1221 | 0
2025-09-25 | 85048.8662 | 5000 | 71031.45 | 42524.4331 | 5000 | 42524.4331 | 0
2025-09-26 | 85285.4883 | 5000 | 72806.625 | 42642.7441 | 5000 | 42642.7441 | 0
2025-09-27 | 85522.1104 | 5000 | 72806.625 | 42761.0552 | 5000 | 42761.0552 | 0
2025-09-28 | 85758.7324 | 5000 | 72806.625 | 42879.3662 | 5000 | 42879.3662 | 0
2025-09-29 | 85995.3545 | 5000 | 74913.85 | 42997.6773 | 5000 | 42997.6773 | 0
2025-09-30 | 86231.9766 | 5000 | 77021.075 | 43115.9883 | 5000 | 43115.9883 | 0
2025-10-01 | 86468.5987 | 5000 | 79128.3 | 43234.2993 | 5000 | 43234.2993 | 0
2025-10-02 | 86705.2207 | 5000 | 81235.525 | 43352.6104 | 5000 | 43352.6104 | 0
2025-10-03 | 86941.8428 | 5000 | 83342.75 | 43470.9214 | 5000 | 43470.9214 | 0
2025-10-04 | 87178.4649 | 5000 | 83342.75 | 43589.2324 | 5000 | 43589.2324 | 0
2025-10-05 | 87415.087 | 5000 | 83342.75 | 43707.5435 | 5000 | 43707.5435 | 0
2025-10-06 | 87651.709 | 5000 | 85089.875 | 43825.8545 | 5000 | 43825.8545 | 0
2025-10-07 | 87888.3311 | 5000 | 86837 | 43944.1656 | 5000 | 43944.1656 | 0
2025-10-08 | 88124.9532 | 5000 | 88584.125 | 44062.4766 | 5000 | 44062.4766 | 0
2025-10-09 | 88361.5753 | 5000 | 90331.25 | 44180.7876 | 5000 | 44180.7876 | 0
2025-10-10 | 88598.1973 | 5000 | 92078.375 | 44299.0987 | 5000 | 44299.0987 | 0
2025-10-11 | 88834.8194 | 5000 | 92078.375 | 44417.4097 | 5000 | 44417.4097 | 0
2025-10-12 | 89071.4415 | 5000 | 92078.375 | 44535.7207 | 5000 | 44535.7207 | 0
2025-10-13 | 89308.0635 | 5000 | 93848.825 | 44654.0318 | 5000 | 44654.0318 | 0
2025-10-14 | 89544.6856 | 5000 | 95619.275 | 44772.3428 | 5000 | 44772.3428 | 0
2025-10-15 | 89781.3077 | 5000 | 97389.725 | 44890.6538 | 5000 | 44890.6538 | 0
2025-10-16 | 90017.9298 | 5000 | 99160.175 | 45008.9649 | 5000 | 45008.9649 | 0
2025-10-17 | 90254.5518 | 5000 | 100930.625 | 45127.2759 | 5000 | 45127.2759 | 0
2025-10-18 | 90491.1739 | 5000 | 100930.625 | 45245.587 | 5000 | 45245.587 | 0
2025-10-19 | 90727.796 | 5000 | 100930.625 | 45363.898 | 5000 | 45363.898 | 0
2025-10-20 | 90964.4181 | 5000 | 103046.55 | 45482.209 | 5000 | 45482.209 | 0
2025-10-21 | 91201.0401 | 5000 | 105162.475 | 45600.5201 | 5000 | 45600.5201 | 0
2025-10-22 | 91437.6622 | 5000 | 107278.4 | 45718.8311 | 5000 | 45718.8311 | 0
2025-10-23 | 91674.2843 | 5000 | 109394.325 | 45837.1421 | 5000 | 45837.1421 | 0
2025-10-24 | 91910.9064 | 5000 | 111510.25 | 45955.4532 | 5000 | 45955.4532 | 0
2025-10-25 | 92147.5284 | 5000 | 111510.25 | 46073.7642 | 5000 | 46073.7642 | 0
2025-10-26 | 92384.1505 | 5000 | 111510.25 | 46192.0753 | 5000 | 46192.0753 | 0
2025-10-27 | 92620.7726 | 5000 | 113280.75 | 46310.3863 | 5000 | 46310.3863 | 0
2025-10-28 | 92857.3946 | 5000 | 115051.25 | 46428.6973 | 5000 | 46428.6973 | 0
2025-10-29 | 93094.0167 | 5000 | 116821.75 | 46547.0084 | 5000 | 46547.0084 | 0
2025-10-30 | 93330.6388 | 5000 | 118592.25 | 46665.3194 | 5000 | 46665.3194 | 0
2025-10-31 | 93567.2609 | 5000 | 120362.75 | 46783.6304 | 5000 | 46783.6304 | 0
2025-11-01 | 93803.8829 | 5000 | 120362.75 | 46901.9415 | 5000 | 46901.9415 | 0
2025-11-02 | 94040.505 | 5000 | 120362.75 | 47020.2525 | 5000 | 47020.2525 | 0
2025-11-03 | 94277.1271 | 5000 | 122034.05 | 47138.5635 | 5000 | 47138.5635 | 0
2025-11-04 | 94513.7492 | 5000 | 123705.35 | 47256.8746 | 5000 | 47256.8746 | 0
2025-11-05 | 94750.3712 | 5000 | 125376.65 | 47375.1856 | 5000 | 47375.1856 | 0
2025-11-06 | 94986.9933 | 5000 | 127047.95 | 47493.4967 | 5000 | 47493.4967 | 0
2025-11-07 | 95223.6154 | 5000 | 128719.25 | 47611.8077 | 5000 | 47611.8077 | 0
2025-11-08 | 95460.2375 | 5000 | 128719.25 | 47730.1187 | 5000 | 47730.1187 | 0
2025-11-09 | 95696.8595 | 5000 | 128719.25 | 47848.4298 | 5000 | 47848.4298 | 0
2025-11-10 | 95933.4816 | 5000 | 130337.625 | 47966.7408 | 5000 | 47966.7408 | 0
2025-11-11 | 96170.1037 | 5000 | 131956 | 48085.0518 | 5000 | 48085.0518 | 0
2025-11-12 | 96406.7258 | 5000 | 133574.375 | 48203.3629 | 5000 | 48203.3629 | 0
2025-11-13 | 96643.3478 | 5000 | 135192.75 | 48321.6739 | 5000 | 48321.6739 | 0
2025-11-14 | 97028.6689 | 5000 | 136811.125 | 48514.3345 | 5000 | 48514.3345 | 0
2025-11-15 | 97413.99 | 5000 | 136811.125 | 48706.995 | 5000 | 48706.995 | 0
2025-11-16 | 97799.3111 | 5000 | 136811.125 | 48899.6556 | 5000 | 48899.6556 | 0
2025-11-17 | 98184.6322 | 5000 | 137515.425 | 49092.3161 | 5000 | 49092.3161 | 0
2025-11-18 | 98569.9533 | 5000 | 138219.725 | 49284.9767 | 5000 | 49284.9767 | 0
2025-11-19 | 98955.2744 | 5000 | 138924.025 | 49477.6372 | 5000 | 49477.6372 | 0
2025-11-20 | 99340.5955 | 5000 | 139628.325 | 49670.2978 | 5000 | 49670.2978 | 0
2025-11-21 | 99725.9166 | 5000 | 140332.625 | 49862.9583 | 5000 | 49862.9583 | 0
2025-11-22 | 100111.2377 | 5000 | 140332.625 | 50055.6189 | 5000 | 50055.6189 | 0
2025-11-23 | 100496.5588 | 5000 | 140332.625 | 50248.2794 | 5000 | 50248.2794 | 0
2025-11-24 | 100881.8799 | 5000 | 141144.85 | 50440.94 | 5000 | 50440.94 | 0
2025-11-25 | 101267.201 | 5000 | 141957.075 | 50633.6005 | 5000 | 50633.6005 | 0
2025-11-26 | 101652.5221 | 5000 | 142769.3 | 50826.2611 | 5000 | 50826.2611 | 0
2025-11-27 | 102037.8432 | 5000 | 143581.525 | 51018.9216 | 5000 | 51018.9216 | 0
2025-11-28 | 102423.1643 | 5000 | 144393.75 | 51211.5822 | 5000 | 51211.5822 | 0
2025-11-29 | 102808.4854 | 5000 | 144393.75 | 51404.2427 | 5000 | 51404.2427 | 0
2025-11-30 | 103193.8065 | 5000 | 144393.75 | 51596.9033 | 5000 | 51596.9033 | 0
2025-12-01 | 103579.1276 | 5217.06 | 145486.9 | 51789.5638 | 5000 | 51789.5638 | 217.06
2025-12-02 | 103964.4487 | 5217.06 | 146580.05 | 51982.2244 | 5000 | 51982.2244 | 217.06
2025-12-03 | 104349.7698 | 5217.06 | 147673.2 | 52174.8849 | 5000 | 52174.8849 | 217.06
2025-12-04 | 104735.0909 | 5217.06 | 148766.35 | 52367.5455 | 5000 | 52367.5455 | 217.06
2025-12-05 | 105120.412 | 5217.06 | 149859.5 | 52560.206 | 5000 | 52560.206 | 217.06
2025-12-06 | 105505.7331 | 5217.06 | 149859.5 | 52752.8666 | 5000 | 52752.8666 | 217.06
2025-12-07 | 105891.0542 | 5217.06 | 149859.5 | 52945.5271 | 5000 | 52945.5271 | 217.06
2025-12-08 | 106276.3753 | 5217.06 | 151023.125 | 53138.1877 | 5000 | 53138.1877 | 217.06
2025-12-09 | 106661.6964 | 5217.06 | 152186.75 | 53330.8482 | 5000 | 53330.8482 | 217.06
2025-12-10 | 107047.0176 | 5217.06 | 153350.375 | 53523.5088 | 5000 | 53523.5088 | 217.06
2025-12-11 | 107432.3387 | 5217.06 | 154514 | 53716.1693 | 5000 | 53716.1693 | 217.06
2025-12-12 | 107817.6598 | 5217.06 | 155677.625 | 53908.8299 | 5000 | 53908.8299 | 217.06
2025-12-13 | 108202.9809 | 5217.06 | 155677.625 | 54101.4904 | 5000 | 54101.4904 | 217.06
2025-12-14 | 108588.302 | 5217.06 | 155677.625 | 54294.151 | 5000 | 54294.151 | 217.06
2025-12-15 | 108973.6231 | 5217.06 | 156841.25 | 54486.8115 | 5000 | 54486.8115 | 217.06
2025-12-16 | 109358.9442 | 5217.06 | 158004.875 | 54679.4721 | 5000 | 54679.4721 | 217.06
2025-12-17 | 109744.2653 | 5217.06 | 159168.5 | 54872.1326 | 5000 | 54872.1326 | 217.06
2025-12-18 | 110129.5864 | 5217.06 | 160332.125 | 55064.7932 | 5000 | 55064.7932 | 217.06
2025-12-19 | 110514.9075 | 5217.06 | 161495.75 | 55257.4537 | 5000 | 55257.4537 | 217.06
2025-12-20 | 110900.2286 | 5217.06 | 161495.75 | 55450.1143 | 5000 | 55450.1143 | 217.06
2025-12-21 | 111285.5497 | 5217.06 | 161495.75 | 55642.7748 | 5000 | 55642.7748 | 217.06
2025-12-22 | 111670.8708 | 5217.06 | 161495.75 | 55835.4354 | 5000 | 55835.4354 | 217.06
2025-12-23 | 112056.1919 | 5217.06 | 161495.75 | 56028.0959 | 5000 | 56028.0959 | 217.06
2025-12-24 | 112441.513 | 5217.06 | 161495.75 | 56220.7565 | 5000 | 56220.7565 | 217.06
2025-12-25 | 112826.8341 | 5217.06 | 161495.75 | 56413.417 | 5000 | 56413.417 | 217.06
2025-12-26 | 113212.1552 | 5217.06 | 161495.75 | 56606.0776 | 5000 | 56606.0776 | 217.06
2025-12-27 | 113597.4763 | 5217.06 | 161495.75 | 56798.7381 | 5000 | 56798.7381 | 217.06
2025-12-28 | 113982.7974 | 5217.06 | 161495.75 | 56991.3987 | 5000 | 56991.3987 | 217.06
2025-12-29 | 114368.1185 | 5217.06 | 162393.1 | 57184.0592 | 5000 | 57184.0592 | 217.06
2025-12-30 | 114753.4396 | 5217.06 | 163290.45 | 57376.7198 | 5000 | 57376.7198 | 217.06
2025-12-31 | 115138.7607 | 5217.06 | 164187.8 | 57569.3803 | 5000 | 57569.3803 | 217.06
2026-01-01 | 115524.0818 | 5217.06 | 165085.15 | 57762.0409 | 5000 | 57762.0409 | 217.06
2026-01-02 | 115909.4029 | 5217.06 | 165982.5 | 57954.7014 | 5000 | 57954.7014 | 217.06
2026-01-03 | 116294.724 | 5217.06 | 165982.5 | 58147.362 | 5000 | 58147.362 | 217.06
2026-01-04 | 116680.0451 | 5217.06 | 165982.5 | 58340.0225 | 5000 | 58340.0225 | 217.06
2026-01-05 | 117065.3662 | 5217.06 | 167054.925 | 58532.6831 | 5000 | 58532.6831 | 217.06
2026-01-06 | 117450.6873 | 5217.06 | 168127.35 | 58725.3436 | 5000 | 58725.3436 | 217.06
2026-01-07 | 117836.0084 | 5217.06 | 169199.775 | 58918.0042 | 5000 | 58918.0042 | 217.06
2026-01-08 | 118221.3295 | 5217.06 | 170272.2 | 59110.6647 | 5000 | 59110.6647 | 217.06
2026-01-09 | 118606.6506 | 5217.06 | 171344.625 | 59303.3253 | 5000 | 59303.3253 | 217.06
2026-01-10 | 118991.9717 | 5217.06 | 171344.625 | 59495.9858 | 5000 | 59495.9858 | 217.06
2026-01-11 | 119377.2928 | 5217.06 | 171344.625 | 59688.6464 | 5000 | 59688.6464 | 217.06
2026-01-12 | 119762.6139 | 5217.06 | 172044.925 | 59881.3069 | 5000 | 59881.3069 | 217.06
2026-01-13 | 120147.935 | 5217.06 | 172745.225 | 60073.9675 | 5000 | 60073.9675 | 217.06
2026-01-14 | 120533.2561 | 5217.06 | 173445.525 | 60266.628 | 5000 | 60266.628 | 217.06
2026-01-15 | 120918.5772 | 5217.06 | 174145.825 | 60459.2886 | 5000 | 60459.2886 | 217.06
2026-01-16 | 121303.8983 | 5217.06 | 174846.125 | 60651.9491 | 5000 | 60651.9491 | 217.06
2026-01-17 | 121689.2194 | 5217.06 | 174846.125 | 60844.6097 | 5000 | 60844.6097 | 217.06
2026-01-18 | 122074.5405 | 5217.06 | 174846.125 | 61037.2702 | 5000 | 61037.2702 | 217.06
2026-01-19 | 122459.8616 | 5217.06 | 175873.425 | 61229.9308 | 5000 | 61229.9308 | 217.06
2026-01-20 | 122845.1827 | 5217.06 | 176900.725 | 61422.5913 | 5000 | 61422.5913 | 217.06
2026-01-21 | 123230.5038 | 5217.06 | 177928.025 | 61615.2519 | 5000 | 61615.2519 | 217.06
2026-01-22 | 123615.8249 | 5217.06 | 178955.325 | 61807.9124 | 5000 | 61807.9124 | 217.06
2026-01-23 | 124001.146 | 5217.06 | 179982.625 | 62000.573 | 5000 | 62000.573 | 217.06
2026-01-24 | 124386.4671 | 5217.06 | 179982.625 | 62193.2335 | 5000 | 62193.2335 | 217.06
2026-01-25 | 124771.7882 | 5217.06 | 179982.625 | 62385.8941 | 5000 | 62385.8941 | 217.06
2026-01-26 | 125157.1093 | 5217.06 | 181735.85 | 62578.5546 | 5000 | 62578.5546 | 217.06
2026-01-27 | 125542.4304 | 5217.06 | 183489.075 | 62771.2152 | 5000 | 62771.2152 | 217.06
2026-01-28 | 125927.7515 | 5217.06 | 185242.3 | 62963.8757 | 5000 | 62963.8757 | 217.06
2026-01-29 | 126313.0726 | 5217.06 | 186995.525 | 63156.5363 | 5000 | 63156.5363 | 217.06
2026-01-30 | 126698.3937 | 5217.06 | 188748.75 | 63349.1968 | 5000 | 63349.1968 | 217.06
2026-01-31 | 127083.7148 | 5217.06 | 188748.75 | 63541.8574 | 5000 | 63541.8574 | 217.06
2026-02-01 | 127469.0359 | 5217.06 | 188748.75 | 63734.5179 | 5000 | 63734.5179 | 217.06
2026-02-02 | 127854.357 | 5217.06 | 189828.5 | 63927.1785 | 5000 | 63927.1785 | 217.06
2026-02-03 | 128239.6781 | 5217.06 | 190908.25 | 64119.8391 | 5000 | 64119.8391 | 217.06
2026-02-04 | 128624.9992 | 5217.06 | 191988 | 64312.4996 | 5000 | 64312.4996 | 217.06
2026-02-05 | 129010.3203 | 5217.06 | 193067.75 | 64505.1602 | 5000 | 64505.1602 | 217.06
2026-02-06 | 129395.6414 | 5217.06 | 194147.5 | 64697.8207 | 5000 | 64697.8207 | 217.06
2026-02-07 | 129780.9625 | 5217.06 | 194147.5 | 64890.4813 | 5000 | 64890.4813 | 217.06
2026-02-08 | 130166.2836 | 5217.06 | 194147.5 | 65083.1418 | 5000 | 65083.1418 | 217.06
2026-02-09 | 130551.6047 | 5217.06 | 195428.55 | 65275.8024 | 5000 | 65275.8024 | 217.06
2026-02-10 | 130936.9258 | 5217.06 | 196709.6 | 65468.4629 | 5000 | 65468.4629 | 217.06
2026-02-11 | 131322.2469 | 5217.06 | 197990.65 | 65661.1235 | 5000 | 65661.1235 | 217.06
2026-02-12 | 131707.568 | 5217.06 | 199271.7 | 65853.784 | 5000 | 65853.784 | 217.06
2026-02-13 | 132092.8891 | 5217.06 | 200552.75 | 66046.4446 | 5000 | 66046.4446 | 217.06
2026-02-14 | 132478.2102 | 5217.06 | 200552.75 | 66239.1051 | 5000 | 66239.1051 | 217.06
2026-02-15 | 132863.5313 | 5217.06 | 200552.75 | 66431.7657 | 5000 | 66431.7657 | 217.06
2026-02-16 | 133248.8524 | 5217.06 | 201679.45 | 66624.4262 | 5000 | 66624.4262 | 217.06
2026-02-17 | 133634.1735 | 5217.06 | 202806.15 | 66817.0868 | 5000 | 66817.0868 | 217.06
2026-02-18 | 134019.4946 | 5217.06 | 203932.85 | 67009.7473 | 5000 | 67009.7473 | 217.06
2026-02-19 | 134404.8157 | 5217.06 | 205059.55 | 67202.4079 | 5000 | 67202.4079 | 217.06
2026-02-20 | 134790.1368 | 5217.06 | 206186.25 | 67395.0684 | 5000 | 67395.0684 | 217.06
2026-02-21 | 135175.4579 | 5217.06 | 206186.25 | 67587.729 | 5000 | 67587.729 | 217.06
2026-02-22 | 135560.779 | 5217.06 | 206186.25 | 67780.3895 | 5000 | 67780.3895 | 217.06
2026-02-23 | 135946.1001 | 5217.06 | 207266 | 67973.0501 | 5000 | 67973.0501 | 217.06
2026-02-24 | 136331.4212 | 5217.06 | 208345.75 | 68165.7106 | 5000 | 68165.7106 | 217.06
2026-02-25 | 136716.7423 | 5217.06 | 209425.5 | 68358.3712 | 5000 | 68358.3712 | 217.06
2026-02-26 | 137102.0634 | 5217.06 | 210505.25 | 68551.0317 | 5000 | 68551.0317 | 217.06
2026-02-27 | 137487.3845 | 5217.06 | 211585 | 68743.6923 | 5000 | 68743.6923 | 217.06
2026-02-28 | 137872.7056 | 5217.06 | 211585 | 68936.3528 | 5000 | 68936.3528 | 217.06
2026-03-01 | 138258.0267 | 5217.06 | 211585 | 69129.0134 | 5000 | 69129.0134 | 217.06
2026-03-02 | 138643.3478 | 5217.06 | 211980.75 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-03 | 138643.3478 | 5217.06 | 212376.5 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-04 | 138643.3478 | 5217.06 | 212772.25 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-05 | 138643.3478 | 5217.06 | 213168 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-06 | 138643.3478 | 5217.06 | 213563.75 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-07 | 138643.3478 | 5217.06 | 213563.75 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-08 | 138643.3478 | 5217.06 | 213563.75 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-09 | 138643.3478 | 5217.06 | 213761.625 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-10 | 138643.3478 | 5217.06 | 213959.5 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-11 | 138643.3478 | 5217.06 | 214157.375 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-12 | 138643.3478 | 5217.06 | 214355.25 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-13 | 138643.3478 | 5217.06 | 214553.125 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-14 | 138643.3478 | 5217.06 | 214553.125 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-15 | 138643.3478 | 5217.06 | 214553.125 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-16 | 138643.3478 | 5217.06 | 215408.95 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-17 | 138643.3478 | 5217.06 | 216264.775 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-18 | 138643.3478 | 5217.06 | 217120.6 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-19 | 138643.3478 | 5217.06 | 217976.425 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-20 | 138643.3478 | 5217.06 | 218832.25 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-21 | 138643.3478 | 5217.06 | 218832.25 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-22 | 138643.3478 | 5217.06 | 218832.25 | 69321.6739 | 5000 | 69321.6739 | 217.06
2026-03-23 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-03-24 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-03-25 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-03-26 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-03-27 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-03-28 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-03-29 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-03-30 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-03-31 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-01 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-02 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-03 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-04 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-05 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-06 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-07 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-08 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-09 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-10 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-11 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-12 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-13 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-14 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-15 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-16 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-17 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-18 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-19 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-20 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-21 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-22 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-23 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-24 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-25 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-26 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-27 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-28 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-29 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-04-30 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-01 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-02 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-03 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-04 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-05 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-06 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-07 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-08 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-09 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-10 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-11 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-12 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-13 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-14 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-15 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-16 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-17 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-18 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-19 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-20 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-21 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-22 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-23 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-24 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-25 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-26 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-27 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-28 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-29 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-30 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-05-31 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-01 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-02 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-03 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-04 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-05 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-06 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-07 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-08 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-09 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-10 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-11 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-12 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-13 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-14 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-15 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-16 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-17 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-18 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-19 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-20 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-21 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-22 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-23 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-24 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-25 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-26 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-27 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-28 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-29 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-06-30 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-01 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-02 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-03 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-04 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-05 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-06 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-07 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-08 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-09 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-10 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-11 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-12 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-13 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-14 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-15 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-16 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-17 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-18 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-19 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-20 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-21 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-22 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-23 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-24 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-25 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-26 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-27 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-28 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-29 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-30 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-07-31 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-01 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-02 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-03 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-04 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-05 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-06 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-07 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-08 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-09 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-10 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-11 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-12 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-13 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-14 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-15 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-16 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-17 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-18 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-19 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-20 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-21 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-22 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-23 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-24 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-25 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-26 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-27 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-28 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-29 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-30 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-08-31 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-01 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-02 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-03 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-04 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-05 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-06 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-07 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-08 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-09 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-10 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-11 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-12 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-13 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-14 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-15 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-16 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-17 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-18 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-19 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-20 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-21 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-22 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-23 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-24 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-25 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-26 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-27 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-28 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-29 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-09-30 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-01 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-02 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-03 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-04 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-05 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-06 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-07 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-08 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-09 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-10 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-11 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-12 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-13 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-14 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-15 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-16 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-17 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-18 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-19 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-20 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-21 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-22 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-23 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-24 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-25 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-26 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-27 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-28 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-29 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-30 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-10-31 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-01 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-02 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-03 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-04 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-05 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-06 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-07 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-08 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-09 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-10 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-11 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-12 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-13 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-14 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-15 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-16 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-17 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-18 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-19 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-20 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-21 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-22 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-23 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-24 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-25 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-26 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-27 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-28 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-29 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-11-30 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-01 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-02 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-03 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-04 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-05 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-06 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-07 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-08 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-09 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-10 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-11 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-12 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-13 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-14 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-15 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-16 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-17 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-18 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-19 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-20 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-21 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-22 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-23 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-24 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739
2026-12-25 | 138643.3478 |  |  | 69321.6739 |  | 69321.6739

## Labor Days
Month | Actual Geo Total (Monthly) | Actual On Site Personal (Monthly) | Actual Remote Personal (Monthly) | Planned GEO total personal (Monthly) | Planned on site personal (Monthly) | Planned remote personal (Monthly) | Planned Technician I (Monthly) | Actual Technician I (Monthly) | Planned Technician II (Monthly) | Actual Technician II (Monthly) | Planned Welder (Monthly) | Actual Welder (Monthly) | Planned Engineer/supervisor (Monthly) | Actual Engineer/supervisor (Monthly) | Planned Manager/senior Engineer (Monthly) | Actual Manager/senior Engineer (Monthly) | Planned Remote mid engineer (Monthly) | Actual Remote mid engineer (Monthly) | Planned Remote senior (Monthly) | Actual Remote senior (Monthly)
April 25 | 14.5 | 0 | 14.5 | 46.9 | 0 | 46.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.25 | 46.9 | 6.25
May 25 | 0 | 0 | 0 | 49.1333 | 0 | 49.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.1333 | 0
June 25 | 19.375 | 0 | 19.375 | 39.3 | 1.3333 | 37.9667 | 0 | 0 | 0.88889 | 0 | 0 | 0 | 0.44444 | 0 | 0 | 0 | 0 | 10.625 | 37.9667 | 8.75
July 25 | 23 | 1 | 22 | 7.6667 | 7.6667 | 0 | 0 | 0 | 5.1111 | 0 | 0 | 0 | 2.5556 | 1 | 0 | 0 | 0 | 14.5 | 0 | 7.5
August 25 | 21.625 | 0 | 21.625 | 7 | 7 | 0 | 0 | 0 | 4.6667 | 0 | 0 | 0 | 2.3333 | 0 | 0 | 0 | 0 | 13.5 | 0 | 8.125
September 25 | 68.625 | 32.125 | 36.5 | 54.9145 | 51.125 | 3.7895 | 0 | 0 | 35.2478 | 32.125 | 9.4737 | 0 | 1.6667 | 0 | 4.7368 | 0 | 0 | 14.875 | 3.7895 | 21.625
October 25 | 75 | 60 | 15 | 191.3388 | 176.8125 | 14.5263 | 0 | 0 | 122.3388 | 60 | 36.3158 | 0 | 0 | 0 | 18.1579 | 0 | 0 | 3 | 14.5263 | 12
November 25 | 47.875 | 37.25 | 10.625 | 119.7268 | 105.6829 | 14.0438 | 3.1193 | 0 | 55.202 | 37.25 | 26.6876 | 0 | 5.7706 | 0 | 14.9034 | 0 | 0 | 0.625 | 14.0438 | 10
December 25 | 44.375 | 38 | 6.375 | 81.7945 | 66.5505 | 15.244 | 5.6881 | 0 | 13.367 | 38 | 22.7523 | 0 | 10.5229 | 0 | 14.2202 | 0 | 0 | 0.125 | 15.244 | 6.25
January 26 | 45.375 | 35.5 | 9.875 | 81.7945 | 66.5505 | 15.244 | 5.6881 | 0 | 13.367 | 27.5 | 22.7523 | 8 | 10.5229 | 0 | 14.2202 | 0 | 0 | 1.125 | 15.244 | 8.75
February 26 | 46.875 | 40 | 6.875 | 73.8789 | 60.1101 | 13.7688 | 5.1376 | 0 | 12.0734 | 40 | 20.5505 | 0 | 9.5046 | 0 | 12.844 | 0 | 0 | 0.125 | 13.7688 | 6.75
March 26 | 14.125 | 10.375 | 3.75 | 46.1718 | 25.2936 | 20.8782 | 21.367 | 0 | 0.86239 | 10.375 | 1.4679 | 0 | 0.6789 | 0 | 0.91743 | 0 | 0 | 0 | 20.8782 | 3.75
April 26 | 0 | 0 | 0 | 42.8421 | 22 | 20.8421 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8421 | 0
May 26 | 0 | 0 | 0 | 40.8947 | 21 | 19.8947 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.8947 | 0
June 26 | 0 | 0 | 0 | 42.8421 | 22 | 20.8421 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8421 | 0
July 26 | 0 | 0 | 0 | 44.7895 | 23 | 21.7895 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.7895 | 0
August 26 | 0 | 0 | 0 | 40.8947 | 21 | 19.8947 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.8947 | 0
September 26 | 0 | 0 | 0 | 42.8421 | 22 | 20.8421 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8421 | 0
October 26 | 0 | 0 | 0 | 42.8421 | 22 | 20.8421 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8421 | 0
November 26 | 0 | 0 | 0 | 51.6162 | 30.5833 | 21.0329 | 18.9167 | 0 | 2.9167 | 0 | 5.8333 | 0 | 2.9167 | 0 | 0 | 0 | 0 | 0 | 21.0329 | 0
December 26 | 0 | 0 | 0 | 77.7417 | 55.4167 | 22.325 | 11.0833 | 0 | 11.0833 | 0 | 22.1667 | 0 | 11.0833 | 0 | 0 | 0 | 0 | 0 | 22.325 | 0

## Deleted Duplicates
Date | Account | Amount | Type | Num | Memo | Split | Source_File | Category
No duplicates found