## Summary
Task ID | Task Name | Status | Start Date | End Date | Duration | Actual Duration | Duration % | Invoice | Income Received | Income % | Planned Spend | Actual Spend | Spent Cost % | Profit % | Planned Labor Days | Actual Labor Days | Applied Labor %
200 | Design Activities | Completed | 2025-04-02 | 2025-06-24 | 60 | 60 | 100% | 96480 | 96480 | 100% | 80400 | 19628.44 | 24% | 392% | 134 | 22.75 | 17%
300 | Pre-Mobilization, Procurement and Manufacturing | Completed | 2025-06-25 | 2025-09-21 | 63 | 63 | 100% | 412231.3668 | 358685.61 | 87.01% | 199649.043 | 77323.215 | 39% | 364% | 21 | 64.5 | 512.7%
400 | Drilling and Subsurface Installation | In Progress | 2025-09-29 | 2025-11-18 | 37 | 20 | 54% | 371216.5516 | 0 | 0% | 284958.9561 | 62843.93 | 22% | -100% | 316.125 | 32.5 | 18.33%
500 | Field Construction | Future | 2025-11-19 | 2026-02-10 | 60 |  |  | 361680.2306 | 0 | 0% | 280440.1921 | 0 |  |  | 287.6 | 0
600 | Operation | Future | 2026-02-11 | 2026-08-19 | 190 |  |  | 376851.0145 | 0 | 0% | 313382.9288 | 0 |  |  | 370 | 0
700 | Demobilization | Future | 2026-08-20 | 2026-09-22 | 24 |  |  | 78952.6325 | 0 | 0% | 64960.5271 | 0 |  |  | 98.2 | 0
TOTAL | PROJECT TOTAL |  | 2025-04-02 | 2026-09-22 | 434 | 143 | 0.32949 | 1697411.796 | 455165.61 | 0.26815 | 1223791.647 | 159795.585 | 0.13057 | 1.8484 | 1226.925 | 119.75 | 0.097602

## Invoice Sum
Date | Planned Income (Cumulative) | Actual Income (Daily) | Actual Income (Cumulative) | Planned Labor Sum (Cumulative) | Planned Travel&perdiem (Direct Cost) Sum (Cumulative) | Planned Parts&materials (Direct Cost) Sum (Cumulative) | Planned Outsource (Direct Cost) Sum (Cumulative) | Planned Equipment (Cumulative) | Planned 1805 · EQUIPMENT - FORKLIFT (Cumulative) | Planned 1818 · EQUIPMENT - BCU (Cumulative) | Planned 1819 · EQUIPMENT - TPMB (Cumulative) | Planned 1820 · EQUIPMENT & TOOLS (Cumulative) | Planned 1821 · EQUIPMENT - C3 (Cumulative) | Planned 1822 · EQUIPMENT - C2 (Cumulative) | Planned 1823 · EQUIPMENT - TCU BASIC (Cumulative) | Planned 1824 · EQUIPMENT - TCU PLC (Cumulative) | Planned 1825 · EQUIPMENT - BLOWER SKIDS (Cumulative) | Planned 1826 · EQUIPMENT - WELL HEADS (Cumulative) | Planned 1827 · EQUIPMENT - THERMAL WELLS (Cumulative) | Planned 1829 · EQUIPMENT - WATER TREATMENT SYS (Cumulative) | Planned 1830 · EQUIPMENT - VAPOR EXTRACTION (Cumulative) | Planned 1831 · EQUIPMENT - GTR/C3 COMPONENTS (Cumulative) | Planned 1832 · EQUIP - CONTROL/DIST PANELS (Cumulative) | Planned 1833 · EQUIPMENT - OFFICE & COMPUTER (Cumulative) | Planned 5004 · GTR COST OF SALES - PARTS (Cumulative) | Planned 5006 · DRILLING EXPENSE (Cumulative) | Planned 5101 · SALARY AND WAGES (DIRECT) (Cumulative) | Planned 5102 · PAYROLL TAXES (DIRECT) (Cumulative) | Planned 5105 · TRAVEL - AIRFARE (DIRECT) (Cumulative) | Planned 5106 · TRAVEL - HOTEL (DIRECT) (Cumulative) | Planned 5107 · TRAVEL - OTHER (DIRECT) (Cumulative) | Planned 5108 · MEALS & ENTERTAINMENT (DIRECT) (Cumulative) | Planned 5110 · TEMPORARY LABOR (DIRECT) (Cumulative) | Planned 5111 · PARTS & MATERIAL COSTS (DIRECT) (Cumulative) | Planned 5112 · CARBON & LAB SAMPLIES (DRIECT) (Cumulative) | Planned 5113 · REPAIRS & MAINT (DIRECT) (Cumulative) | Planned 5114 · RENT - BUILDING (DIRECT) (Cumulative) | Planned 5115 · RENT - EQUIPMENT (DIRECT) (Cumulative) | Planned 5116 · Rent - Storage (Direct) (Cumulative) | Planned 5120 · OUTSIDE SERVICES (DIRECT) (Cumulative) | Planned 5121 · FREIGHT & SHIPPING (DIRECT) (Cumulative) | Planned 5122 · MOTOR VEHICLE EXP (DIRECT) (Cumulative) | Planned 5123 · AUTO FUEL (DIRECT) (Cumulative) | Planned 5124 · LICENSE AND PERMITS (DIRECT) (Cumulative) | Planned 5128 · HEALTH & SAFETY EQUIP (DIRECT) (Cumulative) | Planned 5129 · MISC EXPENSES (DIRECT) (Cumulative) | Planned 5132 · INTERNET FEE (DIRECT) (Cumulative) | Planned 6999 · UNCATEGORIZED EXPENSES (Cumulative)
2025-04-02 | 1148.5714 | 0 | 0 | 1148.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 2297.1429 | 0 | 0 | 2297.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2297.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 3445.7143 | 0 | 0 | 3445.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3445.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 4594.2857 | 0 | 0 | 4594.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4594.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 5742.8571 | 0 | 0 | 5742.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5742.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 6891.4286 | 0 | 0 | 6891.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6891.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 8040 | 0 | 0 | 8040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 9188.5714 | 51408 | 51408 | 9188.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9188.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 10337.1429 | 0 | 51408 | 10337.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10337.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 11485.7143 | 0 | 51408 | 11485.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11485.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 12634.2857 | 0 | 51408 | 12634.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12634.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 13782.8571 | 0 | 51408 | 13782.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13782.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 14931.4286 | 0 | 51408 | 14931.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14931.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 16080 | 0 | 51408 | 16080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 17228.5714 | 0 | 51408 | 17228.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17228.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 18377.1429 | 0 | 51408 | 18377.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18377.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 19525.7143 | 0 | 51408 | 19525.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19525.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 20674.2857 | 0 | 51408 | 20674.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20674.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 21822.8571 | 0 | 51408 | 21822.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21822.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 22971.4286 | 0 | 51408 | 22971.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22971.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 24120 | 0 | 51408 | 24120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 25268.5714 | 0 | 51408 | 25268.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25268.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 26417.1429 | 0 | 51408 | 26417.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26417.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 27565.7143 | 0 | 51408 | 27565.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27565.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 28714.2857 | 0 | 51408 | 28714.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28714.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 29862.8571 | 0 | 51408 | 29862.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29862.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 31011.4286 | 0 | 51408 | 31011.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31011.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 32160 | 0 | 51408 | 32160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 33308.5714 | 0 | 51408 | 33308.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33308.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 34457.1429 | 0 | 51408 | 34457.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34457.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 35605.7143 | 0 | 51408 | 35605.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35605.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 36754.2857 | 0 | 51408 | 36754.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36754.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 37902.8571 | 0 | 51408 | 37902.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37902.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 39051.4286 | 0 | 51408 | 39051.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39051.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 40200 | 0 | 51408 | 40200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 41348.5714 | 0 | 51408 | 41348.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41348.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 42497.1429 | 0 | 51408 | 42497.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42497.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 43645.7143 | 0 | 51408 | 43645.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43645.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 44794.2857 | 0 | 51408 | 44794.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44794.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 45942.8571 | 0 | 51408 | 45942.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45942.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 47091.4286 | 0 | 51408 | 47091.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47091.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 48240 | 0 | 51408 | 48240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 49388.5714 | 0 | 51408 | 49388.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49388.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 50537.1429 | 0 | 51408 | 50537.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50537.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 51685.7143 | 0 | 51408 | 51685.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51685.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 52834.2857 | 0 | 51408 | 52834.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52834.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 53982.8571 | 0 | 51408 | 53982.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53982.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 55131.4286 | 0 | 51408 | 55131.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55131.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 56280 | 0 | 51408 | 56280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 57428.5714 | 0 | 51408 | 57428.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57428.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 58577.1429 | 0 | 51408 | 58577.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58577.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 59725.7143 | 0 | 51408 | 59725.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59725.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 60874.2857 | 0 | 51408 | 60874.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60874.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 62022.8571 | 0 | 51408 | 62022.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62022.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 63171.4286 | 0 | 51408 | 63171.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63171.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 64320 | 0 | 51408 | 64320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 65468.5714 | 45072 | 96480 | 65468.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65468.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 66617.1429 | 0 | 96480 | 66617.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66617.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 67765.7143 | 0 | 96480 | 67765.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67765.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 68914.2857 | 0 | 96480 | 68914.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68914.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 70062.8571 | 0 | 96480 | 70062.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70062.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 71211.4286 | 0 | 96480 | 71211.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71211.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 72360 | 0 | 96480 | 72360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 73508.5714 | 0 | 96480 | 73508.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73508.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 74657.1429 | 0 | 96480 | 74657.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74657.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 75805.7143 | 0 | 96480 | 75805.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75805.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 76954.2857 | 0 | 96480 | 76954.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76954.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 78102.8571 | 0 | 96480 | 78102.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78102.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 79251.4286 | 0 | 96480 | 79251.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79251.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 80400 | 0 | 96480 | 80400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 81548.5714 | 0 | 96480 | 81548.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81548.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 82697.1429 | 0 | 96480 | 82697.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82697.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 83845.7143 | 0 | 96480 | 83845.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83845.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 84994.2857 | 0 | 96480 | 84994.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84994.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 86142.8571 | 0 | 96480 | 86142.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86142.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 87291.4286 | 0 | 96480 | 87291.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87291.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 88440 | 0 | 96480 | 88440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 89588.5714 | 0 | 96480 | 89588.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89588.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 90737.1429 | 0 | 96480 | 90737.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90737.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 91885.7143 | 0 | 96480 | 91885.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91885.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 93034.2857 | 0 | 96480 | 93034.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93034.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 94182.8571 | 0 | 96480 | 94182.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94182.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 95331.4286 | 0 | 96480 | 95331.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95331.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 96480 | 0 | 96480 | 96480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 101111.8131 | 0 | 96480 | 96707.2708 | 162.3119 | 1462.3349 | 424.7191 | 2355.1764 | 0 | 0 | 63.627 | 0 | 0 | 1872.5843 | 105.1685 | 0 | 0 | 49.0787 | 0 | 0 | 111.3472 | 153.3708 | 0 | 0 | 0 | 0 | 96707.2708 | 0 | 62.8737 | 65.7303 | 3.3708 | 8.427 | 0 | 1462.3349 | 0 | 0 | 1.1236 | 29.2135 | 73.0337 | 146.0674 | 146.0674 | 21.9101 | 0 | 0 | 0 | 0 | 29.2135 | 0
2025-06-26 | 105743.6262 | 0 | 96480 | 96934.5415 | 324.6238 | 2924.6699 | 849.4382 | 4710.3528 | 0 | 0 | 127.2539 | 0 | 0 | 3745.1685 | 210.3371 | 0 | 0 | 98.1573 | 0 | 0 | 222.6944 | 306.7416 | 0 | 0 | 0 | 0 | 96934.5415 | 0 | 125.7474 | 131.4607 | 6.7416 | 16.8539 | 0 | 2924.6699 | 0 | 0 | 2.2472 | 58.427 | 146.0674 | 292.1348 | 292.1348 | 43.8202 | 0 | 0 | 0 | 0 | 58.427 | 0
2025-06-27 | 110375.4393 | 0 | 96480 | 97161.8123 | 486.9357 | 4387.0048 | 1274.1573 | 7065.5292 | 0 | 0 | 190.8809 | 0 | 0 | 5617.7528 | 315.5056 | 0 | 0 | 147.236 | 0 | 0 | 334.0416 | 460.1124 | 0 | 0 | 0 | 0 | 97161.8123 | 0 | 188.6211 | 197.191 | 10.1124 | 25.2809 | 0 | 4387.0048 | 0 | 0 | 3.3708 | 87.6404 | 219.1011 | 438.2022 | 438.2022 | 65.7303 | 0 | 0 | 0 | 0 | 87.6404 | 0
2025-06-28 | 115007.2524 | 0 | 96480 | 97389.083 | 649.2476 | 5849.3398 | 1698.8764 | 9420.7056 | 0 | 0 | 254.5079 | 0 | 0 | 7490.3371 | 420.6742 | 0 | 0 | 196.3146 | 0 | 0 | 445.3888 | 613.4831 | 0 | 0 | 0 | 0 | 97389.083 | 0 | 251.4948 | 262.9213 | 13.4831 | 33.7079 | 0 | 5849.3398 | 0 | 0 | 4.4944 | 116.8539 | 292.1348 | 584.2697 | 584.2697 | 87.6404 | 0 | 0 | 0 | 0 | 116.8539 | 0
2025-06-29 | 119639.0655 | 0 | 96480 | 97616.3538 | 811.5596 | 7311.6747 | 2123.5955 | 11775.882 | 0 | 0 | 318.1348 | 0 | 0 | 9362.9213 | 525.8427 | 0 | 0 | 245.3933 | 0 | 0 | 556.736 | 766.8539 | 0 | 0 | 0 | 0 | 97616.3538 | 0 | 314.3685 | 328.6517 | 16.8539 | 42.1348 | 0 | 7311.6747 | 0 | 0 | 5.618 | 146.0674 | 365.1685 | 730.3371 | 730.3371 | 109.5506 | 0 | 0 | 0 | 0 | 146.0674 | 0
2025-06-30 | 124270.8787 | 0 | 96480 | 97843.6245 | 973.8715 | 8774.0097 | 2548.3146 | 14131.0584 | 0 | 0 | 381.7618 | 0 | 0 | 11235.5056 | 631.0112 | 0 | 0 | 294.4719 | 0 | 0 | 668.0831 | 920.2247 | 0 | 0 | 0 | 0 | 97843.6245 | 0 | 377.2422 | 394.382 | 20.2247 | 50.5618 | 0 | 8774.0097 | 0 | 0 | 6.7416 | 175.2809 | 438.2022 | 876.4045 | 876.4045 | 131.4607 | 0 | 0 | 0 | 0 | 175.2809 | 0
2025-07-01 | 128902.6918 | 0 | 96480 | 98070.8953 | 1136.1834 | 10236.3446 | 2973.0337 | 16486.2348 | 0 | 0 | 445.3888 | 0 | 0 | 13108.0899 | 736.1798 | 0 | 0 | 343.5506 | 0 | 0 | 779.4303 | 1073.5955 | 0 | 0 | 0 | 0 | 98070.8953 | 0 | 440.116 | 460.1124 | 23.5955 | 58.9888 | 0 | 10236.3446 | 0 | 0 | 7.8652 | 204.4944 | 511.236 | 1022.4719 | 1022.4719 | 153.3708 | 0 | 0 | 0 | 0 | 204.4944 | 0
2025-07-02 | 133534.5049 | 0 | 96480 | 98298.166 | 1298.4953 | 11698.6796 | 3397.7528 | 18841.4112 | 0 | 0 | 509.0157 | 0 | 0 | 14980.6742 | 841.3483 | 0 | 0 | 392.6292 | 0 | 0 | 890.7775 | 1226.9663 | 0 | 0 | 0 | 0 | 98298.166 | 0 | 502.9897 | 525.8427 | 26.9663 | 67.4157 | 0 | 11698.6796 | 0 | 0 | 8.9888 | 233.7079 | 584.2697 | 1168.5393 | 1168.5393 | 175.2809 | 0 | 0 | 0 | 0 | 233.7079 | 0
2025-07-03 | 138166.318 | 0 | 96480 | 98525.4368 | 1460.8072 | 13161.0145 | 3822.4719 | 21196.5876 | 0 | 0 | 572.6427 | 0 | 0 | 16853.2584 | 946.5169 | 0 | 0 | 441.7079 | 0 | 0 | 1002.1247 | 1380.3371 | 0 | 0 | 0 | 0 | 98525.4368 | 0 | 565.8634 | 591.573 | 30.3371 | 75.8427 | 0 | 13161.0145 | 0 | 0 | 10.1124 | 262.9213 | 657.3034 | 1314.6067 | 1314.6067 | 197.191 | 0 | 0 | 0 | 0 | 262.9213 | 0
2025-07-04 | 142798.1311 | 0 | 96480 | 98752.7075 | 1623.1191 | 14623.3494 | 4247.191 | 23551.764 | 0 | 0 | 636.2697 | 0 | 0 | 18725.8427 | 1051.6854 | 0 | 0 | 490.7865 | 0 | 0 | 1113.4719 | 1533.7079 | 0 | 0 | 0 | 0 | 98752.7075 | 0 | 628.7371 | 657.3034 | 33.7079 | 84.2697 | 0 | 14623.3494 | 0 | 0 | 11.236 | 292.1348 | 730.3371 | 1460.6742 | 1460.6742 | 219.1011 | 0 | 0 | 0 | 0 | 292.1348 | 0
2025-07-05 | 147429.9442 | 0 | 96480 | 98979.9783 | 1785.431 | 16085.6844 | 4671.9101 | 25906.9404 | 0 | 0 | 699.8966 | 0 | 0 | 20598.427 | 1156.8539 | 0 | 0 | 539.8652 | 0 | 0 | 1224.8191 | 1687.0787 | 0 | 0 | 0 | 0 | 98979.9783 | 0 | 691.6108 | 723.0337 | 37.0787 | 92.6966 | 0 | 16085.6844 | 0 | 0 | 12.3596 | 321.3483 | 803.3708 | 1606.7416 | 1606.7416 | 241.0112 | 0 | 0 | 0 | 0 | 321.3483 | 0
2025-07-06 | 152061.7573 | 0 | 96480 | 99207.249 | 1947.7429 | 17548.0193 | 5096.6292 | 28262.1169 | 0 | 0 | 763.5236 | 0 | 0 | 22471.0112 | 1262.0225 | 0 | 0 | 588.9438 | 0 | 0 | 1336.1663 | 1840.4494 | 0 | 0 | 0 | 0 | 99207.249 | 0 | 754.4845 | 788.764 | 40.4494 | 101.1236 | 0 | 17548.0193 | 0 | 0 | 13.4831 | 350.5618 | 876.4045 | 1752.809 | 1752.809 | 262.9213 | 0 | 0 | 0 | 0 | 350.5618 | 0
2025-07-07 | 156693.5704 | 0 | 96480 | 99434.5198 | 2110.0548 | 19010.3543 | 5521.3483 | 30617.2933 | 0 | 0 | 827.1506 | 0 | 0 | 24343.5955 | 1367.191 | 0 | 0 | 638.0225 | 0 | 0 | 1447.5135 | 1993.8202 | 0 | 0 | 0 | 0 | 99434.5198 | 0 | 817.3582 | 854.4944 | 43.8202 | 109.5506 | 0 | 19010.3543 | 0 | 0 | 14.6067 | 379.7753 | 949.4382 | 1898.8764 | 1898.8764 | 284.8315 | 0 | 0 | 0 | 0 | 379.7753 | 0
2025-07-08 | 161325.3835 | 0 | 96480 | 99661.7905 | 2272.3667 | 20472.6892 | 5946.0674 | 32972.4697 | 0 | 0 | 890.7775 | 0 | 0 | 26216.1798 | 1472.3596 | 0 | 0 | 687.1011 | 0 | 0 | 1558.8607 | 2147.191 | 0 | 0 | 0 | 0 | 99661.7905 | 0 | 880.2319 | 920.2247 | 47.191 | 117.9775 | 0 | 20472.6892 | 0 | 0 | 15.7303 | 408.9888 | 1022.4719 | 2044.9438 | 2044.9438 | 306.7416 | 0 | 0 | 0 | 0 | 408.9888 | 0
2025-07-09 | 165957.1966 | 0 | 96480 | 99889.0613 | 2434.6787 | 21935.0242 | 6370.7865 | 35327.6461 | 0 | 0 | 954.4045 | 0 | 0 | 28088.764 | 1577.5281 | 0 | 0 | 736.1798 | 0 | 0 | 1670.2079 | 2300.5618 | 0 | 0 | 0 | 0 | 99889.0613 | 0 | 943.1056 | 985.9551 | 50.5618 | 126.4045 | 0 | 21935.0242 | 0 | 0 | 16.8539 | 438.2022 | 1095.5056 | 2191.0112 | 2191.0112 | 328.6517 | 0 | 0 | 0 | 0 | 438.2022 | 0
2025-07-10 | 170589.0098 | 0 | 96480 | 100116.332 | 2596.9906 | 23397.3591 | 6795.5056 | 37682.8225 | 0 | 0 | 1018.0315 | 0 | 0 | 29961.3483 | 1682.6966 | 0 | 0 | 785.2584 | 0 | 0 | 1781.5551 | 2453.9326 | 0 | 0 | 0 | 0 | 100116.332 | 0 | 1005.9793 | 1051.6854 | 53.9326 | 134.8315 | 0 | 23397.3591 | 0 | 0 | 17.9775 | 467.4157 | 1168.5393 | 2337.0787 | 2337.0787 | 350.5618 | 0 | 0 | 0 | 0 | 467.4157 | 0
2025-07-11 | 175220.8229 | 0 | 96480 | 100343.6028 | 2759.3025 | 24859.694 | 7220.2247 | 40037.9989 | 0 | 0 | 1081.6584 | 0 | 0 | 31833.9326 | 1787.8652 | 0 | 0 | 834.3371 | 0 | 0 | 1892.9022 | 2607.3034 | 0 | 0 | 0 | 0 | 100343.6028 | 0 | 1068.853 | 1117.4157 | 57.3034 | 143.2584 | 0 | 24859.694 | 0 | 0 | 19.1011 | 496.6292 | 1241.573 | 2483.1461 | 2483.1461 | 372.4719 | 0 | 0 | 0 | 0 | 496.6292 | 0
2025-07-12 | 179852.636 | 0 | 96480 | 100570.8735 | 2921.6144 | 26322.029 | 7644.9438 | 42393.1753 | 0 | 0 | 1145.2854 | 0 | 0 | 33706.5169 | 1893.0337 | 0 | 0 | 883.4157 | 0 | 0 | 2004.2494 | 2760.6742 | 0 | 0 | 0 | 0 | 100570.8735 | 0 | 1131.7267 | 1183.1461 | 60.6742 | 151.6854 | 0 | 26322.029 | 0 | 0 | 20.2247 | 525.8427 | 1314.6067 | 2629.2135 | 2629.2135 | 394.382 | 0 | 0 | 0 | 0 | 525.8427 | 0
2025-07-13 | 184484.4491 | 0 | 96480 | 100798.1443 | 3083.9263 | 27784.3639 | 8069.6629 | 44748.3517 | 0 | 0 | 1208.9124 | 0 | 0 | 35579.1011 | 1998.2022 | 0 | 0 | 932.4944 | 0 | 0 | 2115.5966 | 2914.0449 | 0 | 0 | 0 | 0 | 100798.1443 | 0 | 1194.6004 | 1248.8764 | 64.0449 | 160.1124 | 0 | 27784.3639 | 0 | 0 | 21.3483 | 555.0562 | 1387.6404 | 2775.2809 | 2775.2809 | 416.2921 | 0 | 0 | 0 | 0 | 555.0562 | 0
2025-07-14 | 189116.2622 | 0 | 96480 | 101025.415 | 3246.2382 | 29246.6989 | 8494.382 | 47103.5281 | 0 | 0 | 1272.5393 | 0 | 0 | 37451.6854 | 2103.3708 | 0 | 0 | 981.573 | 0 | 0 | 2226.9438 | 3067.4157 | 0 | 0 | 0 | 0 | 101025.415 | 0 | 1257.4742 | 1314.6067 | 67.4157 | 168.5393 | 0 | 29246.6989 | 0 | 0 | 22.4719 | 584.2697 | 1460.6742 | 2921.3483 | 2921.3483 | 438.2022 | 0 | 0 | 0 | 0 | 584.2697 | 0
2025-07-15 | 193748.0753 | 0 | 96480 | 101252.6858 | 3408.5501 | 30709.0338 | 8919.1011 | 49458.7045 | 0 | 0 | 1336.1663 | 0 | 0 | 39324.2697 | 2208.5393 | 0 | 0 | 1030.6517 | 0 | 0 | 2338.291 | 3220.7865 | 0 | 0 | 0 | 0 | 101252.6858 | 0 | 1320.3479 | 1380.3371 | 70.7865 | 176.9663 | 0 | 30709.0338 | 0 | 0 | 23.5955 | 613.4831 | 1533.7079 | 3067.4157 | 3067.4157 | 460.1124 | 0 | 0 | 0 | 0 | 613.4831 | 0
2025-07-16 | 198379.8884 | 0 | 96480 | 101479.9565 | 3570.862 | 32171.3688 | 9343.8202 | 51813.8809 | 0 | 0 | 1399.7933 | 0 | 0 | 41196.8539 | 2313.7079 | 0 | 0 | 1079.7303 | 0 | 0 | 2449.6382 | 3374.1573 | 0 | 0 | 0 | 0 | 101479.9565 | 0 | 1383.2216 | 1446.0674 | 74.1573 | 185.3933 | 0 | 32171.3688 | 0 | 0 | 24.7191 | 642.6966 | 1606.7416 | 3213.4831 | 3213.4831 | 482.0225 | 0 | 0 | 0 | 0 | 642.6966 | 0
2025-07-17 | 203011.7015 | 0 | 96480 | 101707.2273 | 3733.1739 | 33633.7037 | 9768.5393 | 54169.0573 | 0 | 0 | 1463.4202 | 0 | 0 | 43069.4382 | 2418.8764 | 0 | 0 | 1128.809 | 0 | 0 | 2560.9854 | 3527.5281 | 0 | 0 | 0 | 0 | 101707.2273 | 0 | 1446.0953 | 1511.7978 | 77.5281 | 193.8202 | 0 | 33633.7037 | 0 | 0 | 25.8427 | 671.9101 | 1679.7753 | 3359.5506 | 3359.5506 | 503.9326 | 0 | 0 | 0 | 0 | 671.9101 | 0
2025-07-18 | 207643.5146 | 0 | 96480 | 101934.498 | 3895.4858 | 35096.0387 | 10193.2584 | 56524.2337 | 0 | 0 | 1527.0472 | 0 | 0 | 44942.0225 | 2524.0449 | 0 | 0 | 1177.8876 | 0 | 0 | 2672.3326 | 3680.8989 | 0 | 0 | 0 | 0 | 101934.498 | 0 | 1508.969 | 1577.5281 | 80.8989 | 202.2472 | 0 | 35096.0387 | 0 | 0 | 26.9663 | 701.1236 | 1752.809 | 3505.618 | 3505.618 | 525.8427 | 0 | 0 | 0 | 0 | 701.1236 | 0
2025-07-19 | 212275.3277 | 0 | 96480 | 102161.7688 | 4057.7978 | 36558.3736 | 10617.9775 | 58879.4101 | 0 | 0 | 1590.6742 | 0 | 0 | 46814.6067 | 2629.2135 | 0 | 0 | 1226.9663 | 0 | 0 | 2783.6798 | 3834.2697 | 0 | 0 | 0 | 0 | 102161.7688 | 0 | 1571.8427 | 1643.2584 | 84.2697 | 210.6742 | 0 | 36558.3736 | 0 | 0 | 28.0899 | 730.3371 | 1825.8427 | 3651.6854 | 3651.6854 | 547.7528 | 0 | 0 | 0 | 0 | 730.3371 | 0
2025-07-20 | 216907.1409 | 0 | 96480 | 102389.0395 | 4220.1097 | 38020.7085 | 11042.6966 | 61234.5865 | 0 | 0 | 1654.3011 | 0 | 0 | 48687.191 | 2734.382 | 0 | 0 | 1276.0449 | 0 | 0 | 2895.027 | 3987.6404 | 0 | 0 | 0 | 0 | 102389.0395 | 0 | 1634.7164 | 1708.9888 | 87.6404 | 219.1011 | 0 | 38020.7085 | 0 | 0 | 29.2135 | 759.5506 | 1898.8764 | 3797.7528 | 3797.7528 | 569.6629 | 0 | 0 | 0 | 0 | 759.5506 | 0
2025-07-21 | 221538.954 | 0 | 96480 | 102616.3103 | 4382.4216 | 39483.0435 | 11467.4157 | 63589.7629 | 0 | 0 | 1717.9281 | 0 | 0 | 50559.7753 | 2839.5506 | 0 | 0 | 1325.1236 | 0 | 0 | 3006.3742 | 4141.0112 | 0 | 0 | 0 | 0 | 102616.3103 | 0 | 1697.5901 | 1774.7191 | 91.0112 | 227.5281 | 0 | 39483.0435 | 0 | 0 | 30.3371 | 788.764 | 1971.9101 | 3943.8202 | 3943.8202 | 591.573 | 0 | 0 | 0 | 0 | 788.764 | 0
2025-07-22 | 226170.7671 | 0 | 96480 | 102843.581 | 4544.7335 | 40945.3784 | 11892.1348 | 65944.9393 | 0 | 0 | 1781.5551 | 0 | 0 | 52432.3596 | 2944.7191 | 0 | 0 | 1374.2022 | 0 | 0 | 3117.7213 | 4294.382 | 0 | 0 | 0 | 0 | 102843.581 | 0 | 1760.4638 | 1840.4494 | 94.382 | 235.9551 | 0 | 40945.3784 | 0 | 0 | 31.4607 | 817.9775 | 2044.9438 | 4089.8876 | 4089.8876 | 613.4831 | 0 | 0 | 0 | 0 | 817.9775 | 0
2025-07-23 | 230802.5802 | 0 | 96480 | 103070.8518 | 4707.0454 | 42407.7134 | 12316.8539 | 68300.1157 | 0 | 0 | 1845.182 | 0 | 0 | 54304.9438 | 3049.8876 | 0 | 0 | 1423.2809 | 0 | 0 | 3229.0685 | 4447.7528 | 0 | 0 | 0 | 0 | 103070.8518 | 0 | 1823.3375 | 1906.1798 | 97.7528 | 244.382 | 0 | 42407.7134 | 0 | 0 | 32.5843 | 847.191 | 2117.9775 | 4235.9551 | 4235.9551 | 635.3933 | 0 | 0 | 0 | 0 | 847.191 | 0
2025-07-24 | 235434.3933 | 0 | 96480 | 103298.1225 | 4869.3573 | 43870.0483 | 12741.573 | 70655.2921 | 0 | 0 | 1908.809 | 0 | 0 | 56177.5281 | 3155.0562 | 0 | 0 | 1472.3596 | 0 | 0 | 3340.4157 | 4601.1236 | 0 | 0 | 0 | 0 | 103298.1225 | 0 | 1886.2112 | 1971.9101 | 101.1236 | 252.809 | 0 | 43870.0483 | 0 | 0 | 33.7079 | 876.4045 | 2191.0112 | 4382.0225 | 4382.0225 | 657.3034 | 0 | 0 | 0 | 0 | 876.4045 | 0
2025-07-25 | 240066.2064 | 0 | 96480 | 103525.3933 | 5031.6692 | 45332.3833 | 13166.2921 | 73010.4685 | 0 | 0 | 1972.436 | 0 | 0 | 58050.1124 | 3260.2247 | 0 | 0 | 1521.4382 | 0 | 0 | 3451.7629 | 4754.4944 | 0 | 0 | 0 | 0 | 103525.3933 | 0 | 1949.0849 | 2037.6404 | 104.4944 | 261.236 | 0 | 45332.3833 | 0 | 0 | 34.8315 | 905.618 | 2264.0449 | 4528.0899 | 4528.0899 | 679.2135 | 0 | 0 | 0 | 0 | 905.618 | 0
2025-07-26 | 244698.0195 | 0 | 96480 | 103752.664 | 5193.9811 | 46794.7182 | 13591.0112 | 75365.6449 | 0 | 0 | 2036.0629 | 0 | 0 | 59922.6966 | 3365.3933 | 0 | 0 | 1570.5169 | 0 | 0 | 3563.1101 | 4907.8652 | 0 | 0 | 0 | 0 | 103752.664 | 0 | 2011.9587 | 2103.3708 | 107.8652 | 269.6629 | 0 | 46794.7182 | 0 | 0 | 35.9551 | 934.8315 | 2337.0787 | 4674.1573 | 4674.1573 | 701.1236 | 0 | 0 | 0 | 0 | 934.8315 | 0
2025-07-27 | 249329.8326 | 0 | 96480 | 103979.9348 | 5356.293 | 48257.0531 | 14015.7303 | 77720.8213 | 0 | 0 | 2099.6899 | 0 | 0 | 61795.2809 | 3470.5618 | 0 | 0 | 1619.5955 | 0 | 0 | 3674.4573 | 5061.236 | 0 | 0 | 0 | 0 | 103979.9348 | 0 | 2074.8324 | 2169.1011 | 111.236 | 278.0899 | 0 | 48257.0531 | 0 | 0 | 37.0787 | 964.0449 | 2410.1124 | 4820.2247 | 4820.2247 | 723.0337 | 0 | 0 | 0 | 0 | 964.0449 | 0
2025-07-28 | 253961.6457 | 0 | 96480 | 104207.2055 | 5518.6049 | 49719.3881 | 14440.4494 | 80075.9978 | 0 | 0 | 2163.3169 | 0 | 0 | 63667.8652 | 3575.7303 | 0 | 0 | 1668.6742 | 0 | 0 | 3785.8045 | 5214.6067 | 0 | 0 | 0 | 0 | 104207.2055 | 0 | 2137.7061 | 2234.8315 | 114.6067 | 286.5169 | 0 | 49719.3881 | 0 | 0 | 38.2022 | 993.2584 | 2483.1461 | 4966.2921 | 4966.2921 | 744.9438 | 0 | 0 | 0 | 0 | 993.2584 | 0
2025-07-29 | 258593.4588 | 0 | 96480 | 104434.4763 | 5680.9169 | 51181.723 | 14865.1685 | 82431.1742 | 0 | 0 | 2226.9438 | 0 | 0 | 65540.4494 | 3680.8989 | 0 | 0 | 1717.7528 | 0 | 0 | 3897.1517 | 5367.9775 | 0 | 0 | 0 | 0 | 104434.4763 | 0 | 2200.5798 | 2300.5618 | 117.9775 | 294.9438 | 0 | 51181.723 | 0 | 0 | 39.3258 | 1022.4719 | 2556.1798 | 5112.3596 | 5112.3596 | 766.8539 | 0 | 0 | 0 | 0 | 1022.4719 | 0
2025-07-30 | 263225.272 | 0 | 96480 | 104661.747 | 5843.2288 | 52644.058 | 15289.8876 | 84786.3506 | 0 | 0 | 2290.5708 | 0 | 0 | 67413.0337 | 3786.0674 | 0 | 0 | 1766.8315 | 0 | 0 | 4008.4989 | 5521.3483 | 0 | 0 | 0 | 0 | 104661.747 | 0 | 2263.4535 | 2366.2921 | 121.3483 | 303.3708 | 0 | 52644.058 | 0 | 0 | 40.4494 | 1051.6854 | 2629.2135 | 5258.427 | 5258.427 | 788.764 | 0 | 0 | 0 | 0 | 1051.6854 | 0
2025-07-31 | 267857.0851 | 0 | 96480 | 104889.0178 | 6005.5407 | 54106.3929 | 15714.6067 | 87141.527 | 0 | 0 | 2354.1978 | 0 | 0 | 69285.618 | 3891.236 | 0 | 0 | 1815.9101 | 0 | 0 | 4119.8461 | 5674.7191 | 0 | 0 | 0 | 0 | 104889.0178 | 0 | 2326.3272 | 2432.0225 | 124.7191 | 311.7978 | 0 | 54106.3929 | 0 | 0 | 41.573 | 1080.8989 | 2702.2472 | 5404.4944 | 5404.4944 | 810.6742 | 0 | 0 | 0 | 0 | 1080.8989 | 0
2025-08-01 | 272488.8982 | 0 | 96480 | 105116.2885 | 6167.8526 | 55568.7279 | 16139.3258 | 89496.7034 | 0 | 0 | 2417.8247 | 0 | 0 | 71158.2022 | 3996.4045 | 0 | 0 | 1864.9888 | 0 | 0 | 4231.1933 | 5828.0899 | 0 | 0 | 0 | 0 | 105116.2885 | 0 | 2389.2009 | 2497.7528 | 128.0899 | 320.2247 | 0 | 55568.7279 | 0 | 0 | 42.6966 | 1110.1124 | 2775.2809 | 5550.5618 | 5550.5618 | 832.5843 | 0 | 0 | 0 | 0 | 1110.1124 | 0
2025-08-02 | 277120.7113 | 0 | 96480 | 105343.5593 | 6330.1645 | 57031.0628 | 16564.0449 | 91851.8798 | 0 | 0 | 2481.4517 | 0 | 0 | 73030.7865 | 4101.573 | 0 | 0 | 1914.0674 | 0 | 0 | 4342.5404 | 5981.4607 | 0 | 0 | 0 | 0 | 105343.5593 | 0 | 2452.0746 | 2563.4831 | 131.4607 | 328.6517 | 0 | 57031.0628 | 0 | 0 | 43.8202 | 1139.3258 | 2848.3146 | 5696.6292 | 5696.6292 | 854.4944 | 0 | 0 | 0 | 0 | 1139.3258 | 0
2025-08-03 | 281752.5244 | 0 | 96480 | 105570.83 | 6492.4764 | 58493.3978 | 16988.764 | 94207.0562 | 0 | 0 | 2545.0787 | 0 | 0 | 74903.3708 | 4206.7416 | 0 | 0 | 1963.1461 | 0 | 0 | 4453.8876 | 6134.8315 | 0 | 0 | 0 | 0 | 105570.83 | 0 | 2514.9483 | 2629.2135 | 134.8315 | 337.0787 | 0 | 58493.3978 | 0 | 0 | 44.9438 | 1168.5393 | 2921.3483 | 5842.6966 | 5842.6966 | 876.4045 | 0 | 0 | 0 | 0 | 1168.5393 | 0
2025-08-04 | 286384.3375 | 0 | 96480 | 105798.1008 | 6654.7883 | 59955.7327 | 17413.4831 | 96562.2326 | 0 | 0 | 2608.7056 | 0 | 0 | 76775.9551 | 4311.9101 | 0 | 0 | 2012.2247 | 0 | 0 | 4565.2348 | 6288.2022 | 0 | 0 | 0 | 0 | 105798.1008 | 0 | 2577.822 | 2694.9438 | 138.2022 | 345.5056 | 0 | 59955.7327 | 0 | 0 | 46.0674 | 1197.7528 | 2994.382 | 5988.764 | 5988.764 | 898.3146 | 0 | 0 | 0 | 0 | 1197.7528 | 0
2025-08-05 | 291016.1506 | 0 | 96480 | 106025.3715 | 6817.1002 | 61418.0676 | 17838.2022 | 98917.409 | 0 | 0 | 2672.3326 | 0 | 0 | 78648.5393 | 4417.0787 | 0 | 0 | 2061.3034 | 0 | 0 | 4676.582 | 6441.573 | 0 | 0 | 0 | 0 | 106025.3715 | 0 | 2640.6957 | 2760.6742 | 141.573 | 353.9326 | 0 | 61418.0676 | 0 | 0 | 47.191 | 1226.9663 | 3067.4157 | 6134.8315 | 6134.8315 | 920.2247 | 0 | 0 | 0 | 0 | 1226.9663 | 0
2025-08-06 | 295647.9637 | 0 | 96480 | 106252.6423 | 6979.4121 | 62880.4026 | 18262.9213 | 101272.5854 | 0 | 0 | 2735.9596 | 0 | 0 | 80521.1236 | 4522.2472 | 0 | 0 | 2110.382 | 0 | 0 | 4787.9292 | 6594.9438 | 0 | 0 | 0 | 0 | 106252.6423 | 0 | 2703.5694 | 2826.4045 | 144.9438 | 362.3596 | 0 | 62880.4026 | 0 | 0 | 48.3146 | 1256.1798 | 3140.4494 | 6280.8989 | 6280.8989 | 942.1348 | 0 | 0 | 0 | 0 | 1256.1798 | 0
2025-08-07 | 300279.7768 | 0 | 96480 | 106479.913 | 7141.724 | 64342.7375 | 18687.6404 | 103627.7618 | 0 | 0 | 2799.5865 | 0 | 0 | 82393.7079 | 4627.4157 | 0 | 0 | 2159.4607 | 0 | 0 | 4899.2764 | 6748.3146 | 0 | 0 | 0 | 0 | 106479.913 | 0 | 2766.4431 | 2892.1348 | 148.3146 | 370.7865 | 0 | 64342.7375 | 0 | 0 | 49.4382 | 1285.3933 | 3213.4831 | 6426.9663 | 6426.9663 | 964.0449 | 0 | 0 | 0 | 0 | 1285.3933 | 0
2025-08-08 | 304911.5899 | 0 | 96480 | 106707.1838 | 7304.036 | 65805.0725 | 19112.3596 | 105982.9382 | 0 | 0 | 2863.2135 | 0 | 0 | 84266.2921 | 4732.5843 | 0 | 0 | 2208.5393 | 0 | 0 | 5010.6236 | 6901.6854 | 0 | 0 | 0 | 0 | 106707.1838 | 0 | 2829.3169 | 2957.8652 | 151.6854 | 379.2135 | 0 | 65805.0725 | 0 | 0 | 50.5618 | 1314.6067 | 3286.5169 | 6573.0337 | 6573.0337 | 985.9551 | 0 | 0 | 0 | 0 | 1314.6067 | 0
2025-08-09 | 309543.4031 | 0 | 96480 | 106934.4545 | 7466.3479 | 67267.4074 | 19537.0787 | 108338.1146 | 0 | 0 | 2926.8404 | 0 | 0 | 86138.8764 | 4837.7528 | 0 | 0 | 2257.618 | 0 | 0 | 5121.9708 | 7055.0562 | 0 | 0 | 0 | 0 | 106934.4545 | 0 | 2892.1906 | 3023.5955 | 155.0562 | 387.6404 | 0 | 67267.4074 | 0 | 0 | 51.6854 | 1343.8202 | 3359.5506 | 6719.1011 | 6719.1011 | 1007.8652 | 0 | 0 | 0 | 0 | 1343.8202 | 0
2025-08-10 | 314175.2162 | 0 | 96480 | 107161.7253 | 7628.6598 | 68729.7424 | 19961.7978 | 110693.291 | 0 | 0 | 2990.4674 | 0 | 0 | 88011.4607 | 4942.9213 | 0 | 0 | 2306.6966 | 0 | 0 | 5233.318 | 7208.427 | 0 | 0 | 0 | 0 | 107161.7253 | 0 | 2955.0643 | 3089.3258 | 158.427 | 396.0674 | 0 | 68729.7424 | 0 | 0 | 52.809 | 1373.0337 | 3432.5843 | 6865.1685 | 6865.1685 | 1029.7753 | 0 | 0 | 0 | 0 | 1373.0337 | 0
2025-08-11 | 318807.0293 | 0 | 96480 | 107388.996 | 7790.9717 | 70192.0773 | 20386.5169 | 113048.4674 | 0 | 0 | 3054.0944 | 0 | 0 | 89884.0449 | 5048.0899 | 0 | 0 | 2355.7753 | 0 | 0 | 5344.6652 | 7361.7978 | 0 | 0 | 0 | 0 | 107388.996 | 0 | 3017.938 | 3155.0562 | 161.7978 | 404.4944 | 0 | 70192.0773 | 0 | 0 | 53.9326 | 1402.2472 | 3505.618 | 7011.236 | 7011.236 | 1051.6854 | 0 | 0 | 0 | 0 | 1402.2472 | 0
2025-08-12 | 323438.8424 | 0 | 96480 | 107616.2668 | 7953.2836 | 71654.4122 | 20811.236 | 115403.6438 | 0 | 0 | 3117.7213 | 0 | 0 | 91756.6292 | 5153.2584 | 0 | 0 | 2404.8539 | 0 | 0 | 5456.0124 | 7515.1685 | 0 | 0 | 0 | 0 | 107616.2668 | 0 | 3080.8117 | 3220.7865 | 165.1685 | 412.9213 | 0 | 71654.4122 | 0 | 0 | 55.0562 | 1431.4607 | 3578.6517 | 7157.3034 | 7157.3034 | 1073.5955 | 0 | 0 | 0 | 0 | 1431.4607 | 0
2025-08-13 | 328070.6555 | 0 | 96480 | 107843.5375 | 8115.5955 | 73116.7472 | 21235.9551 | 117758.8202 | 0 | 0 | 3181.3483 | 0 | 0 | 93629.2135 | 5258.427 | 0 | 0 | 2453.9326 | 0 | 0 | 5567.3596 | 7668.5393 | 0 | 0 | 0 | 0 | 107843.5375 | 0 | 3143.6854 | 3286.5169 | 168.5393 | 421.3483 | 0 | 73116.7472 | 0 | 0 | 56.1798 | 1460.6742 | 3651.6854 | 7303.3708 | 7303.3708 | 1095.5056 | 0 | 0 | 0 | 0 | 1460.6742 | 0
2025-08-14 | 332702.4686 | 0 | 96480 | 108070.8083 | 8277.9074 | 74579.0821 | 21660.6742 | 120113.9966 | 0 | 0 | 3244.9753 | 0 | 0 | 95501.7978 | 5363.5955 | 0 | 0 | 2503.0112 | 0 | 0 | 5678.7067 | 7821.9101 | 0 | 0 | 0 | 0 | 108070.8083 | 0 | 3206.5591 | 3352.2472 | 171.9101 | 429.7753 | 0 | 74579.0821 | 0 | 0 | 57.3034 | 1489.8876 | 3724.7191 | 7449.4382 | 7449.4382 | 1117.4157 | 0 | 0 | 0 | 0 | 1489.8876 | 0
2025-08-15 | 337334.2817 | 0 | 96480 | 108298.079 | 8440.2193 | 76041.4171 | 22085.3933 | 122469.173 | 0 | 0 | 3308.6022 | 0 | 0 | 97374.382 | 5468.764 | 0 | 0 | 2552.0899 | 0 | 0 | 5790.0539 | 7975.2809 | 0 | 0 | 0 | 0 | 108298.079 | 0 | 3269.4328 | 3417.9775 | 175.2809 | 438.2022 | 0 | 76041.4171 | 0 | 0 | 58.427 | 1519.1011 | 3797.7528 | 7595.5056 | 7595.5056 | 1139.3258 | 0 | 0 | 0 | 0 | 1519.1011 | 0
2025-08-16 | 341966.0948 | 0 | 96480 | 108525.3498 | 8602.5312 | 77503.752 | 22510.1124 | 124824.3494 | 0 | 0 | 3372.2292 | 0 | 0 | 99246.9663 | 5573.9326 | 0 | 0 | 2601.1685 | 0 | 0 | 5901.4011 | 8128.6517 | 0 | 0 | 0 | 0 | 108525.3498 | 0 | 3332.3065 | 3483.7079 | 178.6517 | 446.6292 | 0 | 77503.752 | 0 | 0 | 59.5506 | 1548.3146 | 3870.7865 | 7741.573 | 7741.573 | 1161.236 | 0 | 0 | 0 | 0 | 1548.3146 | 0
2025-08-17 | 346597.9079 | 0 | 96480 | 108752.6205 | 8764.8431 | 78966.087 | 22934.8315 | 127179.5258 | 0 | 0 | 3435.8562 | 0 | 0 | 101119.5506 | 5679.1011 | 0 | 0 | 2650.2472 | 0 | 0 | 6012.7483 | 8282.0225 | 0 | 0 | 0 | 0 | 108752.6205 | 0 | 3395.1802 | 3549.4382 | 182.0225 | 455.0562 | 0 | 78966.087 | 0 | 0 | 60.6742 | 1577.5281 | 3943.8202 | 7887.6404 | 7887.6404 | 1183.1461 | 0 | 0 | 0 | 0 | 1577.5281 | 0
2025-08-18 | 351229.721 | 0 | 96480 | 108979.8913 | 8927.1551 | 80428.4219 | 23359.5506 | 129534.7022 | 0 | 0 | 3499.4831 | 0 | 0 | 102992.1348 | 5784.2697 | 0 | 0 | 2699.3258 | 0 | 0 | 6124.0955 | 8435.3933 | 0 | 0 | 0 | 0 | 108979.8913 | 0 | 3458.0539 | 3615.1685 | 185.3933 | 463.4831 | 0 | 80428.4219 | 0 | 0 | 61.7978 | 1606.7416 | 4016.8539 | 8033.7079 | 8033.7079 | 1205.0562 | 0 | 0 | 0 | 0 | 1606.7416 | 0
2025-08-19 | 355861.5342 | 0 | 96480 | 109207.162 | 9089.467 | 81890.7569 | 23784.2697 | 131889.8787 | 0 | 0 | 3563.1101 | 0 | 0 | 104864.7191 | 5889.4382 | 0 | 0 | 2748.4045 | 0 | 0 | 6235.4427 | 8588.764 | 0 | 0 | 0 | 0 | 109207.162 | 0 | 3520.9276 | 3680.8989 | 188.764 | 471.9101 | 0 | 81890.7569 | 0 | 0 | 62.9213 | 1635.9551 | 4089.8876 | 8179.7753 | 8179.7753 | 1226.9663 | 0 | 0 | 0 | 0 | 1635.9551 | 0
2025-08-20 | 360493.3473 | 0 | 96480 | 109434.4328 | 9251.7789 | 83353.0918 | 24208.9888 | 134245.0551 | 0 | 0 | 3626.7371 | 0 | 0 | 106737.3034 | 5994.6067 | 0 | 0 | 2797.4831 | 0 | 0 | 6346.7899 | 8742.1348 | 0 | 0 | 0 | 0 | 109434.4328 | 0 | 3583.8013 | 3746.6292 | 192.1348 | 480.3371 | 0 | 83353.0918 | 0 | 0 | 64.0449 | 1665.1685 | 4162.9213 | 8325.8427 | 8325.8427 | 1248.8764 | 0 | 0 | 0 | 0 | 1665.1685 | 0
2025-08-21 | 365125.1604 | 0 | 96480 | 109661.7035 | 9414.0908 | 84815.4267 | 24633.7079 | 136600.2315 | 0 | 0 | 3690.364 | 0 | 0 | 108609.8876 | 6099.7753 | 0 | 0 | 2846.5618 | 0 | 0 | 6458.1371 | 8895.5056 | 0 | 0 | 0 | 0 | 109661.7035 | 0 | 3646.6751 | 3812.3596 | 195.5056 | 488.764 | 0 | 84815.4267 | 0 | 0 | 65.1685 | 1694.382 | 4235.9551 | 8471.9101 | 8471.9101 | 1270.7865 | 0 | 0 | 0 | 0 | 1694.382 | 0
2025-08-22 | 369756.9735 | 0 | 96480 | 109888.9743 | 9576.4027 | 86277.7617 | 25058.427 | 138955.4079 | 0 | 0 | 3753.991 | 0 | 0 | 110482.4719 | 6204.9438 | 0 | 0 | 2895.6404 | 0 | 0 | 6569.4843 | 9048.8764 | 0 | 0 | 0 | 0 | 109888.9743 | 0 | 3709.5488 | 3878.0899 | 198.8764 | 497.191 | 0 | 86277.7617 | 0 | 0 | 66.2921 | 1723.5955 | 4308.9888 | 8617.9775 | 8617.9775 | 1292.6966 | 0 | 0 | 0 | 0 | 1723.5955 | 0
2025-08-23 | 374388.7866 | 0 | 96480 | 110116.245 | 9738.7146 | 87740.0966 | 25483.1461 | 141310.5843 | 0 | 0 | 3817.618 | 0 | 0 | 112355.0562 | 6310.1124 | 0 | 0 | 2944.7191 | 0 | 0 | 6680.8315 | 9202.2472 | 0 | 0 | 0 | 0 | 110116.245 | 0 | 3772.4225 | 3943.8202 | 202.2472 | 505.618 | 0 | 87740.0966 | 0 | 0 | 67.4157 | 1752.809 | 4382.0225 | 8764.0449 | 8764.0449 | 1314.6067 | 0 | 0 | 0 | 0 | 1752.809 | 0
2025-08-24 | 379020.5997 | 0 | 96480 | 110343.5158 | 9901.0265 | 89202.4316 | 25907.8652 | 143665.7607 | 0 | 0 | 3881.2449 | 0 | 0 | 114227.6404 | 6415.2809 | 0 | 0 | 2993.7978 | 0 | 0 | 6792.1787 | 9355.618 | 0 | 0 | 0 | 0 | 110343.5158 | 0 | 3835.2962 | 4009.5506 | 205.618 | 514.0449 | 0 | 89202.4316 | 0 | 0 | 68.5393 | 1782.0225 | 4455.0562 | 8910.1124 | 8910.1124 | 1336.5169 | 0 | 0 | 0 | 0 | 1782.0225 | 0
2025-08-25 | 383652.4128 | 0 | 96480 | 110570.7865 | 10063.3384 | 90664.7665 | 26332.5843 | 146020.9371 | 0 | 0 | 3944.8719 | 0 | 0 | 116100.2247 | 6520.4494 | 0 | 0 | 3042.8764 | 0 | 0 | 6903.5258 | 9508.9888 | 0 | 0 | 0 | 0 | 110570.7865 | 0 | 3898.1699 | 4075.2809 | 208.9888 | 522.4719 | 0 | 90664.7665 | 0 | 0 | 69.6629 | 1811.236 | 4528.0899 | 9056.1798 | 9056.1798 | 1358.427 | 0 | 0 | 0 | 0 | 1811.236 | 0
2025-08-26 | 388284.2259 | 0 | 96480 | 110798.0573 | 10225.6503 | 92127.1015 | 26757.3034 | 148376.1135 | 0 | 0 | 4008.4989 | 0 | 0 | 117972.809 | 6625.618 | 0 | 0 | 3091.9551 | 0 | 0 | 7014.873 | 9662.3596 | 0 | 0 | 0 | 0 | 110798.0573 | 0 | 3961.0436 | 4141.0112 | 212.3596 | 530.8989 | 0 | 92127.1015 | 0 | 0 | 70.7865 | 1840.4494 | 4601.1236 | 9202.2472 | 9202.2472 | 1380.3371 | 0 | 0 | 0 | 0 | 1840.4494 | 0
2025-08-27 | 392916.039 | 0 | 96480 | 111025.328 | 10387.9622 | 93589.4364 | 27182.0225 | 150731.2899 | 0 | 0 | 4072.1258 | 0 | 0 | 119845.3933 | 6730.7865 | 0 | 0 | 3141.0337 | 0 | 0 | 7126.2202 | 9815.7303 | 0 | 0 | 0 | 0 | 111025.328 | 0 | 4023.9173 | 4206.7416 | 215.7303 | 539.3258 | 0 | 93589.4364 | 0 | 0 | 71.9101 | 1869.6629 | 4674.1573 | 9348.3146 | 9348.3146 | 1402.2472 | 0 | 0 | 0 | 0 | 1869.6629 | 0
2025-08-28 | 397547.8521 | 0 | 96480 | 111252.5988 | 10550.2742 | 95051.7713 | 27606.7416 | 153086.4663 | 0 | 0 | 4135.7528 | 0 | 0 | 121717.9775 | 6835.9551 | 0 | 0 | 3190.1124 | 0 | 0 | 7237.5674 | 9969.1011 | 0 | 0 | 0 | 0 | 111252.5988 | 0 | 4086.791 | 4272.4719 | 219.1011 | 547.7528 | 0 | 95051.7713 | 0 | 0 | 73.0337 | 1898.8764 | 4747.191 | 9494.382 | 9494.382 | 1424.1573 | 0 | 0 | 0 | 0 | 1898.8764 | 0
2025-08-29 | 402179.6652 | 0 | 96480 | 111479.8695 | 10712.5861 | 96514.1063 | 28031.4607 | 155441.6427 | 0 | 0 | 4199.3798 | 0 | 0 | 123590.5618 | 6941.1236 | 0 | 0 | 3239.191 | 0 | 0 | 7348.9146 | 10122.4719 | 0 | 0 | 0 | 0 | 111479.8695 | 0 | 4149.6647 | 4338.2022 | 222.4719 | 556.1798 | 0 | 96514.1063 | 0 | 0 | 74.1573 | 1928.0899 | 4820.2247 | 9640.4494 | 9640.4494 | 1446.0674 | 0 | 0 | 0 | 0 | 1928.0899 | 0
2025-08-30 | 406811.4784 | 0 | 96480 | 111707.1403 | 10874.898 | 97976.4412 | 28456.1798 | 157796.8191 | 0 | 0 | 4263.0067 | 0 | 0 | 125463.1461 | 7046.2921 | 0 | 0 | 3288.2697 | 0 | 0 | 7460.2618 | 10275.8427 | 0 | 0 | 0 | 0 | 111707.1403 | 0 | 4212.5384 | 4403.9326 | 225.8427 | 564.6067 | 0 | 97976.4412 | 0 | 0 | 75.2809 | 1957.3034 | 4893.2584 | 9786.5169 | 9786.5169 | 1467.9775 | 0 | 0 | 0 | 0 | 1957.3034 | 0
2025-08-31 | 411443.2915 | 0 | 96480 | 111934.411 | 11037.2099 | 99438.7762 | 28880.8989 | 160151.9955 | 0 | 0 | 4326.6337 | 0 | 0 | 127335.7303 | 7151.4607 | 0 | 0 | 3337.3483 | 0 | 0 | 7571.609 | 10429.2135 | 0 | 0 | 0 | 0 | 111934.411 | 0 | 4275.4121 | 4469.6629 | 229.2135 | 573.0337 | 0 | 99438.7762 | 0 | 0 | 76.4045 | 1986.5169 | 4966.2921 | 9932.5843 | 9932.5843 | 1489.8876 | 0 | 0 | 0 | 0 | 1986.5169 | 0
2025-09-01 | 416075.1046 | 0 | 96480 | 112161.6818 | 11199.5218 | 100901.1111 | 29305.618 | 162507.1719 | 0 | 0 | 4390.2607 | 0 | 0 | 129208.3146 | 7256.6292 | 0 | 0 | 3386.427 | 0 | 0 | 7682.9562 | 10582.5843 | 0 | 0 | 0 | 0 | 112161.6818 | 0 | 4338.2858 | 4535.3933 | 232.5843 | 581.4607 | 0 | 100901.1111 | 0 | 0 | 77.5281 | 2015.7303 | 5039.3258 | 10078.6517 | 10078.6517 | 1511.7978 | 0 | 0 | 0 | 0 | 2015.7303 | 0
2025-09-02 | 420706.9177 | 0 | 96480 | 112388.9525 | 11361.8337 | 102363.4461 | 29730.3371 | 164862.3483 | 0 | 0 | 4453.8876 | 0 | 0 | 131080.8989 | 7361.7978 | 0 | 0 | 3435.5056 | 0 | 0 | 7794.3034 | 10735.9551 | 0 | 0 | 0 | 0 | 112388.9525 | 0 | 4401.1596 | 4601.1236 | 235.9551 | 589.8876 | 0 | 102363.4461 | 0 | 0 | 78.6517 | 2044.9438 | 5112.3596 | 10224.7191 | 10224.7191 | 1533.7079 | 0 | 0 | 0 | 0 | 2044.9438 | 0
2025-09-03 | 425338.7308 | 0 | 96480 | 112616.2233 | 11524.1456 | 103825.781 | 30155.0562 | 167217.5247 | 0 | 0 | 4517.5146 | 0 | 0 | 132953.4831 | 7466.9663 | 0 | 0 | 3484.5843 | 0 | 0 | 7905.6506 | 10889.3258 | 0 | 0 | 0 | 0 | 112616.2233 | 0 | 4464.0333 | 4666.8539 | 239.3258 | 598.3146 | 0 | 103825.781 | 0 | 0 | 79.7753 | 2074.1573 | 5185.3933 | 10370.7865 | 10370.7865 | 1555.618 | 0 | 0 | 0 | 0 | 2074.1573 | 0
2025-09-04 | 429970.5439 | 0 | 96480 | 112843.494 | 11686.4575 | 105288.116 | 30579.7753 | 169572.7011 | 0 | 0 | 4581.1416 | 0 | 0 | 134826.0674 | 7572.1348 | 0 | 0 | 3533.6629 | 0 | 0 | 8016.9978 | 11042.6966 | 0 | 0 | 0 | 0 | 112843.494 | 0 | 4526.907 | 4732.5843 | 242.6966 | 606.7416 | 0 | 105288.116 | 0 | 0 | 80.8989 | 2103.3708 | 5258.427 | 10516.8539 | 10516.8539 | 1577.5281 | 0 | 0 | 0 | 0 | 2103.3708 | 0
2025-09-05 | 434602.357 | 0 | 96480 | 113070.7648 | 11848.7694 | 106750.4509 | 31004.4944 | 171927.8775 | 0 | 0 | 4644.7685 | 0 | 0 | 136698.6517 | 7677.3034 | 0 | 0 | 3582.7416 | 0 | 0 | 8128.3449 | 11196.0674 | 0 | 0 | 0 | 0 | 113070.7648 | 0 | 4589.7807 | 4798.3146 | 246.0674 | 615.1685 | 0 | 106750.4509 | 0 | 0 | 82.0225 | 2132.5843 | 5331.4607 | 10662.9213 | 10662.9213 | 1599.4382 | 0 | 0 | 0 | 0 | 2132.5843 | 0
2025-09-06 | 439234.1701 | 0 | 96480 | 113298.0355 | 12011.0813 | 108212.7858 | 31429.2135 | 174283.0539 | 0 | 0 | 4708.3955 | 0 | 0 | 138571.236 | 7782.4719 | 0 | 0 | 3631.8202 | 0 | 0 | 8239.6921 | 11349.4382 | 0 | 0 | 0 | 0 | 113298.0355 | 0 | 4652.6544 | 4864.0449 | 249.4382 | 623.5955 | 0 | 108212.7858 | 0 | 0 | 83.1461 | 2161.7978 | 5404.4944 | 10808.9888 | 10808.9888 | 1621.3483 | 0 | 0 | 0 | 0 | 2161.7978 | 0
2025-09-07 | 443865.9832 | 0 | 96480 | 113525.3063 | 12173.3933 | 109675.1208 | 31853.9326 | 176638.2303 | 0 | 0 | 4772.0225 | 0 | 0 | 140443.8202 | 7887.6404 | 0 | 0 | 3680.8989 | 0 | 0 | 8351.0393 | 11502.809 | 0 | 0 | 0 | 0 | 113525.3063 | 0 | 4715.5281 | 4929.7753 | 252.809 | 632.0225 | 0 | 109675.1208 | 0 | 0 | 84.2697 | 2191.0112 | 5477.5281 | 10955.0562 | 10955.0562 | 1643.2584 | 0 | 0 | 0 | 0 | 2191.0112 | 0
2025-09-08 | 448497.7963 | 0 | 96480 | 113752.577 | 12335.7052 | 111137.4557 | 32278.6517 | 178993.4067 | 0 | 0 | 4835.6494 | 0 | 0 | 142316.4045 | 7992.809 | 0 | 0 | 3729.9775 | 0 | 0 | 8462.3865 | 11656.1798 | 0 | 0 | 0 | 0 | 113752.577 | 0 | 4778.4018 | 4995.5056 | 256.1798 | 640.4494 | 0 | 111137.4557 | 0 | 0 | 85.3933 | 2220.2247 | 5550.5618 | 11101.1236 | 11101.1236 | 1665.1685 | 0 | 0 | 0 | 0 | 2220.2247 | 0
2025-09-09 | 453129.6095 | 0 | 96480 | 113979.8478 | 12498.0171 | 112599.7907 | 32703.3708 | 181348.5831 | 0 | 0 | 4899.2764 | 0 | 0 | 144188.9888 | 8097.9775 | 0 | 0 | 3779.0562 | 0 | 0 | 8573.7337 | 11809.5506 | 0 | 0 | 0 | 0 | 113979.8478 | 0 | 4841.2755 | 5061.236 | 259.5506 | 648.8764 | 0 | 112599.7907 | 0 | 0 | 86.5169 | 2249.4382 | 5623.5955 | 11247.191 | 11247.191 | 1687.0787 | 0 | 0 | 0 | 0 | 2249.4382 | 0
2025-09-10 | 457761.4226 | 0 | 96480 | 114207.1185 | 12660.329 | 114062.1256 | 33128.0899 | 183703.7596 | 0 | 0 | 4962.9034 | 0 | 0 | 146061.573 | 8203.1461 | 0 | 0 | 3828.1348 | 0 | 0 | 8685.0809 | 11962.9213 | 0 | 0 | 0 | 0 | 114207.1185 | 0 | 4904.1492 | 5126.9663 | 262.9213 | 657.3034 | 0 | 114062.1256 | 0 | 0 | 87.6404 | 2278.6517 | 5696.6292 | 11393.2584 | 11393.2584 | 1708.9888 | 0 | 0 | 0 | 0 | 2278.6517 | 0
2025-09-11 | 462393.2357 | 0 | 96480 | 114434.3893 | 12822.6409 | 115524.4606 | 33552.809 | 186058.936 | 0 | 0 | 5026.5303 | 0 | 0 | 147934.1573 | 8308.3146 | 0 | 0 | 3877.2135 | 0 | 0 | 8796.4281 | 12116.2921 | 0 | 0 | 0 | 0 | 114434.3893 | 0 | 4967.0229 | 5192.6966 | 266.2921 | 665.7303 | 0 | 115524.4606 | 0 | 0 | 88.764 | 2307.8652 | 5769.6629 | 11539.3258 | 11539.3258 | 1730.8989 | 0 | 0 | 0 | 0 | 2307.8652 | 0
2025-09-12 | 467025.0488 | 0 | 96480 | 114661.66 | 12984.9528 | 116986.7955 | 33977.5281 | 188414.1124 | 0 | 0 | 5090.1573 | 0 | 0 | 149806.7416 | 8413.4831 | 0 | 0 | 3926.2921 | 0 | 0 | 8907.7753 | 12269.6629 | 0 | 0 | 0 | 0 | 114661.66 | 0 | 5029.8966 | 5258.427 | 269.6629 | 674.1573 | 0 | 116986.7955 | 0 | 0 | 89.8876 | 2337.0787 | 5842.6966 | 11685.3933 | 11685.3933 | 1752.809 | 0 | 0 | 0 | 0 | 2337.0787 | 0
2025-09-13 | 471656.8619 | 0 | 96480 | 114888.9308 | 13147.2647 | 118449.1304 | 34402.2472 | 190769.2888 | 0 | 0 | 5153.7843 | 0 | 0 | 151679.3258 | 8518.6517 | 0 | 0 | 3975.3708 | 0 | 0 | 9019.1225 | 12423.0337 | 0 | 0 | 0 | 0 | 114888.9308 | 0 | 5092.7703 | 5324.1573 | 273.0337 | 682.5843 | 0 | 118449.1304 | 0 | 0 | 91.0112 | 2366.2921 | 5915.7303 | 11831.4607 | 11831.4607 | 1774.7191 | 0 | 0 | 0 | 0 | 2366.2921 | 0
2025-09-14 | 476288.675 | 0 | 96480 | 115116.2015 | 13309.5766 | 119911.4654 | 34826.9663 | 193124.4652 | 0 | 0 | 5217.4112 | 0 | 0 | 153551.9101 | 8623.8202 | 0 | 0 | 4024.4494 | 0 | 0 | 9130.4697 | 12576.4045 | 0 | 0 | 0 | 0 | 115116.2015 | 0 | 5155.644 | 5389.8876 | 276.4045 | 691.0112 | 0 | 119911.4654 | 0 | 0 | 92.1348 | 2395.5056 | 5988.764 | 11977.5281 | 11977.5281 | 1796.6292 | 0 | 0 | 0 | 0 | 2395.5056 | 0
2025-09-15 | 480920.4881 | 0 | 96480 | 115343.4723 | 13471.8885 | 121373.8003 | 35251.6854 | 195479.6416 | 0 | 0 | 5281.0382 | 0 | 0 | 155424.4944 | 8728.9888 | 0 | 0 | 4073.5281 | 0 | 0 | 9241.8169 | 12729.7753 | 0 | 0 | 0 | 0 | 115343.4723 | 0 | 5218.5178 | 5455.618 | 279.7753 | 699.4382 | 0 | 121373.8003 | 0 | 0 | 93.2584 | 2424.7191 | 6061.7978 | 12123.5955 | 12123.5955 | 1818.5393 | 0 | 0 | 0 | 0 | 2424.7191 | 0
2025-09-16 | 485552.3012 | 0 | 96480 | 115570.743 | 13634.2004 | 122836.1353 | 35676.4045 | 197834.818 | 0 | 0 | 5344.6652 | 0 | 0 | 157297.0787 | 8834.1573 | 0 | 0 | 4122.6067 | 0 | 0 | 9353.164 | 12883.1461 | 0 | 0 | 0 | 0 | 115570.743 | 0 | 5281.3915 | 5521.3483 | 283.1461 | 707.8652 | 0 | 122836.1353 | 0 | 0 | 94.382 | 2453.9326 | 6134.8315 | 12269.6629 | 12269.6629 | 1840.4494 | 0 | 0 | 0 | 0 | 2453.9326 | 0
2025-09-17 | 490184.1143 | 0 | 96480 | 115798.0138 | 13796.5124 | 124298.4702 | 36101.1236 | 200189.9944 | 0 | 0 | 5408.2921 | 0 | 0 | 159169.6629 | 8939.3258 | 0 | 0 | 4171.6854 | 0 | 0 | 9464.5112 | 13036.5169 | 0 | 0 | 0 | 0 | 115798.0138 | 0 | 5344.2652 | 5587.0787 | 286.5169 | 716.2921 | 0 | 124298.4702 | 0 | 0 | 95.5056 | 2483.1461 | 6207.8652 | 12415.7303 | 12415.7303 | 1862.3596 | 0 | 0 | 0 | 0 | 2483.1461 | 0
2025-09-18 | 494815.9274 | 0 | 96480 | 116025.2845 | 13958.8243 | 125760.8052 | 36525.8427 | 202545.1708 | 0 | 0 | 5471.9191 | 0 | 0 | 161042.2472 | 9044.4944 | 0 | 0 | 4220.764 | 0 | 0 | 9575.8584 | 13189.8876 | 0 | 0 | 0 | 0 | 116025.2845 | 0 | 5407.1389 | 5652.809 | 289.8876 | 724.7191 | 0 | 125760.8052 | 0 | 0 | 96.6292 | 2512.3596 | 6280.8989 | 12561.7978 | 12561.7978 | 1884.2697 | 0 | 0 | 0 | 0 | 2512.3596 | 0
2025-09-19 | 499447.7406 | 0 | 96480 | 116252.5553 | 14121.1362 | 127223.1401 | 36950.5618 | 204900.3472 | 0 | 0 | 5535.5461 | 0 | 0 | 162914.8315 | 9149.6629 | 0 | 0 | 4269.8427 | 0 | 0 | 9687.2056 | 13343.2584 | 0 | 0 | 0 | 0 | 116252.5553 | 0 | 5470.0126 | 5718.5393 | 293.2584 | 733.1461 | 0 | 127223.1401 | 0 | 0 | 97.7528 | 2541.573 | 6353.9326 | 12707.8652 | 12707.8652 | 1906.1798 | 0 | 0 | 0 | 0 | 2541.573 | 0
2025-09-20 | 504079.5537 | 0 | 96480 | 116479.826 | 14283.4481 | 128685.4751 | 37375.2809 | 207255.5236 | 0 | 0 | 5599.173 | 0 | 0 | 164787.4157 | 9254.8315 | 0 | 0 | 4318.9213 | 0 | 0 | 9798.5528 | 13496.6292 | 0 | 0 | 0 | 0 | 116479.826 | 0 | 5532.8863 | 5784.2697 | 296.6292 | 741.573 | 0 | 128685.4751 | 0 | 0 | 98.8764 | 2570.7865 | 6426.9663 | 12853.9326 | 12853.9326 | 1928.0899 | 0 | 0 | 0 | 0 | 2570.7865 | 0
2025-09-21 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-22 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-23 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-24 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-25 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-26 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-27 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-28 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-29 | 515990.1227 | 0 | 96480 | 121235.7135 | 15652.8678 | 131152.5669 | 38060.8235 | 209888.151 | 277.451 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 557.4039 | 121235.7135 | 0 | 5636.5443 | 6390 | 361.1765 | 902.9412 | 0 | 130595.1629 | 0 | 0 | 100 | 2796.1176 | 6500 | 13020.5882 | 13044.1176 | 2273.5294 | 88.6765 | 0 | 0 | 0 | 2600 | 0
2025-09-30 | 523268.8786 | 358685.61 | 455165.61 | 125764.3302 | 16859.9757 | 132157.3237 | 38321.6471 | 210165.602 | 554.902 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 1114.8078 | 125764.3302 | 0 | 5677.3286 | 6930 | 422.3529 | 1055.8824 | 0 | 131042.5159 | 0 | 0 | 100 | 2992.2353 | 6500 | 13041.1765 | 13088.2353 | 2597.0588 | 177.3529 | 0 | 0 | 0 | 2600 | 0
2025-10-01 | 530547.6345 | 0 | 455165.61 | 130292.9469 | 18067.0835 | 133162.0806 | 38582.4706 | 210443.0529 | 832.3529 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 1672.2118 | 130292.9469 | 0 | 5718.1129 | 7470 | 483.5294 | 1208.8235 | 0 | 131489.8688 | 0 | 0 | 100 | 3188.3529 | 6500 | 13061.7647 | 13132.3529 | 2920.5882 | 266.0294 | 0 | 0 | 0 | 2600 | 0
2025-10-02 | 537826.3904 | 0 | 455165.61 | 134821.5636 | 19274.1914 | 134166.8375 | 38843.2941 | 210720.5039 | 1109.8039 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 2229.6157 | 134821.5636 | 0 | 5758.8973 | 8010 | 544.7059 | 1361.7647 | 0 | 131937.2218 | 0 | 0 | 100 | 3384.4706 | 6500 | 13082.3529 | 13176.4706 | 3244.1176 | 354.7059 | 0 | 0 | 0 | 2600 | 0
2025-10-03 | 545105.1463 | 0 | 455165.61 | 139350.1803 | 20481.2992 | 135171.5943 | 39104.1176 | 210997.9549 | 1387.2549 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 2787.0196 | 139350.1803 | 0 | 5799.6816 | 8550 | 605.8824 | 1514.7059 | 0 | 132384.5747 | 0 | 0 | 100 | 3580.5882 | 6500 | 13102.9412 | 13220.5882 | 3567.6471 | 443.3824 | 0 | 0 | 0 | 2600 | 0
2025-10-04 | 552383.9023 | 0 | 455165.61 | 143878.797 | 21688.4071 | 136176.3512 | 39364.9412 | 211275.4059 | 1664.7059 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 3344.4235 | 143878.797 | 0 | 5840.4659 | 9090 | 667.0588 | 1667.6471 | 0 | 132831.9276 | 0 | 0 | 100 | 3776.7059 | 6500 | 13123.5294 | 13264.7059 | 3891.1765 | 532.0588 | 0 | 0 | 0 | 2600 | 0
2025-10-05 | 559662.6582 | 0 | 455165.61 | 148407.4137 | 22895.5149 | 137181.108 | 39625.7647 | 211552.8569 | 1942.1569 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 3901.8275 | 148407.4137 | 0 | 5881.2502 | 9630 | 728.2353 | 1820.5882 | 0 | 133279.2806 | 0 | 0 | 100 | 3972.8235 | 6500 | 13144.1176 | 13308.8235 | 4214.7059 | 620.7353 | 0 | 0 | 0 | 2600 | 0
2025-10-06 | 566941.4141 | 0 | 455165.61 | 152936.0304 | 24102.6227 | 138185.8649 | 39886.5882 | 211830.3078 | 2219.6078 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 4459.2314 | 152936.0304 | 0 | 5922.0345 | 10170 | 789.4118 | 1973.5294 | 0 | 133726.6335 | 0 | 0 | 100 | 4168.9412 | 6500 | 13164.7059 | 13352.9412 | 4538.2353 | 709.4118 | 0 | 0 | 0 | 2600 | 0
2025-10-07 | 574220.17 | 0 | 455165.61 | 157464.6471 | 25309.7306 | 139190.6218 | 40147.4118 | 212107.7588 | 2497.0588 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 5016.6353 | 157464.6471 | 0 | 5962.8188 | 10710 | 850.5882 | 2126.4706 | 0 | 134173.9865 | 0 | 0 | 100 | 4365.0588 | 6500 | 13185.2941 | 13397.0588 | 4861.7647 | 798.0882 | 0 | 0 | 0 | 2600 | 0
2025-10-08 | 581498.9259 | 0 | 455165.61 | 161993.2638 | 26516.8384 | 140195.3786 | 40408.2353 | 212385.2098 | 2774.5098 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 5574.0392 | 161993.2638 | 0 | 6003.6031 | 11250 | 911.7647 | 2279.4118 | 0 | 134621.3394 | 0 | 0 | 100 | 4561.1765 | 6500 | 13205.8824 | 13441.1765 | 5185.2941 | 886.7647 | 0 | 0 | 0 | 2600 | 0
2025-10-09 | 588777.6818 | 0 | 455165.61 | 166521.8805 | 27723.9463 | 141200.1355 | 40669.0588 | 212662.6608 | 3051.9608 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 6131.4431 | 166521.8805 | 0 | 6044.3875 | 11790 | 972.9412 | 2432.3529 | 0 | 135068.6924 | 0 | 0 | 100 | 4757.2941 | 6500 | 13226.4706 | 13485.2941 | 5508.8235 | 975.4412 | 0 | 0 | 0 | 2600 | 0
2025-10-10 | 596056.4377 | 0 | 455165.61 | 171050.4972 | 28931.0541 | 142204.8924 | 40929.8824 | 212940.1118 | 3329.4118 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 6688.8471 | 171050.4972 | 0 | 6085.1718 | 12330 | 1034.1176 | 2585.2941 | 0 | 135516.0453 | 0 | 0 | 100 | 4953.4118 | 6500 | 13247.0588 | 13529.4118 | 5832.3529 | 1064.1176 | 0 | 0 | 0 | 2600 | 0
2025-10-11 | 603335.1937 | 0 | 455165.61 | 175579.1139 | 30138.162 | 143209.6492 | 41190.7059 | 213217.5627 | 3606.8627 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 7246.251 | 175579.1139 | 0 | 6125.9561 | 12870 | 1095.2941 | 2738.2353 | 0 | 135963.3982 | 0 | 0 | 100 | 5149.5294 | 6500 | 13267.6471 | 13573.5294 | 6155.8824 | 1152.7941 | 0 | 0 | 0 | 2600 | 0
2025-10-12 | 610613.9496 | 0 | 455165.61 | 180107.7306 | 31345.2698 | 144214.4061 | 41451.5294 | 213495.0137 | 3884.3137 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 7803.6549 | 180107.7306 | 0 | 6166.7404 | 13410 | 1156.4706 | 2891.1765 | 0 | 136410.7512 | 0 | 0 | 100 | 5345.6471 | 6500 | 13288.2353 | 13617.6471 | 6479.4118 | 1241.4706 | 0 | 0 | 0 | 2600 | 0
2025-10-13 | 617892.7055 | 0 | 455165.61 | 184636.3472 | 32552.3776 | 145219.1629 | 41712.3529 | 213772.4647 | 4161.7647 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 8361.0588 | 184636.3472 | 0 | 6207.5247 | 13950 | 1217.6471 | 3044.1176 | 0 | 136858.1041 | 0 | 0 | 100 | 5541.7647 | 6500 | 13308.8235 | 13661.7647 | 6802.9412 | 1330.1471 | 0 | 0 | 0 | 2600 | 0
2025-10-14 | 625171.4614 | 0 | 455165.61 | 189164.9639 | 33759.4855 | 146223.9198 | 41973.1765 | 214049.9157 | 4439.2157 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 8918.4627 | 189164.9639 | 0 | 6248.309 | 14490 | 1278.8235 | 3197.0588 | 0 | 137305.4571 | 0 | 0 | 100 | 5737.8824 | 6500 | 13329.4118 | 13705.8824 | 7126.4706 | 1418.8235 | 0 | 0 | 0 | 2600 | 0
2025-10-15 | 632450.2173 | 0 | 455165.61 | 193693.5806 | 34966.5933 | 147228.6767 | 42234 | 214327.3667 | 4716.6667 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 9475.8667 | 193693.5806 | 0 | 6289.0933 | 15030 | 1340 | 3350 | 0 | 137752.81 | 0 | 0 | 100 | 5934 | 6500 | 13350 | 13750 | 7450 | 1507.5 | 0 | 0 | 0 | 2600 | 0
2025-10-16 | 639728.9732 | 0 | 455165.61 | 198222.1973 | 36173.7012 | 148233.4335 | 42494.8235 | 214604.8176 | 4994.1176 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 10033.2706 | 198222.1973 | 0 | 6329.8776 | 15570 | 1401.1765 | 3502.9412 | 0 | 138200.1629 | 0 | 0 | 100 | 6130.1176 | 6500 | 13370.5882 | 13794.1176 | 7773.5294 | 1596.1765 | 0 | 0 | 0 | 2600 | 0
2025-10-17 | 647007.7291 | 0 | 455165.61 | 202750.814 | 37380.809 | 149238.1904 | 42755.6471 | 214882.2686 | 5271.5686 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 10590.6745 | 202750.814 | 0 | 6370.662 | 16110 | 1462.3529 | 3655.8824 | 0 | 138647.5159 | 0 | 0 | 100 | 6326.2353 | 6500 | 13391.1765 | 13838.2353 | 8097.0588 | 1684.8529 | 0 | 0 | 0 | 2600 | 0
2025-10-18 | 654286.4851 | 0 | 455165.61 | 207279.4307 | 38587.9169 | 150242.9473 | 43016.4706 | 215159.7196 | 5549.0196 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 11148.0784 | 207279.4307 | 0 | 6411.4463 | 16650 | 1523.5294 | 3808.8235 | 0 | 139094.8688 | 0 | 0 | 100 | 6522.3529 | 6500 | 13411.7647 | 13882.3529 | 8420.5882 | 1773.5294 | 0 | 0 | 0 | 2600 | 0
2025-10-19 | 661565.241 | 0 | 455165.61 | 211808.0474 | 39795.0247 | 151247.7041 | 43277.2941 | 215437.1706 | 5826.4706 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 11705.4824 | 211808.0474 | 0 | 6452.2306 | 17190 | 1584.7059 | 3961.7647 | 0 | 139542.2218 | 0 | 0 | 100 | 6718.4706 | 6500 | 13432.3529 | 13926.4706 | 8744.1176 | 1862.2059 | 0 | 0 | 0 | 2600 | 0
2025-10-20 | 668843.9969 | 0 | 455165.61 | 216336.6641 | 41002.1325 | 152252.461 | 43538.1176 | 215714.6216 | 6103.9216 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 12262.8863 | 216336.6641 | 0 | 6493.0149 | 17730 | 1645.8824 | 4114.7059 | 0 | 139989.5747 | 0 | 0 | 100 | 6914.5882 | 6500 | 13452.9412 | 13970.5882 | 9067.6471 | 1950.8824 | 0 | 0 | 0 | 2600 | 0
2025-10-21 | 676122.7528 | 0 | 455165.61 | 220865.2808 | 42209.2404 | 153257.2178 | 43798.9412 | 215992.0725 | 6381.3725 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 12820.2902 | 220865.2808 | 0 | 6533.7992 | 18270 | 1707.0588 | 4267.6471 | 0 | 140436.9276 | 0 | 0 | 100 | 7110.7059 | 6500 | 13473.5294 | 14014.7059 | 9391.1765 | 2039.5588 | 0 | 0 | 0 | 2600 | 0
2025-10-22 | 683401.5087 | 0 | 455165.61 | 225393.8975 | 43416.3482 | 154261.9747 | 44059.7647 | 216269.5235 | 6658.8235 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 13377.6941 | 225393.8975 | 0 | 6574.5835 | 18810 | 1768.2353 | 4420.5882 | 0 | 140884.2806 | 0 | 0 | 100 | 7306.8235 | 6500 | 13494.1176 | 14058.8235 | 9714.7059 | 2128.2353 | 0 | 0 | 0 | 2600 | 0
2025-10-23 | 690680.2646 | 0 | 455165.61 | 229922.5142 | 44623.4561 | 155266.7316 | 44320.5882 | 216546.9745 | 6936.2745 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 13935.098 | 229922.5142 | 0 | 6615.3678 | 19350 | 1829.4118 | 4573.5294 | 0 | 141331.6335 | 0 | 0 | 100 | 7502.9412 | 6500 | 13514.7059 | 14102.9412 | 10038.2353 | 2216.9118 | 0 | 0 | 0 | 2600 | 0
2025-10-24 | 697959.0205 | 0 | 455165.61 | 234451.1309 | 45830.5639 | 156271.4884 | 44581.4118 | 216824.4255 | 7213.7255 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 14492.502 | 234451.1309 | 0 | 6656.1522 | 19890 | 1890.5882 | 4726.4706 | 0 | 141778.9865 | 0 | 0 | 100 | 7699.0588 | 6500 | 13535.2941 | 14147.0588 | 10361.7647 | 2305.5882 | 0 | 0 | 0 | 2600 | 0
2025-10-25 | 705237.7765 | 0 | 455165.61 | 238979.7476 | 47037.6718 | 157276.2453 | 44842.2353 | 217101.8765 | 7491.1765 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 15049.9059 | 238979.7476 | 0 | 6696.9365 | 20430 | 1951.7647 | 4879.4118 | 0 | 142226.3394 | 0 | 0 | 100 | 7895.1765 | 6500 | 13555.8824 | 14191.1765 | 10685.2941 | 2394.2647 | 0 | 0 | 0 | 2600 | 0
2025-10-26 | 712516.5324 | 0 | 455165.61 | 243508.3643 | 48244.7796 | 158281.0022 | 45103.0588 | 217379.3275 | 7768.6275 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 15607.3098 | 243508.3643 | 0 | 6737.7208 | 20970 | 2012.9412 | 5032.3529 | 0 | 142673.6924 | 0 | 0 | 100 | 8091.2941 | 6500 | 13576.4706 | 14235.2941 | 11008.8235 | 2482.9412 | 0 | 0 | 0 | 2600 | 0
2025-10-27 | 719795.2883 |  |  | 248036.981 | 49451.8875 | 159285.759 | 45363.8824 | 217656.7784 | 8046.0784 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 16164.7137 | 248036.981 | 0 | 6778.5051 | 21510 | 2074.1176 | 5185.2941 | 0 | 143121.0453 | 0 | 0 | 100 | 8287.4118 | 6500 | 13597.0588 | 14279.4118 | 11332.3529 | 2571.6176 | 0 | 0 | 0 | 2600 | 0
2025-10-28 | 727074.0442 |  |  | 252565.5977 | 50658.9953 | 160290.5159 | 45624.7059 | 217934.2294 | 8323.5294 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 16722.1176 | 252565.5977 | 0 | 6819.2894 | 22050 | 2135.2941 | 5338.2353 | 0 | 143568.3982 | 0 | 0 | 100 | 8483.5294 | 6500 | 13617.6471 | 14323.5294 | 11655.8824 | 2660.2941 | 0 | 0 | 0 | 2600 | 0
2025-10-29 | 734352.8001 |  |  | 257094.2144 | 51866.1031 | 161295.2727 | 45885.5294 | 218211.6804 | 8600.9804 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 17279.5216 | 257094.2144 | 0 | 6860.0737 | 22590 | 2196.4706 | 5491.1765 | 0 | 144015.7512 | 0 | 0 | 100 | 8679.6471 | 6500 | 13638.2353 | 14367.6471 | 11979.4118 | 2748.9706 | 0 | 0 | 0 | 2600 | 0
2025-10-30 | 741631.556 |  |  | 261622.8311 | 53073.211 | 162300.0296 | 46146.3529 | 218489.1314 | 8878.4314 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 17836.9255 | 261622.8311 | 0 | 6900.858 | 23130 | 2257.6471 | 5644.1176 | 0 | 144463.1041 | 0 | 0 | 100 | 8875.7647 | 6500 | 13658.8235 | 14411.7647 | 12302.9412 | 2837.6471 | 0 | 0 | 0 | 2600 | 0
2025-10-31 | 748910.3119 |  |  | 266151.4478 | 54280.3188 | 163304.7865 | 46407.1765 | 218766.5824 | 9155.8824 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 18394.3294 | 266151.4478 | 0 | 6941.6424 | 23670 | 2318.8235 | 5797.0588 | 0 | 144910.4571 | 0 | 0 | 100 | 9071.8824 | 6500 | 13679.4118 | 14455.8824 | 12626.4706 | 2926.3235 | 0 | 0 | 0 | 2600 | 0
2025-11-01 | 756189.0678 |  |  | 270680.0645 | 55487.4267 | 164309.5433 | 46668 | 219044.0333 | 9433.3333 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 18951.7333 | 270680.0645 | 0 | 6982.4267 | 24210 | 2380 | 5950 | 0 | 145357.81 | 0 | 0 | 100 | 9268 | 6500 | 13700 | 14500 | 12950 | 3015 | 0 | 0 | 0 | 2600 | 0
2025-11-02 | 763467.8238 |  |  | 275208.6812 | 56694.5345 | 165314.3002 | 46928.8235 | 219321.4843 | 9710.7843 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 19509.1373 | 275208.6812 | 0 | 7023.211 | 24750 | 2441.1765 | 6102.9412 | 0 | 145805.1629 | 0 | 0 | 100 | 9464.1176 | 6500 | 13720.5882 | 14544.1176 | 13273.5294 | 3103.6765 | 0 | 0 | 0 | 2600 | 0
2025-11-03 | 770746.5797 |  |  | 279737.2979 | 57901.6424 | 166319.0571 | 47189.6471 | 219598.9353 | 9988.2353 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 20066.5412 | 279737.2979 | 0 | 7063.9953 | 25290 | 2502.3529 | 6255.8824 | 0 | 146252.5159 | 0 | 0 | 100 | 9660.2353 | 6500 | 13741.1765 | 14588.2353 | 13597.0588 | 3192.3529 | 0 | 0 | 0 | 2600 | 0
2025-11-04 | 778025.3356 |  |  | 284265.9146 | 59108.7502 | 167323.8139 | 47450.4706 | 219876.3863 | 10265.6863 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 20623.9451 | 284265.9146 | 0 | 7104.7796 | 25830 | 2563.5294 | 6408.8235 | 0 | 146699.8688 | 0 | 0 | 100 | 9856.3529 | 6500 | 13761.7647 | 14632.3529 | 13920.5882 | 3281.0294 | 0 | 0 | 0 | 2600 | 0
2025-11-05 | 785304.0915 |  |  | 288794.5313 | 60315.858 | 168328.5708 | 47711.2941 | 220153.8373 | 10543.1373 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 21181.349 | 288794.5313 | 0 | 7145.5639 | 26370 | 2624.7059 | 6561.7647 | 0 | 147147.2218 | 0 | 0 | 100 | 10052.4706 | 6500 | 13782.3529 | 14676.4706 | 14244.1176 | 3369.7059 | 0 | 0 | 0 | 2600 | 0
2025-11-06 | 792582.8474 |  |  | 293323.148 | 61522.9659 | 169333.3276 | 47972.1176 | 220431.2882 | 10820.5882 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 21738.7529 | 293323.148 | 0 | 7186.3482 | 26910 | 2685.8824 | 6714.7059 | 0 | 147594.5747 | 0 | 0 | 100 | 10248.5882 | 6500 | 13802.9412 | 14720.5882 | 14567.6471 | 3458.3824 | 0 | 0 | 0 | 2600 | 0
2025-11-07 | 799861.6033 |  |  | 297851.7647 | 62730.0737 | 170338.0845 | 48232.9412 | 220708.7392 | 11098.0392 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 22296.1569 | 297851.7647 | 0 | 7227.1325 | 27450 | 2747.0588 | 6867.6471 | 0 | 148041.9276 | 0 | 0 | 100 | 10444.7059 | 6500 | 13823.5294 | 14764.7059 | 14891.1765 | 3547.0588 | 0 | 0 | 0 | 2600 | 0
2025-11-08 | 807140.3592 |  |  | 302380.3814 | 63937.1816 | 171342.8414 | 48493.7647 | 220986.1902 | 11375.4902 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 22853.5608 | 302380.3814 | 0 | 7267.9169 | 27990 | 2808.2353 | 7020.5882 | 0 | 148489.2806 | 0 | 0 | 100 | 10640.8235 | 6500 | 13844.1176 | 14808.8235 | 15214.7059 | 3635.7353 | 0 | 0 | 0 | 2600 | 0
2025-11-09 | 814419.1152 |  |  | 306908.9981 | 65144.2894 | 172347.5982 | 48754.5882 | 221263.6412 | 11652.9412 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 23410.9647 | 306908.9981 | 0 | 7308.7012 | 28530 | 2869.4118 | 7173.5294 | 0 | 148936.6335 | 0 | 0 | 100 | 10836.9412 | 6500 | 13864.7059 | 14852.9412 | 15538.2353 | 3724.4118 | 0 | 0 | 0 | 2600 | 0
2025-11-10 | 821697.8711 |  |  | 311437.6148 | 66351.3973 | 173352.3551 | 49015.4118 | 221541.0922 | 11930.3922 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 23968.3686 | 311437.6148 | 0 | 7349.4855 | 29070 | 2930.5882 | 7326.4706 | 0 | 149383.9865 | 0 | 0 | 100 | 11033.0588 | 6500 | 13885.2941 | 14897.0588 | 15861.7647 | 3813.0882 | 0 | 0 | 0 | 2600 | 0
2025-11-11 | 828976.627 |  |  | 315966.2315 | 67558.5051 | 174357.112 | 49276.2353 | 221818.5431 | 12207.8431 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 24525.7725 | 315966.2315 | 0 | 7390.2698 | 29610 | 2991.7647 | 7479.4118 | 0 | 149831.3394 | 0 | 0 | 100 | 11229.1765 | 6500 | 13905.8824 | 14941.1765 | 16185.2941 | 3901.7647 | 0 | 0 | 0 | 2600 | 0
2025-11-12 | 836255.3829 |  |  | 320494.8482 | 68765.6129 | 175361.8688 | 49537.0588 | 222095.9941 | 12485.2941 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 25083.1765 | 320494.8482 | 0 | 7431.0541 | 30150 | 3052.9412 | 7632.3529 | 0 | 150278.6924 | 0 | 0 | 100 | 11425.2941 | 6500 | 13926.4706 | 14985.2941 | 16508.8235 | 3990.4412 | 0 | 0 | 0 | 2600 | 0
2025-11-13 | 843534.1388 |  |  | 325023.4649 | 69972.7208 | 176366.6257 | 49797.8824 | 222373.4451 | 12762.7451 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 25640.5804 | 325023.4649 | 0 | 7471.8384 | 30690 | 3114.1176 | 7785.2941 | 0 | 150726.0453 | 0 | 0 | 100 | 11621.4118 | 6500 | 13947.0588 | 15029.4118 | 16832.3529 | 4079.1176 | 0 | 0 | 0 | 2600 | 0
2025-11-14 | 850812.8947 |  |  | 329552.0816 | 71179.8286 | 177371.3825 | 50058.7059 | 222650.8961 | 13040.1961 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 26197.9843 | 329552.0816 | 0 | 7512.6227 | 31230 | 3175.2941 | 7938.2353 | 0 | 151173.3982 | 0 | 0 | 100 | 11817.5294 | 6500 | 13967.6471 | 15073.5294 | 17155.8824 | 4167.7941 | 0 | 0 | 0 | 2600 | 0
2025-11-15 | 858091.6506 |  |  | 334080.6983 | 72386.9365 | 178376.1394 | 50319.5294 | 222928.3471 | 13317.6471 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 26755.3882 | 334080.6983 | 0 | 7553.4071 | 31770 | 3236.4706 | 8091.1765 | 0 | 151620.7512 | 0 | 0 | 100 | 12013.6471 | 6500 | 13988.2353 | 15117.6471 | 17479.4118 | 4256.4706 | 0 | 0 | 0 | 2600 | 0
2025-11-16 | 865370.4066 |  |  | 338609.315 | 73594.0443 | 179380.8963 | 50580.3529 | 223205.798 | 13595.098 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 27312.7922 | 338609.315 | 0 | 7594.1914 | 32310 | 3297.6471 | 8244.1176 | 0 | 152068.1041 | 0 | 0 | 100 | 12209.7647 | 6500 | 14008.8235 | 15161.7647 | 17802.9412 | 4345.1471 | 0 | 0 | 0 | 2600 | 0
2025-11-17 | 872649.1625 |  |  | 343137.9317 | 74801.1522 | 180385.6531 | 50841.1765 | 223483.249 | 13872.549 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 27870.1961 | 343137.9317 | 0 | 7634.9757 | 32850 | 3358.8235 | 8397.0588 | 0 | 152515.4571 | 0 | 0 | 100 | 12405.8824 | 6500 | 14029.4118 | 15205.8824 | 18126.4706 | 4433.8235 | 0 | 0 | 0 | 2600 | 0
2025-11-18 | 879927.9184 |  |  | 347666.5484 | 76008.26 | 181390.41 | 51102 | 223760.7 | 14150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 28427.6 | 347666.5484 | 0 | 7675.76 | 33390 | 3420 | 8550 | 0 | 152962.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-19 | 884233.6354 |  |  | 349525.6464 | 76730.879 | 182283.6957 | 51102 | 224591.4143 | 14459.5238 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 521.1905 | 0 | 0 | 28427.6 | 349525.6464 | 0 | 7719.8076 | 33831.0714 | 3487.8571 | 8719.6429 | 0 | 153856.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-20 | 888539.3524 |  |  | 351384.7444 | 77453.4981 | 183176.9814 | 51102 | 225422.1286 | 14769.0476 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 1042.381 | 0 | 0 | 28427.6 | 351384.7444 | 0 | 7763.8552 | 34272.1429 | 3555.7143 | 8889.2857 | 0 | 154749.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-21 | 892845.0695 |  |  | 353243.8423 | 78176.1171 | 184070.2671 | 51102 | 226252.8429 | 15078.5714 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 1563.5714 | 0 | 0 | 28427.6 | 353243.8423 | 0 | 7807.9029 | 34713.2143 | 3623.5714 | 9058.9286 | 0 | 155642.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-22 | 897150.7865 |  |  | 355102.9403 | 78898.7362 | 184963.5529 | 51102 | 227083.5571 | 15388.0952 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 2084.7619 | 0 | 0 | 28427.6 | 355102.9403 | 0 | 7851.9505 | 35154.2857 | 3691.4286 | 9228.5714 | 0 | 156535.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-23 | 901456.5035 |  |  | 356962.0383 | 79621.3552 | 185856.8386 | 51102 | 227914.2714 | 15697.619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 2605.9524 | 0 | 0 | 28427.6 | 356962.0383 | 0 | 7895.9981 | 35595.3571 | 3759.2857 | 9398.2143 | 0 | 157429.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-24 | 905762.2206 |  |  | 358821.1363 | 80343.9743 | 186750.1243 | 51102 | 228744.9857 | 16007.1429 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 3127.1429 | 0 | 0 | 28427.6 | 358821.1363 | 0 | 7940.0457 | 36036.4286 | 3827.1429 | 9567.8571 | 0 | 158322.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-25 | 910067.9376 |  |  | 360680.2343 | 81066.5933 | 187643.41 | 51102 | 229575.7 | 16316.6667 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 3648.3333 | 0 | 0 | 28427.6 | 360680.2343 | 0 | 7984.0933 | 36477.5 | 3895 | 9737.5 | 0 | 159215.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-26 | 914373.6546 |  |  | 362539.3323 | 81789.2124 | 188536.6957 | 51102 | 230406.4143 | 16626.1905 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 4169.5238 | 0 | 0 | 28427.6 | 362539.3323 | 0 | 8028.141 | 36918.5714 | 3962.8571 | 9907.1429 | 0 | 160109.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-27 | 918679.3717 |  |  | 364398.4302 | 82511.8314 | 189429.9814 | 51102 | 231237.1286 | 16935.7143 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 4690.7143 | 0 | 0 | 28427.6 | 364398.4302 | 0 | 8072.1886 | 37359.6429 | 4030.7143 | 10076.7857 | 0 | 161002.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-28 | 922985.0887 |  |  | 366257.5282 | 83234.4505 | 190323.2671 | 51102 | 232067.8429 | 17245.2381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 5211.9048 | 0 | 0 | 28427.6 | 366257.5282 | 0 | 8116.2362 | 37800.7143 | 4098.5714 | 10246.4286 | 0 | 161895.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-29 | 927290.8057 |  |  | 368116.6262 | 83957.0695 | 191216.5529 | 51102 | 232898.5571 | 17554.7619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 5733.0952 | 0 | 0 | 28427.6 | 368116.6262 | 0 | 8160.2838 | 38241.7857 | 4166.4286 | 10416.0714 | 0 | 162788.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-30 | 931596.5228 |  |  | 369975.7242 | 84679.6886 | 192109.8386 | 51102 | 233729.2714 | 17864.2857 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 6254.2857 | 0 | 0 | 28427.6 | 369975.7242 | 0 | 8204.3314 | 38682.8571 | 4234.2857 | 10585.7143 | 0 | 163682.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-01 | 935902.2398 |  |  | 371834.8222 | 85402.3076 | 193003.1243 | 51102 | 234559.9857 | 18173.8095 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 6775.4762 | 0 | 0 | 28427.6 | 371834.8222 | 0 | 8248.379 | 39123.9286 | 4302.1429 | 10755.3571 | 0 | 164575.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-02 | 940207.9568 |  |  | 373693.9201 | 86124.9267 | 193896.41 | 51102 | 235390.7 | 18483.3333 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 7296.6667 | 0 | 0 | 28427.6 | 373693.9201 | 0 | 8292.4267 | 39565 | 4370 | 10925 | 0 | 165468.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-03 | 944513.6738 |  |  | 375553.0181 | 86847.5457 | 194789.6957 | 51102 | 236221.4143 | 18792.8571 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 7817.8571 | 0 | 0 | 28427.6 | 375553.0181 | 0 | 8336.4743 | 40006.0714 | 4437.8571 | 11094.6429 | 0 | 166362.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-04 | 948819.3909 |  |  | 377412.1161 | 87570.1648 | 195682.9814 | 51102 | 237052.1286 | 19102.381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 8339.0476 | 0 | 0 | 28427.6 | 377412.1161 | 0 | 8380.5219 | 40447.1429 | 4505.7143 | 11264.2857 | 0 | 167255.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-05 | 953125.1079 |  |  | 379271.2141 | 88292.7838 | 196576.2671 | 51102 | 237882.8429 | 19411.9048 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 8860.2381 | 0 | 0 | 28427.6 | 379271.2141 | 0 | 8424.5695 | 40888.2143 | 4573.5714 | 11433.9286 | 0 | 168148.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-06 | 957430.8249 |  |  | 381130.3121 | 89015.4029 | 197469.5529 | 51102 | 238713.5571 | 19721.4286 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 9381.4286 | 0 | 0 | 28427.6 | 381130.3121 | 0 | 8468.6171 | 41329.2857 | 4641.4286 | 11603.5714 | 0 | 169041.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-07 | 961736.542 |  |  | 382989.4101 | 89738.0219 | 198362.8386 | 51102 | 239544.2714 | 20030.9524 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 9902.619 | 0 | 0 | 28427.6 | 382989.4101 | 0 | 8512.6648 | 41770.3571 | 4709.2857 | 11773.2143 | 0 | 169935.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-08 | 966042.259 |  |  | 384848.508 | 90460.641 | 199256.1243 | 51102 | 240374.9857 | 20340.4762 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 10423.8095 | 0 | 0 | 28427.6 | 384848.508 | 0 | 8556.7124 | 42211.4286 | 4777.1429 | 11942.8571 | 0 | 170828.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-09 | 970347.976 |  |  | 386707.606 | 91183.26 | 200149.41 | 51102 | 241205.7 | 20650 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 10945 | 0 | 0 | 28427.6 | 386707.606 | 0 | 8600.76 | 42652.5 | 4845 | 12112.5 | 0 | 171721.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-10 | 974653.6931 |  |  | 388566.704 | 91905.879 | 201042.6957 | 51102 | 242036.4143 | 20959.5238 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 11466.1905 | 0 | 0 | 28427.6 | 388566.704 | 0 | 8644.8076 | 43093.5714 | 4912.8571 | 12282.1429 | 0 | 172615.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-11 | 978959.4101 |  |  | 390425.802 | 92628.4981 | 201935.9814 | 51102 | 242867.1286 | 21269.0476 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 11987.381 | 0 | 0 | 28427.6 | 390425.802 | 0 | 8688.8552 | 43534.6429 | 4980.7143 | 12451.7857 | 0 | 173508.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-12 | 983265.1271 |  |  | 392284.9 | 93351.1171 | 202829.2671 | 51102 | 243697.8429 | 21578.5714 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 12508.5714 | 0 | 0 | 28427.6 | 392284.9 | 0 | 8732.9029 | 43975.7143 | 5048.5714 | 12621.4286 | 0 | 174401.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-13 | 987570.8442 |  |  | 394143.998 | 94073.7362 | 203722.5529 | 51102 | 244528.5571 | 21888.0952 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 13029.7619 | 0 | 0 | 28427.6 | 394143.998 | 0 | 8776.9505 | 44416.7857 | 5116.4286 | 12791.0714 | 0 | 175294.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-14 | 991876.5612 |  |  | 396003.0959 | 94796.3552 | 204615.8386 | 51102 | 245359.2714 | 22197.619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 13550.9524 | 0 | 0 | 28427.6 | 396003.0959 | 0 | 8820.9981 | 44857.8571 | 5184.2857 | 12960.7143 | 0 | 176188.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-15 | 996182.2782 |  |  | 397862.1939 | 95518.9743 | 205509.1243 | 51102 | 246189.9857 | 22507.1429 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 14072.1429 | 0 | 0 | 28427.6 | 397862.1939 | 0 | 8865.0457 | 45298.9286 | 5252.1429 | 13130.3571 | 0 | 177081.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-16 | 1000487.9952 |  |  | 399721.2919 | 96241.5933 | 206402.41 | 51102 | 247020.7 | 22816.6667 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 14593.3333 | 0 | 0 | 28427.6 | 399721.2919 | 0 | 8909.0933 | 45740 | 5320 | 13300 | 0 | 177974.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-17 | 1004793.7123 |  |  | 401580.3899 | 96964.2124 | 207295.6957 | 51102 | 247851.4143 | 23126.1905 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 15114.5238 | 0 | 0 | 28427.6 | 401580.3899 | 0 | 8953.141 | 46181.0714 | 5387.8571 | 13469.6429 | 0 | 178868.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-18 | 1009099.4293 |  |  | 403439.4879 | 97686.8314 | 208188.9814 | 51102 | 248682.1286 | 23435.7143 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 15635.7143 | 0 | 0 | 28427.6 | 403439.4879 | 0 | 8997.1886 | 46622.1429 | 5455.7143 | 13639.2857 | 0 | 179761.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-19 | 1013405.1463 |  |  | 405298.5859 | 98409.4505 | 209082.2671 | 51102 | 249512.8429 | 23745.2381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 16156.9048 | 0 | 0 | 28427.6 | 405298.5859 | 0 | 9041.2362 | 47063.2143 | 5523.5714 | 13808.9286 | 0 | 180654.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-20 | 1017710.8634 |  |  | 407157.6838 | 99132.0695 | 209975.5529 | 51102 | 250343.5571 | 24054.7619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 16678.0952 | 0 | 0 | 28427.6 | 407157.6838 | 0 | 9085.2838 | 47504.2857 | 5591.4286 | 13978.5714 | 0 | 181547.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-21 | 1022016.5804 |  |  | 409016.7818 | 99854.6886 | 210868.8386 | 51102 | 251174.2714 | 24364.2857 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 17199.2857 | 0 | 0 | 28427.6 | 409016.7818 | 0 | 9129.3314 | 47945.3571 | 5659.2857 | 14148.2143 | 0 | 182441.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-22 | 1026322.2974 |  |  | 410875.8798 | 100577.3076 | 211762.1243 | 51102 | 252004.9857 | 24673.8095 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 17720.4762 | 0 | 0 | 28427.6 | 410875.8798 | 0 | 9173.379 | 48386.4286 | 5727.1429 | 14317.8571 | 0 | 183334.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-23 | 1030628.0145 |  |  | 412734.9778 | 101299.9267 | 212655.41 | 51102 | 252835.7 | 24983.3333 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 18241.6667 | 0 | 0 | 28427.6 | 412734.9778 | 0 | 9217.4267 | 48827.5 | 5795 | 14487.5 | 0 | 184227.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-24 | 1034933.7315 |  |  | 414594.0758 | 102022.5457 | 213548.6957 | 51102 | 253666.4143 | 25292.8571 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 18762.8571 | 0 | 0 | 28427.6 | 414594.0758 | 0 | 9261.4743 | 49268.5714 | 5862.8571 | 14657.1429 | 0 | 185121.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-25 | 1039239.4485 |  |  | 416453.1738 | 102745.1648 | 214441.9814 | 51102 | 254497.1286 | 25602.381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 19284.0476 | 0 | 0 | 28427.6 | 416453.1738 | 0 | 9305.5219 | 49709.6429 | 5930.7143 | 14826.7857 | 0 | 186014.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-26 | 1043545.1655 |  |  | 418312.2717 | 103467.7838 | 215335.2671 | 51102 | 255327.8429 | 25911.9048 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 19805.2381 | 0 | 0 | 28427.6 | 418312.2717 | 0 | 9349.5695 | 50150.7143 | 5998.5714 | 14996.4286 | 0 | 186907.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-27 | 1047850.8826 |  |  | 420171.3697 | 104190.4029 | 216228.5529 | 51102 | 256158.5571 | 26221.4286 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 20326.4286 | 0 | 0 | 28427.6 | 420171.3697 | 0 | 9393.6171 | 50591.7857 | 6066.4286 | 15166.0714 | 0 | 187800.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-28 | 1052156.5996 |  |  | 422030.4677 | 104913.0219 | 217121.8386 | 51102 | 256989.2714 | 26530.9524 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 20847.619 | 0 | 0 | 28427.6 | 422030.4677 | 0 | 9437.6648 | 51032.8571 | 6134.2857 | 15335.7143 | 0 | 188694.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-29 | 1056462.3166 |  |  | 423889.5657 | 105635.641 | 218015.1243 | 51102 | 257819.9857 | 26840.4762 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 21368.8095 | 0 | 0 | 28427.6 | 423889.5657 | 0 | 9481.7124 | 51473.9286 | 6202.1429 | 15505.3571 | 0 | 189587.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-30 | 1060768.0337 |  |  | 425748.6637 | 106358.26 | 218908.41 | 51102 | 258650.7 | 27150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 21890 | 0 | 0 | 28427.6 | 425748.6637 | 0 | 9525.76 | 51915 | 6270 | 15675 | 0 | 190480.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-31 | 1065073.7507 |  |  | 427607.7617 | 107080.879 | 219801.6957 | 51102 | 259481.4143 | 27459.5238 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 22411.1905 | 0 | 0 | 28427.6 | 427607.7617 | 0 | 9569.8076 | 52356.0714 | 6337.8571 | 15844.6429 | 0 | 191374.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-01 | 1069379.4677 |  |  | 429466.8596 | 107803.4981 | 220694.9814 | 51102 | 260312.1286 | 27769.0476 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 22932.381 | 0 | 0 | 28427.6 | 429466.8596 | 0 | 9613.8552 | 52797.1429 | 6405.7143 | 16014.2857 | 0 | 192267.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-02 | 1073685.1848 |  |  | 431325.9576 | 108526.1171 | 221588.2671 | 51102 | 261142.8429 | 28078.5714 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 23453.5714 | 0 | 0 | 28427.6 | 431325.9576 | 0 | 9657.9029 | 53238.2143 | 6473.5714 | 16183.9286 | 0 | 193160.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-03 | 1077990.9018 |  |  | 433185.0556 | 109248.7362 | 222481.5529 | 51102 | 261973.5571 | 28388.0952 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 23974.7619 | 0 | 0 | 28427.6 | 433185.0556 | 0 | 9701.9505 | 53679.2857 | 6541.4286 | 16353.5714 | 0 | 194053.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-04 | 1082296.6188 |  |  | 435044.1536 | 109971.3552 | 223374.8386 | 51102 | 262804.2714 | 28697.619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 24495.9524 | 0 | 0 | 28427.6 | 435044.1536 | 0 | 9745.9981 | 54120.3571 | 6609.2857 | 16523.2143 | 0 | 194947.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-05 | 1086602.3359 |  |  | 436903.2516 | 110693.9743 | 224268.1243 | 51102 | 263634.9857 | 29007.1429 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 25017.1429 | 0 | 0 | 28427.6 | 436903.2516 | 0 | 9790.0457 | 54561.4286 | 6677.1429 | 16692.8571 | 0 | 195840.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-06 | 1090908.0529 |  |  | 438762.3496 | 111416.5933 | 225161.41 | 51102 | 264465.7 | 29316.6667 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 25538.3333 | 0 | 0 | 28427.6 | 438762.3496 | 0 | 9834.0933 | 55002.5 | 6745 | 16862.5 | 0 | 196733.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-07 | 1095213.7699 |  |  | 440621.4475 | 112139.2124 | 226054.6957 | 51102 | 265296.4143 | 29626.1905 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 26059.5238 | 0 | 0 | 28427.6 | 440621.4475 | 0 | 9878.141 | 55443.5714 | 6812.8571 | 17032.1429 | 0 | 197627.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-08 | 1099519.4869 |  |  | 442480.5455 | 112861.8314 | 226947.9814 | 51102 | 266127.1286 | 29935.7143 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 26580.7143 | 0 | 0 | 28427.6 | 442480.5455 | 0 | 9922.1886 | 55884.6429 | 6880.7143 | 17201.7857 | 0 | 198520.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-09 | 1103825.204 |  |  | 444339.6435 | 113584.4505 | 227841.2671 | 51102 | 266957.8429 | 30245.2381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 27101.9048 | 0 | 0 | 28427.6 | 444339.6435 | 0 | 9966.2362 | 56325.7143 | 6948.5714 | 17371.4286 | 0 | 199413.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-10 | 1108130.921 |  |  | 446198.7415 | 114307.0695 | 228734.5529 | 51102 | 267788.5571 | 30554.7619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 27623.0952 | 0 | 0 | 28427.6 | 446198.7415 | 0 | 10010.2838 | 56766.7857 | 7016.4286 | 17541.0714 | 0 | 200306.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-11 | 1112436.638 |  |  | 448057.8395 | 115029.6886 | 229627.8386 | 51102 | 268619.2714 | 30864.2857 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 28144.2857 | 0 | 0 | 28427.6 | 448057.8395 | 0 | 10054.3314 | 57207.8571 | 7084.2857 | 17710.7143 | 0 | 201200.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-12 | 1116742.3551 |  |  | 449916.9374 | 115752.3076 | 230521.1243 | 51102 | 269449.9857 | 31173.8095 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 28665.4762 | 0 | 0 | 28427.6 | 449916.9374 | 0 | 10098.379 | 57648.9286 | 7152.1429 | 17880.3571 | 0 | 202093.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-13 | 1121048.0721 |  |  | 451776.0354 | 116474.9267 | 231414.41 | 51102 | 270280.7 | 31483.3333 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 29186.6667 | 0 | 0 | 28427.6 | 451776.0354 | 0 | 10142.4267 | 58090 | 7220 | 18050 | 0 | 202986.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-14 | 1125353.7891 |  |  | 453635.1334 | 117197.5457 | 232307.6957 | 51102 | 271111.4143 | 31792.8571 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 29707.8571 | 0 | 0 | 28427.6 | 453635.1334 | 0 | 10186.4743 | 58531.0714 | 7287.8571 | 18219.6429 | 0 | 203880.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-15 | 1129659.5062 |  |  | 455494.2314 | 117920.1648 | 233200.9814 | 51102 | 271942.1286 | 32102.381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 30229.0476 | 0 | 0 | 28427.6 | 455494.2314 | 0 | 10230.5219 | 58972.1429 | 7355.7143 | 18389.2857 | 0 | 204773.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-16 | 1133965.2232 |  |  | 457353.3294 | 118642.7838 | 234094.2671 | 51102 | 272772.8429 | 32411.9048 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 30750.2381 | 0 | 0 | 28427.6 | 457353.3294 | 0 | 10274.5695 | 59413.2143 | 7423.5714 | 18558.9286 | 0 | 205666.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-17 | 1138270.9402 |  |  | 459212.4274 | 119365.4029 | 234987.5529 | 51102 | 273603.5571 | 32721.4286 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 31271.4286 | 0 | 0 | 28427.6 | 459212.4274 | 0 | 10318.6171 | 59854.2857 | 7491.4286 | 18728.5714 | 0 | 206559.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-18 | 1142576.6573 |  |  | 461071.5253 | 120088.0219 | 235880.8386 | 51102 | 274434.2714 | 33030.9524 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 31792.619 | 0 | 0 | 28427.6 | 461071.5253 | 0 | 10362.6648 | 60295.3571 | 7559.2857 | 18898.2143 | 0 | 207453.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-19 | 1146882.3743 |  |  | 462930.6233 | 120810.641 | 236774.1243 | 51102 | 275264.9857 | 33340.4762 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 32313.8095 | 0 | 0 | 28427.6 | 462930.6233 | 0 | 10406.7124 | 60736.4286 | 7627.1429 | 19067.8571 | 0 | 208346.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-20 | 1151188.0913 |  |  | 464789.7213 | 121533.26 | 237667.41 | 51102 | 276095.7 | 33650 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 32835 | 0 | 0 | 28427.6 | 464789.7213 | 0 | 10450.76 | 61177.5 | 7695 | 19237.5 | 0 | 209239.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-21 | 1155493.8083 |  |  | 466648.8193 | 122255.879 | 238560.6957 | 51102 | 276926.4143 | 33959.5238 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 33356.1905 | 0 | 0 | 28427.6 | 466648.8193 | 0 | 10494.8076 | 61618.5714 | 7762.8571 | 19407.1429 | 0 | 210133.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-22 | 1159799.5254 |  |  | 468507.9173 | 122978.4981 | 239453.9814 | 51102 | 277757.1286 | 34269.0476 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 33877.381 | 0 | 0 | 28427.6 | 468507.9173 | 0 | 10538.8552 | 62059.6429 | 7830.7143 | 19576.7857 | 0 | 211026.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-23 | 1164105.2424 |  |  | 470367.0153 | 123701.1171 | 240347.2671 | 51102 | 278587.8429 | 34578.5714 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 34398.5714 | 0 | 0 | 28427.6 | 470367.0153 | 0 | 10582.9029 | 62500.7143 | 7898.5714 | 19746.4286 | 0 | 211919.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-24 | 1168410.9594 |  |  | 472226.1132 | 124423.7362 | 241240.5529 | 51102 | 279418.5571 | 34888.0952 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 34919.7619 | 0 | 0 | 28427.6 | 472226.1132 | 0 | 10626.9505 | 62941.7857 | 7966.4286 | 19916.0714 | 0 | 212812.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-25 | 1172716.6765 |  |  | 474085.2112 | 125146.3552 | 242133.8386 | 51102 | 280249.2714 | 35197.619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 35440.9524 | 0 | 0 | 28427.6 | 474085.2112 | 0 | 10670.9981 | 63382.8571 | 8034.2857 | 20085.7143 | 0 | 213706.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-26 | 1177022.3935 |  |  | 475944.3092 | 125868.9743 | 243027.1243 | 51102 | 281079.9857 | 35507.1429 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 35962.1429 | 0 | 0 | 28427.6 | 475944.3092 | 0 | 10715.0457 | 63823.9286 | 8102.1429 | 20255.3571 | 0 | 214599.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-27 | 1181328.1105 |  |  | 477803.4072 | 126591.5933 | 243920.41 | 51102 | 281910.7 | 35816.6667 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 36483.3333 | 0 | 0 | 28427.6 | 477803.4072 | 0 | 10759.0933 | 64265 | 8170 | 20425 | 0 | 215492.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-28 | 1185633.8276 |  |  | 479662.5052 | 127314.2124 | 244813.6957 | 51102 | 282741.4143 | 36126.1905 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 37004.5238 | 0 | 0 | 28427.6 | 479662.5052 | 0 | 10803.141 | 64706.0714 | 8237.8571 | 20594.6429 | 0 | 216386.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-29 | 1189939.5446 |  |  | 481521.6032 | 128036.8314 | 245706.9814 | 51102 | 283572.1286 | 36435.7143 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 37525.7143 | 0 | 0 | 28427.6 | 481521.6032 | 0 | 10847.1886 | 65147.1429 | 8305.7143 | 20764.2857 | 0 | 217279.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-30 | 1194245.2616 |  |  | 483380.7011 | 128759.4505 | 246600.2671 | 51102 | 284402.8429 | 36745.2381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 38046.9048 | 0 | 0 | 28427.6 | 483380.7011 | 0 | 10891.2362 | 65588.2143 | 8373.5714 | 20933.9286 | 0 | 218172.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-31 | 1198550.9786 |  |  | 485239.7991 | 129482.0695 | 247493.5529 | 51102 | 285233.5571 | 37054.7619 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 38568.0952 | 0 | 0 | 28427.6 | 485239.7991 | 0 | 10935.2838 | 66029.2857 | 8441.4286 | 21103.5714 | 0 | 219065.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-01 | 1202856.6957 |  |  | 487098.8971 | 130204.6886 | 248386.8386 | 51102 | 286064.2714 | 37364.2857 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 39089.2857 | 0 | 0 | 28427.6 | 487098.8971 | 0 | 10979.3314 | 66470.3571 | 8509.2857 | 21273.2143 | 0 | 219959.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-02 | 1207162.4127 |  |  | 488957.9951 | 130927.3076 | 249280.1243 | 51102 | 286894.9857 | 37673.8095 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 39610.4762 | 0 | 0 | 28427.6 | 488957.9951 | 0 | 11023.379 | 66911.4286 | 8577.1429 | 21442.8571 | 0 | 220852.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-03 | 1211468.1297 |  |  | 490817.0931 | 131649.9267 | 250173.41 | 51102 | 287725.7 | 37983.3333 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 40131.6667 | 0 | 0 | 28427.6 | 490817.0931 | 0 | 11067.4267 | 67352.5 | 8645 | 21612.5 | 0 | 221745.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-04 | 1215773.8468 |  |  | 492676.1911 | 132372.5457 | 251066.6957 | 51102 | 288556.4143 | 38292.8571 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 40652.8571 | 0 | 0 | 28427.6 | 492676.1911 | 0 | 11111.4743 | 67793.5714 | 8712.8571 | 21782.1429 | 0 | 222639.0957 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-05 | 1220079.5638 |  |  | 494535.289 | 133095.1648 | 251959.9814 | 51102 | 289387.1286 | 38602.381 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 41174.0476 | 0 | 0 | 28427.6 | 494535.289 | 0 | 11155.5219 | 68234.6429 | 8780.7143 | 21951.7857 | 0 | 223532.3814 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-06 | 1224385.2808 |  |  | 496394.387 | 133817.7838 | 252853.2671 | 51102 | 290217.8429 | 38911.9048 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 41695.2381 | 0 | 0 | 28427.6 | 496394.387 | 0 | 11199.5695 | 68675.7143 | 8848.5714 | 22121.4286 | 0 | 224425.6671 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-07 | 1228690.9979 |  |  | 498253.485 | 134540.4029 | 253746.5529 | 51102 | 291048.5571 | 39221.4286 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 42216.4286 | 0 | 0 | 28427.6 | 498253.485 | 0 | 11243.6171 | 69116.7857 | 8916.4286 | 22291.0714 | 0 | 225318.9529 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-08 | 1232996.7149 |  |  | 500112.583 | 135263.0219 | 254639.8386 | 51102 | 291879.2714 | 39530.9524 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 42737.619 | 0 | 0 | 28427.6 | 500112.583 | 0 | 11287.6648 | 69557.8571 | 8984.2857 | 22460.7143 | 0 | 226212.2386 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-09 | 1237302.4319 |  |  | 501971.681 | 135985.641 | 255533.1243 | 51102 | 292709.9857 | 39840.4762 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43258.8095 | 0 | 0 | 28427.6 | 501971.681 | 0 | 11331.7124 | 69998.9286 | 9052.1429 | 22630.3571 | 0 | 227105.5243 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-10 | 1241608.149 |  |  | 503830.779 | 136708.26 | 256426.41 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 503830.779 | 0 | 11375.76 | 70440 | 9120 | 22800 | 0 | 227998.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-11 | 1243591.5753 |  |  | 505376.4711 | 137091.8389 | 256480.5653 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 505376.4711 | 0 | 11389.8653 | 70680.1579 | 9156.9474 | 22892.3684 | 0 | 228052.9653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-12 | 1245575.0017 |  |  | 506922.1633 | 137475.4179 | 256534.7205 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 506922.1633 | 0 | 11403.9705 | 70920.3158 | 9193.8947 | 22984.7368 | 0 | 228107.1205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-13 | 1247558.4281 |  |  | 508467.8555 | 137858.9968 | 256588.8758 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 508467.8555 | 0 | 11418.0758 | 71160.4737 | 9230.8421 | 23077.1053 | 0 | 228161.2758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-14 | 1249541.8545 |  |  | 510013.5477 | 138242.5758 | 256643.0311 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 510013.5477 | 0 | 11432.1811 | 71400.6316 | 9267.7895 | 23169.4737 | 0 | 228215.4311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-15 | 1251525.2809 |  |  | 511559.2399 | 138626.1547 | 256697.1863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 511559.2399 | 0 | 11446.2863 | 71640.7895 | 9304.7368 | 23261.8421 | 0 | 228269.5863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-16 | 1253508.7073 |  |  | 513104.932 | 139009.7337 | 256751.3416 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 513104.932 | 0 | 11460.3916 | 71880.9474 | 9341.6842 | 23354.2105 | 0 | 228323.7416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-17 | 1255492.1337 |  |  | 514650.6242 | 139393.3126 | 256805.4968 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 514650.6242 | 0 | 11474.4968 | 72121.1053 | 9378.6316 | 23446.5789 | 0 | 228377.8968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-18 | 1257475.5601 |  |  | 516196.3164 | 139776.8916 | 256859.6521 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 516196.3164 | 0 | 11488.6021 | 72361.2632 | 9415.5789 | 23538.9474 | 0 | 228432.0521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-19 | 1259458.9865 |  |  | 517742.0086 | 140160.4705 | 256913.8074 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 517742.0086 | 0 | 11502.7074 | 72601.4211 | 9452.5263 | 23631.3158 | 0 | 228486.2074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-20 | 1261442.4129 |  |  | 519287.7008 | 140544.0495 | 256967.9626 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 519287.7008 | 0 | 11516.8126 | 72841.5789 | 9489.4737 | 23723.6842 | 0 | 228540.3626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-21 | 1263425.8393 |  |  | 520833.393 | 140927.6284 | 257022.1179 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 520833.393 | 0 | 11530.9179 | 73081.7368 | 9526.4211 | 23816.0526 | 0 | 228594.5179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-22 | 1265409.2657 |  |  | 522379.0851 | 141311.2074 | 257076.2732 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 522379.0851 | 0 | 11545.0232 | 73321.8947 | 9563.3684 | 23908.4211 | 0 | 228648.6732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-23 | 1267392.6921 |  |  | 523924.7773 | 141694.7863 | 257130.4284 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 523924.7773 | 0 | 11559.1284 | 73562.0526 | 9600.3158 | 24000.7895 | 0 | 228702.8284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-24 | 1269376.1184 |  |  | 525470.4695 | 142078.3653 | 257184.5837 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 525470.4695 | 0 | 11573.2337 | 73802.2105 | 9637.2632 | 24093.1579 | 0 | 228756.9837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-25 | 1271359.5448 |  |  | 527016.1617 | 142461.9442 | 257238.7389 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 527016.1617 | 0 | 11587.3389 | 74042.3684 | 9674.2105 | 24185.5263 | 0 | 228811.1389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-26 | 1273342.9712 |  |  | 528561.8539 | 142845.5232 | 257292.8942 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 528561.8539 | 0 | 11601.4442 | 74282.5263 | 9711.1579 | 24277.8947 | 0 | 228865.2942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-27 | 1275326.3976 |  |  | 530107.546 | 143229.1021 | 257347.0495 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 530107.546 | 0 | 11615.5495 | 74522.6842 | 9748.1053 | 24370.2632 | 0 | 228919.4495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-28 | 1277309.824 |  |  | 531653.2382 | 143612.6811 | 257401.2047 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 531653.2382 | 0 | 11629.6547 | 74762.8421 | 9785.0526 | 24462.6316 | 0 | 228973.6047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-01 | 1279293.2504 |  |  | 533198.9304 | 143996.26 | 257455.36 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 533198.9304 | 0 | 11643.76 | 75003 | 9822 | 24555 | 0 | 229027.76 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-02 | 1281276.6768 |  |  | 534744.6226 | 144379.8389 | 257509.5153 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 534744.6226 | 0 | 11657.8653 | 75243.1579 | 9858.9474 | 24647.3684 | 0 | 229081.9153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-03 | 1283260.1032 |  |  | 536290.3148 | 144763.4179 | 257563.6705 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 536290.3148 | 0 | 11671.9705 | 75483.3158 | 9895.8947 | 24739.7368 | 0 | 229136.0705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-04 | 1285243.5296 |  |  | 537836.007 | 145146.9968 | 257617.8258 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 537836.007 | 0 | 11686.0758 | 75723.4737 | 9932.8421 | 24832.1053 | 0 | 229190.2258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-05 | 1287226.956 |  |  | 539381.6991 | 145530.5758 | 257671.9811 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 539381.6991 | 0 | 11700.1811 | 75963.6316 | 9969.7895 | 24924.4737 | 0 | 229244.3811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-06 | 1289210.3824 |  |  | 540927.3913 | 145914.1547 | 257726.1363 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 540927.3913 | 0 | 11714.2863 | 76203.7895 | 10006.7368 | 25016.8421 | 0 | 229298.5363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-07 | 1291193.8088 |  |  | 542473.0835 | 146297.7337 | 257780.2916 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 542473.0835 | 0 | 11728.3916 | 76443.9474 | 10043.6842 | 25109.2105 | 0 | 229352.6916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-08 | 1293177.2352 |  |  | 544018.7757 | 146681.3126 | 257834.4468 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 544018.7757 | 0 | 11742.4968 | 76684.1053 | 10080.6316 | 25201.5789 | 0 | 229406.8468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-09 | 1295160.6615 |  |  | 545564.4679 | 147064.8916 | 257888.6021 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 545564.4679 | 0 | 11756.6021 | 76924.2632 | 10117.5789 | 25293.9474 | 0 | 229461.0021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-10 | 1297144.0879 |  |  | 547110.16 | 147448.4705 | 257942.7574 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 547110.16 | 0 | 11770.7074 | 77164.4211 | 10154.5263 | 25386.3158 | 0 | 229515.1574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-11 | 1299127.5143 |  |  | 548655.8522 | 147832.0495 | 257996.9126 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 548655.8522 | 0 | 11784.8126 | 77404.5789 | 10191.4737 | 25478.6842 | 0 | 229569.3126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-12 | 1301110.9407 |  |  | 550201.5444 | 148215.6284 | 258051.0679 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 550201.5444 | 0 | 11798.9179 | 77644.7368 | 10228.4211 | 25571.0526 | 0 | 229623.4679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-13 | 1303094.3671 |  |  | 551747.2366 | 148599.2074 | 258105.2232 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 551747.2366 | 0 | 11813.0232 | 77884.8947 | 10265.3684 | 25663.4211 | 0 | 229677.6232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-14 | 1305077.7935 |  |  | 553292.9288 | 148982.7863 | 258159.3784 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 553292.9288 | 0 | 11827.1284 | 78125.0526 | 10302.3158 | 25755.7895 | 0 | 229731.7784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-15 | 1307061.2199 |  |  | 554838.621 | 149366.3653 | 258213.5337 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 554838.621 | 0 | 11841.2337 | 78365.2105 | 10339.2632 | 25848.1579 | 0 | 229785.9337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-16 | 1309044.6463 |  |  | 556384.3131 | 149749.9442 | 258267.6889 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 556384.3131 | 0 | 11855.3389 | 78605.3684 | 10376.2105 | 25940.5263 | 0 | 229840.0889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-17 | 1311028.0727 |  |  | 557930.0053 | 150133.5232 | 258321.8442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 557930.0053 | 0 | 11869.4442 | 78845.5263 | 10413.1579 | 26032.8947 | 0 | 229894.2442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-18 | 1313011.4991 |  |  | 559475.6975 | 150517.1021 | 258375.9995 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 559475.6975 | 0 | 11883.5495 | 79085.6842 | 10450.1053 | 26125.2632 | 0 | 229948.3995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-19 | 1314994.9255 |  |  | 561021.3897 | 150900.6811 | 258430.1547 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 561021.3897 | 0 | 11897.6547 | 79325.8421 | 10487.0526 | 26217.6316 | 0 | 230002.5547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-20 | 1316978.3519 |  |  | 562567.0819 | 151284.26 | 258484.31 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 562567.0819 | 0 | 11911.76 | 79566 | 10524 | 26310 | 0 | 230056.71 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-21 | 1318961.7783 |  |  | 564112.774 | 151667.8389 | 258538.4653 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 564112.774 | 0 | 11925.8653 | 79806.1579 | 10560.9474 | 26402.3684 | 0 | 230110.8653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-22 | 1320945.2046 |  |  | 565658.4662 | 152051.4179 | 258592.6205 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 565658.4662 | 0 | 11939.9705 | 80046.3158 | 10597.8947 | 26494.7368 | 0 | 230165.0205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-23 | 1322928.631 |  |  | 567204.1584 | 152434.9968 | 258646.7758 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 567204.1584 | 0 | 11954.0758 | 80286.4737 | 10634.8421 | 26587.1053 | 0 | 230219.1758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-24 | 1324912.0574 |  |  | 568749.8506 | 152818.5758 | 258700.9311 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 568749.8506 | 0 | 11968.1811 | 80526.6316 | 10671.7895 | 26679.4737 | 0 | 230273.3311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-25 | 1326895.4838 |  |  | 570295.5428 | 153202.1547 | 258755.0863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 570295.5428 | 0 | 11982.2863 | 80766.7895 | 10708.7368 | 26771.8421 | 0 | 230327.4863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-26 | 1328878.9102 |  |  | 571841.235 | 153585.7337 | 258809.2416 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 571841.235 | 0 | 11996.3916 | 81006.9474 | 10745.6842 | 26864.2105 | 0 | 230381.6416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-27 | 1330862.3366 |  |  | 573386.9271 | 153969.3126 | 258863.3968 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 573386.9271 | 0 | 12010.4968 | 81247.1053 | 10782.6316 | 26956.5789 | 0 | 230435.7968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-28 | 1332845.763 |  |  | 574932.6193 | 154352.8916 | 258917.5521 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 574932.6193 | 0 | 12024.6021 | 81487.2632 | 10819.5789 | 27048.9474 | 0 | 230489.9521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-29 | 1334829.1894 |  |  | 576478.3115 | 154736.4705 | 258971.7074 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 576478.3115 | 0 | 12038.7074 | 81727.4211 | 10856.5263 | 27141.3158 | 0 | 230544.1074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-30 | 1336812.6158 |  |  | 578024.0037 | 155120.0495 | 259025.8626 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 578024.0037 | 0 | 12052.8126 | 81967.5789 | 10893.4737 | 27233.6842 | 0 | 230598.2626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-31 | 1338796.0422 |  |  | 579569.6959 | 155503.6284 | 259080.0179 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 579569.6959 | 0 | 12066.9179 | 82207.7368 | 10930.4211 | 27326.0526 | 0 | 230652.4179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-01 | 1340779.4686 |  |  | 581115.388 | 155887.2074 | 259134.1732 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 581115.388 | 0 | 12081.0232 | 82447.8947 | 10967.3684 | 27418.4211 | 0 | 230706.5732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-02 | 1342762.895 |  |  | 582661.0802 | 156270.7863 | 259188.3284 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 582661.0802 | 0 | 12095.1284 | 82688.0526 | 11004.3158 | 27510.7895 | 0 | 230760.7284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-03 | 1344746.3214 |  |  | 584206.7724 | 156654.3653 | 259242.4837 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 584206.7724 | 0 | 12109.2337 | 82928.2105 | 11041.2632 | 27603.1579 | 0 | 230814.8837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-04 | 1346729.7477 |  |  | 585752.4646 | 157037.9442 | 259296.6389 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 585752.4646 | 0 | 12123.3389 | 83168.3684 | 11078.2105 | 27695.5263 | 0 | 230869.0389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-05 | 1348713.1741 |  |  | 587298.1568 | 157421.5232 | 259350.7942 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 587298.1568 | 0 | 12137.4442 | 83408.5263 | 11115.1579 | 27787.8947 | 0 | 230923.1942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-06 | 1350696.6005 |  |  | 588843.849 | 157805.1021 | 259404.9495 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 588843.849 | 0 | 12151.5495 | 83648.6842 | 11152.1053 | 27880.2632 | 0 | 230977.3495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-07 | 1352680.0269 |  |  | 590389.5411 | 158188.6811 | 259459.1047 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 590389.5411 | 0 | 12165.6547 | 83888.8421 | 11189.0526 | 27972.6316 | 0 | 231031.5047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-08 | 1354663.4533 |  |  | 591935.2333 | 158572.26 | 259513.26 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 591935.2333 | 0 | 12179.76 | 84129 | 11226 | 28065 | 0 | 231085.66 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-09 | 1356646.8797 |  |  | 593480.9255 | 158955.8389 | 259567.4153 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 593480.9255 | 0 | 12193.8653 | 84369.1579 | 11262.9474 | 28157.3684 | 0 | 231139.8153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-10 | 1358630.3061 |  |  | 595026.6177 | 159339.4179 | 259621.5705 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 595026.6177 | 0 | 12207.9705 | 84609.3158 | 11299.8947 | 28249.7368 | 0 | 231193.9705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-11 | 1360613.7325 |  |  | 596572.3099 | 159722.9968 | 259675.7258 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 596572.3099 | 0 | 12222.0758 | 84849.4737 | 11336.8421 | 28342.1053 | 0 | 231248.1258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-12 | 1362597.1589 |  |  | 598118.002 | 160106.5758 | 259729.8811 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 598118.002 | 0 | 12236.1811 | 85089.6316 | 11373.7895 | 28434.4737 | 0 | 231302.2811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-13 | 1364580.5853 |  |  | 599663.6942 | 160490.1547 | 259784.0363 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 599663.6942 | 0 | 12250.2863 | 85329.7895 | 11410.7368 | 28526.8421 | 0 | 231356.4363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-14 | 1366564.0117 |  |  | 601209.3864 | 160873.7337 | 259838.1916 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 601209.3864 | 0 | 12264.3916 | 85569.9474 | 11447.6842 | 28619.2105 | 0 | 231410.5916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-15 | 1368547.4381 |  |  | 602755.0786 | 161257.3126 | 259892.3468 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 602755.0786 | 0 | 12278.4968 | 85810.1053 | 11484.6316 | 28711.5789 | 0 | 231464.7468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-16 | 1370530.8645 |  |  | 604300.7708 | 161640.8916 | 259946.5021 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 604300.7708 | 0 | 12292.6021 | 86050.2632 | 11521.5789 | 28803.9474 | 0 | 231518.9021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-17 | 1372514.2908 |  |  | 605846.463 | 162024.4705 | 260000.6574 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 605846.463 | 0 | 12306.7074 | 86290.4211 | 11558.5263 | 28896.3158 | 0 | 231573.0574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-18 | 1374497.7172 |  |  | 607392.1551 | 162408.0495 | 260054.8126 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 607392.1551 | 0 | 12320.8126 | 86530.5789 | 11595.4737 | 28988.6842 | 0 | 231627.2126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-19 | 1376481.1436 |  |  | 608937.8473 | 162791.6284 | 260108.9679 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 608937.8473 | 0 | 12334.9179 | 86770.7368 | 11632.4211 | 29081.0526 | 0 | 231681.3679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-20 | 1378464.57 |  |  | 610483.5395 | 163175.2074 | 260163.1232 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 610483.5395 | 0 | 12349.0232 | 87010.8947 | 11669.3684 | 29173.4211 | 0 | 231735.5232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-21 | 1380447.9964 |  |  | 612029.2317 | 163558.7863 | 260217.2784 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 612029.2317 | 0 | 12363.1284 | 87251.0526 | 11706.3158 | 29265.7895 | 0 | 231789.6784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-22 | 1382431.4228 |  |  | 613574.9239 | 163942.3653 | 260271.4337 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 613574.9239 | 0 | 12377.2337 | 87491.2105 | 11743.2632 | 29358.1579 | 0 | 231843.8337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-23 | 1384414.8492 |  |  | 615120.616 | 164325.9442 | 260325.5889 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 615120.616 | 0 | 12391.3389 | 87731.3684 | 11780.2105 | 29450.5263 | 0 | 231897.9889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-24 | 1386398.2756 |  |  | 616666.3082 | 164709.5232 | 260379.7442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 616666.3082 | 0 | 12405.4442 | 87971.5263 | 11817.1579 | 29542.8947 | 0 | 231952.1442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-25 | 1388381.702 |  |  | 618212.0004 | 165093.1021 | 260433.8995 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 618212.0004 | 0 | 12419.5495 | 88211.6842 | 11854.1053 | 29635.2632 | 0 | 232006.2995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-26 | 1390365.1284 |  |  | 619757.6926 | 165476.6811 | 260488.0547 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 619757.6926 | 0 | 12433.6547 | 88451.8421 | 11891.0526 | 29727.6316 | 0 | 232060.4547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-27 | 1392348.5548 |  |  | 621303.3848 | 165860.26 | 260542.21 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 621303.3848 | 0 | 12447.76 | 88692 | 11928 | 29820 | 0 | 232114.61 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-28 | 1394331.9812 |  |  | 622849.077 | 166243.8389 | 260596.3653 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 622849.077 | 0 | 12461.8653 | 88932.1579 | 11964.9474 | 29912.3684 | 0 | 232168.7653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-29 | 1396315.4076 |  |  | 624394.7691 | 166627.4179 | 260650.5205 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 624394.7691 | 0 | 12475.9705 | 89172.3158 | 12001.8947 | 30004.7368 | 0 | 232222.9205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-30 | 1398298.8339 |  |  | 625940.4613 | 167010.9968 | 260704.6758 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 625940.4613 | 0 | 12490.0758 | 89412.4737 | 12038.8421 | 30097.1053 | 0 | 232277.0758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-01 | 1400282.2603 |  |  | 627486.1535 | 167394.5758 | 260758.8311 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 627486.1535 | 0 | 12504.1811 | 89652.6316 | 12075.7895 | 30189.4737 | 0 | 232331.2311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-02 | 1402265.6867 |  |  | 629031.8457 | 167778.1547 | 260812.9863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 629031.8457 | 0 | 12518.2863 | 89892.7895 | 12112.7368 | 30281.8421 | 0 | 232385.3863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-03 | 1404249.1131 |  |  | 630577.5379 | 168161.7337 | 260867.1416 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 630577.5379 | 0 | 12532.3916 | 90132.9474 | 12149.6842 | 30374.2105 | 0 | 232439.5416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-04 | 1406232.5395 |  |  | 632123.23 | 168545.3126 | 260921.2968 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 632123.23 | 0 | 12546.4968 | 90373.1053 | 12186.6316 | 30466.5789 | 0 | 232493.6968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-05 | 1408215.9659 |  |  | 633668.9222 | 168928.8916 | 260975.4521 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 633668.9222 | 0 | 12560.6021 | 90613.2632 | 12223.5789 | 30558.9474 | 0 | 232547.8521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-06 | 1410199.3923 |  |  | 635214.6144 | 169312.4705 | 261029.6074 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 635214.6144 | 0 | 12574.7074 | 90853.4211 | 12260.5263 | 30651.3158 | 0 | 232602.0074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-07 | 1412182.8187 |  |  | 636760.3066 | 169696.0495 | 261083.7626 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 636760.3066 | 0 | 12588.8126 | 91093.5789 | 12297.4737 | 30743.6842 | 0 | 232656.1626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-08 | 1414166.2451 |  |  | 638305.9988 | 170079.6284 | 261137.9179 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 638305.9988 | 0 | 12602.9179 | 91333.7368 | 12334.4211 | 30836.0526 | 0 | 232710.3179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-09 | 1416149.6715 |  |  | 639851.691 | 170463.2074 | 261192.0732 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 639851.691 | 0 | 12617.0232 | 91573.8947 | 12371.3684 | 30928.4211 | 0 | 232764.4732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-10 | 1418133.0979 |  |  | 641397.3831 | 170846.7863 | 261246.2284 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 641397.3831 | 0 | 12631.1284 | 91814.0526 | 12408.3158 | 31020.7895 | 0 | 232818.6284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-11 | 1420116.5243 |  |  | 642943.0753 | 171230.3653 | 261300.3837 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 642943.0753 | 0 | 12645.2337 | 92054.2105 | 12445.2632 | 31113.1579 | 0 | 232872.7837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-12 | 1422099.9507 |  |  | 644488.7675 | 171613.9442 | 261354.5389 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 644488.7675 | 0 | 12659.3389 | 92294.3684 | 12482.2105 | 31205.5263 | 0 | 232926.9389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-13 | 1424083.377 |  |  | 646034.4597 | 171997.5232 | 261408.6942 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 646034.4597 | 0 | 12673.4442 | 92534.5263 | 12519.1579 | 31297.8947 | 0 | 232981.0942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-14 | 1426066.8034 |  |  | 647580.1519 | 172381.1021 | 261462.8495 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 647580.1519 | 0 | 12687.5495 | 92774.6842 | 12556.1053 | 31390.2632 | 0 | 233035.2495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-15 | 1428050.2298 |  |  | 649125.844 | 172764.6811 | 261517.0047 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 649125.844 | 0 | 12701.6547 | 93014.8421 | 12593.0526 | 31482.6316 | 0 | 233089.4047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-16 | 1430033.6562 |  |  | 650671.5362 | 173148.26 | 261571.16 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 650671.5362 | 0 | 12715.76 | 93255 | 12630 | 31575 | 0 | 233143.56 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-17 | 1432017.0826 |  |  | 652217.2284 | 173531.8389 | 261625.3153 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 652217.2284 | 0 | 12729.8653 | 93495.1579 | 12666.9474 | 31667.3684 | 0 | 233197.7153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-18 | 1434000.509 |  |  | 653762.9206 | 173915.4179 | 261679.4705 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 653762.9206 | 0 | 12743.9705 | 93735.3158 | 12703.8947 | 31759.7368 | 0 | 233251.8705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-19 | 1435983.9354 |  |  | 655308.6128 | 174298.9968 | 261733.6258 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 655308.6128 | 0 | 12758.0758 | 93975.4737 | 12740.8421 | 31852.1053 | 0 | 233306.0258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-20 | 1437967.3618 |  |  | 656854.305 | 174682.5758 | 261787.7811 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 656854.305 | 0 | 12772.1811 | 94215.6316 | 12777.7895 | 31944.4737 | 0 | 233360.1811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-21 | 1439950.7882 |  |  | 658399.9971 | 175066.1547 | 261841.9363 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 658399.9971 | 0 | 12786.2863 | 94455.7895 | 12814.7368 | 32036.8421 | 0 | 233414.3363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-22 | 1441934.2146 |  |  | 659945.6893 | 175449.7337 | 261896.0916 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 659945.6893 | 0 | 12800.3916 | 94695.9474 | 12851.6842 | 32129.2105 | 0 | 233468.4916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-23 | 1443917.641 |  |  | 661491.3815 | 175833.3126 | 261950.2468 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 661491.3815 | 0 | 12814.4968 | 94936.1053 | 12888.6316 | 32221.5789 | 0 | 233522.6468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-24 | 1445901.0674 |  |  | 663037.0737 | 176216.8916 | 262004.4021 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 663037.0737 | 0 | 12828.6021 | 95176.2632 | 12925.5789 | 32313.9474 | 0 | 233576.8021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-25 | 1447884.4938 |  |  | 664582.7659 | 176600.4705 | 262058.5574 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 664582.7659 | 0 | 12842.7074 | 95416.4211 | 12962.5263 | 32406.3158 | 0 | 233630.9574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-26 | 1449867.9201 |  |  | 666128.458 | 176984.0495 | 262112.7126 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 666128.458 | 0 | 12856.8126 | 95656.5789 | 12999.4737 | 32498.6842 | 0 | 233685.1126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-27 | 1451851.3465 |  |  | 667674.1502 | 177367.6284 | 262166.8679 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 667674.1502 | 0 | 12870.9179 | 95896.7368 | 13036.4211 | 32591.0526 | 0 | 233739.2679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-28 | 1453834.7729 |  |  | 669219.8424 | 177751.2074 | 262221.0232 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 669219.8424 | 0 | 12885.0232 | 96136.8947 | 13073.3684 | 32683.4211 | 0 | 233793.4232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-29 | 1455818.1993 |  |  | 670765.5346 | 178134.7863 | 262275.1784 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 670765.5346 | 0 | 12899.1284 | 96377.0526 | 13110.3158 | 32775.7895 | 0 | 233847.5784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-30 | 1457801.6257 |  |  | 672311.2268 | 178518.3653 | 262329.3337 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 672311.2268 | 0 | 12913.2337 | 96617.2105 | 13147.2632 | 32868.1579 | 0 | 233901.7337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-31 | 1459785.0521 |  |  | 673856.919 | 178901.9442 | 262383.4889 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 673856.919 | 0 | 12927.3389 | 96857.3684 | 13184.2105 | 32960.5263 | 0 | 233955.8889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-01 | 1461768.4785 |  |  | 675402.6111 | 179285.5232 | 262437.6442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 675402.6111 | 0 | 12941.4442 | 97097.5263 | 13221.1579 | 33052.8947 | 0 | 234010.0442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-02 | 1463751.9049 |  |  | 676948.3033 | 179669.1021 | 262491.7995 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 676948.3033 | 0 | 12955.5495 | 97337.6842 | 13258.1053 | 33145.2632 | 0 | 234064.1995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-03 | 1465735.3313 |  |  | 678493.9955 | 180052.6811 | 262545.9547 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 678493.9955 | 0 | 12969.6547 | 97577.8421 | 13295.0526 | 33237.6316 | 0 | 234118.3547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-04 | 1467718.7577 |  |  | 680039.6877 | 180436.26 | 262600.11 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 680039.6877 | 0 | 12983.76 | 97818 | 13332 | 33330 | 0 | 234172.51 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-05 | 1469702.1841 |  |  | 681585.3799 | 180819.8389 | 262654.2653 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 681585.3799 | 0 | 12997.8653 | 98058.1579 | 13368.9474 | 33422.3684 | 0 | 234226.6653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-06 | 1471685.6105 |  |  | 683131.072 | 181203.4179 | 262708.4205 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 683131.072 | 0 | 13011.9705 | 98298.3158 | 13405.8947 | 33514.7368 | 0 | 234280.8205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-07 | 1473669.0369 |  |  | 684676.7642 | 181586.9968 | 262762.5758 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 684676.7642 | 0 | 13026.0758 | 98538.4737 | 13442.8421 | 33607.1053 | 0 | 234334.9758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-08 | 1475652.4632 |  |  | 686222.4564 | 181970.5758 | 262816.7311 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 686222.4564 | 0 | 13040.1811 | 98778.6316 | 13479.7895 | 33699.4737 | 0 | 234389.1311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-09 | 1477635.8896 |  |  | 687768.1486 | 182354.1547 | 262870.8863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 687768.1486 | 0 | 13054.2863 | 99018.7895 | 13516.7368 | 33791.8421 | 0 | 234443.2863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-10 | 1479619.316 |  |  | 689313.8408 | 182737.7337 | 262925.0416 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 689313.8408 | 0 | 13068.3916 | 99258.9474 | 13553.6842 | 33884.2105 | 0 | 234497.4416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-11 | 1481602.7424 |  |  | 690859.533 | 183121.3126 | 262979.1968 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 690859.533 | 0 | 13082.4968 | 99499.1053 | 13590.6316 | 33976.5789 | 0 | 234551.5968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-12 | 1483586.1688 |  |  | 692405.2251 | 183504.8916 | 263033.3521 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 692405.2251 | 0 | 13096.6021 | 99739.2632 | 13627.5789 | 34068.9474 | 0 | 234605.7521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-13 | 1485569.5952 |  |  | 693950.9173 | 183888.4705 | 263087.5074 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 693950.9173 | 0 | 13110.7074 | 99979.4211 | 13664.5263 | 34161.3158 | 0 | 234659.9074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-14 | 1487553.0216 |  |  | 695496.6095 | 184272.0495 | 263141.6626 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 695496.6095 | 0 | 13124.8126 | 100219.5789 | 13701.4737 | 34253.6842 | 0 | 234714.0626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-15 | 1489536.448 |  |  | 697042.3017 | 184655.6284 | 263195.8179 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 697042.3017 | 0 | 13138.9179 | 100459.7368 | 13738.4211 | 34346.0526 | 0 | 234768.2179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-16 | 1491519.8744 |  |  | 698587.9939 | 185039.2074 | 263249.9732 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 698587.9939 | 0 | 13153.0232 | 100699.8947 | 13775.3684 | 34438.4211 | 0 | 234822.3732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-17 | 1493503.3008 |  |  | 700133.686 | 185422.7863 | 263304.1284 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 700133.686 | 0 | 13167.1284 | 100940.0526 | 13812.3158 | 34530.7895 | 0 | 234876.5284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-18 | 1495486.7272 |  |  | 701679.3782 | 185806.3653 | 263358.2837 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 701679.3782 | 0 | 13181.2337 | 101180.2105 | 13849.2632 | 34623.1579 | 0 | 234930.6837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-19 | 1497470.1536 |  |  | 703225.0704 | 186189.9442 | 263412.4389 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 703225.0704 | 0 | 13195.3389 | 101420.3684 | 13886.2105 | 34715.5263 | 0 | 234984.8389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-20 | 1499453.58 |  |  | 704770.7626 | 186573.5232 | 263466.5942 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 704770.7626 | 0 | 13209.4442 | 101660.5263 | 13923.1579 | 34807.8947 | 0 | 235038.9942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-21 | 1501437.0063 |  |  | 706316.4548 | 186957.1021 | 263520.7495 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 706316.4548 | 0 | 13223.5495 | 101900.6842 | 13960.1053 | 34900.2632 | 0 | 235093.1495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-22 | 1503420.4327 |  |  | 707862.147 | 187340.6811 | 263574.9047 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 707862.147 | 0 | 13237.6547 | 102140.8421 | 13997.0526 | 34992.6316 | 0 | 235147.3047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-23 | 1505403.8591 |  |  | 709407.8391 | 187724.26 | 263629.06 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 709407.8391 | 0 | 13251.76 | 102381 | 14034 | 35085 | 0 | 235201.46 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-24 | 1507387.2855 |  |  | 710953.5313 | 188107.8389 | 263683.2153 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 710953.5313 | 0 | 13265.8653 | 102621.1579 | 14070.9474 | 35177.3684 | 0 | 235255.6153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-25 | 1509370.7119 |  |  | 712499.2235 | 188491.4179 | 263737.3705 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 712499.2235 | 0 | 13279.9705 | 102861.3158 | 14107.8947 | 35269.7368 | 0 | 235309.7705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-26 | 1511354.1383 |  |  | 714044.9157 | 188874.9968 | 263791.5258 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 714044.9157 | 0 | 13294.0758 | 103101.4737 | 14144.8421 | 35362.1053 | 0 | 235363.9258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-27 | 1513337.5647 |  |  | 715590.6079 | 189258.5758 | 263845.6811 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 715590.6079 | 0 | 13308.1811 | 103341.6316 | 14181.7895 | 35454.4737 | 0 | 235418.0811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-28 | 1515320.9911 |  |  | 717136.3 | 189642.1547 | 263899.8363 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 717136.3 | 0 | 13322.2863 | 103581.7895 | 14218.7368 | 35546.8421 | 0 | 235472.2363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-29 | 1517304.4175 |  |  | 718681.9922 | 190025.7337 | 263953.9916 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 718681.9922 | 0 | 13336.3916 | 103821.9474 | 14255.6842 | 35639.2105 | 0 | 235526.3916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-30 | 1519287.8439 |  |  | 720227.6844 | 190409.3126 | 264008.1468 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 720227.6844 | 0 | 13350.4968 | 104062.1053 | 14292.6316 | 35731.5789 | 0 | 235580.5468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-01 | 1521271.2703 |  |  | 721773.3766 | 190792.8916 | 264062.3021 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 721773.3766 | 0 | 13364.6021 | 104302.2632 | 14329.5789 | 35823.9474 | 0 | 235634.7021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-02 | 1523254.6967 |  |  | 723319.0688 | 191176.4705 | 264116.4574 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 723319.0688 | 0 | 13378.7074 | 104542.4211 | 14366.5263 | 35916.3158 | 0 | 235688.8574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-03 | 1525238.1231 |  |  | 724864.761 | 191560.0495 | 264170.6126 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 724864.761 | 0 | 13392.8126 | 104782.5789 | 14403.4737 | 36008.6842 | 0 | 235743.0126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-04 | 1527221.5494 |  |  | 726410.4531 | 191943.6284 | 264224.7679 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 726410.4531 | 0 | 13406.9179 | 105022.7368 | 14440.4211 | 36101.0526 | 0 | 235797.1679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-05 | 1529204.9758 |  |  | 727956.1453 | 192327.2074 | 264278.9232 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 727956.1453 | 0 | 13421.0232 | 105262.8947 | 14477.3684 | 36193.4211 | 0 | 235851.3232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-06 | 1531188.4022 |  |  | 729501.8375 | 192710.7863 | 264333.0784 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 729501.8375 | 0 | 13435.1284 | 105503.0526 | 14514.3158 | 36285.7895 | 0 | 235905.4784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-07 | 1533171.8286 |  |  | 731047.5297 | 193094.3653 | 264387.2337 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 731047.5297 | 0 | 13449.2337 | 105743.2105 | 14551.2632 | 36378.1579 | 0 | 235959.6337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-08 | 1535155.255 |  |  | 732593.2219 | 193477.9442 | 264441.3889 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 732593.2219 | 0 | 13463.3389 | 105983.3684 | 14588.2105 | 36470.5263 | 0 | 236013.7889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-09 | 1537138.6814 |  |  | 734138.914 | 193861.5232 | 264495.5442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 734138.914 | 0 | 13477.4442 | 106223.5263 | 14625.1579 | 36562.8947 | 0 | 236067.9442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-10 | 1539122.1078 |  |  | 735684.6062 | 194245.1021 | 264549.6995 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 735684.6062 | 0 | 13491.5495 | 106463.6842 | 14662.1053 | 36655.2632 | 0 | 236122.0995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-11 | 1541105.5342 |  |  | 737230.2984 | 194628.6811 | 264603.8547 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 737230.2984 | 0 | 13505.6547 | 106703.8421 | 14699.0526 | 36747.6316 | 0 | 236176.2547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-12 | 1543088.9606 |  |  | 738775.9906 | 195012.26 | 264658.01 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 738775.9906 | 0 | 13519.76 | 106944 | 14736 | 36840 | 0 | 236230.41 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-13 | 1545072.387 |  |  | 740321.6828 | 195395.8389 | 264712.1653 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 740321.6828 | 0 | 13533.8653 | 107184.1579 | 14772.9474 | 36932.3684 | 0 | 236284.5653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-14 | 1547055.8134 |  |  | 741867.375 | 195779.4179 | 264766.3205 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 741867.375 | 0 | 13547.9705 | 107424.3158 | 14809.8947 | 37024.7368 | 0 | 236338.7205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-15 | 1549039.2398 |  |  | 743413.0671 | 196162.9968 | 264820.4758 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 743413.0671 | 0 | 13562.0758 | 107664.4737 | 14846.8421 | 37117.1053 | 0 | 236392.8758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-16 | 1551022.6662 |  |  | 744958.7593 | 196546.5758 | 264874.6311 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 744958.7593 | 0 | 13576.1811 | 107904.6316 | 14883.7895 | 37209.4737 | 0 | 236447.0311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-17 | 1553006.0925 |  |  | 746504.4515 | 196930.1547 | 264928.7863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 746504.4515 | 0 | 13590.2863 | 108144.7895 | 14920.7368 | 37301.8421 | 0 | 236501.1863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-18 | 1554989.5189 |  |  | 748050.1437 | 197313.7337 | 264982.9416 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 748050.1437 | 0 | 13604.3916 | 108384.9474 | 14957.6842 | 37394.2105 | 0 | 236555.3416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-19 | 1556972.9453 |  |  | 749595.8359 | 197697.3126 | 265037.0968 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 749595.8359 | 0 | 13618.4968 | 108625.1053 | 14994.6316 | 37486.5789 | 0 | 236609.4968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-20 | 1558956.3717 |  |  | 751141.528 | 198080.8916 | 265091.2521 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 751141.528 | 0 | 13632.6021 | 108865.2632 | 15031.5789 | 37578.9474 | 0 | 236663.6521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-21 | 1560939.7981 |  |  | 752687.2202 | 198464.4705 | 265145.4074 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 752687.2202 | 0 | 13646.7074 | 109105.4211 | 15068.5263 | 37671.3158 | 0 | 236717.8074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-22 | 1562923.2245 |  |  | 754232.9124 | 198848.0495 | 265199.5626 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 754232.9124 | 0 | 13660.8126 | 109345.5789 | 15105.4737 | 37763.6842 | 0 | 236771.9626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-23 | 1564906.6509 |  |  | 755778.6046 | 199231.6284 | 265253.7179 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 755778.6046 | 0 | 13674.9179 | 109585.7368 | 15142.4211 | 37856.0526 | 0 | 236826.1179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-24 | 1566890.0773 |  |  | 757324.2968 | 199615.2074 | 265307.8732 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 757324.2968 | 0 | 13689.0232 | 109825.8947 | 15179.3684 | 37948.4211 | 0 | 236880.2732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-25 | 1568873.5037 |  |  | 758869.989 | 199998.7863 | 265362.0284 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 758869.989 | 0 | 13703.1284 | 110066.0526 | 15216.3158 | 38040.7895 | 0 | 236934.4284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-26 | 1570856.9301 |  |  | 760415.6811 | 200382.3653 | 265416.1837 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 760415.6811 | 0 | 13717.2337 | 110306.2105 | 15253.2632 | 38133.1579 | 0 | 236988.5837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-27 | 1572840.3565 |  |  | 761961.3733 | 200765.9442 | 265470.3389 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 761961.3733 | 0 | 13731.3389 | 110546.3684 | 15290.2105 | 38225.5263 | 0 | 237042.7389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-28 | 1574823.7829 |  |  | 763507.0655 | 201149.5232 | 265524.4942 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 763507.0655 | 0 | 13745.4442 | 110786.5263 | 15327.1579 | 38317.8947 | 0 | 237096.8942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-29 | 1576807.2093 |  |  | 765052.7577 | 201533.1021 | 265578.6495 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 765052.7577 | 0 | 13759.5495 | 111026.6842 | 15364.1053 | 38410.2632 | 0 | 237151.0495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-30 | 1578790.6356 |  |  | 766598.4499 | 201916.6811 | 265632.8047 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 766598.4499 | 0 | 13773.6547 | 111266.8421 | 15401.0526 | 38502.6316 | 0 | 237205.2047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-31 | 1580774.062 |  |  | 768144.142 | 202300.26 | 265686.96 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 768144.142 | 0 | 13787.76 | 111507 | 15438 | 38595 | 0 | 237259.36 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-01 | 1582757.4884 |  |  | 769689.8342 | 202683.8389 | 265741.1153 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 769689.8342 | 0 | 13801.8653 | 111747.1579 | 15474.9474 | 38687.3684 | 0 | 237313.5153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-02 | 1584740.9148 |  |  | 771235.5264 | 203067.4179 | 265795.2705 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 771235.5264 | 0 | 13815.9705 | 111987.3158 | 15511.8947 | 38779.7368 | 0 | 237367.6705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-03 | 1586724.3412 |  |  | 772781.2186 | 203450.9968 | 265849.4258 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 772781.2186 | 0 | 13830.0758 | 112227.4737 | 15548.8421 | 38872.1053 | 0 | 237421.8258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-04 | 1588707.7676 |  |  | 774326.9108 | 203834.5758 | 265903.5811 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 774326.9108 | 0 | 13844.1811 | 112467.6316 | 15585.7895 | 38964.4737 | 0 | 237475.9811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-05 | 1590691.194 |  |  | 775872.603 | 204218.1547 | 265957.7363 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 775872.603 | 0 | 13858.2863 | 112707.7895 | 15622.7368 | 39056.8421 | 0 | 237530.1363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-06 | 1592674.6204 |  |  | 777418.2951 | 204601.7337 | 266011.8916 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 777418.2951 | 0 | 13872.3916 | 112947.9474 | 15659.6842 | 39149.2105 | 0 | 237584.2916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-07 | 1594658.0468 |  |  | 778963.9873 | 204985.3126 | 266066.0468 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 778963.9873 | 0 | 13886.4968 | 113188.1053 | 15696.6316 | 39241.5789 | 0 | 237638.4468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-08 | 1596641.4732 |  |  | 780509.6795 | 205368.8916 | 266120.2021 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 780509.6795 | 0 | 13900.6021 | 113428.2632 | 15733.5789 | 39333.9474 | 0 | 237692.6021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-09 | 1598624.8996 |  |  | 782055.3717 | 205752.4705 | 266174.3574 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 782055.3717 | 0 | 13914.7074 | 113668.4211 | 15770.5263 | 39426.3158 | 0 | 237746.7574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-10 | 1600608.326 |  |  | 783601.0639 | 206136.0495 | 266228.5126 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 783601.0639 | 0 | 13928.8126 | 113908.5789 | 15807.4737 | 39518.6842 | 0 | 237800.9126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-11 | 1602591.7524 |  |  | 785146.756 | 206519.6284 | 266282.6679 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 785146.756 | 0 | 13942.9179 | 114148.7368 | 15844.4211 | 39611.0526 | 0 | 237855.0679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-12 | 1604575.1787 |  |  | 786692.4482 | 206903.2074 | 266336.8232 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 786692.4482 | 0 | 13957.0232 | 114388.8947 | 15881.3684 | 39703.4211 | 0 | 237909.2232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-13 | 1606558.6051 |  |  | 788238.1404 | 207286.7863 | 266390.9784 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 788238.1404 | 0 | 13971.1284 | 114629.0526 | 15918.3158 | 39795.7895 | 0 | 237963.3784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-14 | 1608542.0315 |  |  | 789783.8326 | 207670.3653 | 266445.1337 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 789783.8326 | 0 | 13985.2337 | 114869.2105 | 15955.2632 | 39888.1579 | 0 | 238017.5337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-15 | 1610525.4579 |  |  | 791329.5248 | 208053.9442 | 266499.2889 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 791329.5248 | 0 | 13999.3389 | 115109.3684 | 15992.2105 | 39980.5263 | 0 | 238071.6889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-16 | 1612508.8843 |  |  | 792875.217 | 208437.5232 | 266553.4442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 792875.217 | 0 | 14013.4442 | 115349.5263 | 16029.1579 | 40072.8947 | 0 | 238125.8442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-17 | 1614492.3107 |  |  | 794420.9091 | 208821.1021 | 266607.5995 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 794420.9091 | 0 | 14027.5495 | 115589.6842 | 16066.1053 | 40165.2632 | 0 | 238179.9995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-18 | 1616475.7371 |  |  | 795966.6013 | 209204.6811 | 266661.7547 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 795966.6013 | 0 | 14041.6547 | 115829.8421 | 16103.0526 | 40257.6316 | 0 | 238234.1547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-19 | 1618459.1635 |  |  | 797512.2935 | 209588.26 | 266715.91 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 797512.2935 | 0 | 14055.76 | 116070 | 16140 | 40350 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-20 | 1620781.2997 |  |  | 798929.1356 | 210111.2012 | 266715.91 | 51484.3529 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 798929.1356 | 0 | 14084.5835 | 116391.1765 | 16189.4118 | 40473.5294 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15632.3529 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-21 | 1623103.436 |  |  | 800345.9778 | 210634.1424 | 266715.91 | 51866.7059 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 800345.9778 | 0 | 14113.4071 | 116712.3529 | 16238.8235 | 40597.0588 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16014.7059 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-22 | 1625425.5722 |  |  | 801762.8199 | 211157.0835 | 266715.91 | 52249.0588 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 801762.8199 | 0 | 14142.2306 | 117033.5294 | 16288.2353 | 40720.5882 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16397.0588 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-23 | 1627747.7085 |  |  | 803179.662 | 211680.0247 | 266715.91 | 52631.4118 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 803179.662 | 0 | 14171.0541 | 117354.7059 | 16337.6471 | 40844.1176 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16779.4118 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-24 | 1630069.8447 |  |  | 804596.5042 | 212202.9659 | 266715.91 | 53013.7647 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 804596.5042 | 0 | 14199.8776 | 117675.8824 | 16387.0588 | 40967.6471 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 17161.7647 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-25 | 1632391.981 |  |  | 806013.3463 | 212725.9071 | 266715.91 | 53396.1176 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 806013.3463 | 0 | 14228.7012 | 117997.0588 | 16436.4706 | 41091.1765 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 17544.1176 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-26 | 1634714.1172 |  |  | 807430.1884 | 213248.8482 | 266715.91 | 53778.4706 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 807430.1884 | 0 | 14257.5247 | 118318.2353 | 16485.8824 | 41214.7059 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 17926.4706 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-27 | 1637036.2535 |  |  | 808847.0305 | 213771.7894 | 266715.91 | 54160.8235 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 808847.0305 | 0 | 14286.3482 | 118639.4118 | 16535.2941 | 41338.2353 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 18308.8235 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-28 | 1639358.3897 |  |  | 810263.8727 | 214294.7306 | 266715.91 | 54543.1765 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 810263.8727 | 0 | 14315.1718 | 118960.5882 | 16584.7059 | 41461.7647 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 18691.1765 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-29 | 1641680.526 |  |  | 811680.7148 | 214817.6718 | 266715.91 | 54925.5294 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 811680.7148 | 0 | 14343.9953 | 119281.7647 | 16634.1176 | 41585.2941 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 19073.5294 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-30 | 1644002.6622 |  |  | 813097.5569 | 215340.6129 | 266715.91 | 55307.8824 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 813097.5569 | 0 | 14372.8188 | 119602.9412 | 16683.5294 | 41708.8235 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 19455.8824 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-31 | 1646324.7985 |  |  | 814514.3991 | 215863.5541 | 266715.91 | 55690.2353 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 814514.3991 | 0 | 14401.6424 | 119924.1176 | 16732.9412 | 41832.3529 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 19838.2353 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-01 | 1648646.9347 |  |  | 815931.2412 | 216386.4953 | 266715.91 | 56072.5882 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 815931.2412 | 0 | 14430.4659 | 120245.2941 | 16782.3529 | 41955.8824 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 20220.5882 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-02 | 1650969.071 |  |  | 817348.0833 | 216909.4365 | 266715.91 | 56454.9412 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 817348.0833 | 0 | 14459.2894 | 120566.4706 | 16831.7647 | 42079.4118 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 20602.9412 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-03 | 1653291.2072 |  |  | 818764.9255 | 217432.3776 | 266715.91 | 56837.2941 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 818764.9255 | 0 | 14488.1129 | 120887.6471 | 16881.1765 | 42202.9412 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 20985.2941 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-04 | 1655613.3435 |  |  | 820181.7676 | 217955.3188 | 266715.91 | 57219.6471 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 820181.7676 | 0 | 14516.9365 | 121208.8235 | 16930.5882 | 42326.4706 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 21367.6471 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-05 | 1657935.4797 |  |  | 821598.6097 | 218478.26 | 266715.91 | 57602 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 821598.6097 | 0 | 14545.76 | 121530 | 16980 | 42450 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 21750 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-06 | 1660257.616 |  |  | 823015.4519 | 219001.2012 | 266715.91 | 57984.3529 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 823015.4519 | 0 | 14574.5835 | 121851.1765 | 17029.4118 | 42573.5294 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 22132.3529 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-07 | 1662579.7522 |  |  | 824432.294 | 219524.1424 | 266715.91 | 58366.7059 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 824432.294 | 0 | 14603.4071 | 122172.3529 | 17078.8235 | 42697.0588 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 22514.7059 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-08 | 1664901.8885 |  |  | 825849.1361 | 220047.0835 | 266715.91 | 58749.0588 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 825849.1361 | 0 | 14632.2306 | 122493.5294 | 17128.2353 | 42820.5882 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 22897.0588 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-09 | 1667224.0247 |  |  | 827265.9783 | 220570.0247 | 266715.91 | 59131.4118 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 827265.9783 | 0 | 14661.0541 | 122814.7059 | 17177.6471 | 42944.1176 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 23279.4118 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-10 | 1669546.161 |  |  | 828682.8204 | 221092.9659 | 266715.91 | 59513.7647 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 828682.8204 | 0 | 14689.8776 | 123135.8824 | 17227.0588 | 43067.6471 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 23661.7647 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-11 | 1671868.2972 |  |  | 830099.6625 | 221615.9071 | 266715.91 | 59896.1176 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 830099.6625 | 0 | 14718.7012 | 123457.0588 | 17276.4706 | 43191.1765 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 24044.1176 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-12 | 1674190.4335 |  |  | 831516.5047 | 222138.8482 | 266715.91 | 60278.4706 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 831516.5047 | 0 | 14747.5247 | 123778.2353 | 17325.8824 | 43314.7059 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 24426.4706 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-13 | 1676512.5697 |  |  | 832933.3468 | 222661.7894 | 266715.91 | 60660.8235 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 832933.3468 | 0 | 14776.3482 | 124099.4118 | 17375.2941 | 43438.2353 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 24808.8235 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-14 | 1678834.706 |  |  | 834350.1889 | 223184.7306 | 266715.91 | 61043.1765 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 834350.1889 | 0 | 14805.1718 | 124420.5882 | 17424.7059 | 43561.7647 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25191.1765 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-15 | 1681156.8422 |  |  | 835767.031 | 223707.6718 | 266715.91 | 61425.5294 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 835767.031 | 0 | 14833.9953 | 124741.7647 | 17474.1176 | 43685.2941 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25573.5294 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-16 | 1683478.9785 |  |  | 837183.8732 | 224230.6129 | 266715.91 | 61807.8824 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 837183.8732 | 0 | 14862.8188 | 125062.9412 | 17523.5294 | 43808.8235 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25955.8824 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-17 | 1685801.1147 |  |  | 838600.7153 | 224753.5541 | 266715.91 | 62190.2353 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 838600.7153 | 0 | 14891.6424 | 125384.1176 | 17572.9412 | 43932.3529 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 26338.2353 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-18 | 1688123.251 |  |  | 840017.5574 | 225276.4953 | 266715.91 | 62572.5882 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 840017.5574 | 0 | 14920.4659 | 125705.2941 | 17622.3529 | 44055.8824 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 26720.5882 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-19 | 1690445.3872 |  |  | 841434.3996 | 225799.4365 | 266715.91 | 62954.9412 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 841434.3996 | 0 | 14949.2894 | 126026.4706 | 17671.7647 | 44179.4118 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27102.9412 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-20 | 1692767.5235 |  |  | 842851.2417 | 226322.3776 | 266715.91 | 63337.2941 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 842851.2417 | 0 | 14978.1129 | 126347.6471 | 17721.1765 | 44302.9412 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27485.2941 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-21 | 1695089.6597 |  |  | 844268.0838 | 226845.3188 | 266715.91 | 63719.6471 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 844268.0838 | 0 | 15006.9365 | 126668.8235 | 17770.5882 | 44426.4706 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27867.6471 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-22 | 1697411.796 |  |  | 845684.926 | 227368.26 | 266715.91 | 64102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 845684.926 | 0 | 15035.76 | 126990 | 17820 | 44550 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 28250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0

## Cost Sum
Date | Planned Total Cost (Cumulative) | Actual Total Cost (Cumulative) | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Planned Total Cost (Daily) | Actual Total Cost (Daily) | Planned Labor (Daily) | Actual Labor (Daily) | Planned Travel&perdiem (Daily) | Actual Travel&perdiem (Daily) | Planned Parts&materials (Daily) | Actual Parts&materials (Daily) | Planned Outsource (Daily) | Actual Outsource (Daily) | Planned Equipment (Daily) | Actual Equipment (Daily)
2025-04-02 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 1914.2857 | 5000 | 1914.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 5000 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
2025-04-04 | 2871.4286 | 5000 | 2871.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 3828.5714 | 5000 | 3828.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 4785.7143 | 5000 | 4785.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 5742.8571 | 6126.6 | 5742.8571 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1126.6 | 957.1429 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 6700 | 7253.2 | 6700 | 2253.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1126.6 | 957.1429 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 7657.1429 | 8379.8 | 7657.1429 | 3379.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1126.6 | 957.1429 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 8614.2857 | 9716.32 | 8614.2857 | 4506.4 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 5000 | 957.1429 | 1336.52 | 957.1429 | 1126.6 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 9571.4286 | 10879.95 | 9571.4286 | 5633 | 0 | 209.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 1163.63 | 957.1429 | 1126.6 | 0 | 0 | 0 | 37.03 | 0 | 0 | 0 | 0
2025-04-12 | 10528.5714 | 10897.95 | 10528.5714 | 5633 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 18 | 957.1429 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 11485.7143 | 10897.95 | 11485.7143 | 5633 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 12442.8571 | 11112.35 | 12442.8571 | 5847.4 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 13400 | 11326.75 | 13400 | 6061.8 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 14357.1429 | 11541.15 | 14357.1429 | 6276.2 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 15314.2857 | 11755.55 | 15314.2857 | 6490.6 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 16271.4286 | 11969.95 | 16271.4286 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 214.4 | 957.1429 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 17228.5714 | 11969.95 | 17228.5714 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 18185.7143 | 11969.95 | 18185.7143 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 19142.8571 | 12352.1 | 19142.8571 | 7087.15 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 20100 | 12734.25 | 20100 | 7469.3 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 21057.1429 | 13116.4 | 21057.1429 | 7851.45 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 22014.2857 | 13498.55 | 22014.2857 | 8233.6 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 22971.4286 | 13880.7 | 22971.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 23928.5714 | 13880.7 | 23928.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 24885.7143 | 13880.7 | 24885.7143 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 25842.8571 | 13880.7 | 25842.8571 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 26800 | 13880.7 | 26800 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 27757.1429 | 13880.7 | 27757.1429 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 28714.2857 | 13880.7 | 28714.2857 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 29671.4286 | 13880.7 | 29671.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 30628.5714 | 13880.7 | 30628.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 31585.7143 | 13880.7 | 31585.7143 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 32542.8571 | 13880.7 | 32542.8571 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 33500 | 13880.7 | 33500 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 34457.1429 | 13880.7 | 34457.1429 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 35414.2857 | 13880.7 | 35414.2857 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 36371.4286 | 13880.7 | 36371.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 37328.5714 | 13880.7 | 37328.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 38285.7143 | 13880.7 | 38285.7143 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 39242.8571 | 13880.7 | 39242.8571 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 40200 | 13880.7 | 40200 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 41157.1429 | 13880.7 | 41157.1429 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 42114.2857 | 13880.7 | 42114.2857 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 43071.4286 | 13880.7 | 43071.4286 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 44028.5714 | 13880.7 | 44028.5714 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 44985.7143 | 14644.31 | 44985.7143 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 763.61 | 957.1429 | 0 | 0 | 0 | 0 | 763.61 | 0 | 0 | 0 | 0
2025-05-19 | 45942.8571 | 14644.31 | 45942.8571 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 46900 | 14644.31 | 46900 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 47857.1429 | 14644.31 | 47857.1429 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 48814.2857 | 14644.31 | 48814.2857 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 49771.4286 | 14823.29 | 49771.4286 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 178.98 | 957.1429 | 0 | 0 | 0 | 0 | 178.98 | 0 | 0 | 0 | 0
2025-05-24 | 50728.5714 | 14823.29 | 50728.5714 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 51685.7143 | 14823.29 | 51685.7143 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 52642.8571 | 14823.29 | 52642.8571 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 53600 | 14823.29 | 53600 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 54557.1429 | 14823.29 | 54557.1429 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 55514.2857 | 14823.29 | 55514.2857 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 56471.4286 | 14823.29 | 56471.4286 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 57428.5714 | 14823.29 | 57428.5714 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 58385.7143 | 14823.29 | 58385.7143 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 59342.8571 | 15252.09 | 59342.8571 | 9044.55 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 428.8 | 957.1429 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 60300 | 15680.89 | 60300 | 9473.35 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 428.8 | 957.1429 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 61257.1429 | 16109.69 | 61257.1429 | 9902.15 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 428.8 | 957.1429 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 62214.2857 | 16538.49 | 62214.2857 | 10330.95 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 428.8 | 957.1429 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 63171.4286 | 16967.29 | 63171.4286 | 10759.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 428.8 | 957.1429 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 64128.5714 | 16967.29 | 64128.5714 | 10759.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 65085.7143 | 16967.29 | 65085.7143 | 10759.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 66042.8571 | 17074.49 | 66042.8571 | 10866.95 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 67000 | 17181.69 | 67000 | 10974.15 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 67957.1429 | 17288.89 | 67957.1429 | 11081.35 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 68914.2857 | 17396.09 | 68914.2857 | 11188.55 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 69871.4286 | 17503.29 | 69871.4286 | 11295.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 70828.5714 | 17503.29 | 70828.5714 | 11295.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 71785.7143 | 17503.29 | 71785.7143 | 11295.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 72742.8571 | 17885.44 | 72742.8571 | 11677.9 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 73700 | 18267.59 | 73700 | 12060.05 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 74657.1429 | 18649.74 | 74657.1429 | 12442.2 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 75614.2857 | 19031.89 | 75614.2857 | 12824.35 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 76571.4286 | 19414.04 | 76571.4286 | 13206.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 382.15 | 957.1429 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 77528.5714 | 19414.04 | 77528.5714 | 13206.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 78485.7143 | 19414.04 | 78485.7143 | 13206.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 79442.8571 | 19521.24 | 79442.8571 | 13313.7 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 80400 | 19628.44 | 80400 | 13420.9 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 957.1429 | 107.2 | 957.1429 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 82643.2477 | 19735.64 | 80520.2088 | 13528.1 | 139.8381 | 227.92 | 713.6371 | 979.62 | 321.9345 | 0 | 947.6292 | 5000 | 2243.2477 | 107.2 | 120.2088 | 107.2 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-06-26 | 84886.4953 | 19842.84 | 80640.4175 | 13635.3 | 279.6761 | 227.92 | 1427.2742 | 979.62 | 643.8691 | 0 | 1895.2584 | 5000 | 2243.2477 | 107.2 | 120.2088 | 107.2 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-06-27 | 87129.743 | 19950.04 | 80760.6263 | 13742.5 | 419.5142 | 227.92 | 2140.9112 | 979.62 | 965.8036 | 0 | 2842.8876 | 5000 | 2243.2477 | 107.2 | 120.2088 | 107.2 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-06-28 | 89372.9907 | 19950.04 | 80880.8351 | 13742.5 | 559.3523 | 227.92 | 2854.5483 | 979.62 | 1287.7382 | 0 | 3790.5169 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-06-29 | 91616.2384 | 19950.04 | 81001.0439 | 13742.5 | 699.1904 | 227.92 | 3568.1854 | 979.62 | 1609.6727 | 0 | 4738.1461 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-06-30 | 93859.486 | 20399.19 | 81121.2526 | 14191.65 | 839.0284 | 227.92 | 4281.8225 | 979.62 | 1931.6072 | 0 | 5685.7753 | 5000 | 2243.2477 | 449.15 | 120.2088 | 449.15 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-01 | 96102.7337 | 20848.34 | 81241.4614 | 14640.8 | 978.8665 | 227.92 | 4995.4596 | 979.62 | 2253.5418 | 0 | 6633.4045 | 5000 | 2243.2477 | 449.15 | 120.2088 | 449.15 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-02 | 98345.9814 | 21297.49 | 81361.6702 | 15089.95 | 1118.7046 | 227.92 | 5709.0966 | 979.62 | 2575.4763 | 0 | 7581.0337 | 5000 | 2243.2477 | 449.15 | 120.2088 | 449.15 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-03 | 100589.2291 | 21746.64 | 81481.8789 | 15539.1 | 1258.5426 | 227.92 | 6422.7337 | 979.62 | 2897.4108 | 0 | 8528.6629 | 5000 | 2243.2477 | 449.15 | 120.2088 | 449.15 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-04 | 102832.4767 | 22195.79 | 81602.0877 | 15988.25 | 1398.3807 | 227.92 | 7136.3708 | 979.62 | 3219.3454 | 0 | 9476.2921 | 5000 | 2243.2477 | 449.15 | 120.2088 | 449.15 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-05 | 105075.7244 | 22195.79 | 81722.2965 | 15988.25 | 1538.2188 | 227.92 | 7850.0079 | 979.62 | 3541.2799 | 0 | 10423.9213 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-06 | 107318.9721 | 22195.79 | 81842.5053 | 15988.25 | 1678.0569 | 227.92 | 8563.6449 | 979.62 | 3863.2145 | 0 | 11371.5506 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-07 | 109562.2198 | 22597.79 | 81962.714 | 16390.25 | 1817.8949 | 227.92 | 9277.282 | 979.62 | 4185.149 | 0 | 12319.1798 | 5000 | 2243.2477 | 402 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-08 | 111805.4674 | 22999.79 | 82082.9228 | 16792.25 | 1957.733 | 227.92 | 9990.9191 | 979.62 | 4507.0835 | 0 | 13266.809 | 5000 | 2243.2477 | 402 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-09 | 114048.7151 | 23401.79 | 82203.1316 | 17194.25 | 2097.5711 | 227.92 | 10704.5562 | 979.62 | 4829.0181 | 0 | 14214.4382 | 5000 | 2243.2477 | 402 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-10 | 116291.9628 | 23803.79 | 82323.3403 | 17596.25 | 2237.4092 | 227.92 | 11418.1933 | 979.62 | 5150.9526 | 0 | 15162.0674 | 5000 | 2243.2477 | 402 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-11 | 118535.2105 | 24205.79 | 82443.5491 | 17998.25 | 2377.2472 | 227.92 | 12131.8303 | 979.62 | 5472.8872 | 0 | 16109.6966 | 5000 | 2243.2477 | 402 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-12 | 120778.4581 | 24205.79 | 82563.7579 | 17998.25 | 2517.0853 | 227.92 | 12845.4674 | 979.62 | 5794.8217 | 0 | 17057.3258 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-13 | 123021.7058 | 24205.79 | 82683.9667 | 17998.25 | 2656.9234 | 227.92 | 13559.1045 | 979.62 | 6116.7562 | 0 | 18004.9551 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-14 | 125264.9535 | 26149.69 | 82804.1754 | 18400.25 | 2796.7614 | 1769.82 | 14272.7416 | 979.62 | 6438.6908 | 0 | 18952.5843 | 5000 | 2243.2477 | 1943.9 | 120.2088 | 402 | 139.8381 | 1541.9 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-15 | 127508.2011 | 26551.69 | 82924.3842 | 18802.25 | 2936.5995 | 1769.82 | 14986.3787 | 979.62 | 6760.6253 | 0 | 19900.2135 | 5000 | 2243.2477 | 402 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-16 | 129751.4488 | 26953.69 | 83044.593 | 19204.25 | 3076.4376 | 1769.82 | 15700.0157 | 979.62 | 7082.5598 | 0 | 20847.8427 | 5000 | 2243.2477 | 402 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-17 | 131994.6965 | 27420.14 | 83164.8017 | 19606.25 | 3216.2757 | 1834.27 | 16413.6528 | 979.62 | 7404.4944 | 0 | 21795.4719 | 5000 | 2243.2477 | 466.45 | 120.2088 | 402 | 139.8381 | 64.45 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-18 | 134237.9442 | 27849.28 | 83285.0105 | 20008.25 | 3356.1137 | 1861.41 | 17127.2899 | 979.62 | 7726.4289 | 0 | 22743.1011 | 5000 | 2243.2477 | 429.14 | 120.2088 | 402 | 139.8381 | 27.14 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-19 | 136481.1918 | 27879.28 | 83405.2193 | 20008.25 | 3495.9518 | 1891.41 | 17840.927 | 979.62 | 8048.3635 | 0 | 23690.7303 | 5000 | 2243.2477 | 30 | 120.2088 | 0 | 139.8381 | 30 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-20 | 138724.4395 | 27879.28 | 83525.4281 | 20008.25 | 3635.7899 | 1891.41 | 18554.564 | 979.62 | 8370.298 | 0 | 24638.3596 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-21 | 140967.6872 | 28281.28 | 83645.6368 | 20410.25 | 3775.6279 | 1891.41 | 19268.2011 | 979.62 | 8692.2325 | 0 | 25585.9888 | 5000 | 2243.2477 | 402 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-22 | 143210.9349 | 29183.28 | 83765.8456 | 20812.25 | 3915.466 | 1891.41 | 19981.8382 | 979.62 | 9014.1671 | 500 | 26533.618 | 5000 | 2243.2477 | 902 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 500 | 947.6292 | 0
2025-07-23 | 145454.1825 | 29585.28 | 83886.0544 | 21214.25 | 4055.3041 | 1891.41 | 20695.4753 | 979.62 | 9336.1016 | 500 | 27481.2472 | 5000 | 2243.2477 | 402 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-24 | 147697.4302 | 29987.28 | 84006.2631 | 21616.25 | 4195.1422 | 1891.41 | 21409.1124 | 979.62 | 9658.0362 | 500 | 28428.8764 | 5000 | 2243.2477 | 402 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-25 | 149940.6779 | 30389.28 | 84126.4719 | 22018.25 | 4334.9802 | 1891.41 | 22122.7494 | 979.62 | 9979.9707 | 500 | 29376.5056 | 5000 | 2243.2477 | 402 | 120.2088 | 402 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-26 | 152183.9256 | 30389.28 | 84246.6807 | 22018.25 | 4474.8183 | 1891.41 | 22836.3865 | 979.62 | 10301.9052 | 500 | 30324.1348 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-27 | 154427.1732 | 30389.28 | 84366.8895 | 22018.25 | 4614.6564 | 1891.41 | 23550.0236 | 979.62 | 10623.8398 | 500 | 31271.764 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-28 | 156670.4209 | 30737.68 | 84487.0982 | 22366.65 | 4754.4944 | 1891.41 | 24263.6607 | 979.62 | 10945.7743 | 500 | 32219.3933 | 5000 | 2243.2477 | 348.4 | 120.2088 | 348.4 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-29 | 158913.6686 | 31086.08 | 84607.307 | 22715.05 | 4894.3325 | 1891.41 | 24977.2978 | 979.62 | 11267.7088 | 500 | 33167.0225 | 5000 | 2243.2477 | 348.4 | 120.2088 | 348.4 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-30 | 161156.9163 | 31434.48 | 84727.5158 | 23063.45 | 5034.1706 | 1891.41 | 25690.9348 | 979.62 | 11589.6434 | 500 | 34114.6517 | 5000 | 2243.2477 | 348.4 | 120.2088 | 348.4 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-07-31 | 163400.1639 | 31782.88 | 84847.7245 | 23411.85 | 5174.0087 | 1891.41 | 26404.5719 | 979.62 | 11911.5779 | 500 | 35062.2809 | 5000 | 2243.2477 | 348.4 | 120.2088 | 348.4 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-01 | 165643.4116 | 32131.28 | 84967.9333 | 23760.25 | 5313.8467 | 1891.41 | 27118.209 | 979.62 | 12233.5125 | 500 | 36009.9101 | 5000 | 2243.2477 | 348.4 | 120.2088 | 348.4 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-02 | 167886.6593 | 32131.28 | 85088.1421 | 23760.25 | 5453.6848 | 1891.41 | 27831.8461 | 979.62 | 12555.447 | 500 | 36957.5393 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-03 | 170129.907 | 32131.28 | 85208.3509 | 23760.25 | 5593.5229 | 1891.41 | 28545.4831 | 979.62 | 12877.3815 | 500 | 37905.1685 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-04 | 172373.1546 | 33768.43 | 85328.5596 | 24028.25 | 5733.361 | 1891.41 | 29259.1202 | 2348.77 | 13199.3161 | 500 | 38852.7978 | 5000 | 2243.2477 | 1637.15 | 120.2088 | 268 | 139.8381 | 0 | 713.6371 | 1369.15 | 321.9345 | 0 | 947.6292 | 0
2025-08-05 | 174616.4023 | 34036.43 | 85448.7684 | 24296.25 | 5873.199 | 1891.41 | 29972.7573 | 2348.77 | 13521.2506 | 500 | 39800.427 | 5000 | 2243.2477 | 268 | 120.2088 | 268 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-06 | 176859.65 | 34304.43 | 85568.9772 | 24564.25 | 6013.0371 | 1891.41 | 30686.3944 | 2348.77 | 13843.1851 | 500 | 40748.0562 | 5000 | 2243.2477 | 268 | 120.2088 | 268 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-07 | 179102.8976 | 35523.3 | 85689.1859 | 24832.25 | 6152.8752 | 1891.41 | 31400.0315 | 3299.64 | 14165.1197 | 500 | 41695.6854 | 5000 | 2243.2477 | 1218.87 | 120.2088 | 268 | 139.8381 | 0 | 713.6371 | 950.87 | 321.9345 | 0 | 947.6292 | 0
2025-08-08 | 181346.1453 | 35791.3 | 85809.3947 | 25100.25 | 6292.7132 | 1891.41 | 32113.6685 | 3299.64 | 14487.0542 | 500 | 42643.3146 | 5000 | 2243.2477 | 268 | 120.2088 | 268 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-09 | 183589.393 | 35791.3 | 85929.6035 | 25100.25 | 6432.5513 | 1891.41 | 32827.3056 | 3299.64 | 14808.9888 | 500 | 43590.9438 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-10 | 185832.6407 | 35791.3 | 86049.8123 | 25100.25 | 6572.3894 | 1891.41 | 33540.9427 | 3299.64 | 15130.9233 | 500 | 44538.573 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-11 | 188075.8883 | 36272.59 | 86170.021 | 25314.65 | 6712.2275 | 1891.41 | 34254.5798 | 3566.53 | 15452.8578 | 500 | 45486.2022 | 5000 | 2243.2477 | 481.29 | 120.2088 | 214.4 | 139.8381 | 0 | 713.6371 | 266.89 | 321.9345 | 0 | 947.6292 | 0
2025-08-12 | 190319.136 | 36486.99 | 86290.2298 | 25529.05 | 6852.0655 | 1891.41 | 34968.2169 | 3566.53 | 15774.7924 | 500 | 46433.8315 | 5000 | 2243.2477 | 214.4 | 120.2088 | 214.4 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-13 | 192562.3837 | 36701.39 | 86410.4386 | 25743.45 | 6991.9036 | 1891.41 | 35681.8539 | 3566.53 | 16096.7269 | 500 | 47381.4607 | 5000 | 2243.2477 | 214.4 | 120.2088 | 214.4 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-14 | 194805.6314 | 36915.79 | 86530.6473 | 25957.85 | 7131.7417 | 1891.41 | 36395.491 | 3566.53 | 16418.6615 | 500 | 48329.0899 | 5000 | 2243.2477 | 214.4 | 120.2088 | 214.4 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-15 | 197048.879 | 37130.19 | 86650.8561 | 26172.25 | 7271.5797 | 1891.41 | 37109.1281 | 3566.53 | 16740.596 | 500 | 49276.7191 | 5000 | 2243.2477 | 214.4 | 120.2088 | 214.4 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-16 | 199292.1267 | 37130.19 | 86771.0649 | 26172.25 | 7411.4178 | 1891.41 | 37822.7652 | 3566.53 | 17062.5305 | 500 | 50224.3483 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-17 | 201535.3744 | 37130.19 | 86891.2736 | 26172.25 | 7551.2559 | 1891.41 | 38536.4022 | 3566.53 | 17384.4651 | 500 | 51171.9775 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-18 | 203778.6221 | 37666.19 | 87011.4824 | 26708.25 | 7691.094 | 1891.41 | 39250.0393 | 3566.53 | 17706.3996 | 500 | 52119.6067 | 5000 | 2243.2477 | 536 | 120.2088 | 536 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-19 | 206021.8697 | 50711.55 | 87131.6912 | 27244.25 | 7830.932 | 1891.41 | 39963.6764 | 16075.89 | 18028.3341 | 500 | 53067.236 | 5000 | 2243.2477 | 13045.36 | 120.2088 | 536 | 139.8381 | 0 | 713.6371 | 12509.36 | 321.9345 | 0 | 947.6292 | 0
2025-08-20 | 208265.1174 | 51386.36 | 87251.9 | 27780.25 | 7970.7701 | 2030.22 | 40677.3135 | 16075.89 | 18350.2687 | 500 | 54014.8652 | 5000 | 2243.2477 | 674.81 | 120.2088 | 536 | 139.8381 | 138.81 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-21 | 210508.3651 | 51922.36 | 87372.1087 | 28316.25 | 8110.6082 | 2030.22 | 41390.9506 | 16075.89 | 18672.2032 | 500 | 54962.4944 | 5000 | 2243.2477 | 536 | 120.2088 | 536 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-22 | 212751.6128 | 52558.36 | 87492.3175 | 28852.25 | 8250.4462 | 2130.22 | 42104.5876 | 16075.89 | 18994.1378 | 500 | 55910.1236 | 5000 | 2243.2477 | 636 | 120.2088 | 536 | 139.8381 | 100 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-23 | 214994.8604 | 52558.36 | 87612.5263 | 28852.25 | 8390.2843 | 2130.22 | 42818.2247 | 16075.89 | 19316.0723 | 500 | 56857.7528 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-24 | 217238.1081 | 52558.36 | 87732.735 | 28852.25 | 8530.1224 | 2130.22 | 43531.8618 | 16075.89 | 19638.0068 | 500 | 57805.382 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-25 | 219481.3558 | 54392.92 | 87852.9438 | 29952.05 | 8669.9605 | 2130.22 | 44245.4989 | 16795.65 | 19959.9414 | 515 | 58753.0112 | 5000 | 2243.2477 | 1834.56 | 120.2088 | 1099.8 | 139.8381 | 0 | 713.6371 | 719.76 | 321.9345 | 15 | 947.6292 | 0
2025-08-26 | 221724.6034 | 58242.72 | 87973.1526 | 31051.85 | 8809.7985 | 2130.22 | 44959.136 | 16795.65 | 20281.8759 | 3265 | 59700.6404 | 5000 | 2243.2477 | 3849.8 | 120.2088 | 1099.8 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 2750 | 947.6292 | 0
2025-08-27 | 223967.8511 | 59342.52 | 88093.3614 | 32151.65 | 8949.6366 | 2130.22 | 45672.773 | 16795.65 | 20603.8105 | 3265 | 60648.2697 | 5000 | 2243.2477 | 1099.8 | 120.2088 | 1099.8 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-28 | 226211.0988 | 60442.32 | 88213.5701 | 33251.45 | 9089.4747 | 2130.22 | 46386.4101 | 16795.65 | 20925.745 | 3265 | 61595.8989 | 5000 | 2243.2477 | 1099.8 | 120.2088 | 1099.8 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-29 | 228454.3465 | 61542.12 | 88333.7789 | 34351.25 | 9229.3128 | 2130.22 | 47100.0472 | 16795.65 | 21247.6795 | 3265 | 62543.5281 | 5000 | 2243.2477 | 1099.8 | 120.2088 | 1099.8 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-30 | 230697.5941 | 61542.12 | 88453.9877 | 34351.25 | 9369.1508 | 2130.22 | 47813.6843 | 16795.65 | 21569.6141 | 3265 | 63491.1573 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-08-31 | 232940.8418 | 61542.12 | 88574.1964 | 34351.25 | 9508.9889 | 2130.22 | 48527.3213 | 16795.65 | 21891.5486 | 3265 | 64438.7865 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-01 | 235184.0895 | 62286.07 | 88694.4052 | 35095.2 | 9648.827 | 2130.22 | 49240.9584 | 16795.65 | 22213.4831 | 3265 | 65386.4157 | 5000 | 2243.2477 | 743.95 | 120.2088 | 743.95 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-02 | 237427.3372 | 66154.82 | 88814.614 | 35839.15 | 9788.665 | 2130.22 | 49954.5955 | 19920.45 | 22535.4177 | 3265 | 66334.0449 | 5000 | 2243.2477 | 3868.75 | 120.2088 | 743.95 | 139.8381 | 0 | 713.6371 | 3124.8 | 321.9345 | 0 | 947.6292 | 0
2025-09-03 | 239670.5848 | 66898.77 | 88934.8228 | 36583.1 | 9928.5031 | 2130.22 | 50668.2326 | 19920.45 | 22857.3522 | 3265 | 67281.6742 | 5000 | 2243.2477 | 743.95 | 120.2088 | 743.95 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-04 | 241913.8325 | 68329.42 | 89055.0315 | 37327.05 | 10068.3412 | 2130.22 | 51381.8697 | 19920.45 | 23179.2868 | 3951.7 | 68229.3034 | 5000 | 2243.2477 | 1430.65 | 120.2088 | 743.95 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 686.7 | 947.6292 | 0
2025-09-05 | 244157.0802 | 69073.37 | 89175.2403 | 38071 | 10208.1793 | 2130.22 | 52095.5067 | 19920.45 | 23501.2213 | 3951.7 | 69176.9326 | 5000 | 2243.2477 | 743.95 | 120.2088 | 743.95 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-06 | 246400.3279 | 69073.37 | 89295.4491 | 38071 | 10348.0173 | 2130.22 | 52809.1438 | 19920.45 | 23823.1558 | 3951.7 | 70124.5618 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-07 | 248643.5755 | 69073.37 | 89415.6578 | 38071 | 10487.8554 | 2130.22 | 53522.7809 | 19920.45 | 24145.0904 | 3951.7 | 71072.191 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-08 | 250886.8232 | 69576.12 | 89535.8666 | 38573.75 | 10627.6935 | 2130.22 | 54236.418 | 19920.45 | 24467.0249 | 3951.7 | 72019.8202 | 5000 | 2243.2477 | 502.75 | 120.2088 | 502.75 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-09 | 253130.0709 | 70721.23 | 89656.0754 | 39076.5 | 10767.5315 | 2130.22 | 54950.0551 | 20562.81 | 24788.9595 | 3951.7 | 72967.4494 | 5000 | 2243.2477 | 1145.11 | 120.2088 | 502.75 | 139.8381 | 0 | 713.6371 | 642.36 | 321.9345 | 0 | 947.6292 | 0
2025-09-10 | 255373.3186 | 71460.84 | 89776.2842 | 39579.25 | 10907.3696 | 2367.08 | 55663.6921 | 20562.81 | 25110.894 | 3951.7 | 73915.0787 | 5000 | 2243.2477 | 739.61 | 120.2088 | 502.75 | 139.8381 | 236.86 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-11 | 257616.5662 | 71963.59 | 89896.4929 | 40082 | 11047.2077 | 2367.08 | 56377.3292 | 20562.81 | 25432.8285 | 3951.7 | 74862.7079 | 5000 | 2243.2477 | 502.75 | 120.2088 | 502.75 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-12 | 259859.8139 | 86692.28 | 90016.7017 | 40584.75 | 11187.0458 | 2478.02 | 57090.9663 | 20562.81 | 25754.7631 | 18066.7 | 75810.3371 | 5000 | 2243.2477 | 14728.69 | 120.2088 | 502.75 | 139.8381 | 110.94 | 713.6371 | 0 | 321.9345 | 14115 | 947.6292 | 0
2025-09-13 | 262103.0616 | 86692.28 | 90136.9105 | 40584.75 | 11326.8838 | 2478.02 | 57804.6034 | 20562.81 | 26076.6976 | 18066.7 | 76757.9663 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-14 | 264346.3092 | 86692.28 | 90257.1192 | 40584.75 | 11466.7219 | 2478.02 | 58518.2404 | 20562.81 | 26398.6321 | 18066.7 | 77705.5955 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-15 | 266589.5569 | 89104.155 | 90377.328 | 42546.625 | 11606.56 | 2928.02 | 59231.8775 | 20562.81 | 26720.5667 | 18066.7 | 78653.2247 | 5000 | 2243.2477 | 2411.875 | 120.2088 | 1961.875 | 139.8381 | 450 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-16 | 268832.8046 | 91066.03 | 90497.5368 | 44508.5 | 11746.398 | 2928.02 | 59945.5146 | 20562.81 | 27042.5012 | 18066.7 | 79600.8539 | 5000 | 2243.2477 | 1961.875 | 120.2088 | 1961.875 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-17 | 271076.0523 | 93027.905 | 90617.7456 | 46470.375 | 11886.2361 | 2928.02 | 60659.1517 | 20562.81 | 27364.4358 | 18066.7 | 80548.4831 | 5000 | 2243.2477 | 1961.875 | 120.2088 | 1961.875 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-18 | 273319.2999 | 94989.78 | 90737.9543 | 48432.25 | 12026.0742 | 2928.02 | 61372.7888 | 20562.81 | 27686.3703 | 18066.7 | 81496.1124 | 5000 | 2243.2477 | 1961.875 | 120.2088 | 1961.875 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-19 | 275562.5476 | 96951.655 | 90858.1631 | 50394.125 | 12165.9123 | 2928.02 | 62086.4258 | 20562.81 | 28008.3048 | 18066.7 | 82443.7416 | 5000 | 2243.2477 | 1961.875 | 120.2088 | 1961.875 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-20 | 277805.7953 | 96951.655 | 90978.3719 | 50394.125 | 12305.7503 | 2928.02 | 62800.0629 | 20562.81 | 28330.2394 | 18066.7 | 83391.3708 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-21 | 280049.043 | 96951.655 | 91098.5806 | 50394.125 | 12445.5884 | 2928.02 | 63513.7 | 20562.81 | 28652.1739 | 18066.7 | 84339 | 5000 | 2243.2477 | 0 | 120.2088 | 0 | 139.8381 | 0 | 713.6371 | 0 | 321.9345 | 0 | 947.6292 | 0
2025-09-22 | 280049.043 | 100251.23 | 91098.5806 | 51446.2 | 12445.5884 | 3228.02 | 63513.7 | 20562.81 | 28652.1739 | 20014.2 | 84339 | 5000 | 0 | 3299.575 | 0 | 1052.075 | 0 | 300 | 0 | 0 | 0 | 1947.5 | 0 | 0
2025-09-23 | 280049.043 | 102440.825 | 91098.5806 | 52498.275 | 12445.5884 | 3228.02 | 63513.7 | 20562.81 | 28652.1739 | 21151.72 | 84339 | 5000 | 0 | 2189.595 | 0 | 1052.075 | 0 | 0 | 0 | 0 | 0 | 1137.52 | 0 | 0
2025-09-24 | 280049.043 | 116375.11 | 91098.5806 | 53550.35 | 12445.5884 | 3333.29 | 63513.7 | 23165.94 | 28652.1739 | 31325.53 | 84339 | 5000 | 0 | 13934.285 | 0 | 1052.075 | 0 | 105.27 | 0 | 2603.13 | 0 | 10173.81 | 0 | 0
2025-09-25 | 280049.043 | 118372.895 | 91098.5806 | 54602.425 | 12445.5884 | 3333.29 | 63513.7 | 24111.65 | 28652.1739 | 31325.53 | 84339 | 5000 | 0 | 1997.785 | 0 | 1052.075 | 0 | 0 | 0 | 945.71 | 0 | 0 | 0 | 0
2025-09-26 | 280049.043 | 119424.97 | 91098.5806 | 55654.5 | 12445.5884 | 3333.29 | 63513.7 | 24111.65 | 28652.1739 | 31325.53 | 84339 | 5000 | 0 | 1052.075 | 0 | 1052.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-27 | 280049.043 | 119424.97 | 91098.5806 | 55654.5 | 12445.5884 | 3333.29 | 63513.7 | 24111.65 | 28652.1739 | 31325.53 | 84339 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-28 | 280049.043 | 119544.5 | 91098.5806 | 55654.5 | 12445.5884 | 3452.82 | 63513.7 | 24111.65 | 28652.1739 | 31325.53 | 84339 | 5000 | 0 | 119.53 | 0 | 0 | 0 | 119.53 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-29 | 285636.4735 | 129514.195 | 94401.4769 | 56981.625 | 13471.6043 | 4852.82 | 64342.5167 | 31354.22 | 28840.6138 | 31325.53 | 84580.2617 | 5000 | 5587.4305 | 9969.695 | 3302.8963 | 1327.125 | 1026.0159 | 1400 | 828.8167 | 7242.57 | 188.4399 | 0 | 241.2617 | 0
2025-09-30 | 291223.904 | 130841.32 | 97704.3732 | 58308.75 | 14497.6202 | 4852.82 | 65171.3334 | 31354.22 | 29029.0537 | 31325.53 | 84821.5234 | 5000 | 5587.4305 | 1327.125 | 3302.8963 | 1327.125 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-01 | 296811.3345 | 132168.445 | 101007.2694 | 59635.875 | 15523.6361 | 4852.82 | 66000.1501 | 31354.22 | 29217.4936 | 31325.53 | 85062.7852 | 5000 | 5587.4305 | 1327.125 | 3302.8963 | 1327.125 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-02 | 302398.765 | 133630.28 | 104310.1657 | 60963 | 16549.6521 | 4852.82 | 66828.9668 | 31354.22 | 29405.9335 | 31460.24 | 85304.0469 | 5000 | 5587.4305 | 1461.835 | 3302.8963 | 1327.125 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 134.71 | 241.2617 | 0
2025-10-03 | 307986.1955 | 135457.405 | 107613.062 | 62290.125 | 17575.668 | 5352.82 | 67657.7835 | 31354.22 | 29594.3734 | 31460.24 | 85545.3086 | 5000 | 5587.4305 | 1827.125 | 3302.8963 | 1327.125 | 1026.0159 | 500 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-04 | 313573.626 | 135457.405 | 110915.9583 | 62290.125 | 18601.6839 | 5352.82 | 68486.6003 | 31354.22 | 29782.8133 | 31460.24 | 85786.5703 | 5000 | 5587.4305 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-05 | 319161.0565 | 135457.405 | 114218.8545 | 62290.125 | 19627.6998 | 5352.82 | 69315.417 | 31354.22 | 29971.2532 | 31460.24 | 86027.8321 | 5000 | 5587.4305 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-06 | 324748.4871 | 137114.155 | 117521.7508 | 63946.875 | 20653.7157 | 5352.82 | 70144.2337 | 31354.22 | 30159.6931 | 31460.24 | 86269.0938 | 5000 | 5587.4305 | 1656.75 | 3302.8963 | 1656.75 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-07 | 330335.9176 | 138770.905 | 120824.6471 | 65603.625 | 21679.7316 | 5352.82 | 70973.0504 | 31354.22 | 30348.133 | 31460.24 | 86510.3555 | 5000 | 5587.4305 | 1656.75 | 3302.8963 | 1656.75 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-08 | 335923.3481 | 150324.585 | 124127.5433 | 67260.375 | 22705.7475 | 5352.82 | 71801.8671 | 31354.22 | 30536.5729 | 41357.17 | 86751.6172 | 5000 | 5587.4305 | 11553.68 | 3302.8963 | 1656.75 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 9896.93 | 241.2617 | 0
2025-10-09 | 341510.7786 | 151981.335 | 127430.4396 | 68917.125 | 23731.7635 | 5352.82 | 72630.6838 | 31354.22 | 30725.0128 | 41357.17 | 86992.8789 | 5000 | 5587.4305 | 1656.75 | 3302.8963 | 1656.75 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-10 | 347098.2091 | 153638.085 | 130733.3359 | 70573.875 | 24757.7794 | 5352.82 | 73459.5005 | 31354.22 | 30913.4527 | 41357.17 | 87234.1407 | 5000 | 5587.4305 | 1656.75 | 3302.8963 | 1656.75 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-11 | 352685.6396 | 155238.085 | 134036.2321 | 70573.875 | 25783.7953 | 5352.82 | 74288.3172 | 31354.22 | 31101.8926 | 42957.17 | 87475.4024 | 5000 | 5587.4305 | 1600 | 3302.8963 | 0 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 1600 | 241.2617 | 0
2025-10-12 | 358273.0701 | 155238.085 | 137339.1284 | 70573.875 | 26809.8112 | 5352.82 | 75117.1339 | 31354.22 | 31290.3325 | 42957.17 | 87716.6641 | 5000 | 5587.4305 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-13 | 363860.5006 | 155419.035 | 140642.0247 | 70754.825 | 27835.8271 | 5352.82 | 75945.9506 | 31354.22 | 31478.7724 | 42957.17 | 87957.9258 | 5000 | 5587.4305 | 180.95 | 3302.8963 | 180.95 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-14 | 369447.9311 | 156949.985 | 143944.9209 | 70935.775 | 28861.843 | 6702.82 | 76774.7673 | 31354.22 | 31667.2123 | 42957.17 | 88199.1876 | 5000 | 5587.4305 | 1530.95 | 3302.8963 | 180.95 | 1026.0159 | 1350 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-15 | 375035.3616 | 157130.935 | 147247.8172 | 71116.725 | 29887.8589 | 6702.82 | 77603.5841 | 31354.22 | 31855.6522 | 42957.17 | 88440.4493 | 5000 | 5587.4305 | 180.95 | 3302.8963 | 180.95 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-16 | 380622.7922 | 157311.885 | 150550.7135 | 71297.675 | 30913.8749 | 6702.82 | 78432.4008 | 31354.22 | 32044.0921 | 42957.17 | 88681.711 | 5000 | 5587.4305 | 180.95 | 3302.8963 | 180.95 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-17 | 386210.2227 | 158192.835 | 153853.6097 | 71478.625 | 31939.8908 | 7402.82 | 79261.2175 | 31354.22 | 32232.532 | 42957.17 | 88922.9727 | 5000 | 5587.4305 | 880.95 | 3302.8963 | 180.95 | 1026.0159 | 700 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-18 | 391797.6532 | 158192.835 | 157156.506 | 71478.625 | 32965.9067 | 7402.82 | 80090.0342 | 31354.22 | 32420.9719 | 42957.17 | 89164.2344 | 5000 | 5587.4305 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-19 | 397385.0837 | 158192.835 | 160459.4023 | 71478.625 | 33991.9226 | 7402.82 | 80918.8509 | 31354.22 | 32609.4118 | 42957.17 | 89405.4962 | 5000 | 5587.4305 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-20 | 402972.5142 | 158293.385 | 163762.2985 | 71579.175 | 35017.9385 | 7402.82 | 81747.6676 | 31354.22 | 32797.8517 | 42957.17 | 89646.7579 | 5000 | 5587.4305 | 100.55 | 3302.8963 | 100.55 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-21 | 408559.9447 | 158393.935 | 167065.1948 | 71679.725 | 36043.9544 | 7402.82 | 82576.4843 | 31354.22 | 32986.2916 | 42957.17 | 89888.0196 | 5000 | 5587.4305 | 100.55 | 3302.8963 | 100.55 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-22 | 414147.3752 | 158494.485 | 170368.0911 | 71780.275 | 37069.9703 | 7402.82 | 83405.301 | 31354.22 | 33174.7315 | 42957.17 | 90129.2813 | 5000 | 5587.4305 | 100.55 | 3302.8963 | 100.55 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-23 | 419734.8057 | 158595.035 | 173670.9873 | 71880.825 | 38095.9862 | 7402.82 | 84234.1177 | 31354.22 | 33363.1714 | 42957.17 | 90370.5431 | 5000 | 5587.4305 | 100.55 | 3302.8963 | 100.55 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-24 | 425322.2362 | 159795.585 | 176973.8836 | 71981.375 | 39122.0022 | 8502.82 | 85062.9344 | 31354.22 | 33551.6113 | 42957.17 | 90611.8048 | 5000 | 5587.4305 | 1200.55 | 3302.8963 | 100.55 | 1026.0159 | 1100 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-25 | 430909.6668 | 159795.585 | 180276.7799 | 71981.375 | 40148.0181 | 8502.82 | 85891.7512 | 31354.22 | 33740.0512 | 42957.17 | 90853.0665 | 5000 | 5587.4305 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-26 | 436497.0973 | 159795.585 | 183579.6762 | 71981.375 | 41174.034 | 8502.82 | 86720.5679 | 31354.22 | 33928.491 | 42957.17 | 91094.3282 | 5000 | 5587.4305 | 0 | 3302.8963 | 0 | 1026.0159 | 0 | 828.8167 | 0 | 188.4399 | 0 | 241.2617 | 0
2025-10-27 | 442084.5278 |  | 186882.5724 |  | 42200.0499 |  | 87549.3846 |  | 34116.9309 |  | 91335.5899 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-10-28 | 447671.9583 |  | 190185.4687 |  | 43226.0658 |  | 88378.2013 |  | 34305.3708 |  | 91576.8517 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-10-29 | 453259.3888 |  | 193488.365 |  | 44252.0817 |  | 89207.018 |  | 34493.8107 |  | 91818.1134 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-10-30 | 458846.8193 |  | 196791.2612 |  | 45278.0976 |  | 90035.8347 |  | 34682.2506 |  | 92059.3751 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-10-31 | 464434.2498 |  | 200094.1575 |  | 46304.1136 |  | 90864.6514 |  | 34870.6905 |  | 92300.6368 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-01 | 470021.6803 |  | 203397.0538 |  | 47330.1295 |  | 91693.4681 |  | 35059.1304 |  | 92541.8986 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-02 | 475609.1108 |  | 206699.95 |  | 48356.1454 |  | 92522.2848 |  | 35247.5703 |  | 92783.1603 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-03 | 481196.5414 |  | 210002.8463 |  | 49382.1613 |  | 93351.1015 |  | 35436.0102 |  | 93024.422 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-04 | 486783.9719 |  | 213305.7426 |  | 50408.1772 |  | 94179.9182 |  | 35624.4501 |  | 93265.6837 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-05 | 492371.4024 |  | 216608.6388 |  | 51434.1931 |  | 95008.735 |  | 35812.89 |  | 93506.9454 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-06 | 497958.8329 |  | 219911.5351 |  | 52460.209 |  | 95837.5517 |  | 36001.3299 |  | 93748.2072 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-07 | 503546.2634 |  | 223214.4314 |  | 53486.225 |  | 96666.3684 |  | 36189.7698 |  | 93989.4689 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-08 | 509133.6939 |  | 226517.3276 |  | 54512.2409 |  | 97495.1851 |  | 36378.2097 |  | 94230.7306 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-09 | 514721.1244 |  | 229820.2239 |  | 55538.2568 |  | 98324.0018 |  | 36566.6496 |  | 94471.9923 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-10 | 520308.5549 |  | 233123.1202 |  | 56564.2727 |  | 99152.8185 |  | 36755.0895 |  | 94713.254 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-11 | 525895.9854 |  | 236426.0164 |  | 57590.2886 |  | 99981.6352 |  | 36943.5294 |  | 94954.5158 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-12 | 531483.416 |  | 239728.9127 |  | 58616.3045 |  | 100810.4519 |  | 37131.9693 |  | 95195.7775 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-13 | 537070.8465 |  | 243031.809 |  | 59642.3204 |  | 101639.2686 |  | 37320.4092 |  | 95437.0392 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-14 | 542658.277 |  | 246334.7052 |  | 60668.3363 |  | 102468.0853 |  | 37508.8491 |  | 95678.3009 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-15 | 548245.7075 |  | 249637.6015 |  | 61694.3523 |  | 103296.902 |  | 37697.289 |  | 95919.5627 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-16 | 553833.138 |  | 252940.4978 |  | 62720.3682 |  | 104125.7188 |  | 37885.7289 |  | 96160.8244 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-17 | 559420.5685 |  | 256243.3941 |  | 63746.3841 |  | 104954.5355 |  | 38074.1688 |  | 96402.0861 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-18 | 565007.999 |  | 259546.2903 |  | 64772.4 |  | 105783.3522 |  | 38262.6087 |  | 96643.3478 |  | 5587.4305 |  | 3302.8963 |  | 1026.0159 |  | 828.8167 |  | 188.4399 |  | 241.2617
2025-11-19 | 568346.5727 |  | 261095.5386 |  | 65374.5825 |  | 106470.495 |  | 38262.6087 |  | 97143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-20 | 571685.1465 |  | 262644.787 |  | 65976.7651 |  | 107157.6379 |  | 38262.6087 |  | 97643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-21 | 575023.7202 |  | 264194.0353 |  | 66578.9476 |  | 107844.7807 |  | 38262.6087 |  | 98143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-22 | 578362.2939 |  | 265743.2836 |  | 67181.1302 |  | 108531.9236 |  | 38262.6087 |  | 98643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-23 | 581700.8676 |  | 267292.5319 |  | 67783.3127 |  | 109219.0665 |  | 38262.6087 |  | 99143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-24 | 585039.4413 |  | 268841.7802 |  | 68385.4952 |  | 109906.2093 |  | 38262.6087 |  | 99643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-25 | 588378.015 |  | 270391.0286 |  | 68987.6778 |  | 110593.3522 |  | 38262.6087 |  | 100143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-26 | 591716.5887 |  | 271940.2769 |  | 69589.8603 |  | 111280.495 |  | 38262.6087 |  | 100643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-27 | 595055.1625 |  | 273489.5252 |  | 70192.0429 |  | 111967.6379 |  | 38262.6087 |  | 101143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-28 | 598393.7362 |  | 275038.7735 |  | 70794.2254 |  | 112654.7807 |  | 38262.6087 |  | 101643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-29 | 601732.3099 |  | 276588.0218 |  | 71396.4079 |  | 113341.9236 |  | 38262.6087 |  | 102143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-11-30 | 605070.8836 |  | 278137.2702 |  | 71998.5905 |  | 114029.0665 |  | 38262.6087 |  | 102643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-01 | 608409.4573 |  | 279686.5185 |  | 72600.773 |  | 114716.2093 |  | 38262.6087 |  | 103143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-02 | 611748.031 |  | 281235.7668 |  | 73202.9556 |  | 115403.3522 |  | 38262.6087 |  | 103643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-03 | 615086.6048 |  | 282785.0151 |  | 73805.1381 |  | 116090.495 |  | 38262.6087 |  | 104143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-04 | 618425.1785 |  | 284334.2634 |  | 74407.3206 |  | 116777.6379 |  | 38262.6087 |  | 104643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-05 | 621763.7522 |  | 285883.5117 |  | 75009.5032 |  | 117464.7807 |  | 38262.6087 |  | 105143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-06 | 625102.3259 |  | 287432.7601 |  | 75611.6857 |  | 118151.9236 |  | 38262.6087 |  | 105643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-07 | 628440.8996 |  | 288982.0084 |  | 76213.8683 |  | 118839.0665 |  | 38262.6087 |  | 106143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-08 | 631779.4733 |  | 290531.2567 |  | 76816.0508 |  | 119526.2093 |  | 38262.6087 |  | 106643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-09 | 635118.0471 |  | 292080.505 |  | 77418.2333 |  | 120213.3522 |  | 38262.6087 |  | 107143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-10 | 638456.6208 |  | 293629.7533 |  | 78020.4159 |  | 120900.495 |  | 38262.6087 |  | 107643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-11 | 641795.1945 |  | 295179.0017 |  | 78622.5984 |  | 121587.6379 |  | 38262.6087 |  | 108143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-12 | 645133.7682 |  | 296728.25 |  | 79224.781 |  | 122274.7807 |  | 38262.6087 |  | 108643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-13 | 648472.3419 |  | 298277.4983 |  | 79826.9635 |  | 122961.9236 |  | 38262.6087 |  | 109143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-14 | 651810.9156 |  | 299826.7466 |  | 80429.146 |  | 123649.0665 |  | 38262.6087 |  | 109643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-15 | 655149.4893 |  | 301375.9949 |  | 81031.3286 |  | 124336.2093 |  | 38262.6087 |  | 110143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-16 | 658488.0631 |  | 302925.2433 |  | 81633.5111 |  | 125023.3522 |  | 38262.6087 |  | 110643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-17 | 661826.6368 |  | 304474.4916 |  | 82235.6937 |  | 125710.495 |  | 38262.6087 |  | 111143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-18 | 665165.2105 |  | 306023.7399 |  | 82837.8762 |  | 126397.6379 |  | 38262.6087 |  | 111643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-19 | 668503.7842 |  | 307572.9882 |  | 83440.0587 |  | 127084.7807 |  | 38262.6087 |  | 112143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-20 | 671842.3579 |  | 309122.2365 |  | 84042.2413 |  | 127771.9236 |  | 38262.6087 |  | 112643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-21 | 675180.9316 |  | 310671.4849 |  | 84644.4238 |  | 128459.0665 |  | 38262.6087 |  | 113143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-22 | 678519.5054 |  | 312220.7332 |  | 85246.6063 |  | 129146.2093 |  | 38262.6087 |  | 113643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-23 | 681858.0791 |  | 313769.9815 |  | 85848.7889 |  | 129833.3522 |  | 38262.6087 |  | 114143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-24 | 685196.6528 |  | 315319.2298 |  | 86450.9714 |  | 130520.495 |  | 38262.6087 |  | 114643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-25 | 688535.2265 |  | 316868.4781 |  | 87053.154 |  | 131207.6379 |  | 38262.6087 |  | 115143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-26 | 691873.8002 |  | 318417.7264 |  | 87655.3365 |  | 131894.7807 |  | 38262.6087 |  | 115643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-27 | 695212.3739 |  | 319966.9748 |  | 88257.519 |  | 132581.9236 |  | 38262.6087 |  | 116143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-28 | 698550.9477 |  | 321516.2231 |  | 88859.7016 |  | 133269.0665 |  | 38262.6087 |  | 116643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-29 | 701889.5214 |  | 323065.4714 |  | 89461.8841 |  | 133956.2093 |  | 38262.6087 |  | 117143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-30 | 705228.0951 |  | 324614.7197 |  | 90064.0667 |  | 134643.3522 |  | 38262.6087 |  | 117643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2025-12-31 | 708566.6688 |  | 326163.968 |  | 90666.2492 |  | 135330.495 |  | 38262.6087 |  | 118143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-01 | 711905.2425 |  | 327713.2164 |  | 91268.4317 |  | 136017.6379 |  | 38262.6087 |  | 118643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-02 | 715243.8162 |  | 329262.4647 |  | 91870.6143 |  | 136704.7807 |  | 38262.6087 |  | 119143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-03 | 718582.39 |  | 330811.713 |  | 92472.7968 |  | 137391.9236 |  | 38262.6087 |  | 119643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-04 | 721920.9637 |  | 332360.9613 |  | 93074.9794 |  | 138079.0665 |  | 38262.6087 |  | 120143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-05 | 725259.5374 |  | 333910.2096 |  | 93677.1619 |  | 138766.2093 |  | 38262.6087 |  | 120643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-06 | 728598.1111 |  | 335459.458 |  | 94279.3444 |  | 139453.3522 |  | 38262.6087 |  | 121143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-07 | 731936.6848 |  | 337008.7063 |  | 94881.527 |  | 140140.495 |  | 38262.6087 |  | 121643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-08 | 735275.2585 |  | 338557.9546 |  | 95483.7095 |  | 140827.6379 |  | 38262.6087 |  | 122143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-09 | 738613.8322 |  | 340107.2029 |  | 96085.8921 |  | 141514.7807 |  | 38262.6087 |  | 122643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-10 | 741952.406 |  | 341656.4512 |  | 96688.0746 |  | 142201.9236 |  | 38262.6087 |  | 123143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-11 | 745290.9797 |  | 343205.6996 |  | 97290.2571 |  | 142889.0665 |  | 38262.6087 |  | 123643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-12 | 748629.5534 |  | 344754.9479 |  | 97892.4397 |  | 143576.2093 |  | 38262.6087 |  | 124143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-13 | 751968.1271 |  | 346304.1962 |  | 98494.6222 |  | 144263.3522 |  | 38262.6087 |  | 124643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-14 | 755306.7008 |  | 347853.4445 |  | 99096.8048 |  | 144950.495 |  | 38262.6087 |  | 125143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-15 | 758645.2745 |  | 349402.6928 |  | 99698.9873 |  | 145637.6379 |  | 38262.6087 |  | 125643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-16 | 761983.8483 |  | 350951.9411 |  | 100301.1698 |  | 146324.7807 |  | 38262.6087 |  | 126143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-17 | 765322.422 |  | 352501.1895 |  | 100903.3524 |  | 147011.9236 |  | 38262.6087 |  | 126643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-18 | 768660.9957 |  | 354050.4378 |  | 101505.5349 |  | 147699.0665 |  | 38262.6087 |  | 127143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-19 | 771999.5694 |  | 355599.6861 |  | 102107.7175 |  | 148386.2093 |  | 38262.6087 |  | 127643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-20 | 775338.1431 |  | 357148.9344 |  | 102709.9 |  | 149073.3522 |  | 38262.6087 |  | 128143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-21 | 778676.7168 |  | 358698.1827 |  | 103312.0825 |  | 149760.495 |  | 38262.6087 |  | 128643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-22 | 782015.2906 |  | 360247.4311 |  | 103914.2651 |  | 150447.6379 |  | 38262.6087 |  | 129143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-23 | 785353.8643 |  | 361796.6794 |  | 104516.4476 |  | 151134.7807 |  | 38262.6087 |  | 129643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-24 | 788692.438 |  | 363345.9277 |  | 105118.6302 |  | 151821.9236 |  | 38262.6087 |  | 130143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-25 | 792031.0117 |  | 364895.176 |  | 105720.8127 |  | 152509.0665 |  | 38262.6087 |  | 130643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-26 | 795369.5854 |  | 366444.4243 |  | 106322.9952 |  | 153196.2093 |  | 38262.6087 |  | 131143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-27 | 798708.1591 |  | 367993.6727 |  | 106925.1778 |  | 153883.3522 |  | 38262.6087 |  | 131643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-28 | 802046.7328 |  | 369542.921 |  | 107527.3603 |  | 154570.495 |  | 38262.6087 |  | 132143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-29 | 805385.3066 |  | 371092.1693 |  | 108129.5429 |  | 155257.6379 |  | 38262.6087 |  | 132643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-30 | 808723.8803 |  | 372641.4176 |  | 108731.7254 |  | 155944.7807 |  | 38262.6087 |  | 133143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-01-31 | 812062.454 |  | 374190.6659 |  | 109333.9079 |  | 156631.9236 |  | 38262.6087 |  | 133643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-01 | 815401.0277 |  | 375739.9143 |  | 109936.0905 |  | 157319.0665 |  | 38262.6087 |  | 134143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-02 | 818739.6014 |  | 377289.1626 |  | 110538.273 |  | 158006.2093 |  | 38262.6087 |  | 134643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-03 | 822078.1751 |  | 378838.4109 |  | 111140.4556 |  | 158693.3522 |  | 38262.6087 |  | 135143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-04 | 825416.7489 |  | 380387.6592 |  | 111742.6381 |  | 159380.495 |  | 38262.6087 |  | 135643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-05 | 828755.3226 |  | 381936.9075 |  | 112344.8206 |  | 160067.6379 |  | 38262.6087 |  | 136143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-06 | 832093.8963 |  | 383486.1559 |  | 112947.0032 |  | 160754.7807 |  | 38262.6087 |  | 136643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-07 | 835432.47 |  | 385035.4042 |  | 113549.1857 |  | 161441.9236 |  | 38262.6087 |  | 137143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-08 | 838771.0437 |  | 386584.6525 |  | 114151.3683 |  | 162129.0665 |  | 38262.6087 |  | 137643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-09 | 842109.6174 |  | 388133.9008 |  | 114753.5508 |  | 162816.2093 |  | 38262.6087 |  | 138143.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-10 | 845448.1912 |  | 389683.1491 |  | 115355.7333 |  | 163503.3522 |  | 38262.6087 |  | 138643.3478 |  | 3338.5737 |  | 1549.2483 |  | 602.1825 |  | 687.1429 |  | 0 |  | 500
2026-02-11 | 847097.575 |  | 390971.2259 |  | 115675.3825 |  | 163545.0101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-12 | 848746.9588 |  | 392259.3028 |  | 115995.0316 |  | 163586.668 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-13 | 850396.3427 |  | 393547.3796 |  | 116314.6807 |  | 163628.3259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-14 | 852045.7265 |  | 394835.4564 |  | 116634.3298 |  | 163669.9838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-15 | 853695.1103 |  | 396123.5332 |  | 116953.9789 |  | 163711.6416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-16 | 855344.4942 |  | 397411.61 |  | 117273.6281 |  | 163753.2995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-17 | 856993.878 |  | 398699.6869 |  | 117593.2772 |  | 163794.9574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-18 | 858643.2618 |  | 399987.7637 |  | 117912.9263 |  | 163836.6153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-19 | 860292.6457 |  | 401275.8405 |  | 118232.5754 |  | 163878.2732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-20 | 861942.0295 |  | 402563.9173 |  | 118552.2246 |  | 163919.9311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-21 | 863591.4133 |  | 403851.9941 |  | 118871.8737 |  | 163961.589 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-22 | 865240.7972 |  | 405140.0709 |  | 119191.5228 |  | 164003.2469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-23 | 866890.181 |  | 406428.1478 |  | 119511.1719 |  | 164044.9048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-24 | 868539.5649 |  | 407716.2246 |  | 119830.8211 |  | 164086.5627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-25 | 870188.9487 |  | 409004.3014 |  | 120150.4702 |  | 164128.2206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-26 | 871838.3325 |  | 410292.3782 |  | 120470.1193 |  | 164169.8785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-27 | 873487.7164 |  | 411580.455 |  | 120789.7684 |  | 164211.5364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-28 | 875137.1002 |  | 412868.5319 |  | 121109.4175 |  | 164253.1943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-01 | 876786.484 |  | 414156.6087 |  | 121429.0667 |  | 164294.8522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-02 | 878435.8679 |  | 415444.6855 |  | 121748.7158 |  | 164336.5101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-03 | 880085.2517 |  | 416732.7623 |  | 122068.3649 |  | 164378.168 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-04 | 881734.6355 |  | 418020.8391 |  | 122388.014 |  | 164419.8259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-05 | 883384.0194 |  | 419308.9159 |  | 122707.6632 |  | 164461.4838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-06 | 885033.4032 |  | 420596.9928 |  | 123027.3123 |  | 164503.1416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-07 | 886682.787 |  | 421885.0696 |  | 123346.9614 |  | 164544.7995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-08 | 888332.1709 |  | 423173.1464 |  | 123666.6105 |  | 164586.4574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-09 | 889981.5547 |  | 424461.2232 |  | 123986.2596 |  | 164628.1153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-10 | 891630.9386 |  | 425749.3 |  | 124305.9088 |  | 164669.7732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-11 | 893280.3224 |  | 427037.3769 |  | 124625.5579 |  | 164711.4311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-12 | 894929.7062 |  | 428325.4537 |  | 124945.207 |  | 164753.089 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-13 | 896579.0901 |  | 429613.5305 |  | 125264.8561 |  | 164794.7469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-14 | 898228.4739 |  | 430901.6073 |  | 125584.5053 |  | 164836.4048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-15 | 899877.8577 |  | 432189.6841 |  | 125904.1544 |  | 164878.0627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-16 | 901527.2416 |  | 433477.7609 |  | 126223.8035 |  | 164919.7206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-17 | 903176.6254 |  | 434765.8378 |  | 126543.4526 |  | 164961.3785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-18 | 904826.0092 |  | 436053.9146 |  | 126863.1018 |  | 165003.0364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-19 | 906475.3931 |  | 437341.9914 |  | 127182.7509 |  | 165044.6943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-20 | 908124.7769 |  | 438630.0682 |  | 127502.4 |  | 165086.3522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-21 | 909774.1607 |  | 439918.145 |  | 127822.0491 |  | 165128.0101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-22 | 911423.5446 |  | 441206.2219 |  | 128141.6982 |  | 165169.668 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-23 | 913072.9284 |  | 442494.2987 |  | 128461.3474 |  | 165211.3259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-24 | 914722.3123 |  | 443782.3755 |  | 128780.9965 |  | 165252.9838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-25 | 916371.6961 |  | 445070.4523 |  | 129100.6456 |  | 165294.6416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-26 | 918021.0799 |  | 446358.5291 |  | 129420.2947 |  | 165336.2995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-27 | 919670.4638 |  | 447646.6059 |  | 129739.9439 |  | 165377.9574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-28 | 921319.8476 |  | 448934.6828 |  | 130059.593 |  | 165419.6153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-29 | 922969.2314 |  | 450222.7596 |  | 130379.2421 |  | 165461.2732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-30 | 924618.6153 |  | 451510.8364 |  | 130698.8912 |  | 165502.9311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-31 | 926267.9991 |  | 452798.9132 |  | 131018.5404 |  | 165544.589 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-01 | 927917.3829 |  | 454086.99 |  | 131338.1895 |  | 165586.2469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-02 | 929566.7668 |  | 455375.0669 |  | 131657.8386 |  | 165627.9048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-03 | 931216.1506 |  | 456663.1437 |  | 131977.4877 |  | 165669.5627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-04 | 932865.5344 |  | 457951.2205 |  | 132297.1368 |  | 165711.2206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-05 | 934514.9183 |  | 459239.2973 |  | 132616.786 |  | 165752.8785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-06 | 936164.3021 |  | 460527.3741 |  | 132936.4351 |  | 165794.5364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-07 | 937813.686 |  | 461815.4509 |  | 133256.0842 |  | 165836.1943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-08 | 939463.0698 |  | 463103.5278 |  | 133575.7333 |  | 165877.8522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-09 | 941112.4536 |  | 464391.6046 |  | 133895.3825 |  | 165919.5101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-10 | 942761.8375 |  | 465679.6814 |  | 134215.0316 |  | 165961.168 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-11 | 944411.2213 |  | 466967.7582 |  | 134534.6807 |  | 166002.8259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-12 | 946060.6051 |  | 468255.835 |  | 134854.3298 |  | 166044.4838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-13 | 947709.989 |  | 469543.9119 |  | 135173.9789 |  | 166086.1416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-14 | 949359.3728 |  | 470831.9887 |  | 135493.6281 |  | 166127.7995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-15 | 951008.7566 |  | 472120.0655 |  | 135813.2772 |  | 166169.4574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-16 | 952658.1405 |  | 473408.1423 |  | 136132.9263 |  | 166211.1153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-17 | 954307.5243 |  | 474696.2191 |  | 136452.5754 |  | 166252.7732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-18 | 955956.9081 |  | 475984.2959 |  | 136772.2246 |  | 166294.4311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-19 | 957606.292 |  | 477272.3728 |  | 137091.8737 |  | 166336.089 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-20 | 959255.6758 |  | 478560.4496 |  | 137411.5228 |  | 166377.7469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-21 | 960905.0597 |  | 479848.5264 |  | 137731.1719 |  | 166419.4048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-22 | 962554.4435 |  | 481136.6032 |  | 138050.8211 |  | 166461.0627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-23 | 964203.8273 |  | 482424.68 |  | 138370.4702 |  | 166502.7206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-24 | 965853.2112 |  | 483712.7569 |  | 138690.1193 |  | 166544.3785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-25 | 967502.595 |  | 485000.8337 |  | 139009.7684 |  | 166586.0364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-26 | 969151.9788 |  | 486288.9105 |  | 139329.4175 |  | 166627.6943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-27 | 970801.3627 |  | 487576.9873 |  | 139649.0667 |  | 166669.3522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-28 | 972450.7465 |  | 488865.0641 |  | 139968.7158 |  | 166711.0101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-29 | 974100.1303 |  | 490153.1409 |  | 140288.3649 |  | 166752.668 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-30 | 975749.5142 |  | 491441.2178 |  | 140608.014 |  | 166794.3259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-01 | 977398.898 |  | 492729.2946 |  | 140927.6632 |  | 166835.9838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-02 | 979048.2818 |  | 494017.3714 |  | 141247.3123 |  | 166877.6416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-03 | 980697.6657 |  | 495305.4482 |  | 141566.9614 |  | 166919.2995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-04 | 982347.0495 |  | 496593.525 |  | 141886.6105 |  | 166960.9574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-05 | 983996.4334 |  | 497881.6019 |  | 142206.2596 |  | 167002.6153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-06 | 985645.8172 |  | 499169.6787 |  | 142525.9088 |  | 167044.2732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-07 | 987295.201 |  | 500457.7555 |  | 142845.5579 |  | 167085.9311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-08 | 988944.5849 |  | 501745.8323 |  | 143165.207 |  | 167127.589 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-09 | 990593.9687 |  | 503033.9091 |  | 143484.8561 |  | 167169.2469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-10 | 992243.3525 |  | 504321.9859 |  | 143804.5053 |  | 167210.9048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-11 | 993892.7364 |  | 505610.0628 |  | 144124.1544 |  | 167252.5627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-12 | 995542.1202 |  | 506898.1396 |  | 144443.8035 |  | 167294.2206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-13 | 997191.504 |  | 508186.2164 |  | 144763.4526 |  | 167335.8785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-14 | 998840.8879 |  | 509474.2932 |  | 145083.1018 |  | 167377.5364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-15 | 1000490.2717 |  | 510762.37 |  | 145402.7509 |  | 167419.1943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-16 | 1002139.6555 |  | 512050.4469 |  | 145722.4 |  | 167460.8522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-17 | 1003789.0394 |  | 513338.5237 |  | 146042.0491 |  | 167502.5101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-18 | 1005438.4232 |  | 514626.6005 |  | 146361.6982 |  | 167544.168 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-19 | 1007087.8071 |  | 515914.6773 |  | 146681.3474 |  | 167585.8259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-20 | 1008737.1909 |  | 517202.7541 |  | 147000.9965 |  | 167627.4838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-21 | 1010386.5747 |  | 518490.8309 |  | 147320.6456 |  | 167669.1416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-22 | 1012035.9586 |  | 519778.9078 |  | 147640.2947 |  | 167710.7995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-23 | 1013685.3424 |  | 521066.9846 |  | 147959.9439 |  | 167752.4574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-24 | 1015334.7262 |  | 522355.0614 |  | 148279.593 |  | 167794.1153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-25 | 1016984.1101 |  | 523643.1382 |  | 148599.2421 |  | 167835.7732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-26 | 1018633.4939 |  | 524931.215 |  | 148918.8912 |  | 167877.4311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-27 | 1020282.8777 |  | 526219.2919 |  | 149238.5404 |  | 167919.089 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-28 | 1021932.2616 |  | 527507.3687 |  | 149558.1895 |  | 167960.7469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-29 | 1023581.6454 |  | 528795.4455 |  | 149877.8386 |  | 168002.4048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-30 | 1025231.0292 |  | 530083.5223 |  | 150197.4877 |  | 168044.0627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-31 | 1026880.4131 |  | 531371.5991 |  | 150517.1368 |  | 168085.7206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-01 | 1028529.7969 |  | 532659.6759 |  | 150836.786 |  | 168127.3785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-02 | 1030179.1808 |  | 533947.7528 |  | 151156.4351 |  | 168169.0364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-03 | 1031828.5646 |  | 535235.8296 |  | 151476.0842 |  | 168210.6943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-04 | 1033477.9484 |  | 536523.9064 |  | 151795.7333 |  | 168252.3522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-05 | 1035127.3323 |  | 537811.9832 |  | 152115.3825 |  | 168294.0101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-06 | 1036776.7161 |  | 539100.06 |  | 152435.0316 |  | 168335.668 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-07 | 1038426.0999 |  | 540388.1369 |  | 152754.6807 |  | 168377.3259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-08 | 1040075.4838 |  | 541676.2137 |  | 153074.3298 |  | 168418.9838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-09 | 1041724.8676 |  | 542964.2905 |  | 153393.9789 |  | 168460.6416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-10 | 1043374.2514 |  | 544252.3673 |  | 153713.6281 |  | 168502.2995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-11 | 1045023.6353 |  | 545540.4441 |  | 154033.2772 |  | 168543.9574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-12 | 1046673.0191 |  | 546828.5209 |  | 154352.9263 |  | 168585.6153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-13 | 1048322.4029 |  | 548116.5978 |  | 154672.5754 |  | 168627.2732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-14 | 1049971.7868 |  | 549404.6746 |  | 154992.2246 |  | 168668.9311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-15 | 1051621.1706 |  | 550692.7514 |  | 155311.8737 |  | 168710.589 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-16 | 1053270.5545 |  | 551980.8282 |  | 155631.5228 |  | 168752.2469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-17 | 1054919.9383 |  | 553268.905 |  | 155951.1719 |  | 168793.9048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-18 | 1056569.3221 |  | 554556.9819 |  | 156270.8211 |  | 168835.5627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-19 | 1058218.706 |  | 555845.0587 |  | 156590.4702 |  | 168877.2206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-20 | 1059868.0898 |  | 557133.1355 |  | 156910.1193 |  | 168918.8785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-21 | 1061517.4736 |  | 558421.2123 |  | 157229.7684 |  | 168960.5364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-22 | 1063166.8575 |  | 559709.2891 |  | 157549.4175 |  | 169002.1943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-23 | 1064816.2413 |  | 560997.3659 |  | 157869.0667 |  | 169043.8522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-24 | 1066465.6251 |  | 562285.4428 |  | 158188.7158 |  | 169085.5101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-25 | 1068115.009 |  | 563573.5196 |  | 158508.3649 |  | 169127.168 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-26 | 1069764.3928 |  | 564861.5964 |  | 158828.014 |  | 169168.8259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-27 | 1071413.7766 |  | 566149.6732 |  | 159147.6632 |  | 169210.4838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-28 | 1073063.1605 |  | 567437.75 |  | 159467.3123 |  | 169252.1416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-29 | 1074712.5443 |  | 568725.8269 |  | 159786.9614 |  | 169293.7995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-30 | 1076361.9282 |  | 570013.9037 |  | 160106.6105 |  | 169335.4574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-01 | 1078011.312 |  | 571301.9805 |  | 160426.2596 |  | 169377.1153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-02 | 1079660.6958 |  | 572590.0573 |  | 160745.9088 |  | 169418.7732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-03 | 1081310.0797 |  | 573878.1341 |  | 161065.5579 |  | 169460.4311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-04 | 1082959.4635 |  | 575166.2109 |  | 161385.207 |  | 169502.089 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-05 | 1084608.8473 |  | 576454.2878 |  | 161704.8561 |  | 169543.7469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-06 | 1086258.2312 |  | 577742.3646 |  | 162024.5053 |  | 169585.4048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-07 | 1087907.615 |  | 579030.4414 |  | 162344.1544 |  | 169627.0627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-08 | 1089556.9988 |  | 580318.5182 |  | 162663.8035 |  | 169668.7206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-09 | 1091206.3827 |  | 581606.595 |  | 162983.4526 |  | 169710.3785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-10 | 1092855.7665 |  | 582894.6719 |  | 163303.1018 |  | 169752.0364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-11 | 1094505.1503 |  | 584182.7487 |  | 163622.7509 |  | 169793.6943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-12 | 1096154.5342 |  | 585470.8255 |  | 163942.4 |  | 169835.3522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-13 | 1097803.918 |  | 586758.9023 |  | 164262.0491 |  | 169877.0101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-14 | 1099453.3019 |  | 588046.9791 |  | 164581.6982 |  | 169918.668 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-15 | 1101102.6857 |  | 589335.0559 |  | 164901.3474 |  | 169960.3259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-16 | 1102752.0695 |  | 590623.1328 |  | 165220.9965 |  | 170001.9838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-17 | 1104401.4534 |  | 591911.2096 |  | 165540.6456 |  | 170043.6416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-18 | 1106050.8372 |  | 593199.2864 |  | 165860.2947 |  | 170085.2995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-19 | 1107700.221 |  | 594487.3632 |  | 166179.9439 |  | 170126.9574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-20 | 1109349.6049 |  | 595775.44 |  | 166499.593 |  | 170168.6153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-21 | 1110998.9887 |  | 597063.5169 |  | 166819.2421 |  | 170210.2732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-22 | 1112648.3725 |  | 598351.5937 |  | 167138.8912 |  | 170251.9311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-23 | 1114297.7564 |  | 599639.6705 |  | 167458.5404 |  | 170293.589 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-24 | 1115947.1402 |  | 600927.7473 |  | 167778.1895 |  | 170335.2469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-25 | 1117596.524 |  | 602215.8241 |  | 168097.8386 |  | 170376.9048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-26 | 1119245.9079 |  | 603503.9009 |  | 168417.4877 |  | 170418.5627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-27 | 1120895.2917 |  | 604791.9778 |  | 168737.1368 |  | 170460.2206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-28 | 1122544.6756 |  | 606080.0546 |  | 169056.786 |  | 170501.8785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-29 | 1124194.0594 |  | 607368.1314 |  | 169376.4351 |  | 170543.5364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-30 | 1125843.4432 |  | 608656.2082 |  | 169696.0842 |  | 170585.1943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-31 | 1127492.8271 |  | 609944.285 |  | 170015.7333 |  | 170626.8522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-01 | 1129142.2109 |  | 611232.3619 |  | 170335.3825 |  | 170668.5101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-02 | 1130791.5947 |  | 612520.4387 |  | 170655.0316 |  | 170710.168 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-03 | 1132440.9786 |  | 613808.5155 |  | 170974.6807 |  | 170751.8259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-04 | 1134090.3624 |  | 615096.5923 |  | 171294.3298 |  | 170793.4838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-05 | 1135739.7462 |  | 616384.6691 |  | 171613.9789 |  | 170835.1416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-06 | 1137389.1301 |  | 617672.7459 |  | 171933.6281 |  | 170876.7995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-07 | 1139038.5139 |  | 618960.8228 |  | 172253.2772 |  | 170918.4574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-08 | 1140687.8977 |  | 620248.8996 |  | 172572.9263 |  | 170960.1153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-09 | 1142337.2816 |  | 621536.9764 |  | 172892.5754 |  | 171001.7732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-10 | 1143986.6654 |  | 622825.0532 |  | 173212.2246 |  | 171043.4311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-11 | 1145636.0493 |  | 624113.13 |  | 173531.8737 |  | 171085.089 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-12 | 1147285.4331 |  | 625401.2069 |  | 173851.5228 |  | 171126.7469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-13 | 1148934.8169 |  | 626689.2837 |  | 174171.1719 |  | 171168.4048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-14 | 1150584.2008 |  | 627977.3605 |  | 174490.8211 |  | 171210.0627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-15 | 1152233.5846 |  | 629265.4373 |  | 174810.4702 |  | 171251.7206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-16 | 1153882.9684 |  | 630553.5141 |  | 175130.1193 |  | 171293.3785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-17 | 1155532.3523 |  | 631841.5909 |  | 175449.7684 |  | 171335.0364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-18 | 1157181.7361 |  | 633129.6678 |  | 175769.4175 |  | 171376.6943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-19 | 1158831.1199 |  | 634417.7446 |  | 176089.0667 |  | 171418.3522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-20 | 1160741.7237 |  | 635598.4464 |  | 176524.851 |  | 171418.3522 |  | 38556.7263 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-08-21 | 1162652.3274 |  | 636779.1481 |  | 176960.6353 |  | 171418.3522 |  | 38850.844 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-08-22 | 1164562.9312 |  | 637959.8499 |  | 177396.4196 |  | 171418.3522 |  | 39144.9616 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-08-23 | 1166473.5349 |  | 639140.5517 |  | 177832.2039 |  | 171418.3522 |  | 39439.0793 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-08-24 | 1168384.1386 |  | 640321.2535 |  | 178267.9882 |  | 171418.3522 |  | 39733.1969 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-08-25 | 1170294.7424 |  | 641501.9552 |  | 178703.7725 |  | 171418.3522 |  | 40027.3146 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-08-26 | 1172205.3461 |  | 642682.657 |  | 179139.5569 |  | 171418.3522 |  | 40321.4322 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-08-27 | 1174115.9498 |  | 643863.3588 |  | 179575.3412 |  | 171418.3522 |  | 40615.5499 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-08-28 | 1176026.5536 |  | 645044.0606 |  | 180011.1255 |  | 171418.3522 |  | 40909.6675 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-08-29 | 1177937.1573 |  | 646224.7623 |  | 180446.9098 |  | 171418.3522 |  | 41203.7852 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-08-30 | 1179847.761 |  | 647405.4641 |  | 180882.6941 |  | 171418.3522 |  | 41497.9028 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-08-31 | 1181758.3648 |  | 648586.1659 |  | 181318.4784 |  | 171418.3522 |  | 41792.0205 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-01 | 1183668.9685 |  | 649766.8677 |  | 181754.2627 |  | 171418.3522 |  | 42086.1381 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-02 | 1185579.5723 |  | 650947.5694 |  | 182190.0471 |  | 171418.3522 |  | 42380.2558 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-03 | 1187490.176 |  | 652128.2712 |  | 182625.8314 |  | 171418.3522 |  | 42674.3734 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-04 | 1189400.7797 |  | 653308.973 |  | 183061.6157 |  | 171418.3522 |  | 42968.491 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-05 | 1191311.3835 |  | 654489.6748 |  | 183497.4 |  | 171418.3522 |  | 43262.6087 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-06 | 1193221.9872 |  | 655670.3766 |  | 183933.1843 |  | 171418.3522 |  | 43556.7263 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-07 | 1195132.5909 |  | 656851.0783 |  | 184368.9686 |  | 171418.3522 |  | 43850.844 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-08 | 1197043.1947 |  | 658031.7801 |  | 184804.7529 |  | 171418.3522 |  | 44144.9616 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-09 | 1198953.7984 |  | 659212.4819 |  | 185240.5373 |  | 171418.3522 |  | 44439.0793 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-10 | 1200864.4022 |  | 660393.1837 |  | 185676.3216 |  | 171418.3522 |  | 44733.1969 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-11 | 1202775.0059 |  | 661573.8854 |  | 186112.1059 |  | 171418.3522 |  | 45027.3146 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-12 | 1204685.6096 |  | 662754.5872 |  | 186547.8902 |  | 171418.3522 |  | 45321.4322 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-13 | 1206596.2134 |  | 663935.289 |  | 186983.6745 |  | 171418.3522 |  | 45615.5499 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-14 | 1208506.8171 |  | 665115.9908 |  | 187419.4588 |  | 171418.3522 |  | 45909.6675 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-15 | 1210417.4208 |  | 666296.6925 |  | 187855.2431 |  | 171418.3522 |  | 46203.7852 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-16 | 1212328.0246 |  | 667477.3943 |  | 188291.0275 |  | 171418.3522 |  | 46497.9028 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-17 | 1214238.6283 |  | 668658.0961 |  | 188726.8118 |  | 171418.3522 |  | 46792.0205 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-18 | 1216149.2321 |  | 669838.7979 |  | 189162.5961 |  | 171418.3522 |  | 47086.1381 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-19 | 1218059.8358 |  | 671019.4996 |  | 189598.3804 |  | 171418.3522 |  | 47380.2558 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-20 | 1219970.4395 |  | 672200.2014 |  | 190034.1647 |  | 171418.3522 |  | 47674.3734 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-21 | 1221881.0433 |  | 673380.9032 |  | 190469.949 |  | 171418.3522 |  | 47968.491 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0
2026-09-22 | 1223791.647 |  | 674561.605 |  | 190905.7333 |  | 171418.3522 |  | 48262.6087 |  | 138643.3478 |  | 1910.6037 |  | 1180.7018 |  | 435.7843 |  | 0 |  | 294.1176 |  | 0

## Labor Cost
Date | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned 5101 · Salary and wages (Direct) (Cumulative) | Actual 5101 · Salary and wages (Direct) (Cumulative) | Planned 5102 · Payroll taxes (Direct) (Cumulative) | Actual 5102 · Payroll taxes (Direct) (Cumulative)
2025-04-02 | 957.1429 | 0 | 957.1429 | 0 | 0 | 0
2025-04-03 | 1914.2857 | 0 | 1914.2857 | 0 | 0 | 0
2025-04-04 | 2871.4286 | 0 | 2871.4286 | 0 | 0 | 0
2025-04-05 | 3828.5714 | 0 | 3828.5714 | 0 | 0 | 0
2025-04-06 | 4785.7143 | 0 | 4785.7143 | 0 | 0 | 0
2025-04-07 | 5742.8571 | 1126.6 | 5742.8571 | 1126.6 | 0 | 1126.6
2025-04-08 | 6700 | 2253.2 | 6700 | 2253.2 | 0 | 2253.2
2025-04-09 | 7657.1429 | 3379.8 | 7657.1429 | 3379.8 | 0 | 3379.8
2025-04-10 | 8614.2857 | 4506.4 | 8614.2857 | 4506.4 | 0 | 4506.4
2025-04-11 | 9571.4286 | 5633 | 9571.4286 | 5633 | 0 | 5633
2025-04-12 | 10528.5714 | 5633 | 10528.5714 | 5633 | 0 | 5633
2025-04-13 | 11485.7143 | 5633 | 11485.7143 | 5633 | 0 | 5633
2025-04-14 | 12442.8571 | 5847.4 | 12442.8571 | 5847.4 | 0 | 5847.4
2025-04-15 | 13400 | 6061.8 | 13400 | 6061.8 | 0 | 6061.8
2025-04-16 | 14357.1429 | 6276.2 | 14357.1429 | 6276.2 | 0 | 6276.2
2025-04-17 | 15314.2857 | 6490.6 | 15314.2857 | 6490.6 | 0 | 6490.6
2025-04-18 | 16271.4286 | 6705 | 16271.4286 | 6705 | 0 | 6705
2025-04-19 | 17228.5714 | 6705 | 17228.5714 | 6705 | 0 | 6705
2025-04-20 | 18185.7143 | 6705 | 18185.7143 | 6705 | 0 | 6705
2025-04-21 | 19142.8571 | 7087.15 | 19142.8571 | 7087.15 | 0 | 7087.15
2025-04-22 | 20100 | 7469.3 | 20100 | 7469.3 | 0 | 7469.3
2025-04-23 | 21057.1429 | 7851.45 | 21057.1429 | 7851.45 | 0 | 7851.45
2025-04-24 | 22014.2857 | 8233.6 | 22014.2857 | 8233.6 | 0 | 8233.6
2025-04-25 | 22971.4286 | 8615.75 | 22971.4286 | 8615.75 | 0 | 8615.75
2025-04-26 | 23928.5714 | 8615.75 | 23928.5714 | 8615.75 | 0 | 8615.75
2025-04-27 | 24885.7143 | 8615.75 | 24885.7143 | 8615.75 | 0 | 8615.75
2025-04-28 | 25842.8571 | 8615.75 | 25842.8571 | 8615.75 | 0 | 8615.75
2025-04-29 | 26800 | 8615.75 | 26800 | 8615.75 | 0 | 8615.75
2025-04-30 | 27757.1429 | 8615.75 | 27757.1429 | 8615.75 | 0 | 8615.75
2025-05-01 | 28714.2857 | 8615.75 | 28714.2857 | 8615.75 | 0 | 8615.75
2025-05-02 | 29671.4286 | 8615.75 | 29671.4286 | 8615.75 | 0 | 8615.75
2025-05-03 | 30628.5714 | 8615.75 | 30628.5714 | 8615.75 | 0 | 8615.75
2025-05-04 | 31585.7143 | 8615.75 | 31585.7143 | 8615.75 | 0 | 8615.75
2025-05-05 | 32542.8571 | 8615.75 | 32542.8571 | 8615.75 | 0 | 8615.75
2025-05-06 | 33500 | 8615.75 | 33500 | 8615.75 | 0 | 8615.75
2025-05-07 | 34457.1429 | 8615.75 | 34457.1429 | 8615.75 | 0 | 8615.75
2025-05-08 | 35414.2857 | 8615.75 | 35414.2857 | 8615.75 | 0 | 8615.75
2025-05-09 | 36371.4286 | 8615.75 | 36371.4286 | 8615.75 | 0 | 8615.75
2025-05-10 | 37328.5714 | 8615.75 | 37328.5714 | 8615.75 | 0 | 8615.75
2025-05-11 | 38285.7143 | 8615.75 | 38285.7143 | 8615.75 | 0 | 8615.75
2025-05-12 | 39242.8571 | 8615.75 | 39242.8571 | 8615.75 | 0 | 8615.75
2025-05-13 | 40200 | 8615.75 | 40200 | 8615.75 | 0 | 8615.75
2025-05-14 | 41157.1429 | 8615.75 | 41157.1429 | 8615.75 | 0 | 8615.75
2025-05-15 | 42114.2857 | 8615.75 | 42114.2857 | 8615.75 | 0 | 8615.75
2025-05-16 | 43071.4286 | 8615.75 | 43071.4286 | 8615.75 | 0 | 8615.75
2025-05-17 | 44028.5714 | 8615.75 | 44028.5714 | 8615.75 | 0 | 8615.75
2025-05-18 | 44985.7143 | 8615.75 | 44985.7143 | 8615.75 | 0 | 8615.75
2025-05-19 | 45942.8571 | 8615.75 | 45942.8571 | 8615.75 | 0 | 8615.75
2025-05-20 | 46900 | 8615.75 | 46900 | 8615.75 | 0 | 8615.75
2025-05-21 | 47857.1429 | 8615.75 | 47857.1429 | 8615.75 | 0 | 8615.75
2025-05-22 | 48814.2857 | 8615.75 | 48814.2857 | 8615.75 | 0 | 8615.75
2025-05-23 | 49771.4286 | 8615.75 | 49771.4286 | 8615.75 | 0 | 8615.75
2025-05-24 | 50728.5714 | 8615.75 | 50728.5714 | 8615.75 | 0 | 8615.75
2025-05-25 | 51685.7143 | 8615.75 | 51685.7143 | 8615.75 | 0 | 8615.75
2025-05-26 | 52642.8571 | 8615.75 | 52642.8571 | 8615.75 | 0 | 8615.75
2025-05-27 | 53600 | 8615.75 | 53600 | 8615.75 | 0 | 8615.75
2025-05-28 | 54557.1429 | 8615.75 | 54557.1429 | 8615.75 | 0 | 8615.75
2025-05-29 | 55514.2857 | 8615.75 | 55514.2857 | 8615.75 | 0 | 8615.75
2025-05-30 | 56471.4286 | 8615.75 | 56471.4286 | 8615.75 | 0 | 8615.75
2025-05-31 | 57428.5714 | 8615.75 | 57428.5714 | 8615.75 | 0 | 8615.75
2025-06-01 | 58385.7143 | 8615.75 | 58385.7143 | 8615.75 | 0 | 8615.75
2025-06-02 | 59342.8571 | 9044.55 | 59342.8571 | 9044.55 | 0 | 9044.55
2025-06-03 | 60300 | 9473.35 | 60300 | 9473.35 | 0 | 9473.35
2025-06-04 | 61257.1429 | 9902.15 | 61257.1429 | 9902.15 | 0 | 9902.15
2025-06-05 | 62214.2857 | 10330.95 | 62214.2857 | 10330.95 | 0 | 10330.95
2025-06-06 | 63171.4286 | 10759.75 | 63171.4286 | 10759.75 | 0 | 10759.75
2025-06-07 | 64128.5714 | 10759.75 | 64128.5714 | 10759.75 | 0 | 10759.75
2025-06-08 | 65085.7143 | 10759.75 | 65085.7143 | 10759.75 | 0 | 10759.75
2025-06-09 | 66042.8571 | 10866.95 | 66042.8571 | 10866.95 | 0 | 10866.95
2025-06-10 | 67000 | 10974.15 | 67000 | 10974.15 | 0 | 10974.15
2025-06-11 | 67957.1429 | 11081.35 | 67957.1429 | 11081.35 | 0 | 11081.35
2025-06-12 | 68914.2857 | 11188.55 | 68914.2857 | 11188.55 | 0 | 11188.55
2025-06-13 | 69871.4286 | 11295.75 | 69871.4286 | 11295.75 | 0 | 11295.75
2025-06-14 | 70828.5714 | 11295.75 | 70828.5714 | 11295.75 | 0 | 11295.75
2025-06-15 | 71785.7143 | 11295.75 | 71785.7143 | 11295.75 | 0 | 11295.75
2025-06-16 | 72742.8571 | 11677.9 | 72742.8571 | 11677.9 | 0 | 11677.9
2025-06-17 | 73700 | 12060.05 | 73700 | 12060.05 | 0 | 12060.05
2025-06-18 | 74657.1429 | 12442.2 | 74657.1429 | 12442.2 | 0 | 12442.2
2025-06-19 | 75614.2857 | 12824.35 | 75614.2857 | 12824.35 | 0 | 12824.35
2025-06-20 | 76571.4286 | 13206.5 | 76571.4286 | 13206.5 | 0 | 13206.5
2025-06-21 | 77528.5714 | 13206.5 | 77528.5714 | 13206.5 | 0 | 13206.5
2025-06-22 | 78485.7143 | 13206.5 | 78485.7143 | 13206.5 | 0 | 13206.5
2025-06-23 | 79442.8571 | 13313.7 | 79442.8571 | 13313.7 | 0 | 13313.7
2025-06-24 | 80400 | 13420.9 | 80400 | 13420.9 | 0 | 13420.9
2025-06-25 | 80520.2088 | 13528.1 | 80520.2088 | 13528.1 | 0 | 13528.1
2025-06-26 | 80640.4175 | 13635.3 | 80640.4175 | 13635.3 | 0 | 13635.3
2025-06-27 | 80760.6263 | 13742.5 | 80760.6263 | 13742.5 | 0 | 13742.5
2025-06-28 | 80880.8351 | 13742.5 | 80880.8351 | 13742.5 | 0 | 13742.5
2025-06-29 | 81001.0439 | 13742.5 | 81001.0439 | 13742.5 | 0 | 13742.5
2025-06-30 | 81121.2526 | 14191.65 | 81121.2526 | 14191.65 | 0 | 14191.65
2025-07-01 | 81241.4614 | 14640.8 | 81241.4614 | 14640.8 | 0 | 14640.8
2025-07-02 | 81361.6702 | 15089.95 | 81361.6702 | 15089.95 | 0 | 15089.95
2025-07-03 | 81481.8789 | 15539.1 | 81481.8789 | 15539.1 | 0 | 15539.1
2025-07-04 | 81602.0877 | 15988.25 | 81602.0877 | 15988.25 | 0 | 15988.25
2025-07-05 | 81722.2965 | 15988.25 | 81722.2965 | 15988.25 | 0 | 15988.25
2025-07-06 | 81842.5053 | 15988.25 | 81842.5053 | 15988.25 | 0 | 15988.25
2025-07-07 | 81962.714 | 16390.25 | 81962.714 | 16390.25 | 0 | 16390.25
2025-07-08 | 82082.9228 | 16792.25 | 82082.9228 | 16792.25 | 0 | 16792.25
2025-07-09 | 82203.1316 | 17194.25 | 82203.1316 | 17194.25 | 0 | 17194.25
2025-07-10 | 82323.3403 | 17596.25 | 82323.3403 | 17596.25 | 0 | 17596.25
2025-07-11 | 82443.5491 | 17998.25 | 82443.5491 | 17998.25 | 0 | 17998.25
2025-07-12 | 82563.7579 | 17998.25 | 82563.7579 | 17998.25 | 0 | 17998.25
2025-07-13 | 82683.9667 | 17998.25 | 82683.9667 | 17998.25 | 0 | 17998.25
2025-07-14 | 82804.1754 | 18400.25 | 82804.1754 | 18400.25 | 0 | 18400.25
2025-07-15 | 82924.3842 | 18802.25 | 82924.3842 | 18802.25 | 0 | 18802.25
2025-07-16 | 83044.593 | 19204.25 | 83044.593 | 19204.25 | 0 | 19204.25
2025-07-17 | 83164.8017 | 19606.25 | 83164.8017 | 19606.25 | 0 | 19606.25
2025-07-18 | 83285.0105 | 20008.25 | 83285.0105 | 20008.25 | 0 | 20008.25
2025-07-19 | 83405.2193 | 20008.25 | 83405.2193 | 20008.25 | 0 | 20008.25
2025-07-20 | 83525.4281 | 20008.25 | 83525.4281 | 20008.25 | 0 | 20008.25
2025-07-21 | 83645.6368 | 20410.25 | 83645.6368 | 20410.25 | 0 | 20410.25
2025-07-22 | 83765.8456 | 20812.25 | 83765.8456 | 20812.25 | 0 | 20812.25
2025-07-23 | 83886.0544 | 21214.25 | 83886.0544 | 21214.25 | 0 | 21214.25
2025-07-24 | 84006.2631 | 21616.25 | 84006.2631 | 21616.25 | 0 | 21616.25
2025-07-25 | 84126.4719 | 22018.25 | 84126.4719 | 22018.25 | 0 | 22018.25
2025-07-26 | 84246.6807 | 22018.25 | 84246.6807 | 22018.25 | 0 | 22018.25
2025-07-27 | 84366.8895 | 22018.25 | 84366.8895 | 22018.25 | 0 | 22018.25
2025-07-28 | 84487.0982 | 22366.65 | 84487.0982 | 22366.65 | 0 | 22366.65
2025-07-29 | 84607.307 | 22715.05 | 84607.307 | 22715.05 | 0 | 22715.05
2025-07-30 | 84727.5158 | 23063.45 | 84727.5158 | 23063.45 | 0 | 23063.45
2025-07-31 | 84847.7245 | 23411.85 | 84847.7245 | 23411.85 | 0 | 23411.85
2025-08-01 | 84967.9333 | 23760.25 | 84967.9333 | 23760.25 | 0 | 23760.25
2025-08-02 | 85088.1421 | 23760.25 | 85088.1421 | 23760.25 | 0 | 23760.25
2025-08-03 | 85208.3509 | 23760.25 | 85208.3509 | 23760.25 | 0 | 23760.25
2025-08-04 | 85328.5596 | 24028.25 | 85328.5596 | 24028.25 | 0 | 24028.25
2025-08-05 | 85448.7684 | 24296.25 | 85448.7684 | 24296.25 | 0 | 24296.25
2025-08-06 | 85568.9772 | 24564.25 | 85568.9772 | 24564.25 | 0 | 24564.25
2025-08-07 | 85689.1859 | 24832.25 | 85689.1859 | 24832.25 | 0 | 24832.25
2025-08-08 | 85809.3947 | 25100.25 | 85809.3947 | 25100.25 | 0 | 25100.25
2025-08-09 | 85929.6035 | 25100.25 | 85929.6035 | 25100.25 | 0 | 25100.25
2025-08-10 | 86049.8123 | 25100.25 | 86049.8123 | 25100.25 | 0 | 25100.25
2025-08-11 | 86170.021 | 25314.65 | 86170.021 | 25314.65 | 0 | 25314.65
2025-08-12 | 86290.2298 | 25529.05 | 86290.2298 | 25529.05 | 0 | 25529.05
2025-08-13 | 86410.4386 | 25743.45 | 86410.4386 | 25743.45 | 0 | 25743.45
2025-08-14 | 86530.6473 | 25957.85 | 86530.6473 | 25957.85 | 0 | 25957.85
2025-08-15 | 86650.8561 | 26172.25 | 86650.8561 | 26172.25 | 0 | 26172.25
2025-08-16 | 86771.0649 | 26172.25 | 86771.0649 | 26172.25 | 0 | 26172.25
2025-08-17 | 86891.2736 | 26172.25 | 86891.2736 | 26172.25 | 0 | 26172.25
2025-08-18 | 87011.4824 | 26708.25 | 87011.4824 | 26708.25 | 0 | 26708.25
2025-08-19 | 87131.6912 | 27244.25 | 87131.6912 | 27244.25 | 0 | 27244.25
2025-08-20 | 87251.9 | 27780.25 | 87251.9 | 27780.25 | 0 | 27780.25
2025-08-21 | 87372.1087 | 28316.25 | 87372.1087 | 28316.25 | 0 | 28316.25
2025-08-22 | 87492.3175 | 28852.25 | 87492.3175 | 28852.25 | 0 | 28852.25
2025-08-23 | 87612.5263 | 28852.25 | 87612.5263 | 28852.25 | 0 | 28852.25
2025-08-24 | 87732.735 | 28852.25 | 87732.735 | 28852.25 | 0 | 28852.25
2025-08-25 | 87852.9438 | 29952.05 | 87852.9438 | 29952.05 | 0 | 29952.05
2025-08-26 | 87973.1526 | 31051.85 | 87973.1526 | 31051.85 | 0 | 31051.85
2025-08-27 | 88093.3614 | 32151.65 | 88093.3614 | 32151.65 | 0 | 32151.65
2025-08-28 | 88213.5701 | 33251.45 | 88213.5701 | 33251.45 | 0 | 33251.45
2025-08-29 | 88333.7789 | 34351.25 | 88333.7789 | 34351.25 | 0 | 34351.25
2025-08-30 | 88453.9877 | 34351.25 | 88453.9877 | 34351.25 | 0 | 34351.25
2025-08-31 | 88574.1964 | 34351.25 | 88574.1964 | 34351.25 | 0 | 34351.25
2025-09-01 | 88694.4052 | 35095.2 | 88694.4052 | 35095.2 | 0 | 35095.2
2025-09-02 | 88814.614 | 35839.15 | 88814.614 | 35839.15 | 0 | 35839.15
2025-09-03 | 88934.8228 | 36583.1 | 88934.8228 | 36583.1 | 0 | 36583.1
2025-09-04 | 89055.0315 | 37327.05 | 89055.0315 | 37327.05 | 0 | 37327.05
2025-09-05 | 89175.2403 | 38071 | 89175.2403 | 38071 | 0 | 38071
2025-09-06 | 89295.4491 | 38071 | 89295.4491 | 38071 | 0 | 38071
2025-09-07 | 89415.6578 | 38071 | 89415.6578 | 38071 | 0 | 38071
2025-09-08 | 89535.8666 | 38573.75 | 89535.8666 | 38573.75 | 0 | 38573.75
2025-09-09 | 89656.0754 | 39076.5 | 89656.0754 | 39076.5 | 0 | 39076.5
2025-09-10 | 89776.2842 | 39579.25 | 89776.2842 | 39579.25 | 0 | 39579.25
2025-09-11 | 89896.4929 | 40082 | 89896.4929 | 40082 | 0 | 40082
2025-09-12 | 90016.7017 | 40584.75 | 90016.7017 | 40584.75 | 0 | 40584.75
2025-09-13 | 90136.9105 | 40584.75 | 90136.9105 | 40584.75 | 0 | 40584.75
2025-09-14 | 90257.1192 | 40584.75 | 90257.1192 | 40584.75 | 0 | 40584.75
2025-09-15 | 90377.328 | 42546.625 | 90377.328 | 42546.625 | 0 | 42546.625
2025-09-16 | 90497.5368 | 44508.5 | 90497.5368 | 44508.5 | 0 | 44508.5
2025-09-17 | 90617.7456 | 46470.375 | 90617.7456 | 46470.375 | 0 | 46470.375
2025-09-18 | 90737.9543 | 48432.25 | 90737.9543 | 48432.25 | 0 | 48432.25
2025-09-19 | 90858.1631 | 50394.125 | 90858.1631 | 50394.125 | 0 | 50394.125
2025-09-20 | 90978.3719 | 50394.125 | 90978.3719 | 50394.125 | 0 | 50394.125
2025-09-21 | 91098.5806 | 50394.125 | 91098.5806 | 50394.125 | 0 | 50394.125
2025-09-22 | 91098.5806 | 51446.2 | 91098.5806 | 51446.2 | 0 | 51446.2
2025-09-23 | 91098.5806 | 52498.275 | 91098.5806 | 52498.275 | 0 | 52498.275
2025-09-24 | 91098.5806 | 53550.35 | 91098.5806 | 53550.35 | 0 | 53550.35
2025-09-25 | 91098.5806 | 54602.425 | 91098.5806 | 54602.425 | 0 | 54602.425
2025-09-26 | 91098.5806 | 55654.5 | 91098.5806 | 55654.5 | 0 | 55654.5
2025-09-27 | 91098.5806 | 55654.5 | 91098.5806 | 55654.5 | 0 | 55654.5
2025-09-28 | 91098.5806 | 55654.5 | 91098.5806 | 55654.5 | 0 | 55654.5
2025-09-29 | 94401.4769 | 56981.625 | 94401.4769 | 56981.625 | 0 | 56981.625
2025-09-30 | 97704.3732 | 58308.75 | 97704.3732 | 58308.75 | 0 | 58308.75
2025-10-01 | 101007.2694 | 59635.875 | 101007.2694 | 59635.875 | 0 | 59635.875
2025-10-02 | 104310.1657 | 60963 | 104310.1657 | 60963 | 0 | 60963
2025-10-03 | 107613.062 | 62290.125 | 107613.062 | 62290.125 | 0 | 62290.125
2025-10-04 | 110915.9583 | 62290.125 | 110915.9583 | 62290.125 | 0 | 62290.125
2025-10-05 | 114218.8545 | 62290.125 | 114218.8545 | 62290.125 | 0 | 62290.125
2025-10-06 | 117521.7508 | 63946.875 | 117521.7508 | 63946.875 | 0 | 63946.875
2025-10-07 | 120824.6471 | 65603.625 | 120824.6471 | 65603.625 | 0 | 65603.625
2025-10-08 | 124127.5433 | 67260.375 | 124127.5433 | 67260.375 | 0 | 67260.375
2025-10-09 | 127430.4396 | 68917.125 | 127430.4396 | 68917.125 | 0 | 68917.125
2025-10-10 | 130733.3359 | 70573.875 | 130733.3359 | 70573.875 | 0 | 70573.875
2025-10-11 | 134036.2321 | 70573.875 | 134036.2321 | 70573.875 | 0 | 70573.875
2025-10-12 | 137339.1284 | 70573.875 | 137339.1284 | 70573.875 | 0 | 70573.875
2025-10-13 | 140642.0247 | 70754.825 | 140642.0247 | 70754.825 | 0 | 70754.825
2025-10-14 | 143944.9209 | 70935.775 | 143944.9209 | 70935.775 | 0 | 70935.775
2025-10-15 | 147247.8172 | 71116.725 | 147247.8172 | 71116.725 | 0 | 71116.725
2025-10-16 | 150550.7135 | 71297.675 | 150550.7135 | 71297.675 | 0 | 71297.675
2025-10-17 | 153853.6097 | 71478.625 | 153853.6097 | 71478.625 | 0 | 71478.625
2025-10-18 | 157156.506 | 71478.625 | 157156.506 | 71478.625 | 0 | 71478.625
2025-10-19 | 160459.4023 | 71478.625 | 160459.4023 | 71478.625 | 0 | 71478.625
2025-10-20 | 163762.2985 | 71579.175 | 163762.2985 | 71579.175 | 0 | 71579.175
2025-10-21 | 167065.1948 | 71679.725 | 167065.1948 | 71679.725 | 0 | 71679.725
2025-10-22 | 170368.0911 | 71780.275 | 170368.0911 | 71780.275 | 0 | 71780.275
2025-10-23 | 173670.9873 | 71880.825 | 173670.9873 | 71880.825 | 0 | 71880.825
2025-10-24 | 176973.8836 | 71981.375 | 176973.8836 | 71981.375 | 0 | 71981.375
2025-10-25 | 180276.7799 | 71981.375 | 180276.7799 | 71981.375 | 0 | 71981.375
2025-10-26 | 183579.6762 | 71981.375 | 183579.6762 | 71981.375 | 0 | 71981.375
2025-10-27 | 186882.5724 |  | 186882.5724 |  | 0
2025-10-28 | 190185.4687 |  | 190185.4687 |  | 0
2025-10-29 | 193488.365 |  | 193488.365 |  | 0
2025-10-30 | 196791.2612 |  | 196791.2612 |  | 0
2025-10-31 | 200094.1575 |  | 200094.1575 |  | 0
2025-11-01 | 203397.0538 |  | 203397.0538 |  | 0
2025-11-02 | 206699.95 |  | 206699.95 |  | 0
2025-11-03 | 210002.8463 |  | 210002.8463 |  | 0
2025-11-04 | 213305.7426 |  | 213305.7426 |  | 0
2025-11-05 | 216608.6388 |  | 216608.6388 |  | 0
2025-11-06 | 219911.5351 |  | 219911.5351 |  | 0
2025-11-07 | 223214.4314 |  | 223214.4314 |  | 0
2025-11-08 | 226517.3276 |  | 226517.3276 |  | 0
2025-11-09 | 229820.2239 |  | 229820.2239 |  | 0
2025-11-10 | 233123.1202 |  | 233123.1202 |  | 0
2025-11-11 | 236426.0164 |  | 236426.0164 |  | 0
2025-11-12 | 239728.9127 |  | 239728.9127 |  | 0
2025-11-13 | 243031.809 |  | 243031.809 |  | 0
2025-11-14 | 246334.7052 |  | 246334.7052 |  | 0
2025-11-15 | 249637.6015 |  | 249637.6015 |  | 0
2025-11-16 | 252940.4978 |  | 252940.4978 |  | 0
2025-11-17 | 256243.3941 |  | 256243.3941 |  | 0
2025-11-18 | 259546.2903 |  | 259546.2903 |  | 0
2025-11-19 | 261095.5386 |  | 261095.5386 |  | 0
2025-11-20 | 262644.787 |  | 262644.787 |  | 0
2025-11-21 | 264194.0353 |  | 264194.0353 |  | 0
2025-11-22 | 265743.2836 |  | 265743.2836 |  | 0
2025-11-23 | 267292.5319 |  | 267292.5319 |  | 0
2025-11-24 | 268841.7802 |  | 268841.7802 |  | 0
2025-11-25 | 270391.0286 |  | 270391.0286 |  | 0
2025-11-26 | 271940.2769 |  | 271940.2769 |  | 0
2025-11-27 | 273489.5252 |  | 273489.5252 |  | 0
2025-11-28 | 275038.7735 |  | 275038.7735 |  | 0
2025-11-29 | 276588.0218 |  | 276588.0218 |  | 0
2025-11-30 | 278137.2702 |  | 278137.2702 |  | 0
2025-12-01 | 279686.5185 |  | 279686.5185 |  | 0
2025-12-02 | 281235.7668 |  | 281235.7668 |  | 0
2025-12-03 | 282785.0151 |  | 282785.0151 |  | 0
2025-12-04 | 284334.2634 |  | 284334.2634 |  | 0
2025-12-05 | 285883.5117 |  | 285883.5117 |  | 0
2025-12-06 | 287432.7601 |  | 287432.7601 |  | 0
2025-12-07 | 288982.0084 |  | 288982.0084 |  | 0
2025-12-08 | 290531.2567 |  | 290531.2567 |  | 0
2025-12-09 | 292080.505 |  | 292080.505 |  | 0
2025-12-10 | 293629.7533 |  | 293629.7533 |  | 0
2025-12-11 | 295179.0017 |  | 295179.0017 |  | 0
2025-12-12 | 296728.25 |  | 296728.25 |  | 0
2025-12-13 | 298277.4983 |  | 298277.4983 |  | 0
2025-12-14 | 299826.7466 |  | 299826.7466 |  | 0
2025-12-15 | 301375.9949 |  | 301375.9949 |  | 0
2025-12-16 | 302925.2433 |  | 302925.2433 |  | 0
2025-12-17 | 304474.4916 |  | 304474.4916 |  | 0
2025-12-18 | 306023.7399 |  | 306023.7399 |  | 0
2025-12-19 | 307572.9882 |  | 307572.9882 |  | 0
2025-12-20 | 309122.2365 |  | 309122.2365 |  | 0
2025-12-21 | 310671.4849 |  | 310671.4849 |  | 0
2025-12-22 | 312220.7332 |  | 312220.7332 |  | 0
2025-12-23 | 313769.9815 |  | 313769.9815 |  | 0
2025-12-24 | 315319.2298 |  | 315319.2298 |  | 0
2025-12-25 | 316868.4781 |  | 316868.4781 |  | 0
2025-12-26 | 318417.7264 |  | 318417.7264 |  | 0
2025-12-27 | 319966.9748 |  | 319966.9748 |  | 0
2025-12-28 | 321516.2231 |  | 321516.2231 |  | 0
2025-12-29 | 323065.4714 |  | 323065.4714 |  | 0
2025-12-30 | 324614.7197 |  | 324614.7197 |  | 0
2025-12-31 | 326163.968 |  | 326163.968 |  | 0
2026-01-01 | 327713.2164 |  | 327713.2164 |  | 0
2026-01-02 | 329262.4647 |  | 329262.4647 |  | 0
2026-01-03 | 330811.713 |  | 330811.713 |  | 0
2026-01-04 | 332360.9613 |  | 332360.9613 |  | 0
2026-01-05 | 333910.2096 |  | 333910.2096 |  | 0
2026-01-06 | 335459.458 |  | 335459.458 |  | 0
2026-01-07 | 337008.7063 |  | 337008.7063 |  | 0
2026-01-08 | 338557.9546 |  | 338557.9546 |  | 0
2026-01-09 | 340107.2029 |  | 340107.2029 |  | 0
2026-01-10 | 341656.4512 |  | 341656.4512 |  | 0
2026-01-11 | 343205.6996 |  | 343205.6996 |  | 0
2026-01-12 | 344754.9479 |  | 344754.9479 |  | 0
2026-01-13 | 346304.1962 |  | 346304.1962 |  | 0
2026-01-14 | 347853.4445 |  | 347853.4445 |  | 0
2026-01-15 | 349402.6928 |  | 349402.6928 |  | 0
2026-01-16 | 350951.9411 |  | 350951.9411 |  | 0
2026-01-17 | 352501.1895 |  | 352501.1895 |  | 0
2026-01-18 | 354050.4378 |  | 354050.4378 |  | 0
2026-01-19 | 355599.6861 |  | 355599.6861 |  | 0
2026-01-20 | 357148.9344 |  | 357148.9344 |  | 0
2026-01-21 | 358698.1827 |  | 358698.1827 |  | 0
2026-01-22 | 360247.4311 |  | 360247.4311 |  | 0
2026-01-23 | 361796.6794 |  | 361796.6794 |  | 0
2026-01-24 | 363345.9277 |  | 363345.9277 |  | 0
2026-01-25 | 364895.176 |  | 364895.176 |  | 0
2026-01-26 | 366444.4243 |  | 366444.4243 |  | 0
2026-01-27 | 367993.6727 |  | 367993.6727 |  | 0
2026-01-28 | 369542.921 |  | 369542.921 |  | 0
2026-01-29 | 371092.1693 |  | 371092.1693 |  | 0
2026-01-30 | 372641.4176 |  | 372641.4176 |  | 0
2026-01-31 | 374190.6659 |  | 374190.6659 |  | 0
2026-02-01 | 375739.9143 |  | 375739.9143 |  | 0
2026-02-02 | 377289.1626 |  | 377289.1626 |  | 0
2026-02-03 | 378838.4109 |  | 378838.4109 |  | 0
2026-02-04 | 380387.6592 |  | 380387.6592 |  | 0
2026-02-05 | 381936.9075 |  | 381936.9075 |  | 0
2026-02-06 | 383486.1559 |  | 383486.1559 |  | 0
2026-02-07 | 385035.4042 |  | 385035.4042 |  | 0
2026-02-08 | 386584.6525 |  | 386584.6525 |  | 0
2026-02-09 | 388133.9008 |  | 388133.9008 |  | 0
2026-02-10 | 389683.1491 |  | 389683.1491 |  | 0
2026-02-11 | 390971.2259 |  | 390971.2259 |  | 0
2026-02-12 | 392259.3028 |  | 392259.3028 |  | 0
2026-02-13 | 393547.3796 |  | 393547.3796 |  | 0
2026-02-14 | 394835.4564 |  | 394835.4564 |  | 0
2026-02-15 | 396123.5332 |  | 396123.5332 |  | 0
2026-02-16 | 397411.61 |  | 397411.61 |  | 0
2026-02-17 | 398699.6869 |  | 398699.6869 |  | 0
2026-02-18 | 399987.7637 |  | 399987.7637 |  | 0
2026-02-19 | 401275.8405 |  | 401275.8405 |  | 0
2026-02-20 | 402563.9173 |  | 402563.9173 |  | 0
2026-02-21 | 403851.9941 |  | 403851.9941 |  | 0
2026-02-22 | 405140.0709 |  | 405140.0709 |  | 0
2026-02-23 | 406428.1478 |  | 406428.1478 |  | 0
2026-02-24 | 407716.2246 |  | 407716.2246 |  | 0
2026-02-25 | 409004.3014 |  | 409004.3014 |  | 0
2026-02-26 | 410292.3782 |  | 410292.3782 |  | 0
2026-02-27 | 411580.455 |  | 411580.455 |  | 0
2026-02-28 | 412868.5319 |  | 412868.5319 |  | 0
2026-03-01 | 414156.6087 |  | 414156.6087 |  | 0
2026-03-02 | 415444.6855 |  | 415444.6855 |  | 0
2026-03-03 | 416732.7623 |  | 416732.7623 |  | 0
2026-03-04 | 418020.8391 |  | 418020.8391 |  | 0
2026-03-05 | 419308.9159 |  | 419308.9159 |  | 0
2026-03-06 | 420596.9928 |  | 420596.9928 |  | 0
2026-03-07 | 421885.0696 |  | 421885.0696 |  | 0
2026-03-08 | 423173.1464 |  | 423173.1464 |  | 0
2026-03-09 | 424461.2232 |  | 424461.2232 |  | 0
2026-03-10 | 425749.3 |  | 425749.3 |  | 0
2026-03-11 | 427037.3769 |  | 427037.3769 |  | 0
2026-03-12 | 428325.4537 |  | 428325.4537 |  | 0
2026-03-13 | 429613.5305 |  | 429613.5305 |  | 0
2026-03-14 | 430901.6073 |  | 430901.6073 |  | 0
2026-03-15 | 432189.6841 |  | 432189.6841 |  | 0
2026-03-16 | 433477.7609 |  | 433477.7609 |  | 0
2026-03-17 | 434765.8378 |  | 434765.8378 |  | 0
2026-03-18 | 436053.9146 |  | 436053.9146 |  | 0
2026-03-19 | 437341.9914 |  | 437341.9914 |  | 0
2026-03-20 | 438630.0682 |  | 438630.0682 |  | 0
2026-03-21 | 439918.145 |  | 439918.145 |  | 0
2026-03-22 | 441206.2219 |  | 441206.2219 |  | 0
2026-03-23 | 442494.2987 |  | 442494.2987 |  | 0
2026-03-24 | 443782.3755 |  | 443782.3755 |  | 0
2026-03-25 | 445070.4523 |  | 445070.4523 |  | 0
2026-03-26 | 446358.5291 |  | 446358.5291 |  | 0
2026-03-27 | 447646.6059 |  | 447646.6059 |  | 0
2026-03-28 | 448934.6828 |  | 448934.6828 |  | 0
2026-03-29 | 450222.7596 |  | 450222.7596 |  | 0
2026-03-30 | 451510.8364 |  | 451510.8364 |  | 0
2026-03-31 | 452798.9132 |  | 452798.9132 |  | 0
2026-04-01 | 454086.99 |  | 454086.99 |  | 0
2026-04-02 | 455375.0669 |  | 455375.0669 |  | 0
2026-04-03 | 456663.1437 |  | 456663.1437 |  | 0
2026-04-04 | 457951.2205 |  | 457951.2205 |  | 0
2026-04-05 | 459239.2973 |  | 459239.2973 |  | 0
2026-04-06 | 460527.3741 |  | 460527.3741 |  | 0
2026-04-07 | 461815.4509 |  | 461815.4509 |  | 0
2026-04-08 | 463103.5278 |  | 463103.5278 |  | 0
2026-04-09 | 464391.6046 |  | 464391.6046 |  | 0
2026-04-10 | 465679.6814 |  | 465679.6814 |  | 0
2026-04-11 | 466967.7582 |  | 466967.7582 |  | 0
2026-04-12 | 468255.835 |  | 468255.835 |  | 0
2026-04-13 | 469543.9119 |  | 469543.9119 |  | 0
2026-04-14 | 470831.9887 |  | 470831.9887 |  | 0
2026-04-15 | 472120.0655 |  | 472120.0655 |  | 0
2026-04-16 | 473408.1423 |  | 473408.1423 |  | 0
2026-04-17 | 474696.2191 |  | 474696.2191 |  | 0
2026-04-18 | 475984.2959 |  | 475984.2959 |  | 0
2026-04-19 | 477272.3728 |  | 477272.3728 |  | 0
2026-04-20 | 478560.4496 |  | 478560.4496 |  | 0
2026-04-21 | 479848.5264 |  | 479848.5264 |  | 0
2026-04-22 | 481136.6032 |  | 481136.6032 |  | 0
2026-04-23 | 482424.68 |  | 482424.68 |  | 0
2026-04-24 | 483712.7569 |  | 483712.7569 |  | 0
2026-04-25 | 485000.8337 |  | 485000.8337 |  | 0
2026-04-26 | 486288.9105 |  | 486288.9105 |  | 0
2026-04-27 | 487576.9873 |  | 487576.9873 |  | 0
2026-04-28 | 488865.0641 |  | 488865.0641 |  | 0
2026-04-29 | 490153.1409 |  | 490153.1409 |  | 0
2026-04-30 | 491441.2178 |  | 491441.2178 |  | 0
2026-05-01 | 492729.2946 |  | 492729.2946 |  | 0
2026-05-02 | 494017.3714 |  | 494017.3714 |  | 0
2026-05-03 | 495305.4482 |  | 495305.4482 |  | 0
2026-05-04 | 496593.525 |  | 496593.525 |  | 0
2026-05-05 | 497881.6019 |  | 497881.6019 |  | 0
2026-05-06 | 499169.6787 |  | 499169.6787 |  | 0
2026-05-07 | 500457.7555 |  | 500457.7555 |  | 0
2026-05-08 | 501745.8323 |  | 501745.8323 |  | 0
2026-05-09 | 503033.9091 |  | 503033.9091 |  | 0
2026-05-10 | 504321.9859 |  | 504321.9859 |  | 0
2026-05-11 | 505610.0628 |  | 505610.0628 |  | 0
2026-05-12 | 506898.1396 |  | 506898.1396 |  | 0
2026-05-13 | 508186.2164 |  | 508186.2164 |  | 0
2026-05-14 | 509474.2932 |  | 509474.2932 |  | 0
2026-05-15 | 510762.37 |  | 510762.37 |  | 0
2026-05-16 | 512050.4469 |  | 512050.4469 |  | 0
2026-05-17 | 513338.5237 |  | 513338.5237 |  | 0
2026-05-18 | 514626.6005 |  | 514626.6005 |  | 0
2026-05-19 | 515914.6773 |  | 515914.6773 |  | 0
2026-05-20 | 517202.7541 |  | 517202.7541 |  | 0
2026-05-21 | 518490.8309 |  | 518490.8309 |  | 0
2026-05-22 | 519778.9078 |  | 519778.9078 |  | 0
2026-05-23 | 521066.9846 |  | 521066.9846 |  | 0
2026-05-24 | 522355.0614 |  | 522355.0614 |  | 0
2026-05-25 | 523643.1382 |  | 523643.1382 |  | 0
2026-05-26 | 524931.215 |  | 524931.215 |  | 0
2026-05-27 | 526219.2919 |  | 526219.2919 |  | 0
2026-05-28 | 527507.3687 |  | 527507.3687 |  | 0
2026-05-29 | 528795.4455 |  | 528795.4455 |  | 0
2026-05-30 | 530083.5223 |  | 530083.5223 |  | 0
2026-05-31 | 531371.5991 |  | 531371.5991 |  | 0
2026-06-01 | 532659.6759 |  | 532659.6759 |  | 0
2026-06-02 | 533947.7528 |  | 533947.7528 |  | 0
2026-06-03 | 535235.8296 |  | 535235.8296 |  | 0
2026-06-04 | 536523.9064 |  | 536523.9064 |  | 0
2026-06-05 | 537811.9832 |  | 537811.9832 |  | 0
2026-06-06 | 539100.06 |  | 539100.06 |  | 0
2026-06-07 | 540388.1369 |  | 540388.1369 |  | 0
2026-06-08 | 541676.2137 |  | 541676.2137 |  | 0
2026-06-09 | 542964.2905 |  | 542964.2905 |  | 0
2026-06-10 | 544252.3673 |  | 544252.3673 |  | 0
2026-06-11 | 545540.4441 |  | 545540.4441 |  | 0
2026-06-12 | 546828.5209 |  | 546828.5209 |  | 0
2026-06-13 | 548116.5978 |  | 548116.5978 |  | 0
2026-06-14 | 549404.6746 |  | 549404.6746 |  | 0
2026-06-15 | 550692.7514 |  | 550692.7514 |  | 0
2026-06-16 | 551980.8282 |  | 551980.8282 |  | 0
2026-06-17 | 553268.905 |  | 553268.905 |  | 0
2026-06-18 | 554556.9819 |  | 554556.9819 |  | 0
2026-06-19 | 555845.0587 |  | 555845.0587 |  | 0
2026-06-20 | 557133.1355 |  | 557133.1355 |  | 0
2026-06-21 | 558421.2123 |  | 558421.2123 |  | 0
2026-06-22 | 559709.2891 |  | 559709.2891 |  | 0
2026-06-23 | 560997.3659 |  | 560997.3659 |  | 0
2026-06-24 | 562285.4428 |  | 562285.4428 |  | 0
2026-06-25 | 563573.5196 |  | 563573.5196 |  | 0
2026-06-26 | 564861.5964 |  | 564861.5964 |  | 0
2026-06-27 | 566149.6732 |  | 566149.6732 |  | 0
2026-06-28 | 567437.75 |  | 567437.75 |  | 0
2026-06-29 | 568725.8269 |  | 568725.8269 |  | 0
2026-06-30 | 570013.9037 |  | 570013.9037 |  | 0
2026-07-01 | 571301.9805 |  | 571301.9805 |  | 0
2026-07-02 | 572590.0573 |  | 572590.0573 |  | 0
2026-07-03 | 573878.1341 |  | 573878.1341 |  | 0
2026-07-04 | 575166.2109 |  | 575166.2109 |  | 0
2026-07-05 | 576454.2878 |  | 576454.2878 |  | 0
2026-07-06 | 577742.3646 |  | 577742.3646 |  | 0
2026-07-07 | 579030.4414 |  | 579030.4414 |  | 0
2026-07-08 | 580318.5182 |  | 580318.5182 |  | 0
2026-07-09 | 581606.595 |  | 581606.595 |  | 0
2026-07-10 | 582894.6719 |  | 582894.6719 |  | 0
2026-07-11 | 584182.7487 |  | 584182.7487 |  | 0
2026-07-12 | 585470.8255 |  | 585470.8255 |  | 0
2026-07-13 | 586758.9023 |  | 586758.9023 |  | 0
2026-07-14 | 588046.9791 |  | 588046.9791 |  | 0
2026-07-15 | 589335.0559 |  | 589335.0559 |  | 0
2026-07-16 | 590623.1328 |  | 590623.1328 |  | 0
2026-07-17 | 591911.2096 |  | 591911.2096 |  | 0
2026-07-18 | 593199.2864 |  | 593199.2864 |  | 0
2026-07-19 | 594487.3632 |  | 594487.3632 |  | 0
2026-07-20 | 595775.44 |  | 595775.44 |  | 0
2026-07-21 | 597063.5169 |  | 597063.5169 |  | 0
2026-07-22 | 598351.5937 |  | 598351.5937 |  | 0
2026-07-23 | 599639.6705 |  | 599639.6705 |  | 0
2026-07-24 | 600927.7473 |  | 600927.7473 |  | 0
2026-07-25 | 602215.8241 |  | 602215.8241 |  | 0
2026-07-26 | 603503.9009 |  | 603503.9009 |  | 0
2026-07-27 | 604791.9778 |  | 604791.9778 |  | 0
2026-07-28 | 606080.0546 |  | 606080.0546 |  | 0
2026-07-29 | 607368.1314 |  | 607368.1314 |  | 0
2026-07-30 | 608656.2082 |  | 608656.2082 |  | 0
2026-07-31 | 609944.285 |  | 609944.285 |  | 0
2026-08-01 | 611232.3619 |  | 611232.3619 |  | 0
2026-08-02 | 612520.4387 |  | 612520.4387 |  | 0
2026-08-03 | 613808.5155 |  | 613808.5155 |  | 0
2026-08-04 | 615096.5923 |  | 615096.5923 |  | 0
2026-08-05 | 616384.6691 |  | 616384.6691 |  | 0
2026-08-06 | 617672.7459 |  | 617672.7459 |  | 0
2026-08-07 | 618960.8228 |  | 618960.8228 |  | 0
2026-08-08 | 620248.8996 |  | 620248.8996 |  | 0
2026-08-09 | 621536.9764 |  | 621536.9764 |  | 0
2026-08-10 | 622825.0532 |  | 622825.0532 |  | 0
2026-08-11 | 624113.13 |  | 624113.13 |  | 0
2026-08-12 | 625401.2069 |  | 625401.2069 |  | 0
2026-08-13 | 626689.2837 |  | 626689.2837 |  | 0
2026-08-14 | 627977.3605 |  | 627977.3605 |  | 0
2026-08-15 | 629265.4373 |  | 629265.4373 |  | 0
2026-08-16 | 630553.5141 |  | 630553.5141 |  | 0
2026-08-17 | 631841.5909 |  | 631841.5909 |  | 0
2026-08-18 | 633129.6678 |  | 633129.6678 |  | 0
2026-08-19 | 634417.7446 |  | 634417.7446 |  | 0
2026-08-20 | 635598.4464 |  | 635598.4464 |  | 0
2026-08-21 | 636779.1481 |  | 636779.1481 |  | 0
2026-08-22 | 637959.8499 |  | 637959.8499 |  | 0
2026-08-23 | 639140.5517 |  | 639140.5517 |  | 0
2026-08-24 | 640321.2535 |  | 640321.2535 |  | 0
2026-08-25 | 641501.9552 |  | 641501.9552 |  | 0
2026-08-26 | 642682.657 |  | 642682.657 |  | 0
2026-08-27 | 643863.3588 |  | 643863.3588 |  | 0
2026-08-28 | 645044.0606 |  | 645044.0606 |  | 0
2026-08-29 | 646224.7623 |  | 646224.7623 |  | 0
2026-08-30 | 647405.4641 |  | 647405.4641 |  | 0
2026-08-31 | 648586.1659 |  | 648586.1659 |  | 0
2026-09-01 | 649766.8677 |  | 649766.8677 |  | 0
2026-09-02 | 650947.5694 |  | 650947.5694 |  | 0
2026-09-03 | 652128.2712 |  | 652128.2712 |  | 0
2026-09-04 | 653308.973 |  | 653308.973 |  | 0
2026-09-05 | 654489.6748 |  | 654489.6748 |  | 0
2026-09-06 | 655670.3766 |  | 655670.3766 |  | 0
2026-09-07 | 656851.0783 |  | 656851.0783 |  | 0
2026-09-08 | 658031.7801 |  | 658031.7801 |  | 0
2026-09-09 | 659212.4819 |  | 659212.4819 |  | 0
2026-09-10 | 660393.1837 |  | 660393.1837 |  | 0
2026-09-11 | 661573.8854 |  | 661573.8854 |  | 0
2026-09-12 | 662754.5872 |  | 662754.5872 |  | 0
2026-09-13 | 663935.289 |  | 663935.289 |  | 0
2026-09-14 | 665115.9908 |  | 665115.9908 |  | 0
2026-09-15 | 666296.6925 |  | 666296.6925 |  | 0
2026-09-16 | 667477.3943 |  | 667477.3943 |  | 0
2026-09-17 | 668658.0961 |  | 668658.0961 |  | 0
2026-09-18 | 669838.7979 |  | 669838.7979 |  | 0
2026-09-19 | 671019.4996 |  | 671019.4996 |  | 0
2026-09-20 | 672200.2014 |  | 672200.2014 |  | 0
2026-09-21 | 673380.9032 |  | 673380.9032 |  | 0
2026-09-22 | 674561.605 |  | 674561.605 |  | 0

## Travel&perdiem (Direct Cost)
Date | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Planned 5105 · Travel - Airfare (Direct) (Cumulative) | Actual 5105 · Travel - Airfare (Direct) (Cumulative) | Planned 5106 · Travel - Hotel (Direct) (Cumulative) | Actual 5106 · Travel - Hotel (Direct) (Cumulative) | Planned 5107 · Travel - Other (Direct) (Cumulative) | Actual 5107 · Travel - Other (Direct) (Cumulative) | Planned 5108 · Meals & entertainment (Direct) (Cumulative) | Actual 5108 · Meals & entertainment (Direct) (Cumulative) | Planned 5122 · Motor vehicle exp (Direct) (Cumulative) | Actual 5122 · Motor vehicle exp (Direct) (Cumulative) | Planned 5123 · Auto fuel (Direct) (Cumulative) | Actual 5123 · Auto fuel (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 139.8381 | 227.92 | 23.3063 | 0 | 23.3063 | 0 | 23.3063 | 18 | 23.3063 | 0 | 23.3063 | 0 | 23.3063 | 0
2025-06-26 | 279.6761 | 227.92 | 46.6127 | 0 | 46.6127 | 0 | 46.6127 | 18 | 46.6127 | 0 | 46.6127 | 0 | 46.6127 | 0
2025-06-27 | 419.5142 | 227.92 | 69.919 | 0 | 69.919 | 0 | 69.919 | 18 | 69.919 | 0 | 69.919 | 0 | 69.919 | 0
2025-06-28 | 559.3523 | 227.92 | 93.2254 | 0 | 93.2254 | 0 | 93.2254 | 18 | 93.2254 | 0 | 93.2254 | 0 | 93.2254 | 0
2025-06-29 | 699.1904 | 227.92 | 116.5317 | 0 | 116.5317 | 0 | 116.5317 | 18 | 116.5317 | 0 | 116.5317 | 0 | 116.5317 | 0
2025-06-30 | 839.0284 | 227.92 | 139.8381 | 0 | 139.8381 | 0 | 139.8381 | 18 | 139.8381 | 0 | 139.8381 | 0 | 139.8381 | 0
2025-07-01 | 978.8665 | 227.92 | 163.1444 | 0 | 163.1444 | 0 | 163.1444 | 18 | 163.1444 | 0 | 163.1444 | 0 | 163.1444 | 0
2025-07-02 | 1118.7046 | 227.92 | 186.4508 | 0 | 186.4508 | 0 | 186.4508 | 18 | 186.4508 | 0 | 186.4508 | 0 | 186.4508 | 0
2025-07-03 | 1258.5426 | 227.92 | 209.7571 | 0 | 209.7571 | 0 | 209.7571 | 18 | 209.7571 | 0 | 209.7571 | 0 | 209.7571 | 0
2025-07-04 | 1398.3807 | 227.92 | 233.0635 | 0 | 233.0635 | 0 | 233.0635 | 18 | 233.0635 | 0 | 233.0635 | 0 | 233.0635 | 0
2025-07-05 | 1538.2188 | 227.92 | 256.3698 | 0 | 256.3698 | 0 | 256.3698 | 18 | 256.3698 | 0 | 256.3698 | 0 | 256.3698 | 0
2025-07-06 | 1678.0569 | 227.92 | 279.6761 | 0 | 279.6761 | 0 | 279.6761 | 18 | 279.6761 | 0 | 279.6761 | 0 | 279.6761 | 0
2025-07-07 | 1817.8949 | 227.92 | 302.9825 | 0 | 302.9825 | 0 | 302.9825 | 18 | 302.9825 | 0 | 302.9825 | 0 | 302.9825 | 0
2025-07-08 | 1957.733 | 227.92 | 326.2888 | 0 | 326.2888 | 0 | 326.2888 | 18 | 326.2888 | 0 | 326.2888 | 0 | 326.2888 | 0
2025-07-09 | 2097.5711 | 227.92 | 349.5952 | 0 | 349.5952 | 0 | 349.5952 | 18 | 349.5952 | 0 | 349.5952 | 0 | 349.5952 | 0
2025-07-10 | 2237.4092 | 227.92 | 372.9015 | 0 | 372.9015 | 0 | 372.9015 | 18 | 372.9015 | 0 | 372.9015 | 0 | 372.9015 | 0
2025-07-11 | 2377.2472 | 227.92 | 396.2079 | 0 | 396.2079 | 0 | 396.2079 | 18 | 396.2079 | 0 | 396.2079 | 0 | 396.2079 | 0
2025-07-12 | 2517.0853 | 227.92 | 419.5142 | 0 | 419.5142 | 0 | 419.5142 | 18 | 419.5142 | 0 | 419.5142 | 0 | 419.5142 | 0
2025-07-13 | 2656.9234 | 227.92 | 442.8206 | 0 | 442.8206 | 0 | 442.8206 | 18 | 442.8206 | 0 | 442.8206 | 0 | 442.8206 | 0
2025-07-14 | 2796.7614 | 1769.82 | 466.1269 | 1541.9 | 466.1269 | 0 | 466.1269 | 18 | 466.1269 | 0 | 466.1269 | 0 | 466.1269 | 0
2025-07-15 | 2936.5995 | 1769.82 | 489.4333 | 1541.9 | 489.4333 | 0 | 489.4333 | 18 | 489.4333 | 0 | 489.4333 | 0 | 489.4333 | 0
2025-07-16 | 3076.4376 | 1769.82 | 512.7396 | 1541.9 | 512.7396 | 0 | 512.7396 | 18 | 512.7396 | 0 | 512.7396 | 0 | 512.7396 | 0
2025-07-17 | 3216.2757 | 1834.27 | 536.0459 | 1541.9 | 536.0459 | 0 | 536.0459 | 18 | 536.0459 | 0 | 536.0459 | 0 | 536.0459 | 0
2025-07-18 | 3356.1137 | 1861.41 | 559.3523 | 1569.04 | 559.3523 | 0 | 559.3523 | 18 | 559.3523 | 0 | 559.3523 | 0 | 559.3523 | 0
2025-07-19 | 3495.9518 | 1891.41 | 582.6586 | 1569.04 | 582.6586 | 0 | 582.6586 | 48 | 582.6586 | 0 | 582.6586 | 0 | 582.6586 | 0
2025-07-20 | 3635.7899 | 1891.41 | 605.965 | 1569.04 | 605.965 | 0 | 605.965 | 48 | 605.965 | 0 | 605.965 | 0 | 605.965 | 0
2025-07-21 | 3775.6279 | 1891.41 | 629.2713 | 1569.04 | 629.2713 | 0 | 629.2713 | 48 | 629.2713 | 0 | 629.2713 | 0 | 629.2713 | 0
2025-07-22 | 3915.466 | 1891.41 | 652.5777 | 1569.04 | 652.5777 | 0 | 652.5777 | 48 | 652.5777 | 0 | 652.5777 | 0 | 652.5777 | 0
2025-07-23 | 4055.3041 | 1891.41 | 675.884 | 1569.04 | 675.884 | 0 | 675.884 | 48 | 675.884 | 0 | 675.884 | 0 | 675.884 | 0
2025-07-24 | 4195.1422 | 1891.41 | 699.1904 | 1569.04 | 699.1904 | 0 | 699.1904 | 48 | 699.1904 | 0 | 699.1904 | 0 | 699.1904 | 0
2025-07-25 | 4334.9802 | 1891.41 | 722.4967 | 1569.04 | 722.4967 | 0 | 722.4967 | 48 | 722.4967 | 0 | 722.4967 | 0 | 722.4967 | 0
2025-07-26 | 4474.8183 | 1891.41 | 745.8031 | 1569.04 | 745.8031 | 0 | 745.8031 | 48 | 745.8031 | 0 | 745.8031 | 0 | 745.8031 | 0
2025-07-27 | 4614.6564 | 1891.41 | 769.1094 | 1569.04 | 769.1094 | 0 | 769.1094 | 48 | 769.1094 | 0 | 769.1094 | 0 | 769.1094 | 0
2025-07-28 | 4754.4944 | 1891.41 | 792.4157 | 1569.04 | 792.4157 | 0 | 792.4157 | 48 | 792.4157 | 0 | 792.4157 | 0 | 792.4157 | 0
2025-07-29 | 4894.3325 | 1891.41 | 815.7221 | 1569.04 | 815.7221 | 0 | 815.7221 | 48 | 815.7221 | 0 | 815.7221 | 0 | 815.7221 | 0
2025-07-30 | 5034.1706 | 1891.41 | 839.0284 | 1569.04 | 839.0284 | 0 | 839.0284 | 48 | 839.0284 | 0 | 839.0284 | 0 | 839.0284 | 0
2025-07-31 | 5174.0087 | 1891.41 | 862.3348 | 1569.04 | 862.3348 | 0 | 862.3348 | 48 | 862.3348 | 0 | 862.3348 | 0 | 862.3348 | 0
2025-08-01 | 5313.8467 | 1891.41 | 885.6411 | 1569.04 | 885.6411 | 0 | 885.6411 | 48 | 885.6411 | 0 | 885.6411 | 0 | 885.6411 | 0
2025-08-02 | 5453.6848 | 1891.41 | 908.9475 | 1569.04 | 908.9475 | 0 | 908.9475 | 48 | 908.9475 | 0 | 908.9475 | 0 | 908.9475 | 0
2025-08-03 | 5593.5229 | 1891.41 | 932.2538 | 1569.04 | 932.2538 | 0 | 932.2538 | 48 | 932.2538 | 0 | 932.2538 | 0 | 932.2538 | 0
2025-08-04 | 5733.361 | 1891.41 | 955.5602 | 1569.04 | 955.5602 | 0 | 955.5602 | 48 | 955.5602 | 0 | 955.5602 | 0 | 955.5602 | 0
2025-08-05 | 5873.199 | 1891.41 | 978.8665 | 1569.04 | 978.8665 | 0 | 978.8665 | 48 | 978.8665 | 0 | 978.8665 | 0 | 978.8665 | 0
2025-08-06 | 6013.0371 | 1891.41 | 1002.1728 | 1569.04 | 1002.1728 | 0 | 1002.1728 | 48 | 1002.1728 | 0 | 1002.1728 | 0 | 1002.1728 | 0
2025-08-07 | 6152.8752 | 1891.41 | 1025.4792 | 1569.04 | 1025.4792 | 0 | 1025.4792 | 48 | 1025.4792 | 0 | 1025.4792 | 0 | 1025.4792 | 0
2025-08-08 | 6292.7132 | 1891.41 | 1048.7855 | 1569.04 | 1048.7855 | 0 | 1048.7855 | 48 | 1048.7855 | 0 | 1048.7855 | 0 | 1048.7855 | 0
2025-08-09 | 6432.5513 | 1891.41 | 1072.0919 | 1569.04 | 1072.0919 | 0 | 1072.0919 | 48 | 1072.0919 | 0 | 1072.0919 | 0 | 1072.0919 | 0
2025-08-10 | 6572.3894 | 1891.41 | 1095.3982 | 1569.04 | 1095.3982 | 0 | 1095.3982 | 48 | 1095.3982 | 0 | 1095.3982 | 0 | 1095.3982 | 0
2025-08-11 | 6712.2275 | 1891.41 | 1118.7046 | 1569.04 | 1118.7046 | 0 | 1118.7046 | 48 | 1118.7046 | 0 | 1118.7046 | 0 | 1118.7046 | 0
2025-08-12 | 6852.0655 | 1891.41 | 1142.0109 | 1569.04 | 1142.0109 | 0 | 1142.0109 | 48 | 1142.0109 | 0 | 1142.0109 | 0 | 1142.0109 | 0
2025-08-13 | 6991.9036 | 1891.41 | 1165.3173 | 1569.04 | 1165.3173 | 0 | 1165.3173 | 48 | 1165.3173 | 0 | 1165.3173 | 0 | 1165.3173 | 0
2025-08-14 | 7131.7417 | 1891.41 | 1188.6236 | 1569.04 | 1188.6236 | 0 | 1188.6236 | 48 | 1188.6236 | 0 | 1188.6236 | 0 | 1188.6236 | 0
2025-08-15 | 7271.5797 | 1891.41 | 1211.93 | 1569.04 | 1211.93 | 0 | 1211.93 | 48 | 1211.93 | 0 | 1211.93 | 0 | 1211.93 | 0
2025-08-16 | 7411.4178 | 1891.41 | 1235.2363 | 1569.04 | 1235.2363 | 0 | 1235.2363 | 48 | 1235.2363 | 0 | 1235.2363 | 0 | 1235.2363 | 0
2025-08-17 | 7551.2559 | 1891.41 | 1258.5426 | 1569.04 | 1258.5426 | 0 | 1258.5426 | 48 | 1258.5426 | 0 | 1258.5426 | 0 | 1258.5426 | 0
2025-08-18 | 7691.094 | 1891.41 | 1281.849 | 1569.04 | 1281.849 | 0 | 1281.849 | 48 | 1281.849 | 0 | 1281.849 | 0 | 1281.849 | 0
2025-08-19 | 7830.932 | 1891.41 | 1305.1553 | 1569.04 | 1305.1553 | 0 | 1305.1553 | 48 | 1305.1553 | 0 | 1305.1553 | 0 | 1305.1553 | 0
2025-08-20 | 7970.7701 | 2030.22 | 1328.4617 | 1569.04 | 1328.4617 | 0 | 1328.4617 | 48 | 1328.4617 | 0 | 1328.4617 | 0 | 1328.4617 | 0
2025-08-21 | 8110.6082 | 2030.22 | 1351.768 | 1569.04 | 1351.768 | 0 | 1351.768 | 48 | 1351.768 | 0 | 1351.768 | 0 | 1351.768 | 0
2025-08-22 | 8250.4462 | 2130.22 | 1375.0744 | 1569.04 | 1375.0744 | 0 | 1375.0744 | 48 | 1375.0744 | 100 | 1375.0744 | 0 | 1375.0744 | 0
2025-08-23 | 8390.2843 | 2130.22 | 1398.3807 | 1569.04 | 1398.3807 | 0 | 1398.3807 | 48 | 1398.3807 | 100 | 1398.3807 | 0 | 1398.3807 | 0
2025-08-24 | 8530.1224 | 2130.22 | 1421.6871 | 1569.04 | 1421.6871 | 0 | 1421.6871 | 48 | 1421.6871 | 100 | 1421.6871 | 0 | 1421.6871 | 0
2025-08-25 | 8669.9605 | 2130.22 | 1444.9934 | 1569.04 | 1444.9934 | 0 | 1444.9934 | 48 | 1444.9934 | 100 | 1444.9934 | 0 | 1444.9934 | 0
2025-08-26 | 8809.7985 | 2130.22 | 1468.2998 | 1569.04 | 1468.2998 | 0 | 1468.2998 | 48 | 1468.2998 | 100 | 1468.2998 | 0 | 1468.2998 | 0
2025-08-27 | 8949.6366 | 2130.22 | 1491.6061 | 1569.04 | 1491.6061 | 0 | 1491.6061 | 48 | 1491.6061 | 100 | 1491.6061 | 0 | 1491.6061 | 0
2025-08-28 | 9089.4747 | 2130.22 | 1514.9124 | 1569.04 | 1514.9124 | 0 | 1514.9124 | 48 | 1514.9124 | 100 | 1514.9124 | 0 | 1514.9124 | 0
2025-08-29 | 9229.3128 | 2130.22 | 1538.2188 | 1569.04 | 1538.2188 | 0 | 1538.2188 | 48 | 1538.2188 | 100 | 1538.2188 | 0 | 1538.2188 | 0
2025-08-30 | 9369.1508 | 2130.22 | 1561.5251 | 1569.04 | 1561.5251 | 0 | 1561.5251 | 48 | 1561.5251 | 100 | 1561.5251 | 0 | 1561.5251 | 0
2025-08-31 | 9508.9889 | 2130.22 | 1584.8315 | 1569.04 | 1584.8315 | 0 | 1584.8315 | 48 | 1584.8315 | 100 | 1584.8315 | 0 | 1584.8315 | 0
2025-09-01 | 9648.827 | 2130.22 | 1608.1378 | 1569.04 | 1608.1378 | 0 | 1608.1378 | 48 | 1608.1378 | 100 | 1608.1378 | 0 | 1608.1378 | 0
2025-09-02 | 9788.665 | 2130.22 | 1631.4442 | 1569.04 | 1631.4442 | 0 | 1631.4442 | 48 | 1631.4442 | 100 | 1631.4442 | 0 | 1631.4442 | 0
2025-09-03 | 9928.5031 | 2130.22 | 1654.7505 | 1569.04 | 1654.7505 | 0 | 1654.7505 | 48 | 1654.7505 | 100 | 1654.7505 | 0 | 1654.7505 | 0
2025-09-04 | 10068.3412 | 2130.22 | 1678.0569 | 1569.04 | 1678.0569 | 0 | 1678.0569 | 48 | 1678.0569 | 100 | 1678.0569 | 0 | 1678.0569 | 0
2025-09-05 | 10208.1793 | 2130.22 | 1701.3632 | 1569.04 | 1701.3632 | 0 | 1701.3632 | 48 | 1701.3632 | 100 | 1701.3632 | 0 | 1701.3632 | 0
2025-09-06 | 10348.0173 | 2130.22 | 1724.6696 | 1569.04 | 1724.6696 | 0 | 1724.6696 | 48 | 1724.6696 | 100 | 1724.6696 | 0 | 1724.6696 | 0
2025-09-07 | 10487.8554 | 2130.22 | 1747.9759 | 1569.04 | 1747.9759 | 0 | 1747.9759 | 48 | 1747.9759 | 100 | 1747.9759 | 0 | 1747.9759 | 0
2025-09-08 | 10627.6935 | 2130.22 | 1771.2822 | 1569.04 | 1771.2822 | 0 | 1771.2822 | 48 | 1771.2822 | 100 | 1771.2822 | 0 | 1771.2822 | 0
2025-09-09 | 10767.5315 | 2130.22 | 1794.5886 | 1569.04 | 1794.5886 | 0 | 1794.5886 | 48 | 1794.5886 | 100 | 1794.5886 | 0 | 1794.5886 | 0
2025-09-10 | 10907.3696 | 2367.08 | 1817.8949 | 1569.04 | 1817.8949 | 0 | 1817.8949 | 48 | 1817.8949 | 100 | 1817.8949 | 0 | 1817.8949 | 0
2025-09-11 | 11047.2077 | 2367.08 | 1841.2013 | 1569.04 | 1841.2013 | 0 | 1841.2013 | 48 | 1841.2013 | 100 | 1841.2013 | 0 | 1841.2013 | 0
2025-09-12 | 11187.0458 | 2478.02 | 1864.5076 | 1569.04 | 1864.5076 | 0 | 1864.5076 | 158.94 | 1864.5076 | 100 | 1864.5076 | 0 | 1864.5076 | 0
2025-09-13 | 11326.8838 | 2478.02 | 1887.814 | 1569.04 | 1887.814 | 0 | 1887.814 | 158.94 | 1887.814 | 100 | 1887.814 | 0 | 1887.814 | 0
2025-09-14 | 11466.7219 | 2478.02 | 1911.1203 | 1569.04 | 1911.1203 | 0 | 1911.1203 | 158.94 | 1911.1203 | 100 | 1911.1203 | 0 | 1911.1203 | 0
2025-09-15 | 11606.56 | 2928.02 | 1934.4267 | 1569.04 | 1934.4267 | 0 | 1934.4267 | 158.94 | 1934.4267 | 550 | 1934.4267 | 0 | 1934.4267 | 0
2025-09-16 | 11746.398 | 2928.02 | 1957.733 | 1569.04 | 1957.733 | 0 | 1957.733 | 158.94 | 1957.733 | 550 | 1957.733 | 0 | 1957.733 | 0
2025-09-17 | 11886.2361 | 2928.02 | 1981.0394 | 1569.04 | 1981.0394 | 0 | 1981.0394 | 158.94 | 1981.0394 | 550 | 1981.0394 | 0 | 1981.0394 | 0
2025-09-18 | 12026.0742 | 2928.02 | 2004.3457 | 1569.04 | 2004.3457 | 0 | 2004.3457 | 158.94 | 2004.3457 | 550 | 2004.3457 | 0 | 2004.3457 | 0
2025-09-19 | 12165.9123 | 2928.02 | 2027.652 | 1569.04 | 2027.652 | 0 | 2027.652 | 158.94 | 2027.652 | 550 | 2027.652 | 0 | 2027.652 | 0
2025-09-20 | 12305.7503 | 2928.02 | 2050.9584 | 1569.04 | 2050.9584 | 0 | 2050.9584 | 158.94 | 2050.9584 | 550 | 2050.9584 | 0 | 2050.9584 | 0
2025-09-21 | 12445.5884 | 2928.02 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 550 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-22 | 12445.5884 | 3228.02 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-23 | 12445.5884 | 3228.02 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-24 | 12445.5884 | 3333.29 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 105.27
2025-09-25 | 12445.5884 | 3333.29 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 105.27
2025-09-26 | 12445.5884 | 3333.29 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 105.27
2025-09-27 | 12445.5884 | 3333.29 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 105.27
2025-09-28 | 12445.5884 | 3452.82 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 224.8
2025-09-29 | 13471.6043 | 4852.82 | 2245.2674 | 1569.04 | 2245.2674 | 0 | 2245.2674 | 158.94 | 2245.2674 | 2250 | 2245.2674 | 0 | 2245.2674 | 224.8
2025-09-30 | 14497.6202 | 4852.82 | 2416.27 | 1569.04 | 2416.27 | 0 | 2416.27 | 158.94 | 2416.27 | 2250 | 2416.27 | 0 | 2416.27 | 224.8
2025-10-01 | 15523.6361 | 4852.82 | 2587.2727 | 1569.04 | 2587.2727 | 0 | 2587.2727 | 158.94 | 2587.2727 | 2250 | 2587.2727 | 0 | 2587.2727 | 224.8
2025-10-02 | 16549.6521 | 4852.82 | 2758.2753 | 1569.04 | 2758.2753 | 0 | 2758.2753 | 158.94 | 2758.2753 | 2250 | 2758.2753 | 0 | 2758.2753 | 224.8
2025-10-03 | 17575.668 | 5352.82 | 2929.278 | 1569.04 | 2929.278 | 0 | 2929.278 | 158.94 | 2929.278 | 2750 | 2929.278 | 0 | 2929.278 | 224.8
2025-10-04 | 18601.6839 | 5352.82 | 3100.2806 | 1569.04 | 3100.2806 | 0 | 3100.2806 | 158.94 | 3100.2806 | 2750 | 3100.2806 | 0 | 3100.2806 | 224.8
2025-10-05 | 19627.6998 | 5352.82 | 3271.2833 | 1569.04 | 3271.2833 | 0 | 3271.2833 | 158.94 | 3271.2833 | 2750 | 3271.2833 | 0 | 3271.2833 | 224.8
2025-10-06 | 20653.7157 | 5352.82 | 3442.286 | 1569.04 | 3442.286 | 0 | 3442.286 | 158.94 | 3442.286 | 2750 | 3442.286 | 0 | 3442.286 | 224.8
2025-10-07 | 21679.7316 | 5352.82 | 3613.2886 | 1569.04 | 3613.2886 | 0 | 3613.2886 | 158.94 | 3613.2886 | 2750 | 3613.2886 | 0 | 3613.2886 | 224.8
2025-10-08 | 22705.7475 | 5352.82 | 3784.2913 | 1569.04 | 3784.2913 | 0 | 3784.2913 | 158.94 | 3784.2913 | 2750 | 3784.2913 | 0 | 3784.2913 | 224.8
2025-10-09 | 23731.7635 | 5352.82 | 3955.2939 | 1569.04 | 3955.2939 | 0 | 3955.2939 | 158.94 | 3955.2939 | 2750 | 3955.2939 | 0 | 3955.2939 | 224.8
2025-10-10 | 24757.7794 | 5352.82 | 4126.2966 | 1569.04 | 4126.2966 | 0 | 4126.2966 | 158.94 | 4126.2966 | 2750 | 4126.2966 | 0 | 4126.2966 | 224.8
2025-10-11 | 25783.7953 | 5352.82 | 4297.2992 | 1569.04 | 4297.2992 | 0 | 4297.2992 | 158.94 | 4297.2992 | 2750 | 4297.2992 | 0 | 4297.2992 | 224.8
2025-10-12 | 26809.8112 | 5352.82 | 4468.3019 | 1569.04 | 4468.3019 | 0 | 4468.3019 | 158.94 | 4468.3019 | 2750 | 4468.3019 | 0 | 4468.3019 | 224.8
2025-10-13 | 27835.8271 | 5352.82 | 4639.3045 | 1569.04 | 4639.3045 | 0 | 4639.3045 | 158.94 | 4639.3045 | 2750 | 4639.3045 | 0 | 4639.3045 | 224.8
2025-10-14 | 28861.843 | 6702.82 | 4810.3072 | 1569.04 | 4810.3072 | 0 | 4810.3072 | 158.94 | 4810.3072 | 4100 | 4810.3072 | 0 | 4810.3072 | 224.8
2025-10-15 | 29887.8589 | 6702.82 | 4981.3098 | 1569.04 | 4981.3098 | 0 | 4981.3098 | 158.94 | 4981.3098 | 4100 | 4981.3098 | 0 | 4981.3098 | 224.8
2025-10-16 | 30913.8749 | 6702.82 | 5152.3125 | 1569.04 | 5152.3125 | 0 | 5152.3125 | 158.94 | 5152.3125 | 4100 | 5152.3125 | 0 | 5152.3125 | 224.8
2025-10-17 | 31939.8908 | 7402.82 | 5323.3151 | 1569.04 | 5323.3151 | 0 | 5323.3151 | 158.94 | 5323.3151 | 4800 | 5323.3151 | 0 | 5323.3151 | 224.8
2025-10-18 | 32965.9067 | 7402.82 | 5494.3178 | 1569.04 | 5494.3178 | 0 | 5494.3178 | 158.94 | 5494.3178 | 4800 | 5494.3178 | 0 | 5494.3178 | 224.8
2025-10-19 | 33991.9226 | 7402.82 | 5665.3204 | 1569.04 | 5665.3204 | 0 | 5665.3204 | 158.94 | 5665.3204 | 4800 | 5665.3204 | 0 | 5665.3204 | 224.8
2025-10-20 | 35017.9385 | 7402.82 | 5836.3231 | 1569.04 | 5836.3231 | 0 | 5836.3231 | 158.94 | 5836.3231 | 4800 | 5836.3231 | 0 | 5836.3231 | 224.8
2025-10-21 | 36043.9544 | 7402.82 | 6007.3257 | 1569.04 | 6007.3257 | 0 | 6007.3257 | 158.94 | 6007.3257 | 4800 | 6007.3257 | 0 | 6007.3257 | 224.8
2025-10-22 | 37069.9703 | 7402.82 | 6178.3284 | 1569.04 | 6178.3284 | 0 | 6178.3284 | 158.94 | 6178.3284 | 4800 | 6178.3284 | 0 | 6178.3284 | 224.8
2025-10-23 | 38095.9862 | 7402.82 | 6349.331 | 1569.04 | 6349.331 | 0 | 6349.331 | 158.94 | 6349.331 | 4800 | 6349.331 | 0 | 6349.331 | 224.8
2025-10-24 | 39122.0022 | 8502.82 | 6520.3337 | 1569.04 | 6520.3337 | 0 | 6520.3337 | 158.94 | 6520.3337 | 5900 | 6520.3337 | 0 | 6520.3337 | 224.8
2025-10-25 | 40148.0181 | 8502.82 | 6691.3363 | 1569.04 | 6691.3363 | 0 | 6691.3363 | 158.94 | 6691.3363 | 5900 | 6691.3363 | 0 | 6691.3363 | 224.8
2025-10-26 | 41174.034 | 8502.82 | 6862.339 | 1569.04 | 6862.339 | 0 | 6862.339 | 158.94 | 6862.339 | 5900 | 6862.339 | 0 | 6862.339 | 224.8
2025-10-27 | 42200.0499 |  | 7033.3417 |  | 7033.3417 |  | 7033.3417 |  | 7033.3417 |  | 7033.3417 |  | 7033.3417
2025-10-28 | 43226.0658 |  | 7204.3443 |  | 7204.3443 |  | 7204.3443 |  | 7204.3443 |  | 7204.3443 |  | 7204.3443
2025-10-29 | 44252.0817 |  | 7375.347 |  | 7375.347 |  | 7375.347 |  | 7375.347 |  | 7375.347 |  | 7375.347
2025-10-30 | 45278.0976 |  | 7546.3496 |  | 7546.3496 |  | 7546.3496 |  | 7546.3496 |  | 7546.3496 |  | 7546.3496
2025-10-31 | 46304.1136 |  | 7717.3523 |  | 7717.3523 |  | 7717.3523 |  | 7717.3523 |  | 7717.3523 |  | 7717.3523
2025-11-01 | 47330.1295 |  | 7888.3549 |  | 7888.3549 |  | 7888.3549 |  | 7888.3549 |  | 7888.3549 |  | 7888.3549
2025-11-02 | 48356.1454 |  | 8059.3576 |  | 8059.3576 |  | 8059.3576 |  | 8059.3576 |  | 8059.3576 |  | 8059.3576
2025-11-03 | 49382.1613 |  | 8230.3602 |  | 8230.3602 |  | 8230.3602 |  | 8230.3602 |  | 8230.3602 |  | 8230.3602
2025-11-04 | 50408.1772 |  | 8401.3629 |  | 8401.3629 |  | 8401.3629 |  | 8401.3629 |  | 8401.3629 |  | 8401.3629
2025-11-05 | 51434.1931 |  | 8572.3655 |  | 8572.3655 |  | 8572.3655 |  | 8572.3655 |  | 8572.3655 |  | 8572.3655
2025-11-06 | 52460.209 |  | 8743.3682 |  | 8743.3682 |  | 8743.3682 |  | 8743.3682 |  | 8743.3682 |  | 8743.3682
2025-11-07 | 53486.225 |  | 8914.3708 |  | 8914.3708 |  | 8914.3708 |  | 8914.3708 |  | 8914.3708 |  | 8914.3708
2025-11-08 | 54512.2409 |  | 9085.3735 |  | 9085.3735 |  | 9085.3735 |  | 9085.3735 |  | 9085.3735 |  | 9085.3735
2025-11-09 | 55538.2568 |  | 9256.3761 |  | 9256.3761 |  | 9256.3761 |  | 9256.3761 |  | 9256.3761 |  | 9256.3761
2025-11-10 | 56564.2727 |  | 9427.3788 |  | 9427.3788 |  | 9427.3788 |  | 9427.3788 |  | 9427.3788 |  | 9427.3788
2025-11-11 | 57590.2886 |  | 9598.3814 |  | 9598.3814 |  | 9598.3814 |  | 9598.3814 |  | 9598.3814 |  | 9598.3814
2025-11-12 | 58616.3045 |  | 9769.3841 |  | 9769.3841 |  | 9769.3841 |  | 9769.3841 |  | 9769.3841 |  | 9769.3841
2025-11-13 | 59642.3204 |  | 9940.3867 |  | 9940.3867 |  | 9940.3867 |  | 9940.3867 |  | 9940.3867 |  | 9940.3867
2025-11-14 | 60668.3363 |  | 10111.3894 |  | 10111.3894 |  | 10111.3894 |  | 10111.3894 |  | 10111.3894 |  | 10111.3894
2025-11-15 | 61694.3523 |  | 10282.392 |  | 10282.392 |  | 10282.392 |  | 10282.392 |  | 10282.392 |  | 10282.392
2025-11-16 | 62720.3682 |  | 10453.3947 |  | 10453.3947 |  | 10453.3947 |  | 10453.3947 |  | 10453.3947 |  | 10453.3947
2025-11-17 | 63746.3841 |  | 10624.3973 |  | 10624.3973 |  | 10624.3973 |  | 10624.3973 |  | 10624.3973 |  | 10624.3973
2025-11-18 | 64772.4 |  | 10795.4 |  | 10795.4 |  | 10795.4 |  | 10795.4 |  | 10795.4 |  | 10795.4
2025-11-19 | 65374.5825 |  | 10895.7638 |  | 10895.7638 |  | 10895.7638 |  | 10895.7638 |  | 10895.7638 |  | 10895.7638
2025-11-20 | 65976.7651 |  | 10996.1275 |  | 10996.1275 |  | 10996.1275 |  | 10996.1275 |  | 10996.1275 |  | 10996.1275
2025-11-21 | 66578.9476 |  | 11096.4913 |  | 11096.4913 |  | 11096.4913 |  | 11096.4913 |  | 11096.4913 |  | 11096.4913
2025-11-22 | 67181.1302 |  | 11196.855 |  | 11196.855 |  | 11196.855 |  | 11196.855 |  | 11196.855 |  | 11196.855
2025-11-23 | 67783.3127 |  | 11297.2188 |  | 11297.2188 |  | 11297.2188 |  | 11297.2188 |  | 11297.2188 |  | 11297.2188
2025-11-24 | 68385.4952 |  | 11397.5825 |  | 11397.5825 |  | 11397.5825 |  | 11397.5825 |  | 11397.5825 |  | 11397.5825
2025-11-25 | 68987.6778 |  | 11497.9463 |  | 11497.9463 |  | 11497.9463 |  | 11497.9463 |  | 11497.9463 |  | 11497.9463
2025-11-26 | 69589.8603 |  | 11598.3101 |  | 11598.3101 |  | 11598.3101 |  | 11598.3101 |  | 11598.3101 |  | 11598.3101
2025-11-27 | 70192.0429 |  | 11698.6738 |  | 11698.6738 |  | 11698.6738 |  | 11698.6738 |  | 11698.6738 |  | 11698.6738
2025-11-28 | 70794.2254 |  | 11799.0376 |  | 11799.0376 |  | 11799.0376 |  | 11799.0376 |  | 11799.0376 |  | 11799.0376
2025-11-29 | 71396.4079 |  | 11899.4013 |  | 11899.4013 |  | 11899.4013 |  | 11899.4013 |  | 11899.4013 |  | 11899.4013
2025-11-30 | 71998.5905 |  | 11999.7651 |  | 11999.7651 |  | 11999.7651 |  | 11999.7651 |  | 11999.7651 |  | 11999.7651
2025-12-01 | 72600.773 |  | 12100.1288 |  | 12100.1288 |  | 12100.1288 |  | 12100.1288 |  | 12100.1288 |  | 12100.1288
2025-12-02 | 73202.9556 |  | 12200.4926 |  | 12200.4926 |  | 12200.4926 |  | 12200.4926 |  | 12200.4926 |  | 12200.4926
2025-12-03 | 73805.1381 |  | 12300.8563 |  | 12300.8563 |  | 12300.8563 |  | 12300.8563 |  | 12300.8563 |  | 12300.8563
2025-12-04 | 74407.3206 |  | 12401.2201 |  | 12401.2201 |  | 12401.2201 |  | 12401.2201 |  | 12401.2201 |  | 12401.2201
2025-12-05 | 75009.5032 |  | 12501.5839 |  | 12501.5839 |  | 12501.5839 |  | 12501.5839 |  | 12501.5839 |  | 12501.5839
2025-12-06 | 75611.6857 |  | 12601.9476 |  | 12601.9476 |  | 12601.9476 |  | 12601.9476 |  | 12601.9476 |  | 12601.9476
2025-12-07 | 76213.8683 |  | 12702.3114 |  | 12702.3114 |  | 12702.3114 |  | 12702.3114 |  | 12702.3114 |  | 12702.3114
2025-12-08 | 76816.0508 |  | 12802.6751 |  | 12802.6751 |  | 12802.6751 |  | 12802.6751 |  | 12802.6751 |  | 12802.6751
2025-12-09 | 77418.2333 |  | 12903.0389 |  | 12903.0389 |  | 12903.0389 |  | 12903.0389 |  | 12903.0389 |  | 12903.0389
2025-12-10 | 78020.4159 |  | 13003.4026 |  | 13003.4026 |  | 13003.4026 |  | 13003.4026 |  | 13003.4026 |  | 13003.4026
2025-12-11 | 78622.5984 |  | 13103.7664 |  | 13103.7664 |  | 13103.7664 |  | 13103.7664 |  | 13103.7664 |  | 13103.7664
2025-12-12 | 79224.781 |  | 13204.1302 |  | 13204.1302 |  | 13204.1302 |  | 13204.1302 |  | 13204.1302 |  | 13204.1302
2025-12-13 | 79826.9635 |  | 13304.4939 |  | 13304.4939 |  | 13304.4939 |  | 13304.4939 |  | 13304.4939 |  | 13304.4939
2025-12-14 | 80429.146 |  | 13404.8577 |  | 13404.8577 |  | 13404.8577 |  | 13404.8577 |  | 13404.8577 |  | 13404.8577
2025-12-15 | 81031.3286 |  | 13505.2214 |  | 13505.2214 |  | 13505.2214 |  | 13505.2214 |  | 13505.2214 |  | 13505.2214
2025-12-16 | 81633.5111 |  | 13605.5852 |  | 13605.5852 |  | 13605.5852 |  | 13605.5852 |  | 13605.5852 |  | 13605.5852
2025-12-17 | 82235.6937 |  | 13705.9489 |  | 13705.9489 |  | 13705.9489 |  | 13705.9489 |  | 13705.9489 |  | 13705.9489
2025-12-18 | 82837.8762 |  | 13806.3127 |  | 13806.3127 |  | 13806.3127 |  | 13806.3127 |  | 13806.3127 |  | 13806.3127
2025-12-19 | 83440.0587 |  | 13906.6765 |  | 13906.6765 |  | 13906.6765 |  | 13906.6765 |  | 13906.6765 |  | 13906.6765
2025-12-20 | 84042.2413 |  | 14007.0402 |  | 14007.0402 |  | 14007.0402 |  | 14007.0402 |  | 14007.0402 |  | 14007.0402
2025-12-21 | 84644.4238 |  | 14107.404 |  | 14107.404 |  | 14107.404 |  | 14107.404 |  | 14107.404 |  | 14107.404
2025-12-22 | 85246.6063 |  | 14207.7677 |  | 14207.7677 |  | 14207.7677 |  | 14207.7677 |  | 14207.7677 |  | 14207.7677
2025-12-23 | 85848.7889 |  | 14308.1315 |  | 14308.1315 |  | 14308.1315 |  | 14308.1315 |  | 14308.1315 |  | 14308.1315
2025-12-24 | 86450.9714 |  | 14408.4952 |  | 14408.4952 |  | 14408.4952 |  | 14408.4952 |  | 14408.4952 |  | 14408.4952
2025-12-25 | 87053.154 |  | 14508.859 |  | 14508.859 |  | 14508.859 |  | 14508.859 |  | 14508.859 |  | 14508.859
2025-12-26 | 87655.3365 |  | 14609.2228 |  | 14609.2228 |  | 14609.2228 |  | 14609.2228 |  | 14609.2228 |  | 14609.2228
2025-12-27 | 88257.519 |  | 14709.5865 |  | 14709.5865 |  | 14709.5865 |  | 14709.5865 |  | 14709.5865 |  | 14709.5865
2025-12-28 | 88859.7016 |  | 14809.9503 |  | 14809.9503 |  | 14809.9503 |  | 14809.9503 |  | 14809.9503 |  | 14809.9503
2025-12-29 | 89461.8841 |  | 14910.314 |  | 14910.314 |  | 14910.314 |  | 14910.314 |  | 14910.314 |  | 14910.314
2025-12-30 | 90064.0667 |  | 15010.6778 |  | 15010.6778 |  | 15010.6778 |  | 15010.6778 |  | 15010.6778 |  | 15010.6778
2025-12-31 | 90666.2492 |  | 15111.0415 |  | 15111.0415 |  | 15111.0415 |  | 15111.0415 |  | 15111.0415 |  | 15111.0415
2026-01-01 | 91268.4317 |  | 15211.4053 |  | 15211.4053 |  | 15211.4053 |  | 15211.4053 |  | 15211.4053 |  | 15211.4053
2026-01-02 | 91870.6143 |  | 15311.769 |  | 15311.769 |  | 15311.769 |  | 15311.769 |  | 15311.769 |  | 15311.769
2026-01-03 | 92472.7968 |  | 15412.1328 |  | 15412.1328 |  | 15412.1328 |  | 15412.1328 |  | 15412.1328 |  | 15412.1328
2026-01-04 | 93074.9794 |  | 15512.4966 |  | 15512.4966 |  | 15512.4966 |  | 15512.4966 |  | 15512.4966 |  | 15512.4966
2026-01-05 | 93677.1619 |  | 15612.8603 |  | 15612.8603 |  | 15612.8603 |  | 15612.8603 |  | 15612.8603 |  | 15612.8603
2026-01-06 | 94279.3444 |  | 15713.2241 |  | 15713.2241 |  | 15713.2241 |  | 15713.2241 |  | 15713.2241 |  | 15713.2241
2026-01-07 | 94881.527 |  | 15813.5878 |  | 15813.5878 |  | 15813.5878 |  | 15813.5878 |  | 15813.5878 |  | 15813.5878
2026-01-08 | 95483.7095 |  | 15913.9516 |  | 15913.9516 |  | 15913.9516 |  | 15913.9516 |  | 15913.9516 |  | 15913.9516
2026-01-09 | 96085.8921 |  | 16014.3153 |  | 16014.3153 |  | 16014.3153 |  | 16014.3153 |  | 16014.3153 |  | 16014.3153
2026-01-10 | 96688.0746 |  | 16114.6791 |  | 16114.6791 |  | 16114.6791 |  | 16114.6791 |  | 16114.6791 |  | 16114.6791
2026-01-11 | 97290.2571 |  | 16215.0429 |  | 16215.0429 |  | 16215.0429 |  | 16215.0429 |  | 16215.0429 |  | 16215.0429
2026-01-12 | 97892.4397 |  | 16315.4066 |  | 16315.4066 |  | 16315.4066 |  | 16315.4066 |  | 16315.4066 |  | 16315.4066
2026-01-13 | 98494.6222 |  | 16415.7704 |  | 16415.7704 |  | 16415.7704 |  | 16415.7704 |  | 16415.7704 |  | 16415.7704
2026-01-14 | 99096.8048 |  | 16516.1341 |  | 16516.1341 |  | 16516.1341 |  | 16516.1341 |  | 16516.1341 |  | 16516.1341
2026-01-15 | 99698.9873 |  | 16616.4979 |  | 16616.4979 |  | 16616.4979 |  | 16616.4979 |  | 16616.4979 |  | 16616.4979
2026-01-16 | 100301.1698 |  | 16716.8616 |  | 16716.8616 |  | 16716.8616 |  | 16716.8616 |  | 16716.8616 |  | 16716.8616
2026-01-17 | 100903.3524 |  | 16817.2254 |  | 16817.2254 |  | 16817.2254 |  | 16817.2254 |  | 16817.2254 |  | 16817.2254
2026-01-18 | 101505.5349 |  | 16917.5892 |  | 16917.5892 |  | 16917.5892 |  | 16917.5892 |  | 16917.5892 |  | 16917.5892
2026-01-19 | 102107.7175 |  | 17017.9529 |  | 17017.9529 |  | 17017.9529 |  | 17017.9529 |  | 17017.9529 |  | 17017.9529
2026-01-20 | 102709.9 |  | 17118.3167 |  | 17118.3167 |  | 17118.3167 |  | 17118.3167 |  | 17118.3167 |  | 17118.3167
2026-01-21 | 103312.0825 |  | 17218.6804 |  | 17218.6804 |  | 17218.6804 |  | 17218.6804 |  | 17218.6804 |  | 17218.6804
2026-01-22 | 103914.2651 |  | 17319.0442 |  | 17319.0442 |  | 17319.0442 |  | 17319.0442 |  | 17319.0442 |  | 17319.0442
2026-01-23 | 104516.4476 |  | 17419.4079 |  | 17419.4079 |  | 17419.4079 |  | 17419.4079 |  | 17419.4079 |  | 17419.4079
2026-01-24 | 105118.6302 |  | 17519.7717 |  | 17519.7717 |  | 17519.7717 |  | 17519.7717 |  | 17519.7717 |  | 17519.7717
2026-01-25 | 105720.8127 |  | 17620.1354 |  | 17620.1354 |  | 17620.1354 |  | 17620.1354 |  | 17620.1354 |  | 17620.1354
2026-01-26 | 106322.9952 |  | 17720.4992 |  | 17720.4992 |  | 17720.4992 |  | 17720.4992 |  | 17720.4992 |  | 17720.4992
2026-01-27 | 106925.1778 |  | 17820.863 |  | 17820.863 |  | 17820.863 |  | 17820.863 |  | 17820.863 |  | 17820.863
2026-01-28 | 107527.3603 |  | 17921.2267 |  | 17921.2267 |  | 17921.2267 |  | 17921.2267 |  | 17921.2267 |  | 17921.2267
2026-01-29 | 108129.5429 |  | 18021.5905 |  | 18021.5905 |  | 18021.5905 |  | 18021.5905 |  | 18021.5905 |  | 18021.5905
2026-01-30 | 108731.7254 |  | 18121.9542 |  | 18121.9542 |  | 18121.9542 |  | 18121.9542 |  | 18121.9542 |  | 18121.9542
2026-01-31 | 109333.9079 |  | 18222.318 |  | 18222.318 |  | 18222.318 |  | 18222.318 |  | 18222.318 |  | 18222.318
2026-02-01 | 109936.0905 |  | 18322.6817 |  | 18322.6817 |  | 18322.6817 |  | 18322.6817 |  | 18322.6817 |  | 18322.6817
2026-02-02 | 110538.273 |  | 18423.0455 |  | 18423.0455 |  | 18423.0455 |  | 18423.0455 |  | 18423.0455 |  | 18423.0455
2026-02-03 | 111140.4556 |  | 18523.4093 |  | 18523.4093 |  | 18523.4093 |  | 18523.4093 |  | 18523.4093 |  | 18523.4093
2026-02-04 | 111742.6381 |  | 18623.773 |  | 18623.773 |  | 18623.773 |  | 18623.773 |  | 18623.773 |  | 18623.773
2026-02-05 | 112344.8206 |  | 18724.1368 |  | 18724.1368 |  | 18724.1368 |  | 18724.1368 |  | 18724.1368 |  | 18724.1368
2026-02-06 | 112947.0032 |  | 18824.5005 |  | 18824.5005 |  | 18824.5005 |  | 18824.5005 |  | 18824.5005 |  | 18824.5005
2026-02-07 | 113549.1857 |  | 18924.8643 |  | 18924.8643 |  | 18924.8643 |  | 18924.8643 |  | 18924.8643 |  | 18924.8643
2026-02-08 | 114151.3683 |  | 19025.228 |  | 19025.228 |  | 19025.228 |  | 19025.228 |  | 19025.228 |  | 19025.228
2026-02-09 | 114753.5508 |  | 19125.5918 |  | 19125.5918 |  | 19125.5918 |  | 19125.5918 |  | 19125.5918 |  | 19125.5918
2026-02-10 | 115355.7333 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556
2026-02-11 | 115675.3825 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304
2026-02-12 | 115995.0316 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053
2026-02-13 | 116314.6807 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801
2026-02-14 | 116634.3298 |  | 19439.055 |  | 19439.055 |  | 19439.055 |  | 19439.055 |  | 19439.055 |  | 19439.055
2026-02-15 | 116953.9789 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298
2026-02-16 | 117273.6281 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047
2026-02-17 | 117593.2772 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795
2026-02-18 | 117912.9263 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544
2026-02-19 | 118232.5754 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292
2026-02-20 | 118552.2246 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041
2026-02-21 | 118871.8737 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789
2026-02-22 | 119191.5228 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538
2026-02-23 | 119511.1719 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287
2026-02-24 | 119830.8211 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035
2026-02-25 | 120150.4702 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784
2026-02-26 | 120470.1193 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532
2026-02-27 | 120789.7684 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281
2026-02-28 | 121109.4175 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029
2026-03-01 | 121429.0667 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778
2026-03-02 | 121748.7158 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526
2026-03-03 | 122068.3649 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275
2026-03-04 | 122388.014 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023
2026-03-05 | 122707.6632 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772
2026-03-06 | 123027.3123 |  | 20504.552 |  | 20504.552 |  | 20504.552 |  | 20504.552 |  | 20504.552 |  | 20504.552
2026-03-07 | 123346.9614 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269
2026-03-08 | 123666.6105 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018
2026-03-09 | 123986.2596 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766
2026-03-10 | 124305.9088 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515
2026-03-11 | 124625.5579 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263
2026-03-12 | 124945.207 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012
2026-03-13 | 125264.8561 |  | 20877.476 |  | 20877.476 |  | 20877.476 |  | 20877.476 |  | 20877.476 |  | 20877.476
2026-03-14 | 125584.5053 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509
2026-03-15 | 125904.1544 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257
2026-03-16 | 126223.8035 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006
2026-03-17 | 126543.4526 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754
2026-03-18 | 126863.1018 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503
2026-03-19 | 127182.7509 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251
2026-03-20 | 127502.4 |  | 21250.4 |  | 21250.4 |  | 21250.4 |  | 21250.4 |  | 21250.4 |  | 21250.4
2026-03-21 | 127822.0491 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749
2026-03-22 | 128141.6982 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497
2026-03-23 | 128461.3474 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246
2026-03-24 | 128780.9965 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994
2026-03-25 | 129100.6456 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743
2026-03-26 | 129420.2947 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491
2026-03-27 | 129739.9439 |  | 21623.324 |  | 21623.324 |  | 21623.324 |  | 21623.324 |  | 21623.324 |  | 21623.324
2026-03-28 | 130059.593 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988
2026-03-29 | 130379.2421 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737
2026-03-30 | 130698.8912 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485
2026-03-31 | 131018.5404 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234
2026-04-01 | 131338.1895 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982
2026-04-02 | 131657.8386 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731
2026-04-03 | 131977.4877 |  | 21996.248 |  | 21996.248 |  | 21996.248 |  | 21996.248 |  | 21996.248 |  | 21996.248
2026-04-04 | 132297.1368 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228
2026-04-05 | 132616.786 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977
2026-04-06 | 132936.4351 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725
2026-04-07 | 133256.0842 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474
2026-04-08 | 133575.7333 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222
2026-04-09 | 133895.3825 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971
2026-04-10 | 134215.0316 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719
2026-04-11 | 134534.6807 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468
2026-04-12 | 134854.3298 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216
2026-04-13 | 135173.9789 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965
2026-04-14 | 135493.6281 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713
2026-04-15 | 135813.2772 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462
2026-04-16 | 136132.9263 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211
2026-04-17 | 136452.5754 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959
2026-04-18 | 136772.2246 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708
2026-04-19 | 137091.8737 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456
2026-04-20 | 137411.5228 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205
2026-04-21 | 137731.1719 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953
2026-04-22 | 138050.8211 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702
2026-04-23 | 138370.4702 |  | 23061.745 |  | 23061.745 |  | 23061.745 |  | 23061.745 |  | 23061.745 |  | 23061.745
2026-04-24 | 138690.1193 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199
2026-04-25 | 139009.7684 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947
2026-04-26 | 139329.4175 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696
2026-04-27 | 139649.0667 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444
2026-04-28 | 139968.7158 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193
2026-04-29 | 140288.3649 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942
2026-04-30 | 140608.014 |  | 23434.669 |  | 23434.669 |  | 23434.669 |  | 23434.669 |  | 23434.669 |  | 23434.669
2026-05-01 | 140927.6632 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439
2026-05-02 | 141247.3123 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187
2026-05-03 | 141566.9614 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936
2026-05-04 | 141886.6105 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684
2026-05-05 | 142206.2596 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433
2026-05-06 | 142525.9088 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181
2026-05-07 | 142845.5579 |  | 23807.593 |  | 23807.593 |  | 23807.593 |  | 23807.593 |  | 23807.593 |  | 23807.593
2026-05-08 | 143165.207 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678
2026-05-09 | 143484.8561 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427
2026-05-10 | 143804.5053 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175
2026-05-11 | 144124.1544 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924
2026-05-12 | 144443.8035 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673
2026-05-13 | 144763.4526 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421
2026-05-14 | 145083.1018 |  | 24180.517 |  | 24180.517 |  | 24180.517 |  | 24180.517 |  | 24180.517 |  | 24180.517
2026-05-15 | 145402.7509 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918
2026-05-16 | 145722.4 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667
2026-05-17 | 146042.0491 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415
2026-05-18 | 146361.6982 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164
2026-05-19 | 146681.3474 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912
2026-05-20 | 147000.9965 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661
2026-05-21 | 147320.6456 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409
2026-05-22 | 147640.2947 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158
2026-05-23 | 147959.9439 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906
2026-05-24 | 148279.593 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655
2026-05-25 | 148599.2421 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404
2026-05-26 | 148918.8912 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152
2026-05-27 | 149238.5404 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901
2026-05-28 | 149558.1895 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649
2026-05-29 | 149877.8386 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398
2026-05-30 | 150197.4877 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146
2026-05-31 | 150517.1368 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895
2026-06-01 | 150836.786 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643
2026-06-02 | 151156.4351 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392
2026-06-03 | 151476.0842 |  | 25246.014 |  | 25246.014 |  | 25246.014 |  | 25246.014 |  | 25246.014 |  | 25246.014
2026-06-04 | 151795.7333 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889
2026-06-05 | 152115.3825 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637
2026-06-06 | 152435.0316 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386
2026-06-07 | 152754.6807 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135
2026-06-08 | 153074.3298 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883
2026-06-09 | 153393.9789 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632
2026-06-10 | 153713.6281 |  | 25618.938 |  | 25618.938 |  | 25618.938 |  | 25618.938 |  | 25618.938 |  | 25618.938
2026-06-11 | 154033.2772 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129
2026-06-12 | 154352.9263 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877
2026-06-13 | 154672.5754 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626
2026-06-14 | 154992.2246 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374
2026-06-15 | 155311.8737 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123
2026-06-16 | 155631.5228 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871
2026-06-17 | 155951.1719 |  | 25991.862 |  | 25991.862 |  | 25991.862 |  | 25991.862 |  | 25991.862 |  | 25991.862
2026-06-18 | 156270.8211 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368
2026-06-19 | 156590.4702 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117
2026-06-20 | 156910.1193 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865
2026-06-21 | 157229.7684 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614
2026-06-22 | 157549.4175 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363
2026-06-23 | 157869.0667 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111
2026-06-24 | 158188.7158 |  | 26364.786 |  | 26364.786 |  | 26364.786 |  | 26364.786 |  | 26364.786 |  | 26364.786
2026-06-25 | 158508.3649 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608
2026-06-26 | 158828.014 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357
2026-06-27 | 159147.6632 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105
2026-06-28 | 159467.3123 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854
2026-06-29 | 159786.9614 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602
2026-06-30 | 160106.6105 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351
2026-07-01 | 160426.2596 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099
2026-07-02 | 160745.9088 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848
2026-07-03 | 161065.5579 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596
2026-07-04 | 161385.207 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345
2026-07-05 | 161704.8561 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094
2026-07-06 | 162024.5053 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842
2026-07-07 | 162344.1544 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591
2026-07-08 | 162663.8035 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339
2026-07-09 | 162983.4526 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088
2026-07-10 | 163303.1018 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836
2026-07-11 | 163622.7509 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585
2026-07-12 | 163942.4 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333
2026-07-13 | 164262.0491 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082
2026-07-14 | 164581.6982 |  | 27430.283 |  | 27430.283 |  | 27430.283 |  | 27430.283 |  | 27430.283 |  | 27430.283
2026-07-15 | 164901.3474 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579
2026-07-16 | 165220.9965 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327
2026-07-17 | 165540.6456 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076
2026-07-18 | 165860.2947 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825
2026-07-19 | 166179.9439 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573
2026-07-20 | 166499.593 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322
2026-07-21 | 166819.2421 |  | 27803.207 |  | 27803.207 |  | 27803.207 |  | 27803.207 |  | 27803.207 |  | 27803.207
2026-07-22 | 167138.8912 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819
2026-07-23 | 167458.5404 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567
2026-07-24 | 167778.1895 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316
2026-07-25 | 168097.8386 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064
2026-07-26 | 168417.4877 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813
2026-07-27 | 168737.1368 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561
2026-07-28 | 169056.786 |  | 28176.131 |  | 28176.131 |  | 28176.131 |  | 28176.131 |  | 28176.131 |  | 28176.131
2026-07-29 | 169376.4351 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058
2026-07-30 | 169696.0842 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807
2026-07-31 | 170015.7333 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556
2026-08-01 | 170335.3825 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304
2026-08-02 | 170655.0316 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053
2026-08-03 | 170974.6807 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801
2026-08-04 | 171294.3298 |  | 28549.055 |  | 28549.055 |  | 28549.055 |  | 28549.055 |  | 28549.055 |  | 28549.055
2026-08-05 | 171613.9789 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298
2026-08-06 | 171933.6281 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047
2026-08-07 | 172253.2772 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795
2026-08-08 | 172572.9263 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544
2026-08-09 | 172892.5754 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292
2026-08-10 | 173212.2246 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041
2026-08-11 | 173531.8737 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789
2026-08-12 | 173851.5228 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538
2026-08-13 | 174171.1719 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287
2026-08-14 | 174490.8211 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035
2026-08-15 | 174810.4702 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784
2026-08-16 | 175130.1193 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532
2026-08-17 | 175449.7684 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281
2026-08-18 | 175769.4175 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029
2026-08-19 | 176089.0667 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778
2026-08-20 | 176524.851 |  | 29420.8085 |  | 29420.8085 |  | 29420.8085 |  | 29420.8085 |  | 29420.8085 |  | 29420.8085
2026-08-21 | 176960.6353 |  | 29493.4392 |  | 29493.4392 |  | 29493.4392 |  | 29493.4392 |  | 29493.4392 |  | 29493.4392
2026-08-22 | 177396.4196 |  | 29566.0699 |  | 29566.0699 |  | 29566.0699 |  | 29566.0699 |  | 29566.0699 |  | 29566.0699
2026-08-23 | 177832.2039 |  | 29638.7007 |  | 29638.7007 |  | 29638.7007 |  | 29638.7007 |  | 29638.7007 |  | 29638.7007
2026-08-24 | 178267.9882 |  | 29711.3314 |  | 29711.3314 |  | 29711.3314 |  | 29711.3314 |  | 29711.3314 |  | 29711.3314
2026-08-25 | 178703.7725 |  | 29783.9621 |  | 29783.9621 |  | 29783.9621 |  | 29783.9621 |  | 29783.9621 |  | 29783.9621
2026-08-26 | 179139.5569 |  | 29856.5928 |  | 29856.5928 |  | 29856.5928 |  | 29856.5928 |  | 29856.5928 |  | 29856.5928
2026-08-27 | 179575.3412 |  | 29929.2235 |  | 29929.2235 |  | 29929.2235 |  | 29929.2235 |  | 29929.2235 |  | 29929.2235
2026-08-28 | 180011.1255 |  | 30001.8542 |  | 30001.8542 |  | 30001.8542 |  | 30001.8542 |  | 30001.8542 |  | 30001.8542
2026-08-29 | 180446.9098 |  | 30074.485 |  | 30074.485 |  | 30074.485 |  | 30074.485 |  | 30074.485 |  | 30074.485
2026-08-30 | 180882.6941 |  | 30147.1157 |  | 30147.1157 |  | 30147.1157 |  | 30147.1157 |  | 30147.1157 |  | 30147.1157
2026-08-31 | 181318.4784 |  | 30219.7464 |  | 30219.7464 |  | 30219.7464 |  | 30219.7464 |  | 30219.7464 |  | 30219.7464
2026-09-01 | 181754.2627 |  | 30292.3771 |  | 30292.3771 |  | 30292.3771 |  | 30292.3771 |  | 30292.3771 |  | 30292.3771
2026-09-02 | 182190.0471 |  | 30365.0078 |  | 30365.0078 |  | 30365.0078 |  | 30365.0078 |  | 30365.0078 |  | 30365.0078
2026-09-03 | 182625.8314 |  | 30437.6386 |  | 30437.6386 |  | 30437.6386 |  | 30437.6386 |  | 30437.6386 |  | 30437.6386
2026-09-04 | 183061.6157 |  | 30510.2693 |  | 30510.2693 |  | 30510.2693 |  | 30510.2693 |  | 30510.2693 |  | 30510.2693
2026-09-05 | 183497.4 |  | 30582.9 |  | 30582.9 |  | 30582.9 |  | 30582.9 |  | 30582.9 |  | 30582.9
2026-09-06 | 183933.1843 |  | 30655.5307 |  | 30655.5307 |  | 30655.5307 |  | 30655.5307 |  | 30655.5307 |  | 30655.5307
2026-09-07 | 184368.9686 |  | 30728.1614 |  | 30728.1614 |  | 30728.1614 |  | 30728.1614 |  | 30728.1614 |  | 30728.1614
2026-09-08 | 184804.7529 |  | 30800.7922 |  | 30800.7922 |  | 30800.7922 |  | 30800.7922 |  | 30800.7922 |  | 30800.7922
2026-09-09 | 185240.5373 |  | 30873.4229 |  | 30873.4229 |  | 30873.4229 |  | 30873.4229 |  | 30873.4229 |  | 30873.4229
2026-09-10 | 185676.3216 |  | 30946.0536 |  | 30946.0536 |  | 30946.0536 |  | 30946.0536 |  | 30946.0536 |  | 30946.0536
2026-09-11 | 186112.1059 |  | 31018.6843 |  | 31018.6843 |  | 31018.6843 |  | 31018.6843 |  | 31018.6843 |  | 31018.6843
2026-09-12 | 186547.8902 |  | 31091.315 |  | 31091.315 |  | 31091.315 |  | 31091.315 |  | 31091.315 |  | 31091.315
2026-09-13 | 186983.6745 |  | 31163.9458 |  | 31163.9458 |  | 31163.9458 |  | 31163.9458 |  | 31163.9458 |  | 31163.9458
2026-09-14 | 187419.4588 |  | 31236.5765 |  | 31236.5765 |  | 31236.5765 |  | 31236.5765 |  | 31236.5765 |  | 31236.5765
2026-09-15 | 187855.2431 |  | 31309.2072 |  | 31309.2072 |  | 31309.2072 |  | 31309.2072 |  | 31309.2072 |  | 31309.2072
2026-09-16 | 188291.0275 |  | 31381.8379 |  | 31381.8379 |  | 31381.8379 |  | 31381.8379 |  | 31381.8379 |  | 31381.8379
2026-09-17 | 188726.8118 |  | 31454.4686 |  | 31454.4686 |  | 31454.4686 |  | 31454.4686 |  | 31454.4686 |  | 31454.4686
2026-09-18 | 189162.5961 |  | 31527.0993 |  | 31527.0993 |  | 31527.0993 |  | 31527.0993 |  | 31527.0993 |  | 31527.0993
2026-09-19 | 189598.3804 |  | 31599.7301 |  | 31599.7301 |  | 31599.7301 |  | 31599.7301 |  | 31599.7301 |  | 31599.7301
2026-09-20 | 190034.1647 |  | 31672.3608 |  | 31672.3608 |  | 31672.3608 |  | 31672.3608 |  | 31672.3608 |  | 31672.3608
2026-09-21 | 190469.949 |  | 31744.9915 |  | 31744.9915 |  | 31744.9915 |  | 31744.9915 |  | 31744.9915 |  | 31744.9915
2026-09-22 | 190905.7333 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222

## Parts&materials (Direct Cost)
Date | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Planned 5004 · GTR Cost of Sales - Parts (Cumulative) | Actual 5004 · GTR Cost of Sales - Parts (Cumulative) | Planned 5111 · Parts & material costs (Direct) (Cumulative) | Actual 5111 · Parts & material costs (Direct) (Cumulative) | Planned 5128 · Health & Safety Equip (Direct) (Cumulative) | Actual 5128 · Health & Safety Equip (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-12 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-13 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-14 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-15 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-16 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-17 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-18 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-19 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-20 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-21 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-22 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-23 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-24 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-25 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-26 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-27 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-28 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-29 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-30 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-01 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-02 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-03 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-04 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-05 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-06 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-07 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-08 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-09 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-10 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-11 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-12 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-13 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-14 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-15 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-16 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-17 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-18 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-19 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-20 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-21 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-22 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-23 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-24 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-25 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-26 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-27 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-28 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-29 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-30 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-31 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-01 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-02 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-03 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-04 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-05 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-06 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-07 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-08 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-09 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-10 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-11 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-12 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-13 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-14 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-15 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-16 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-17 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-18 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-19 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-20 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-21 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-22 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-23 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-24 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-25 | 713.6371 | 979.62 | 237.879 | 0 | 237.879 | 979.62 | 237.879 | 0
2025-06-26 | 1427.2742 | 979.62 | 475.7581 | 0 | 475.7581 | 979.62 | 475.7581 | 0
2025-06-27 | 2140.9112 | 979.62 | 713.6371 | 0 | 713.6371 | 979.62 | 713.6371 | 0
2025-06-28 | 2854.5483 | 979.62 | 951.5161 | 0 | 951.5161 | 979.62 | 951.5161 | 0
2025-06-29 | 3568.1854 | 979.62 | 1189.3951 | 0 | 1189.3951 | 979.62 | 1189.3951 | 0
2025-06-30 | 4281.8225 | 979.62 | 1427.2742 | 0 | 1427.2742 | 979.62 | 1427.2742 | 0
2025-07-01 | 4995.4596 | 979.62 | 1665.1532 | 0 | 1665.1532 | 979.62 | 1665.1532 | 0
2025-07-02 | 5709.0966 | 979.62 | 1903.0322 | 0 | 1903.0322 | 979.62 | 1903.0322 | 0
2025-07-03 | 6422.7337 | 979.62 | 2140.9112 | 0 | 2140.9112 | 979.62 | 2140.9112 | 0
2025-07-04 | 7136.3708 | 979.62 | 2378.7903 | 0 | 2378.7903 | 979.62 | 2378.7903 | 0
2025-07-05 | 7850.0079 | 979.62 | 2616.6693 | 0 | 2616.6693 | 979.62 | 2616.6693 | 0
2025-07-06 | 8563.6449 | 979.62 | 2854.5483 | 0 | 2854.5483 | 979.62 | 2854.5483 | 0
2025-07-07 | 9277.282 | 979.62 | 3092.4273 | 0 | 3092.4273 | 979.62 | 3092.4273 | 0
2025-07-08 | 9990.9191 | 979.62 | 3330.3064 | 0 | 3330.3064 | 979.62 | 3330.3064 | 0
2025-07-09 | 10704.5562 | 979.62 | 3568.1854 | 0 | 3568.1854 | 979.62 | 3568.1854 | 0
2025-07-10 | 11418.1933 | 979.62 | 3806.0644 | 0 | 3806.0644 | 979.62 | 3806.0644 | 0
2025-07-11 | 12131.8303 | 979.62 | 4043.9434 | 0 | 4043.9434 | 979.62 | 4043.9434 | 0
2025-07-12 | 12845.4674 | 979.62 | 4281.8225 | 0 | 4281.8225 | 979.62 | 4281.8225 | 0
2025-07-13 | 13559.1045 | 979.62 | 4519.7015 | 0 | 4519.7015 | 979.62 | 4519.7015 | 0
2025-07-14 | 14272.7416 | 979.62 | 4757.5805 | 0 | 4757.5805 | 979.62 | 4757.5805 | 0
2025-07-15 | 14986.3787 | 979.62 | 4995.4596 | 0 | 4995.4596 | 979.62 | 4995.4596 | 0
2025-07-16 | 15700.0157 | 979.62 | 5233.3386 | 0 | 5233.3386 | 979.62 | 5233.3386 | 0
2025-07-17 | 16413.6528 | 979.62 | 5471.2176 | 0 | 5471.2176 | 979.62 | 5471.2176 | 0
2025-07-18 | 17127.2899 | 979.62 | 5709.0966 | 0 | 5709.0966 | 979.62 | 5709.0966 | 0
2025-07-19 | 17840.927 | 979.62 | 5946.9757 | 0 | 5946.9757 | 979.62 | 5946.9757 | 0
2025-07-20 | 18554.564 | 979.62 | 6184.8547 | 0 | 6184.8547 | 979.62 | 6184.8547 | 0
2025-07-21 | 19268.2011 | 979.62 | 6422.7337 | 0 | 6422.7337 | 979.62 | 6422.7337 | 0
2025-07-22 | 19981.8382 | 979.62 | 6660.6127 | 0 | 6660.6127 | 979.62 | 6660.6127 | 0
2025-07-23 | 20695.4753 | 979.62 | 6898.4918 | 0 | 6898.4918 | 979.62 | 6898.4918 | 0
2025-07-24 | 21409.1124 | 979.62 | 7136.3708 | 0 | 7136.3708 | 979.62 | 7136.3708 | 0
2025-07-25 | 22122.7494 | 979.62 | 7374.2498 | 0 | 7374.2498 | 979.62 | 7374.2498 | 0
2025-07-26 | 22836.3865 | 979.62 | 7612.1288 | 0 | 7612.1288 | 979.62 | 7612.1288 | 0
2025-07-27 | 23550.0236 | 979.62 | 7850.0079 | 0 | 7850.0079 | 979.62 | 7850.0079 | 0
2025-07-28 | 24263.6607 | 979.62 | 8087.8869 | 0 | 8087.8869 | 979.62 | 8087.8869 | 0
2025-07-29 | 24977.2978 | 979.62 | 8325.7659 | 0 | 8325.7659 | 979.62 | 8325.7659 | 0
2025-07-30 | 25690.9348 | 979.62 | 8563.6449 | 0 | 8563.6449 | 979.62 | 8563.6449 | 0
2025-07-31 | 26404.5719 | 979.62 | 8801.524 | 0 | 8801.524 | 979.62 | 8801.524 | 0
2025-08-01 | 27118.209 | 979.62 | 9039.403 | 0 | 9039.403 | 979.62 | 9039.403 | 0
2025-08-02 | 27831.8461 | 979.62 | 9277.282 | 0 | 9277.282 | 979.62 | 9277.282 | 0
2025-08-03 | 28545.4831 | 979.62 | 9515.161 | 0 | 9515.161 | 979.62 | 9515.161 | 0
2025-08-04 | 29259.1202 | 2348.77 | 9753.0401 | 0 | 9753.0401 | 2348.77 | 9753.0401 | 0
2025-08-05 | 29972.7573 | 2348.77 | 9990.9191 | 0 | 9990.9191 | 2348.77 | 9990.9191 | 0
2025-08-06 | 30686.3944 | 2348.77 | 10228.7981 | 0 | 10228.7981 | 2348.77 | 10228.7981 | 0
2025-08-07 | 31400.0315 | 3299.64 | 10466.6772 | 0 | 10466.6772 | 3299.64 | 10466.6772 | 0
2025-08-08 | 32113.6685 | 3299.64 | 10704.5562 | 0 | 10704.5562 | 3299.64 | 10704.5562 | 0
2025-08-09 | 32827.3056 | 3299.64 | 10942.4352 | 0 | 10942.4352 | 3299.64 | 10942.4352 | 0
2025-08-10 | 33540.9427 | 3299.64 | 11180.3142 | 0 | 11180.3142 | 3299.64 | 11180.3142 | 0
2025-08-11 | 34254.5798 | 3566.53 | 11418.1933 | 0 | 11418.1933 | 3566.53 | 11418.1933 | 0
2025-08-12 | 34968.2169 | 3566.53 | 11656.0723 | 0 | 11656.0723 | 3566.53 | 11656.0723 | 0
2025-08-13 | 35681.8539 | 3566.53 | 11893.9513 | 0 | 11893.9513 | 3566.53 | 11893.9513 | 0
2025-08-14 | 36395.491 | 3566.53 | 12131.8303 | 0 | 12131.8303 | 3566.53 | 12131.8303 | 0
2025-08-15 | 37109.1281 | 3566.53 | 12369.7094 | 0 | 12369.7094 | 3566.53 | 12369.7094 | 0
2025-08-16 | 37822.7652 | 3566.53 | 12607.5884 | 0 | 12607.5884 | 3566.53 | 12607.5884 | 0
2025-08-17 | 38536.4022 | 3566.53 | 12845.4674 | 0 | 12845.4674 | 3566.53 | 12845.4674 | 0
2025-08-18 | 39250.0393 | 3566.53 | 13083.3464 | 0 | 13083.3464 | 3566.53 | 13083.3464 | 0
2025-08-19 | 39963.6764 | 16075.89 | 13321.2255 | 0 | 13321.2255 | 16075.89 | 13321.2255 | 0
2025-08-20 | 40677.3135 | 16075.89 | 13559.1045 | 0 | 13559.1045 | 16075.89 | 13559.1045 | 0
2025-08-21 | 41390.9506 | 16075.89 | 13796.9835 | 0 | 13796.9835 | 16075.89 | 13796.9835 | 0
2025-08-22 | 42104.5876 | 16075.89 | 14034.8625 | 0 | 14034.8625 | 16075.89 | 14034.8625 | 0
2025-08-23 | 42818.2247 | 16075.89 | 14272.7416 | 0 | 14272.7416 | 16075.89 | 14272.7416 | 0
2025-08-24 | 43531.8618 | 16075.89 | 14510.6206 | 0 | 14510.6206 | 16075.89 | 14510.6206 | 0
2025-08-25 | 44245.4989 | 16795.65 | 14748.4996 | 0 | 14748.4996 | 16795.65 | 14748.4996 | 0
2025-08-26 | 44959.136 | 16795.65 | 14986.3787 | 0 | 14986.3787 | 16795.65 | 14986.3787 | 0
2025-08-27 | 45672.773 | 16795.65 | 15224.2577 | 0 | 15224.2577 | 16795.65 | 15224.2577 | 0
2025-08-28 | 46386.4101 | 16795.65 | 15462.1367 | 0 | 15462.1367 | 16795.65 | 15462.1367 | 0
2025-08-29 | 47100.0472 | 16795.65 | 15700.0157 | 0 | 15700.0157 | 16795.65 | 15700.0157 | 0
2025-08-30 | 47813.6843 | 16795.65 | 15937.8948 | 0 | 15937.8948 | 16795.65 | 15937.8948 | 0
2025-08-31 | 48527.3213 | 16795.65 | 16175.7738 | 0 | 16175.7738 | 16795.65 | 16175.7738 | 0
2025-09-01 | 49240.9584 | 16795.65 | 16413.6528 | 0 | 16413.6528 | 16795.65 | 16413.6528 | 0
2025-09-02 | 49954.5955 | 19920.45 | 16651.5318 | 0 | 16651.5318 | 19920.45 | 16651.5318 | 0
2025-09-03 | 50668.2326 | 19920.45 | 16889.4109 | 0 | 16889.4109 | 19920.45 | 16889.4109 | 0
2025-09-04 | 51381.8697 | 19920.45 | 17127.2899 | 0 | 17127.2899 | 19920.45 | 17127.2899 | 0
2025-09-05 | 52095.5067 | 19920.45 | 17365.1689 | 0 | 17365.1689 | 19920.45 | 17365.1689 | 0
2025-09-06 | 52809.1438 | 19920.45 | 17603.0479 | 0 | 17603.0479 | 19920.45 | 17603.0479 | 0
2025-09-07 | 53522.7809 | 19920.45 | 17840.927 | 0 | 17840.927 | 19920.45 | 17840.927 | 0
2025-09-08 | 54236.418 | 19920.45 | 18078.806 | 0 | 18078.806 | 19920.45 | 18078.806 | 0
2025-09-09 | 54950.0551 | 20562.81 | 18316.685 | 0 | 18316.685 | 20562.81 | 18316.685 | 0
2025-09-10 | 55663.6921 | 20562.81 | 18554.564 | 0 | 18554.564 | 20562.81 | 18554.564 | 0
2025-09-11 | 56377.3292 | 20562.81 | 18792.4431 | 0 | 18792.4431 | 20562.81 | 18792.4431 | 0
2025-09-12 | 57090.9663 | 20562.81 | 19030.3221 | 0 | 19030.3221 | 20562.81 | 19030.3221 | 0
2025-09-13 | 57804.6034 | 20562.81 | 19268.2011 | 0 | 19268.2011 | 20562.81 | 19268.2011 | 0
2025-09-14 | 58518.2404 | 20562.81 | 19506.0801 | 0 | 19506.0801 | 20562.81 | 19506.0801 | 0
2025-09-15 | 59231.8775 | 20562.81 | 19743.9592 | 0 | 19743.9592 | 20562.81 | 19743.9592 | 0
2025-09-16 | 59945.5146 | 20562.81 | 19981.8382 | 0 | 19981.8382 | 20562.81 | 19981.8382 | 0
2025-09-17 | 60659.1517 | 20562.81 | 20219.7172 | 0 | 20219.7172 | 20562.81 | 20219.7172 | 0
2025-09-18 | 61372.7888 | 20562.81 | 20457.5963 | 0 | 20457.5963 | 20562.81 | 20457.5963 | 0
2025-09-19 | 62086.4258 | 20562.81 | 20695.4753 | 0 | 20695.4753 | 20562.81 | 20695.4753 | 0
2025-09-20 | 62800.0629 | 20562.81 | 20933.3543 | 0 | 20933.3543 | 20562.81 | 20933.3543 | 0
2025-09-21 | 63513.7 | 20562.81 | 21171.2333 | 0 | 21171.2333 | 20562.81 | 21171.2333 | 0
2025-09-22 | 63513.7 | 20562.81 | 21171.2333 | 0 | 21171.2333 | 20562.81 | 21171.2333 | 0
2025-09-23 | 63513.7 | 20562.81 | 21171.2333 | 0 | 21171.2333 | 20562.81 | 21171.2333 | 0
2025-09-24 | 63513.7 | 23165.94 | 21171.2333 | 0 | 21171.2333 | 23165.94 | 21171.2333 | 0
2025-09-25 | 63513.7 | 24111.65 | 21171.2333 | 0 | 21171.2333 | 23820.67 | 21171.2333 | 290.98
2025-09-26 | 63513.7 | 24111.65 | 21171.2333 | 0 | 21171.2333 | 23820.67 | 21171.2333 | 290.98
2025-09-27 | 63513.7 | 24111.65 | 21171.2333 | 0 | 21171.2333 | 23820.67 | 21171.2333 | 290.98
2025-09-28 | 63513.7 | 24111.65 | 21171.2333 | 0 | 21171.2333 | 23820.67 | 21171.2333 | 290.98
2025-09-29 | 64342.5167 | 31354.22 | 21447.5056 | 0 | 21447.5056 | 31063.24 | 21447.5056 | 290.98
2025-09-30 | 65171.3334 | 31354.22 | 21723.7778 | 0 | 21723.7778 | 31063.24 | 21723.7778 | 290.98
2025-10-01 | 66000.1501 | 31354.22 | 22000.05 | 0 | 22000.05 | 31063.24 | 22000.05 | 290.98
2025-10-02 | 66828.9668 | 31354.22 | 22276.3223 | 0 | 22276.3223 | 31063.24 | 22276.3223 | 290.98
2025-10-03 | 67657.7835 | 31354.22 | 22552.5945 | 0 | 22552.5945 | 31063.24 | 22552.5945 | 290.98
2025-10-04 | 68486.6003 | 31354.22 | 22828.8668 | 0 | 22828.8668 | 31063.24 | 22828.8668 | 290.98
2025-10-05 | 69315.417 | 31354.22 | 23105.139 | 0 | 23105.139 | 31063.24 | 23105.139 | 290.98
2025-10-06 | 70144.2337 | 31354.22 | 23381.4112 | 0 | 23381.4112 | 31063.24 | 23381.4112 | 290.98
2025-10-07 | 70973.0504 | 31354.22 | 23657.6835 | 0 | 23657.6835 | 31063.24 | 23657.6835 | 290.98
2025-10-08 | 71801.8671 | 31354.22 | 23933.9557 | 0 | 23933.9557 | 31063.24 | 23933.9557 | 290.98
2025-10-09 | 72630.6838 | 31354.22 | 24210.2279 | 0 | 24210.2279 | 31063.24 | 24210.2279 | 290.98
2025-10-10 | 73459.5005 | 31354.22 | 24486.5002 | 0 | 24486.5002 | 31063.24 | 24486.5002 | 290.98
2025-10-11 | 74288.3172 | 31354.22 | 24762.7724 | 0 | 24762.7724 | 31063.24 | 24762.7724 | 290.98
2025-10-12 | 75117.1339 | 31354.22 | 25039.0446 | 0 | 25039.0446 | 31063.24 | 25039.0446 | 290.98
2025-10-13 | 75945.9506 | 31354.22 | 25315.3169 | 0 | 25315.3169 | 31063.24 | 25315.3169 | 290.98
2025-10-14 | 76774.7673 | 31354.22 | 25591.5891 | 0 | 25591.5891 | 31063.24 | 25591.5891 | 290.98
2025-10-15 | 77603.5841 | 31354.22 | 25867.8614 | 0 | 25867.8614 | 31063.24 | 25867.8614 | 290.98
2025-10-16 | 78432.4008 | 31354.22 | 26144.1336 | 0 | 26144.1336 | 31063.24 | 26144.1336 | 290.98
2025-10-17 | 79261.2175 | 31354.22 | 26420.4058 | 0 | 26420.4058 | 31063.24 | 26420.4058 | 290.98
2025-10-18 | 80090.0342 | 31354.22 | 26696.6781 | 0 | 26696.6781 | 31063.24 | 26696.6781 | 290.98
2025-10-19 | 80918.8509 | 31354.22 | 26972.9503 | 0 | 26972.9503 | 31063.24 | 26972.9503 | 290.98
2025-10-20 | 81747.6676 | 31354.22 | 27249.2225 | 0 | 27249.2225 | 31063.24 | 27249.2225 | 290.98
2025-10-21 | 82576.4843 | 31354.22 | 27525.4948 | 0 | 27525.4948 | 31063.24 | 27525.4948 | 290.98
2025-10-22 | 83405.301 | 31354.22 | 27801.767 | 0 | 27801.767 | 31063.24 | 27801.767 | 290.98
2025-10-23 | 84234.1177 | 31354.22 | 28078.0392 | 0 | 28078.0392 | 31063.24 | 28078.0392 | 290.98
2025-10-24 | 85062.9344 | 31354.22 | 28354.3115 | 0 | 28354.3115 | 31063.24 | 28354.3115 | 290.98
2025-10-25 | 85891.7512 | 31354.22 | 28630.5837 | 0 | 28630.5837 | 31063.24 | 28630.5837 | 290.98
2025-10-26 | 86720.5679 | 31354.22 | 28906.856 | 0 | 28906.856 | 31063.24 | 28906.856 | 290.98
2025-10-27 | 87549.3846 |  | 29183.1282 |  | 29183.1282 |  | 29183.1282
2025-10-28 | 88378.2013 |  | 29459.4004 |  | 29459.4004 |  | 29459.4004
2025-10-29 | 89207.018 |  | 29735.6727 |  | 29735.6727 |  | 29735.6727
2025-10-30 | 90035.8347 |  | 30011.9449 |  | 30011.9449 |  | 30011.9449
2025-10-31 | 90864.6514 |  | 30288.2171 |  | 30288.2171 |  | 30288.2171
2025-11-01 | 91693.4681 |  | 30564.4894 |  | 30564.4894 |  | 30564.4894
2025-11-02 | 92522.2848 |  | 30840.7616 |  | 30840.7616 |  | 30840.7616
2025-11-03 | 93351.1015 |  | 31117.0338 |  | 31117.0338 |  | 31117.0338
2025-11-04 | 94179.9182 |  | 31393.3061 |  | 31393.3061 |  | 31393.3061
2025-11-05 | 95008.735 |  | 31669.5783 |  | 31669.5783 |  | 31669.5783
2025-11-06 | 95837.5517 |  | 31945.8506 |  | 31945.8506 |  | 31945.8506
2025-11-07 | 96666.3684 |  | 32222.1228 |  | 32222.1228 |  | 32222.1228
2025-11-08 | 97495.1851 |  | 32498.395 |  | 32498.395 |  | 32498.395
2025-11-09 | 98324.0018 |  | 32774.6673 |  | 32774.6673 |  | 32774.6673
2025-11-10 | 99152.8185 |  | 33050.9395 |  | 33050.9395 |  | 33050.9395
2025-11-11 | 99981.6352 |  | 33327.2117 |  | 33327.2117 |  | 33327.2117
2025-11-12 | 100810.4519 |  | 33603.484 |  | 33603.484 |  | 33603.484
2025-11-13 | 101639.2686 |  | 33879.7562 |  | 33879.7562 |  | 33879.7562
2025-11-14 | 102468.0853 |  | 34156.0284 |  | 34156.0284 |  | 34156.0284
2025-11-15 | 103296.902 |  | 34432.3007 |  | 34432.3007 |  | 34432.3007
2025-11-16 | 104125.7188 |  | 34708.5729 |  | 34708.5729 |  | 34708.5729
2025-11-17 | 104954.5355 |  | 34984.8452 |  | 34984.8452 |  | 34984.8452
2025-11-18 | 105783.3522 |  | 35261.1174 |  | 35261.1174 |  | 35261.1174
2025-11-19 | 106470.495 |  | 35490.165 |  | 35490.165 |  | 35490.165
2025-11-20 | 107157.6379 |  | 35719.2126 |  | 35719.2126 |  | 35719.2126
2025-11-21 | 107844.7807 |  | 35948.2602 |  | 35948.2602 |  | 35948.2602
2025-11-22 | 108531.9236 |  | 36177.3079 |  | 36177.3079 |  | 36177.3079
2025-11-23 | 109219.0665 |  | 36406.3555 |  | 36406.3555 |  | 36406.3555
2025-11-24 | 109906.2093 |  | 36635.4031 |  | 36635.4031 |  | 36635.4031
2025-11-25 | 110593.3522 |  | 36864.4507 |  | 36864.4507 |  | 36864.4507
2025-11-26 | 111280.495 |  | 37093.4983 |  | 37093.4983 |  | 37093.4983
2025-11-27 | 111967.6379 |  | 37322.546 |  | 37322.546 |  | 37322.546
2025-11-28 | 112654.7807 |  | 37551.5936 |  | 37551.5936 |  | 37551.5936
2025-11-29 | 113341.9236 |  | 37780.6412 |  | 37780.6412 |  | 37780.6412
2025-11-30 | 114029.0665 |  | 38009.6888 |  | 38009.6888 |  | 38009.6888
2025-12-01 | 114716.2093 |  | 38238.7364 |  | 38238.7364 |  | 38238.7364
2025-12-02 | 115403.3522 |  | 38467.7841 |  | 38467.7841 |  | 38467.7841
2025-12-03 | 116090.495 |  | 38696.8317 |  | 38696.8317 |  | 38696.8317
2025-12-04 | 116777.6379 |  | 38925.8793 |  | 38925.8793 |  | 38925.8793
2025-12-05 | 117464.7807 |  | 39154.9269 |  | 39154.9269 |  | 39154.9269
2025-12-06 | 118151.9236 |  | 39383.9745 |  | 39383.9745 |  | 39383.9745
2025-12-07 | 118839.0665 |  | 39613.0222 |  | 39613.0222 |  | 39613.0222
2025-12-08 | 119526.2093 |  | 39842.0698 |  | 39842.0698 |  | 39842.0698
2025-12-09 | 120213.3522 |  | 40071.1174 |  | 40071.1174 |  | 40071.1174
2025-12-10 | 120900.495 |  | 40300.165 |  | 40300.165 |  | 40300.165
2025-12-11 | 121587.6379 |  | 40529.2126 |  | 40529.2126 |  | 40529.2126
2025-12-12 | 122274.7807 |  | 40758.2602 |  | 40758.2602 |  | 40758.2602
2025-12-13 | 122961.9236 |  | 40987.3079 |  | 40987.3079 |  | 40987.3079
2025-12-14 | 123649.0665 |  | 41216.3555 |  | 41216.3555 |  | 41216.3555
2025-12-15 | 124336.2093 |  | 41445.4031 |  | 41445.4031 |  | 41445.4031
2025-12-16 | 125023.3522 |  | 41674.4507 |  | 41674.4507 |  | 41674.4507
2025-12-17 | 125710.495 |  | 41903.4983 |  | 41903.4983 |  | 41903.4983
2025-12-18 | 126397.6379 |  | 42132.546 |  | 42132.546 |  | 42132.546
2025-12-19 | 127084.7807 |  | 42361.5936 |  | 42361.5936 |  | 42361.5936
2025-12-20 | 127771.9236 |  | 42590.6412 |  | 42590.6412 |  | 42590.6412
2025-12-21 | 128459.0665 |  | 42819.6888 |  | 42819.6888 |  | 42819.6888
2025-12-22 | 129146.2093 |  | 43048.7364 |  | 43048.7364 |  | 43048.7364
2025-12-23 | 129833.3522 |  | 43277.7841 |  | 43277.7841 |  | 43277.7841
2025-12-24 | 130520.495 |  | 43506.8317 |  | 43506.8317 |  | 43506.8317
2025-12-25 | 131207.6379 |  | 43735.8793 |  | 43735.8793 |  | 43735.8793
2025-12-26 | 131894.7807 |  | 43964.9269 |  | 43964.9269 |  | 43964.9269
2025-12-27 | 132581.9236 |  | 44193.9745 |  | 44193.9745 |  | 44193.9745
2025-12-28 | 133269.0665 |  | 44423.0222 |  | 44423.0222 |  | 44423.0222
2025-12-29 | 133956.2093 |  | 44652.0698 |  | 44652.0698 |  | 44652.0698
2025-12-30 | 134643.3522 |  | 44881.1174 |  | 44881.1174 |  | 44881.1174
2025-12-31 | 135330.495 |  | 45110.165 |  | 45110.165 |  | 45110.165
2026-01-01 | 136017.6379 |  | 45339.2126 |  | 45339.2126 |  | 45339.2126
2026-01-02 | 136704.7807 |  | 45568.2602 |  | 45568.2602 |  | 45568.2602
2026-01-03 | 137391.9236 |  | 45797.3079 |  | 45797.3079 |  | 45797.3079
2026-01-04 | 138079.0665 |  | 46026.3555 |  | 46026.3555 |  | 46026.3555
2026-01-05 | 138766.2093 |  | 46255.4031 |  | 46255.4031 |  | 46255.4031
2026-01-06 | 139453.3522 |  | 46484.4507 |  | 46484.4507 |  | 46484.4507
2026-01-07 | 140140.495 |  | 46713.4983 |  | 46713.4983 |  | 46713.4983
2026-01-08 | 140827.6379 |  | 46942.546 |  | 46942.546 |  | 46942.546
2026-01-09 | 141514.7807 |  | 47171.5936 |  | 47171.5936 |  | 47171.5936
2026-01-10 | 142201.9236 |  | 47400.6412 |  | 47400.6412 |  | 47400.6412
2026-01-11 | 142889.0665 |  | 47629.6888 |  | 47629.6888 |  | 47629.6888
2026-01-12 | 143576.2093 |  | 47858.7364 |  | 47858.7364 |  | 47858.7364
2026-01-13 | 144263.3522 |  | 48087.7841 |  | 48087.7841 |  | 48087.7841
2026-01-14 | 144950.495 |  | 48316.8317 |  | 48316.8317 |  | 48316.8317
2026-01-15 | 145637.6379 |  | 48545.8793 |  | 48545.8793 |  | 48545.8793
2026-01-16 | 146324.7807 |  | 48774.9269 |  | 48774.9269 |  | 48774.9269
2026-01-17 | 147011.9236 |  | 49003.9745 |  | 49003.9745 |  | 49003.9745
2026-01-18 | 147699.0665 |  | 49233.0222 |  | 49233.0222 |  | 49233.0222
2026-01-19 | 148386.2093 |  | 49462.0698 |  | 49462.0698 |  | 49462.0698
2026-01-20 | 149073.3522 |  | 49691.1174 |  | 49691.1174 |  | 49691.1174
2026-01-21 | 149760.495 |  | 49920.165 |  | 49920.165 |  | 49920.165
2026-01-22 | 150447.6379 |  | 50149.2126 |  | 50149.2126 |  | 50149.2126
2026-01-23 | 151134.7807 |  | 50378.2602 |  | 50378.2602 |  | 50378.2602
2026-01-24 | 151821.9236 |  | 50607.3079 |  | 50607.3079 |  | 50607.3079
2026-01-25 | 152509.0665 |  | 50836.3555 |  | 50836.3555 |  | 50836.3555
2026-01-26 | 153196.2093 |  | 51065.4031 |  | 51065.4031 |  | 51065.4031
2026-01-27 | 153883.3522 |  | 51294.4507 |  | 51294.4507 |  | 51294.4507
2026-01-28 | 154570.495 |  | 51523.4983 |  | 51523.4983 |  | 51523.4983
2026-01-29 | 155257.6379 |  | 51752.546 |  | 51752.546 |  | 51752.546
2026-01-30 | 155944.7807 |  | 51981.5936 |  | 51981.5936 |  | 51981.5936
2026-01-31 | 156631.9236 |  | 52210.6412 |  | 52210.6412 |  | 52210.6412
2026-02-01 | 157319.0665 |  | 52439.6888 |  | 52439.6888 |  | 52439.6888
2026-02-02 | 158006.2093 |  | 52668.7364 |  | 52668.7364 |  | 52668.7364
2026-02-03 | 158693.3522 |  | 52897.7841 |  | 52897.7841 |  | 52897.7841
2026-02-04 | 159380.495 |  | 53126.8317 |  | 53126.8317 |  | 53126.8317
2026-02-05 | 160067.6379 |  | 53355.8793 |  | 53355.8793 |  | 53355.8793
2026-02-06 | 160754.7807 |  | 53584.9269 |  | 53584.9269 |  | 53584.9269
2026-02-07 | 161441.9236 |  | 53813.9745 |  | 53813.9745 |  | 53813.9745
2026-02-08 | 162129.0665 |  | 54043.0222 |  | 54043.0222 |  | 54043.0222
2026-02-09 | 162816.2093 |  | 54272.0698 |  | 54272.0698 |  | 54272.0698
2026-02-10 | 163503.3522 |  | 54501.1174 |  | 54501.1174 |  | 54501.1174
2026-02-11 | 163545.0101 |  | 54515.0034 |  | 54515.0034 |  | 54515.0034
2026-02-12 | 163586.668 |  | 54528.8893 |  | 54528.8893 |  | 54528.8893
2026-02-13 | 163628.3259 |  | 54542.7753 |  | 54542.7753 |  | 54542.7753
2026-02-14 | 163669.9838 |  | 54556.6613 |  | 54556.6613 |  | 54556.6613
2026-02-15 | 163711.6416 |  | 54570.5472 |  | 54570.5472 |  | 54570.5472
2026-02-16 | 163753.2995 |  | 54584.4332 |  | 54584.4332 |  | 54584.4332
2026-02-17 | 163794.9574 |  | 54598.3191 |  | 54598.3191 |  | 54598.3191
2026-02-18 | 163836.6153 |  | 54612.2051 |  | 54612.2051 |  | 54612.2051
2026-02-19 | 163878.2732 |  | 54626.0911 |  | 54626.0911 |  | 54626.0911
2026-02-20 | 163919.9311 |  | 54639.977 |  | 54639.977 |  | 54639.977
2026-02-21 | 163961.589 |  | 54653.863 |  | 54653.863 |  | 54653.863
2026-02-22 | 164003.2469 |  | 54667.749 |  | 54667.749 |  | 54667.749
2026-02-23 | 164044.9048 |  | 54681.6349 |  | 54681.6349 |  | 54681.6349
2026-02-24 | 164086.5627 |  | 54695.5209 |  | 54695.5209 |  | 54695.5209
2026-02-25 | 164128.2206 |  | 54709.4069 |  | 54709.4069 |  | 54709.4069
2026-02-26 | 164169.8785 |  | 54723.2928 |  | 54723.2928 |  | 54723.2928
2026-02-27 | 164211.5364 |  | 54737.1788 |  | 54737.1788 |  | 54737.1788
2026-02-28 | 164253.1943 |  | 54751.0648 |  | 54751.0648 |  | 54751.0648
2026-03-01 | 164294.8522 |  | 54764.9507 |  | 54764.9507 |  | 54764.9507
2026-03-02 | 164336.5101 |  | 54778.8367 |  | 54778.8367 |  | 54778.8367
2026-03-03 | 164378.168 |  | 54792.7227 |  | 54792.7227 |  | 54792.7227
2026-03-04 | 164419.8259 |  | 54806.6086 |  | 54806.6086 |  | 54806.6086
2026-03-05 | 164461.4838 |  | 54820.4946 |  | 54820.4946 |  | 54820.4946
2026-03-06 | 164503.1416 |  | 54834.3805 |  | 54834.3805 |  | 54834.3805
2026-03-07 | 164544.7995 |  | 54848.2665 |  | 54848.2665 |  | 54848.2665
2026-03-08 | 164586.4574 |  | 54862.1525 |  | 54862.1525 |  | 54862.1525
2026-03-09 | 164628.1153 |  | 54876.0384 |  | 54876.0384 |  | 54876.0384
2026-03-10 | 164669.7732 |  | 54889.9244 |  | 54889.9244 |  | 54889.9244
2026-03-11 | 164711.4311 |  | 54903.8104 |  | 54903.8104 |  | 54903.8104
2026-03-12 | 164753.089 |  | 54917.6963 |  | 54917.6963 |  | 54917.6963
2026-03-13 | 164794.7469 |  | 54931.5823 |  | 54931.5823 |  | 54931.5823
2026-03-14 | 164836.4048 |  | 54945.4683 |  | 54945.4683 |  | 54945.4683
2026-03-15 | 164878.0627 |  | 54959.3542 |  | 54959.3542 |  | 54959.3542
2026-03-16 | 164919.7206 |  | 54973.2402 |  | 54973.2402 |  | 54973.2402
2026-03-17 | 164961.3785 |  | 54987.1262 |  | 54987.1262 |  | 54987.1262
2026-03-18 | 165003.0364 |  | 55001.0121 |  | 55001.0121 |  | 55001.0121
2026-03-19 | 165044.6943 |  | 55014.8981 |  | 55014.8981 |  | 55014.8981
2026-03-20 | 165086.3522 |  | 55028.7841 |  | 55028.7841 |  | 55028.7841
2026-03-21 | 165128.0101 |  | 55042.67 |  | 55042.67 |  | 55042.67
2026-03-22 | 165169.668 |  | 55056.556 |  | 55056.556 |  | 55056.556
2026-03-23 | 165211.3259 |  | 55070.442 |  | 55070.442 |  | 55070.442
2026-03-24 | 165252.9838 |  | 55084.3279 |  | 55084.3279 |  | 55084.3279
2026-03-25 | 165294.6416 |  | 55098.2139 |  | 55098.2139 |  | 55098.2139
2026-03-26 | 165336.2995 |  | 55112.0998 |  | 55112.0998 |  | 55112.0998
2026-03-27 | 165377.9574 |  | 55125.9858 |  | 55125.9858 |  | 55125.9858
2026-03-28 | 165419.6153 |  | 55139.8718 |  | 55139.8718 |  | 55139.8718
2026-03-29 | 165461.2732 |  | 55153.7577 |  | 55153.7577 |  | 55153.7577
2026-03-30 | 165502.9311 |  | 55167.6437 |  | 55167.6437 |  | 55167.6437
2026-03-31 | 165544.589 |  | 55181.5297 |  | 55181.5297 |  | 55181.5297
2026-04-01 | 165586.2469 |  | 55195.4156 |  | 55195.4156 |  | 55195.4156
2026-04-02 | 165627.9048 |  | 55209.3016 |  | 55209.3016 |  | 55209.3016
2026-04-03 | 165669.5627 |  | 55223.1876 |  | 55223.1876 |  | 55223.1876
2026-04-04 | 165711.2206 |  | 55237.0735 |  | 55237.0735 |  | 55237.0735
2026-04-05 | 165752.8785 |  | 55250.9595 |  | 55250.9595 |  | 55250.9595
2026-04-06 | 165794.5364 |  | 55264.8455 |  | 55264.8455 |  | 55264.8455
2026-04-07 | 165836.1943 |  | 55278.7314 |  | 55278.7314 |  | 55278.7314
2026-04-08 | 165877.8522 |  | 55292.6174 |  | 55292.6174 |  | 55292.6174
2026-04-09 | 165919.5101 |  | 55306.5034 |  | 55306.5034 |  | 55306.5034
2026-04-10 | 165961.168 |  | 55320.3893 |  | 55320.3893 |  | 55320.3893
2026-04-11 | 166002.8259 |  | 55334.2753 |  | 55334.2753 |  | 55334.2753
2026-04-12 | 166044.4838 |  | 55348.1613 |  | 55348.1613 |  | 55348.1613
2026-04-13 | 166086.1416 |  | 55362.0472 |  | 55362.0472 |  | 55362.0472
2026-04-14 | 166127.7995 |  | 55375.9332 |  | 55375.9332 |  | 55375.9332
2026-04-15 | 166169.4574 |  | 55389.8191 |  | 55389.8191 |  | 55389.8191
2026-04-16 | 166211.1153 |  | 55403.7051 |  | 55403.7051 |  | 55403.7051
2026-04-17 | 166252.7732 |  | 55417.5911 |  | 55417.5911 |  | 55417.5911
2026-04-18 | 166294.4311 |  | 55431.477 |  | 55431.477 |  | 55431.477
2026-04-19 | 166336.089 |  | 55445.363 |  | 55445.363 |  | 55445.363
2026-04-20 | 166377.7469 |  | 55459.249 |  | 55459.249 |  | 55459.249
2026-04-21 | 166419.4048 |  | 55473.1349 |  | 55473.1349 |  | 55473.1349
2026-04-22 | 166461.0627 |  | 55487.0209 |  | 55487.0209 |  | 55487.0209
2026-04-23 | 166502.7206 |  | 55500.9069 |  | 55500.9069 |  | 55500.9069
2026-04-24 | 166544.3785 |  | 55514.7928 |  | 55514.7928 |  | 55514.7928
2026-04-25 | 166586.0364 |  | 55528.6788 |  | 55528.6788 |  | 55528.6788
2026-04-26 | 166627.6943 |  | 55542.5648 |  | 55542.5648 |  | 55542.5648
2026-04-27 | 166669.3522 |  | 55556.4507 |  | 55556.4507 |  | 55556.4507
2026-04-28 | 166711.0101 |  | 55570.3367 |  | 55570.3367 |  | 55570.3367
2026-04-29 | 166752.668 |  | 55584.2227 |  | 55584.2227 |  | 55584.2227
2026-04-30 | 166794.3259 |  | 55598.1086 |  | 55598.1086 |  | 55598.1086
2026-05-01 | 166835.9838 |  | 55611.9946 |  | 55611.9946 |  | 55611.9946
2026-05-02 | 166877.6416 |  | 55625.8805 |  | 55625.8805 |  | 55625.8805
2026-05-03 | 166919.2995 |  | 55639.7665 |  | 55639.7665 |  | 55639.7665
2026-05-04 | 166960.9574 |  | 55653.6525 |  | 55653.6525 |  | 55653.6525
2026-05-05 | 167002.6153 |  | 55667.5384 |  | 55667.5384 |  | 55667.5384
2026-05-06 | 167044.2732 |  | 55681.4244 |  | 55681.4244 |  | 55681.4244
2026-05-07 | 167085.9311 |  | 55695.3104 |  | 55695.3104 |  | 55695.3104
2026-05-08 | 167127.589 |  | 55709.1963 |  | 55709.1963 |  | 55709.1963
2026-05-09 | 167169.2469 |  | 55723.0823 |  | 55723.0823 |  | 55723.0823
2026-05-10 | 167210.9048 |  | 55736.9683 |  | 55736.9683 |  | 55736.9683
2026-05-11 | 167252.5627 |  | 55750.8542 |  | 55750.8542 |  | 55750.8542
2026-05-12 | 167294.2206 |  | 55764.7402 |  | 55764.7402 |  | 55764.7402
2026-05-13 | 167335.8785 |  | 55778.6262 |  | 55778.6262 |  | 55778.6262
2026-05-14 | 167377.5364 |  | 55792.5121 |  | 55792.5121 |  | 55792.5121
2026-05-15 | 167419.1943 |  | 55806.3981 |  | 55806.3981 |  | 55806.3981
2026-05-16 | 167460.8522 |  | 55820.2841 |  | 55820.2841 |  | 55820.2841
2026-05-17 | 167502.5101 |  | 55834.17 |  | 55834.17 |  | 55834.17
2026-05-18 | 167544.168 |  | 55848.056 |  | 55848.056 |  | 55848.056
2026-05-19 | 167585.8259 |  | 55861.942 |  | 55861.942 |  | 55861.942
2026-05-20 | 167627.4838 |  | 55875.8279 |  | 55875.8279 |  | 55875.8279
2026-05-21 | 167669.1416 |  | 55889.7139 |  | 55889.7139 |  | 55889.7139
2026-05-22 | 167710.7995 |  | 55903.5998 |  | 55903.5998 |  | 55903.5998
2026-05-23 | 167752.4574 |  | 55917.4858 |  | 55917.4858 |  | 55917.4858
2026-05-24 | 167794.1153 |  | 55931.3718 |  | 55931.3718 |  | 55931.3718
2026-05-25 | 167835.7732 |  | 55945.2577 |  | 55945.2577 |  | 55945.2577
2026-05-26 | 167877.4311 |  | 55959.1437 |  | 55959.1437 |  | 55959.1437
2026-05-27 | 167919.089 |  | 55973.0297 |  | 55973.0297 |  | 55973.0297
2026-05-28 | 167960.7469 |  | 55986.9156 |  | 55986.9156 |  | 55986.9156
2026-05-29 | 168002.4048 |  | 56000.8016 |  | 56000.8016 |  | 56000.8016
2026-05-30 | 168044.0627 |  | 56014.6876 |  | 56014.6876 |  | 56014.6876
2026-05-31 | 168085.7206 |  | 56028.5735 |  | 56028.5735 |  | 56028.5735
2026-06-01 | 168127.3785 |  | 56042.4595 |  | 56042.4595 |  | 56042.4595
2026-06-02 | 168169.0364 |  | 56056.3455 |  | 56056.3455 |  | 56056.3455
2026-06-03 | 168210.6943 |  | 56070.2314 |  | 56070.2314 |  | 56070.2314
2026-06-04 | 168252.3522 |  | 56084.1174 |  | 56084.1174 |  | 56084.1174
2026-06-05 | 168294.0101 |  | 56098.0034 |  | 56098.0034 |  | 56098.0034
2026-06-06 | 168335.668 |  | 56111.8893 |  | 56111.8893 |  | 56111.8893
2026-06-07 | 168377.3259 |  | 56125.7753 |  | 56125.7753 |  | 56125.7753
2026-06-08 | 168418.9838 |  | 56139.6613 |  | 56139.6613 |  | 56139.6613
2026-06-09 | 168460.6416 |  | 56153.5472 |  | 56153.5472 |  | 56153.5472
2026-06-10 | 168502.2995 |  | 56167.4332 |  | 56167.4332 |  | 56167.4332
2026-06-11 | 168543.9574 |  | 56181.3191 |  | 56181.3191 |  | 56181.3191
2026-06-12 | 168585.6153 |  | 56195.2051 |  | 56195.2051 |  | 56195.2051
2026-06-13 | 168627.2732 |  | 56209.0911 |  | 56209.0911 |  | 56209.0911
2026-06-14 | 168668.9311 |  | 56222.977 |  | 56222.977 |  | 56222.977
2026-06-15 | 168710.589 |  | 56236.863 |  | 56236.863 |  | 56236.863
2026-06-16 | 168752.2469 |  | 56250.749 |  | 56250.749 |  | 56250.749
2026-06-17 | 168793.9048 |  | 56264.6349 |  | 56264.6349 |  | 56264.6349
2026-06-18 | 168835.5627 |  | 56278.5209 |  | 56278.5209 |  | 56278.5209
2026-06-19 | 168877.2206 |  | 56292.4069 |  | 56292.4069 |  | 56292.4069
2026-06-20 | 168918.8785 |  | 56306.2928 |  | 56306.2928 |  | 56306.2928
2026-06-21 | 168960.5364 |  | 56320.1788 |  | 56320.1788 |  | 56320.1788
2026-06-22 | 169002.1943 |  | 56334.0648 |  | 56334.0648 |  | 56334.0648
2026-06-23 | 169043.8522 |  | 56347.9507 |  | 56347.9507 |  | 56347.9507
2026-06-24 | 169085.5101 |  | 56361.8367 |  | 56361.8367 |  | 56361.8367
2026-06-25 | 169127.168 |  | 56375.7227 |  | 56375.7227 |  | 56375.7227
2026-06-26 | 169168.8259 |  | 56389.6086 |  | 56389.6086 |  | 56389.6086
2026-06-27 | 169210.4838 |  | 56403.4946 |  | 56403.4946 |  | 56403.4946
2026-06-28 | 169252.1416 |  | 56417.3805 |  | 56417.3805 |  | 56417.3805
2026-06-29 | 169293.7995 |  | 56431.2665 |  | 56431.2665 |  | 56431.2665
2026-06-30 | 169335.4574 |  | 56445.1525 |  | 56445.1525 |  | 56445.1525
2026-07-01 | 169377.1153 |  | 56459.0384 |  | 56459.0384 |  | 56459.0384
2026-07-02 | 169418.7732 |  | 56472.9244 |  | 56472.9244 |  | 56472.9244
2026-07-03 | 169460.4311 |  | 56486.8104 |  | 56486.8104 |  | 56486.8104
2026-07-04 | 169502.089 |  | 56500.6963 |  | 56500.6963 |  | 56500.6963
2026-07-05 | 169543.7469 |  | 56514.5823 |  | 56514.5823 |  | 56514.5823
2026-07-06 | 169585.4048 |  | 56528.4683 |  | 56528.4683 |  | 56528.4683
2026-07-07 | 169627.0627 |  | 56542.3542 |  | 56542.3542 |  | 56542.3542
2026-07-08 | 169668.7206 |  | 56556.2402 |  | 56556.2402 |  | 56556.2402
2026-07-09 | 169710.3785 |  | 56570.1262 |  | 56570.1262 |  | 56570.1262
2026-07-10 | 169752.0364 |  | 56584.0121 |  | 56584.0121 |  | 56584.0121
2026-07-11 | 169793.6943 |  | 56597.8981 |  | 56597.8981 |  | 56597.8981
2026-07-12 | 169835.3522 |  | 56611.7841 |  | 56611.7841 |  | 56611.7841
2026-07-13 | 169877.0101 |  | 56625.67 |  | 56625.67 |  | 56625.67
2026-07-14 | 169918.668 |  | 56639.556 |  | 56639.556 |  | 56639.556
2026-07-15 | 169960.3259 |  | 56653.442 |  | 56653.442 |  | 56653.442
2026-07-16 | 170001.9838 |  | 56667.3279 |  | 56667.3279 |  | 56667.3279
2026-07-17 | 170043.6416 |  | 56681.2139 |  | 56681.2139 |  | 56681.2139
2026-07-18 | 170085.2995 |  | 56695.0998 |  | 56695.0998 |  | 56695.0998
2026-07-19 | 170126.9574 |  | 56708.9858 |  | 56708.9858 |  | 56708.9858
2026-07-20 | 170168.6153 |  | 56722.8718 |  | 56722.8718 |  | 56722.8718
2026-07-21 | 170210.2732 |  | 56736.7577 |  | 56736.7577 |  | 56736.7577
2026-07-22 | 170251.9311 |  | 56750.6437 |  | 56750.6437 |  | 56750.6437
2026-07-23 | 170293.589 |  | 56764.5297 |  | 56764.5297 |  | 56764.5297
2026-07-24 | 170335.2469 |  | 56778.4156 |  | 56778.4156 |  | 56778.4156
2026-07-25 | 170376.9048 |  | 56792.3016 |  | 56792.3016 |  | 56792.3016
2026-07-26 | 170418.5627 |  | 56806.1876 |  | 56806.1876 |  | 56806.1876
2026-07-27 | 170460.2206 |  | 56820.0735 |  | 56820.0735 |  | 56820.0735
2026-07-28 | 170501.8785 |  | 56833.9595 |  | 56833.9595 |  | 56833.9595
2026-07-29 | 170543.5364 |  | 56847.8455 |  | 56847.8455 |  | 56847.8455
2026-07-30 | 170585.1943 |  | 56861.7314 |  | 56861.7314 |  | 56861.7314
2026-07-31 | 170626.8522 |  | 56875.6174 |  | 56875.6174 |  | 56875.6174
2026-08-01 | 170668.5101 |  | 56889.5034 |  | 56889.5034 |  | 56889.5034
2026-08-02 | 170710.168 |  | 56903.3893 |  | 56903.3893 |  | 56903.3893
2026-08-03 | 170751.8259 |  | 56917.2753 |  | 56917.2753 |  | 56917.2753
2026-08-04 | 170793.4838 |  | 56931.1613 |  | 56931.1613 |  | 56931.1613
2026-08-05 | 170835.1416 |  | 56945.0472 |  | 56945.0472 |  | 56945.0472
2026-08-06 | 170876.7995 |  | 56958.9332 |  | 56958.9332 |  | 56958.9332
2026-08-07 | 170918.4574 |  | 56972.8191 |  | 56972.8191 |  | 56972.8191
2026-08-08 | 170960.1153 |  | 56986.7051 |  | 56986.7051 |  | 56986.7051
2026-08-09 | 171001.7732 |  | 57000.5911 |  | 57000.5911 |  | 57000.5911
2026-08-10 | 171043.4311 |  | 57014.477 |  | 57014.477 |  | 57014.477
2026-08-11 | 171085.089 |  | 57028.363 |  | 57028.363 |  | 57028.363
2026-08-12 | 171126.7469 |  | 57042.249 |  | 57042.249 |  | 57042.249
2026-08-13 | 171168.4048 |  | 57056.1349 |  | 57056.1349 |  | 57056.1349
2026-08-14 | 171210.0627 |  | 57070.0209 |  | 57070.0209 |  | 57070.0209
2026-08-15 | 171251.7206 |  | 57083.9069 |  | 57083.9069 |  | 57083.9069
2026-08-16 | 171293.3785 |  | 57097.7928 |  | 57097.7928 |  | 57097.7928
2026-08-17 | 171335.0364 |  | 57111.6788 |  | 57111.6788 |  | 57111.6788
2026-08-18 | 171376.6943 |  | 57125.5648 |  | 57125.5648 |  | 57125.5648
2026-08-19 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-20 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-21 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-22 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-23 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-24 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-25 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-26 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-27 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-28 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-29 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-30 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-31 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-01 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-02 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-03 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-04 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-05 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-06 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-07 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-08 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-09 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-10 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-11 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-12 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-13 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-14 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-15 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-16 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-17 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-18 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-19 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-20 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-21 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-22 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507

## Outsource (Direct Cost)
Date | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Planned 5006 · Drilling Expense (Cumulative) | Actual 5006 · Drilling Expense (Cumulative) | Planned 5110 · Temporary labor (Direct) (Cumulative) | Actual 5110 · Temporary labor (Direct) (Cumulative) | Planned 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Actual 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Planned 5114 · Rent - Building (Direct) (Cumulative) | Actual 5114 · Rent - Building (Direct) (Cumulative) | Planned 5115 · Rent - Equipment (direct) (Cumulative) | Actual 5115 · Rent - Equipment (direct) (Cumulative) | Planned 5116 · Rent - Storage (Direct) (Cumulative) | Actual 5116 · Rent - Storage (Direct) (Cumulative) | Planned 5120 · Outside services (Direct) (Cumulative) | Actual 5120 · Outside services (Direct) (Cumulative) | Planned 5121 · Freight & Shipping (Direct) (Cumulative) | Actual 5121 · Freight & Shipping (Direct) (Cumulative) | Planned 5124 · License and permits (Direct) (Cumulative) | Actual 5124 · License and permits (Direct) (Cumulative) | Planned 5129 · Misc expenses (Direct) (Cumulative) | Actual 5129 · Misc expenses (Direct) (Cumulative) | Planned 5132 · Internet fee (Direct) (Cumulative) | Actual 5132 · Internet fee (Direct) (Cumulative) | Planned 6999 · Uncategorized Expenses (Cumulative) | Actual 6999 · Uncategorized Expenses (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 321.9345 | 0 | 26.8279 | 0 | 26.8279 | 0 | 26.8279 | 0 | 26.8279 | 0 | 26.8279 | 0 | 26.8279 | 0 | 26.8279 | 0 | 26.8279 | 0 | 26.8279 | 0 | 26.8279 | 0 | 26.8279 | 0 | 26.8279 | 0
2025-06-26 | 643.8691 | 0 | 53.6558 | 0 | 53.6558 | 0 | 53.6558 | 0 | 53.6558 | 0 | 53.6558 | 0 | 53.6558 | 0 | 53.6558 | 0 | 53.6558 | 0 | 53.6558 | 0 | 53.6558 | 0 | 53.6558 | 0 | 53.6558 | 0
2025-06-27 | 965.8036 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0 | 80.4836 | 0
2025-06-28 | 1287.7382 | 0 | 107.3115 | 0 | 107.3115 | 0 | 107.3115 | 0 | 107.3115 | 0 | 107.3115 | 0 | 107.3115 | 0 | 107.3115 | 0 | 107.3115 | 0 | 107.3115 | 0 | 107.3115 | 0 | 107.3115 | 0 | 107.3115 | 0
2025-06-29 | 1609.6727 | 0 | 134.1394 | 0 | 134.1394 | 0 | 134.1394 | 0 | 134.1394 | 0 | 134.1394 | 0 | 134.1394 | 0 | 134.1394 | 0 | 134.1394 | 0 | 134.1394 | 0 | 134.1394 | 0 | 134.1394 | 0 | 134.1394 | 0
2025-06-30 | 1931.6072 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0 | 160.9673 | 0
2025-07-01 | 2253.5418 | 0 | 187.7951 | 0 | 187.7951 | 0 | 187.7951 | 0 | 187.7951 | 0 | 187.7951 | 0 | 187.7951 | 0 | 187.7951 | 0 | 187.7951 | 0 | 187.7951 | 0 | 187.7951 | 0 | 187.7951 | 0 | 187.7951 | 0
2025-07-02 | 2575.4763 | 0 | 214.623 | 0 | 214.623 | 0 | 214.623 | 0 | 214.623 | 0 | 214.623 | 0 | 214.623 | 0 | 214.623 | 0 | 214.623 | 0 | 214.623 | 0 | 214.623 | 0 | 214.623 | 0 | 214.623 | 0
2025-07-03 | 2897.4108 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0 | 241.4509 | 0
2025-07-04 | 3219.3454 | 0 | 268.2788 | 0 | 268.2788 | 0 | 268.2788 | 0 | 268.2788 | 0 | 268.2788 | 0 | 268.2788 | 0 | 268.2788 | 0 | 268.2788 | 0 | 268.2788 | 0 | 268.2788 | 0 | 268.2788 | 0 | 268.2788 | 0
2025-07-05 | 3541.2799 | 0 | 295.1067 | 0 | 295.1067 | 0 | 295.1067 | 0 | 295.1067 | 0 | 295.1067 | 0 | 295.1067 | 0 | 295.1067 | 0 | 295.1067 | 0 | 295.1067 | 0 | 295.1067 | 0 | 295.1067 | 0 | 295.1067 | 0
2025-07-06 | 3863.2145 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0 | 321.9345 | 0
2025-07-07 | 4185.149 | 0 | 348.7624 | 0 | 348.7624 | 0 | 348.7624 | 0 | 348.7624 | 0 | 348.7624 | 0 | 348.7624 | 0 | 348.7624 | 0 | 348.7624 | 0 | 348.7624 | 0 | 348.7624 | 0 | 348.7624 | 0 | 348.7624 | 0
2025-07-08 | 4507.0835 | 0 | 375.5903 | 0 | 375.5903 | 0 | 375.5903 | 0 | 375.5903 | 0 | 375.5903 | 0 | 375.5903 | 0 | 375.5903 | 0 | 375.5903 | 0 | 375.5903 | 0 | 375.5903 | 0 | 375.5903 | 0 | 375.5903 | 0
2025-07-09 | 4829.0181 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0 | 402.4182 | 0
2025-07-10 | 5150.9526 | 0 | 429.2461 | 0 | 429.2461 | 0 | 429.2461 | 0 | 429.2461 | 0 | 429.2461 | 0 | 429.2461 | 0 | 429.2461 | 0 | 429.2461 | 0 | 429.2461 | 0 | 429.2461 | 0 | 429.2461 | 0 | 429.2461 | 0
2025-07-11 | 5472.8872 | 0 | 456.0739 | 0 | 456.0739 | 0 | 456.0739 | 0 | 456.0739 | 0 | 456.0739 | 0 | 456.0739 | 0 | 456.0739 | 0 | 456.0739 | 0 | 456.0739 | 0 | 456.0739 | 0 | 456.0739 | 0 | 456.0739 | 0
2025-07-12 | 5794.8217 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0 | 482.9018 | 0
2025-07-13 | 6116.7562 | 0 | 509.7297 | 0 | 509.7297 | 0 | 509.7297 | 0 | 509.7297 | 0 | 509.7297 | 0 | 509.7297 | 0 | 509.7297 | 0 | 509.7297 | 0 | 509.7297 | 0 | 509.7297 | 0 | 509.7297 | 0 | 509.7297 | 0
2025-07-14 | 6438.6908 | 0 | 536.5576 | 0 | 536.5576 | 0 | 536.5576 | 0 | 536.5576 | 0 | 536.5576 | 0 | 536.5576 | 0 | 536.5576 | 0 | 536.5576 | 0 | 536.5576 | 0 | 536.5576 | 0 | 536.5576 | 0 | 536.5576 | 0
2025-07-15 | 6760.6253 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0 | 563.3854 | 0
2025-07-16 | 7082.5598 | 0 | 590.2133 | 0 | 590.2133 | 0 | 590.2133 | 0 | 590.2133 | 0 | 590.2133 | 0 | 590.2133 | 0 | 590.2133 | 0 | 590.2133 | 0 | 590.2133 | 0 | 590.2133 | 0 | 590.2133 | 0 | 590.2133 | 0
2025-07-17 | 7404.4944 | 0 | 617.0412 | 0 | 617.0412 | 0 | 617.0412 | 0 | 617.0412 | 0 | 617.0412 | 0 | 617.0412 | 0 | 617.0412 | 0 | 617.0412 | 0 | 617.0412 | 0 | 617.0412 | 0 | 617.0412 | 0 | 617.0412 | 0
2025-07-18 | 7726.4289 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0 | 643.8691 | 0
2025-07-19 | 8048.3635 | 0 | 670.697 | 0 | 670.697 | 0 | 670.697 | 0 | 670.697 | 0 | 670.697 | 0 | 670.697 | 0 | 670.697 | 0 | 670.697 | 0 | 670.697 | 0 | 670.697 | 0 | 670.697 | 0 | 670.697 | 0
2025-07-20 | 8370.298 | 0 | 697.5248 | 0 | 697.5248 | 0 | 697.5248 | 0 | 697.5248 | 0 | 697.5248 | 0 | 697.5248 | 0 | 697.5248 | 0 | 697.5248 | 0 | 697.5248 | 0 | 697.5248 | 0 | 697.5248 | 0 | 697.5248 | 0
2025-07-21 | 8692.2325 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0 | 724.3527 | 0
2025-07-22 | 9014.1671 | 500 | 751.1806 | 0 | 751.1806 | 0 | 751.1806 | 0 | 751.1806 | 0 | 751.1806 | 0 | 751.1806 | 0 | 751.1806 | 0 | 751.1806 | 0 | 751.1806 | 500 | 751.1806 | 0 | 751.1806 | 0 | 751.1806 | 0
2025-07-23 | 9336.1016 | 500 | 778.0085 | 0 | 778.0085 | 0 | 778.0085 | 0 | 778.0085 | 0 | 778.0085 | 0 | 778.0085 | 0 | 778.0085 | 0 | 778.0085 | 0 | 778.0085 | 500 | 778.0085 | 0 | 778.0085 | 0 | 778.0085 | 0
2025-07-24 | 9658.0362 | 500 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 500 | 804.8363 | 0 | 804.8363 | 0 | 804.8363 | 0
2025-07-25 | 9979.9707 | 500 | 831.6642 | 0 | 831.6642 | 0 | 831.6642 | 0 | 831.6642 | 0 | 831.6642 | 0 | 831.6642 | 0 | 831.6642 | 0 | 831.6642 | 0 | 831.6642 | 500 | 831.6642 | 0 | 831.6642 | 0 | 831.6642 | 0
2025-07-26 | 10301.9052 | 500 | 858.4921 | 0 | 858.4921 | 0 | 858.4921 | 0 | 858.4921 | 0 | 858.4921 | 0 | 858.4921 | 0 | 858.4921 | 0 | 858.4921 | 0 | 858.4921 | 500 | 858.4921 | 0 | 858.4921 | 0 | 858.4921 | 0
2025-07-27 | 10623.8398 | 500 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0 | 885.32 | 500 | 885.32 | 0 | 885.32 | 0 | 885.32 | 0
2025-07-28 | 10945.7743 | 500 | 912.1479 | 0 | 912.1479 | 0 | 912.1479 | 0 | 912.1479 | 0 | 912.1479 | 0 | 912.1479 | 0 | 912.1479 | 0 | 912.1479 | 0 | 912.1479 | 500 | 912.1479 | 0 | 912.1479 | 0 | 912.1479 | 0
2025-07-29 | 11267.7088 | 500 | 938.9757 | 0 | 938.9757 | 0 | 938.9757 | 0 | 938.9757 | 0 | 938.9757 | 0 | 938.9757 | 0 | 938.9757 | 0 | 938.9757 | 0 | 938.9757 | 500 | 938.9757 | 0 | 938.9757 | 0 | 938.9757 | 0
2025-07-30 | 11589.6434 | 500 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 500 | 965.8036 | 0 | 965.8036 | 0 | 965.8036 | 0
2025-07-31 | 11911.5779 | 500 | 992.6315 | 0 | 992.6315 | 0 | 992.6315 | 0 | 992.6315 | 0 | 992.6315 | 0 | 992.6315 | 0 | 992.6315 | 0 | 992.6315 | 0 | 992.6315 | 500 | 992.6315 | 0 | 992.6315 | 0 | 992.6315 | 0
2025-08-01 | 12233.5125 | 500 | 1019.4594 | 0 | 1019.4594 | 0 | 1019.4594 | 0 | 1019.4594 | 0 | 1019.4594 | 0 | 1019.4594 | 0 | 1019.4594 | 0 | 1019.4594 | 0 | 1019.4594 | 500 | 1019.4594 | 0 | 1019.4594 | 0 | 1019.4594 | 0
2025-08-02 | 12555.447 | 500 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 500 | 1046.2872 | 0 | 1046.2872 | 0 | 1046.2872 | 0
2025-08-03 | 12877.3815 | 500 | 1073.1151 | 0 | 1073.1151 | 0 | 1073.1151 | 0 | 1073.1151 | 0 | 1073.1151 | 0 | 1073.1151 | 0 | 1073.1151 | 0 | 1073.1151 | 0 | 1073.1151 | 500 | 1073.1151 | 0 | 1073.1151 | 0 | 1073.1151 | 0
2025-08-04 | 13199.3161 | 500 | 1099.943 | 0 | 1099.943 | 0 | 1099.943 | 0 | 1099.943 | 0 | 1099.943 | 0 | 1099.943 | 0 | 1099.943 | 0 | 1099.943 | 0 | 1099.943 | 500 | 1099.943 | 0 | 1099.943 | 0 | 1099.943 | 0
2025-08-05 | 13521.2506 | 500 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 500 | 1126.7709 | 0 | 1126.7709 | 0 | 1126.7709 | 0
2025-08-06 | 13843.1851 | 500 | 1153.5988 | 0 | 1153.5988 | 0 | 1153.5988 | 0 | 1153.5988 | 0 | 1153.5988 | 0 | 1153.5988 | 0 | 1153.5988 | 0 | 1153.5988 | 0 | 1153.5988 | 500 | 1153.5988 | 0 | 1153.5988 | 0 | 1153.5988 | 0
2025-08-07 | 14165.1197 | 500 | 1180.4266 | 0 | 1180.4266 | 0 | 1180.4266 | 0 | 1180.4266 | 0 | 1180.4266 | 0 | 1180.4266 | 0 | 1180.4266 | 0 | 1180.4266 | 0 | 1180.4266 | 500 | 1180.4266 | 0 | 1180.4266 | 0 | 1180.4266 | 0
2025-08-08 | 14487.0542 | 500 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 500 | 1207.2545 | 0 | 1207.2545 | 0 | 1207.2545 | 0
2025-08-09 | 14808.9888 | 500 | 1234.0824 | 0 | 1234.0824 | 0 | 1234.0824 | 0 | 1234.0824 | 0 | 1234.0824 | 0 | 1234.0824 | 0 | 1234.0824 | 0 | 1234.0824 | 0 | 1234.0824 | 500 | 1234.0824 | 0 | 1234.0824 | 0 | 1234.0824 | 0
2025-08-10 | 15130.9233 | 500 | 1260.9103 | 0 | 1260.9103 | 0 | 1260.9103 | 0 | 1260.9103 | 0 | 1260.9103 | 0 | 1260.9103 | 0 | 1260.9103 | 0 | 1260.9103 | 0 | 1260.9103 | 500 | 1260.9103 | 0 | 1260.9103 | 0 | 1260.9103 | 0
2025-08-11 | 15452.8578 | 500 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 500 | 1287.7382 | 0 | 1287.7382 | 0 | 1287.7382 | 0
2025-08-12 | 15774.7924 | 500 | 1314.566 | 0 | 1314.566 | 0 | 1314.566 | 0 | 1314.566 | 0 | 1314.566 | 0 | 1314.566 | 0 | 1314.566 | 0 | 1314.566 | 0 | 1314.566 | 500 | 1314.566 | 0 | 1314.566 | 0 | 1314.566 | 0
2025-08-13 | 16096.7269 | 500 | 1341.3939 | 0 | 1341.3939 | 0 | 1341.3939 | 0 | 1341.3939 | 0 | 1341.3939 | 0 | 1341.3939 | 0 | 1341.3939 | 0 | 1341.3939 | 0 | 1341.3939 | 500 | 1341.3939 | 0 | 1341.3939 | 0 | 1341.3939 | 0
2025-08-14 | 16418.6615 | 500 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 500 | 1368.2218 | 0 | 1368.2218 | 0 | 1368.2218 | 0
2025-08-15 | 16740.596 | 500 | 1395.0497 | 0 | 1395.0497 | 0 | 1395.0497 | 0 | 1395.0497 | 0 | 1395.0497 | 0 | 1395.0497 | 0 | 1395.0497 | 0 | 1395.0497 | 0 | 1395.0497 | 500 | 1395.0497 | 0 | 1395.0497 | 0 | 1395.0497 | 0
2025-08-16 | 17062.5305 | 500 | 1421.8775 | 0 | 1421.8775 | 0 | 1421.8775 | 0 | 1421.8775 | 0 | 1421.8775 | 0 | 1421.8775 | 0 | 1421.8775 | 0 | 1421.8775 | 0 | 1421.8775 | 500 | 1421.8775 | 0 | 1421.8775 | 0 | 1421.8775 | 0
2025-08-17 | 17384.4651 | 500 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 500 | 1448.7054 | 0 | 1448.7054 | 0 | 1448.7054 | 0
2025-08-18 | 17706.3996 | 500 | 1475.5333 | 0 | 1475.5333 | 0 | 1475.5333 | 0 | 1475.5333 | 0 | 1475.5333 | 0 | 1475.5333 | 0 | 1475.5333 | 0 | 1475.5333 | 0 | 1475.5333 | 500 | 1475.5333 | 0 | 1475.5333 | 0 | 1475.5333 | 0
2025-08-19 | 18028.3341 | 500 | 1502.3612 | 0 | 1502.3612 | 0 | 1502.3612 | 0 | 1502.3612 | 0 | 1502.3612 | 0 | 1502.3612 | 0 | 1502.3612 | 0 | 1502.3612 | 0 | 1502.3612 | 500 | 1502.3612 | 0 | 1502.3612 | 0 | 1502.3612 | 0
2025-08-20 | 18350.2687 | 500 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 500 | 1529.1891 | 0 | 1529.1891 | 0 | 1529.1891 | 0
2025-08-21 | 18672.2032 | 500 | 1556.0169 | 0 | 1556.0169 | 0 | 1556.0169 | 0 | 1556.0169 | 0 | 1556.0169 | 0 | 1556.0169 | 0 | 1556.0169 | 0 | 1556.0169 | 0 | 1556.0169 | 500 | 1556.0169 | 0 | 1556.0169 | 0 | 1556.0169 | 0
2025-08-22 | 18994.1378 | 500 | 1582.8448 | 0 | 1582.8448 | 0 | 1582.8448 | 0 | 1582.8448 | 0 | 1582.8448 | 0 | 1582.8448 | 0 | 1582.8448 | 0 | 1582.8448 | 0 | 1582.8448 | 500 | 1582.8448 | 0 | 1582.8448 | 0 | 1582.8448 | 0
2025-08-23 | 19316.0723 | 500 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 500 | 1609.6727 | 0 | 1609.6727 | 0 | 1609.6727 | 0
2025-08-24 | 19638.0068 | 500 | 1636.5006 | 0 | 1636.5006 | 0 | 1636.5006 | 0 | 1636.5006 | 0 | 1636.5006 | 0 | 1636.5006 | 0 | 1636.5006 | 0 | 1636.5006 | 0 | 1636.5006 | 500 | 1636.5006 | 0 | 1636.5006 | 0 | 1636.5006 | 0
2025-08-25 | 19959.9414 | 515 | 1663.3284 | 0 | 1663.3284 | 0 | 1663.3284 | 0 | 1663.3284 | 0 | 1663.3284 | 0 | 1663.3284 | 0 | 1663.3284 | 0 | 1663.3284 | 15 | 1663.3284 | 500 | 1663.3284 | 0 | 1663.3284 | 0 | 1663.3284 | 0
2025-08-26 | 20281.8759 | 3265 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 2765 | 1690.1563 | 500 | 1690.1563 | 0 | 1690.1563 | 0 | 1690.1563 | 0
2025-08-27 | 20603.8105 | 3265 | 1716.9842 | 0 | 1716.9842 | 0 | 1716.9842 | 0 | 1716.9842 | 0 | 1716.9842 | 0 | 1716.9842 | 0 | 1716.9842 | 0 | 1716.9842 | 2765 | 1716.9842 | 500 | 1716.9842 | 0 | 1716.9842 | 0 | 1716.9842 | 0
2025-08-28 | 20925.745 | 3265 | 1743.8121 | 0 | 1743.8121 | 0 | 1743.8121 | 0 | 1743.8121 | 0 | 1743.8121 | 0 | 1743.8121 | 0 | 1743.8121 | 0 | 1743.8121 | 2765 | 1743.8121 | 500 | 1743.8121 | 0 | 1743.8121 | 0 | 1743.8121 | 0
2025-08-29 | 21247.6795 | 3265 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 2765 | 1770.64 | 500 | 1770.64 | 0 | 1770.64 | 0 | 1770.64 | 0
2025-08-30 | 21569.6141 | 3265 | 1797.4678 | 0 | 1797.4678 | 0 | 1797.4678 | 0 | 1797.4678 | 0 | 1797.4678 | 0 | 1797.4678 | 0 | 1797.4678 | 0 | 1797.4678 | 2765 | 1797.4678 | 500 | 1797.4678 | 0 | 1797.4678 | 0 | 1797.4678 | 0
2025-08-31 | 21891.5486 | 3265 | 1824.2957 | 0 | 1824.2957 | 0 | 1824.2957 | 0 | 1824.2957 | 0 | 1824.2957 | 0 | 1824.2957 | 0 | 1824.2957 | 0 | 1824.2957 | 2765 | 1824.2957 | 500 | 1824.2957 | 0 | 1824.2957 | 0 | 1824.2957 | 0
2025-09-01 | 22213.4831 | 3265 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 2765 | 1851.1236 | 500 | 1851.1236 | 0 | 1851.1236 | 0 | 1851.1236 | 0
2025-09-02 | 22535.4177 | 3265 | 1877.9515 | 0 | 1877.9515 | 0 | 1877.9515 | 0 | 1877.9515 | 0 | 1877.9515 | 0 | 1877.9515 | 0 | 1877.9515 | 0 | 1877.9515 | 2765 | 1877.9515 | 500 | 1877.9515 | 0 | 1877.9515 | 0 | 1877.9515 | 0
2025-09-03 | 22857.3522 | 3265 | 1904.7794 | 0 | 1904.7794 | 0 | 1904.7794 | 0 | 1904.7794 | 0 | 1904.7794 | 0 | 1904.7794 | 0 | 1904.7794 | 0 | 1904.7794 | 2765 | 1904.7794 | 500 | 1904.7794 | 0 | 1904.7794 | 0 | 1904.7794 | 0
2025-09-04 | 23179.2868 | 3951.7 | 1931.6072 | 0 | 1931.6072 | 0 | 1931.6072 | 0 | 1931.6072 | 0 | 1931.6072 | 686.7 | 1931.6072 | 0 | 1931.6072 | 0 | 1931.6072 | 2765 | 1931.6072 | 500 | 1931.6072 | 0 | 1931.6072 | 0 | 1931.6072 | 0
2025-09-05 | 23501.2213 | 3951.7 | 1958.4351 | 0 | 1958.4351 | 0 | 1958.4351 | 0 | 1958.4351 | 0 | 1958.4351 | 686.7 | 1958.4351 | 0 | 1958.4351 | 0 | 1958.4351 | 2765 | 1958.4351 | 500 | 1958.4351 | 0 | 1958.4351 | 0 | 1958.4351 | 0
2025-09-06 | 23823.1558 | 3951.7 | 1985.263 | 0 | 1985.263 | 0 | 1985.263 | 0 | 1985.263 | 0 | 1985.263 | 686.7 | 1985.263 | 0 | 1985.263 | 0 | 1985.263 | 2765 | 1985.263 | 500 | 1985.263 | 0 | 1985.263 | 0 | 1985.263 | 0
2025-09-07 | 24145.0904 | 3951.7 | 2012.0909 | 0 | 2012.0909 | 0 | 2012.0909 | 0 | 2012.0909 | 0 | 2012.0909 | 686.7 | 2012.0909 | 0 | 2012.0909 | 0 | 2012.0909 | 2765 | 2012.0909 | 500 | 2012.0909 | 0 | 2012.0909 | 0 | 2012.0909 | 0
2025-09-08 | 24467.0249 | 3951.7 | 2038.9187 | 0 | 2038.9187 | 0 | 2038.9187 | 0 | 2038.9187 | 0 | 2038.9187 | 686.7 | 2038.9187 | 0 | 2038.9187 | 0 | 2038.9187 | 2765 | 2038.9187 | 500 | 2038.9187 | 0 | 2038.9187 | 0 | 2038.9187 | 0
2025-09-09 | 24788.9595 | 3951.7 | 2065.7466 | 0 | 2065.7466 | 0 | 2065.7466 | 0 | 2065.7466 | 0 | 2065.7466 | 686.7 | 2065.7466 | 0 | 2065.7466 | 0 | 2065.7466 | 2765 | 2065.7466 | 500 | 2065.7466 | 0 | 2065.7466 | 0 | 2065.7466 | 0
2025-09-10 | 25110.894 | 3951.7 | 2092.5745 | 0 | 2092.5745 | 0 | 2092.5745 | 0 | 2092.5745 | 0 | 2092.5745 | 686.7 | 2092.5745 | 0 | 2092.5745 | 0 | 2092.5745 | 2765 | 2092.5745 | 500 | 2092.5745 | 0 | 2092.5745 | 0 | 2092.5745 | 0
2025-09-11 | 25432.8285 | 3951.7 | 2119.4024 | 0 | 2119.4024 | 0 | 2119.4024 | 0 | 2119.4024 | 0 | 2119.4024 | 686.7 | 2119.4024 | 0 | 2119.4024 | 0 | 2119.4024 | 2765 | 2119.4024 | 500 | 2119.4024 | 0 | 2119.4024 | 0 | 2119.4024 | 0
2025-09-12 | 25754.7631 | 18066.7 | 2146.2303 | 14115 | 2146.2303 | 0 | 2146.2303 | 0 | 2146.2303 | 0 | 2146.2303 | 686.7 | 2146.2303 | 0 | 2146.2303 | 0 | 2146.2303 | 2765 | 2146.2303 | 500 | 2146.2303 | 0 | 2146.2303 | 0 | 2146.2303 | 0
2025-09-13 | 26076.6976 | 18066.7 | 2173.0581 | 14115 | 2173.0581 | 0 | 2173.0581 | 0 | 2173.0581 | 0 | 2173.0581 | 686.7 | 2173.0581 | 0 | 2173.0581 | 0 | 2173.0581 | 2765 | 2173.0581 | 500 | 2173.0581 | 0 | 2173.0581 | 0 | 2173.0581 | 0
2025-09-14 | 26398.6321 | 18066.7 | 2199.886 | 14115 | 2199.886 | 0 | 2199.886 | 0 | 2199.886 | 0 | 2199.886 | 686.7 | 2199.886 | 0 | 2199.886 | 0 | 2199.886 | 2765 | 2199.886 | 500 | 2199.886 | 0 | 2199.886 | 0 | 2199.886 | 0
2025-09-15 | 26720.5667 | 18066.7 | 2226.7139 | 14115 | 2226.7139 | 0 | 2226.7139 | 0 | 2226.7139 | 0 | 2226.7139 | 686.7 | 2226.7139 | 0 | 2226.7139 | 0 | 2226.7139 | 2765 | 2226.7139 | 500 | 2226.7139 | 0 | 2226.7139 | 0 | 2226.7139 | 0
2025-09-16 | 27042.5012 | 18066.7 | 2253.5418 | 14115 | 2253.5418 | 0 | 2253.5418 | 0 | 2253.5418 | 0 | 2253.5418 | 686.7 | 2253.5418 | 0 | 2253.5418 | 0 | 2253.5418 | 2765 | 2253.5418 | 500 | 2253.5418 | 0 | 2253.5418 | 0 | 2253.5418 | 0
2025-09-17 | 27364.4358 | 18066.7 | 2280.3696 | 14115 | 2280.3696 | 0 | 2280.3696 | 0 | 2280.3696 | 0 | 2280.3696 | 686.7 | 2280.3696 | 0 | 2280.3696 | 0 | 2280.3696 | 2765 | 2280.3696 | 500 | 2280.3696 | 0 | 2280.3696 | 0 | 2280.3696 | 0
2025-09-18 | 27686.3703 | 18066.7 | 2307.1975 | 14115 | 2307.1975 | 0 | 2307.1975 | 0 | 2307.1975 | 0 | 2307.1975 | 686.7 | 2307.1975 | 0 | 2307.1975 | 0 | 2307.1975 | 2765 | 2307.1975 | 500 | 2307.1975 | 0 | 2307.1975 | 0 | 2307.1975 | 0
2025-09-19 | 28008.3048 | 18066.7 | 2334.0254 | 14115 | 2334.0254 | 0 | 2334.0254 | 0 | 2334.0254 | 0 | 2334.0254 | 686.7 | 2334.0254 | 0 | 2334.0254 | 0 | 2334.0254 | 2765 | 2334.0254 | 500 | 2334.0254 | 0 | 2334.0254 | 0 | 2334.0254 | 0
2025-09-20 | 28330.2394 | 18066.7 | 2360.8533 | 14115 | 2360.8533 | 0 | 2360.8533 | 0 | 2360.8533 | 0 | 2360.8533 | 686.7 | 2360.8533 | 0 | 2360.8533 | 0 | 2360.8533 | 2765 | 2360.8533 | 500 | 2360.8533 | 0 | 2360.8533 | 0 | 2360.8533 | 0
2025-09-21 | 28652.1739 | 18066.7 | 2387.6812 | 14115 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 686.7 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 2765 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-22 | 28652.1739 | 20014.2 | 2387.6812 | 14115 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-23 | 28652.1739 | 21151.72 | 2387.6812 | 14262.52 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-24 | 28652.1739 | 31325.53 | 2387.6812 | 24436.33 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-25 | 28652.1739 | 31325.53 | 2387.6812 | 24436.33 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-26 | 28652.1739 | 31325.53 | 2387.6812 | 24436.33 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-27 | 28652.1739 | 31325.53 | 2387.6812 | 24436.33 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-28 | 28652.1739 | 31325.53 | 2387.6812 | 24436.33 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-29 | 28840.6138 | 31325.53 | 2403.3845 | 24436.33 | 2403.3845 | 0 | 2403.3845 | 0 | 2403.3845 | 0 | 2403.3845 | 1184.2 | 2403.3845 | 990 | 2403.3845 | 0 | 2403.3845 | 4215 | 2403.3845 | 500 | 2403.3845 | 0 | 2403.3845 | 0 | 2403.3845 | 0
2025-09-30 | 29029.0537 | 31325.53 | 2419.0878 | 24436.33 | 2419.0878 | 0 | 2419.0878 | 0 | 2419.0878 | 0 | 2419.0878 | 1184.2 | 2419.0878 | 990 | 2419.0878 | 0 | 2419.0878 | 4215 | 2419.0878 | 500 | 2419.0878 | 0 | 2419.0878 | 0 | 2419.0878 | 0
2025-10-01 | 29217.4936 | 31325.53 | 2434.7911 | 24436.33 | 2434.7911 | 0 | 2434.7911 | 0 | 2434.7911 | 0 | 2434.7911 | 1184.2 | 2434.7911 | 990 | 2434.7911 | 0 | 2434.7911 | 4215 | 2434.7911 | 500 | 2434.7911 | 0 | 2434.7911 | 0 | 2434.7911 | 0
2025-10-02 | 29405.9335 | 31460.24 | 2450.4945 | 24436.33 | 2450.4945 | 0 | 2450.4945 | 0 | 2450.4945 | 0 | 2450.4945 | 1318.91 | 2450.4945 | 990 | 2450.4945 | 0 | 2450.4945 | 4215 | 2450.4945 | 500 | 2450.4945 | 0 | 2450.4945 | 0 | 2450.4945 | 0
2025-10-03 | 29594.3734 | 31460.24 | 2466.1978 | 24436.33 | 2466.1978 | 0 | 2466.1978 | 0 | 2466.1978 | 0 | 2466.1978 | 1318.91 | 2466.1978 | 990 | 2466.1978 | 0 | 2466.1978 | 4215 | 2466.1978 | 500 | 2466.1978 | 0 | 2466.1978 | 0 | 2466.1978 | 0
2025-10-04 | 29782.8133 | 31460.24 | 2481.9011 | 24436.33 | 2481.9011 | 0 | 2481.9011 | 0 | 2481.9011 | 0 | 2481.9011 | 1318.91 | 2481.9011 | 990 | 2481.9011 | 0 | 2481.9011 | 4215 | 2481.9011 | 500 | 2481.9011 | 0 | 2481.9011 | 0 | 2481.9011 | 0
2025-10-05 | 29971.2532 | 31460.24 | 2497.6044 | 24436.33 | 2497.6044 | 0 | 2497.6044 | 0 | 2497.6044 | 0 | 2497.6044 | 1318.91 | 2497.6044 | 990 | 2497.6044 | 0 | 2497.6044 | 4215 | 2497.6044 | 500 | 2497.6044 | 0 | 2497.6044 | 0 | 2497.6044 | 0
2025-10-06 | 30159.6931 | 31460.24 | 2513.3078 | 24436.33 | 2513.3078 | 0 | 2513.3078 | 0 | 2513.3078 | 0 | 2513.3078 | 1318.91 | 2513.3078 | 990 | 2513.3078 | 0 | 2513.3078 | 4215 | 2513.3078 | 500 | 2513.3078 | 0 | 2513.3078 | 0 | 2513.3078 | 0
2025-10-07 | 30348.133 | 31460.24 | 2529.0111 | 24436.33 | 2529.0111 | 0 | 2529.0111 | 0 | 2529.0111 | 0 | 2529.0111 | 1318.91 | 2529.0111 | 990 | 2529.0111 | 0 | 2529.0111 | 4215 | 2529.0111 | 500 | 2529.0111 | 0 | 2529.0111 | 0 | 2529.0111 | 0
2025-10-08 | 30536.5729 | 41357.17 | 2544.7144 | 24436.33 | 2544.7144 | 0 | 2544.7144 | 0 | 2544.7144 | 0 | 2544.7144 | 11215.84 | 2544.7144 | 990 | 2544.7144 | 0 | 2544.7144 | 4215 | 2544.7144 | 500 | 2544.7144 | 0 | 2544.7144 | 0 | 2544.7144 | 0
2025-10-09 | 30725.0128 | 41357.17 | 2560.4177 | 24436.33 | 2560.4177 | 0 | 2560.4177 | 0 | 2560.4177 | 0 | 2560.4177 | 11215.84 | 2560.4177 | 990 | 2560.4177 | 0 | 2560.4177 | 4215 | 2560.4177 | 500 | 2560.4177 | 0 | 2560.4177 | 0 | 2560.4177 | 0
2025-10-10 | 30913.4527 | 41357.17 | 2576.1211 | 24436.33 | 2576.1211 | 0 | 2576.1211 | 0 | 2576.1211 | 0 | 2576.1211 | 11215.84 | 2576.1211 | 990 | 2576.1211 | 0 | 2576.1211 | 4215 | 2576.1211 | 500 | 2576.1211 | 0 | 2576.1211 | 0 | 2576.1211 | 0
2025-10-11 | 31101.8926 | 42957.17 | 2591.8244 | 26036.33 | 2591.8244 | 0 | 2591.8244 | 0 | 2591.8244 | 0 | 2591.8244 | 11215.84 | 2591.8244 | 990 | 2591.8244 | 0 | 2591.8244 | 4215 | 2591.8244 | 500 | 2591.8244 | 0 | 2591.8244 | 0 | 2591.8244 | 0
2025-10-12 | 31290.3325 | 42957.17 | 2607.5277 | 26036.33 | 2607.5277 | 0 | 2607.5277 | 0 | 2607.5277 | 0 | 2607.5277 | 11215.84 | 2607.5277 | 990 | 2607.5277 | 0 | 2607.5277 | 4215 | 2607.5277 | 500 | 2607.5277 | 0 | 2607.5277 | 0 | 2607.5277 | 0
2025-10-13 | 31478.7724 | 42957.17 | 2623.231 | 26036.33 | 2623.231 | 0 | 2623.231 | 0 | 2623.231 | 0 | 2623.231 | 11215.84 | 2623.231 | 990 | 2623.231 | 0 | 2623.231 | 4215 | 2623.231 | 500 | 2623.231 | 0 | 2623.231 | 0 | 2623.231 | 0
2025-10-14 | 31667.2123 | 42957.17 | 2638.9344 | 26036.33 | 2638.9344 | 0 | 2638.9344 | 0 | 2638.9344 | 0 | 2638.9344 | 11215.84 | 2638.9344 | 990 | 2638.9344 | 0 | 2638.9344 | 4215 | 2638.9344 | 500 | 2638.9344 | 0 | 2638.9344 | 0 | 2638.9344 | 0
2025-10-15 | 31855.6522 | 42957.17 | 2654.6377 | 26036.33 | 2654.6377 | 0 | 2654.6377 | 0 | 2654.6377 | 0 | 2654.6377 | 11215.84 | 2654.6377 | 990 | 2654.6377 | 0 | 2654.6377 | 4215 | 2654.6377 | 500 | 2654.6377 | 0 | 2654.6377 | 0 | 2654.6377 | 0
2025-10-16 | 32044.0921 | 42957.17 | 2670.341 | 26036.33 | 2670.341 | 0 | 2670.341 | 0 | 2670.341 | 0 | 2670.341 | 11215.84 | 2670.341 | 990 | 2670.341 | 0 | 2670.341 | 4215 | 2670.341 | 500 | 2670.341 | 0 | 2670.341 | 0 | 2670.341 | 0
2025-10-17 | 32232.532 | 42957.17 | 2686.0443 | 26036.33 | 2686.0443 | 0 | 2686.0443 | 0 | 2686.0443 | 0 | 2686.0443 | 11215.84 | 2686.0443 | 990 | 2686.0443 | 0 | 2686.0443 | 4215 | 2686.0443 | 500 | 2686.0443 | 0 | 2686.0443 | 0 | 2686.0443 | 0
2025-10-18 | 32420.9719 | 42957.17 | 2701.7477 | 26036.33 | 2701.7477 | 0 | 2701.7477 | 0 | 2701.7477 | 0 | 2701.7477 | 11215.84 | 2701.7477 | 990 | 2701.7477 | 0 | 2701.7477 | 4215 | 2701.7477 | 500 | 2701.7477 | 0 | 2701.7477 | 0 | 2701.7477 | 0
2025-10-19 | 32609.4118 | 42957.17 | 2717.451 | 26036.33 | 2717.451 | 0 | 2717.451 | 0 | 2717.451 | 0 | 2717.451 | 11215.84 | 2717.451 | 990 | 2717.451 | 0 | 2717.451 | 4215 | 2717.451 | 500 | 2717.451 | 0 | 2717.451 | 0 | 2717.451 | 0
2025-10-20 | 32797.8517 | 42957.17 | 2733.1543 | 26036.33 | 2733.1543 | 0 | 2733.1543 | 0 | 2733.1543 | 0 | 2733.1543 | 11215.84 | 2733.1543 | 990 | 2733.1543 | 0 | 2733.1543 | 4215 | 2733.1543 | 500 | 2733.1543 | 0 | 2733.1543 | 0 | 2733.1543 | 0
2025-10-21 | 32986.2916 | 42957.17 | 2748.8576 | 26036.33 | 2748.8576 | 0 | 2748.8576 | 0 | 2748.8576 | 0 | 2748.8576 | 11215.84 | 2748.8576 | 990 | 2748.8576 | 0 | 2748.8576 | 4215 | 2748.8576 | 500 | 2748.8576 | 0 | 2748.8576 | 0 | 2748.8576 | 0
2025-10-22 | 33174.7315 | 42957.17 | 2764.561 | 26036.33 | 2764.561 | 0 | 2764.561 | 0 | 2764.561 | 0 | 2764.561 | 11215.84 | 2764.561 | 990 | 2764.561 | 0 | 2764.561 | 4215 | 2764.561 | 500 | 2764.561 | 0 | 2764.561 | 0 | 2764.561 | 0
2025-10-23 | 33363.1714 | 42957.17 | 2780.2643 | 26036.33 | 2780.2643 | 0 | 2780.2643 | 0 | 2780.2643 | 0 | 2780.2643 | 11215.84 | 2780.2643 | 990 | 2780.2643 | 0 | 2780.2643 | 4215 | 2780.2643 | 500 | 2780.2643 | 0 | 2780.2643 | 0 | 2780.2643 | 0
2025-10-24 | 33551.6113 | 42957.17 | 2795.9676 | 26036.33 | 2795.9676 | 0 | 2795.9676 | 0 | 2795.9676 | 0 | 2795.9676 | 11215.84 | 2795.9676 | 990 | 2795.9676 | 0 | 2795.9676 | 4215 | 2795.9676 | 500 | 2795.9676 | 0 | 2795.9676 | 0 | 2795.9676 | 0
2025-10-25 | 33740.0512 | 42957.17 | 2811.6709 | 26036.33 | 2811.6709 | 0 | 2811.6709 | 0 | 2811.6709 | 0 | 2811.6709 | 11215.84 | 2811.6709 | 990 | 2811.6709 | 0 | 2811.6709 | 4215 | 2811.6709 | 500 | 2811.6709 | 0 | 2811.6709 | 0 | 2811.6709 | 0
2025-10-26 | 33928.491 | 42957.17 | 2827.3743 | 26036.33 | 2827.3743 | 0 | 2827.3743 | 0 | 2827.3743 | 0 | 2827.3743 | 11215.84 | 2827.3743 | 990 | 2827.3743 | 0 | 2827.3743 | 4215 | 2827.3743 | 500 | 2827.3743 | 0 | 2827.3743 | 0 | 2827.3743 | 0
2025-10-27 | 34116.9309 |  | 2843.0776 |  | 2843.0776 |  | 2843.0776 |  | 2843.0776 |  | 2843.0776 |  | 2843.0776 |  | 2843.0776 |  | 2843.0776 |  | 2843.0776 |  | 2843.0776 |  | 2843.0776 |  | 2843.0776
2025-10-28 | 34305.3708 |  | 2858.7809 |  | 2858.7809 |  | 2858.7809 |  | 2858.7809 |  | 2858.7809 |  | 2858.7809 |  | 2858.7809 |  | 2858.7809 |  | 2858.7809 |  | 2858.7809 |  | 2858.7809 |  | 2858.7809
2025-10-29 | 34493.8107 |  | 2874.4842 |  | 2874.4842 |  | 2874.4842 |  | 2874.4842 |  | 2874.4842 |  | 2874.4842 |  | 2874.4842 |  | 2874.4842 |  | 2874.4842 |  | 2874.4842 |  | 2874.4842 |  | 2874.4842
2025-10-30 | 34682.2506 |  | 2890.1876 |  | 2890.1876 |  | 2890.1876 |  | 2890.1876 |  | 2890.1876 |  | 2890.1876 |  | 2890.1876 |  | 2890.1876 |  | 2890.1876 |  | 2890.1876 |  | 2890.1876 |  | 2890.1876
2025-10-31 | 34870.6905 |  | 2905.8909 |  | 2905.8909 |  | 2905.8909 |  | 2905.8909 |  | 2905.8909 |  | 2905.8909 |  | 2905.8909 |  | 2905.8909 |  | 2905.8909 |  | 2905.8909 |  | 2905.8909 |  | 2905.8909
2025-11-01 | 35059.1304 |  | 2921.5942 |  | 2921.5942 |  | 2921.5942 |  | 2921.5942 |  | 2921.5942 |  | 2921.5942 |  | 2921.5942 |  | 2921.5942 |  | 2921.5942 |  | 2921.5942 |  | 2921.5942 |  | 2921.5942
2025-11-02 | 35247.5703 |  | 2937.2975 |  | 2937.2975 |  | 2937.2975 |  | 2937.2975 |  | 2937.2975 |  | 2937.2975 |  | 2937.2975 |  | 2937.2975 |  | 2937.2975 |  | 2937.2975 |  | 2937.2975 |  | 2937.2975
2025-11-03 | 35436.0102 |  | 2953.0009 |  | 2953.0009 |  | 2953.0009 |  | 2953.0009 |  | 2953.0009 |  | 2953.0009 |  | 2953.0009 |  | 2953.0009 |  | 2953.0009 |  | 2953.0009 |  | 2953.0009 |  | 2953.0009
2025-11-04 | 35624.4501 |  | 2968.7042 |  | 2968.7042 |  | 2968.7042 |  | 2968.7042 |  | 2968.7042 |  | 2968.7042 |  | 2968.7042 |  | 2968.7042 |  | 2968.7042 |  | 2968.7042 |  | 2968.7042 |  | 2968.7042
2025-11-05 | 35812.89 |  | 2984.4075 |  | 2984.4075 |  | 2984.4075 |  | 2984.4075 |  | 2984.4075 |  | 2984.4075 |  | 2984.4075 |  | 2984.4075 |  | 2984.4075 |  | 2984.4075 |  | 2984.4075 |  | 2984.4075
2025-11-06 | 36001.3299 |  | 3000.1108 |  | 3000.1108 |  | 3000.1108 |  | 3000.1108 |  | 3000.1108 |  | 3000.1108 |  | 3000.1108 |  | 3000.1108 |  | 3000.1108 |  | 3000.1108 |  | 3000.1108 |  | 3000.1108
2025-11-07 | 36189.7698 |  | 3015.8142 |  | 3015.8142 |  | 3015.8142 |  | 3015.8142 |  | 3015.8142 |  | 3015.8142 |  | 3015.8142 |  | 3015.8142 |  | 3015.8142 |  | 3015.8142 |  | 3015.8142 |  | 3015.8142
2025-11-08 | 36378.2097 |  | 3031.5175 |  | 3031.5175 |  | 3031.5175 |  | 3031.5175 |  | 3031.5175 |  | 3031.5175 |  | 3031.5175 |  | 3031.5175 |  | 3031.5175 |  | 3031.5175 |  | 3031.5175 |  | 3031.5175
2025-11-09 | 36566.6496 |  | 3047.2208 |  | 3047.2208 |  | 3047.2208 |  | 3047.2208 |  | 3047.2208 |  | 3047.2208 |  | 3047.2208 |  | 3047.2208 |  | 3047.2208 |  | 3047.2208 |  | 3047.2208 |  | 3047.2208
2025-11-10 | 36755.0895 |  | 3062.9241 |  | 3062.9241 |  | 3062.9241 |  | 3062.9241 |  | 3062.9241 |  | 3062.9241 |  | 3062.9241 |  | 3062.9241 |  | 3062.9241 |  | 3062.9241 |  | 3062.9241 |  | 3062.9241
2025-11-11 | 36943.5294 |  | 3078.6275 |  | 3078.6275 |  | 3078.6275 |  | 3078.6275 |  | 3078.6275 |  | 3078.6275 |  | 3078.6275 |  | 3078.6275 |  | 3078.6275 |  | 3078.6275 |  | 3078.6275 |  | 3078.6275
2025-11-12 | 37131.9693 |  | 3094.3308 |  | 3094.3308 |  | 3094.3308 |  | 3094.3308 |  | 3094.3308 |  | 3094.3308 |  | 3094.3308 |  | 3094.3308 |  | 3094.3308 |  | 3094.3308 |  | 3094.3308 |  | 3094.3308
2025-11-13 | 37320.4092 |  | 3110.0341 |  | 3110.0341 |  | 3110.0341 |  | 3110.0341 |  | 3110.0341 |  | 3110.0341 |  | 3110.0341 |  | 3110.0341 |  | 3110.0341 |  | 3110.0341 |  | 3110.0341 |  | 3110.0341
2025-11-14 | 37508.8491 |  | 3125.7374 |  | 3125.7374 |  | 3125.7374 |  | 3125.7374 |  | 3125.7374 |  | 3125.7374 |  | 3125.7374 |  | 3125.7374 |  | 3125.7374 |  | 3125.7374 |  | 3125.7374 |  | 3125.7374
2025-11-15 | 37697.289 |  | 3141.4408 |  | 3141.4408 |  | 3141.4408 |  | 3141.4408 |  | 3141.4408 |  | 3141.4408 |  | 3141.4408 |  | 3141.4408 |  | 3141.4408 |  | 3141.4408 |  | 3141.4408 |  | 3141.4408
2025-11-16 | 37885.7289 |  | 3157.1441 |  | 3157.1441 |  | 3157.1441 |  | 3157.1441 |  | 3157.1441 |  | 3157.1441 |  | 3157.1441 |  | 3157.1441 |  | 3157.1441 |  | 3157.1441 |  | 3157.1441 |  | 3157.1441
2025-11-17 | 38074.1688 |  | 3172.8474 |  | 3172.8474 |  | 3172.8474 |  | 3172.8474 |  | 3172.8474 |  | 3172.8474 |  | 3172.8474 |  | 3172.8474 |  | 3172.8474 |  | 3172.8474 |  | 3172.8474 |  | 3172.8474
2025-11-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-31 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-31 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-31 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-31 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-31 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-20 | 38556.7263 |  | 3213.0605 |  | 3213.0605 |  | 3213.0605 |  | 3213.0605 |  | 3213.0605 |  | 3213.0605 |  | 3213.0605 |  | 3213.0605 |  | 3213.0605 |  | 3213.0605 |  | 3213.0605 |  | 3213.0605
2026-08-21 | 38850.844 |  | 3237.5703 |  | 3237.5703 |  | 3237.5703 |  | 3237.5703 |  | 3237.5703 |  | 3237.5703 |  | 3237.5703 |  | 3237.5703 |  | 3237.5703 |  | 3237.5703 |  | 3237.5703 |  | 3237.5703
2026-08-22 | 39144.9616 |  | 3262.0801 |  | 3262.0801 |  | 3262.0801 |  | 3262.0801 |  | 3262.0801 |  | 3262.0801 |  | 3262.0801 |  | 3262.0801 |  | 3262.0801 |  | 3262.0801 |  | 3262.0801 |  | 3262.0801
2026-08-23 | 39439.0793 |  | 3286.5899 |  | 3286.5899 |  | 3286.5899 |  | 3286.5899 |  | 3286.5899 |  | 3286.5899 |  | 3286.5899 |  | 3286.5899 |  | 3286.5899 |  | 3286.5899 |  | 3286.5899 |  | 3286.5899
2026-08-24 | 39733.1969 |  | 3311.0997 |  | 3311.0997 |  | 3311.0997 |  | 3311.0997 |  | 3311.0997 |  | 3311.0997 |  | 3311.0997 |  | 3311.0997 |  | 3311.0997 |  | 3311.0997 |  | 3311.0997 |  | 3311.0997
2026-08-25 | 40027.3146 |  | 3335.6095 |  | 3335.6095 |  | 3335.6095 |  | 3335.6095 |  | 3335.6095 |  | 3335.6095 |  | 3335.6095 |  | 3335.6095 |  | 3335.6095 |  | 3335.6095 |  | 3335.6095 |  | 3335.6095
2026-08-26 | 40321.4322 |  | 3360.1194 |  | 3360.1194 |  | 3360.1194 |  | 3360.1194 |  | 3360.1194 |  | 3360.1194 |  | 3360.1194 |  | 3360.1194 |  | 3360.1194 |  | 3360.1194 |  | 3360.1194 |  | 3360.1194
2026-08-27 | 40615.5499 |  | 3384.6292 |  | 3384.6292 |  | 3384.6292 |  | 3384.6292 |  | 3384.6292 |  | 3384.6292 |  | 3384.6292 |  | 3384.6292 |  | 3384.6292 |  | 3384.6292 |  | 3384.6292 |  | 3384.6292
2026-08-28 | 40909.6675 |  | 3409.139 |  | 3409.139 |  | 3409.139 |  | 3409.139 |  | 3409.139 |  | 3409.139 |  | 3409.139 |  | 3409.139 |  | 3409.139 |  | 3409.139 |  | 3409.139 |  | 3409.139
2026-08-29 | 41203.7852 |  | 3433.6488 |  | 3433.6488 |  | 3433.6488 |  | 3433.6488 |  | 3433.6488 |  | 3433.6488 |  | 3433.6488 |  | 3433.6488 |  | 3433.6488 |  | 3433.6488 |  | 3433.6488 |  | 3433.6488
2026-08-30 | 41497.9028 |  | 3458.1586 |  | 3458.1586 |  | 3458.1586 |  | 3458.1586 |  | 3458.1586 |  | 3458.1586 |  | 3458.1586 |  | 3458.1586 |  | 3458.1586 |  | 3458.1586 |  | 3458.1586 |  | 3458.1586
2026-08-31 | 41792.0205 |  | 3482.6684 |  | 3482.6684 |  | 3482.6684 |  | 3482.6684 |  | 3482.6684 |  | 3482.6684 |  | 3482.6684 |  | 3482.6684 |  | 3482.6684 |  | 3482.6684 |  | 3482.6684 |  | 3482.6684
2026-09-01 | 42086.1381 |  | 3507.1782 |  | 3507.1782 |  | 3507.1782 |  | 3507.1782 |  | 3507.1782 |  | 3507.1782 |  | 3507.1782 |  | 3507.1782 |  | 3507.1782 |  | 3507.1782 |  | 3507.1782 |  | 3507.1782
2026-09-02 | 42380.2558 |  | 3531.688 |  | 3531.688 |  | 3531.688 |  | 3531.688 |  | 3531.688 |  | 3531.688 |  | 3531.688 |  | 3531.688 |  | 3531.688 |  | 3531.688 |  | 3531.688 |  | 3531.688
2026-09-03 | 42674.3734 |  | 3556.1978 |  | 3556.1978 |  | 3556.1978 |  | 3556.1978 |  | 3556.1978 |  | 3556.1978 |  | 3556.1978 |  | 3556.1978 |  | 3556.1978 |  | 3556.1978 |  | 3556.1978 |  | 3556.1978
2026-09-04 | 42968.491 |  | 3580.7076 |  | 3580.7076 |  | 3580.7076 |  | 3580.7076 |  | 3580.7076 |  | 3580.7076 |  | 3580.7076 |  | 3580.7076 |  | 3580.7076 |  | 3580.7076 |  | 3580.7076 |  | 3580.7076
2026-09-05 | 43262.6087 |  | 3605.2174 |  | 3605.2174 |  | 3605.2174 |  | 3605.2174 |  | 3605.2174 |  | 3605.2174 |  | 3605.2174 |  | 3605.2174 |  | 3605.2174 |  | 3605.2174 |  | 3605.2174 |  | 3605.2174
2026-09-06 | 43556.7263 |  | 3629.7272 |  | 3629.7272 |  | 3629.7272 |  | 3629.7272 |  | 3629.7272 |  | 3629.7272 |  | 3629.7272 |  | 3629.7272 |  | 3629.7272 |  | 3629.7272 |  | 3629.7272 |  | 3629.7272
2026-09-07 | 43850.844 |  | 3654.237 |  | 3654.237 |  | 3654.237 |  | 3654.237 |  | 3654.237 |  | 3654.237 |  | 3654.237 |  | 3654.237 |  | 3654.237 |  | 3654.237 |  | 3654.237 |  | 3654.237
2026-09-08 | 44144.9616 |  | 3678.7468 |  | 3678.7468 |  | 3678.7468 |  | 3678.7468 |  | 3678.7468 |  | 3678.7468 |  | 3678.7468 |  | 3678.7468 |  | 3678.7468 |  | 3678.7468 |  | 3678.7468 |  | 3678.7468
2026-09-09 | 44439.0793 |  | 3703.2566 |  | 3703.2566 |  | 3703.2566 |  | 3703.2566 |  | 3703.2566 |  | 3703.2566 |  | 3703.2566 |  | 3703.2566 |  | 3703.2566 |  | 3703.2566 |  | 3703.2566 |  | 3703.2566
2026-09-10 | 44733.1969 |  | 3727.7664 |  | 3727.7664 |  | 3727.7664 |  | 3727.7664 |  | 3727.7664 |  | 3727.7664 |  | 3727.7664 |  | 3727.7664 |  | 3727.7664 |  | 3727.7664 |  | 3727.7664 |  | 3727.7664
2026-09-11 | 45027.3146 |  | 3752.2762 |  | 3752.2762 |  | 3752.2762 |  | 3752.2762 |  | 3752.2762 |  | 3752.2762 |  | 3752.2762 |  | 3752.2762 |  | 3752.2762 |  | 3752.2762 |  | 3752.2762 |  | 3752.2762
2026-09-12 | 45321.4322 |  | 3776.786 |  | 3776.786 |  | 3776.786 |  | 3776.786 |  | 3776.786 |  | 3776.786 |  | 3776.786 |  | 3776.786 |  | 3776.786 |  | 3776.786 |  | 3776.786 |  | 3776.786
2026-09-13 | 45615.5499 |  | 3801.2958 |  | 3801.2958 |  | 3801.2958 |  | 3801.2958 |  | 3801.2958 |  | 3801.2958 |  | 3801.2958 |  | 3801.2958 |  | 3801.2958 |  | 3801.2958 |  | 3801.2958 |  | 3801.2958
2026-09-14 | 45909.6675 |  | 3825.8056 |  | 3825.8056 |  | 3825.8056 |  | 3825.8056 |  | 3825.8056 |  | 3825.8056 |  | 3825.8056 |  | 3825.8056 |  | 3825.8056 |  | 3825.8056 |  | 3825.8056 |  | 3825.8056
2026-09-15 | 46203.7852 |  | 3850.3154 |  | 3850.3154 |  | 3850.3154 |  | 3850.3154 |  | 3850.3154 |  | 3850.3154 |  | 3850.3154 |  | 3850.3154 |  | 3850.3154 |  | 3850.3154 |  | 3850.3154 |  | 3850.3154
2026-09-16 | 46497.9028 |  | 3874.8252 |  | 3874.8252 |  | 3874.8252 |  | 3874.8252 |  | 3874.8252 |  | 3874.8252 |  | 3874.8252 |  | 3874.8252 |  | 3874.8252 |  | 3874.8252 |  | 3874.8252 |  | 3874.8252
2026-09-17 | 46792.0205 |  | 3899.335 |  | 3899.335 |  | 3899.335 |  | 3899.335 |  | 3899.335 |  | 3899.335 |  | 3899.335 |  | 3899.335 |  | 3899.335 |  | 3899.335 |  | 3899.335 |  | 3899.335
2026-09-18 | 47086.1381 |  | 3923.8448 |  | 3923.8448 |  | 3923.8448 |  | 3923.8448 |  | 3923.8448 |  | 3923.8448 |  | 3923.8448 |  | 3923.8448 |  | 3923.8448 |  | 3923.8448 |  | 3923.8448 |  | 3923.8448
2026-09-19 | 47380.2558 |  | 3948.3546 |  | 3948.3546 |  | 3948.3546 |  | 3948.3546 |  | 3948.3546 |  | 3948.3546 |  | 3948.3546 |  | 3948.3546 |  | 3948.3546 |  | 3948.3546 |  | 3948.3546 |  | 3948.3546
2026-09-20 | 47674.3734 |  | 3972.8645 |  | 3972.8645 |  | 3972.8645 |  | 3972.8645 |  | 3972.8645 |  | 3972.8645 |  | 3972.8645 |  | 3972.8645 |  | 3972.8645 |  | 3972.8645 |  | 3972.8645 |  | 3972.8645
2026-09-21 | 47968.491 |  | 3997.3743 |  | 3997.3743 |  | 3997.3743 |  | 3997.3743 |  | 3997.3743 |  | 3997.3743 |  | 3997.3743 |  | 3997.3743 |  | 3997.3743 |  | 3997.3743 |  | 3997.3743 |  | 3997.3743
2026-09-22 | 48262.6087 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841

## Equipment Cost
Date | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Planned 1805 · Equipment - Forklift (Cumulative) | Actual 1805 · Equipment - Forklift (Cumulative) | Planned 1818 · Equipment - BCU (Cumulative) | Actual 1818 · Equipment - BCU (Cumulative) | Planned 1819 · Equipment - TPMB (Cumulative) | Actual 1819 · Equipment - TPMB (Cumulative) | Planned 1820 · Equipment & Tools (Cumulative) | Actual 1820 · Equipment & Tools (Cumulative) | Planned 1821 · Equipment - C3 (Cumulative) | Actual 1821 · Equipment - C3 (Cumulative) | Planned 1822 · Equipment - C2 (Cumulative) | Actual 1822 · Equipment - C2 (Cumulative) | Planned 1823 · Equipment - TCU Basic (Cumulative) | Actual 1823 · Equipment - TCU Basic (Cumulative) | Planned 1824 · Equipment - TCU PLC (Cumulative) | Actual 1824 · Equipment - TCU PLC (Cumulative) | Planned 1825 · Equipment - Blower Skids (Cumulative) | Actual 1825 · Equipment - Blower Skids (Cumulative) | Planned 1826 · Equipment - Well Heads (Cumulative) | Actual 1826 · Equipment - Well Heads (Cumulative) | Planned 1827 · Equipment - Thermal Wells (Cumulative) | Actual 1827 · Equipment - Thermal Wells (Cumulative) | Planned 1829 · Equipment - Water Treatment Sys (Cumulative) | Actual 1829 · Equipment - Water Treatment Sys (Cumulative) | Planned 1830 · Equipment - Vapor Extraction (Cumulative) | Actual 1830 · Equipment - Vapor Extraction (Cumulative) | Planned 1831 · Equipment - GTR/C3 Components (Cumulative) | Actual 1831 · Equipment - GTR/C3 Components (Cumulative) | Planned 1832 · Equip - Control/Dist panels (Cumulative) | Actual 1832 · Equip - Control/Dist panels (Cumulative) | Planned 1833 · Equipment - Office & computer (Cumulative) | Actual 1833 · Equipment - Office & computer (Cumulative) | Planned 5113 · Repairs & maint (Direct) (Cumulative) | Actual 5113 · Repairs & maint (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 947.6292 | 5000 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 5000 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0 | 55.7429 | 0
2025-06-26 | 1895.2584 | 5000 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 5000 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0 | 111.4858 | 0
2025-06-27 | 2842.8876 | 5000 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 5000 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0 | 167.2287 | 0
2025-06-28 | 3790.5169 | 5000 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 5000 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0 | 222.9716 | 0
2025-06-29 | 4738.1461 | 5000 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 5000 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0 | 278.7145 | 0
2025-06-30 | 5685.7753 | 5000 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 5000 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0 | 334.4574 | 0
2025-07-01 | 6633.4045 | 5000 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 5000 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0 | 390.2003 | 0
2025-07-02 | 7581.0337 | 5000 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 5000 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0 | 445.9432 | 0
2025-07-03 | 8528.6629 | 5000 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 5000 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0 | 501.6861 | 0
2025-07-04 | 9476.2921 | 5000 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 5000 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0 | 557.4289 | 0
2025-07-05 | 10423.9213 | 5000 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 5000 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0 | 613.1718 | 0
2025-07-06 | 11371.5506 | 5000 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 5000 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0 | 668.9147 | 0
2025-07-07 | 12319.1798 | 5000 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 5000 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0 | 724.6576 | 0
2025-07-08 | 13266.809 | 5000 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 5000 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0 | 780.4005 | 0
2025-07-09 | 14214.4382 | 5000 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 5000 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0 | 836.1434 | 0
2025-07-10 | 15162.0674 | 5000 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 5000 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0 | 891.8863 | 0
2025-07-11 | 16109.6966 | 5000 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 5000 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0 | 947.6292 | 0
2025-07-12 | 17057.3258 | 5000 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 5000 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0 | 1003.3721 | 0
2025-07-13 | 18004.9551 | 5000 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 5000 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0 | 1059.115 | 0
2025-07-14 | 18952.5843 | 5000 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 5000 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0 | 1114.8579 | 0
2025-07-15 | 19900.2135 | 5000 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 5000 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0 | 1170.6008 | 0
2025-07-16 | 20847.8427 | 5000 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 5000 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0 | 1226.3437 | 0
2025-07-17 | 21795.4719 | 5000 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 5000 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0 | 1282.0866 | 0
2025-07-18 | 22743.1011 | 5000 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 5000 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0 | 1337.8295 | 0
2025-07-19 | 23690.7303 | 5000 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 5000 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0 | 1393.5724 | 0
2025-07-20 | 24638.3596 | 5000 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 5000 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0 | 1449.3153 | 0
2025-07-21 | 25585.9888 | 5000 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 5000 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0 | 1505.0582 | 0
2025-07-22 | 26533.618 | 5000 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 5000 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0 | 1560.8011 | 0
2025-07-23 | 27481.2472 | 5000 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 5000 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0 | 1616.544 | 0
2025-07-24 | 28428.8764 | 5000 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 5000 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0 | 1672.2868 | 0
2025-07-25 | 29376.5056 | 5000 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 5000 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0 | 1728.0297 | 0
2025-07-26 | 30324.1348 | 5000 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 5000 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0 | 1783.7726 | 0
2025-07-27 | 31271.764 | 5000 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 5000 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0 | 1839.5155 | 0
2025-07-28 | 32219.3933 | 5000 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 5000 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0 | 1895.2584 | 0
2025-07-29 | 33167.0225 | 5000 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 5000 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0 | 1951.0013 | 0
2025-07-30 | 34114.6517 | 5000 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 5000 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0 | 2006.7442 | 0
2025-07-31 | 35062.2809 | 5000 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 5000 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0 | 2062.4871 | 0
2025-08-01 | 36009.9101 | 5000 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 5000 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0 | 2118.23 | 0
2025-08-02 | 36957.5393 | 5000 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 5000 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0 | 2173.9729 | 0
2025-08-03 | 37905.1685 | 5000 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 5000 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0 | 2229.7158 | 0
2025-08-04 | 38852.7978 | 5000 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 5000 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0 | 2285.4587 | 0
2025-08-05 | 39800.427 | 5000 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 5000 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0 | 2341.2016 | 0
2025-08-06 | 40748.0562 | 5000 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 5000 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0 | 2396.9445 | 0
2025-08-07 | 41695.6854 | 5000 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 5000 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0 | 2452.6874 | 0
2025-08-08 | 42643.3146 | 5000 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 5000 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0 | 2508.4303 | 0
2025-08-09 | 43590.9438 | 5000 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 5000 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0 | 2564.1732 | 0
2025-08-10 | 44538.573 | 5000 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 5000 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0 | 2619.9161 | 0
2025-08-11 | 45486.2022 | 5000 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 5000 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0 | 2675.659 | 0
2025-08-12 | 46433.8315 | 5000 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 5000 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0 | 2731.4019 | 0
2025-08-13 | 47381.4607 | 5000 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 5000 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0 | 2787.1447 | 0
2025-08-14 | 48329.0899 | 5000 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 5000 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0 | 2842.8876 | 0
2025-08-15 | 49276.7191 | 5000 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 5000 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0 | 2898.6305 | 0
2025-08-16 | 50224.3483 | 5000 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 5000 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0 | 2954.3734 | 0
2025-08-17 | 51171.9775 | 5000 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 5000 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0 | 3010.1163 | 0
2025-08-18 | 52119.6067 | 5000 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 5000 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0 | 3065.8592 | 0
2025-08-19 | 53067.236 | 5000 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 5000 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0 | 3121.6021 | 0
2025-08-20 | 54014.8652 | 5000 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 5000 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0 | 3177.345 | 0
2025-08-21 | 54962.4944 | 5000 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 5000 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0 | 3233.0879 | 0
2025-08-22 | 55910.1236 | 5000 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 5000 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0 | 3288.8308 | 0
2025-08-23 | 56857.7528 | 5000 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 5000 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0 | 3344.5737 | 0
2025-08-24 | 57805.382 | 5000 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 5000 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0 | 3400.3166 | 0
2025-08-25 | 58753.0112 | 5000 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 5000 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0 | 3456.0595 | 0
2025-08-26 | 59700.6404 | 5000 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 5000 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0 | 3511.8024 | 0
2025-08-27 | 60648.2697 | 5000 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 5000 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0 | 3567.5453 | 0
2025-08-28 | 61595.8989 | 5000 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 5000 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0 | 3623.2882 | 0
2025-08-29 | 62543.5281 | 5000 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 5000 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0 | 3679.0311 | 0
2025-08-30 | 63491.1573 | 5000 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 5000 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0 | 3734.774 | 0
2025-08-31 | 64438.7865 | 5000 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 5000 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0 | 3790.5169 | 0
2025-09-01 | 65386.4157 | 5000 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 5000 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0 | 3846.2597 | 0
2025-09-02 | 66334.0449 | 5000 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 5000 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0 | 3902.0026 | 0
2025-09-03 | 67281.6742 | 5000 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 5000 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0 | 3957.7455 | 0
2025-09-04 | 68229.3034 | 5000 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 5000 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0 | 4013.4884 | 0
2025-09-05 | 69176.9326 | 5000 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 5000 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0 | 4069.2313 | 0
2025-09-06 | 70124.5618 | 5000 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 5000 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0 | 4124.9742 | 0
2025-09-07 | 71072.191 | 5000 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 5000 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0 | 4180.7171 | 0
2025-09-08 | 72019.8202 | 5000 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 5000 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0 | 4236.46 | 0
2025-09-09 | 72967.4494 | 5000 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 5000 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0 | 4292.2029 | 0
2025-09-10 | 73915.0787 | 5000 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 5000 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0 | 4347.9458 | 0
2025-09-11 | 74862.7079 | 5000 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 5000 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0 | 4403.6887 | 0
2025-09-12 | 75810.3371 | 5000 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 5000 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0 | 4459.4316 | 0
2025-09-13 | 76757.9663 | 5000 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 5000 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0 | 4515.1745 | 0
2025-09-14 | 77705.5955 | 5000 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 5000 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0 | 4570.9174 | 0
2025-09-15 | 78653.2247 | 5000 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 5000 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0 | 4626.6603 | 0
2025-09-16 | 79600.8539 | 5000 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 5000 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0 | 4682.4032 | 0
2025-09-17 | 80548.4831 | 5000 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 5000 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0 | 4738.1461 | 0
2025-09-18 | 81496.1124 | 5000 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 5000 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0 | 4793.889 | 0
2025-09-19 | 82443.7416 | 5000 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 5000 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0 | 4849.6319 | 0
2025-09-20 | 83391.3708 | 5000 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 5000 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0 | 4905.3748 | 0
2025-09-21 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-22 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-23 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-24 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-25 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-26 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-27 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-28 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-29 | 84580.2617 | 5000 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 5000 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0 | 4975.3095 | 0
2025-09-30 | 84821.5234 | 5000 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 5000 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0 | 4989.5014 | 0
2025-10-01 | 85062.7852 | 5000 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 5000 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0 | 5003.6932 | 0
2025-10-02 | 85304.0469 | 5000 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 5000 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0 | 5017.8851 | 0
2025-10-03 | 85545.3086 | 5000 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 5000 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0 | 5032.077 | 0
2025-10-04 | 85786.5703 | 5000 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 5000 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0 | 5046.2688 | 0
2025-10-05 | 86027.8321 | 5000 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 5000 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0 | 5060.4607 | 0
2025-10-06 | 86269.0938 | 5000 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 5000 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0 | 5074.6526 | 0
2025-10-07 | 86510.3555 | 5000 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 5000 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0 | 5088.8444 | 0
2025-10-08 | 86751.6172 | 5000 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 5000 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0 | 5103.0363 | 0
2025-10-09 | 86992.8789 | 5000 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 5000 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0 | 5117.2282 | 0
2025-10-10 | 87234.1407 | 5000 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 5000 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0 | 5131.42 | 0
2025-10-11 | 87475.4024 | 5000 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 5000 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0 | 5145.6119 | 0
2025-10-12 | 87716.6641 | 5000 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 5000 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0 | 5159.8038 | 0
2025-10-13 | 87957.9258 | 5000 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 5000 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0 | 5173.9956 | 0
2025-10-14 | 88199.1876 | 5000 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 5000 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0 | 5188.1875 | 0
2025-10-15 | 88440.4493 | 5000 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 5000 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0 | 5202.3794 | 0
2025-10-16 | 88681.711 | 5000 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 5000 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0 | 5216.5712 | 0
2025-10-17 | 88922.9727 | 5000 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 5000 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0 | 5230.7631 | 0
2025-10-18 | 89164.2344 | 5000 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 5000 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0 | 5244.955 | 0
2025-10-19 | 89405.4962 | 5000 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 5000 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0 | 5259.1468 | 0
2025-10-20 | 89646.7579 | 5000 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 5000 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0 | 5273.3387 | 0
2025-10-21 | 89888.0196 | 5000 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 5000 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0 | 5287.5306 | 0
2025-10-22 | 90129.2813 | 5000 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 5000 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0 | 5301.7224 | 0
2025-10-23 | 90370.5431 | 5000 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 5000 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0 | 5315.9143 | 0
2025-10-24 | 90611.8048 | 5000 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 5000 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0 | 5330.1062 | 0
2025-10-25 | 90853.0665 | 5000 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 5000 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0 | 5344.298 | 0
2025-10-26 | 91094.3282 | 5000 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 5000 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0 | 5358.4899 | 0
2025-10-27 | 91335.5899 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818 |  | 5372.6818
2025-10-28 | 91576.8517 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736 |  | 5386.8736
2025-10-29 | 91818.1134 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655 |  | 5401.0655
2025-10-30 | 92059.3751 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574 |  | 5415.2574
2025-10-31 | 92300.6368 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492 |  | 5429.4492
2025-11-01 | 92541.8986 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411 |  | 5443.6411
2025-11-02 | 92783.1603 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833 |  | 5457.833
2025-11-03 | 93024.422 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248 |  | 5472.0248
2025-11-04 | 93265.6837 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167 |  | 5486.2167
2025-11-05 | 93506.9454 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086 |  | 5500.4086
2025-11-06 | 93748.2072 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004 |  | 5514.6004
2025-11-07 | 93989.4689 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923 |  | 5528.7923
2025-11-08 | 94230.7306 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842 |  | 5542.9842
2025-11-09 | 94471.9923 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176 |  | 5557.176
2025-11-10 | 94713.254 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679 |  | 5571.3679
2025-11-11 | 94954.5158 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598 |  | 5585.5598
2025-11-12 | 95195.7775 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516 |  | 5599.7516
2025-11-13 | 95437.0392 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435 |  | 5613.9435
2025-11-14 | 95678.3009 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353 |  | 5628.1353
2025-11-15 | 95919.5627 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272 |  | 5642.3272
2025-11-16 | 96160.8244 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191 |  | 5656.5191
2025-11-17 | 96402.0861 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109 |  | 5670.7109
2025-11-18 | 96643.3478 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028
2025-11-19 | 97143.3478 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146 |  | 5714.3146
2025-11-20 | 97643.3478 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263 |  | 5743.7263
2025-11-21 | 98143.3478 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381 |  | 5773.1381
2025-11-22 | 98643.3478 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499 |  | 5802.5499
2025-11-23 | 99143.3478 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616 |  | 5831.9616
2025-11-24 | 99643.3478 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734 |  | 5861.3734
2025-11-25 | 100143.3478 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852 |  | 5890.7852
2025-11-26 | 100643.3478 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969 |  | 5920.1969
2025-11-27 | 101143.3478 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087 |  | 5949.6087
2025-11-28 | 101643.3478 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205 |  | 5979.0205
2025-11-29 | 102143.3478 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322 |  | 6008.4322
2025-11-30 | 102643.3478 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844 |  | 6037.844
2025-12-01 | 103143.3478 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558 |  | 6067.2558
2025-12-02 | 103643.3478 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675 |  | 6096.6675
2025-12-03 | 104143.3478 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793 |  | 6126.0793
2025-12-04 | 104643.3478 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491 |  | 6155.491
2025-12-05 | 105143.3478 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028 |  | 6184.9028
2025-12-06 | 105643.3478 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146 |  | 6214.3146
2025-12-07 | 106143.3478 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263 |  | 6243.7263
2025-12-08 | 106643.3478 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381 |  | 6273.1381
2025-12-09 | 107143.3478 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499 |  | 6302.5499
2025-12-10 | 107643.3478 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616 |  | 6331.9616
2025-12-11 | 108143.3478 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734 |  | 6361.3734
2025-12-12 | 108643.3478 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852 |  | 6390.7852
2025-12-13 | 109143.3478 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969 |  | 6420.1969
2025-12-14 | 109643.3478 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087 |  | 6449.6087
2025-12-15 | 110143.3478 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205 |  | 6479.0205
2025-12-16 | 110643.3478 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322 |  | 6508.4322
2025-12-17 | 111143.3478 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844 |  | 6537.844
2025-12-18 | 111643.3478 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558 |  | 6567.2558
2025-12-19 | 112143.3478 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675 |  | 6596.6675
2025-12-20 | 112643.3478 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793 |  | 6626.0793
2025-12-21 | 113143.3478 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491 |  | 6655.491
2025-12-22 | 113643.3478 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028 |  | 6684.9028
2025-12-23 | 114143.3478 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146 |  | 6714.3146
2025-12-24 | 114643.3478 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263 |  | 6743.7263
2025-12-25 | 115143.3478 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381 |  | 6773.1381
2025-12-26 | 115643.3478 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499 |  | 6802.5499
2025-12-27 | 116143.3478 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616 |  | 6831.9616
2025-12-28 | 116643.3478 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734 |  | 6861.3734
2025-12-29 | 117143.3478 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852 |  | 6890.7852
2025-12-30 | 117643.3478 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969 |  | 6920.1969
2025-12-31 | 118143.3478 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087 |  | 6949.6087
2026-01-01 | 118643.3478 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205 |  | 6979.0205
2026-01-02 | 119143.3478 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322 |  | 7008.4322
2026-01-03 | 119643.3478 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844 |  | 7037.844
2026-01-04 | 120143.3478 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558 |  | 7067.2558
2026-01-05 | 120643.3478 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675 |  | 7096.6675
2026-01-06 | 121143.3478 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793 |  | 7126.0793
2026-01-07 | 121643.3478 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491 |  | 7155.491
2026-01-08 | 122143.3478 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028 |  | 7184.9028
2026-01-09 | 122643.3478 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146 |  | 7214.3146
2026-01-10 | 123143.3478 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263 |  | 7243.7263
2026-01-11 | 123643.3478 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381 |  | 7273.1381
2026-01-12 | 124143.3478 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499 |  | 7302.5499
2026-01-13 | 124643.3478 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616 |  | 7331.9616
2026-01-14 | 125143.3478 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734 |  | 7361.3734
2026-01-15 | 125643.3478 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852 |  | 7390.7852
2026-01-16 | 126143.3478 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969 |  | 7420.1969
2026-01-17 | 126643.3478 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087 |  | 7449.6087
2026-01-18 | 127143.3478 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205 |  | 7479.0205
2026-01-19 | 127643.3478 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322 |  | 7508.4322
2026-01-20 | 128143.3478 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844 |  | 7537.844
2026-01-21 | 128643.3478 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558 |  | 7567.2558
2026-01-22 | 129143.3478 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675 |  | 7596.6675
2026-01-23 | 129643.3478 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793 |  | 7626.0793
2026-01-24 | 130143.3478 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491 |  | 7655.491
2026-01-25 | 130643.3478 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028 |  | 7684.9028
2026-01-26 | 131143.3478 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146 |  | 7714.3146
2026-01-27 | 131643.3478 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263 |  | 7743.7263
2026-01-28 | 132143.3478 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381 |  | 7773.1381
2026-01-29 | 132643.3478 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499 |  | 7802.5499
2026-01-30 | 133143.3478 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616 |  | 7831.9616
2026-01-31 | 133643.3478 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734 |  | 7861.3734
2026-02-01 | 134143.3478 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852 |  | 7890.7852
2026-02-02 | 134643.3478 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969 |  | 7920.1969
2026-02-03 | 135143.3478 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087 |  | 7949.6087
2026-02-04 | 135643.3478 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205 |  | 7979.0205
2026-02-05 | 136143.3478 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322 |  | 8008.4322
2026-02-06 | 136643.3478 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844 |  | 8037.844
2026-02-07 | 137143.3478 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558 |  | 8067.2558
2026-02-08 | 137643.3478 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675 |  | 8096.6675
2026-02-09 | 138143.3478 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793 |  | 8126.0793
2026-02-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491

## Labor Days
Month | Actual Geo Total (Monthly) | Actual On Site Personal (Monthly) | Actual Remote Personal (Monthly) | Planned GEO total personal (Monthly) | Planned on site personal (Monthly) | Planned remote personal (Monthly) | Planned Technician I (Monthly) | Actual Technician I (Monthly) | Planned Technician II (Monthly) | Actual Technician II (Monthly) | Planned Welder (Monthly) | Actual Welder (Monthly) | Planned Engineer/supervisor (Monthly) | Actual Engineer/supervisor (Monthly) | Planned Manager/senior Engineer (Monthly) | Actual Manager/senior Engineer (Monthly) | Planned Remote mid engineer (Monthly) | Actual Remote mid engineer (Monthly) | Planned Remote senior (Monthly) | Actual Remote senior (Monthly)
April 25 | 14.5 | 0 | 14.5 | 46.9 | 0 | 46.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.25 | 46.9 | 6.25
May 25 | 0 | 0 | 0 | 49.1333 | 0 | 49.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.1333 | 0
June 25 | 13.125 | 0 | 13.125 | 39.3 | 1.3333 | 37.9667 | 0 | 0 | 0.88889 | 0 | 0 | 0 | 0.44444 | 0 | 0 | 0 | 0 | 10.625 | 37.9667 | 2.5
July 25 | 14.5 | 0 | 14.5 | 7.6667 | 7.6667 | 0 | 0 | 0 | 5.1111 | 0 | 0 | 0 | 2.5556 | 0 | 0 | 0 | 0 | 14.5 | 0 | 0
August 25 | 18.5 | 0 | 18.5 | 7 | 7 | 0 | 0 | 0 | 4.6667 | 0 | 0 | 0 | 2.3333 | 0 | 0 | 0 | 0 | 13.5 | 0 | 5
September 25 | 52 | 23 | 29 | 22.0878 | 20.7905 | 1.2973 | 0 | 0 | 14.259 | 23 | 3.2432 | 0 | 1.6667 | 0 | 1.6216 | 0 | 0 | 14.875 | 1.2973 | 14.125
October 25 | 18.125 | 10 | 8.125 | 196.5101 | 181.5912 | 14.9189 | 0 | 0 | 125.6453 | 10 | 37.2973 | 0 | 0 | 0 | 18.6486 | 0 | 0 | 2.375 | 14.9189 | 5.75
November 25 | 0 | 0 | 0 | 143.6127 | 128.1718 | 15.4409 | 2.8571 | 0 | 72.2683 | 0 | 30.888 | 0 | 5.2857 | 0 | 16.8726 | 0 | 0 | 0 | 15.4409 | 0
December 25 | 0 | 0 | 0 | 106.1381 | 86.3571 | 19.781 | 7.381 | 0 | 17.3452 | 0 | 29.5238 | 0 | 13.6548 | 0 | 18.4524 | 0 | 0 | 0 | 19.781 | 0
January 26 | 0 | 0 | 0 | 106.1381 | 86.3571 | 19.781 | 7.381 | 0 | 17.3452 | 0 | 29.5238 | 0 | 13.6548 | 0 | 18.4524 | 0 | 0 | 0 | 19.781 | 0
February 26 | 0 | 0 | 0 | 69.6057 | 46.0189 | 23.5868 | 20.5427 | 0 | 5.5952 | 0 | 9.5238 | 0 | 4.4048 | 0 | 5.9524 | 0 | 0 | 0 | 23.5868 | 0
March 26 | 0 | 0 | 0 | 59.8529 | 30.7353 | 29.1176 | 30.7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.1176 | 0
April 26 | 0 | 0 | 0 | 59.8529 | 30.7353 | 29.1176 | 30.7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.1176 | 0
May 26 | 0 | 0 | 0 | 57.1324 | 29.3382 | 27.7941 | 29.3382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7941 | 0
June 26 | 0 | 0 | 0 | 59.8529 | 30.7353 | 29.1176 | 30.7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.1176 | 0
July 26 | 0 | 0 | 0 | 62.5735 | 32.1324 | 30.4412 | 32.1324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.4412 | 0
August 26 | 0 | 0 | 0 | 68.101 | 41.4951 | 26.6059 | 22.8284 | 0 | 4.6667 | 0 | 9.3333 | 0 | 4.6667 | 0 | 0 | 0 | 0 | 0 | 26.6059 | 0
September 26 | 0 | 0 | 0 | 65.4667 | 46.6667 | 18.8 | 9.3333 | 0 | 9.3333 | 0 | 18.6667 | 0 | 9.3333 | 0 | 0 | 0 | 0 | 0 | 18.8 | 0

## Deleted Duplicates
Date | Account | Amount | Type | Num | Memo | Split | Source_File | Category
No duplicates found