## Summary
Task ID | Task Name | Status | Start Date | End Date | Duration | Actual Duration | Duration % | Invoice | Income Received | Income % | Planned Spend | Actual Spend | Spent Cost % | Profit % | Planned Labor Days | Actual Labor Days | Applied Labor %
200 | Design Activities | Completed | 2025-04-02 | 2025-06-25 | 60 | 61 | 102% | 96480 | 96480 | 100% | 80400 | 19735.64 | 25% | 389% | 134 | 22.75 | 17%
300 | Pre-Mobilization, Procurement and Manufacturing | Completed | 2025-06-26 | 2025-09-23 | 63 | 64 | 102% | 412231.3668 | 0 | 0% | 199649.043 | 82468.325 | 41% | -100% | 21 | 75.5 | 600.3%
400 | Drilling and Subsurface Installation | In Progress | 2025-09-29 | 2025-11-19 | 37 | 13 | 35% | 371216.5516 | 0 | 0% | 284958.9561 | 32752.54 | 11% | -100% | 316.125 | 30 | 16.67%
500 | Field Construction | Future | 2025-11-20 | 2026-02-12 | 60 |  |  | 361680.2306 | 0 | 0% | 280440.1921 | 0 |  |  | 287.6 | 0
600 | Operation | Future | 2026-02-13 | 2026-08-21 | 190 |  |  | 376851.0145 | 0 | 0% | 313382.9288 | 0 |  |  | 370 | 0
700 | Demobilization | Future | 2026-08-24 | 2026-09-25 | 24 |  |  | 78952.6325 | 0 | 0% | 64960.5271 | 0 |  |  | 98.2 | 0
TOTAL | PROJECT TOTAL |  | 2025-04-02 | 2026-09-25 | 434 | 138 | 0.31797 | 1697411.796 | 96480 | 0.056839 | 1223791.647 | 134956.505 | 0.11028 | -0.2851 | 1226.925 | 128.25 | 0.10453

## Invoice Sum
Date | Planned Income (Cumulative) | Actual Income (Daily) | Actual Income (Cumulative) | Planned Labor Sum (Cumulative) | Planned Travel&perdiem (Direct Cost) Sum (Cumulative) | Planned Parts&materials (Direct Cost) Sum (Cumulative) | Planned Outsource (Direct Cost) Sum (Cumulative) | Planned Equipment (Cumulative) | Planned 1805 · EQUIPMENT - FORKLIFT (Cumulative) | Planned 1818 · EQUIPMENT - BCU (Cumulative) | Planned 1819 · EQUIPMENT - TPMB (Cumulative) | Planned 1820 · EQUIPMENT & TOOLS (Cumulative) | Planned 1821 · EQUIPMENT - C3 (Cumulative) | Planned 1822 · EQUIPMENT - C2 (Cumulative) | Planned 1823 · EQUIPMENT - TCU BASIC (Cumulative) | Planned 1824 · EQUIPMENT - TCU PLC (Cumulative) | Planned 1825 · EQUIPMENT - BLOWER SKIDS (Cumulative) | Planned 1826 · EQUIPMENT - WELL HEADS (Cumulative) | Planned 1827 · EQUIPMENT - THERMAL WELLS (Cumulative) | Planned 1829 · EQUIPMENT - WATER TREATMENT SYS (Cumulative) | Planned 1830 · EQUIPMENT - VAPOR EXTRACTION (Cumulative) | Planned 1831 · EQUIPMENT - GTR/C3 COMPONENTS (Cumulative) | Planned 1832 · EQUIP - CONTROL/DIST PANELS (Cumulative) | Planned 1833 · EQUIPMENT - OFFICE & COMPUTER (Cumulative) | Planned 5004 · GTR COST OF SALES - PARTS (Cumulative) | Planned 5006 · DRILLING EXPENSE (Cumulative) | Planned 5101 · SALARY AND WAGES (DIRECT) (Cumulative) | Planned 5102 · PAYROLL TAXES (DIRECT) (Cumulative) | Planned 5105 · TRAVEL - AIRFARE (DIRECT) (Cumulative) | Planned 5106 · TRAVEL - HOTEL (DIRECT) (Cumulative) | Planned 5107 · TRAVEL - OTHER (DIRECT) (Cumulative) | Planned 5108 · MEALS & ENTERTAINMENT (DIRECT) (Cumulative) | Planned 5110 · TEMPORARY LABOR (DIRECT) (Cumulative) | Planned 5111 · PARTS & MATERIAL COSTS (DIRECT) (Cumulative) | Planned 5112 · CARBON & LAB SAMPLIES (DRIECT) (Cumulative) | Planned 5113 · REPAIRS & MAINT (DIRECT) (Cumulative) | Planned 5114 · RENT - BUILDING (DIRECT) (Cumulative) | Planned 5115 · RENT - EQUIPMENT (DIRECT) (Cumulative) | Planned 5116 · Rent - Storage (Direct) (Cumulative) | Planned 5120 · OUTSIDE SERVICES (DIRECT) (Cumulative) | Planned 5121 · FREIGHT & SHIPPING (DIRECT) (Cumulative) | Planned 5122 · MOTOR VEHICLE EXP (DIRECT) (Cumulative) | Planned 5123 · AUTO FUEL (DIRECT) (Cumulative) | Planned 5124 · LICENSE AND PERMITS (DIRECT) (Cumulative) | Planned 5128 · HEALTH & SAFETY EQUIP (DIRECT) (Cumulative) | Planned 5129 · MISC EXPENSES (DIRECT) (Cumulative) | Planned 5132 · INTERNET FEE (DIRECT) (Cumulative) | Planned 6999 · UNCATEGORIZED EXPENSES (Cumulative)
2025-04-02 | 1135.0588 | 0 | 0 | 1135.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1135.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 2270.1176 | 0 | 0 | 2270.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2270.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 3405.1765 | 0 | 0 | 3405.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3405.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 4540.2353 | 0 | 0 | 4540.2353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4540.2353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 5675.2941 | 0 | 0 | 5675.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5675.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 6810.3529 | 0 | 0 | 6810.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6810.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 7945.4118 | 0 | 0 | 7945.4118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7945.4118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 9080.4706 | 51408 | 51408 | 9080.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9080.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 10215.5294 | 0 | 51408 | 10215.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10215.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 11350.5882 | 0 | 51408 | 11350.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11350.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 12485.6471 | 0 | 51408 | 12485.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12485.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 13620.7059 | 0 | 51408 | 13620.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13620.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 14755.7647 | 0 | 51408 | 14755.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14755.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 15890.8235 | 0 | 51408 | 15890.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15890.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 17025.8824 | 0 | 51408 | 17025.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17025.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 18160.9412 | 0 | 51408 | 18160.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18160.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 19296 | 0 | 51408 | 19296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 20431.0588 | 0 | 51408 | 20431.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20431.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 21566.1176 | 0 | 51408 | 21566.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21566.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 22701.1765 | 0 | 51408 | 22701.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22701.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 23836.2353 | 0 | 51408 | 23836.2353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23836.2353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 24971.2941 | 0 | 51408 | 24971.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24971.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 26106.3529 | 0 | 51408 | 26106.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26106.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 27241.4118 | 0 | 51408 | 27241.4118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27241.4118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 28376.4706 | 0 | 51408 | 28376.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28376.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 29511.5294 | 0 | 51408 | 29511.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29511.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 30646.5882 | 0 | 51408 | 30646.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30646.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 31781.6471 | 0 | 51408 | 31781.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31781.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 32916.7059 | 0 | 51408 | 32916.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32916.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 34051.7647 | 0 | 51408 | 34051.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34051.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 35186.8235 | 0 | 51408 | 35186.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35186.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 36321.8824 | 0 | 51408 | 36321.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36321.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 37456.9412 | 0 | 51408 | 37456.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37456.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 38592 | 0 | 51408 | 38592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 39727.0588 | 0 | 51408 | 39727.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39727.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 40862.1176 | 0 | 51408 | 40862.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40862.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 41997.1765 | 0 | 51408 | 41997.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41997.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 43132.2353 | 0 | 51408 | 43132.2353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43132.2353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 44267.2941 | 0 | 51408 | 44267.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44267.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 45402.3529 | 0 | 51408 | 45402.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45402.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 46537.4118 | 0 | 51408 | 46537.4118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46537.4118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 47672.4706 | 0 | 51408 | 47672.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47672.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 48807.5294 | 0 | 51408 | 48807.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48807.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 49942.5882 | 0 | 51408 | 49942.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49942.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 51077.6471 | 0 | 51408 | 51077.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51077.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 52212.7059 | 0 | 51408 | 52212.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52212.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 53347.7647 | 0 | 51408 | 53347.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53347.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 54482.8235 | 0 | 51408 | 54482.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54482.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 55617.8824 | 0 | 51408 | 55617.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55617.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 56752.9412 | 0 | 51408 | 56752.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56752.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 57888 | 0 | 51408 | 57888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 59023.0588 | 0 | 51408 | 59023.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59023.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 60158.1176 | 0 | 51408 | 60158.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60158.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 61293.1765 | 0 | 51408 | 61293.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61293.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 62428.2353 | 0 | 51408 | 62428.2353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62428.2353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 63563.2941 | 0 | 51408 | 63563.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63563.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 64698.3529 | 45072 | 96480 | 64698.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64698.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 65833.4118 | 0 | 96480 | 65833.4118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65833.4118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 66968.4706 | 0 | 96480 | 66968.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66968.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 68103.5294 | 0 | 96480 | 68103.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68103.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 69238.5882 | 0 | 96480 | 69238.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69238.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 70373.6471 | 0 | 96480 | 70373.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70373.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 71508.7059 | 0 | 96480 | 71508.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71508.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 72643.7647 | 0 | 96480 | 72643.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72643.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 73778.8235 | 0 | 96480 | 73778.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73778.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 74913.8824 | 0 | 96480 | 74913.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74913.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 76048.9412 | 0 | 96480 | 76048.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76048.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 77184 | 0 | 96480 | 77184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 78319.0588 | 0 | 96480 | 78319.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78319.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 79454.1176 | 0 | 96480 | 79454.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79454.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 80589.1765 | 0 | 96480 | 80589.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80589.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 81724.2353 | 0 | 96480 | 81724.2353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81724.2353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 82859.2941 | 0 | 96480 | 82859.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82859.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 83994.3529 | 0 | 96480 | 83994.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83994.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 85129.4118 | 0 | 96480 | 85129.4118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85129.4118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 86264.4706 | 0 | 96480 | 86264.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86264.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 87399.5294 | 0 | 96480 | 87399.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87399.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 88534.5882 | 0 | 96480 | 88534.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88534.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 89669.6471 | 0 | 96480 | 89669.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89669.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 90804.7059 | 0 | 96480 | 90804.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90804.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 91939.7647 | 0 | 96480 | 91939.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91939.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 93074.8235 | 0 | 96480 | 93074.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93074.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 94209.8824 | 0 | 96480 | 94209.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94209.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 95344.9412 | 0 | 96480 | 95344.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95344.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 96480 | 0 | 96480 | 96480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-26 | 101060.3485 | 0 | 96480 | 96704.7455 | 160.5084 | 1446.0868 | 420 | 2329.0078 | 0 | 0 | 62.92 | 0 | 0 | 1851.7778 | 104 | 0 | 0 | 48.5333 | 0 | 0 | 110.11 | 151.6667 | 0 | 0 | 0 | 0 | 96704.7455 | 0 | 62.1751 | 65 | 3.3333 | 8.3333 | 0 | 1446.0868 | 0 | 0 | 1.1111 | 28.8889 | 72.2222 | 144.4444 | 144.4444 | 21.6667 | 0 | 0 | 0 | 0 | 28.8889 | 0
2025-06-27 | 105640.697 | 0 | 96480 | 96929.491 | 321.0169 | 2892.1736 | 840 | 4658.0156 | 0 | 0 | 125.84 | 0 | 0 | 3703.5556 | 208 | 0 | 0 | 97.0667 | 0 | 0 | 220.22 | 303.3333 | 0 | 0 | 0 | 0 | 96929.491 | 0 | 124.3502 | 130 | 6.6667 | 16.6667 | 0 | 2892.1736 | 0 | 0 | 2.2222 | 57.7778 | 144.4444 | 288.8889 | 288.8889 | 43.3333 | 0 | 0 | 0 | 0 | 57.7778 | 0
2025-06-28 | 110221.0456 | 0 | 96480 | 97154.2366 | 481.5253 | 4338.2603 | 1260 | 6987.0233 | 0 | 0 | 188.76 | 0 | 0 | 5555.3333 | 312 | 0 | 0 | 145.6 | 0 | 0 | 330.33 | 455 | 0 | 0 | 0 | 0 | 97154.2366 | 0 | 186.5253 | 195 | 10 | 25 | 0 | 4338.2603 | 0 | 0 | 3.3333 | 86.6667 | 216.6667 | 433.3333 | 433.3333 | 65 | 0 | 0 | 0 | 0 | 86.6667 | 0
2025-06-29 | 114801.3941 | 0 | 96480 | 97378.9821 | 642.0338 | 5784.3471 | 1680 | 9316.0311 | 0 | 0 | 251.68 | 0 | 0 | 7407.1111 | 416 | 0 | 0 | 194.1333 | 0 | 0 | 440.44 | 606.6667 | 0 | 0 | 0 | 0 | 97378.9821 | 0 | 248.7004 | 260 | 13.3333 | 33.3333 | 0 | 5784.3471 | 0 | 0 | 4.4444 | 115.5556 | 288.8889 | 577.7778 | 577.7778 | 86.6667 | 0 | 0 | 0 | 0 | 115.5556 | 0
2025-06-30 | 119381.7426 | 0 | 96480 | 97603.7276 | 802.5422 | 7230.4339 | 2100 | 11645.0389 | 0 | 0 | 314.6 | 0 | 0 | 9258.8889 | 520 | 0 | 0 | 242.6667 | 0 | 0 | 550.55 | 758.3333 | 0 | 0 | 0 | 0 | 97603.7276 | 0 | 310.8756 | 325 | 16.6667 | 41.6667 | 0 | 7230.4339 | 0 | 0 | 5.5556 | 144.4444 | 361.1111 | 722.2222 | 722.2222 | 108.3333 | 0 | 0 | 0 | 0 | 144.4444 | 0
2025-07-01 | 123962.0911 | 0 | 96480 | 97828.4731 | 963.0507 | 8676.5207 | 2520 | 13974.0467 | 0 | 0 | 377.52 | 0 | 0 | 11110.6667 | 624 | 0 | 0 | 291.2 | 0 | 0 | 660.66 | 910 | 0 | 0 | 0 | 0 | 97828.4731 | 0 | 373.0507 | 390 | 20 | 50 | 0 | 8676.5207 | 0 | 0 | 6.6667 | 173.3333 | 433.3333 | 866.6667 | 866.6667 | 130 | 0 | 0 | 0 | 0 | 173.3333 | 0
2025-07-02 | 128542.4396 | 0 | 96480 | 98053.2186 | 1123.5591 | 10122.6074 | 2940 | 16303.0544 | 0 | 0 | 440.44 | 0 | 0 | 12962.4444 | 728 | 0 | 0 | 339.7333 | 0 | 0 | 770.77 | 1061.6667 | 0 | 0 | 0 | 0 | 98053.2186 | 0 | 435.2258 | 455 | 23.3333 | 58.3333 | 0 | 10122.6074 | 0 | 0 | 7.7778 | 202.2222 | 505.5556 | 1011.1111 | 1011.1111 | 151.6667 | 0 | 0 | 0 | 0 | 202.2222 | 0
2025-07-03 | 133122.7882 | 0 | 96480 | 98277.9642 | 1284.0676 | 11568.6942 | 3360 | 18632.0622 | 0 | 0 | 503.36 | 0 | 0 | 14814.2222 | 832 | 0 | 0 | 388.2667 | 0 | 0 | 880.88 | 1213.3333 | 0 | 0 | 0 | 0 | 98277.9642 | 0 | 497.4009 | 520 | 26.6667 | 66.6667 | 0 | 11568.6942 | 0 | 0 | 8.8889 | 231.1111 | 577.7778 | 1155.5556 | 1155.5556 | 173.3333 | 0 | 0 | 0 | 0 | 231.1111 | 0
2025-07-04 | 137703.1367 | 0 | 96480 | 98502.7097 | 1444.576 | 13014.781 | 3780 | 20961.07 | 0 | 0 | 566.28 | 0 | 0 | 16666 | 936 | 0 | 0 | 436.8 | 0 | 0 | 990.99 | 1365 | 0 | 0 | 0 | 0 | 98502.7097 | 0 | 559.576 | 585 | 30 | 75 | 0 | 13014.781 | 0 | 0 | 10 | 260 | 650 | 1300 | 1300 | 195 | 0 | 0 | 0 | 0 | 260 | 0
2025-07-05 | 142283.4852 | 0 | 96480 | 98727.4552 | 1605.0844 | 14460.8678 | 4200 | 23290.0778 | 0 | 0 | 629.2 | 0 | 0 | 18517.7778 | 1040 | 0 | 0 | 485.3333 | 0 | 0 | 1101.1 | 1516.6667 | 0 | 0 | 0 | 0 | 98727.4552 | 0 | 621.7511 | 650 | 33.3333 | 83.3333 | 0 | 14460.8678 | 0 | 0 | 11.1111 | 288.8889 | 722.2222 | 1444.4444 | 1444.4444 | 216.6667 | 0 | 0 | 0 | 0 | 288.8889 | 0
2025-07-06 | 146863.8337 | 0 | 96480 | 98952.2007 | 1765.5929 | 15906.9546 | 4620 | 25619.0856 | 0 | 0 | 692.12 | 0 | 0 | 20369.5556 | 1144 | 0 | 0 | 533.8667 | 0 | 0 | 1211.21 | 1668.3333 | 0 | 0 | 0 | 0 | 98952.2007 | 0 | 683.9262 | 715 | 36.6667 | 91.6667 | 0 | 15906.9546 | 0 | 0 | 12.2222 | 317.7778 | 794.4444 | 1588.8889 | 1588.8889 | 238.3333 | 0 | 0 | 0 | 0 | 317.7778 | 0
2025-07-07 | 151444.1822 | 0 | 96480 | 99176.9462 | 1926.1013 | 17353.0413 | 5040 | 27948.0933 | 0 | 0 | 755.04 | 0 | 0 | 22221.3333 | 1248 | 0 | 0 | 582.4 | 0 | 0 | 1321.32 | 1820 | 0 | 0 | 0 | 0 | 99176.9462 | 0 | 746.1013 | 780 | 40 | 100 | 0 | 17353.0413 | 0 | 0 | 13.3333 | 346.6667 | 866.6667 | 1733.3333 | 1733.3333 | 260 | 0 | 0 | 0 | 0 | 346.6667 | 0
2025-07-08 | 156024.5308 | 0 | 96480 | 99401.6918 | 2086.6098 | 18799.1281 | 5460 | 30277.1011 | 0 | 0 | 817.96 | 0 | 0 | 24073.1111 | 1352 | 0 | 0 | 630.9333 | 0 | 0 | 1431.43 | 1971.6667 | 0 | 0 | 0 | 0 | 99401.6918 | 0 | 808.2764 | 845 | 43.3333 | 108.3333 | 0 | 18799.1281 | 0 | 0 | 14.4444 | 375.5556 | 938.8889 | 1877.7778 | 1877.7778 | 281.6667 | 0 | 0 | 0 | 0 | 375.5556 | 0
2025-07-09 | 160604.8793 | 0 | 96480 | 99626.4373 | 2247.1182 | 20245.2149 | 5880 | 32606.1089 | 0 | 0 | 880.88 | 0 | 0 | 25924.8889 | 1456 | 0 | 0 | 679.4667 | 0 | 0 | 1541.54 | 2123.3333 | 0 | 0 | 0 | 0 | 99626.4373 | 0 | 870.4516 | 910 | 46.6667 | 116.6667 | 0 | 20245.2149 | 0 | 0 | 15.5556 | 404.4444 | 1011.1111 | 2022.2222 | 2022.2222 | 303.3333 | 0 | 0 | 0 | 0 | 404.4444 | 0
2025-07-10 | 165185.2278 | 0 | 96480 | 99851.1828 | 2407.6267 | 21691.3017 | 6300 | 34935.1167 | 0 | 0 | 943.8 | 0 | 0 | 27776.6667 | 1560 | 0 | 0 | 728 | 0 | 0 | 1651.65 | 2275 | 0 | 0 | 0 | 0 | 99851.1828 | 0 | 932.6267 | 975 | 50 | 125 | 0 | 21691.3017 | 0 | 0 | 16.6667 | 433.3333 | 1083.3333 | 2166.6667 | 2166.6667 | 325 | 0 | 0 | 0 | 0 | 433.3333 | 0
2025-07-11 | 169765.5763 | 0 | 96480 | 100075.9283 | 2568.1351 | 23137.3884 | 6720 | 37264.1244 | 0 | 0 | 1006.72 | 0 | 0 | 29628.4444 | 1664 | 0 | 0 | 776.5333 | 0 | 0 | 1761.76 | 2426.6667 | 0 | 0 | 0 | 0 | 100075.9283 | 0 | 994.8018 | 1040 | 53.3333 | 133.3333 | 0 | 23137.3884 | 0 | 0 | 17.7778 | 462.2222 | 1155.5556 | 2311.1111 | 2311.1111 | 346.6667 | 0 | 0 | 0 | 0 | 462.2222 | 0
2025-07-12 | 174345.9248 | 0 | 96480 | 100300.6738 | 2728.6436 | 24583.4752 | 7140 | 39593.1322 | 0 | 0 | 1069.64 | 0 | 0 | 31480.2222 | 1768 | 0 | 0 | 825.0667 | 0 | 0 | 1871.87 | 2578.3333 | 0 | 0 | 0 | 0 | 100300.6738 | 0 | 1056.9769 | 1105 | 56.6667 | 141.6667 | 0 | 24583.4752 | 0 | 0 | 18.8889 | 491.1111 | 1227.7778 | 2455.5556 | 2455.5556 | 368.3333 | 0 | 0 | 0 | 0 | 491.1111 | 0
2025-07-13 | 178926.2734 | 0 | 96480 | 100525.4194 | 2889.152 | 26029.562 | 7560 | 41922.14 | 0 | 0 | 1132.56 | 0 | 0 | 33332 | 1872 | 0 | 0 | 873.6 | 0 | 0 | 1981.98 | 2730 | 0 | 0 | 0 | 0 | 100525.4194 | 0 | 1119.152 | 1170 | 60 | 150 | 0 | 26029.562 | 0 | 0 | 20 | 520 | 1300 | 2600 | 2600 | 390 | 0 | 0 | 0 | 0 | 520 | 0
2025-07-14 | 183506.6219 | 0 | 96480 | 100750.1649 | 3049.6604 | 27475.6488 | 7980 | 44251.1478 | 0 | 0 | 1195.48 | 0 | 0 | 35183.7778 | 1976 | 0 | 0 | 922.1333 | 0 | 0 | 2092.09 | 2881.6667 | 0 | 0 | 0 | 0 | 100750.1649 | 0 | 1181.3271 | 1235 | 63.3333 | 158.3333 | 0 | 27475.6488 | 0 | 0 | 21.1111 | 548.8889 | 1372.2222 | 2744.4444 | 2744.4444 | 411.6667 | 0 | 0 | 0 | 0 | 548.8889 | 0
2025-07-15 | 188086.9704 | 0 | 96480 | 100974.9104 | 3210.1689 | 28921.7356 | 8400 | 46580.1556 | 0 | 0 | 1258.4 | 0 | 0 | 37035.5556 | 2080 | 0 | 0 | 970.6667 | 0 | 0 | 2202.2 | 3033.3333 | 0 | 0 | 0 | 0 | 100974.9104 | 0 | 1243.5022 | 1300 | 66.6667 | 166.6667 | 0 | 28921.7356 | 0 | 0 | 22.2222 | 577.7778 | 1444.4444 | 2888.8889 | 2888.8889 | 433.3333 | 0 | 0 | 0 | 0 | 577.7778 | 0
2025-07-16 | 192667.3189 | 0 | 96480 | 101199.6559 | 3370.6773 | 30367.8223 | 8820 | 48909.1633 | 0 | 0 | 1321.32 | 0 | 0 | 38887.3333 | 2184 | 0 | 0 | 1019.2 | 0 | 0 | 2312.31 | 3185 | 0 | 0 | 0 | 0 | 101199.6559 | 0 | 1305.6773 | 1365 | 70 | 175 | 0 | 30367.8223 | 0 | 0 | 23.3333 | 606.6667 | 1516.6667 | 3033.3333 | 3033.3333 | 455 | 0 | 0 | 0 | 0 | 606.6667 | 0
2025-07-17 | 197247.6674 | 0 | 96480 | 101424.4014 | 3531.1858 | 31813.9091 | 9240 | 51238.1711 | 0 | 0 | 1384.24 | 0 | 0 | 40739.1111 | 2288 | 0 | 0 | 1067.7333 | 0 | 0 | 2422.42 | 3336.6667 | 0 | 0 | 0 | 0 | 101424.4014 | 0 | 1367.8524 | 1430 | 73.3333 | 183.3333 | 0 | 31813.9091 | 0 | 0 | 24.4444 | 635.5556 | 1588.8889 | 3177.7778 | 3177.7778 | 476.6667 | 0 | 0 | 0 | 0 | 635.5556 | 0
2025-07-18 | 201828.016 | 0 | 96480 | 101649.147 | 3691.6942 | 33259.9959 | 9660 | 53567.1789 | 0 | 0 | 1447.16 | 0 | 0 | 42590.8889 | 2392 | 0 | 0 | 1116.2667 | 0 | 0 | 2532.53 | 3488.3333 | 0 | 0 | 0 | 0 | 101649.147 | 0 | 1430.0276 | 1495 | 76.6667 | 191.6667 | 0 | 33259.9959 | 0 | 0 | 25.5556 | 664.4444 | 1661.1111 | 3322.2222 | 3322.2222 | 498.3333 | 0 | 0 | 0 | 0 | 664.4444 | 0
2025-07-19 | 206408.3645 | 0 | 96480 | 101873.8925 | 3852.2027 | 34706.0827 | 10080 | 55896.1867 | 0 | 0 | 1510.08 | 0 | 0 | 44442.6667 | 2496 | 0 | 0 | 1164.8 | 0 | 0 | 2642.64 | 3640 | 0 | 0 | 0 | 0 | 101873.8925 | 0 | 1492.2027 | 1560 | 80 | 200 | 0 | 34706.0827 | 0 | 0 | 26.6667 | 693.3333 | 1733.3333 | 3466.6667 | 3466.6667 | 520 | 0 | 0 | 0 | 0 | 693.3333 | 0
2025-07-20 | 210988.713 | 0 | 96480 | 102098.638 | 4012.7111 | 36152.1694 | 10500 | 58225.1944 | 0 | 0 | 1573 | 0 | 0 | 46294.4444 | 2600 | 0 | 0 | 1213.3333 | 0 | 0 | 2752.75 | 3791.6667 | 0 | 0 | 0 | 0 | 102098.638 | 0 | 1554.3778 | 1625 | 83.3333 | 208.3333 | 0 | 36152.1694 | 0 | 0 | 27.7778 | 722.2222 | 1805.5556 | 3611.1111 | 3611.1111 | 541.6667 | 0 | 0 | 0 | 0 | 722.2222 | 0
2025-07-21 | 215569.0615 | 0 | 96480 | 102323.3835 | 4173.2196 | 37598.2562 | 10920 | 60554.2022 | 0 | 0 | 1635.92 | 0 | 0 | 48146.2222 | 2704 | 0 | 0 | 1261.8667 | 0 | 0 | 2862.86 | 3943.3333 | 0 | 0 | 0 | 0 | 102323.3835 | 0 | 1616.5529 | 1690 | 86.6667 | 216.6667 | 0 | 37598.2562 | 0 | 0 | 28.8889 | 751.1111 | 1877.7778 | 3755.5556 | 3755.5556 | 563.3333 | 0 | 0 | 0 | 0 | 751.1111 | 0
2025-07-22 | 220149.41 | 0 | 96480 | 102548.129 | 4333.728 | 39044.343 | 11340 | 62883.21 | 0 | 0 | 1698.84 | 0 | 0 | 49998 | 2808 | 0 | 0 | 1310.4 | 0 | 0 | 2972.97 | 4095 | 0 | 0 | 0 | 0 | 102548.129 | 0 | 1678.728 | 1755 | 90 | 225 | 0 | 39044.343 | 0 | 0 | 30 | 780 | 1950 | 3900 | 3900 | 585 | 0 | 0 | 0 | 0 | 780 | 0
2025-07-23 | 224729.7586 | 0 | 96480 | 102772.8746 | 4494.2364 | 40490.4298 | 11760 | 65212.2178 | 0 | 0 | 1761.76 | 0 | 0 | 51849.7778 | 2912 | 0 | 0 | 1358.9333 | 0 | 0 | 3083.08 | 4246.6667 | 0 | 0 | 0 | 0 | 102772.8746 | 0 | 1740.9031 | 1820 | 93.3333 | 233.3333 | 0 | 40490.4298 | 0 | 0 | 31.1111 | 808.8889 | 2022.2222 | 4044.4444 | 4044.4444 | 606.6667 | 0 | 0 | 0 | 0 | 808.8889 | 0
2025-07-24 | 229310.1071 | 0 | 96480 | 102997.6201 | 4654.7449 | 41936.5166 | 12180 | 67541.2256 | 0 | 0 | 1824.68 | 0 | 0 | 53701.5556 | 3016 | 0 | 0 | 1407.4667 | 0 | 0 | 3193.19 | 4398.3333 | 0 | 0 | 0 | 0 | 102997.6201 | 0 | 1803.0782 | 1885 | 96.6667 | 241.6667 | 0 | 41936.5166 | 0 | 0 | 32.2222 | 837.7778 | 2094.4444 | 4188.8889 | 4188.8889 | 628.3333 | 0 | 0 | 0 | 0 | 837.7778 | 0
2025-07-25 | 233890.4556 | 0 | 96480 | 103222.3656 | 4815.2533 | 43382.6033 | 12600 | 69870.2333 | 0 | 0 | 1887.6 | 0 | 0 | 55553.3333 | 3120 | 0 | 0 | 1456 | 0 | 0 | 3303.3 | 4550 | 0 | 0 | 0 | 0 | 103222.3656 | 0 | 1865.2533 | 1950 | 100 | 250 | 0 | 43382.6033 | 0 | 0 | 33.3333 | 866.6667 | 2166.6667 | 4333.3333 | 4333.3333 | 650 | 0 | 0 | 0 | 0 | 866.6667 | 0
2025-07-26 | 238470.8041 | 0 | 96480 | 103447.1111 | 4975.7618 | 44828.6901 | 13020 | 72199.2411 | 0 | 0 | 1950.52 | 0 | 0 | 57405.1111 | 3224 | 0 | 0 | 1504.5333 | 0 | 0 | 3413.41 | 4701.6667 | 0 | 0 | 0 | 0 | 103447.1111 | 0 | 1927.4284 | 2015 | 103.3333 | 258.3333 | 0 | 44828.6901 | 0 | 0 | 34.4444 | 895.5556 | 2238.8889 | 4477.7778 | 4477.7778 | 671.6667 | 0 | 0 | 0 | 0 | 895.5556 | 0
2025-07-27 | 243051.1526 | 0 | 96480 | 103671.8566 | 5136.2702 | 46274.7769 | 13440 | 74528.2489 | 0 | 0 | 2013.44 | 0 | 0 | 59256.8889 | 3328 | 0 | 0 | 1553.0667 | 0 | 0 | 3523.52 | 4853.3333 | 0 | 0 | 0 | 0 | 103671.8566 | 0 | 1989.6036 | 2080 | 106.6667 | 266.6667 | 0 | 46274.7769 | 0 | 0 | 35.5556 | 924.4444 | 2311.1111 | 4622.2222 | 4622.2222 | 693.3333 | 0 | 0 | 0 | 0 | 924.4444 | 0
2025-07-28 | 247631.5012 | 0 | 96480 | 103896.6022 | 5296.7787 | 47720.8637 | 13860 | 76857.2567 | 0 | 0 | 2076.36 | 0 | 0 | 61108.6667 | 3432 | 0 | 0 | 1601.6 | 0 | 0 | 3633.63 | 5005 | 0 | 0 | 0 | 0 | 103896.6022 | 0 | 2051.7787 | 2145 | 110 | 275 | 0 | 47720.8637 | 0 | 0 | 36.6667 | 953.3333 | 2383.3333 | 4766.6667 | 4766.6667 | 715 | 0 | 0 | 0 | 0 | 953.3333 | 0
2025-07-29 | 252211.8497 | 0 | 96480 | 104121.3477 | 5457.2871 | 49166.9504 | 14280 | 79186.2644 | 0 | 0 | 2139.28 | 0 | 0 | 62960.4444 | 3536 | 0 | 0 | 1650.1333 | 0 | 0 | 3743.74 | 5156.6667 | 0 | 0 | 0 | 0 | 104121.3477 | 0 | 2113.9538 | 2210 | 113.3333 | 283.3333 | 0 | 49166.9504 | 0 | 0 | 37.7778 | 982.2222 | 2455.5556 | 4911.1111 | 4911.1111 | 736.6667 | 0 | 0 | 0 | 0 | 982.2222 | 0
2025-07-30 | 256792.1982 | 0 | 96480 | 104346.0932 | 5617.7956 | 50613.0372 | 14700 | 81515.2722 | 0 | 0 | 2202.2 | 0 | 0 | 64812.2222 | 3640 | 0 | 0 | 1698.6667 | 0 | 0 | 3853.85 | 5308.3333 | 0 | 0 | 0 | 0 | 104346.0932 | 0 | 2176.1289 | 2275 | 116.6667 | 291.6667 | 0 | 50613.0372 | 0 | 0 | 38.8889 | 1011.1111 | 2527.7778 | 5055.5556 | 5055.5556 | 758.3333 | 0 | 0 | 0 | 0 | 1011.1111 | 0
2025-07-31 | 261372.5467 | 0 | 96480 | 104570.8387 | 5778.304 | 52059.124 | 15120 | 83844.28 | 0 | 0 | 2265.12 | 0 | 0 | 66664 | 3744 | 0 | 0 | 1747.2 | 0 | 0 | 3963.96 | 5460 | 0 | 0 | 0 | 0 | 104570.8387 | 0 | 2238.304 | 2340 | 120 | 300 | 0 | 52059.124 | 0 | 0 | 40 | 1040 | 2600 | 5200 | 5200 | 780 | 0 | 0 | 0 | 0 | 1040 | 0
2025-08-01 | 265952.8952 | 0 | 96480 | 104795.5842 | 5938.8124 | 53505.2108 | 15540 | 86173.2878 | 0 | 0 | 2328.04 | 0 | 0 | 68515.7778 | 3848 | 0 | 0 | 1795.7333 | 0 | 0 | 4074.07 | 5611.6667 | 0 | 0 | 0 | 0 | 104795.5842 | 0 | 2300.4791 | 2405 | 123.3333 | 308.3333 | 0 | 53505.2108 | 0 | 0 | 41.1111 | 1068.8889 | 2672.2222 | 5344.4444 | 5344.4444 | 801.6667 | 0 | 0 | 0 | 0 | 1068.8889 | 0
2025-08-02 | 270533.2437 | 0 | 96480 | 105020.3297 | 6099.3209 | 54951.2976 | 15960 | 88502.2956 | 0 | 0 | 2390.96 | 0 | 0 | 70367.5556 | 3952 | 0 | 0 | 1844.2667 | 0 | 0 | 4184.18 | 5763.3333 | 0 | 0 | 0 | 0 | 105020.3297 | 0 | 2362.6542 | 2470 | 126.6667 | 316.6667 | 0 | 54951.2976 | 0 | 0 | 42.2222 | 1097.7778 | 2744.4444 | 5488.8889 | 5488.8889 | 823.3333 | 0 | 0 | 0 | 0 | 1097.7778 | 0
2025-08-03 | 275113.5923 | 0 | 96480 | 105245.0753 | 6259.8293 | 56397.3843 | 16380 | 90831.3033 | 0 | 0 | 2453.88 | 0 | 0 | 72219.3333 | 4056 | 0 | 0 | 1892.8 | 0 | 0 | 4294.29 | 5915 | 0 | 0 | 0 | 0 | 105245.0753 | 0 | 2424.8293 | 2535 | 130 | 325 | 0 | 56397.3843 | 0 | 0 | 43.3333 | 1126.6667 | 2816.6667 | 5633.3333 | 5633.3333 | 845 | 0 | 0 | 0 | 0 | 1126.6667 | 0
2025-08-04 | 279693.9408 | 0 | 96480 | 105469.8208 | 6420.3378 | 57843.4711 | 16800 | 93160.3111 | 0 | 0 | 2516.8 | 0 | 0 | 74071.1111 | 4160 | 0 | 0 | 1941.3333 | 0 | 0 | 4404.4 | 6066.6667 | 0 | 0 | 0 | 0 | 105469.8208 | 0 | 2487.0044 | 2600 | 133.3333 | 333.3333 | 0 | 57843.4711 | 0 | 0 | 44.4444 | 1155.5556 | 2888.8889 | 5777.7778 | 5777.7778 | 866.6667 | 0 | 0 | 0 | 0 | 1155.5556 | 0
2025-08-05 | 284274.2893 | 0 | 96480 | 105694.5663 | 6580.8462 | 59289.5579 | 17220 | 95489.3189 | 0 | 0 | 2579.72 | 0 | 0 | 75922.8889 | 4264 | 0 | 0 | 1989.8667 | 0 | 0 | 4514.51 | 6218.3333 | 0 | 0 | 0 | 0 | 105694.5663 | 0 | 2549.1796 | 2665 | 136.6667 | 341.6667 | 0 | 59289.5579 | 0 | 0 | 45.5556 | 1184.4444 | 2961.1111 | 5922.2222 | 5922.2222 | 888.3333 | 0 | 0 | 0 | 0 | 1184.4444 | 0
2025-08-06 | 288854.6378 | 0 | 96480 | 105919.3118 | 6741.3547 | 60735.6447 | 17640 | 97818.3267 | 0 | 0 | 2642.64 | 0 | 0 | 77774.6667 | 4368 | 0 | 0 | 2038.4 | 0 | 0 | 4624.62 | 6370 | 0 | 0 | 0 | 0 | 105919.3118 | 0 | 2611.3547 | 2730 | 140 | 350 | 0 | 60735.6447 | 0 | 0 | 46.6667 | 1213.3333 | 3033.3333 | 6066.6667 | 6066.6667 | 910 | 0 | 0 | 0 | 0 | 1213.3333 | 0
2025-08-07 | 293434.9863 | 0 | 96480 | 106144.0573 | 6901.8631 | 62181.7314 | 18060 | 100147.3344 | 0 | 0 | 2705.56 | 0 | 0 | 79626.4444 | 4472 | 0 | 0 | 2086.9333 | 0 | 0 | 4734.73 | 6521.6667 | 0 | 0 | 0 | 0 | 106144.0573 | 0 | 2673.5298 | 2795 | 143.3333 | 358.3333 | 0 | 62181.7314 | 0 | 0 | 47.7778 | 1242.2222 | 3105.5556 | 6211.1111 | 6211.1111 | 931.6667 | 0 | 0 | 0 | 0 | 1242.2222 | 0
2025-08-08 | 298015.3349 | 0 | 96480 | 106368.8029 | 7062.3716 | 63627.8182 | 18480 | 102476.3422 | 0 | 0 | 2768.48 | 0 | 0 | 81478.2222 | 4576 | 0 | 0 | 2135.4667 | 0 | 0 | 4844.84 | 6673.3333 | 0 | 0 | 0 | 0 | 106368.8029 | 0 | 2735.7049 | 2860 | 146.6667 | 366.6667 | 0 | 63627.8182 | 0 | 0 | 48.8889 | 1271.1111 | 3177.7778 | 6355.5556 | 6355.5556 | 953.3333 | 0 | 0 | 0 | 0 | 1271.1111 | 0
2025-08-09 | 302595.6834 | 0 | 96480 | 106593.5484 | 7222.88 | 65073.905 | 18900 | 104805.35 | 0 | 0 | 2831.4 | 0 | 0 | 83330 | 4680 | 0 | 0 | 2184 | 0 | 0 | 4954.95 | 6825 | 0 | 0 | 0 | 0 | 106593.5484 | 0 | 2797.88 | 2925 | 150 | 375 | 0 | 65073.905 | 0 | 0 | 50 | 1300 | 3250 | 6500 | 6500 | 975 | 0 | 0 | 0 | 0 | 1300 | 0
2025-08-10 | 307176.0319 | 0 | 96480 | 106818.2939 | 7383.3884 | 66519.9918 | 19320 | 107134.3578 | 0 | 0 | 2894.32 | 0 | 0 | 85181.7778 | 4784 | 0 | 0 | 2232.5333 | 0 | 0 | 5065.06 | 6976.6667 | 0 | 0 | 0 | 0 | 106818.2939 | 0 | 2860.0551 | 2990 | 153.3333 | 383.3333 | 0 | 66519.9918 | 0 | 0 | 51.1111 | 1328.8889 | 3322.2222 | 6644.4444 | 6644.4444 | 996.6667 | 0 | 0 | 0 | 0 | 1328.8889 | 0
2025-08-11 | 311756.3804 | 0 | 96480 | 107043.0394 | 7543.8969 | 67966.0786 | 19740 | 109463.3656 | 0 | 0 | 2957.24 | 0 | 0 | 87033.5556 | 4888 | 0 | 0 | 2281.0667 | 0 | 0 | 5175.17 | 7128.3333 | 0 | 0 | 0 | 0 | 107043.0394 | 0 | 2922.2302 | 3055 | 156.6667 | 391.6667 | 0 | 67966.0786 | 0 | 0 | 52.2222 | 1357.7778 | 3394.4444 | 6788.8889 | 6788.8889 | 1018.3333 | 0 | 0 | 0 | 0 | 1357.7778 | 0
2025-08-12 | 316336.7289 | 0 | 96480 | 107267.7849 | 7704.4053 | 69412.1653 | 20160 | 111792.3733 | 0 | 0 | 3020.16 | 0 | 0 | 88885.3333 | 4992 | 0 | 0 | 2329.6 | 0 | 0 | 5285.28 | 7280 | 0 | 0 | 0 | 0 | 107267.7849 | 0 | 2984.4053 | 3120 | 160 | 400 | 0 | 69412.1653 | 0 | 0 | 53.3333 | 1386.6667 | 3466.6667 | 6933.3333 | 6933.3333 | 1040 | 0 | 0 | 0 | 0 | 1386.6667 | 0
2025-08-13 | 320917.0775 | 0 | 96480 | 107492.5305 | 7864.9138 | 70858.2521 | 20580 | 114121.3811 | 0 | 0 | 3083.08 | 0 | 0 | 90737.1111 | 5096 | 0 | 0 | 2378.1333 | 0 | 0 | 5395.39 | 7431.6667 | 0 | 0 | 0 | 0 | 107492.5305 | 0 | 3046.5804 | 3185 | 163.3333 | 408.3333 | 0 | 70858.2521 | 0 | 0 | 54.4444 | 1415.5556 | 3538.8889 | 7077.7778 | 7077.7778 | 1061.6667 | 0 | 0 | 0 | 0 | 1415.5556 | 0
2025-08-14 | 325497.426 | 0 | 96480 | 107717.276 | 8025.4222 | 72304.3389 | 21000 | 116450.3889 | 0 | 0 | 3146 | 0 | 0 | 92588.8889 | 5200 | 0 | 0 | 2426.6667 | 0 | 0 | 5505.5 | 7583.3333 | 0 | 0 | 0 | 0 | 107717.276 | 0 | 3108.7556 | 3250 | 166.6667 | 416.6667 | 0 | 72304.3389 | 0 | 0 | 55.5556 | 1444.4444 | 3611.1111 | 7222.2222 | 7222.2222 | 1083.3333 | 0 | 0 | 0 | 0 | 1444.4444 | 0
2025-08-15 | 330077.7745 | 0 | 96480 | 107942.0215 | 8185.9307 | 73750.4257 | 21420 | 118779.3967 | 0 | 0 | 3208.92 | 0 | 0 | 94440.6667 | 5304 | 0 | 0 | 2475.2 | 0 | 0 | 5615.61 | 7735 | 0 | 0 | 0 | 0 | 107942.0215 | 0 | 3170.9307 | 3315 | 170 | 425 | 0 | 73750.4257 | 0 | 0 | 56.6667 | 1473.3333 | 3683.3333 | 7366.6667 | 7366.6667 | 1105 | 0 | 0 | 0 | 0 | 1473.3333 | 0
2025-08-16 | 334658.123 | 0 | 96480 | 108166.767 | 8346.4391 | 75196.5124 | 21840 | 121108.4044 | 0 | 0 | 3271.84 | 0 | 0 | 96292.4444 | 5408 | 0 | 0 | 2523.7333 | 0 | 0 | 5725.72 | 7886.6667 | 0 | 0 | 0 | 0 | 108166.767 | 0 | 3233.1058 | 3380 | 173.3333 | 433.3333 | 0 | 75196.5124 | 0 | 0 | 57.7778 | 1502.2222 | 3755.5556 | 7511.1111 | 7511.1111 | 1126.6667 | 0 | 0 | 0 | 0 | 1502.2222 | 0
2025-08-17 | 339238.4715 | 0 | 96480 | 108391.5125 | 8506.9476 | 76642.5992 | 22260 | 123437.4122 | 0 | 0 | 3334.76 | 0 | 0 | 98144.2222 | 5512 | 0 | 0 | 2572.2667 | 0 | 0 | 5835.83 | 8038.3333 | 0 | 0 | 0 | 0 | 108391.5125 | 0 | 3295.2809 | 3445 | 176.6667 | 441.6667 | 0 | 76642.5992 | 0 | 0 | 58.8889 | 1531.1111 | 3827.7778 | 7655.5556 | 7655.5556 | 1148.3333 | 0 | 0 | 0 | 0 | 1531.1111 | 0
2025-08-18 | 343818.8201 | 0 | 96480 | 108616.2581 | 8667.456 | 78088.686 | 22680 | 125766.42 | 0 | 0 | 3397.68 | 0 | 0 | 99996 | 5616 | 0 | 0 | 2620.8 | 0 | 0 | 5945.94 | 8190 | 0 | 0 | 0 | 0 | 108616.2581 | 0 | 3357.456 | 3510 | 180 | 450 | 0 | 78088.686 | 0 | 0 | 60 | 1560 | 3900 | 7800 | 7800 | 1170 | 0 | 0 | 0 | 0 | 1560 | 0
2025-08-19 | 348399.1686 | 0 | 96480 | 108841.0036 | 8827.9644 | 79534.7728 | 23100 | 128095.4278 | 0 | 0 | 3460.6 | 0 | 0 | 101847.7778 | 5720 | 0 | 0 | 2669.3333 | 0 | 0 | 6056.05 | 8341.6667 | 0 | 0 | 0 | 0 | 108841.0036 | 0 | 3419.6311 | 3575 | 183.3333 | 458.3333 | 0 | 79534.7728 | 0 | 0 | 61.1111 | 1588.8889 | 3972.2222 | 7944.4444 | 7944.4444 | 1191.6667 | 0 | 0 | 0 | 0 | 1588.8889 | 0
2025-08-20 | 352979.5171 | 0 | 96480 | 109065.7491 | 8988.4729 | 80980.8596 | 23520 | 130424.4356 | 0 | 0 | 3523.52 | 0 | 0 | 103699.5556 | 5824 | 0 | 0 | 2717.8667 | 0 | 0 | 6166.16 | 8493.3333 | 0 | 0 | 0 | 0 | 109065.7491 | 0 | 3481.8062 | 3640 | 186.6667 | 466.6667 | 0 | 80980.8596 | 0 | 0 | 62.2222 | 1617.7778 | 4044.4444 | 8088.8889 | 8088.8889 | 1213.3333 | 0 | 0 | 0 | 0 | 1617.7778 | 0
2025-08-21 | 357559.8656 | 0 | 96480 | 109290.4946 | 9148.9813 | 82426.9463 | 23940 | 132753.4433 | 0 | 0 | 3586.44 | 0 | 0 | 105551.3333 | 5928 | 0 | 0 | 2766.4 | 0 | 0 | 6276.27 | 8645 | 0 | 0 | 0 | 0 | 109290.4946 | 0 | 3543.9813 | 3705 | 190 | 475 | 0 | 82426.9463 | 0 | 0 | 63.3333 | 1646.6667 | 4116.6667 | 8233.3333 | 8233.3333 | 1235 | 0 | 0 | 0 | 0 | 1646.6667 | 0
2025-08-22 | 362140.2141 | 0 | 96480 | 109515.2401 | 9309.4898 | 83873.0331 | 24360 | 135082.4511 | 0 | 0 | 3649.36 | 0 | 0 | 107403.1111 | 6032 | 0 | 0 | 2814.9333 | 0 | 0 | 6386.38 | 8796.6667 | 0 | 0 | 0 | 0 | 109515.2401 | 0 | 3606.1564 | 3770 | 193.3333 | 483.3333 | 0 | 83873.0331 | 0 | 0 | 64.4444 | 1675.5556 | 4188.8889 | 8377.7778 | 8377.7778 | 1256.6667 | 0 | 0 | 0 | 0 | 1675.5556 | 0
2025-08-23 | 366720.5627 | 0 | 96480 | 109739.9857 | 9469.9982 | 85319.1199 | 24780 | 137411.4589 | 0 | 0 | 3712.28 | 0 | 0 | 109254.8889 | 6136 | 0 | 0 | 2863.4667 | 0 | 0 | 6496.49 | 8948.3333 | 0 | 0 | 0 | 0 | 109739.9857 | 0 | 3668.3316 | 3835 | 196.6667 | 491.6667 | 0 | 85319.1199 | 0 | 0 | 65.5556 | 1704.4444 | 4261.1111 | 8522.2222 | 8522.2222 | 1278.3333 | 0 | 0 | 0 | 0 | 1704.4444 | 0
2025-08-24 | 371300.9112 | 0 | 96480 | 109964.7312 | 9630.5067 | 86765.2067 | 25200 | 139740.4667 | 0 | 0 | 3775.2 | 0 | 0 | 111106.6667 | 6240 | 0 | 0 | 2912 | 0 | 0 | 6606.6 | 9100 | 0 | 0 | 0 | 0 | 109964.7312 | 0 | 3730.5067 | 3900 | 200 | 500 | 0 | 86765.2067 | 0 | 0 | 66.6667 | 1733.3333 | 4333.3333 | 8666.6667 | 8666.6667 | 1300 | 0 | 0 | 0 | 0 | 1733.3333 | 0
2025-08-25 | 375881.2597 | 0 | 96480 | 110189.4767 | 9791.0151 | 88211.2934 | 25620 | 142069.4744 | 0 | 0 | 3838.12 | 0 | 0 | 112958.4444 | 6344 | 0 | 0 | 2960.5333 | 0 | 0 | 6716.71 | 9251.6667 | 0 | 0 | 0 | 0 | 110189.4767 | 0 | 3792.6818 | 3965 | 203.3333 | 508.3333 | 0 | 88211.2934 | 0 | 0 | 67.7778 | 1762.2222 | 4405.5556 | 8811.1111 | 8811.1111 | 1321.6667 | 0 | 0 | 0 | 0 | 1762.2222 | 0
2025-08-26 | 380461.6082 | 0 | 96480 | 110414.2222 | 9951.5236 | 89657.3802 | 26040 | 144398.4822 | 0 | 0 | 3901.04 | 0 | 0 | 114810.2222 | 6448 | 0 | 0 | 3009.0667 | 0 | 0 | 6826.82 | 9403.3333 | 0 | 0 | 0 | 0 | 110414.2222 | 0 | 3854.8569 | 4030 | 206.6667 | 516.6667 | 0 | 89657.3802 | 0 | 0 | 68.8889 | 1791.1111 | 4477.7778 | 8955.5556 | 8955.5556 | 1343.3333 | 0 | 0 | 0 | 0 | 1791.1111 | 0
2025-08-27 | 385041.9567 | 0 | 96480 | 110638.9677 | 10112.032 | 91103.467 | 26460 | 146727.49 | 0 | 0 | 3963.96 | 0 | 0 | 116662 | 6552 | 0 | 0 | 3057.6 | 0 | 0 | 6936.93 | 9555 | 0 | 0 | 0 | 0 | 110638.9677 | 0 | 3917.032 | 4095 | 210 | 525 | 0 | 91103.467 | 0 | 0 | 70 | 1820 | 4550 | 9100 | 9100 | 1365 | 0 | 0 | 0 | 0 | 1820 | 0
2025-08-28 | 389622.3053 | 0 | 96480 | 110863.7133 | 10272.5404 | 92549.5538 | 26880 | 149056.4978 | 0 | 0 | 4026.88 | 0 | 0 | 118513.7778 | 6656 | 0 | 0 | 3106.1333 | 0 | 0 | 7047.04 | 9706.6667 | 0 | 0 | 0 | 0 | 110863.7133 | 0 | 3979.2071 | 4160 | 213.3333 | 533.3333 | 0 | 92549.5538 | 0 | 0 | 71.1111 | 1848.8889 | 4622.2222 | 9244.4444 | 9244.4444 | 1386.6667 | 0 | 0 | 0 | 0 | 1848.8889 | 0
2025-08-29 | 394202.6538 | 0 | 96480 | 111088.4588 | 10433.0489 | 93995.6406 | 27300 | 151385.5056 | 0 | 0 | 4089.8 | 0 | 0 | 120365.5556 | 6760 | 0 | 0 | 3154.6667 | 0 | 0 | 7157.15 | 9858.3333 | 0 | 0 | 0 | 0 | 111088.4588 | 0 | 4041.3822 | 4225 | 216.6667 | 541.6667 | 0 | 93995.6406 | 0 | 0 | 72.2222 | 1877.7778 | 4694.4444 | 9388.8889 | 9388.8889 | 1408.3333 | 0 | 0 | 0 | 0 | 1877.7778 | 0
2025-08-30 | 398783.0023 | 0 | 96480 | 111313.2043 | 10593.5573 | 95441.7273 | 27720 | 153714.5133 | 0 | 0 | 4152.72 | 0 | 0 | 122217.3333 | 6864 | 0 | 0 | 3203.2 | 0 | 0 | 7267.26 | 10010 | 0 | 0 | 0 | 0 | 111313.2043 | 0 | 4103.5573 | 4290 | 220 | 550 | 0 | 95441.7273 | 0 | 0 | 73.3333 | 1906.6667 | 4766.6667 | 9533.3333 | 9533.3333 | 1430 | 0 | 0 | 0 | 0 | 1906.6667 | 0
2025-08-31 | 403363.3508 | 0 | 96480 | 111537.9498 | 10754.0658 | 96887.8141 | 28140 | 156043.5211 | 0 | 0 | 4215.64 | 0 | 0 | 124069.1111 | 6968 | 0 | 0 | 3251.7333 | 0 | 0 | 7377.37 | 10161.6667 | 0 | 0 | 0 | 0 | 111537.9498 | 0 | 4165.7324 | 4355 | 223.3333 | 558.3333 | 0 | 96887.8141 | 0 | 0 | 74.4444 | 1935.5556 | 4838.8889 | 9677.7778 | 9677.7778 | 1451.6667 | 0 | 0 | 0 | 0 | 1935.5556 | 0
2025-09-01 | 407943.6993 | 0 | 96480 | 111762.6953 | 10914.5742 | 98333.9009 | 28560 | 158372.5289 | 0 | 0 | 4278.56 | 0 | 0 | 125920.8889 | 7072 | 0 | 0 | 3300.2667 | 0 | 0 | 7487.48 | 10313.3333 | 0 | 0 | 0 | 0 | 111762.6953 | 0 | 4227.9076 | 4420 | 226.6667 | 566.6667 | 0 | 98333.9009 | 0 | 0 | 75.5556 | 1964.4444 | 4911.1111 | 9822.2222 | 9822.2222 | 1473.3333 | 0 | 0 | 0 | 0 | 1964.4444 | 0
2025-09-02 | 412524.0479 | 0 | 96480 | 111987.4409 | 11075.0827 | 99779.9877 | 28980 | 160701.5367 | 0 | 0 | 4341.48 | 0 | 0 | 127772.6667 | 7176 | 0 | 0 | 3348.8 | 0 | 0 | 7597.59 | 10465 | 0 | 0 | 0 | 0 | 111987.4409 | 0 | 4290.0827 | 4485 | 230 | 575 | 0 | 99779.9877 | 0 | 0 | 76.6667 | 1993.3333 | 4983.3333 | 9966.6667 | 9966.6667 | 1495 | 0 | 0 | 0 | 0 | 1993.3333 | 0
2025-09-03 | 417104.3964 | 0 | 96480 | 112212.1864 | 11235.5911 | 101226.0744 | 29400 | 163030.5444 | 0 | 0 | 4404.4 | 0 | 0 | 129624.4444 | 7280 | 0 | 0 | 3397.3333 | 0 | 0 | 7707.7 | 10616.6667 | 0 | 0 | 0 | 0 | 112212.1864 | 0 | 4352.2578 | 4550 | 233.3333 | 583.3333 | 0 | 101226.0744 | 0 | 0 | 77.7778 | 2022.2222 | 5055.5556 | 10111.1111 | 10111.1111 | 1516.6667 | 0 | 0 | 0 | 0 | 2022.2222 | 0
2025-09-04 | 421684.7449 | 0 | 96480 | 112436.9319 | 11396.0996 | 102672.1612 | 29820 | 165359.5522 | 0 | 0 | 4467.32 | 0 | 0 | 131476.2222 | 7384 | 0 | 0 | 3445.8667 | 0 | 0 | 7817.81 | 10768.3333 | 0 | 0 | 0 | 0 | 112436.9319 | 0 | 4414.4329 | 4615 | 236.6667 | 591.6667 | 0 | 102672.1612 | 0 | 0 | 78.8889 | 2051.1111 | 5127.7778 | 10255.5556 | 10255.5556 | 1538.3333 | 0 | 0 | 0 | 0 | 2051.1111 | 0
2025-09-05 | 426265.0934 | 0 | 96480 | 112661.6774 | 11556.608 | 104118.248 | 30240 | 167688.56 | 0 | 0 | 4530.24 | 0 | 0 | 133328 | 7488 | 0 | 0 | 3494.4 | 0 | 0 | 7927.92 | 10920 | 0 | 0 | 0 | 0 | 112661.6774 | 0 | 4476.608 | 4680 | 240 | 600 | 0 | 104118.248 | 0 | 0 | 80 | 2080 | 5200 | 10400 | 10400 | 1560 | 0 | 0 | 0 | 0 | 2080 | 0
2025-09-06 | 430845.4419 | 0 | 96480 | 112886.4229 | 11717.1164 | 105564.3348 | 30660 | 170017.5678 | 0 | 0 | 4593.16 | 0 | 0 | 135179.7778 | 7592 | 0 | 0 | 3542.9333 | 0 | 0 | 8038.03 | 11071.6667 | 0 | 0 | 0 | 0 | 112886.4229 | 0 | 4538.7831 | 4745 | 243.3333 | 608.3333 | 0 | 105564.3348 | 0 | 0 | 81.1111 | 2108.8889 | 5272.2222 | 10544.4444 | 10544.4444 | 1581.6667 | 0 | 0 | 0 | 0 | 2108.8889 | 0
2025-09-07 | 435425.7905 | 0 | 96480 | 113111.1685 | 11877.6249 | 107010.4216 | 31080 | 172346.5756 | 0 | 0 | 4656.08 | 0 | 0 | 137031.5556 | 7696 | 0 | 0 | 3591.4667 | 0 | 0 | 8148.14 | 11223.3333 | 0 | 0 | 0 | 0 | 113111.1685 | 0 | 4600.9582 | 4810 | 246.6667 | 616.6667 | 0 | 107010.4216 | 0 | 0 | 82.2222 | 2137.7778 | 5344.4444 | 10688.8889 | 10688.8889 | 1603.3333 | 0 | 0 | 0 | 0 | 2137.7778 | 0
2025-09-08 | 440006.139 | 0 | 96480 | 113335.914 | 12038.1333 | 108456.5083 | 31500 | 174675.5833 | 0 | 0 | 4719 | 0 | 0 | 138883.3333 | 7800 | 0 | 0 | 3640 | 0 | 0 | 8258.25 | 11375 | 0 | 0 | 0 | 0 | 113335.914 | 0 | 4663.1333 | 4875 | 250 | 625 | 0 | 108456.5083 | 0 | 0 | 83.3333 | 2166.6667 | 5416.6667 | 10833.3333 | 10833.3333 | 1625 | 0 | 0 | 0 | 0 | 2166.6667 | 0
2025-09-09 | 444586.4875 | 0 | 96480 | 113560.6595 | 12198.6418 | 109902.5951 | 31920 | 177004.5911 | 0 | 0 | 4781.92 | 0 | 0 | 140735.1111 | 7904 | 0 | 0 | 3688.5333 | 0 | 0 | 8368.36 | 11526.6667 | 0 | 0 | 0 | 0 | 113560.6595 | 0 | 4725.3084 | 4940 | 253.3333 | 633.3333 | 0 | 109902.5951 | 0 | 0 | 84.4444 | 2195.5556 | 5488.8889 | 10977.7778 | 10977.7778 | 1646.6667 | 0 | 0 | 0 | 0 | 2195.5556 | 0
2025-09-10 | 449166.836 | 0 | 96480 | 113785.405 | 12359.1502 | 111348.6819 | 32340 | 179333.5989 | 0 | 0 | 4844.84 | 0 | 0 | 142586.8889 | 8008 | 0 | 0 | 3737.0667 | 0 | 0 | 8478.47 | 11678.3333 | 0 | 0 | 0 | 0 | 113785.405 | 0 | 4787.4836 | 5005 | 256.6667 | 641.6667 | 0 | 111348.6819 | 0 | 0 | 85.5556 | 2224.4444 | 5561.1111 | 11122.2222 | 11122.2222 | 1668.3333 | 0 | 0 | 0 | 0 | 2224.4444 | 0
2025-09-11 | 453747.1845 | 0 | 96480 | 114010.1505 | 12519.6587 | 112794.7687 | 32760 | 181662.6067 | 0 | 0 | 4907.76 | 0 | 0 | 144438.6667 | 8112 | 0 | 0 | 3785.6 | 0 | 0 | 8588.58 | 11830 | 0 | 0 | 0 | 0 | 114010.1505 | 0 | 4849.6587 | 5070 | 260 | 650 | 0 | 112794.7687 | 0 | 0 | 86.6667 | 2253.3333 | 5633.3333 | 11266.6667 | 11266.6667 | 1690 | 0 | 0 | 0 | 0 | 2253.3333 | 0
2025-09-12 | 458327.5331 | 0 | 96480 | 114234.8961 | 12680.1671 | 114240.8554 | 33180 | 183991.6144 | 0 | 0 | 4970.68 | 0 | 0 | 146290.4444 | 8216 | 0 | 0 | 3834.1333 | 0 | 0 | 8698.69 | 11981.6667 | 0 | 0 | 0 | 0 | 114234.8961 | 0 | 4911.8338 | 5135 | 263.3333 | 658.3333 | 0 | 114240.8554 | 0 | 0 | 87.7778 | 2282.2222 | 5705.5556 | 11411.1111 | 11411.1111 | 1711.6667 | 0 | 0 | 0 | 0 | 2282.2222 | 0
2025-09-13 | 462907.8816 | 0 | 96480 | 114459.6416 | 12840.6756 | 115686.9422 | 33600 | 186320.6222 | 0 | 0 | 5033.6 | 0 | 0 | 148142.2222 | 8320 | 0 | 0 | 3882.6667 | 0 | 0 | 8808.8 | 12133.3333 | 0 | 0 | 0 | 0 | 114459.6416 | 0 | 4974.0089 | 5200 | 266.6667 | 666.6667 | 0 | 115686.9422 | 0 | 0 | 88.8889 | 2311.1111 | 5777.7778 | 11555.5556 | 11555.5556 | 1733.3333 | 0 | 0 | 0 | 0 | 2311.1111 | 0
2025-09-14 | 467488.2301 | 0 | 96480 | 114684.3871 | 13001.184 | 117133.029 | 34020 | 188649.63 | 0 | 0 | 5096.52 | 0 | 0 | 149994 | 8424 | 0 | 0 | 3931.2 | 0 | 0 | 8918.91 | 12285 | 0 | 0 | 0 | 0 | 114684.3871 | 0 | 5036.184 | 5265 | 270 | 675 | 0 | 117133.029 | 0 | 0 | 90 | 2340 | 5850 | 11700 | 11700 | 1755 | 0 | 0 | 0 | 0 | 2340 | 0
2025-09-15 | 472068.5786 | 0 | 96480 | 114909.1326 | 13161.6924 | 118579.1158 | 34440 | 190978.6378 | 0 | 0 | 5159.44 | 0 | 0 | 151845.7778 | 8528 | 0 | 0 | 3979.7333 | 0 | 0 | 9029.02 | 12436.6667 | 0 | 0 | 0 | 0 | 114909.1326 | 0 | 5098.3591 | 5330 | 273.3333 | 683.3333 | 0 | 118579.1158 | 0 | 0 | 91.1111 | 2368.8889 | 5922.2222 | 11844.4444 | 11844.4444 | 1776.6667 | 0 | 0 | 0 | 0 | 2368.8889 | 0
2025-09-16 | 476648.9271 | 0 | 96480 | 115133.8781 | 13322.2009 | 120025.2026 | 34860 | 193307.6456 | 0 | 0 | 5222.36 | 0 | 0 | 153697.5556 | 8632 | 0 | 0 | 4028.2667 | 0 | 0 | 9139.13 | 12588.3333 | 0 | 0 | 0 | 0 | 115133.8781 | 0 | 5160.5342 | 5395 | 276.6667 | 691.6667 | 0 | 120025.2026 | 0 | 0 | 92.2222 | 2397.7778 | 5994.4444 | 11988.8889 | 11988.8889 | 1798.3333 | 0 | 0 | 0 | 0 | 2397.7778 | 0
2025-09-17 | 481229.2757 | 0 | 96480 | 115358.6237 | 13482.7093 | 121471.2893 | 35280 | 195636.6533 | 0 | 0 | 5285.28 | 0 | 0 | 155549.3333 | 8736 | 0 | 0 | 4076.8 | 0 | 0 | 9249.24 | 12740 | 0 | 0 | 0 | 0 | 115358.6237 | 0 | 5222.7093 | 5460 | 280 | 700 | 0 | 121471.2893 | 0 | 0 | 93.3333 | 2426.6667 | 6066.6667 | 12133.3333 | 12133.3333 | 1820 | 0 | 0 | 0 | 0 | 2426.6667 | 0
2025-09-18 | 485809.6242 | 0 | 96480 | 115583.3692 | 13643.2178 | 122917.3761 | 35700 | 197965.6611 | 0 | 0 | 5348.2 | 0 | 0 | 157401.1111 | 8840 | 0 | 0 | 4125.3333 | 0 | 0 | 9359.35 | 12891.6667 | 0 | 0 | 0 | 0 | 115583.3692 | 0 | 5284.8844 | 5525 | 283.3333 | 708.3333 | 0 | 122917.3761 | 0 | 0 | 94.4444 | 2455.5556 | 6138.8889 | 12277.7778 | 12277.7778 | 1841.6667 | 0 | 0 | 0 | 0 | 2455.5556 | 0
2025-09-19 | 490389.9727 | 0 | 96480 | 115808.1147 | 13803.7262 | 124363.4629 | 36120 | 200294.6689 | 0 | 0 | 5411.12 | 0 | 0 | 159252.8889 | 8944 | 0 | 0 | 4173.8667 | 0 | 0 | 9469.46 | 13043.3333 | 0 | 0 | 0 | 0 | 115808.1147 | 0 | 5347.0596 | 5590 | 286.6667 | 716.6667 | 0 | 124363.4629 | 0 | 0 | 95.5556 | 2484.4444 | 6211.1111 | 12422.2222 | 12422.2222 | 1863.3333 | 0 | 0 | 0 | 0 | 2484.4444 | 0
2025-09-20 | 494970.3212 | 0 | 96480 | 116032.8602 | 13964.2347 | 125809.5497 | 36540 | 202623.6767 | 0 | 0 | 5474.04 | 0 | 0 | 161104.6667 | 9048 | 0 | 0 | 4222.4 | 0 | 0 | 9579.57 | 13195 | 0 | 0 | 0 | 0 | 116032.8602 | 0 | 5409.2347 | 5655 | 290 | 725 | 0 | 125809.5497 | 0 | 0 | 96.6667 | 2513.3333 | 6283.3333 | 12566.6667 | 12566.6667 | 1885 | 0 | 0 | 0 | 0 | 2513.3333 | 0
2025-09-21 | 499550.6697 | 0 | 96480 | 116257.6057 | 14124.7431 | 127255.6364 | 36960 | 204952.6844 | 0 | 0 | 5536.96 | 0 | 0 | 162956.4444 | 9152 | 0 | 0 | 4270.9333 | 0 | 0 | 9689.68 | 13346.6667 | 0 | 0 | 0 | 0 | 116257.6057 | 0 | 5471.4098 | 5720 | 293.3333 | 733.3333 | 0 | 127255.6364 | 0 | 0 | 97.7778 | 2542.2222 | 6355.5556 | 12711.1111 | 12711.1111 | 1906.6667 | 0 | 0 | 0 | 0 | 2542.2222 | 0
2025-09-22 | 504131.0183 | 0 | 96480 | 116482.3513 | 14285.2516 | 128701.7232 | 37380 | 207281.6922 | 0 | 0 | 5599.88 | 0 | 0 | 164808.2222 | 9256 | 0 | 0 | 4319.4667 | 0 | 0 | 9799.79 | 13498.3333 | 0 | 0 | 0 | 0 | 116482.3513 | 0 | 5533.5849 | 5785 | 296.6667 | 741.6667 | 0 | 128701.7232 | 0 | 0 | 98.8889 | 2571.1111 | 6427.7778 | 12855.5556 | 12855.5556 | 1928.3333 | 0 | 0 | 0 | 0 | 2571.1111 | 0
2025-09-23 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-24 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-25 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-26 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-27 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-28 | 508711.3668 | 0 | 96480 | 116707.0968 | 14445.76 | 130147.81 | 37800 | 209610.7 | 0 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 0 | 116707.0968 | 0 | 5595.76 | 5850 | 300 | 750 | 0 | 130147.81 | 0 | 0 | 100 | 2600 | 6500 | 13000 | 13000 | 1950 | 0 | 0 | 0 | 0 | 2600 | 0
2025-09-29 | 515850.1466 | 0 | 96480 | 121148.6247 | 15629.6542 | 131133.2446 | 38055.8077 | 209882.8154 | 272.1154 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 546.6846 | 121148.6247 | 0 | 5635.76 | 6379.6154 | 360 | 900 | 0 | 130586.56 | 0 | 0 | 100 | 2792.3462 | 6500 | 13020.1923 | 13043.2692 | 2267.3077 | 86.9712 | 0 | 0 | 0 | 2600 | 0
2025-09-30 | 522988.9265 | 0 | 96480 | 125590.1526 | 16813.5485 | 132118.6792 | 38311.6154 | 210154.9308 | 544.2308 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 1093.3692 | 125590.1526 | 0 | 5675.76 | 6909.2308 | 420 | 1050 | 0 | 131025.31 | 0 | 0 | 100 | 2984.6923 | 6500 | 13040.3846 | 13086.5385 | 2584.6154 | 173.9423 | 0 | 0 | 0 | 2600 | 0
2025-10-01 | 530127.7063 | 0 | 96480 | 130031.6805 | 17997.4427 | 133104.1138 | 38567.4231 | 210427.0462 | 816.3462 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 1640.0538 | 130031.6805 | 0 | 5715.76 | 7438.8462 | 480 | 1200 | 0 | 131464.06 | 0 | 0 | 100 | 3177.0385 | 6500 | 13060.5769 | 13129.8077 | 2901.9231 | 260.9135 | 0 | 0 | 0 | 2600 | 0
2025-10-02 | 537266.4861 | 0 | 96480 | 134473.2084 | 19181.3369 | 134089.5485 | 38823.2308 | 210699.1615 | 1088.4615 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 2186.7385 | 134473.2084 | 0 | 5755.76 | 7968.4615 | 540 | 1350 | 0 | 131902.81 | 0 | 0 | 100 | 3369.3846 | 6500 | 13080.7692 | 13173.0769 | 3219.2308 | 347.8846 | 0 | 0 | 0 | 2600 | 0
2025-10-03 | 544405.266 | 0 | 96480 | 138914.7364 | 20365.2312 | 135074.9831 | 39079.0385 | 210971.2769 | 1360.5769 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 2733.4231 | 138914.7364 | 0 | 5795.76 | 8498.0769 | 600 | 1500 | 0 | 132341.56 | 0 | 0 | 100 | 3561.7308 | 6500 | 13100.9615 | 13216.3462 | 3536.5385 | 434.8558 | 0 | 0 | 0 | 2600 | 0
2025-10-04 | 551544.0458 | 0 | 96480 | 143356.2643 | 21549.1254 | 136060.4177 | 39334.8462 | 211243.3923 | 1632.6923 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 3280.1077 | 143356.2643 | 0 | 5835.76 | 9027.6923 | 660 | 1650 | 0 | 132780.31 | 0 | 0 | 100 | 3754.0769 | 6500 | 13121.1538 | 13259.6154 | 3853.8462 | 521.8269 | 0 | 0 | 0 | 2600 | 0
2025-10-05 | 558682.8256 | 0 | 96480 | 147797.7922 | 22733.0196 | 137045.8523 | 39590.6538 | 211515.5077 | 1904.8077 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 3826.7923 | 147797.7922 | 0 | 5875.76 | 9557.3077 | 720 | 1800 | 0 | 133219.06 | 0 | 0 | 100 | 3946.4231 | 6500 | 13141.3462 | 13302.8846 | 4171.1538 | 608.7981 | 0 | 0 | 0 | 2600 | 0
2025-10-06 | 565821.6055 | 0 | 96480 | 152239.3201 | 23916.9138 | 138031.2869 | 39846.4615 | 211787.6231 | 2176.9231 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 4373.4769 | 152239.3201 | 0 | 5915.76 | 10086.9231 | 780 | 1950 | 0 | 133657.81 | 0 | 0 | 100 | 4138.7692 | 6500 | 13161.5385 | 13346.1538 | 4488.4615 | 695.7692 | 0 | 0 | 0 | 2600 | 0
2025-10-07 | 572960.3853 | 0 | 96480 | 156680.848 | 25100.8081 | 139016.7215 | 40102.2692 | 212059.7385 | 2449.0385 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 4920.1615 | 156680.848 | 0 | 5955.76 | 10616.5385 | 840 | 2100 | 0 | 134096.56 | 0 | 0 | 100 | 4331.1154 | 6500 | 13181.7308 | 13389.4231 | 4805.7692 | 782.7404 | 0 | 0 | 0 | 2600 | 0
2025-10-08 | 580099.1652 | 0 | 96480 | 161122.3759 | 26284.7023 | 140002.1562 | 40358.0769 | 212331.8538 | 2721.1538 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 5466.8462 | 161122.3759 | 0 | 5995.76 | 11146.1538 | 900 | 2250 | 0 | 134535.31 | 0 | 0 | 100 | 4523.4615 | 6500 | 13201.9231 | 13432.6923 | 5123.0769 | 869.7115 | 0 | 0 | 0 | 2600 | 0
2025-10-09 | 587237.945 | 0 | 96480 | 165563.9038 | 27468.5965 | 140987.5908 | 40613.8846 | 212603.9692 | 2993.2692 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 6013.5308 | 165563.9038 | 0 | 6035.76 | 11675.7692 | 960 | 2400 | 0 | 134974.06 | 0 | 0 | 100 | 4715.8077 | 6500 | 13222.1154 | 13475.9615 | 5440.3846 | 956.6827 | 0 | 0 | 0 | 2600 | 0
2025-10-10 | 594376.7248 | 0 | 96480 | 170005.4318 | 28652.4908 | 141973.0254 | 40869.6923 | 212876.0846 | 3265.3846 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 6560.2154 | 170005.4318 | 0 | 6075.76 | 12205.3846 | 1020 | 2550 | 0 | 135412.81 | 0 | 0 | 100 | 4908.1538 | 6500 | 13242.3077 | 13519.2308 | 5757.6923 | 1043.6538 | 0 | 0 | 0 | 2600 | 0
2025-10-11 | 601515.5047 | 0 | 96480 | 174446.9597 | 29836.385 | 142958.46 | 41125.5 | 213148.2 | 3537.5 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 7106.9 | 174446.9597 | 0 | 6115.76 | 12735 | 1080 | 2700 | 0 | 135851.56 | 0 | 0 | 100 | 5100.5 | 6500 | 13262.5 | 13562.5 | 6075 | 1130.625 | 0 | 0 | 0 | 2600 | 0
2025-10-12 | 608654.2845 | 0 | 96480 | 178888.4876 | 31020.2792 | 143943.8946 | 41381.3077 | 213420.3154 | 3809.6154 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 7653.5846 | 178888.4876 | 0 | 6155.76 | 13264.6154 | 1140 | 2850 | 0 | 136290.31 | 0 | 0 | 100 | 5292.8462 | 6500 | 13282.6923 | 13605.7692 | 6392.3077 | 1217.5962 | 0 | 0 | 0 | 2600 | 0
2025-10-13 | 615793.0644 |  |  | 183330.0155 | 32204.1735 | 144929.3292 | 41637.1154 | 213692.4308 | 4081.7308 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 8200.2692 | 183330.0155 | 0 | 6195.76 | 13794.2308 | 1200 | 3000 | 0 | 136729.06 | 0 | 0 | 100 | 5485.1923 | 6500 | 13302.8846 | 13649.0385 | 6709.6154 | 1304.5673 | 0 | 0 | 0 | 2600 | 0
2025-10-14 | 622931.8442 |  |  | 187771.5434 | 33388.0677 | 145914.7638 | 41892.9231 | 213964.5462 | 4353.8462 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 8746.9538 | 187771.5434 | 0 | 6235.76 | 14323.8462 | 1260 | 3150 | 0 | 137167.81 | 0 | 0 | 100 | 5677.5385 | 6500 | 13323.0769 | 13692.3077 | 7026.9231 | 1391.5385 | 0 | 0 | 0 | 2600 | 0
2025-10-15 | 630070.624 |  |  | 192213.0713 | 34571.9619 | 146900.1985 | 42148.7308 | 214236.6615 | 4625.9615 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 9293.6385 | 192213.0713 | 0 | 6275.76 | 14853.4615 | 1320 | 3300 | 0 | 137606.56 | 0 | 0 | 100 | 5869.8846 | 6500 | 13343.2692 | 13735.5769 | 7344.2308 | 1478.5096 | 0 | 0 | 0 | 2600 | 0
2025-10-16 | 637209.4039 |  |  | 196654.5993 | 35755.8562 | 147885.6331 | 42404.5385 | 214508.7769 | 4898.0769 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 9840.3231 | 196654.5993 | 0 | 6315.76 | 15383.0769 | 1380 | 3450 | 0 | 138045.31 | 0 | 0 | 100 | 6062.2308 | 6500 | 13363.4615 | 13778.8462 | 7661.5385 | 1565.4808 | 0 | 0 | 0 | 2600 | 0
2025-10-17 | 644348.1837 |  |  | 201096.1272 | 36939.7504 | 148871.0677 | 42660.3462 | 214780.8923 | 5170.1923 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 10387.0077 | 201096.1272 | 0 | 6355.76 | 15912.6923 | 1440 | 3600 | 0 | 138484.06 | 0 | 0 | 100 | 6254.5769 | 6500 | 13383.6538 | 13822.1154 | 7978.8462 | 1652.4519 | 0 | 0 | 0 | 2600 | 0
2025-10-18 | 651486.9635 |  |  | 205537.6551 | 38123.6446 | 149856.5023 | 42916.1538 | 215053.0077 | 5442.3077 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 10933.6923 | 205537.6551 | 0 | 6395.76 | 16442.3077 | 1500 | 3750 | 0 | 138922.81 | 0 | 0 | 100 | 6446.9231 | 6500 | 13403.8462 | 13865.3846 | 8296.1538 | 1739.4231 | 0 | 0 | 0 | 2600 | 0
2025-10-19 | 658625.7434 |  |  | 209979.183 | 39307.5388 | 150841.9369 | 43171.9615 | 215325.1231 | 5714.4231 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 11480.3769 | 209979.183 | 0 | 6435.76 | 16971.9231 | 1560 | 3900 | 0 | 139361.56 | 0 | 0 | 100 | 6639.2692 | 6500 | 13424.0385 | 13908.6538 | 8613.4615 | 1826.3942 | 0 | 0 | 0 | 2600 | 0
2025-10-20 | 665764.5232 |  |  | 214420.7109 | 40491.4331 | 151827.3715 | 43427.7692 | 215597.2385 | 5986.5385 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 12027.0615 | 214420.7109 | 0 | 6475.76 | 17501.5385 | 1620 | 4050 | 0 | 139800.31 | 0 | 0 | 100 | 6831.6154 | 6500 | 13444.2308 | 13951.9231 | 8930.7692 | 1913.3654 | 0 | 0 | 0 | 2600 | 0
2025-10-21 | 672903.3031 |  |  | 218862.2388 | 41675.3273 | 152812.8062 | 43683.5769 | 215869.3538 | 6258.6538 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 12573.7462 | 218862.2388 | 0 | 6515.76 | 18031.1538 | 1680 | 4200 | 0 | 140239.06 | 0 | 0 | 100 | 7023.9615 | 6500 | 13464.4231 | 13995.1923 | 9248.0769 | 2000.3365 | 0 | 0 | 0 | 2600 | 0
2025-10-22 | 680042.0829 |  |  | 223303.7667 | 42859.2215 | 153798.2408 | 43939.3846 | 216141.4692 | 6530.7692 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 13120.4308 | 223303.7667 | 0 | 6555.76 | 18560.7692 | 1740 | 4350 | 0 | 140677.81 | 0 | 0 | 100 | 7216.3077 | 6500 | 13484.6154 | 14038.4615 | 9565.3846 | 2087.3077 | 0 | 0 | 0 | 2600 | 0
2025-10-23 | 687180.8627 |  |  | 227745.2947 | 44043.1158 | 154783.6754 | 44195.1923 | 216413.5846 | 6802.8846 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 13667.1154 | 227745.2947 | 0 | 6595.76 | 19090.3846 | 1800 | 4500 | 0 | 141116.56 | 0 | 0 | 100 | 7408.6538 | 6500 | 13504.8077 | 14081.7308 | 9882.6923 | 2174.2788 | 0 | 0 | 0 | 2600 | 0
2025-10-24 | 694319.6426 |  |  | 232186.8226 | 45227.01 | 155769.11 | 44451 | 216685.7 | 7075 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 14213.8 | 232186.8226 | 0 | 6635.76 | 19620 | 1860 | 4650 | 0 | 141555.31 | 0 | 0 | 100 | 7601 | 6500 | 13525 | 14125 | 10200 | 2261.25 | 0 | 0 | 0 | 2600 | 0
2025-10-25 | 701458.4224 |  |  | 236628.3505 | 46410.9042 | 156754.5446 | 44706.8077 | 216957.8154 | 7347.1154 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 14760.4846 | 236628.3505 | 0 | 6675.76 | 20149.6154 | 1920 | 4800 | 0 | 141994.06 | 0 | 0 | 100 | 7793.3462 | 6500 | 13545.1923 | 14168.2692 | 10517.3077 | 2348.2212 | 0 | 0 | 0 | 2600 | 0
2025-10-26 | 708597.2023 |  |  | 241069.8784 | 47594.7985 | 157739.9792 | 44962.6154 | 217229.9308 | 7619.2308 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 15307.1692 | 241069.8784 | 0 | 6715.76 | 20679.2308 | 1980 | 4950 | 0 | 142432.81 | 0 | 0 | 100 | 7985.6923 | 6500 | 13565.3846 | 14211.5385 | 10834.6154 | 2435.1923 | 0 | 0 | 0 | 2600 | 0
2025-10-27 | 715735.9821 |  |  | 245511.4063 | 48778.6927 | 158725.4138 | 45218.4231 | 217502.0462 | 7891.3462 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 15853.8538 | 245511.4063 | 0 | 6755.76 | 21208.8462 | 2040 | 5100 | 0 | 142871.56 | 0 | 0 | 100 | 8178.0385 | 6500 | 13585.5769 | 14254.8077 | 11151.9231 | 2522.1635 | 0 | 0 | 0 | 2600 | 0
2025-10-28 | 722874.7619 |  |  | 249952.9342 | 49962.5869 | 159710.8485 | 45474.2308 | 217774.1615 | 8163.4615 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 16400.5385 | 249952.9342 | 0 | 6795.76 | 21738.4615 | 2100 | 5250 | 0 | 143310.31 | 0 | 0 | 100 | 8370.3846 | 6500 | 13605.7692 | 14298.0769 | 11469.2308 | 2609.1346 | 0 | 0 | 0 | 2600 | 0
2025-10-29 | 730013.5418 |  |  | 254394.4622 | 51146.4812 | 160696.2831 | 45730.0385 | 218046.2769 | 8435.5769 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 16947.2231 | 254394.4622 | 0 | 6835.76 | 22268.0769 | 2160 | 5400 | 0 | 143749.06 | 0 | 0 | 100 | 8562.7308 | 6500 | 13625.9615 | 14341.3462 | 11786.5385 | 2696.1058 | 0 | 0 | 0 | 2600 | 0
2025-10-30 | 737152.3216 |  |  | 258835.9901 | 52330.3754 | 161681.7177 | 45985.8462 | 218318.3923 | 8707.6923 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 17493.9077 | 258835.9901 | 0 | 6875.76 | 22797.6923 | 2220 | 5550 | 0 | 144187.81 | 0 | 0 | 100 | 8755.0769 | 6500 | 13646.1538 | 14384.6154 | 12103.8462 | 2783.0769 | 0 | 0 | 0 | 2600 | 0
2025-10-31 | 744291.1015 |  |  | 263277.518 | 53514.2696 | 162667.1523 | 46241.6538 | 218590.5077 | 8979.8077 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 18040.5923 | 263277.518 | 0 | 6915.76 | 23327.3077 | 2280 | 5700 | 0 | 144626.56 | 0 | 0 | 100 | 8947.4231 | 6500 | 13666.3462 | 14427.8846 | 12421.1538 | 2870.0481 | 0 | 0 | 0 | 2600 | 0
2025-11-01 | 751429.8813 |  |  | 267719.0459 | 54698.1638 | 163652.5869 | 46497.4615 | 218862.6231 | 9251.9231 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 18587.2769 | 267719.0459 | 0 | 6955.76 | 23856.9231 | 2340 | 5850 | 0 | 145065.31 | 0 | 0 | 100 | 9139.7692 | 6500 | 13686.5385 | 14471.1538 | 12738.4615 | 2957.0192 | 0 | 0 | 0 | 2600 | 0
2025-11-02 | 758568.6611 |  |  | 272160.5738 | 55882.0581 | 164638.0215 | 46753.2692 | 219134.7385 | 9524.0385 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 19133.9615 | 272160.5738 | 0 | 6995.76 | 24386.5385 | 2400 | 6000 | 0 | 145504.06 | 0 | 0 | 100 | 9332.1154 | 6500 | 13706.7308 | 14514.4231 | 13055.7692 | 3043.9904 | 0 | 0 | 0 | 2600 | 0
2025-11-03 | 765707.441 |  |  | 276602.1017 | 57065.9523 | 165623.4562 | 47009.0769 | 219406.8538 | 9796.1538 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 19680.6462 | 276602.1017 | 0 | 7035.76 | 24916.1538 | 2460 | 6150 | 0 | 145942.81 | 0 | 0 | 100 | 9524.4615 | 6500 | 13726.9231 | 14557.6923 | 13373.0769 | 3130.9615 | 0 | 0 | 0 | 2600 | 0
2025-11-04 | 772846.2208 |  |  | 281043.6297 | 58249.8465 | 166608.8908 | 47264.8846 | 219678.9692 | 10068.2692 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 20227.3308 | 281043.6297 | 0 | 7075.76 | 25445.7692 | 2520 | 6300 | 0 | 146381.56 | 0 | 0 | 100 | 9716.8077 | 6500 | 13747.1154 | 14600.9615 | 13690.3846 | 3217.9327 | 0 | 0 | 0 | 2600 | 0
2025-11-05 | 779985.0006 |  |  | 285485.1576 | 59433.7408 | 167594.3254 | 47520.6923 | 219951.0846 | 10340.3846 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 20774.0154 | 285485.1576 | 0 | 7115.76 | 25975.3846 | 2580 | 6450 | 0 | 146820.31 | 0 | 0 | 100 | 9909.1538 | 6500 | 13767.3077 | 14644.2308 | 14007.6923 | 3304.9038 | 0 | 0 | 0 | 2600 | 0
2025-11-06 | 787123.7805 |  |  | 289926.6855 | 60617.635 | 168579.76 | 47776.5 | 220223.2 | 10612.5 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 21320.7 | 289926.6855 | 0 | 7155.76 | 26505 | 2640 | 6600 | 0 | 147259.06 | 0 | 0 | 100 | 10101.5 | 6500 | 13787.5 | 14687.5 | 14325 | 3391.875 | 0 | 0 | 0 | 2600 | 0
2025-11-07 | 794262.5603 |  |  | 294368.2134 | 61801.5292 | 169565.1946 | 48032.3077 | 220495.3154 | 10884.6154 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 21867.3846 | 294368.2134 | 0 | 7195.76 | 27034.6154 | 2700 | 6750 | 0 | 147697.81 | 0 | 0 | 100 | 10293.8462 | 6500 | 13807.6923 | 14730.7692 | 14642.3077 | 3478.8462 | 0 | 0 | 0 | 2600 | 0
2025-11-08 | 801401.3402 |  |  | 298809.7413 | 62985.4235 | 170550.6292 | 48288.1154 | 220767.4308 | 11156.7308 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 22414.0692 | 298809.7413 | 0 | 7235.76 | 27564.2308 | 2760 | 6900 | 0 | 148136.56 | 0 | 0 | 100 | 10486.1923 | 6500 | 13827.8846 | 14774.0385 | 14959.6154 | 3565.8173 | 0 | 0 | 0 | 2600 | 0
2025-11-09 | 808540.12 |  |  | 303251.2692 | 64169.3177 | 171536.0638 | 48543.9231 | 221039.5462 | 11428.8462 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 22960.7538 | 303251.2692 | 0 | 7275.76 | 28093.8462 | 2820 | 7050 | 0 | 148575.31 | 0 | 0 | 100 | 10678.5385 | 6500 | 13848.0769 | 14817.3077 | 15276.9231 | 3652.7885 | 0 | 0 | 0 | 2600 | 0
2025-11-10 | 815678.8998 |  |  | 307692.7971 | 65353.2119 | 172521.4985 | 48799.7308 | 221311.6615 | 11700.9615 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 23507.4385 | 307692.7971 | 0 | 7315.76 | 28623.4615 | 2880 | 7200 | 0 | 149014.06 | 0 | 0 | 100 | 10870.8846 | 6500 | 13868.2692 | 14860.5769 | 15594.2308 | 3739.7596 | 0 | 0 | 0 | 2600 | 0
2025-11-11 | 822817.6797 |  |  | 312134.3251 | 66537.1062 | 173506.9331 | 49055.5385 | 221583.7769 | 11973.0769 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 24054.1231 | 312134.3251 | 0 | 7355.76 | 29153.0769 | 2940 | 7350 | 0 | 149452.81 | 0 | 0 | 100 | 11063.2308 | 6500 | 13888.4615 | 14903.8462 | 15911.5385 | 3826.7308 | 0 | 0 | 0 | 2600 | 0
2025-11-12 | 829956.4595 |  |  | 316575.853 | 67721.0004 | 174492.3677 | 49311.3462 | 221855.8923 | 12245.1923 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 24600.8077 | 316575.853 | 0 | 7395.76 | 29682.6923 | 3000 | 7500 | 0 | 149891.56 | 0 | 0 | 100 | 11255.5769 | 6500 | 13908.6538 | 14947.1154 | 16228.8462 | 3913.7019 | 0 | 0 | 0 | 2600 | 0
2025-11-13 | 837095.2394 |  |  | 321017.3809 | 68904.8946 | 175477.8023 | 49567.1538 | 222128.0077 | 12517.3077 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 25147.4923 | 321017.3809 | 0 | 7435.76 | 30212.3077 | 3060 | 7650 | 0 | 150330.31 | 0 | 0 | 100 | 11447.9231 | 6500 | 13928.8462 | 14990.3846 | 16546.1538 | 4000.6731 | 0 | 0 | 0 | 2600 | 0
2025-11-14 | 844234.0192 |  |  | 325458.9088 | 70088.7888 | 176463.2369 | 49822.9615 | 222400.1231 | 12789.4231 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 25694.1769 | 325458.9088 | 0 | 7475.76 | 30741.9231 | 3120 | 7800 | 0 | 150769.06 | 0 | 0 | 100 | 11640.2692 | 6500 | 13949.0385 | 15033.6538 | 16863.4615 | 4087.6442 | 0 | 0 | 0 | 2600 | 0
2025-11-15 | 851372.799 |  |  | 329900.4367 | 71272.6831 | 177448.6715 | 50078.7692 | 222672.2385 | 13061.5385 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 26240.8615 | 329900.4367 | 0 | 7515.76 | 31271.5385 | 3180 | 7950 | 0 | 151207.81 | 0 | 0 | 100 | 11832.6154 | 6500 | 13969.2308 | 15076.9231 | 17180.7692 | 4174.6154 | 0 | 0 | 0 | 2600 | 0
2025-11-16 | 858511.5789 |  |  | 334341.9646 | 72456.5773 | 178434.1062 | 50334.5769 | 222944.3538 | 13333.6538 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 26787.5462 | 334341.9646 | 0 | 7555.76 | 31801.1538 | 3240 | 8100 | 0 | 151646.56 | 0 | 0 | 100 | 12024.9615 | 6500 | 13989.4231 | 15120.1923 | 17498.0769 | 4261.5865 | 0 | 0 | 0 | 2600 | 0
2025-11-17 | 865650.3587 |  |  | 338783.4926 | 73640.4715 | 179419.5408 | 50590.3846 | 223216.4692 | 13605.7692 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 27334.2308 | 338783.4926 | 0 | 7595.76 | 32330.7692 | 3300 | 8250 | 0 | 152085.31 | 0 | 0 | 100 | 12217.3077 | 6500 | 14009.6154 | 15163.4615 | 17815.3846 | 4348.5577 | 0 | 0 | 0 | 2600 | 0
2025-11-18 | 872789.1385 |  |  | 343225.0205 | 74824.3658 | 180404.9754 | 50846.1923 | 223488.5846 | 13877.8846 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 27880.9154 | 343225.0205 | 0 | 7635.76 | 32860.3846 | 3360 | 8400 | 0 | 152524.06 | 0 | 0 | 100 | 12409.6538 | 6500 | 14029.8077 | 15206.7308 | 18132.6923 | 4435.5288 | 0 | 0 | 0 | 2600 | 0
2025-11-19 | 879927.9184 |  |  | 347666.5484 | 76008.26 | 181390.41 | 51102 | 223760.7 | 14150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 0 | 0 | 0 | 28427.6 | 347666.5484 | 0 | 7675.76 | 33390 | 3420 | 8550 | 0 | 152962.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-20 | 884182.9799 |  |  | 349503.7746 | 76722.3776 | 182273.1865 | 51102 | 224581.6412 | 14455.8824 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 515.0588 | 0 | 0 | 28427.6 | 349503.7746 | 0 | 7719.2894 | 33825.8824 | 3487.0588 | 8717.6471 | 0 | 153845.5865 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-21 | 888438.0415 |  |  | 351341.0009 | 77436.4953 | 183155.9629 | 51102 | 225402.5824 | 14761.7647 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 1030.1176 | 0 | 0 | 28427.6 | 351341.0009 | 0 | 7762.8188 | 34261.7647 | 3554.1176 | 8885.2941 | 0 | 154728.3629 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-22 | 892693.103 |  |  | 353178.2271 | 78150.6129 | 184038.7394 | 51102 | 226223.5235 | 15067.6471 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 1545.1765 | 0 | 0 | 28427.6 | 353178.2271 | 0 | 7806.3482 | 34697.6471 | 3621.1765 | 9052.9412 | 0 | 155611.1394 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-23 | 896948.1645 |  |  | 355015.4534 | 78864.7306 | 184921.5159 | 51102 | 227044.4647 | 15373.5294 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 2060.2353 | 0 | 0 | 28427.6 | 355015.4534 | 0 | 7849.8776 | 35133.5294 | 3688.2353 | 9220.5882 | 0 | 156493.9159 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-24 | 901203.2261 |  |  | 356852.6796 | 79578.8482 | 185804.2924 | 51102 | 227865.4059 | 15679.4118 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 2575.2941 | 0 | 0 | 28427.6 | 356852.6796 | 0 | 7893.4071 | 35569.4118 | 3755.2941 | 9388.2353 | 0 | 157376.6924 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-25 | 905458.2876 |  |  | 358689.9058 | 80292.9659 | 186687.0688 | 51102 | 228686.3471 | 15985.2941 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 3090.3529 | 0 | 0 | 28427.6 | 358689.9058 | 0 | 7936.9365 | 36005.2941 | 3822.3529 | 9555.8824 | 0 | 158259.4688 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-26 | 909713.3491 |  |  | 360527.1321 | 81007.0835 | 187569.8453 | 51102 | 229507.2882 | 16291.1765 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 3605.4118 | 0 | 0 | 28427.6 | 360527.1321 | 0 | 7980.4659 | 36441.1765 | 3889.4118 | 9723.5294 | 0 | 159142.2453 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-27 | 913968.4107 |  |  | 362364.3583 | 81721.2012 | 188452.6218 | 51102 | 230328.2294 | 16597.0588 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 4120.4706 | 0 | 0 | 28427.6 | 362364.3583 | 0 | 8023.9953 | 36877.0588 | 3956.4706 | 9891.1765 | 0 | 160025.0218 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-28 | 918223.4722 |  |  | 364201.5846 | 82435.3188 | 189335.3982 | 51102 | 231149.1706 | 16902.9412 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 4635.5294 | 0 | 0 | 28427.6 | 364201.5846 | 0 | 8067.5247 | 37312.9412 | 4023.5294 | 10058.8235 | 0 | 160907.7982 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-29 | 922478.5337 |  |  | 366038.8108 | 83149.4365 | 190218.1747 | 51102 | 231970.1118 | 17208.8235 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 5150.5882 | 0 | 0 | 28427.6 | 366038.8108 | 0 | 8111.0541 | 37748.8235 | 4090.5882 | 10226.4706 | 0 | 161790.5747 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-11-30 | 926733.5953 |  |  | 367876.037 | 83863.5541 | 191100.9512 | 51102 | 232791.0529 | 17514.7059 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 5665.6471 | 0 | 0 | 28427.6 | 367876.037 | 0 | 8154.5835 | 38184.7059 | 4157.6471 | 10394.1176 | 0 | 162673.3512 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-01 | 930988.6568 |  |  | 369713.2633 | 84577.6718 | 191983.7276 | 51102 | 233611.9941 | 17820.5882 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 6180.7059 | 0 | 0 | 28427.6 | 369713.2633 | 0 | 8198.1129 | 38620.5882 | 4224.7059 | 10561.7647 | 0 | 163556.1276 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-02 | 935243.7184 |  |  | 371550.4895 | 85291.7894 | 192866.5041 | 51102 | 234432.9353 | 18126.4706 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 6695.7647 | 0 | 0 | 28427.6 | 371550.4895 | 0 | 8241.6424 | 39056.4706 | 4291.7647 | 10729.4118 | 0 | 164438.9041 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-03 | 939498.7799 |  |  | 373387.7158 | 86005.9071 | 193749.2806 | 51102 | 235253.8765 | 18432.3529 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 7210.8235 | 0 | 0 | 28427.6 | 373387.7158 | 0 | 8285.1718 | 39492.3529 | 4358.8235 | 10897.0588 | 0 | 165321.6806 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-04 | 943753.8414 |  |  | 375224.942 | 86720.0247 | 194632.0571 | 51102 | 236074.8176 | 18738.2353 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 7725.8824 | 0 | 0 | 28427.6 | 375224.942 | 0 | 8328.7012 | 39928.2353 | 4425.8824 | 11064.7059 | 0 | 166204.4571 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-05 | 948008.903 |  |  | 377062.1683 | 87434.1424 | 195514.8335 | 51102 | 236895.7588 | 19044.1176 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 8240.9412 | 0 | 0 | 28427.6 | 377062.1683 | 0 | 8372.2306 | 40364.1176 | 4492.9412 | 11232.3529 | 0 | 167087.2335 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-06 | 952263.9645 |  |  | 378899.3945 | 88148.26 | 196397.61 | 51102 | 237716.7 | 19350 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 8756 | 0 | 0 | 28427.6 | 378899.3945 | 0 | 8415.76 | 40800 | 4560 | 11400 | 0 | 167970.01 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-07 | 956519.026 |  |  | 380736.6207 | 88862.3776 | 197280.3865 | 51102 | 238537.6412 | 19655.8824 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 9271.0588 | 0 | 0 | 28427.6 | 380736.6207 | 0 | 8459.2894 | 41235.8824 | 4627.0588 | 11567.6471 | 0 | 168852.7865 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-08 | 960774.0876 |  |  | 382573.847 | 89576.4953 | 198163.1629 | 51102 | 239358.5824 | 19961.7647 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 9786.1176 | 0 | 0 | 28427.6 | 382573.847 | 0 | 8502.8188 | 41671.7647 | 4694.1176 | 11735.2941 | 0 | 169735.5629 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-09 | 965029.1491 |  |  | 384411.0732 | 90290.6129 | 199045.9394 | 51102 | 240179.5235 | 20267.6471 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 10301.1765 | 0 | 0 | 28427.6 | 384411.0732 | 0 | 8546.3482 | 42107.6471 | 4761.1765 | 11902.9412 | 0 | 170618.3394 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-10 | 969284.2106 |  |  | 386248.2995 | 91004.7306 | 199928.7159 | 51102 | 241000.4647 | 20573.5294 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 10816.2353 | 0 | 0 | 28427.6 | 386248.2995 | 0 | 8589.8776 | 42543.5294 | 4828.2353 | 12070.5882 | 0 | 171501.1159 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-11 | 973539.2722 |  |  | 388085.5257 | 91718.8482 | 200811.4924 | 51102 | 241821.4059 | 20879.4118 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 11331.2941 | 0 | 0 | 28427.6 | 388085.5257 | 0 | 8633.4071 | 42979.4118 | 4895.2941 | 12238.2353 | 0 | 172383.8924 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-12 | 977794.3337 |  |  | 389922.752 | 92432.9659 | 201694.2688 | 51102 | 242642.3471 | 21185.2941 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 11846.3529 | 0 | 0 | 28427.6 | 389922.752 | 0 | 8676.9365 | 43415.2941 | 4962.3529 | 12405.8824 | 0 | 173266.6688 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-13 | 982049.3953 |  |  | 391759.9782 | 93147.0835 | 202577.0453 | 51102 | 243463.2882 | 21491.1765 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 12361.4118 | 0 | 0 | 28427.6 | 391759.9782 | 0 | 8720.4659 | 43851.1765 | 5029.4118 | 12573.5294 | 0 | 174149.4453 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-14 | 986304.4568 |  |  | 393597.2044 | 93861.2012 | 203459.8218 | 51102 | 244284.2294 | 21797.0588 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 12876.4706 | 0 | 0 | 28427.6 | 393597.2044 | 0 | 8763.9953 | 44287.0588 | 5096.4706 | 12741.1765 | 0 | 175032.2218 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-15 | 990559.5183 |  |  | 395434.4307 | 94575.3188 | 204342.5982 | 51102 | 245105.1706 | 22102.9412 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 13391.5294 | 0 | 0 | 28427.6 | 395434.4307 | 0 | 8807.5247 | 44722.9412 | 5163.5294 | 12908.8235 | 0 | 175914.9982 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-16 | 994814.5799 |  |  | 397271.6569 | 95289.4365 | 205225.3747 | 51102 | 245926.1118 | 22408.8235 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 13906.5882 | 0 | 0 | 28427.6 | 397271.6569 | 0 | 8851.0541 | 45158.8235 | 5230.5882 | 13076.4706 | 0 | 176797.7747 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-17 | 999069.6414 |  |  | 399108.8832 | 96003.5541 | 206108.1512 | 51102 | 246747.0529 | 22714.7059 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 14421.6471 | 0 | 0 | 28427.6 | 399108.8832 | 0 | 8894.5835 | 45594.7059 | 5297.6471 | 13244.1176 | 0 | 177680.5512 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-18 | 1003324.7029 |  |  | 400946.1094 | 96717.6718 | 206990.9276 | 51102 | 247567.9941 | 23020.5882 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 14936.7059 | 0 | 0 | 28427.6 | 400946.1094 | 0 | 8938.1129 | 46030.5882 | 5364.7059 | 13411.7647 | 0 | 178563.3276 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-19 | 1007579.7645 |  |  | 402783.3356 | 97431.7894 | 207873.7041 | 51102 | 248388.9353 | 23326.4706 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 15451.7647 | 0 | 0 | 28427.6 | 402783.3356 | 0 | 8981.6424 | 46466.4706 | 5431.7647 | 13579.4118 | 0 | 179446.1041 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-20 | 1011834.826 |  |  | 404620.5619 | 98145.9071 | 208756.4806 | 51102 | 249209.8765 | 23632.3529 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 15966.8235 | 0 | 0 | 28427.6 | 404620.5619 | 0 | 9025.1718 | 46902.3529 | 5498.8235 | 13747.0588 | 0 | 180328.8806 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-21 | 1016089.8875 |  |  | 406457.7881 | 98860.0247 | 209639.2571 | 51102 | 250030.8176 | 23938.2353 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 16481.8824 | 0 | 0 | 28427.6 | 406457.7881 | 0 | 9068.7012 | 47338.2353 | 5565.8824 | 13914.7059 | 0 | 181211.6571 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-22 | 1020344.9491 |  |  | 408295.0144 | 99574.1424 | 210522.0335 | 51102 | 250851.7588 | 24244.1176 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 16996.9412 | 0 | 0 | 28427.6 | 408295.0144 | 0 | 9112.2306 | 47774.1176 | 5632.9412 | 14082.3529 | 0 | 182094.4335 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-23 | 1024600.0106 |  |  | 410132.2406 | 100288.26 | 211404.81 | 51102 | 251672.7 | 24550 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 17512 | 0 | 0 | 28427.6 | 410132.2406 | 0 | 9155.76 | 48210 | 5700 | 14250 | 0 | 182977.21 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-24 | 1028855.0721 |  |  | 411969.4669 | 101002.3776 | 212287.5865 | 51102 | 252493.6412 | 24855.8824 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 18027.0588 | 0 | 0 | 28427.6 | 411969.4669 | 0 | 9199.2894 | 48645.8824 | 5767.0588 | 14417.6471 | 0 | 183859.9865 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-25 | 1033110.1337 |  |  | 413806.6931 | 101716.4953 | 213170.3629 | 51102 | 253314.5824 | 25161.7647 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 18542.1176 | 0 | 0 | 28427.6 | 413806.6931 | 0 | 9242.8188 | 49081.7647 | 5834.1176 | 14585.2941 | 0 | 184742.7629 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-26 | 1037365.1952 |  |  | 415643.9193 | 102430.6129 | 214053.1394 | 51102 | 254135.5235 | 25467.6471 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 19057.1765 | 0 | 0 | 28427.6 | 415643.9193 | 0 | 9286.3482 | 49517.6471 | 5901.1765 | 14752.9412 | 0 | 185625.5394 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-27 | 1041620.2568 |  |  | 417481.1456 | 103144.7306 | 214935.9159 | 51102 | 254956.4647 | 25773.5294 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 19572.2353 | 0 | 0 | 28427.6 | 417481.1456 | 0 | 9329.8776 | 49953.5294 | 5968.2353 | 14920.5882 | 0 | 186508.3159 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-28 | 1045875.3183 |  |  | 419318.3718 | 103858.8482 | 215818.6924 | 51102 | 255777.4059 | 26079.4118 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 20087.2941 | 0 | 0 | 28427.6 | 419318.3718 | 0 | 9373.4071 | 50389.4118 | 6035.2941 | 15088.2353 | 0 | 187391.0924 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-29 | 1050130.3798 |  |  | 421155.5981 | 104572.9659 | 216701.4688 | 51102 | 256598.3471 | 26385.2941 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 20602.3529 | 0 | 0 | 28427.6 | 421155.5981 | 0 | 9416.9365 | 50825.2941 | 6102.3529 | 15255.8824 | 0 | 188273.8688 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-30 | 1054385.4414 |  |  | 422992.8243 | 105287.0835 | 217584.2453 | 51102 | 257419.2882 | 26691.1765 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 21117.4118 | 0 | 0 | 28427.6 | 422992.8243 | 0 | 9460.4659 | 51261.1765 | 6169.4118 | 15423.5294 | 0 | 189156.6453 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2025-12-31 | 1058640.5029 |  |  | 424830.0505 | 106001.2012 | 218467.0218 | 51102 | 258240.2294 | 26997.0588 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 21632.4706 | 0 | 0 | 28427.6 | 424830.0505 | 0 | 9503.9953 | 51697.0588 | 6236.4706 | 15591.1765 | 0 | 190039.4218 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-01 | 1062895.5644 |  |  | 426667.2768 | 106715.3188 | 219349.7982 | 51102 | 259061.1706 | 27302.9412 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 22147.5294 | 0 | 0 | 28427.6 | 426667.2768 | 0 | 9547.5247 | 52132.9412 | 6303.5294 | 15758.8235 | 0 | 190922.1982 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-02 | 1067150.626 |  |  | 428504.503 | 107429.4365 | 220232.5747 | 51102 | 259882.1118 | 27608.8235 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 22662.5882 | 0 | 0 | 28427.6 | 428504.503 | 0 | 9591.0541 | 52568.8235 | 6370.5882 | 15926.4706 | 0 | 191804.9747 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-03 | 1071405.6875 |  |  | 430341.7293 | 108143.5541 | 221115.3512 | 51102 | 260703.0529 | 27914.7059 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 23177.6471 | 0 | 0 | 28427.6 | 430341.7293 | 0 | 9634.5835 | 53004.7059 | 6437.6471 | 16094.1176 | 0 | 192687.7512 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-04 | 1075660.749 |  |  | 432178.9555 | 108857.6718 | 221998.1276 | 51102 | 261523.9941 | 28220.5882 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 23692.7059 | 0 | 0 | 28427.6 | 432178.9555 | 0 | 9678.1129 | 53440.5882 | 6504.7059 | 16261.7647 | 0 | 193570.5276 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-05 | 1079915.8106 |  |  | 434016.1818 | 109571.7894 | 222880.9041 | 51102 | 262344.9353 | 28526.4706 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 24207.7647 | 0 | 0 | 28427.6 | 434016.1818 | 0 | 9721.6424 | 53876.4706 | 6571.7647 | 16429.4118 | 0 | 194453.3041 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-06 | 1084170.8721 |  |  | 435853.408 | 110285.9071 | 223763.6806 | 51102 | 263165.8765 | 28832.3529 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 24722.8235 | 0 | 0 | 28427.6 | 435853.408 | 0 | 9765.1718 | 54312.3529 | 6638.8235 | 16597.0588 | 0 | 195336.0806 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-07 | 1088425.9337 |  |  | 437690.6342 | 111000.0247 | 224646.4571 | 51102 | 263986.8176 | 29138.2353 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 25237.8824 | 0 | 0 | 28427.6 | 437690.6342 | 0 | 9808.7012 | 54748.2353 | 6705.8824 | 16764.7059 | 0 | 196218.8571 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-08 | 1092680.9952 |  |  | 439527.8605 | 111714.1424 | 225529.2335 | 51102 | 264807.7588 | 29444.1176 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 25752.9412 | 0 | 0 | 28427.6 | 439527.8605 | 0 | 9852.2306 | 55184.1176 | 6772.9412 | 16932.3529 | 0 | 197101.6335 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-09 | 1096936.0567 |  |  | 441365.0867 | 112428.26 | 226412.01 | 51102 | 265628.7 | 29750 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 26268 | 0 | 0 | 28427.6 | 441365.0867 | 0 | 9895.76 | 55620 | 6840 | 17100 | 0 | 197984.41 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-10 | 1101191.1183 |  |  | 443202.313 | 113142.3776 | 227294.7865 | 51102 | 266449.6412 | 30055.8824 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 26783.0588 | 0 | 0 | 28427.6 | 443202.313 | 0 | 9939.2894 | 56055.8824 | 6907.0588 | 17267.6471 | 0 | 198867.1865 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-11 | 1105446.1798 |  |  | 445039.5392 | 113856.4953 | 228177.5629 | 51102 | 267270.5824 | 30361.7647 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 27298.1176 | 0 | 0 | 28427.6 | 445039.5392 | 0 | 9982.8188 | 56491.7647 | 6974.1176 | 17435.2941 | 0 | 199749.9629 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-12 | 1109701.2413 |  |  | 446876.7655 | 114570.6129 | 229060.3394 | 51102 | 268091.5235 | 30667.6471 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 27813.1765 | 0 | 0 | 28427.6 | 446876.7655 | 0 | 10026.3482 | 56927.6471 | 7041.1765 | 17602.9412 | 0 | 200632.7394 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-13 | 1113956.3029 |  |  | 448713.9917 | 115284.7306 | 229943.1159 | 51102 | 268912.4647 | 30973.5294 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 28328.2353 | 0 | 0 | 28427.6 | 448713.9917 | 0 | 10069.8776 | 57363.5294 | 7108.2353 | 17770.5882 | 0 | 201515.5159 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-14 | 1118211.3644 |  |  | 450551.2179 | 115998.8482 | 230825.8924 | 51102 | 269733.4059 | 31279.4118 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 28843.2941 | 0 | 0 | 28427.6 | 450551.2179 | 0 | 10113.4071 | 57799.4118 | 7175.2941 | 17938.2353 | 0 | 202398.2924 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-15 | 1122466.4259 |  |  | 452388.4442 | 116712.9659 | 231708.6688 | 51102 | 270554.3471 | 31585.2941 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 29358.3529 | 0 | 0 | 28427.6 | 452388.4442 | 0 | 10156.9365 | 58235.2941 | 7242.3529 | 18105.8824 | 0 | 203281.0688 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-16 | 1126721.4875 |  |  | 454225.6704 | 117427.0835 | 232591.4453 | 51102 | 271375.2882 | 31891.1765 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 29873.4118 | 0 | 0 | 28427.6 | 454225.6704 | 0 | 10200.4659 | 58671.1765 | 7309.4118 | 18273.5294 | 0 | 204163.8453 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-17 | 1130976.549 |  |  | 456062.8967 | 118141.2012 | 233474.2218 | 51102 | 272196.2294 | 32197.0588 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 30388.4706 | 0 | 0 | 28427.6 | 456062.8967 | 0 | 10243.9953 | 59107.0588 | 7376.4706 | 18441.1765 | 0 | 205046.6218 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-18 | 1135231.6106 |  |  | 457900.1229 | 118855.3188 | 234356.9982 | 51102 | 273017.1706 | 32502.9412 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 30903.5294 | 0 | 0 | 28427.6 | 457900.1229 | 0 | 10287.5247 | 59542.9412 | 7443.5294 | 18608.8235 | 0 | 205929.3982 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-19 | 1139486.6721 |  |  | 459737.3491 | 119569.4365 | 235239.7747 | 51102 | 273838.1118 | 32808.8235 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 31418.5882 | 0 | 0 | 28427.6 | 459737.3491 | 0 | 10331.0541 | 59978.8235 | 7510.5882 | 18776.4706 | 0 | 206812.1747 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-20 | 1143741.7336 |  |  | 461574.5754 | 120283.5541 | 236122.5512 | 51102 | 274659.0529 | 33114.7059 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 31933.6471 | 0 | 0 | 28427.6 | 461574.5754 | 0 | 10374.5835 | 60414.7059 | 7577.6471 | 18944.1176 | 0 | 207694.9512 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-21 | 1147996.7952 |  |  | 463411.8016 | 120997.6718 | 237005.3276 | 51102 | 275479.9941 | 33420.5882 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 32448.7059 | 0 | 0 | 28427.6 | 463411.8016 | 0 | 10418.1129 | 60850.5882 | 7644.7059 | 19111.7647 | 0 | 208577.7276 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-22 | 1152251.8567 |  |  | 465249.0279 | 121711.7894 | 237888.1041 | 51102 | 276300.9353 | 33726.4706 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 32963.7647 | 0 | 0 | 28427.6 | 465249.0279 | 0 | 10461.6424 | 61286.4706 | 7711.7647 | 19279.4118 | 0 | 209460.5041 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-23 | 1156506.9182 |  |  | 467086.2541 | 122425.9071 | 238770.8806 | 51102 | 277121.8765 | 34032.3529 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 33478.8235 | 0 | 0 | 28427.6 | 467086.2541 | 0 | 10505.1718 | 61722.3529 | 7778.8235 | 19447.0588 | 0 | 210343.2806 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-24 | 1160761.9798 |  |  | 468923.4804 | 123140.0247 | 239653.6571 | 51102 | 277942.8176 | 34338.2353 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 33993.8824 | 0 | 0 | 28427.6 | 468923.4804 | 0 | 10548.7012 | 62158.2353 | 7845.8824 | 19614.7059 | 0 | 211226.0571 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-25 | 1165017.0413 |  |  | 470760.7066 | 123854.1424 | 240536.4335 | 51102 | 278763.7588 | 34644.1176 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 34508.9412 | 0 | 0 | 28427.6 | 470760.7066 | 0 | 10592.2306 | 62594.1176 | 7912.9412 | 19782.3529 | 0 | 212108.8335 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-26 | 1169272.1028 |  |  | 472597.9328 | 124568.26 | 241419.21 | 51102 | 279584.7 | 34950 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 35024 | 0 | 0 | 28427.6 | 472597.9328 | 0 | 10635.76 | 63030 | 7980 | 19950 | 0 | 212991.61 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-27 | 1173527.1644 |  |  | 474435.1591 | 125282.3776 | 242301.9865 | 51102 | 280405.6412 | 35255.8824 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 35539.0588 | 0 | 0 | 28427.6 | 474435.1591 | 0 | 10679.2894 | 63465.8824 | 8047.0588 | 20117.6471 | 0 | 213874.3865 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-28 | 1177782.2259 |  |  | 476272.3853 | 125996.4953 | 243184.7629 | 51102 | 281226.5824 | 35561.7647 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 36054.1176 | 0 | 0 | 28427.6 | 476272.3853 | 0 | 10722.8188 | 63901.7647 | 8114.1176 | 20285.2941 | 0 | 214757.1629 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-29 | 1182037.2874 |  |  | 478109.6116 | 126710.6129 | 244067.5394 | 51102 | 282047.5235 | 35867.6471 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 36569.1765 | 0 | 0 | 28427.6 | 478109.6116 | 0 | 10766.3482 | 64337.6471 | 8181.1765 | 20452.9412 | 0 | 215639.9394 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-30 | 1186292.349 |  |  | 479946.8378 | 127424.7306 | 244950.3159 | 51102 | 282868.4647 | 36173.5294 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 37084.2353 | 0 | 0 | 28427.6 | 479946.8378 | 0 | 10809.8776 | 64773.5294 | 8248.2353 | 20620.5882 | 0 | 216522.7159 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-01-31 | 1190547.4105 |  |  | 481784.064 | 128138.8482 | 245833.0924 | 51102 | 283689.4059 | 36479.4118 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 37599.2941 | 0 | 0 | 28427.6 | 481784.064 | 0 | 10853.4071 | 65209.4118 | 8315.2941 | 20788.2353 | 0 | 217405.4924 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-01 | 1194802.4721 |  |  | 483621.2903 | 128852.9659 | 246715.8688 | 51102 | 284510.3471 | 36785.2941 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 38114.3529 | 0 | 0 | 28427.6 | 483621.2903 | 0 | 10896.9365 | 65645.2941 | 8382.3529 | 20955.8824 | 0 | 218288.2688 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-02 | 1199057.5336 |  |  | 485458.5165 | 129567.0835 | 247598.6453 | 51102 | 285331.2882 | 37091.1765 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 38629.4118 | 0 | 0 | 28427.6 | 485458.5165 | 0 | 10940.4659 | 66081.1765 | 8449.4118 | 21123.5294 | 0 | 219171.0453 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-03 | 1203312.5951 |  |  | 487295.7428 | 130281.2012 | 248481.4218 | 51102 | 286152.2294 | 37397.0588 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 39144.4706 | 0 | 0 | 28427.6 | 487295.7428 | 0 | 10983.9953 | 66517.0588 | 8516.4706 | 21291.1765 | 0 | 220053.8218 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-04 | 1207567.6567 |  |  | 489132.969 | 130995.3188 | 249364.1982 | 51102 | 286973.1706 | 37702.9412 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 39659.5294 | 0 | 0 | 28427.6 | 489132.969 | 0 | 11027.5247 | 66952.9412 | 8583.5294 | 21458.8235 | 0 | 220936.5982 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-05 | 1211822.7182 |  |  | 490970.1953 | 131709.4365 | 250246.9747 | 51102 | 287794.1118 | 38008.8235 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 40174.5882 | 0 | 0 | 28427.6 | 490970.1953 | 0 | 11071.0541 | 67388.8235 | 8650.5882 | 21626.4706 | 0 | 221819.3747 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-06 | 1216077.7797 |  |  | 492807.4215 | 132423.5541 | 251129.7512 | 51102 | 288615.0529 | 38314.7059 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 40689.6471 | 0 | 0 | 28427.6 | 492807.4215 | 0 | 11114.5835 | 67824.7059 | 8717.6471 | 21794.1176 | 0 | 222702.1512 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-07 | 1220332.8413 |  |  | 494644.6477 | 133137.6718 | 252012.5276 | 51102 | 289435.9941 | 38620.5882 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 41204.7059 | 0 | 0 | 28427.6 | 494644.6477 | 0 | 11158.1129 | 68260.5882 | 8784.7059 | 21961.7647 | 0 | 223584.9276 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-08 | 1224587.9028 |  |  | 496481.874 | 133851.7894 | 252895.3041 | 51102 | 290256.9353 | 38926.4706 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 41719.7647 | 0 | 0 | 28427.6 | 496481.874 | 0 | 11201.6424 | 68696.4706 | 8851.7647 | 22129.4118 | 0 | 224467.7041 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-09 | 1228842.9643 |  |  | 498319.1002 | 134565.9071 | 253778.0806 | 51102 | 291077.8765 | 39232.3529 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 42234.8235 | 0 | 0 | 28427.6 | 498319.1002 | 0 | 11245.1718 | 69132.3529 | 8918.8235 | 22297.0588 | 0 | 225350.4806 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-10 | 1233098.0259 |  |  | 500156.3265 | 135280.0247 | 254660.8571 | 51102 | 291898.8176 | 39538.2353 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 42749.8824 | 0 | 0 | 28427.6 | 500156.3265 | 0 | 11288.7012 | 69568.2353 | 8985.8824 | 22464.7059 | 0 | 226233.2571 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-11 | 1237353.0874 |  |  | 501993.5527 | 135994.1424 | 255543.6335 | 51102 | 292719.7588 | 39844.1176 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43264.9412 | 0 | 0 | 28427.6 | 501993.5527 | 0 | 11332.2306 | 70004.1176 | 9052.9412 | 22632.3529 | 0 | 227116.0335 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-12 | 1241608.149 |  |  | 503830.779 | 136708.26 | 256426.41 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 503830.779 | 0 | 11375.76 | 70440 | 9120 | 22800 | 0 | 227998.81 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-13 | 1243591.5753 |  |  | 505376.4711 | 137091.8389 | 256480.5653 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 505376.4711 | 0 | 11389.8653 | 70680.1579 | 9156.9474 | 22892.3684 | 0 | 228052.9653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-14 | 1245575.0017 |  |  | 506922.1633 | 137475.4179 | 256534.7205 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 506922.1633 | 0 | 11403.9705 | 70920.3158 | 9193.8947 | 22984.7368 | 0 | 228107.1205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-15 | 1247558.4281 |  |  | 508467.8555 | 137858.9968 | 256588.8758 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 508467.8555 | 0 | 11418.0758 | 71160.4737 | 9230.8421 | 23077.1053 | 0 | 228161.2758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-16 | 1249541.8545 |  |  | 510013.5477 | 138242.5758 | 256643.0311 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 510013.5477 | 0 | 11432.1811 | 71400.6316 | 9267.7895 | 23169.4737 | 0 | 228215.4311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-17 | 1251525.2809 |  |  | 511559.2399 | 138626.1547 | 256697.1863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 511559.2399 | 0 | 11446.2863 | 71640.7895 | 9304.7368 | 23261.8421 | 0 | 228269.5863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-18 | 1253508.7073 |  |  | 513104.932 | 139009.7337 | 256751.3416 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 513104.932 | 0 | 11460.3916 | 71880.9474 | 9341.6842 | 23354.2105 | 0 | 228323.7416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-19 | 1255492.1337 |  |  | 514650.6242 | 139393.3126 | 256805.4968 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 514650.6242 | 0 | 11474.4968 | 72121.1053 | 9378.6316 | 23446.5789 | 0 | 228377.8968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-20 | 1257475.5601 |  |  | 516196.3164 | 139776.8916 | 256859.6521 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 516196.3164 | 0 | 11488.6021 | 72361.2632 | 9415.5789 | 23538.9474 | 0 | 228432.0521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-21 | 1259458.9865 |  |  | 517742.0086 | 140160.4705 | 256913.8074 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 517742.0086 | 0 | 11502.7074 | 72601.4211 | 9452.5263 | 23631.3158 | 0 | 228486.2074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-22 | 1261442.4129 |  |  | 519287.7008 | 140544.0495 | 256967.9626 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 519287.7008 | 0 | 11516.8126 | 72841.5789 | 9489.4737 | 23723.6842 | 0 | 228540.3626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-23 | 1263425.8393 |  |  | 520833.393 | 140927.6284 | 257022.1179 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 520833.393 | 0 | 11530.9179 | 73081.7368 | 9526.4211 | 23816.0526 | 0 | 228594.5179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-24 | 1265409.2657 |  |  | 522379.0851 | 141311.2074 | 257076.2732 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 522379.0851 | 0 | 11545.0232 | 73321.8947 | 9563.3684 | 23908.4211 | 0 | 228648.6732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-25 | 1267392.6921 |  |  | 523924.7773 | 141694.7863 | 257130.4284 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 523924.7773 | 0 | 11559.1284 | 73562.0526 | 9600.3158 | 24000.7895 | 0 | 228702.8284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-26 | 1269376.1184 |  |  | 525470.4695 | 142078.3653 | 257184.5837 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 525470.4695 | 0 | 11573.2337 | 73802.2105 | 9637.2632 | 24093.1579 | 0 | 228756.9837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-27 | 1271359.5448 |  |  | 527016.1617 | 142461.9442 | 257238.7389 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 527016.1617 | 0 | 11587.3389 | 74042.3684 | 9674.2105 | 24185.5263 | 0 | 228811.1389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-02-28 | 1273342.9712 |  |  | 528561.8539 | 142845.5232 | 257292.8942 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 528561.8539 | 0 | 11601.4442 | 74282.5263 | 9711.1579 | 24277.8947 | 0 | 228865.2942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-01 | 1275326.3976 |  |  | 530107.546 | 143229.1021 | 257347.0495 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 530107.546 | 0 | 11615.5495 | 74522.6842 | 9748.1053 | 24370.2632 | 0 | 228919.4495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-02 | 1277309.824 |  |  | 531653.2382 | 143612.6811 | 257401.2047 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 531653.2382 | 0 | 11629.6547 | 74762.8421 | 9785.0526 | 24462.6316 | 0 | 228973.6047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-03 | 1279293.2504 |  |  | 533198.9304 | 143996.26 | 257455.36 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 533198.9304 | 0 | 11643.76 | 75003 | 9822 | 24555 | 0 | 229027.76 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-04 | 1281276.6768 |  |  | 534744.6226 | 144379.8389 | 257509.5153 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 534744.6226 | 0 | 11657.8653 | 75243.1579 | 9858.9474 | 24647.3684 | 0 | 229081.9153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-05 | 1283260.1032 |  |  | 536290.3148 | 144763.4179 | 257563.6705 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 536290.3148 | 0 | 11671.9705 | 75483.3158 | 9895.8947 | 24739.7368 | 0 | 229136.0705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-06 | 1285243.5296 |  |  | 537836.007 | 145146.9968 | 257617.8258 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 537836.007 | 0 | 11686.0758 | 75723.4737 | 9932.8421 | 24832.1053 | 0 | 229190.2258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-07 | 1287226.956 |  |  | 539381.6991 | 145530.5758 | 257671.9811 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 539381.6991 | 0 | 11700.1811 | 75963.6316 | 9969.7895 | 24924.4737 | 0 | 229244.3811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-08 | 1289210.3824 |  |  | 540927.3913 | 145914.1547 | 257726.1363 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 540927.3913 | 0 | 11714.2863 | 76203.7895 | 10006.7368 | 25016.8421 | 0 | 229298.5363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-09 | 1291193.8088 |  |  | 542473.0835 | 146297.7337 | 257780.2916 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 542473.0835 | 0 | 11728.3916 | 76443.9474 | 10043.6842 | 25109.2105 | 0 | 229352.6916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-10 | 1293177.2352 |  |  | 544018.7757 | 146681.3126 | 257834.4468 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 544018.7757 | 0 | 11742.4968 | 76684.1053 | 10080.6316 | 25201.5789 | 0 | 229406.8468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-11 | 1295160.6615 |  |  | 545564.4679 | 147064.8916 | 257888.6021 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 545564.4679 | 0 | 11756.6021 | 76924.2632 | 10117.5789 | 25293.9474 | 0 | 229461.0021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-12 | 1297144.0879 |  |  | 547110.16 | 147448.4705 | 257942.7574 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 547110.16 | 0 | 11770.7074 | 77164.4211 | 10154.5263 | 25386.3158 | 0 | 229515.1574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-13 | 1299127.5143 |  |  | 548655.8522 | 147832.0495 | 257996.9126 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 548655.8522 | 0 | 11784.8126 | 77404.5789 | 10191.4737 | 25478.6842 | 0 | 229569.3126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-14 | 1301110.9407 |  |  | 550201.5444 | 148215.6284 | 258051.0679 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 550201.5444 | 0 | 11798.9179 | 77644.7368 | 10228.4211 | 25571.0526 | 0 | 229623.4679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-15 | 1303094.3671 |  |  | 551747.2366 | 148599.2074 | 258105.2232 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 551747.2366 | 0 | 11813.0232 | 77884.8947 | 10265.3684 | 25663.4211 | 0 | 229677.6232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-16 | 1305077.7935 |  |  | 553292.9288 | 148982.7863 | 258159.3784 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 553292.9288 | 0 | 11827.1284 | 78125.0526 | 10302.3158 | 25755.7895 | 0 | 229731.7784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-17 | 1307061.2199 |  |  | 554838.621 | 149366.3653 | 258213.5337 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 554838.621 | 0 | 11841.2337 | 78365.2105 | 10339.2632 | 25848.1579 | 0 | 229785.9337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-18 | 1309044.6463 |  |  | 556384.3131 | 149749.9442 | 258267.6889 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 556384.3131 | 0 | 11855.3389 | 78605.3684 | 10376.2105 | 25940.5263 | 0 | 229840.0889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-19 | 1311028.0727 |  |  | 557930.0053 | 150133.5232 | 258321.8442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 557930.0053 | 0 | 11869.4442 | 78845.5263 | 10413.1579 | 26032.8947 | 0 | 229894.2442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-20 | 1313011.4991 |  |  | 559475.6975 | 150517.1021 | 258375.9995 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 559475.6975 | 0 | 11883.5495 | 79085.6842 | 10450.1053 | 26125.2632 | 0 | 229948.3995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-21 | 1314994.9255 |  |  | 561021.3897 | 150900.6811 | 258430.1547 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 561021.3897 | 0 | 11897.6547 | 79325.8421 | 10487.0526 | 26217.6316 | 0 | 230002.5547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-22 | 1316978.3519 |  |  | 562567.0819 | 151284.26 | 258484.31 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 562567.0819 | 0 | 11911.76 | 79566 | 10524 | 26310 | 0 | 230056.71 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-23 | 1318961.7783 |  |  | 564112.774 | 151667.8389 | 258538.4653 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 564112.774 | 0 | 11925.8653 | 79806.1579 | 10560.9474 | 26402.3684 | 0 | 230110.8653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-24 | 1320945.2046 |  |  | 565658.4662 | 152051.4179 | 258592.6205 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 565658.4662 | 0 | 11939.9705 | 80046.3158 | 10597.8947 | 26494.7368 | 0 | 230165.0205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-25 | 1322928.631 |  |  | 567204.1584 | 152434.9968 | 258646.7758 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 567204.1584 | 0 | 11954.0758 | 80286.4737 | 10634.8421 | 26587.1053 | 0 | 230219.1758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-26 | 1324912.0574 |  |  | 568749.8506 | 152818.5758 | 258700.9311 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 568749.8506 | 0 | 11968.1811 | 80526.6316 | 10671.7895 | 26679.4737 | 0 | 230273.3311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-27 | 1326895.4838 |  |  | 570295.5428 | 153202.1547 | 258755.0863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 570295.5428 | 0 | 11982.2863 | 80766.7895 | 10708.7368 | 26771.8421 | 0 | 230327.4863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-28 | 1328878.9102 |  |  | 571841.235 | 153585.7337 | 258809.2416 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 571841.235 | 0 | 11996.3916 | 81006.9474 | 10745.6842 | 26864.2105 | 0 | 230381.6416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-29 | 1330862.3366 |  |  | 573386.9271 | 153969.3126 | 258863.3968 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 573386.9271 | 0 | 12010.4968 | 81247.1053 | 10782.6316 | 26956.5789 | 0 | 230435.7968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-30 | 1332845.763 |  |  | 574932.6193 | 154352.8916 | 258917.5521 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 574932.6193 | 0 | 12024.6021 | 81487.2632 | 10819.5789 | 27048.9474 | 0 | 230489.9521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-03-31 | 1334829.1894 |  |  | 576478.3115 | 154736.4705 | 258971.7074 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 576478.3115 | 0 | 12038.7074 | 81727.4211 | 10856.5263 | 27141.3158 | 0 | 230544.1074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-01 | 1336812.6158 |  |  | 578024.0037 | 155120.0495 | 259025.8626 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 578024.0037 | 0 | 12052.8126 | 81967.5789 | 10893.4737 | 27233.6842 | 0 | 230598.2626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-02 | 1338796.0422 |  |  | 579569.6959 | 155503.6284 | 259080.0179 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 579569.6959 | 0 | 12066.9179 | 82207.7368 | 10930.4211 | 27326.0526 | 0 | 230652.4179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-03 | 1340779.4686 |  |  | 581115.388 | 155887.2074 | 259134.1732 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 581115.388 | 0 | 12081.0232 | 82447.8947 | 10967.3684 | 27418.4211 | 0 | 230706.5732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-04 | 1342762.895 |  |  | 582661.0802 | 156270.7863 | 259188.3284 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 582661.0802 | 0 | 12095.1284 | 82688.0526 | 11004.3158 | 27510.7895 | 0 | 230760.7284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-05 | 1344746.3214 |  |  | 584206.7724 | 156654.3653 | 259242.4837 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 584206.7724 | 0 | 12109.2337 | 82928.2105 | 11041.2632 | 27603.1579 | 0 | 230814.8837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-06 | 1346729.7477 |  |  | 585752.4646 | 157037.9442 | 259296.6389 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 585752.4646 | 0 | 12123.3389 | 83168.3684 | 11078.2105 | 27695.5263 | 0 | 230869.0389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-07 | 1348713.1741 |  |  | 587298.1568 | 157421.5232 | 259350.7942 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 587298.1568 | 0 | 12137.4442 | 83408.5263 | 11115.1579 | 27787.8947 | 0 | 230923.1942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-08 | 1350696.6005 |  |  | 588843.849 | 157805.1021 | 259404.9495 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 588843.849 | 0 | 12151.5495 | 83648.6842 | 11152.1053 | 27880.2632 | 0 | 230977.3495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-09 | 1352680.0269 |  |  | 590389.5411 | 158188.6811 | 259459.1047 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 590389.5411 | 0 | 12165.6547 | 83888.8421 | 11189.0526 | 27972.6316 | 0 | 231031.5047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-10 | 1354663.4533 |  |  | 591935.2333 | 158572.26 | 259513.26 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 591935.2333 | 0 | 12179.76 | 84129 | 11226 | 28065 | 0 | 231085.66 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-11 | 1356646.8797 |  |  | 593480.9255 | 158955.8389 | 259567.4153 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 593480.9255 | 0 | 12193.8653 | 84369.1579 | 11262.9474 | 28157.3684 | 0 | 231139.8153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-12 | 1358630.3061 |  |  | 595026.6177 | 159339.4179 | 259621.5705 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 595026.6177 | 0 | 12207.9705 | 84609.3158 | 11299.8947 | 28249.7368 | 0 | 231193.9705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-13 | 1360613.7325 |  |  | 596572.3099 | 159722.9968 | 259675.7258 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 596572.3099 | 0 | 12222.0758 | 84849.4737 | 11336.8421 | 28342.1053 | 0 | 231248.1258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-14 | 1362597.1589 |  |  | 598118.002 | 160106.5758 | 259729.8811 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 598118.002 | 0 | 12236.1811 | 85089.6316 | 11373.7895 | 28434.4737 | 0 | 231302.2811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-15 | 1364580.5853 |  |  | 599663.6942 | 160490.1547 | 259784.0363 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 599663.6942 | 0 | 12250.2863 | 85329.7895 | 11410.7368 | 28526.8421 | 0 | 231356.4363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-16 | 1366564.0117 |  |  | 601209.3864 | 160873.7337 | 259838.1916 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 601209.3864 | 0 | 12264.3916 | 85569.9474 | 11447.6842 | 28619.2105 | 0 | 231410.5916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-17 | 1368547.4381 |  |  | 602755.0786 | 161257.3126 | 259892.3468 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 602755.0786 | 0 | 12278.4968 | 85810.1053 | 11484.6316 | 28711.5789 | 0 | 231464.7468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-18 | 1370530.8645 |  |  | 604300.7708 | 161640.8916 | 259946.5021 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 604300.7708 | 0 | 12292.6021 | 86050.2632 | 11521.5789 | 28803.9474 | 0 | 231518.9021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-19 | 1372514.2908 |  |  | 605846.463 | 162024.4705 | 260000.6574 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 605846.463 | 0 | 12306.7074 | 86290.4211 | 11558.5263 | 28896.3158 | 0 | 231573.0574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-20 | 1374497.7172 |  |  | 607392.1551 | 162408.0495 | 260054.8126 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 607392.1551 | 0 | 12320.8126 | 86530.5789 | 11595.4737 | 28988.6842 | 0 | 231627.2126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-21 | 1376481.1436 |  |  | 608937.8473 | 162791.6284 | 260108.9679 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 608937.8473 | 0 | 12334.9179 | 86770.7368 | 11632.4211 | 29081.0526 | 0 | 231681.3679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-22 | 1378464.57 |  |  | 610483.5395 | 163175.2074 | 260163.1232 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 610483.5395 | 0 | 12349.0232 | 87010.8947 | 11669.3684 | 29173.4211 | 0 | 231735.5232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-23 | 1380447.9964 |  |  | 612029.2317 | 163558.7863 | 260217.2784 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 612029.2317 | 0 | 12363.1284 | 87251.0526 | 11706.3158 | 29265.7895 | 0 | 231789.6784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-24 | 1382431.4228 |  |  | 613574.9239 | 163942.3653 | 260271.4337 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 613574.9239 | 0 | 12377.2337 | 87491.2105 | 11743.2632 | 29358.1579 | 0 | 231843.8337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-25 | 1384414.8492 |  |  | 615120.616 | 164325.9442 | 260325.5889 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 615120.616 | 0 | 12391.3389 | 87731.3684 | 11780.2105 | 29450.5263 | 0 | 231897.9889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-26 | 1386398.2756 |  |  | 616666.3082 | 164709.5232 | 260379.7442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 616666.3082 | 0 | 12405.4442 | 87971.5263 | 11817.1579 | 29542.8947 | 0 | 231952.1442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-27 | 1388381.702 |  |  | 618212.0004 | 165093.1021 | 260433.8995 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 618212.0004 | 0 | 12419.5495 | 88211.6842 | 11854.1053 | 29635.2632 | 0 | 232006.2995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-28 | 1390365.1284 |  |  | 619757.6926 | 165476.6811 | 260488.0547 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 619757.6926 | 0 | 12433.6547 | 88451.8421 | 11891.0526 | 29727.6316 | 0 | 232060.4547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-29 | 1392348.5548 |  |  | 621303.3848 | 165860.26 | 260542.21 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 621303.3848 | 0 | 12447.76 | 88692 | 11928 | 29820 | 0 | 232114.61 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-04-30 | 1394331.9812 |  |  | 622849.077 | 166243.8389 | 260596.3653 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 622849.077 | 0 | 12461.8653 | 88932.1579 | 11964.9474 | 29912.3684 | 0 | 232168.7653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-01 | 1396315.4076 |  |  | 624394.7691 | 166627.4179 | 260650.5205 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 624394.7691 | 0 | 12475.9705 | 89172.3158 | 12001.8947 | 30004.7368 | 0 | 232222.9205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-02 | 1398298.8339 |  |  | 625940.4613 | 167010.9968 | 260704.6758 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 625940.4613 | 0 | 12490.0758 | 89412.4737 | 12038.8421 | 30097.1053 | 0 | 232277.0758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-03 | 1400282.2603 |  |  | 627486.1535 | 167394.5758 | 260758.8311 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 627486.1535 | 0 | 12504.1811 | 89652.6316 | 12075.7895 | 30189.4737 | 0 | 232331.2311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-04 | 1402265.6867 |  |  | 629031.8457 | 167778.1547 | 260812.9863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 629031.8457 | 0 | 12518.2863 | 89892.7895 | 12112.7368 | 30281.8421 | 0 | 232385.3863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-05 | 1404249.1131 |  |  | 630577.5379 | 168161.7337 | 260867.1416 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 630577.5379 | 0 | 12532.3916 | 90132.9474 | 12149.6842 | 30374.2105 | 0 | 232439.5416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-06 | 1406232.5395 |  |  | 632123.23 | 168545.3126 | 260921.2968 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 632123.23 | 0 | 12546.4968 | 90373.1053 | 12186.6316 | 30466.5789 | 0 | 232493.6968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-07 | 1408215.9659 |  |  | 633668.9222 | 168928.8916 | 260975.4521 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 633668.9222 | 0 | 12560.6021 | 90613.2632 | 12223.5789 | 30558.9474 | 0 | 232547.8521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-08 | 1410199.3923 |  |  | 635214.6144 | 169312.4705 | 261029.6074 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 635214.6144 | 0 | 12574.7074 | 90853.4211 | 12260.5263 | 30651.3158 | 0 | 232602.0074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-09 | 1412182.8187 |  |  | 636760.3066 | 169696.0495 | 261083.7626 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 636760.3066 | 0 | 12588.8126 | 91093.5789 | 12297.4737 | 30743.6842 | 0 | 232656.1626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-10 | 1414166.2451 |  |  | 638305.9988 | 170079.6284 | 261137.9179 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 638305.9988 | 0 | 12602.9179 | 91333.7368 | 12334.4211 | 30836.0526 | 0 | 232710.3179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-11 | 1416149.6715 |  |  | 639851.691 | 170463.2074 | 261192.0732 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 639851.691 | 0 | 12617.0232 | 91573.8947 | 12371.3684 | 30928.4211 | 0 | 232764.4732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-12 | 1418133.0979 |  |  | 641397.3831 | 170846.7863 | 261246.2284 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 641397.3831 | 0 | 12631.1284 | 91814.0526 | 12408.3158 | 31020.7895 | 0 | 232818.6284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-13 | 1420116.5243 |  |  | 642943.0753 | 171230.3653 | 261300.3837 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 642943.0753 | 0 | 12645.2337 | 92054.2105 | 12445.2632 | 31113.1579 | 0 | 232872.7837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-14 | 1422099.9507 |  |  | 644488.7675 | 171613.9442 | 261354.5389 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 644488.7675 | 0 | 12659.3389 | 92294.3684 | 12482.2105 | 31205.5263 | 0 | 232926.9389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-15 | 1424083.377 |  |  | 646034.4597 | 171997.5232 | 261408.6942 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 646034.4597 | 0 | 12673.4442 | 92534.5263 | 12519.1579 | 31297.8947 | 0 | 232981.0942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-16 | 1426066.8034 |  |  | 647580.1519 | 172381.1021 | 261462.8495 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 647580.1519 | 0 | 12687.5495 | 92774.6842 | 12556.1053 | 31390.2632 | 0 | 233035.2495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-17 | 1428050.2298 |  |  | 649125.844 | 172764.6811 | 261517.0047 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 649125.844 | 0 | 12701.6547 | 93014.8421 | 12593.0526 | 31482.6316 | 0 | 233089.4047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-18 | 1430033.6562 |  |  | 650671.5362 | 173148.26 | 261571.16 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 650671.5362 | 0 | 12715.76 | 93255 | 12630 | 31575 | 0 | 233143.56 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-19 | 1432017.0826 |  |  | 652217.2284 | 173531.8389 | 261625.3153 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 652217.2284 | 0 | 12729.8653 | 93495.1579 | 12666.9474 | 31667.3684 | 0 | 233197.7153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-20 | 1434000.509 |  |  | 653762.9206 | 173915.4179 | 261679.4705 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 653762.9206 | 0 | 12743.9705 | 93735.3158 | 12703.8947 | 31759.7368 | 0 | 233251.8705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-21 | 1435983.9354 |  |  | 655308.6128 | 174298.9968 | 261733.6258 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 655308.6128 | 0 | 12758.0758 | 93975.4737 | 12740.8421 | 31852.1053 | 0 | 233306.0258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-22 | 1437967.3618 |  |  | 656854.305 | 174682.5758 | 261787.7811 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 656854.305 | 0 | 12772.1811 | 94215.6316 | 12777.7895 | 31944.4737 | 0 | 233360.1811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-23 | 1439950.7882 |  |  | 658399.9971 | 175066.1547 | 261841.9363 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 658399.9971 | 0 | 12786.2863 | 94455.7895 | 12814.7368 | 32036.8421 | 0 | 233414.3363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-24 | 1441934.2146 |  |  | 659945.6893 | 175449.7337 | 261896.0916 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 659945.6893 | 0 | 12800.3916 | 94695.9474 | 12851.6842 | 32129.2105 | 0 | 233468.4916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-25 | 1443917.641 |  |  | 661491.3815 | 175833.3126 | 261950.2468 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 661491.3815 | 0 | 12814.4968 | 94936.1053 | 12888.6316 | 32221.5789 | 0 | 233522.6468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-26 | 1445901.0674 |  |  | 663037.0737 | 176216.8916 | 262004.4021 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 663037.0737 | 0 | 12828.6021 | 95176.2632 | 12925.5789 | 32313.9474 | 0 | 233576.8021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-27 | 1447884.4938 |  |  | 664582.7659 | 176600.4705 | 262058.5574 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 664582.7659 | 0 | 12842.7074 | 95416.4211 | 12962.5263 | 32406.3158 | 0 | 233630.9574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-28 | 1449867.9201 |  |  | 666128.458 | 176984.0495 | 262112.7126 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 666128.458 | 0 | 12856.8126 | 95656.5789 | 12999.4737 | 32498.6842 | 0 | 233685.1126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-29 | 1451851.3465 |  |  | 667674.1502 | 177367.6284 | 262166.8679 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 667674.1502 | 0 | 12870.9179 | 95896.7368 | 13036.4211 | 32591.0526 | 0 | 233739.2679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-30 | 1453834.7729 |  |  | 669219.8424 | 177751.2074 | 262221.0232 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 669219.8424 | 0 | 12885.0232 | 96136.8947 | 13073.3684 | 32683.4211 | 0 | 233793.4232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-05-31 | 1455818.1993 |  |  | 670765.5346 | 178134.7863 | 262275.1784 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 670765.5346 | 0 | 12899.1284 | 96377.0526 | 13110.3158 | 32775.7895 | 0 | 233847.5784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-01 | 1457801.6257 |  |  | 672311.2268 | 178518.3653 | 262329.3337 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 672311.2268 | 0 | 12913.2337 | 96617.2105 | 13147.2632 | 32868.1579 | 0 | 233901.7337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-02 | 1459785.0521 |  |  | 673856.919 | 178901.9442 | 262383.4889 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 673856.919 | 0 | 12927.3389 | 96857.3684 | 13184.2105 | 32960.5263 | 0 | 233955.8889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-03 | 1461768.4785 |  |  | 675402.6111 | 179285.5232 | 262437.6442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 675402.6111 | 0 | 12941.4442 | 97097.5263 | 13221.1579 | 33052.8947 | 0 | 234010.0442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-04 | 1463751.9049 |  |  | 676948.3033 | 179669.1021 | 262491.7995 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 676948.3033 | 0 | 12955.5495 | 97337.6842 | 13258.1053 | 33145.2632 | 0 | 234064.1995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-05 | 1465735.3313 |  |  | 678493.9955 | 180052.6811 | 262545.9547 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 678493.9955 | 0 | 12969.6547 | 97577.8421 | 13295.0526 | 33237.6316 | 0 | 234118.3547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-06 | 1467718.7577 |  |  | 680039.6877 | 180436.26 | 262600.11 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 680039.6877 | 0 | 12983.76 | 97818 | 13332 | 33330 | 0 | 234172.51 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-07 | 1469702.1841 |  |  | 681585.3799 | 180819.8389 | 262654.2653 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 681585.3799 | 0 | 12997.8653 | 98058.1579 | 13368.9474 | 33422.3684 | 0 | 234226.6653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-08 | 1471685.6105 |  |  | 683131.072 | 181203.4179 | 262708.4205 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 683131.072 | 0 | 13011.9705 | 98298.3158 | 13405.8947 | 33514.7368 | 0 | 234280.8205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-09 | 1473669.0369 |  |  | 684676.7642 | 181586.9968 | 262762.5758 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 684676.7642 | 0 | 13026.0758 | 98538.4737 | 13442.8421 | 33607.1053 | 0 | 234334.9758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-10 | 1475652.4632 |  |  | 686222.4564 | 181970.5758 | 262816.7311 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 686222.4564 | 0 | 13040.1811 | 98778.6316 | 13479.7895 | 33699.4737 | 0 | 234389.1311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-11 | 1477635.8896 |  |  | 687768.1486 | 182354.1547 | 262870.8863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 687768.1486 | 0 | 13054.2863 | 99018.7895 | 13516.7368 | 33791.8421 | 0 | 234443.2863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-12 | 1479619.316 |  |  | 689313.8408 | 182737.7337 | 262925.0416 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 689313.8408 | 0 | 13068.3916 | 99258.9474 | 13553.6842 | 33884.2105 | 0 | 234497.4416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-13 | 1481602.7424 |  |  | 690859.533 | 183121.3126 | 262979.1968 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 690859.533 | 0 | 13082.4968 | 99499.1053 | 13590.6316 | 33976.5789 | 0 | 234551.5968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-14 | 1483586.1688 |  |  | 692405.2251 | 183504.8916 | 263033.3521 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 692405.2251 | 0 | 13096.6021 | 99739.2632 | 13627.5789 | 34068.9474 | 0 | 234605.7521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-15 | 1485569.5952 |  |  | 693950.9173 | 183888.4705 | 263087.5074 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 693950.9173 | 0 | 13110.7074 | 99979.4211 | 13664.5263 | 34161.3158 | 0 | 234659.9074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-16 | 1487553.0216 |  |  | 695496.6095 | 184272.0495 | 263141.6626 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 695496.6095 | 0 | 13124.8126 | 100219.5789 | 13701.4737 | 34253.6842 | 0 | 234714.0626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-17 | 1489536.448 |  |  | 697042.3017 | 184655.6284 | 263195.8179 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 697042.3017 | 0 | 13138.9179 | 100459.7368 | 13738.4211 | 34346.0526 | 0 | 234768.2179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-18 | 1491519.8744 |  |  | 698587.9939 | 185039.2074 | 263249.9732 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 698587.9939 | 0 | 13153.0232 | 100699.8947 | 13775.3684 | 34438.4211 | 0 | 234822.3732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-19 | 1493503.3008 |  |  | 700133.686 | 185422.7863 | 263304.1284 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 700133.686 | 0 | 13167.1284 | 100940.0526 | 13812.3158 | 34530.7895 | 0 | 234876.5284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-20 | 1495486.7272 |  |  | 701679.3782 | 185806.3653 | 263358.2837 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 701679.3782 | 0 | 13181.2337 | 101180.2105 | 13849.2632 | 34623.1579 | 0 | 234930.6837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-21 | 1497470.1536 |  |  | 703225.0704 | 186189.9442 | 263412.4389 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 703225.0704 | 0 | 13195.3389 | 101420.3684 | 13886.2105 | 34715.5263 | 0 | 234984.8389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-22 | 1499453.58 |  |  | 704770.7626 | 186573.5232 | 263466.5942 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 704770.7626 | 0 | 13209.4442 | 101660.5263 | 13923.1579 | 34807.8947 | 0 | 235038.9942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-23 | 1501437.0063 |  |  | 706316.4548 | 186957.1021 | 263520.7495 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 706316.4548 | 0 | 13223.5495 | 101900.6842 | 13960.1053 | 34900.2632 | 0 | 235093.1495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-24 | 1503420.4327 |  |  | 707862.147 | 187340.6811 | 263574.9047 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 707862.147 | 0 | 13237.6547 | 102140.8421 | 13997.0526 | 34992.6316 | 0 | 235147.3047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-25 | 1505403.8591 |  |  | 709407.8391 | 187724.26 | 263629.06 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 709407.8391 | 0 | 13251.76 | 102381 | 14034 | 35085 | 0 | 235201.46 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-26 | 1507387.2855 |  |  | 710953.5313 | 188107.8389 | 263683.2153 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 710953.5313 | 0 | 13265.8653 | 102621.1579 | 14070.9474 | 35177.3684 | 0 | 235255.6153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-27 | 1509370.7119 |  |  | 712499.2235 | 188491.4179 | 263737.3705 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 712499.2235 | 0 | 13279.9705 | 102861.3158 | 14107.8947 | 35269.7368 | 0 | 235309.7705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-28 | 1511354.1383 |  |  | 714044.9157 | 188874.9968 | 263791.5258 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 714044.9157 | 0 | 13294.0758 | 103101.4737 | 14144.8421 | 35362.1053 | 0 | 235363.9258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-29 | 1513337.5647 |  |  | 715590.6079 | 189258.5758 | 263845.6811 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 715590.6079 | 0 | 13308.1811 | 103341.6316 | 14181.7895 | 35454.4737 | 0 | 235418.0811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-06-30 | 1515320.9911 |  |  | 717136.3 | 189642.1547 | 263899.8363 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 717136.3 | 0 | 13322.2863 | 103581.7895 | 14218.7368 | 35546.8421 | 0 | 235472.2363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-01 | 1517304.4175 |  |  | 718681.9922 | 190025.7337 | 263953.9916 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 718681.9922 | 0 | 13336.3916 | 103821.9474 | 14255.6842 | 35639.2105 | 0 | 235526.3916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-02 | 1519287.8439 |  |  | 720227.6844 | 190409.3126 | 264008.1468 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 720227.6844 | 0 | 13350.4968 | 104062.1053 | 14292.6316 | 35731.5789 | 0 | 235580.5468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-03 | 1521271.2703 |  |  | 721773.3766 | 190792.8916 | 264062.3021 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 721773.3766 | 0 | 13364.6021 | 104302.2632 | 14329.5789 | 35823.9474 | 0 | 235634.7021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-04 | 1523254.6967 |  |  | 723319.0688 | 191176.4705 | 264116.4574 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 723319.0688 | 0 | 13378.7074 | 104542.4211 | 14366.5263 | 35916.3158 | 0 | 235688.8574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-05 | 1525238.1231 |  |  | 724864.761 | 191560.0495 | 264170.6126 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 724864.761 | 0 | 13392.8126 | 104782.5789 | 14403.4737 | 36008.6842 | 0 | 235743.0126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-06 | 1527221.5494 |  |  | 726410.4531 | 191943.6284 | 264224.7679 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 726410.4531 | 0 | 13406.9179 | 105022.7368 | 14440.4211 | 36101.0526 | 0 | 235797.1679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-07 | 1529204.9758 |  |  | 727956.1453 | 192327.2074 | 264278.9232 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 727956.1453 | 0 | 13421.0232 | 105262.8947 | 14477.3684 | 36193.4211 | 0 | 235851.3232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-08 | 1531188.4022 |  |  | 729501.8375 | 192710.7863 | 264333.0784 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 729501.8375 | 0 | 13435.1284 | 105503.0526 | 14514.3158 | 36285.7895 | 0 | 235905.4784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-09 | 1533171.8286 |  |  | 731047.5297 | 193094.3653 | 264387.2337 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 731047.5297 | 0 | 13449.2337 | 105743.2105 | 14551.2632 | 36378.1579 | 0 | 235959.6337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-10 | 1535155.255 |  |  | 732593.2219 | 193477.9442 | 264441.3889 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 732593.2219 | 0 | 13463.3389 | 105983.3684 | 14588.2105 | 36470.5263 | 0 | 236013.7889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-11 | 1537138.6814 |  |  | 734138.914 | 193861.5232 | 264495.5442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 734138.914 | 0 | 13477.4442 | 106223.5263 | 14625.1579 | 36562.8947 | 0 | 236067.9442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-12 | 1539122.1078 |  |  | 735684.6062 | 194245.1021 | 264549.6995 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 735684.6062 | 0 | 13491.5495 | 106463.6842 | 14662.1053 | 36655.2632 | 0 | 236122.0995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-13 | 1541105.5342 |  |  | 737230.2984 | 194628.6811 | 264603.8547 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 737230.2984 | 0 | 13505.6547 | 106703.8421 | 14699.0526 | 36747.6316 | 0 | 236176.2547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-14 | 1543088.9606 |  |  | 738775.9906 | 195012.26 | 264658.01 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 738775.9906 | 0 | 13519.76 | 106944 | 14736 | 36840 | 0 | 236230.41 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-15 | 1545072.387 |  |  | 740321.6828 | 195395.8389 | 264712.1653 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 740321.6828 | 0 | 13533.8653 | 107184.1579 | 14772.9474 | 36932.3684 | 0 | 236284.5653 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-16 | 1547055.8134 |  |  | 741867.375 | 195779.4179 | 264766.3205 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 741867.375 | 0 | 13547.9705 | 107424.3158 | 14809.8947 | 37024.7368 | 0 | 236338.7205 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-17 | 1549039.2398 |  |  | 743413.0671 | 196162.9968 | 264820.4758 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 743413.0671 | 0 | 13562.0758 | 107664.4737 | 14846.8421 | 37117.1053 | 0 | 236392.8758 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-18 | 1551022.6662 |  |  | 744958.7593 | 196546.5758 | 264874.6311 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 744958.7593 | 0 | 13576.1811 | 107904.6316 | 14883.7895 | 37209.4737 | 0 | 236447.0311 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-19 | 1553006.0925 |  |  | 746504.4515 | 196930.1547 | 264928.7863 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 746504.4515 | 0 | 13590.2863 | 108144.7895 | 14920.7368 | 37301.8421 | 0 | 236501.1863 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-20 | 1554989.5189 |  |  | 748050.1437 | 197313.7337 | 264982.9416 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 748050.1437 | 0 | 13604.3916 | 108384.9474 | 14957.6842 | 37394.2105 | 0 | 236555.3416 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-21 | 1556972.9453 |  |  | 749595.8359 | 197697.3126 | 265037.0968 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 749595.8359 | 0 | 13618.4968 | 108625.1053 | 14994.6316 | 37486.5789 | 0 | 236609.4968 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-22 | 1558956.3717 |  |  | 751141.528 | 198080.8916 | 265091.2521 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 751141.528 | 0 | 13632.6021 | 108865.2632 | 15031.5789 | 37578.9474 | 0 | 236663.6521 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-23 | 1560939.7981 |  |  | 752687.2202 | 198464.4705 | 265145.4074 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 752687.2202 | 0 | 13646.7074 | 109105.4211 | 15068.5263 | 37671.3158 | 0 | 236717.8074 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-24 | 1562923.2245 |  |  | 754232.9124 | 198848.0495 | 265199.5626 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 754232.9124 | 0 | 13660.8126 | 109345.5789 | 15105.4737 | 37763.6842 | 0 | 236771.9626 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-25 | 1564906.6509 |  |  | 755778.6046 | 199231.6284 | 265253.7179 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 755778.6046 | 0 | 13674.9179 | 109585.7368 | 15142.4211 | 37856.0526 | 0 | 236826.1179 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-26 | 1566890.0773 |  |  | 757324.2968 | 199615.2074 | 265307.8732 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 757324.2968 | 0 | 13689.0232 | 109825.8947 | 15179.3684 | 37948.4211 | 0 | 236880.2732 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-27 | 1568873.5037 |  |  | 758869.989 | 199998.7863 | 265362.0284 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 758869.989 | 0 | 13703.1284 | 110066.0526 | 15216.3158 | 38040.7895 | 0 | 236934.4284 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-28 | 1570856.9301 |  |  | 760415.6811 | 200382.3653 | 265416.1837 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 760415.6811 | 0 | 13717.2337 | 110306.2105 | 15253.2632 | 38133.1579 | 0 | 236988.5837 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-29 | 1572840.3565 |  |  | 761961.3733 | 200765.9442 | 265470.3389 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 761961.3733 | 0 | 13731.3389 | 110546.3684 | 15290.2105 | 38225.5263 | 0 | 237042.7389 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-30 | 1574823.7829 |  |  | 763507.0655 | 201149.5232 | 265524.4942 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 763507.0655 | 0 | 13745.4442 | 110786.5263 | 15327.1579 | 38317.8947 | 0 | 237096.8942 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-07-31 | 1576807.2093 |  |  | 765052.7577 | 201533.1021 | 265578.6495 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 765052.7577 | 0 | 13759.5495 | 111026.6842 | 15364.1053 | 38410.2632 | 0 | 237151.0495 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-01 | 1578790.6356 |  |  | 766598.4499 | 201916.6811 | 265632.8047 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 766598.4499 | 0 | 13773.6547 | 111266.8421 | 15401.0526 | 38502.6316 | 0 | 237205.2047 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-02 | 1580774.062 |  |  | 768144.142 | 202300.26 | 265686.96 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 768144.142 | 0 | 13787.76 | 111507 | 15438 | 38595 | 0 | 237259.36 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-03 | 1582757.4884 |  |  | 769689.8342 | 202683.8389 | 265741.1153 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 769689.8342 | 0 | 13801.8653 | 111747.1579 | 15474.9474 | 38687.3684 | 0 | 237313.5153 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-04 | 1584740.9148 |  |  | 771235.5264 | 203067.4179 | 265795.2705 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 771235.5264 | 0 | 13815.9705 | 111987.3158 | 15511.8947 | 38779.7368 | 0 | 237367.6705 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-05 | 1586724.3412 |  |  | 772781.2186 | 203450.9968 | 265849.4258 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 772781.2186 | 0 | 13830.0758 | 112227.4737 | 15548.8421 | 38872.1053 | 0 | 237421.8258 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-06 | 1588707.7676 |  |  | 774326.9108 | 203834.5758 | 265903.5811 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 774326.9108 | 0 | 13844.1811 | 112467.6316 | 15585.7895 | 38964.4737 | 0 | 237475.9811 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-07 | 1590691.194 |  |  | 775872.603 | 204218.1547 | 265957.7363 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 775872.603 | 0 | 13858.2863 | 112707.7895 | 15622.7368 | 39056.8421 | 0 | 237530.1363 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-08 | 1592674.6204 |  |  | 777418.2951 | 204601.7337 | 266011.8916 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 777418.2951 | 0 | 13872.3916 | 112947.9474 | 15659.6842 | 39149.2105 | 0 | 237584.2916 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-09 | 1594658.0468 |  |  | 778963.9873 | 204985.3126 | 266066.0468 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 778963.9873 | 0 | 13886.4968 | 113188.1053 | 15696.6316 | 39241.5789 | 0 | 237638.4468 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-10 | 1596641.4732 |  |  | 780509.6795 | 205368.8916 | 266120.2021 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 780509.6795 | 0 | 13900.6021 | 113428.2632 | 15733.5789 | 39333.9474 | 0 | 237692.6021 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-11 | 1598624.8996 |  |  | 782055.3717 | 205752.4705 | 266174.3574 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 782055.3717 | 0 | 13914.7074 | 113668.4211 | 15770.5263 | 39426.3158 | 0 | 237746.7574 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-12 | 1600608.326 |  |  | 783601.0639 | 206136.0495 | 266228.5126 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 783601.0639 | 0 | 13928.8126 | 113908.5789 | 15807.4737 | 39518.6842 | 0 | 237800.9126 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-13 | 1602591.7524 |  |  | 785146.756 | 206519.6284 | 266282.6679 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 785146.756 | 0 | 13942.9179 | 114148.7368 | 15844.4211 | 39611.0526 | 0 | 237855.0679 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-14 | 1604575.1787 |  |  | 786692.4482 | 206903.2074 | 266336.8232 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 786692.4482 | 0 | 13957.0232 | 114388.8947 | 15881.3684 | 39703.4211 | 0 | 237909.2232 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-15 | 1606558.6051 |  |  | 788238.1404 | 207286.7863 | 266390.9784 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 788238.1404 | 0 | 13971.1284 | 114629.0526 | 15918.3158 | 39795.7895 | 0 | 237963.3784 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-16 | 1608542.0315 |  |  | 789783.8326 | 207670.3653 | 266445.1337 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 789783.8326 | 0 | 13985.2337 | 114869.2105 | 15955.2632 | 39888.1579 | 0 | 238017.5337 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-17 | 1610525.4579 |  |  | 791329.5248 | 208053.9442 | 266499.2889 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 791329.5248 | 0 | 13999.3389 | 115109.3684 | 15992.2105 | 39980.5263 | 0 | 238071.6889 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-18 | 1612508.8843 |  |  | 792875.217 | 208437.5232 | 266553.4442 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 792875.217 | 0 | 14013.4442 | 115349.5263 | 16029.1579 | 40072.8947 | 0 | 238125.8442 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-19 | 1614492.3107 |  |  | 794420.9091 | 208821.1021 | 266607.5995 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 794420.9091 | 0 | 14027.5495 | 115589.6842 | 16066.1053 | 40165.2632 | 0 | 238179.9995 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-20 | 1616475.7371 |  |  | 795966.6013 | 209204.6811 | 266661.7547 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 795966.6013 | 0 | 14041.6547 | 115829.8421 | 16103.0526 | 40257.6316 | 0 | 238234.1547 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-21 | 1618459.1635 |  |  | 797512.2935 | 209588.26 | 266715.91 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 797512.2935 | 0 | 14055.76 | 116070 | 16140 | 40350 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-22 | 1618459.1635 |  |  | 797512.2935 | 209588.26 | 266715.91 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 797512.2935 | 0 | 14055.76 | 116070 | 16140 | 40350 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-23 | 1618459.1635 |  |  | 797512.2935 | 209588.26 | 266715.91 | 51102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 797512.2935 | 0 | 14055.76 | 116070 | 16140 | 40350 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-24 | 1620851.6675 |  |  | 798972.0702 | 210127.0479 | 266715.91 | 51495.9394 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 798972.0702 | 0 | 14085.457 | 116400.9091 | 16190.9091 | 40477.2727 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 15643.9394 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-25 | 1623244.1715 |  |  | 800431.847 | 210665.8358 | 266715.91 | 51889.8788 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 800431.847 | 0 | 14115.1539 | 116731.8182 | 16241.8182 | 40604.5455 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16037.8788 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-26 | 1625636.6755 |  |  | 801891.6237 | 211204.6236 | 266715.91 | 52283.8182 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 801891.6237 | 0 | 14144.8509 | 117062.7273 | 16292.7273 | 40731.8182 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16431.8182 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-27 | 1628029.1796 |  |  | 803351.4005 | 211743.4115 | 266715.91 | 52677.7576 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 803351.4005 | 0 | 14174.5479 | 117393.6364 | 16343.6364 | 40859.0909 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 16825.7576 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-28 | 1630421.6836 |  |  | 804811.1772 | 212282.1994 | 266715.91 | 53071.697 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 804811.1772 | 0 | 14204.2448 | 117724.5455 | 16394.5455 | 40986.3636 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 17219.697 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-29 | 1632814.1876 |  |  | 806270.9539 | 212820.9873 | 266715.91 | 53465.6364 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 806270.9539 | 0 | 14233.9418 | 118055.4545 | 16445.4545 | 41113.6364 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 17613.6364 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-30 | 1635206.6916 |  |  | 807730.7307 | 213359.7752 | 266715.91 | 53859.5758 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 807730.7307 | 0 | 14263.6388 | 118386.3636 | 16496.3636 | 41240.9091 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 18007.5758 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-08-31 | 1637599.1956 |  |  | 809190.5074 | 213898.563 | 266715.91 | 54253.5152 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 809190.5074 | 0 | 14293.3358 | 118717.2727 | 16547.2727 | 41368.1818 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 18401.5152 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-01 | 1639991.6996 |  |  | 810650.2842 | 214437.3509 | 266715.91 | 54647.4545 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 810650.2842 | 0 | 14323.0327 | 119048.1818 | 16598.1818 | 41495.4545 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 18795.4545 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-02 | 1642384.2036 |  |  | 812110.0609 | 214976.1388 | 266715.91 | 55041.3939 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 812110.0609 | 0 | 14352.7297 | 119379.0909 | 16649.0909 | 41622.7273 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 19189.3939 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-03 | 1644776.7077 |  |  | 813569.8377 | 215514.9267 | 266715.91 | 55435.3333 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 813569.8377 | 0 | 14382.4267 | 119710 | 16700 | 41750 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 19583.3333 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-04 | 1647169.2117 |  |  | 815029.6144 | 216053.7145 | 266715.91 | 55829.2727 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 815029.6144 | 0 | 14412.1236 | 120040.9091 | 16750.9091 | 41877.2727 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 19977.2727 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-05 | 1649561.7157 |  |  | 816489.3911 | 216592.5024 | 266715.91 | 56223.2121 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 816489.3911 | 0 | 14441.8206 | 120371.8182 | 16801.8182 | 42004.5455 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 20371.2121 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-06 | 1651954.2197 |  |  | 817949.1679 | 217131.2903 | 266715.91 | 56617.1515 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 817949.1679 | 0 | 14471.5176 | 120702.7273 | 16852.7273 | 42131.8182 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 20765.1515 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-07 | 1654346.7237 |  |  | 819408.9446 | 217670.0782 | 266715.91 | 57011.0909 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 819408.9446 | 0 | 14501.2145 | 121033.6364 | 16903.6364 | 42259.0909 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 21159.0909 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-08 | 1656739.2277 |  |  | 820868.7214 | 218208.8661 | 266715.91 | 57405.0303 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 820868.7214 | 0 | 14530.9115 | 121364.5455 | 16954.5455 | 42386.3636 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 21553.0303 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-09 | 1659131.7317 |  |  | 822328.4981 | 218747.6539 | 266715.91 | 57798.9697 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 822328.4981 | 0 | 14560.6085 | 121695.4545 | 17005.4545 | 42513.6364 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 21946.9697 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-10 | 1661524.2358 |  |  | 823788.2748 | 219286.4418 | 266715.91 | 58192.9091 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 823788.2748 | 0 | 14590.3055 | 122026.3636 | 17056.3636 | 42640.9091 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 22340.9091 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-11 | 1663916.7398 |  |  | 825248.0516 | 219825.2297 | 266715.91 | 58586.8485 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 825248.0516 | 0 | 14620.0024 | 122357.2727 | 17107.2727 | 42768.1818 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 22734.8485 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-12 | 1666309.2438 |  |  | 826707.8283 | 220364.0176 | 266715.91 | 58980.7879 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 826707.8283 | 0 | 14649.6994 | 122688.1818 | 17158.1818 | 42895.4545 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 23128.7879 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-13 | 1668701.7478 |  |  | 828167.6051 | 220902.8055 | 266715.91 | 59374.7273 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 828167.6051 | 0 | 14679.3964 | 123019.0909 | 17209.0909 | 43022.7273 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 23522.7273 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-14 | 1671094.2518 |  |  | 829627.3818 | 221441.5933 | 266715.91 | 59768.6667 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 829627.3818 | 0 | 14709.0933 | 123350 | 17260 | 43150 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 23916.6667 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-15 | 1673486.7558 |  |  | 831087.1586 | 221980.3812 | 266715.91 | 60162.6061 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 831087.1586 | 0 | 14738.7903 | 123680.9091 | 17310.9091 | 43277.2727 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 24310.6061 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-16 | 1675879.2598 |  |  | 832546.9353 | 222519.1691 | 266715.91 | 60556.5455 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 832546.9353 | 0 | 14768.4873 | 124011.8182 | 17361.8182 | 43404.5455 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 24704.5455 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-17 | 1678271.7639 |  |  | 834006.712 | 223057.957 | 266715.91 | 60950.4848 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 834006.712 | 0 | 14798.1842 | 124342.7273 | 17412.7273 | 43531.8182 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25098.4848 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-18 | 1680664.2679 |  |  | 835466.4888 | 223596.7448 | 266715.91 | 61344.4242 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 835466.4888 | 0 | 14827.8812 | 124673.6364 | 17463.6364 | 43659.0909 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25492.4242 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-19 | 1683056.7719 |  |  | 836926.2655 | 224135.5327 | 266715.91 | 61738.3636 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 836926.2655 | 0 | 14857.5782 | 125004.5455 | 17514.5455 | 43786.3636 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 25886.3636 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-20 | 1685449.2759 |  |  | 838386.0423 | 224674.3206 | 266715.91 | 62132.303 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 838386.0423 | 0 | 14887.2752 | 125335.4545 | 17565.4545 | 43913.6364 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 26280.303 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-21 | 1687841.7799 |  |  | 839845.819 | 225213.1085 | 266715.91 | 62526.2424 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 839845.819 | 0 | 14916.9721 | 125666.3636 | 17616.3636 | 44040.9091 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 26674.2424 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-22 | 1690234.2839 |  |  | 841305.5957 | 225751.8964 | 266715.91 | 62920.1818 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 841305.5957 | 0 | 14946.6691 | 125997.2727 | 17667.2727 | 44168.1818 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27068.1818 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-23 | 1692626.7879 |  |  | 842765.3725 | 226290.6842 | 266715.91 | 63314.1212 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 842765.3725 | 0 | 14976.3661 | 126328.1818 | 17718.1818 | 44295.4545 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27462.1212 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-24 | 1695019.292 |  |  | 844225.1492 | 226829.4721 | 266715.91 | 63708.0606 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 844225.1492 | 0 | 15006.063 | 126659.0909 | 17769.0909 | 44422.7273 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 27856.0606 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0
2026-09-25 | 1697411.796 |  |  | 845684.926 | 227368.26 | 266715.91 | 64102 | 293540.7 | 40150 | 0 | 5662.8 | 0 | 0 | 166660 | 9360 | 0 | 0 | 4368 | 0 | 0 | 9909.9 | 13650 | 43780 | 0 | 0 | 28427.6 | 845684.926 | 0 | 15035.76 | 126990 | 17820 | 44550 | 0 | 238288.31 | 0 | 0 | 100 | 12602 | 6500 | 14050 | 28250 | 18450 | 4522.5 | 0 | 0 | 0 | 2600 | 0

## Cost Sum
Date | Planned Total Cost (Cumulative) | Actual Total Cost (Cumulative) | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Planned Total Cost (Daily) | Actual Total Cost (Daily) | Planned Labor (Daily) | Actual Labor (Daily) | Planned Travel&perdiem (Daily) | Actual Travel&perdiem (Daily) | Planned Parts&materials (Daily) | Actual Parts&materials (Daily) | Planned Outsource (Daily) | Actual Outsource (Daily) | Planned Equipment (Daily) | Actual Equipment (Daily)
2025-04-02 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 1891.7647 | 5000 | 1891.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 945.8824 | 5000 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
2025-04-04 | 2837.6471 | 5000 | 2837.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 3783.5294 | 5000 | 3783.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 4729.4118 | 5000 | 4729.4118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 5675.2941 | 6126.6 | 5675.2941 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 945.8824 | 1126.6 | 945.8824 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 6621.1765 | 7253.2 | 6621.1765 | 2253.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 945.8824 | 1126.6 | 945.8824 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 7567.0588 | 8379.8 | 7567.0588 | 3379.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 945.8824 | 1126.6 | 945.8824 | 1126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 8512.9412 | 9716.32 | 8512.9412 | 4506.4 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 5000 | 945.8824 | 1336.52 | 945.8824 | 1126.6 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 9458.8235 | 10879.95 | 9458.8235 | 5633 | 0 | 209.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 1163.63 | 945.8824 | 1126.6 | 0 | 0 | 0 | 37.03 | 0 | 0 | 0 | 0
2025-04-12 | 10404.7059 | 10897.95 | 10404.7059 | 5633 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 18 | 945.8824 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 11350.5882 | 10897.95 | 11350.5882 | 5633 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 12296.4706 | 11112.35 | 12296.4706 | 5847.4 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 214.4 | 945.8824 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 13242.3529 | 11326.75 | 13242.3529 | 6061.8 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 214.4 | 945.8824 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 14188.2353 | 11541.15 | 14188.2353 | 6276.2 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 214.4 | 945.8824 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 15134.1176 | 11755.55 | 15134.1176 | 6490.6 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 214.4 | 945.8824 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 16080 | 11969.95 | 16080 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 214.4 | 945.8824 | 214.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 17025.8824 | 11969.95 | 17025.8824 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 17971.7647 | 11969.95 | 17971.7647 | 6705 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 18917.6471 | 12352.1 | 18917.6471 | 7087.15 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 382.15 | 945.8824 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 19863.5294 | 12734.25 | 19863.5294 | 7469.3 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 382.15 | 945.8824 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 20809.4118 | 13116.4 | 20809.4118 | 7851.45 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 382.15 | 945.8824 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 21755.2941 | 13498.55 | 21755.2941 | 8233.6 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 382.15 | 945.8824 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 22701.1765 | 13880.7 | 22701.1765 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 382.15 | 945.8824 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 23647.0588 | 13880.7 | 23647.0588 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 24592.9412 | 13880.7 | 24592.9412 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 25538.8235 | 13880.7 | 25538.8235 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 26484.7059 | 13880.7 | 26484.7059 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 27430.5882 | 13880.7 | 27430.5882 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 28376.4706 | 13880.7 | 28376.4706 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 29322.3529 | 13880.7 | 29322.3529 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 30268.2353 | 13880.7 | 30268.2353 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 31214.1176 | 13880.7 | 31214.1176 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 32160 | 13880.7 | 32160 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 33105.8824 | 13880.7 | 33105.8824 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 34051.7647 | 13880.7 | 34051.7647 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 34997.6471 | 13880.7 | 34997.6471 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 35943.5294 | 13880.7 | 35943.5294 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 36889.4118 | 13880.7 | 36889.4118 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 37835.2941 | 13880.7 | 37835.2941 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 38781.1765 | 13880.7 | 38781.1765 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 39727.0588 | 13880.7 | 39727.0588 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 40672.9412 | 13880.7 | 40672.9412 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 41618.8235 | 13880.7 | 41618.8235 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 42564.7059 | 13880.7 | 42564.7059 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 43510.5882 | 13880.7 | 43510.5882 | 8615.75 | 0 | 227.92 | 0 | 37.03 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 44456.4706 | 14644.31 | 44456.4706 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 945.8824 | 763.61 | 945.8824 | 0 | 0 | 0 | 0 | 763.61 | 0 | 0 | 0 | 0
2025-05-19 | 45402.3529 | 14644.31 | 45402.3529 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 46348.2353 | 14644.31 | 46348.2353 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 47294.1176 | 14644.31 | 47294.1176 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 48240 | 14644.31 | 48240 | 8615.75 | 0 | 227.92 | 0 | 800.64 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 49185.8824 | 14823.29 | 49185.8824 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 178.98 | 945.8824 | 0 | 0 | 0 | 0 | 178.98 | 0 | 0 | 0 | 0
2025-05-24 | 50131.7647 | 14823.29 | 50131.7647 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 51077.6471 | 14823.29 | 51077.6471 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 52023.5294 | 14823.29 | 52023.5294 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 52969.4118 | 14823.29 | 52969.4118 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 53915.2941 | 14823.29 | 53915.2941 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 54861.1765 | 14823.29 | 54861.1765 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 55807.0588 | 14823.29 | 55807.0588 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 56752.9412 | 14823.29 | 56752.9412 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 57698.8235 | 14823.29 | 57698.8235 | 8615.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 58644.7059 | 15252.09 | 58644.7059 | 9044.55 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 428.8 | 945.8824 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 59590.5882 | 15680.89 | 59590.5882 | 9473.35 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 428.8 | 945.8824 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 60536.4706 | 16109.69 | 60536.4706 | 9902.15 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 428.8 | 945.8824 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 61482.3529 | 16538.49 | 61482.3529 | 10330.95 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 428.8 | 945.8824 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 62428.2353 | 16967.29 | 62428.2353 | 10759.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 428.8 | 945.8824 | 428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 63374.1176 | 16967.29 | 63374.1176 | 10759.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 64320 | 16967.29 | 64320 | 10759.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 65265.8824 | 17074.49 | 65265.8824 | 10866.95 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 107.2 | 945.8824 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 66211.7647 | 17181.69 | 66211.7647 | 10974.15 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 107.2 | 945.8824 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 67157.6471 | 17288.89 | 67157.6471 | 11081.35 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 107.2 | 945.8824 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 68103.5294 | 17396.09 | 68103.5294 | 11188.55 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 107.2 | 945.8824 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 69049.4118 | 17503.29 | 69049.4118 | 11295.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 107.2 | 945.8824 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 69995.2941 | 17503.29 | 69995.2941 | 11295.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 70941.1765 | 17503.29 | 70941.1765 | 11295.75 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 71887.0588 | 17885.44 | 71887.0588 | 11677.9 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 382.15 | 945.8824 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 72832.9412 | 18267.59 | 72832.9412 | 12060.05 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 382.15 | 945.8824 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 73778.8235 | 18649.74 | 73778.8235 | 12442.2 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 382.15 | 945.8824 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 74724.7059 | 19031.89 | 74724.7059 | 12824.35 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 382.15 | 945.8824 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 75670.5882 | 19414.04 | 75670.5882 | 13206.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 382.15 | 945.8824 | 382.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 76616.4706 | 19414.04 | 76616.4706 | 13206.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 77562.3529 | 19414.04 | 77562.3529 | 13206.5 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 78508.2353 | 19521.24 | 78508.2353 | 13313.7 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 107.2 | 945.8824 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 79454.1176 | 19628.44 | 79454.1176 | 13420.9 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 107.2 | 945.8824 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 80400 | 19735.64 | 80400 | 13528.1 | 0 | 227.92 | 0 | 979.62 | 0 | 0 | 0 | 5000 | 945.8824 | 107.2 | 945.8824 | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-26 | 82618.3227 | 19842.84 | 80518.8731 | 13635.3 | 138.2843 | 227.92 | 705.7078 | 979.62 | 318.3575 | 0 | 937.1 | 5000 | 2218.3227 | 107.2 | 118.8731 | 107.2 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-06-27 | 84836.6454 | 19950.04 | 80637.7462 | 13742.5 | 276.5686 | 227.92 | 1411.4156 | 979.62 | 636.715 | 0 | 1874.2 | 5000 | 2218.3227 | 107.2 | 118.8731 | 107.2 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-06-28 | 87054.9681 | 19950.04 | 80756.6194 | 13742.5 | 414.8529 | 227.92 | 2117.1233 | 979.62 | 955.0725 | 0 | 2811.3 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-06-29 | 89273.2908 | 19950.04 | 80875.4925 | 13742.5 | 553.1373 | 227.92 | 2822.8311 | 979.62 | 1273.43 | 0 | 3748.4 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-06-30 | 91491.6135 | 20399.19 | 80994.3656 | 14191.65 | 691.4216 | 227.92 | 3528.5389 | 979.62 | 1591.7874 | 0 | 4685.5 | 5000 | 2218.3227 | 449.15 | 118.8731 | 449.15 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-01 | 93709.9362 | 20848.34 | 81113.2387 | 14640.8 | 829.7059 | 227.92 | 4234.2467 | 979.62 | 1910.1449 | 0 | 5622.6 | 5000 | 2218.3227 | 449.15 | 118.8731 | 449.15 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-02 | 95928.2589 | 21297.49 | 81232.1118 | 15089.95 | 967.9902 | 227.92 | 4939.9544 | 979.62 | 2228.5024 | 0 | 6559.7 | 5000 | 2218.3227 | 449.15 | 118.8731 | 449.15 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-03 | 98146.5816 | 21746.64 | 81350.9849 | 15539.1 | 1106.2745 | 227.92 | 5645.6622 | 979.62 | 2546.8599 | 0 | 7496.8 | 5000 | 2218.3227 | 449.15 | 118.8731 | 449.15 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-04 | 100364.9043 | 22195.79 | 81469.8581 | 15988.25 | 1244.5588 | 227.92 | 6351.37 | 979.62 | 2865.2174 | 0 | 8433.9 | 5000 | 2218.3227 | 449.15 | 118.8731 | 449.15 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-05 | 102583.227 | 22195.79 | 81588.7312 | 15988.25 | 1382.8432 | 227.92 | 7057.0778 | 979.62 | 3183.5749 | 0 | 9371 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-06 | 104801.5497 | 22195.79 | 81707.6043 | 15988.25 | 1521.1275 | 227.92 | 7762.7856 | 979.62 | 3501.9324 | 0 | 10308.1 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-07 | 107019.8724 | 22597.79 | 81826.4774 | 16390.25 | 1659.4118 | 227.92 | 8468.4933 | 979.62 | 3820.2899 | 0 | 11245.2 | 5000 | 2218.3227 | 402 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-08 | 109238.1951 | 22999.79 | 81945.3505 | 16792.25 | 1797.6961 | 227.92 | 9174.2011 | 979.62 | 4138.6473 | 0 | 12182.3 | 5000 | 2218.3227 | 402 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-09 | 111456.5178 | 23401.79 | 82064.2237 | 17194.25 | 1935.9804 | 227.92 | 9879.9089 | 979.62 | 4457.0048 | 0 | 13119.4 | 5000 | 2218.3227 | 402 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-10 | 113674.8405 | 23803.79 | 82183.0968 | 17596.25 | 2074.2647 | 227.92 | 10585.6167 | 979.62 | 4775.3623 | 0 | 14056.5 | 5000 | 2218.3227 | 402 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-11 | 115893.1632 | 24205.79 | 82301.9699 | 17998.25 | 2212.549 | 227.92 | 11291.3244 | 979.62 | 5093.7198 | 0 | 14993.6 | 5000 | 2218.3227 | 402 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-12 | 118111.4859 | 24205.79 | 82420.843 | 17998.25 | 2350.8334 | 227.92 | 11997.0322 | 979.62 | 5412.0773 | 0 | 15930.7 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-13 | 120329.8086 | 24205.79 | 82539.7161 | 17998.25 | 2489.1177 | 227.92 | 12702.74 | 979.62 | 5730.4348 | 0 | 16867.8 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-14 | 122548.1313 | 26149.69 | 82658.5892 | 18400.25 | 2627.402 | 1769.82 | 13408.4478 | 979.62 | 6048.7923 | 0 | 17804.9 | 5000 | 2218.3227 | 1943.9 | 118.8731 | 402 | 138.2843 | 1541.9 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-15 | 124766.454 | 26551.69 | 82777.4624 | 18802.25 | 2765.6863 | 1769.82 | 14114.1556 | 979.62 | 6367.1498 | 0 | 18742 | 5000 | 2218.3227 | 402 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-16 | 126984.7767 | 26953.69 | 82896.3355 | 19204.25 | 2903.9706 | 1769.82 | 14819.8633 | 979.62 | 6685.5072 | 0 | 19679.1 | 5000 | 2218.3227 | 402 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-17 | 129203.0994 | 27420.14 | 83015.2086 | 19606.25 | 3042.2549 | 1834.27 | 15525.5711 | 979.62 | 7003.8647 | 0 | 20616.2 | 5000 | 2218.3227 | 466.45 | 118.8731 | 402 | 138.2843 | 64.45 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-18 | 131421.4221 | 27849.28 | 83134.0817 | 20008.25 | 3180.5393 | 1861.41 | 16231.2789 | 979.62 | 7322.2222 | 0 | 21553.3 | 5000 | 2218.3227 | 429.14 | 118.8731 | 402 | 138.2843 | 27.14 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-19 | 133639.7448 | 27879.28 | 83252.9548 | 20008.25 | 3318.8236 | 1891.41 | 16936.9867 | 979.62 | 7640.5797 | 0 | 22490.4 | 5000 | 2218.3227 | 30 | 118.8731 | 0 | 138.2843 | 30 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-20 | 135858.0675 | 27879.28 | 83371.828 | 20008.25 | 3457.1079 | 1891.41 | 17642.6944 | 979.62 | 7958.9372 | 0 | 23427.5 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-21 | 138076.3902 | 28281.28 | 83490.7011 | 20410.25 | 3595.3922 | 1891.41 | 18348.4022 | 979.62 | 8277.2947 | 0 | 24364.6 | 5000 | 2218.3227 | 402 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-22 | 140294.7129 | 29183.28 | 83609.5742 | 20812.25 | 3733.6765 | 1891.41 | 19054.11 | 979.62 | 8595.6522 | 500 | 25301.7 | 5000 | 2218.3227 | 902 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 500 | 937.1 | 0
2025-07-23 | 142513.0356 | 29585.28 | 83728.4473 | 21214.25 | 3871.9608 | 1891.41 | 19759.8178 | 979.62 | 8914.0097 | 500 | 26238.8 | 5000 | 2218.3227 | 402 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-24 | 144731.3583 | 29987.28 | 83847.3204 | 21616.25 | 4010.2452 | 1891.41 | 20465.5256 | 979.62 | 9232.3671 | 500 | 27175.9 | 5000 | 2218.3227 | 402 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-25 | 146949.681 | 30389.28 | 83966.1935 | 22018.25 | 4148.5295 | 1891.41 | 21171.2333 | 979.62 | 9550.7246 | 500 | 28113 | 5000 | 2218.3227 | 402 | 118.8731 | 402 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-26 | 149168.0037 | 30389.28 | 84085.0667 | 22018.25 | 4286.8138 | 1891.41 | 21876.9411 | 979.62 | 9869.0821 | 500 | 29050.1 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-27 | 151386.3264 | 30389.28 | 84203.9398 | 22018.25 | 4425.0981 | 1891.41 | 22582.6489 | 979.62 | 10187.4396 | 500 | 29987.2 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-28 | 153604.6491 | 30737.68 | 84322.8129 | 22366.65 | 4563.3824 | 1891.41 | 23288.3567 | 979.62 | 10505.7971 | 500 | 30924.3 | 5000 | 2218.3227 | 348.4 | 118.8731 | 348.4 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-29 | 155822.9718 | 31086.08 | 84441.686 | 22715.05 | 4701.6667 | 1891.41 | 23994.0644 | 979.62 | 10824.1546 | 500 | 31861.4 | 5000 | 2218.3227 | 348.4 | 118.8731 | 348.4 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-30 | 158041.2945 | 31434.48 | 84560.5591 | 23063.45 | 4839.951 | 1891.41 | 24699.7722 | 979.62 | 11142.5121 | 500 | 32798.5 | 5000 | 2218.3227 | 348.4 | 118.8731 | 348.4 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-07-31 | 160259.6172 | 31782.88 | 84679.4323 | 23411.85 | 4978.2354 | 1891.41 | 25405.48 | 979.62 | 11460.8696 | 500 | 33735.6 | 5000 | 2218.3227 | 348.4 | 118.8731 | 348.4 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-01 | 162477.9399 | 32131.28 | 84798.3054 | 23760.25 | 5116.5197 | 1891.41 | 26111.1878 | 979.62 | 11779.2271 | 500 | 34672.7 | 5000 | 2218.3227 | 348.4 | 118.8731 | 348.4 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-02 | 164696.2626 | 32131.28 | 84917.1785 | 23760.25 | 5254.804 | 1891.41 | 26816.8956 | 979.62 | 12097.5845 | 500 | 35609.8 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-03 | 166914.5853 | 32131.28 | 85036.0516 | 23760.25 | 5393.0883 | 1891.41 | 27522.6033 | 979.62 | 12415.942 | 500 | 36546.9 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-04 | 169132.908 | 33768.43 | 85154.9247 | 24028.25 | 5531.3726 | 1891.41 | 28228.3111 | 2348.77 | 12734.2995 | 500 | 37484 | 5000 | 2218.3227 | 1637.15 | 118.8731 | 268 | 138.2843 | 0 | 705.7078 | 1369.15 | 318.3575 | 0 | 937.1 | 0
2025-08-05 | 171351.2307 | 34036.43 | 85273.7978 | 24296.25 | 5669.6569 | 1891.41 | 28934.0189 | 2348.77 | 13052.657 | 500 | 38421.1 | 5000 | 2218.3227 | 268 | 118.8731 | 268 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-06 | 173569.5534 | 34304.43 | 85392.671 | 24564.25 | 5807.9413 | 1891.41 | 29639.7267 | 2348.77 | 13371.0145 | 500 | 39358.2 | 5000 | 2218.3227 | 268 | 118.8731 | 268 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-07 | 175787.8761 | 35523.3 | 85511.5441 | 24832.25 | 5946.2256 | 1891.41 | 30345.4344 | 3299.64 | 13689.372 | 500 | 40295.3 | 5000 | 2218.3227 | 1218.87 | 118.8731 | 268 | 138.2843 | 0 | 705.7078 | 950.87 | 318.3575 | 0 | 937.1 | 0
2025-08-08 | 178006.1988 | 35791.3 | 85630.4172 | 25100.25 | 6084.5099 | 1891.41 | 31051.1422 | 3299.64 | 14007.7295 | 500 | 41232.4 | 5000 | 2218.3227 | 268 | 118.8731 | 268 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-09 | 180224.5215 | 35791.3 | 85749.2903 | 25100.25 | 6222.7942 | 1891.41 | 31756.85 | 3299.64 | 14326.087 | 500 | 42169.5 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-10 | 182442.8442 | 35791.3 | 85868.1634 | 25100.25 | 6361.0785 | 1891.41 | 32462.5578 | 3299.64 | 14644.4444 | 500 | 43106.6 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-11 | 184661.1669 | 36272.59 | 85987.0366 | 25314.65 | 6499.3628 | 1891.41 | 33168.2656 | 3566.53 | 14962.8019 | 500 | 44043.7 | 5000 | 2218.3227 | 481.29 | 118.8731 | 214.4 | 138.2843 | 0 | 705.7078 | 266.89 | 318.3575 | 0 | 937.1 | 0
2025-08-12 | 186879.4896 | 36486.99 | 86105.9097 | 25529.05 | 6637.6471 | 1891.41 | 33873.9733 | 3566.53 | 15281.1594 | 500 | 44980.8 | 5000 | 2218.3227 | 214.4 | 118.8731 | 214.4 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-13 | 189097.8123 | 36701.39 | 86224.7828 | 25743.45 | 6775.9315 | 1891.41 | 34579.6811 | 3566.53 | 15599.5169 | 500 | 45917.9 | 5000 | 2218.3227 | 214.4 | 118.8731 | 214.4 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-14 | 191316.135 | 36915.79 | 86343.6559 | 25957.85 | 6914.2158 | 1891.41 | 35285.3889 | 3566.53 | 15917.8744 | 500 | 46855 | 5000 | 2218.3227 | 214.4 | 118.8731 | 214.4 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-15 | 193534.4577 | 37130.19 | 86462.529 | 26172.25 | 7052.5001 | 1891.41 | 35991.0967 | 3566.53 | 16236.2319 | 500 | 47792.1 | 5000 | 2218.3227 | 214.4 | 118.8731 | 214.4 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-16 | 195752.7804 | 37130.19 | 86581.4022 | 26172.25 | 7190.7844 | 1891.41 | 36696.8044 | 3566.53 | 16554.5894 | 500 | 48729.2 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-17 | 197971.1031 | 37130.19 | 86700.2753 | 26172.25 | 7329.0687 | 1891.41 | 37402.5122 | 3566.53 | 16872.9469 | 500 | 49666.3 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-18 | 200189.4258 | 37666.19 | 86819.1484 | 26708.25 | 7467.353 | 1891.41 | 38108.22 | 3566.53 | 17191.3043 | 500 | 50603.4 | 5000 | 2218.3227 | 536 | 118.8731 | 536 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-19 | 202407.7485 | 50711.55 | 86938.0215 | 27244.25 | 7605.6374 | 1891.41 | 38813.9278 | 16075.89 | 17509.6618 | 500 | 51540.5 | 5000 | 2218.3227 | 13045.36 | 118.8731 | 536 | 138.2843 | 0 | 705.7078 | 12509.36 | 318.3575 | 0 | 937.1 | 0
2025-08-20 | 204626.0712 | 51386.36 | 87056.8946 | 27780.25 | 7743.9217 | 2030.22 | 39519.6356 | 16075.89 | 17828.0193 | 500 | 52477.6 | 5000 | 2218.3227 | 674.81 | 118.8731 | 536 | 138.2843 | 138.81 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-21 | 206844.3939 | 51922.36 | 87175.7677 | 28316.25 | 7882.206 | 2030.22 | 40225.3433 | 16075.89 | 18146.3768 | 500 | 53414.7 | 5000 | 2218.3227 | 536 | 118.8731 | 536 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-22 | 209062.7166 | 52558.36 | 87294.6409 | 28852.25 | 8020.4903 | 2130.22 | 40931.0511 | 16075.89 | 18464.7343 | 500 | 54351.8 | 5000 | 2218.3227 | 636 | 118.8731 | 536 | 138.2843 | 100 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-23 | 211281.0393 | 52558.36 | 87413.514 | 28852.25 | 8158.7746 | 2130.22 | 41636.7589 | 16075.89 | 18783.0918 | 500 | 55288.9 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-24 | 213499.362 | 52558.36 | 87532.3871 | 28852.25 | 8297.0589 | 2130.22 | 42342.4667 | 16075.89 | 19101.4493 | 500 | 56226 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-25 | 215717.6847 | 54392.92 | 87651.2602 | 29952.05 | 8435.3433 | 2130.22 | 43048.1744 | 16795.65 | 19419.8068 | 515 | 57163.1 | 5000 | 2218.3227 | 1834.56 | 118.8731 | 1099.8 | 138.2843 | 0 | 705.7078 | 719.76 | 318.3575 | 15 | 937.1 | 0
2025-08-26 | 217936.0074 | 58242.72 | 87770.1333 | 31051.85 | 8573.6276 | 2130.22 | 43753.8822 | 16795.65 | 19738.1643 | 3265 | 58100.2 | 5000 | 2218.3227 | 3849.8 | 118.8731 | 1099.8 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 2750 | 937.1 | 0
2025-08-27 | 220154.3301 | 59342.52 | 87889.0065 | 32151.65 | 8711.9119 | 2130.22 | 44459.59 | 16795.65 | 20056.5217 | 3265 | 59037.3 | 5000 | 2218.3227 | 1099.8 | 118.8731 | 1099.8 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-28 | 222372.6528 | 60442.32 | 88007.8796 | 33251.45 | 8850.1962 | 2130.22 | 45165.2978 | 16795.65 | 20374.8792 | 3265 | 59974.4 | 5000 | 2218.3227 | 1099.8 | 118.8731 | 1099.8 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-29 | 224590.9755 | 61542.12 | 88126.7527 | 34351.25 | 8988.4805 | 2130.22 | 45871.0056 | 16795.65 | 20693.2367 | 3265 | 60911.5 | 5000 | 2218.3227 | 1099.8 | 118.8731 | 1099.8 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-30 | 226809.2982 | 61542.12 | 88245.6258 | 34351.25 | 9126.7648 | 2130.22 | 46576.7133 | 16795.65 | 21011.5942 | 3265 | 61848.6 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-08-31 | 229027.6209 | 61542.12 | 88364.4989 | 34351.25 | 9265.0491 | 2130.22 | 47282.4211 | 16795.65 | 21329.9517 | 3265 | 62785.7 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-01 | 231245.9436 | 62286.07 | 88483.372 | 35095.2 | 9403.3335 | 2130.22 | 47988.1289 | 16795.65 | 21648.3092 | 3265 | 63722.8 | 5000 | 2218.3227 | 743.95 | 118.8731 | 743.95 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-02 | 233464.2663 | 66154.82 | 88602.2452 | 35839.15 | 9541.6178 | 2130.22 | 48693.8367 | 19920.45 | 21966.6667 | 3265 | 64659.9 | 5000 | 2218.3227 | 3868.75 | 118.8731 | 743.95 | 138.2843 | 0 | 705.7078 | 3124.8 | 318.3575 | 0 | 937.1 | 0
2025-09-03 | 235682.589 | 66898.77 | 88721.1183 | 36583.1 | 9679.9021 | 2130.22 | 49399.5444 | 19920.45 | 22285.0242 | 3265 | 65597 | 5000 | 2218.3227 | 743.95 | 118.8731 | 743.95 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-04 | 237900.9117 | 68329.42 | 88839.9914 | 37327.05 | 9818.1864 | 2130.22 | 50105.2522 | 19920.45 | 22603.3816 | 3951.7 | 66534.1 | 5000 | 2218.3227 | 1430.65 | 118.8731 | 743.95 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 686.7 | 937.1 | 0
2025-09-05 | 240119.2344 | 69073.37 | 88958.8645 | 38071 | 9956.4707 | 2130.22 | 50810.96 | 19920.45 | 22921.7391 | 3951.7 | 67471.2 | 5000 | 2218.3227 | 743.95 | 118.8731 | 743.95 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-06 | 242337.5571 | 69073.37 | 89077.7376 | 38071 | 10094.755 | 2130.22 | 51516.6678 | 19920.45 | 23240.0966 | 3951.7 | 68408.3 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-07 | 244555.8798 | 69073.37 | 89196.6108 | 38071 | 10233.0394 | 2130.22 | 52222.3756 | 19920.45 | 23558.4541 | 3951.7 | 69345.4 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-08 | 246774.2025 | 69576.12 | 89315.4839 | 38573.75 | 10371.3237 | 2130.22 | 52928.0833 | 19920.45 | 23876.8116 | 3951.7 | 70282.5 | 5000 | 2218.3227 | 502.75 | 118.8731 | 502.75 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-09 | 248992.5252 | 70721.23 | 89434.357 | 39076.5 | 10509.608 | 2130.22 | 53633.7911 | 20562.81 | 24195.1691 | 3951.7 | 71219.6 | 5000 | 2218.3227 | 1145.11 | 118.8731 | 502.75 | 138.2843 | 0 | 705.7078 | 642.36 | 318.3575 | 0 | 937.1 | 0
2025-09-10 | 251210.8479 | 71223.98 | 89553.2301 | 39579.25 | 10647.8923 | 2130.22 | 54339.4989 | 20562.81 | 24513.5266 | 3951.7 | 72156.7 | 5000 | 2218.3227 | 502.75 | 118.8731 | 502.75 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-11 | 253429.1706 | 71726.73 | 89672.1032 | 40082 | 10786.1766 | 2130.22 | 55045.2067 | 20562.81 | 24831.8841 | 3951.7 | 73093.8 | 5000 | 2218.3227 | 502.75 | 118.8731 | 502.75 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-12 | 255647.4933 | 86455.42 | 89790.9763 | 40584.75 | 10924.4609 | 2241.16 | 55750.9144 | 20562.81 | 25150.2415 | 18066.7 | 74030.9 | 5000 | 2218.3227 | 14728.69 | 118.8731 | 502.75 | 138.2843 | 110.94 | 705.7078 | 0 | 318.3575 | 14115 | 937.1 | 0
2025-09-13 | 257865.816 | 86455.42 | 89909.8495 | 40584.75 | 11062.7452 | 2241.16 | 56456.6222 | 20562.81 | 25468.599 | 18066.7 | 74968 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-14 | 260084.1387 | 86455.42 | 90028.7226 | 40584.75 | 11201.0296 | 2241.16 | 57162.33 | 20562.81 | 25786.9565 | 18066.7 | 75905.1 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-15 | 262302.4614 | 88867.295 | 90147.5957 | 42546.625 | 11339.3139 | 2691.16 | 57868.0378 | 20562.81 | 26105.314 | 18066.7 | 76842.2 | 5000 | 2218.3227 | 2411.875 | 118.8731 | 1961.875 | 138.2843 | 450 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-16 | 264520.7841 | 90829.17 | 90266.4688 | 44508.5 | 11477.5982 | 2691.16 | 58573.7456 | 20562.81 | 26423.6715 | 18066.7 | 77779.3 | 5000 | 2218.3227 | 1961.875 | 118.8731 | 1961.875 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-17 | 266739.1068 | 92791.045 | 90385.3419 | 46470.375 | 11615.8825 | 2691.16 | 59279.4533 | 20562.81 | 26742.029 | 18066.7 | 78716.4 | 5000 | 2218.3227 | 1961.875 | 118.8731 | 1961.875 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-18 | 268957.4295 | 94752.92 | 90504.2151 | 48432.25 | 11754.1668 | 2691.16 | 59985.1611 | 20562.81 | 27060.3865 | 18066.7 | 79653.5 | 5000 | 2218.3227 | 1961.875 | 118.8731 | 1961.875 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-19 | 271175.7522 | 96714.795 | 90623.0882 | 50394.125 | 11892.4511 | 2691.16 | 60690.8689 | 20562.81 | 27378.744 | 18066.7 | 80590.6 | 5000 | 2218.3227 | 1961.875 | 118.8731 | 1961.875 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-20 | 273394.0749 | 96714.795 | 90741.9613 | 50394.125 | 12030.7355 | 2691.16 | 61396.5767 | 20562.81 | 27697.1014 | 18066.7 | 81527.7 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-21 | 275612.3976 | 96714.795 | 90860.8344 | 50394.125 | 12169.0198 | 2691.16 | 62102.2844 | 20562.81 | 28015.4589 | 18066.7 | 82464.8 | 5000 | 2218.3227 | 0 | 118.8731 | 0 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 0 | 937.1 | 0
2025-09-22 | 277830.7203 | 100014.37 | 90979.7075 | 51446.2 | 12307.3041 | 2991.16 | 62807.9922 | 20562.81 | 28333.8164 | 20014.2 | 83401.9 | 5000 | 2218.3227 | 3299.575 | 118.8731 | 1052.075 | 138.2843 | 300 | 705.7078 | 0 | 318.3575 | 1947.5 | 937.1 | 0
2025-09-23 | 280049.043 | 102203.965 | 91098.5806 | 52498.275 | 12445.5884 | 2991.16 | 63513.7 | 20562.81 | 28652.1739 | 21151.72 | 84339 | 5000 | 2218.3227 | 2189.595 | 118.8731 | 1052.075 | 138.2843 | 0 | 705.7078 | 0 | 318.3575 | 1137.52 | 937.1 | 0
2025-09-24 | 280049.043 | 116032.98 | 91098.5806 | 53550.35 | 12445.5884 | 2991.16 | 63513.7 | 23165.94 | 28652.1739 | 31325.53 | 84339 | 5000 | 0 | 13829.015 | 0 | 1052.075 | 0 | 0 | 0 | 2603.13 | 0 | 10173.81 | 0 | 0
2025-09-25 | 280049.043 | 117085.055 | 91098.5806 | 54602.425 | 12445.5884 | 2991.16 | 63513.7 | 23165.94 | 28652.1739 | 31325.53 | 84339 | 5000 | 0 | 1052.075 | 0 | 1052.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-26 | 280049.043 | 118137.13 | 91098.5806 | 55654.5 | 12445.5884 | 2991.16 | 63513.7 | 23165.94 | 28652.1739 | 31325.53 | 84339 | 5000 | 0 | 1052.075 | 0 | 1052.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-27 | 280049.043 | 118137.13 | 91098.5806 | 55654.5 | 12445.5884 | 2991.16 | 63513.7 | 23165.94 | 28652.1739 | 31325.53 | 84339 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-28 | 280049.043 | 118137.13 | 91098.5806 | 55654.5 | 12445.5884 | 2991.16 | 63513.7 | 23165.94 | 28652.1739 | 31325.53 | 84339 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-29 | 285529.0229 | 120864.255 | 94337.9597 | 56981.625 | 13451.8732 | 4391.16 | 64326.5779 | 23165.94 | 28836.99 | 31325.53 | 84575.6221 | 5000 | 5479.9799 | 2727.125 | 3239.379 | 1327.125 | 1006.2848 | 1400 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-09-30 | 291009.0028 | 122191.38 | 97577.3387 | 58308.75 | 14458.1581 | 4391.16 | 65139.4559 | 23165.94 | 29021.806 | 31325.53 | 84812.2441 | 5000 | 5479.9799 | 1327.125 | 3239.379 | 1327.125 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-01 | 296488.9827 | 123518.505 | 100816.7177 | 59635.875 | 15464.4429 | 4391.16 | 65952.3338 | 23165.94 | 29206.6221 | 31325.53 | 85048.8662 | 5000 | 5479.9799 | 1327.125 | 3239.379 | 1327.125 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-02 | 301968.9627 | 124845.63 | 104056.0968 | 60963 | 16470.7278 | 4391.16 | 66765.2117 | 23165.94 | 29391.4381 | 31325.53 | 85285.4883 | 5000 | 5479.9799 | 1327.125 | 3239.379 | 1327.125 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-03 | 307448.9426 | 126672.755 | 107295.4758 | 62290.125 | 17477.0126 | 4891.16 | 67578.0896 | 23165.94 | 29576.2542 | 31325.53 | 85522.1104 | 5000 | 5479.9799 | 1827.125 | 3239.379 | 1327.125 | 1006.2848 | 500 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-04 | 312928.9225 | 126672.755 | 110534.8548 | 62290.125 | 18483.2974 | 4891.16 | 68390.9676 | 23165.94 | 29761.0702 | 31325.53 | 85758.7324 | 5000 | 5479.9799 | 0 | 3239.379 | 0 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-05 | 318408.9024 | 126672.755 | 113774.2339 | 62290.125 | 19489.5823 | 4891.16 | 69203.8455 | 23165.94 | 29945.8863 | 31325.53 | 85995.3545 | 5000 | 5479.9799 | 0 | 3239.379 | 0 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-06 | 323888.8824 | 128329.505 | 117013.6129 | 63946.875 | 20495.8671 | 4891.16 | 70016.7234 | 23165.94 | 30130.7023 | 31325.53 | 86231.9766 | 5000 | 5479.9799 | 1656.75 | 3239.379 | 1656.75 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-07 | 329368.8623 | 129986.255 | 120252.9919 | 65603.625 | 21502.152 | 4891.16 | 70829.6013 | 23165.94 | 30315.5184 | 31325.53 | 86468.5987 | 5000 | 5479.9799 | 1656.75 | 3239.379 | 1656.75 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-08 | 334848.8422 | 131643.005 | 123492.371 | 67260.375 | 22508.4368 | 4891.16 | 71642.4793 | 23165.94 | 30500.3344 | 31325.53 | 86705.2207 | 5000 | 5479.9799 | 1656.75 | 3239.379 | 1656.75 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-09 | 340328.8221 | 133299.755 | 126731.75 | 68917.125 | 23514.7216 | 4891.16 | 72455.3572 | 23165.94 | 30685.1505 | 31325.53 | 86941.8428 | 5000 | 5479.9799 | 1656.75 | 3239.379 | 1656.75 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-10 | 345808.8021 | 134956.505 | 129971.129 | 70573.875 | 24521.0065 | 4891.16 | 73268.2351 | 23165.94 | 30869.9666 | 31325.53 | 87178.4649 | 5000 | 5479.9799 | 1656.75 | 3239.379 | 1656.75 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-11 | 351288.782 | 134956.505 | 133210.5081 | 70573.875 | 25527.2913 | 4891.16 | 74081.113 | 23165.94 | 31054.7826 | 31325.53 | 87415.087 | 5000 | 5479.9799 | 0 | 3239.379 | 0 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-12 | 356768.7619 | 134956.505 | 136449.8871 | 70573.875 | 26533.5761 | 4891.16 | 74893.991 | 23165.94 | 31239.5987 | 31325.53 | 87651.709 | 5000 | 5479.9799 | 0 | 3239.379 | 0 | 1006.2848 | 0 | 812.8779 | 0 | 184.8161 | 0 | 236.6221 | 0
2025-10-13 | 362248.7418 |  | 139689.2661 |  | 27539.861 |  | 75706.8689 |  | 31424.4147 |  | 87888.3311 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-14 | 367728.7217 |  | 142928.6452 |  | 28546.1458 |  | 76519.7468 |  | 31609.2308 |  | 88124.9532 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-15 | 373208.7017 |  | 146168.0242 |  | 29552.4307 |  | 77332.6247 |  | 31794.0468 |  | 88361.5753 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-16 | 378688.6816 |  | 149407.4032 |  | 30558.7155 |  | 78145.5027 |  | 31978.8629 |  | 88598.1973 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-17 | 384168.6615 |  | 152646.7823 |  | 31565.0003 |  | 78958.3806 |  | 32163.6789 |  | 88834.8194 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-18 | 389648.6414 |  | 155886.1613 |  | 32571.2852 |  | 79771.2585 |  | 32348.495 |  | 89071.4415 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-19 | 395128.6214 |  | 159125.5403 |  | 33577.57 |  | 80584.1365 |  | 32533.311 |  | 89308.0635 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-20 | 400608.6013 |  | 162364.9194 |  | 34583.8548 |  | 81397.0144 |  | 32718.1271 |  | 89544.6856 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-21 | 406088.5812 |  | 165604.2984 |  | 35590.1397 |  | 82209.8923 |  | 32902.9431 |  | 89781.3077 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-22 | 411568.5611 |  | 168843.6774 |  | 36596.4245 |  | 83022.7702 |  | 33087.7592 |  | 90017.9298 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-23 | 417048.5411 |  | 172083.0565 |  | 37602.7094 |  | 83835.6482 |  | 33272.5753 |  | 90254.5518 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-24 | 422528.521 |  | 175322.4355 |  | 38608.9942 |  | 84648.5261 |  | 33457.3913 |  | 90491.1739 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-25 | 428008.5009 |  | 178561.8145 |  | 39615.279 |  | 85461.404 |  | 33642.2074 |  | 90727.796 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-26 | 433488.4808 |  | 181801.1935 |  | 40621.5639 |  | 86274.2819 |  | 33827.0234 |  | 90964.4181 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-27 | 438968.4608 |  | 185040.5726 |  | 41627.8487 |  | 87087.1599 |  | 34011.8395 |  | 91201.0401 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-28 | 444448.4407 |  | 188279.9516 |  | 42634.1336 |  | 87900.0378 |  | 34196.6555 |  | 91437.6622 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-29 | 449928.4206 |  | 191519.3306 |  | 43640.4184 |  | 88712.9157 |  | 34381.4716 |  | 91674.2843 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-30 | 455408.4005 |  | 194758.7097 |  | 44646.7032 |  | 89525.7936 |  | 34566.2876 |  | 91910.9064 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-10-31 | 460888.3805 |  | 197998.0887 |  | 45652.9881 |  | 90338.6716 |  | 34751.1037 |  | 92147.5284 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-01 | 466368.3604 |  | 201237.4677 |  | 46659.2729 |  | 91151.5495 |  | 34935.9197 |  | 92384.1505 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-02 | 471848.3403 |  | 204476.8468 |  | 47665.5577 |  | 91964.4274 |  | 35120.7358 |  | 92620.7726 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-03 | 477328.3202 |  | 207716.2258 |  | 48671.8426 |  | 92777.3054 |  | 35305.5518 |  | 92857.3946 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-04 | 482808.3002 |  | 210955.6048 |  | 49678.1274 |  | 93590.1833 |  | 35490.3679 |  | 93094.0167 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-05 | 488288.2801 |  | 214194.9839 |  | 50684.4123 |  | 94403.0612 |  | 35675.1839 |  | 93330.6388 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-06 | 493768.26 |  | 217434.3629 |  | 51690.6971 |  | 95215.9391 |  | 35860 |  | 93567.2609 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-07 | 499248.2399 |  | 220673.7419 |  | 52696.9819 |  | 96028.8171 |  | 36044.8161 |  | 93803.8829 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-08 | 504728.2199 |  | 223913.121 |  | 53703.2668 |  | 96841.695 |  | 36229.6321 |  | 94040.505 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-09 | 510208.1998 |  | 227152.5 |  | 54709.5516 |  | 97654.5729 |  | 36414.4482 |  | 94277.1271 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-10 | 515688.1797 |  | 230391.879 |  | 55715.8365 |  | 98467.4508 |  | 36599.2642 |  | 94513.7492 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-11 | 521168.1596 |  | 233631.2581 |  | 56722.1213 |  | 99280.3288 |  | 36784.0803 |  | 94750.3712 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-12 | 526648.1395 |  | 236870.6371 |  | 57728.4061 |  | 100093.2067 |  | 36968.8963 |  | 94986.9933 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-13 | 532128.1195 |  | 240110.0161 |  | 58734.691 |  | 100906.0846 |  | 37153.7124 |  | 95223.6154 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-14 | 537608.0994 |  | 243349.3952 |  | 59740.9758 |  | 101718.9625 |  | 37338.5284 |  | 95460.2375 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-15 | 543088.0793 |  | 246588.7742 |  | 60747.2606 |  | 102531.8405 |  | 37523.3445 |  | 95696.8595 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-16 | 548568.0592 |  | 249828.1532 |  | 61753.5455 |  | 103344.7184 |  | 37708.1605 |  | 95933.4816 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-17 | 554048.0392 |  | 253067.5323 |  | 62759.8303 |  | 104157.5963 |  | 37892.9766 |  | 96170.1037 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-18 | 559528.0191 |  | 256306.9113 |  | 63766.1152 |  | 104970.4742 |  | 38077.7926 |  | 96406.7258 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-19 | 565007.999 |  | 259546.2903 |  | 64772.4 |  | 105783.3522 |  | 38262.6087 |  | 96643.3478 |  | 5479.9799 |  | 3239.379 |  | 1006.2848 |  | 812.8779 |  | 184.8161 |  | 236.6221
2025-11-20 | 568307.2954 |  | 261077.3122 |  | 65367.498 |  | 106462.411 |  | 38262.6087 |  | 97137.4655 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-11-21 | 571606.5918 |  | 262608.3341 |  | 65962.5961 |  | 107141.4698 |  | 38262.6087 |  | 97631.5831 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-11-22 | 574905.8882 |  | 264139.3559 |  | 66557.6941 |  | 107820.5286 |  | 38262.6087 |  | 98125.7008 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-11-23 | 578205.1845 |  | 265670.3778 |  | 67152.7922 |  | 108499.5875 |  | 38262.6087 |  | 98619.8184 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-11-24 | 581504.4809 |  | 267201.3997 |  | 67747.8902 |  | 109178.6463 |  | 38262.6087 |  | 99113.9361 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-11-25 | 584803.7773 |  | 268732.4215 |  | 68342.9882 |  | 109857.7051 |  | 38262.6087 |  | 99608.0537 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-11-26 | 588103.0737 |  | 270263.4434 |  | 68938.0863 |  | 110536.7639 |  | 38262.6087 |  | 100102.1714 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-11-27 | 591402.37 |  | 271794.4653 |  | 69533.1843 |  | 111215.8228 |  | 38262.6087 |  | 100596.289 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-11-28 | 594701.6664 |  | 273325.4871 |  | 70128.2824 |  | 111894.8816 |  | 38262.6087 |  | 101090.4066 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-11-29 | 598000.9628 |  | 274856.509 |  | 70723.3804 |  | 112573.9404 |  | 38262.6087 |  | 101584.5243 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-11-30 | 601300.2592 |  | 276387.5309 |  | 71318.4784 |  | 113252.9992 |  | 38262.6087 |  | 102078.6419 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-01 | 604599.5556 |  | 277918.5527 |  | 71913.5765 |  | 113932.0581 |  | 38262.6087 |  | 102572.7596 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-02 | 607898.8519 |  | 279449.5746 |  | 72508.6745 |  | 114611.1169 |  | 38262.6087 |  | 103066.8772 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-03 | 611198.1483 |  | 280980.5965 |  | 73103.7725 |  | 115290.1757 |  | 38262.6087 |  | 103560.9949 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-04 | 614497.4447 |  | 282511.6183 |  | 73698.8706 |  | 115969.2345 |  | 38262.6087 |  | 104055.1125 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-05 | 617796.7411 |  | 284042.6402 |  | 74293.9686 |  | 116648.2934 |  | 38262.6087 |  | 104549.2302 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-06 | 621096.0374 |  | 285573.6621 |  | 74889.0667 |  | 117327.3522 |  | 38262.6087 |  | 105043.3478 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-07 | 624395.3338 |  | 287104.684 |  | 75484.1647 |  | 118006.411 |  | 38262.6087 |  | 105537.4655 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-08 | 627694.6302 |  | 288635.7058 |  | 76079.2627 |  | 118685.4698 |  | 38262.6087 |  | 106031.5831 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-09 | 630993.9266 |  | 290166.7277 |  | 76674.3608 |  | 119364.5286 |  | 38262.6087 |  | 106525.7008 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-10 | 634293.223 |  | 291697.7496 |  | 77269.4588 |  | 120043.5875 |  | 38262.6087 |  | 107019.8184 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-11 | 637592.5193 |  | 293228.7714 |  | 77864.5569 |  | 120722.6463 |  | 38262.6087 |  | 107513.9361 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-12 | 640891.8157 |  | 294759.7933 |  | 78459.6549 |  | 121401.7051 |  | 38262.6087 |  | 108008.0537 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-13 | 644191.1121 |  | 296290.8152 |  | 79054.7529 |  | 122080.7639 |  | 38262.6087 |  | 108502.1714 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-14 | 647490.4085 |  | 297821.837 |  | 79649.851 |  | 122759.8228 |  | 38262.6087 |  | 108996.289 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-15 | 650789.7048 |  | 299352.8589 |  | 80244.949 |  | 123438.8816 |  | 38262.6087 |  | 109490.4066 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-16 | 654089.0012 |  | 300883.8808 |  | 80840.0471 |  | 124117.9404 |  | 38262.6087 |  | 109984.5243 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-17 | 657388.2976 |  | 302414.9026 |  | 81435.1451 |  | 124796.9992 |  | 38262.6087 |  | 110478.6419 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-18 | 660687.594 |  | 303945.9245 |  | 82030.2431 |  | 125476.0581 |  | 38262.6087 |  | 110972.7596 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-19 | 663986.8904 |  | 305476.9464 |  | 82625.3412 |  | 126155.1169 |  | 38262.6087 |  | 111466.8772 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-20 | 667286.1867 |  | 307007.9682 |  | 83220.4392 |  | 126834.1757 |  | 38262.6087 |  | 111960.9949 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-21 | 670585.4831 |  | 308538.9901 |  | 83815.5373 |  | 127513.2345 |  | 38262.6087 |  | 112455.1125 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-22 | 673884.7795 |  | 310070.012 |  | 84410.6353 |  | 128192.2934 |  | 38262.6087 |  | 112949.2302 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-23 | 677184.0759 |  | 311601.0338 |  | 85005.7333 |  | 128871.3522 |  | 38262.6087 |  | 113443.3478 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-24 | 680483.3723 |  | 313132.0557 |  | 85600.8314 |  | 129550.411 |  | 38262.6087 |  | 113937.4655 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-25 | 683782.6686 |  | 314663.0776 |  | 86195.9294 |  | 130229.4698 |  | 38262.6087 |  | 114431.5831 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-26 | 687081.965 |  | 316194.0994 |  | 86791.0275 |  | 130908.5286 |  | 38262.6087 |  | 114925.7008 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-27 | 690381.2614 |  | 317725.1213 |  | 87386.1255 |  | 131587.5875 |  | 38262.6087 |  | 115419.8184 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-28 | 693680.5578 |  | 319256.1432 |  | 87981.2235 |  | 132266.6463 |  | 38262.6087 |  | 115913.9361 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-29 | 696979.8541 |  | 320787.1651 |  | 88576.3216 |  | 132945.7051 |  | 38262.6087 |  | 116408.0537 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-30 | 700279.1505 |  | 322318.1869 |  | 89171.4196 |  | 133624.7639 |  | 38262.6087 |  | 116902.1714 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2025-12-31 | 703578.4469 |  | 323849.2088 |  | 89766.5176 |  | 134303.8228 |  | 38262.6087 |  | 117396.289 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-01 | 706877.7433 |  | 325380.2307 |  | 90361.6157 |  | 134982.8816 |  | 38262.6087 |  | 117890.4066 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-02 | 710177.0397 |  | 326911.2525 |  | 90956.7137 |  | 135661.9404 |  | 38262.6087 |  | 118384.5243 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-03 | 713476.336 |  | 328442.2744 |  | 91551.8118 |  | 136340.9992 |  | 38262.6087 |  | 118878.6419 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-04 | 716775.6324 |  | 329973.2963 |  | 92146.9098 |  | 137020.0581 |  | 38262.6087 |  | 119372.7596 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-05 | 720074.9288 |  | 331504.3181 |  | 92742.0078 |  | 137699.1169 |  | 38262.6087 |  | 119866.8772 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-06 | 723374.2252 |  | 333035.34 |  | 93337.1059 |  | 138378.1757 |  | 38262.6087 |  | 120360.9949 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-07 | 726673.5215 |  | 334566.3619 |  | 93932.2039 |  | 139057.2345 |  | 38262.6087 |  | 120855.1125 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-08 | 729972.8179 |  | 336097.3837 |  | 94527.302 |  | 139736.2934 |  | 38262.6087 |  | 121349.2302 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-09 | 733272.1143 |  | 337628.4056 |  | 95122.4 |  | 140415.3522 |  | 38262.6087 |  | 121843.3478 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-10 | 736571.4107 |  | 339159.4275 |  | 95717.498 |  | 141094.411 |  | 38262.6087 |  | 122337.4655 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-11 | 739870.7071 |  | 340690.4493 |  | 96312.5961 |  | 141773.4698 |  | 38262.6087 |  | 122831.5831 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-12 | 743170.0034 |  | 342221.4712 |  | 96907.6941 |  | 142452.5286 |  | 38262.6087 |  | 123325.7008 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-13 | 746469.2998 |  | 343752.4931 |  | 97502.7922 |  | 143131.5875 |  | 38262.6087 |  | 123819.8184 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-14 | 749768.5962 |  | 345283.5149 |  | 98097.8902 |  | 143810.6463 |  | 38262.6087 |  | 124313.9361 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-15 | 753067.8926 |  | 346814.5368 |  | 98692.9882 |  | 144489.7051 |  | 38262.6087 |  | 124808.0537 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-16 | 756367.1889 |  | 348345.5587 |  | 99288.0863 |  | 145168.7639 |  | 38262.6087 |  | 125302.1714 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-17 | 759666.4853 |  | 349876.5806 |  | 99883.1843 |  | 145847.8228 |  | 38262.6087 |  | 125796.289 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-18 | 762965.7817 |  | 351407.6024 |  | 100478.2824 |  | 146526.8816 |  | 38262.6087 |  | 126290.4066 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-19 | 766265.0781 |  | 352938.6243 |  | 101073.3804 |  | 147205.9404 |  | 38262.6087 |  | 126784.5243 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-20 | 769564.3745 |  | 354469.6462 |  | 101668.4784 |  | 147884.9992 |  | 38262.6087 |  | 127278.6419 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-21 | 772863.6708 |  | 356000.668 |  | 102263.5765 |  | 148564.0581 |  | 38262.6087 |  | 127772.7596 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-22 | 776162.9672 |  | 357531.6899 |  | 102858.6745 |  | 149243.1169 |  | 38262.6087 |  | 128266.8772 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-23 | 779462.2636 |  | 359062.7118 |  | 103453.7725 |  | 149922.1757 |  | 38262.6087 |  | 128760.9949 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-24 | 782761.56 |  | 360593.7336 |  | 104048.8706 |  | 150601.2345 |  | 38262.6087 |  | 129255.1125 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-25 | 786060.8564 |  | 362124.7555 |  | 104643.9686 |  | 151280.2934 |  | 38262.6087 |  | 129749.2302 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-26 | 789360.1527 |  | 363655.7774 |  | 105239.0667 |  | 151959.3522 |  | 38262.6087 |  | 130243.3478 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-27 | 792659.4491 |  | 365186.7992 |  | 105834.1647 |  | 152638.411 |  | 38262.6087 |  | 130737.4655 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-28 | 795958.7455 |  | 366717.8211 |  | 106429.2627 |  | 153317.4698 |  | 38262.6087 |  | 131231.5831 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-29 | 799258.0419 |  | 368248.843 |  | 107024.3608 |  | 153996.5286 |  | 38262.6087 |  | 131725.7008 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-30 | 802557.3382 |  | 369779.8648 |  | 107619.4588 |  | 154675.5875 |  | 38262.6087 |  | 132219.8184 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-01-31 | 805856.6346 |  | 371310.8867 |  | 108214.5569 |  | 155354.6463 |  | 38262.6087 |  | 132713.9361 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-01 | 809155.931 |  | 372841.9086 |  | 108809.6549 |  | 156033.7051 |  | 38262.6087 |  | 133208.0537 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-02 | 812455.2274 |  | 374372.9304 |  | 109404.7529 |  | 156712.7639 |  | 38262.6087 |  | 133702.1714 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-03 | 815754.5238 |  | 375903.9523 |  | 109999.851 |  | 157391.8228 |  | 38262.6087 |  | 134196.289 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-04 | 819053.8201 |  | 377434.9742 |  | 110594.949 |  | 158070.8816 |  | 38262.6087 |  | 134690.4066 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-05 | 822353.1165 |  | 378965.996 |  | 111190.0471 |  | 158749.9404 |  | 38262.6087 |  | 135184.5243 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-06 | 825652.4129 |  | 380497.0179 |  | 111785.1451 |  | 159428.9992 |  | 38262.6087 |  | 135678.6419 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-07 | 828951.7093 |  | 382028.0398 |  | 112380.2431 |  | 160108.0581 |  | 38262.6087 |  | 136172.7596 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-08 | 832251.0056 |  | 383559.0617 |  | 112975.3412 |  | 160787.1169 |  | 38262.6087 |  | 136666.8772 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-09 | 835550.302 |  | 385090.0835 |  | 113570.4392 |  | 161466.1757 |  | 38262.6087 |  | 137160.9949 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-10 | 838849.5984 |  | 386621.1054 |  | 114165.5373 |  | 162145.2345 |  | 38262.6087 |  | 137655.1125 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-11 | 842148.8948 |  | 388152.1273 |  | 114760.6353 |  | 162824.2934 |  | 38262.6087 |  | 138149.2302 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-12 | 845448.1912 |  | 389683.1491 |  | 115355.7333 |  | 163503.3522 |  | 38262.6087 |  | 138643.3478 |  | 3299.2964 |  | 1531.0219 |  | 595.098 |  | 679.0588 |  | 0 |  | 494.1176
2026-02-13 | 847097.575 |  | 390971.2259 |  | 115675.3825 |  | 163545.0101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-14 | 848746.9588 |  | 392259.3028 |  | 115995.0316 |  | 163586.668 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-15 | 850396.3427 |  | 393547.3796 |  | 116314.6807 |  | 163628.3259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-16 | 852045.7265 |  | 394835.4564 |  | 116634.3298 |  | 163669.9838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-17 | 853695.1103 |  | 396123.5332 |  | 116953.9789 |  | 163711.6416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-18 | 855344.4942 |  | 397411.61 |  | 117273.6281 |  | 163753.2995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-19 | 856993.878 |  | 398699.6869 |  | 117593.2772 |  | 163794.9574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-20 | 858643.2618 |  | 399987.7637 |  | 117912.9263 |  | 163836.6153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-21 | 860292.6457 |  | 401275.8405 |  | 118232.5754 |  | 163878.2732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-22 | 861942.0295 |  | 402563.9173 |  | 118552.2246 |  | 163919.9311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-23 | 863591.4133 |  | 403851.9941 |  | 118871.8737 |  | 163961.589 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-24 | 865240.7972 |  | 405140.0709 |  | 119191.5228 |  | 164003.2469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-25 | 866890.181 |  | 406428.1478 |  | 119511.1719 |  | 164044.9048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-26 | 868539.5649 |  | 407716.2246 |  | 119830.8211 |  | 164086.5627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-27 | 870188.9487 |  | 409004.3014 |  | 120150.4702 |  | 164128.2206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-02-28 | 871838.3325 |  | 410292.3782 |  | 120470.1193 |  | 164169.8785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-01 | 873487.7164 |  | 411580.455 |  | 120789.7684 |  | 164211.5364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-02 | 875137.1002 |  | 412868.5319 |  | 121109.4175 |  | 164253.1943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-03 | 876786.484 |  | 414156.6087 |  | 121429.0667 |  | 164294.8522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-04 | 878435.8679 |  | 415444.6855 |  | 121748.7158 |  | 164336.5101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-05 | 880085.2517 |  | 416732.7623 |  | 122068.3649 |  | 164378.168 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-06 | 881734.6355 |  | 418020.8391 |  | 122388.014 |  | 164419.8259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-07 | 883384.0194 |  | 419308.9159 |  | 122707.6632 |  | 164461.4838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-08 | 885033.4032 |  | 420596.9928 |  | 123027.3123 |  | 164503.1416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-09 | 886682.787 |  | 421885.0696 |  | 123346.9614 |  | 164544.7995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-10 | 888332.1709 |  | 423173.1464 |  | 123666.6105 |  | 164586.4574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-11 | 889981.5547 |  | 424461.2232 |  | 123986.2596 |  | 164628.1153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-12 | 891630.9386 |  | 425749.3 |  | 124305.9088 |  | 164669.7732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-13 | 893280.3224 |  | 427037.3769 |  | 124625.5579 |  | 164711.4311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-14 | 894929.7062 |  | 428325.4537 |  | 124945.207 |  | 164753.089 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-15 | 896579.0901 |  | 429613.5305 |  | 125264.8561 |  | 164794.7469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-16 | 898228.4739 |  | 430901.6073 |  | 125584.5053 |  | 164836.4048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-17 | 899877.8577 |  | 432189.6841 |  | 125904.1544 |  | 164878.0627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-18 | 901527.2416 |  | 433477.7609 |  | 126223.8035 |  | 164919.7206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-19 | 903176.6254 |  | 434765.8378 |  | 126543.4526 |  | 164961.3785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-20 | 904826.0092 |  | 436053.9146 |  | 126863.1018 |  | 165003.0364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-21 | 906475.3931 |  | 437341.9914 |  | 127182.7509 |  | 165044.6943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-22 | 908124.7769 |  | 438630.0682 |  | 127502.4 |  | 165086.3522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-23 | 909774.1607 |  | 439918.145 |  | 127822.0491 |  | 165128.0101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-24 | 911423.5446 |  | 441206.2219 |  | 128141.6982 |  | 165169.668 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-25 | 913072.9284 |  | 442494.2987 |  | 128461.3474 |  | 165211.3259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-26 | 914722.3123 |  | 443782.3755 |  | 128780.9965 |  | 165252.9838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-27 | 916371.6961 |  | 445070.4523 |  | 129100.6456 |  | 165294.6416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-28 | 918021.0799 |  | 446358.5291 |  | 129420.2947 |  | 165336.2995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-29 | 919670.4638 |  | 447646.6059 |  | 129739.9439 |  | 165377.9574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-30 | 921319.8476 |  | 448934.6828 |  | 130059.593 |  | 165419.6153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-03-31 | 922969.2314 |  | 450222.7596 |  | 130379.2421 |  | 165461.2732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-01 | 924618.6153 |  | 451510.8364 |  | 130698.8912 |  | 165502.9311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-02 | 926267.9991 |  | 452798.9132 |  | 131018.5404 |  | 165544.589 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-03 | 927917.3829 |  | 454086.99 |  | 131338.1895 |  | 165586.2469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-04 | 929566.7668 |  | 455375.0669 |  | 131657.8386 |  | 165627.9048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-05 | 931216.1506 |  | 456663.1437 |  | 131977.4877 |  | 165669.5627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-06 | 932865.5344 |  | 457951.2205 |  | 132297.1368 |  | 165711.2206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-07 | 934514.9183 |  | 459239.2973 |  | 132616.786 |  | 165752.8785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-08 | 936164.3021 |  | 460527.3741 |  | 132936.4351 |  | 165794.5364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-09 | 937813.686 |  | 461815.4509 |  | 133256.0842 |  | 165836.1943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-10 | 939463.0698 |  | 463103.5278 |  | 133575.7333 |  | 165877.8522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-11 | 941112.4536 |  | 464391.6046 |  | 133895.3825 |  | 165919.5101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-12 | 942761.8375 |  | 465679.6814 |  | 134215.0316 |  | 165961.168 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-13 | 944411.2213 |  | 466967.7582 |  | 134534.6807 |  | 166002.8259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-14 | 946060.6051 |  | 468255.835 |  | 134854.3298 |  | 166044.4838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-15 | 947709.989 |  | 469543.9119 |  | 135173.9789 |  | 166086.1416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-16 | 949359.3728 |  | 470831.9887 |  | 135493.6281 |  | 166127.7995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-17 | 951008.7566 |  | 472120.0655 |  | 135813.2772 |  | 166169.4574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-18 | 952658.1405 |  | 473408.1423 |  | 136132.9263 |  | 166211.1153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-19 | 954307.5243 |  | 474696.2191 |  | 136452.5754 |  | 166252.7732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-20 | 955956.9081 |  | 475984.2959 |  | 136772.2246 |  | 166294.4311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-21 | 957606.292 |  | 477272.3728 |  | 137091.8737 |  | 166336.089 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-22 | 959255.6758 |  | 478560.4496 |  | 137411.5228 |  | 166377.7469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-23 | 960905.0597 |  | 479848.5264 |  | 137731.1719 |  | 166419.4048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-24 | 962554.4435 |  | 481136.6032 |  | 138050.8211 |  | 166461.0627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-25 | 964203.8273 |  | 482424.68 |  | 138370.4702 |  | 166502.7206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-26 | 965853.2112 |  | 483712.7569 |  | 138690.1193 |  | 166544.3785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-27 | 967502.595 |  | 485000.8337 |  | 139009.7684 |  | 166586.0364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-28 | 969151.9788 |  | 486288.9105 |  | 139329.4175 |  | 166627.6943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-29 | 970801.3627 |  | 487576.9873 |  | 139649.0667 |  | 166669.3522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-04-30 | 972450.7465 |  | 488865.0641 |  | 139968.7158 |  | 166711.0101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-01 | 974100.1303 |  | 490153.1409 |  | 140288.3649 |  | 166752.668 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-02 | 975749.5142 |  | 491441.2178 |  | 140608.014 |  | 166794.3259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-03 | 977398.898 |  | 492729.2946 |  | 140927.6632 |  | 166835.9838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-04 | 979048.2818 |  | 494017.3714 |  | 141247.3123 |  | 166877.6416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-05 | 980697.6657 |  | 495305.4482 |  | 141566.9614 |  | 166919.2995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-06 | 982347.0495 |  | 496593.525 |  | 141886.6105 |  | 166960.9574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-07 | 983996.4334 |  | 497881.6019 |  | 142206.2596 |  | 167002.6153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-08 | 985645.8172 |  | 499169.6787 |  | 142525.9088 |  | 167044.2732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-09 | 987295.201 |  | 500457.7555 |  | 142845.5579 |  | 167085.9311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-10 | 988944.5849 |  | 501745.8323 |  | 143165.207 |  | 167127.589 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-11 | 990593.9687 |  | 503033.9091 |  | 143484.8561 |  | 167169.2469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-12 | 992243.3525 |  | 504321.9859 |  | 143804.5053 |  | 167210.9048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-13 | 993892.7364 |  | 505610.0628 |  | 144124.1544 |  | 167252.5627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-14 | 995542.1202 |  | 506898.1396 |  | 144443.8035 |  | 167294.2206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-15 | 997191.504 |  | 508186.2164 |  | 144763.4526 |  | 167335.8785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-16 | 998840.8879 |  | 509474.2932 |  | 145083.1018 |  | 167377.5364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-17 | 1000490.2717 |  | 510762.37 |  | 145402.7509 |  | 167419.1943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-18 | 1002139.6555 |  | 512050.4469 |  | 145722.4 |  | 167460.8522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-19 | 1003789.0394 |  | 513338.5237 |  | 146042.0491 |  | 167502.5101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-20 | 1005438.4232 |  | 514626.6005 |  | 146361.6982 |  | 167544.168 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-21 | 1007087.8071 |  | 515914.6773 |  | 146681.3474 |  | 167585.8259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-22 | 1008737.1909 |  | 517202.7541 |  | 147000.9965 |  | 167627.4838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-23 | 1010386.5747 |  | 518490.8309 |  | 147320.6456 |  | 167669.1416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-24 | 1012035.9586 |  | 519778.9078 |  | 147640.2947 |  | 167710.7995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-25 | 1013685.3424 |  | 521066.9846 |  | 147959.9439 |  | 167752.4574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-26 | 1015334.7262 |  | 522355.0614 |  | 148279.593 |  | 167794.1153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-27 | 1016984.1101 |  | 523643.1382 |  | 148599.2421 |  | 167835.7732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-28 | 1018633.4939 |  | 524931.215 |  | 148918.8912 |  | 167877.4311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-29 | 1020282.8777 |  | 526219.2919 |  | 149238.5404 |  | 167919.089 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-30 | 1021932.2616 |  | 527507.3687 |  | 149558.1895 |  | 167960.7469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-05-31 | 1023581.6454 |  | 528795.4455 |  | 149877.8386 |  | 168002.4048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-01 | 1025231.0292 |  | 530083.5223 |  | 150197.4877 |  | 168044.0627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-02 | 1026880.4131 |  | 531371.5991 |  | 150517.1368 |  | 168085.7206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-03 | 1028529.7969 |  | 532659.6759 |  | 150836.786 |  | 168127.3785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-04 | 1030179.1808 |  | 533947.7528 |  | 151156.4351 |  | 168169.0364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-05 | 1031828.5646 |  | 535235.8296 |  | 151476.0842 |  | 168210.6943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-06 | 1033477.9484 |  | 536523.9064 |  | 151795.7333 |  | 168252.3522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-07 | 1035127.3323 |  | 537811.9832 |  | 152115.3825 |  | 168294.0101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-08 | 1036776.7161 |  | 539100.06 |  | 152435.0316 |  | 168335.668 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-09 | 1038426.0999 |  | 540388.1369 |  | 152754.6807 |  | 168377.3259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-10 | 1040075.4838 |  | 541676.2137 |  | 153074.3298 |  | 168418.9838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-11 | 1041724.8676 |  | 542964.2905 |  | 153393.9789 |  | 168460.6416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-12 | 1043374.2514 |  | 544252.3673 |  | 153713.6281 |  | 168502.2995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-13 | 1045023.6353 |  | 545540.4441 |  | 154033.2772 |  | 168543.9574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-14 | 1046673.0191 |  | 546828.5209 |  | 154352.9263 |  | 168585.6153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-15 | 1048322.4029 |  | 548116.5978 |  | 154672.5754 |  | 168627.2732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-16 | 1049971.7868 |  | 549404.6746 |  | 154992.2246 |  | 168668.9311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-17 | 1051621.1706 |  | 550692.7514 |  | 155311.8737 |  | 168710.589 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-18 | 1053270.5545 |  | 551980.8282 |  | 155631.5228 |  | 168752.2469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-19 | 1054919.9383 |  | 553268.905 |  | 155951.1719 |  | 168793.9048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-20 | 1056569.3221 |  | 554556.9819 |  | 156270.8211 |  | 168835.5627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-21 | 1058218.706 |  | 555845.0587 |  | 156590.4702 |  | 168877.2206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-22 | 1059868.0898 |  | 557133.1355 |  | 156910.1193 |  | 168918.8785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-23 | 1061517.4736 |  | 558421.2123 |  | 157229.7684 |  | 168960.5364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-24 | 1063166.8575 |  | 559709.2891 |  | 157549.4175 |  | 169002.1943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-25 | 1064816.2413 |  | 560997.3659 |  | 157869.0667 |  | 169043.8522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-26 | 1066465.6251 |  | 562285.4428 |  | 158188.7158 |  | 169085.5101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-27 | 1068115.009 |  | 563573.5196 |  | 158508.3649 |  | 169127.168 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-28 | 1069764.3928 |  | 564861.5964 |  | 158828.014 |  | 169168.8259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-29 | 1071413.7766 |  | 566149.6732 |  | 159147.6632 |  | 169210.4838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-06-30 | 1073063.1605 |  | 567437.75 |  | 159467.3123 |  | 169252.1416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-01 | 1074712.5443 |  | 568725.8269 |  | 159786.9614 |  | 169293.7995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-02 | 1076361.9282 |  | 570013.9037 |  | 160106.6105 |  | 169335.4574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-03 | 1078011.312 |  | 571301.9805 |  | 160426.2596 |  | 169377.1153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-04 | 1079660.6958 |  | 572590.0573 |  | 160745.9088 |  | 169418.7732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-05 | 1081310.0797 |  | 573878.1341 |  | 161065.5579 |  | 169460.4311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-06 | 1082959.4635 |  | 575166.2109 |  | 161385.207 |  | 169502.089 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-07 | 1084608.8473 |  | 576454.2878 |  | 161704.8561 |  | 169543.7469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-08 | 1086258.2312 |  | 577742.3646 |  | 162024.5053 |  | 169585.4048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-09 | 1087907.615 |  | 579030.4414 |  | 162344.1544 |  | 169627.0627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-10 | 1089556.9988 |  | 580318.5182 |  | 162663.8035 |  | 169668.7206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-11 | 1091206.3827 |  | 581606.595 |  | 162983.4526 |  | 169710.3785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-12 | 1092855.7665 |  | 582894.6719 |  | 163303.1018 |  | 169752.0364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-13 | 1094505.1503 |  | 584182.7487 |  | 163622.7509 |  | 169793.6943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-14 | 1096154.5342 |  | 585470.8255 |  | 163942.4 |  | 169835.3522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-15 | 1097803.918 |  | 586758.9023 |  | 164262.0491 |  | 169877.0101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-16 | 1099453.3019 |  | 588046.9791 |  | 164581.6982 |  | 169918.668 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-17 | 1101102.6857 |  | 589335.0559 |  | 164901.3474 |  | 169960.3259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-18 | 1102752.0695 |  | 590623.1328 |  | 165220.9965 |  | 170001.9838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-19 | 1104401.4534 |  | 591911.2096 |  | 165540.6456 |  | 170043.6416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-20 | 1106050.8372 |  | 593199.2864 |  | 165860.2947 |  | 170085.2995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-21 | 1107700.221 |  | 594487.3632 |  | 166179.9439 |  | 170126.9574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-22 | 1109349.6049 |  | 595775.44 |  | 166499.593 |  | 170168.6153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-23 | 1110998.9887 |  | 597063.5169 |  | 166819.2421 |  | 170210.2732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-24 | 1112648.3725 |  | 598351.5937 |  | 167138.8912 |  | 170251.9311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-25 | 1114297.7564 |  | 599639.6705 |  | 167458.5404 |  | 170293.589 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-26 | 1115947.1402 |  | 600927.7473 |  | 167778.1895 |  | 170335.2469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-27 | 1117596.524 |  | 602215.8241 |  | 168097.8386 |  | 170376.9048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-28 | 1119245.9079 |  | 603503.9009 |  | 168417.4877 |  | 170418.5627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-29 | 1120895.2917 |  | 604791.9778 |  | 168737.1368 |  | 170460.2206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-30 | 1122544.6756 |  | 606080.0546 |  | 169056.786 |  | 170501.8785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-07-31 | 1124194.0594 |  | 607368.1314 |  | 169376.4351 |  | 170543.5364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-01 | 1125843.4432 |  | 608656.2082 |  | 169696.0842 |  | 170585.1943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-02 | 1127492.8271 |  | 609944.285 |  | 170015.7333 |  | 170626.8522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-03 | 1129142.2109 |  | 611232.3619 |  | 170335.3825 |  | 170668.5101 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-04 | 1130791.5947 |  | 612520.4387 |  | 170655.0316 |  | 170710.168 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-05 | 1132440.9786 |  | 613808.5155 |  | 170974.6807 |  | 170751.8259 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-06 | 1134090.3624 |  | 615096.5923 |  | 171294.3298 |  | 170793.4838 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-07 | 1135739.7462 |  | 616384.6691 |  | 171613.9789 |  | 170835.1416 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-08 | 1137389.1301 |  | 617672.7459 |  | 171933.6281 |  | 170876.7995 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-09 | 1139038.5139 |  | 618960.8228 |  | 172253.2772 |  | 170918.4574 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-10 | 1140687.8977 |  | 620248.8996 |  | 172572.9263 |  | 170960.1153 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-11 | 1142337.2816 |  | 621536.9764 |  | 172892.5754 |  | 171001.7732 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-12 | 1143986.6654 |  | 622825.0532 |  | 173212.2246 |  | 171043.4311 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-13 | 1145636.0493 |  | 624113.13 |  | 173531.8737 |  | 171085.089 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-14 | 1147285.4331 |  | 625401.2069 |  | 173851.5228 |  | 171126.7469 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-15 | 1148934.8169 |  | 626689.2837 |  | 174171.1719 |  | 171168.4048 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-16 | 1150584.2008 |  | 627977.3605 |  | 174490.8211 |  | 171210.0627 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-17 | 1152233.5846 |  | 629265.4373 |  | 174810.4702 |  | 171251.7206 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-18 | 1153882.9684 |  | 630553.5141 |  | 175130.1193 |  | 171293.3785 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-19 | 1155532.3523 |  | 631841.5909 |  | 175449.7684 |  | 171335.0364 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-20 | 1157181.7361 |  | 633129.6678 |  | 175769.4175 |  | 171376.6943 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-21 | 1158831.1199 |  | 634417.7446 |  | 176089.0667 |  | 171418.3522 |  | 38262.6087 |  | 138643.3478 |  | 1649.3838 |  | 1288.0768 |  | 319.6491 |  | 41.6579 |  | 0 |  | 0
2026-08-22 | 1158831.1199 |  | 634417.7446 |  | 176089.0667 |  | 171418.3522 |  | 38262.6087 |  | 138643.3478 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2026-08-23 | 1158831.1199 |  | 634417.7446 |  | 176089.0667 |  | 171418.3522 |  | 38262.6087 |  | 138643.3478 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2026-08-24 | 1160799.6208 |  | 635634.2252 |  | 176538.0566 |  | 171418.3522 |  | 38565.639 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-08-25 | 1162768.1216 |  | 636850.7058 |  | 176987.0465 |  | 171418.3522 |  | 38868.6693 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-08-26 | 1164736.6224 |  | 638067.1864 |  | 177436.0364 |  | 171418.3522 |  | 39171.6996 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-08-27 | 1166705.1232 |  | 639283.6671 |  | 177885.0263 |  | 171418.3522 |  | 39474.7299 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-08-28 | 1168673.624 |  | 640500.1477 |  | 178334.0162 |  | 171418.3522 |  | 39777.7602 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-08-29 | 1170642.1249 |  | 641716.6283 |  | 178783.0061 |  | 171418.3522 |  | 40080.7905 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-08-30 | 1172610.6257 |  | 642933.1089 |  | 179231.996 |  | 171418.3522 |  | 40383.8208 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-08-31 | 1174579.1265 |  | 644149.5895 |  | 179680.9859 |  | 171418.3522 |  | 40686.8511 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-01 | 1176547.6273 |  | 645366.0701 |  | 180129.9758 |  | 171418.3522 |  | 40989.8814 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-02 | 1178516.1281 |  | 646582.5508 |  | 180578.9657 |  | 171418.3522 |  | 41292.9117 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-03 | 1180484.629 |  | 647799.0314 |  | 181027.9556 |  | 171418.3522 |  | 41595.942 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-04 | 1182453.1298 |  | 649015.512 |  | 181476.9455 |  | 171418.3522 |  | 41898.9723 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-05 | 1184421.6306 |  | 650231.9926 |  | 181925.9354 |  | 171418.3522 |  | 42202.0026 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-06 | 1186390.1314 |  | 651448.4732 |  | 182374.9253 |  | 171418.3522 |  | 42505.0329 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-07 | 1188358.6322 |  | 652664.9538 |  | 182823.9152 |  | 171418.3522 |  | 42808.0632 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-08 | 1190327.1331 |  | 653881.4345 |  | 183272.9051 |  | 171418.3522 |  | 43111.0935 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-09 | 1192295.6339 |  | 655097.9151 |  | 183721.8949 |  | 171418.3522 |  | 43414.1238 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-10 | 1194264.1347 |  | 656314.3957 |  | 184170.8848 |  | 171418.3522 |  | 43717.1542 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-11 | 1196232.6355 |  | 657530.8763 |  | 184619.8747 |  | 171418.3522 |  | 44020.1845 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-12 | 1198201.1363 |  | 658747.3569 |  | 185068.8646 |  | 171418.3522 |  | 44323.2148 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-13 | 1200169.6372 |  | 659963.8376 |  | 185517.8545 |  | 171418.3522 |  | 44626.2451 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-14 | 1202138.138 |  | 661180.3182 |  | 185966.8444 |  | 171418.3522 |  | 44929.2754 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-15 | 1204106.6388 |  | 662396.7988 |  | 186415.8343 |  | 171418.3522 |  | 45232.3057 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-16 | 1206075.1396 |  | 663613.2794 |  | 186864.8242 |  | 171418.3522 |  | 45535.336 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-17 | 1208043.6404 |  | 664829.76 |  | 187313.8141 |  | 171418.3522 |  | 45838.3663 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-18 | 1210012.1413 |  | 666046.2406 |  | 187762.804 |  | 171418.3522 |  | 46141.3966 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-19 | 1211980.6421 |  | 667262.7213 |  | 188211.7939 |  | 171418.3522 |  | 46444.4269 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-20 | 1213949.1429 |  | 668479.2019 |  | 188660.7838 |  | 171418.3522 |  | 46747.4572 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-21 | 1215917.6437 |  | 669695.6825 |  | 189109.7737 |  | 171418.3522 |  | 47050.4875 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-22 | 1217886.1445 |  | 670912.1631 |  | 189558.7636 |  | 171418.3522 |  | 47353.5178 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-23 | 1219854.6454 |  | 672128.6437 |  | 190007.7535 |  | 171418.3522 |  | 47656.5481 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-24 | 1221823.1462 |  | 673345.1244 |  | 190456.7434 |  | 171418.3522 |  | 47959.5784 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0
2026-09-25 | 1223791.647 |  | 674561.605 |  | 190905.7333 |  | 171418.3522 |  | 48262.6087 |  | 138643.3478 |  | 1968.5008 |  | 1216.4806 |  | 448.9899 |  | 0 |  | 303.0303 |  | 0

## Labor Cost
Date | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned 5101 · Salary and wages (Direct) (Cumulative) | Actual 5101 · Salary and wages (Direct) (Cumulative) | Planned 5102 · Payroll taxes (Direct) (Cumulative) | Actual 5102 · Payroll taxes (Direct) (Cumulative)
2025-04-02 | 945.8824 | 0 | 945.8824 | 0 | 0 | 0
2025-04-03 | 1891.7647 | 0 | 1891.7647 | 0 | 0 | 0
2025-04-04 | 2837.6471 | 0 | 2837.6471 | 0 | 0 | 0
2025-04-05 | 3783.5294 | 0 | 3783.5294 | 0 | 0 | 0
2025-04-06 | 4729.4118 | 0 | 4729.4118 | 0 | 0 | 0
2025-04-07 | 5675.2941 | 1126.6 | 5675.2941 | 1126.6 | 0 | 1126.6
2025-04-08 | 6621.1765 | 2253.2 | 6621.1765 | 2253.2 | 0 | 2253.2
2025-04-09 | 7567.0588 | 3379.8 | 7567.0588 | 3379.8 | 0 | 3379.8
2025-04-10 | 8512.9412 | 4506.4 | 8512.9412 | 4506.4 | 0 | 4506.4
2025-04-11 | 9458.8235 | 5633 | 9458.8235 | 5633 | 0 | 5633
2025-04-12 | 10404.7059 | 5633 | 10404.7059 | 5633 | 0 | 5633
2025-04-13 | 11350.5882 | 5633 | 11350.5882 | 5633 | 0 | 5633
2025-04-14 | 12296.4706 | 5847.4 | 12296.4706 | 5847.4 | 0 | 5847.4
2025-04-15 | 13242.3529 | 6061.8 | 13242.3529 | 6061.8 | 0 | 6061.8
2025-04-16 | 14188.2353 | 6276.2 | 14188.2353 | 6276.2 | 0 | 6276.2
2025-04-17 | 15134.1176 | 6490.6 | 15134.1176 | 6490.6 | 0 | 6490.6
2025-04-18 | 16080 | 6705 | 16080 | 6705 | 0 | 6705
2025-04-19 | 17025.8824 | 6705 | 17025.8824 | 6705 | 0 | 6705
2025-04-20 | 17971.7647 | 6705 | 17971.7647 | 6705 | 0 | 6705
2025-04-21 | 18917.6471 | 7087.15 | 18917.6471 | 7087.15 | 0 | 7087.15
2025-04-22 | 19863.5294 | 7469.3 | 19863.5294 | 7469.3 | 0 | 7469.3
2025-04-23 | 20809.4118 | 7851.45 | 20809.4118 | 7851.45 | 0 | 7851.45
2025-04-24 | 21755.2941 | 8233.6 | 21755.2941 | 8233.6 | 0 | 8233.6
2025-04-25 | 22701.1765 | 8615.75 | 22701.1765 | 8615.75 | 0 | 8615.75
2025-04-26 | 23647.0588 | 8615.75 | 23647.0588 | 8615.75 | 0 | 8615.75
2025-04-27 | 24592.9412 | 8615.75 | 24592.9412 | 8615.75 | 0 | 8615.75
2025-04-28 | 25538.8235 | 8615.75 | 25538.8235 | 8615.75 | 0 | 8615.75
2025-04-29 | 26484.7059 | 8615.75 | 26484.7059 | 8615.75 | 0 | 8615.75
2025-04-30 | 27430.5882 | 8615.75 | 27430.5882 | 8615.75 | 0 | 8615.75
2025-05-01 | 28376.4706 | 8615.75 | 28376.4706 | 8615.75 | 0 | 8615.75
2025-05-02 | 29322.3529 | 8615.75 | 29322.3529 | 8615.75 | 0 | 8615.75
2025-05-03 | 30268.2353 | 8615.75 | 30268.2353 | 8615.75 | 0 | 8615.75
2025-05-04 | 31214.1176 | 8615.75 | 31214.1176 | 8615.75 | 0 | 8615.75
2025-05-05 | 32160 | 8615.75 | 32160 | 8615.75 | 0 | 8615.75
2025-05-06 | 33105.8824 | 8615.75 | 33105.8824 | 8615.75 | 0 | 8615.75
2025-05-07 | 34051.7647 | 8615.75 | 34051.7647 | 8615.75 | 0 | 8615.75
2025-05-08 | 34997.6471 | 8615.75 | 34997.6471 | 8615.75 | 0 | 8615.75
2025-05-09 | 35943.5294 | 8615.75 | 35943.5294 | 8615.75 | 0 | 8615.75
2025-05-10 | 36889.4118 | 8615.75 | 36889.4118 | 8615.75 | 0 | 8615.75
2025-05-11 | 37835.2941 | 8615.75 | 37835.2941 | 8615.75 | 0 | 8615.75
2025-05-12 | 38781.1765 | 8615.75 | 38781.1765 | 8615.75 | 0 | 8615.75
2025-05-13 | 39727.0588 | 8615.75 | 39727.0588 | 8615.75 | 0 | 8615.75
2025-05-14 | 40672.9412 | 8615.75 | 40672.9412 | 8615.75 | 0 | 8615.75
2025-05-15 | 41618.8235 | 8615.75 | 41618.8235 | 8615.75 | 0 | 8615.75
2025-05-16 | 42564.7059 | 8615.75 | 42564.7059 | 8615.75 | 0 | 8615.75
2025-05-17 | 43510.5882 | 8615.75 | 43510.5882 | 8615.75 | 0 | 8615.75
2025-05-18 | 44456.4706 | 8615.75 | 44456.4706 | 8615.75 | 0 | 8615.75
2025-05-19 | 45402.3529 | 8615.75 | 45402.3529 | 8615.75 | 0 | 8615.75
2025-05-20 | 46348.2353 | 8615.75 | 46348.2353 | 8615.75 | 0 | 8615.75
2025-05-21 | 47294.1176 | 8615.75 | 47294.1176 | 8615.75 | 0 | 8615.75
2025-05-22 | 48240 | 8615.75 | 48240 | 8615.75 | 0 | 8615.75
2025-05-23 | 49185.8824 | 8615.75 | 49185.8824 | 8615.75 | 0 | 8615.75
2025-05-24 | 50131.7647 | 8615.75 | 50131.7647 | 8615.75 | 0 | 8615.75
2025-05-25 | 51077.6471 | 8615.75 | 51077.6471 | 8615.75 | 0 | 8615.75
2025-05-26 | 52023.5294 | 8615.75 | 52023.5294 | 8615.75 | 0 | 8615.75
2025-05-27 | 52969.4118 | 8615.75 | 52969.4118 | 8615.75 | 0 | 8615.75
2025-05-28 | 53915.2941 | 8615.75 | 53915.2941 | 8615.75 | 0 | 8615.75
2025-05-29 | 54861.1765 | 8615.75 | 54861.1765 | 8615.75 | 0 | 8615.75
2025-05-30 | 55807.0588 | 8615.75 | 55807.0588 | 8615.75 | 0 | 8615.75
2025-05-31 | 56752.9412 | 8615.75 | 56752.9412 | 8615.75 | 0 | 8615.75
2025-06-01 | 57698.8235 | 8615.75 | 57698.8235 | 8615.75 | 0 | 8615.75
2025-06-02 | 58644.7059 | 9044.55 | 58644.7059 | 9044.55 | 0 | 9044.55
2025-06-03 | 59590.5882 | 9473.35 | 59590.5882 | 9473.35 | 0 | 9473.35
2025-06-04 | 60536.4706 | 9902.15 | 60536.4706 | 9902.15 | 0 | 9902.15
2025-06-05 | 61482.3529 | 10330.95 | 61482.3529 | 10330.95 | 0 | 10330.95
2025-06-06 | 62428.2353 | 10759.75 | 62428.2353 | 10759.75 | 0 | 10759.75
2025-06-07 | 63374.1176 | 10759.75 | 63374.1176 | 10759.75 | 0 | 10759.75
2025-06-08 | 64320 | 10759.75 | 64320 | 10759.75 | 0 | 10759.75
2025-06-09 | 65265.8824 | 10866.95 | 65265.8824 | 10866.95 | 0 | 10866.95
2025-06-10 | 66211.7647 | 10974.15 | 66211.7647 | 10974.15 | 0 | 10974.15
2025-06-11 | 67157.6471 | 11081.35 | 67157.6471 | 11081.35 | 0 | 11081.35
2025-06-12 | 68103.5294 | 11188.55 | 68103.5294 | 11188.55 | 0 | 11188.55
2025-06-13 | 69049.4118 | 11295.75 | 69049.4118 | 11295.75 | 0 | 11295.75
2025-06-14 | 69995.2941 | 11295.75 | 69995.2941 | 11295.75 | 0 | 11295.75
2025-06-15 | 70941.1765 | 11295.75 | 70941.1765 | 11295.75 | 0 | 11295.75
2025-06-16 | 71887.0588 | 11677.9 | 71887.0588 | 11677.9 | 0 | 11677.9
2025-06-17 | 72832.9412 | 12060.05 | 72832.9412 | 12060.05 | 0 | 12060.05
2025-06-18 | 73778.8235 | 12442.2 | 73778.8235 | 12442.2 | 0 | 12442.2
2025-06-19 | 74724.7059 | 12824.35 | 74724.7059 | 12824.35 | 0 | 12824.35
2025-06-20 | 75670.5882 | 13206.5 | 75670.5882 | 13206.5 | 0 | 13206.5
2025-06-21 | 76616.4706 | 13206.5 | 76616.4706 | 13206.5 | 0 | 13206.5
2025-06-22 | 77562.3529 | 13206.5 | 77562.3529 | 13206.5 | 0 | 13206.5
2025-06-23 | 78508.2353 | 13313.7 | 78508.2353 | 13313.7 | 0 | 13313.7
2025-06-24 | 79454.1176 | 13420.9 | 79454.1176 | 13420.9 | 0 | 13420.9
2025-06-25 | 80400 | 13528.1 | 80400 | 13528.1 | 0 | 13528.1
2025-06-26 | 80518.8731 | 13635.3 | 80518.8731 | 13635.3 | 0 | 13635.3
2025-06-27 | 80637.7462 | 13742.5 | 80637.7462 | 13742.5 | 0 | 13742.5
2025-06-28 | 80756.6194 | 13742.5 | 80756.6194 | 13742.5 | 0 | 13742.5
2025-06-29 | 80875.4925 | 13742.5 | 80875.4925 | 13742.5 | 0 | 13742.5
2025-06-30 | 80994.3656 | 14191.65 | 80994.3656 | 14191.65 | 0 | 14191.65
2025-07-01 | 81113.2387 | 14640.8 | 81113.2387 | 14640.8 | 0 | 14640.8
2025-07-02 | 81232.1118 | 15089.95 | 81232.1118 | 15089.95 | 0 | 15089.95
2025-07-03 | 81350.9849 | 15539.1 | 81350.9849 | 15539.1 | 0 | 15539.1
2025-07-04 | 81469.8581 | 15988.25 | 81469.8581 | 15988.25 | 0 | 15988.25
2025-07-05 | 81588.7312 | 15988.25 | 81588.7312 | 15988.25 | 0 | 15988.25
2025-07-06 | 81707.6043 | 15988.25 | 81707.6043 | 15988.25 | 0 | 15988.25
2025-07-07 | 81826.4774 | 16390.25 | 81826.4774 | 16390.25 | 0 | 16390.25
2025-07-08 | 81945.3505 | 16792.25 | 81945.3505 | 16792.25 | 0 | 16792.25
2025-07-09 | 82064.2237 | 17194.25 | 82064.2237 | 17194.25 | 0 | 17194.25
2025-07-10 | 82183.0968 | 17596.25 | 82183.0968 | 17596.25 | 0 | 17596.25
2025-07-11 | 82301.9699 | 17998.25 | 82301.9699 | 17998.25 | 0 | 17998.25
2025-07-12 | 82420.843 | 17998.25 | 82420.843 | 17998.25 | 0 | 17998.25
2025-07-13 | 82539.7161 | 17998.25 | 82539.7161 | 17998.25 | 0 | 17998.25
2025-07-14 | 82658.5892 | 18400.25 | 82658.5892 | 18400.25 | 0 | 18400.25
2025-07-15 | 82777.4624 | 18802.25 | 82777.4624 | 18802.25 | 0 | 18802.25
2025-07-16 | 82896.3355 | 19204.25 | 82896.3355 | 19204.25 | 0 | 19204.25
2025-07-17 | 83015.2086 | 19606.25 | 83015.2086 | 19606.25 | 0 | 19606.25
2025-07-18 | 83134.0817 | 20008.25 | 83134.0817 | 20008.25 | 0 | 20008.25
2025-07-19 | 83252.9548 | 20008.25 | 83252.9548 | 20008.25 | 0 | 20008.25
2025-07-20 | 83371.828 | 20008.25 | 83371.828 | 20008.25 | 0 | 20008.25
2025-07-21 | 83490.7011 | 20410.25 | 83490.7011 | 20410.25 | 0 | 20410.25
2025-07-22 | 83609.5742 | 20812.25 | 83609.5742 | 20812.25 | 0 | 20812.25
2025-07-23 | 83728.4473 | 21214.25 | 83728.4473 | 21214.25 | 0 | 21214.25
2025-07-24 | 83847.3204 | 21616.25 | 83847.3204 | 21616.25 | 0 | 21616.25
2025-07-25 | 83966.1935 | 22018.25 | 83966.1935 | 22018.25 | 0 | 22018.25
2025-07-26 | 84085.0667 | 22018.25 | 84085.0667 | 22018.25 | 0 | 22018.25
2025-07-27 | 84203.9398 | 22018.25 | 84203.9398 | 22018.25 | 0 | 22018.25
2025-07-28 | 84322.8129 | 22366.65 | 84322.8129 | 22366.65 | 0 | 22366.65
2025-07-29 | 84441.686 | 22715.05 | 84441.686 | 22715.05 | 0 | 22715.05
2025-07-30 | 84560.5591 | 23063.45 | 84560.5591 | 23063.45 | 0 | 23063.45
2025-07-31 | 84679.4323 | 23411.85 | 84679.4323 | 23411.85 | 0 | 23411.85
2025-08-01 | 84798.3054 | 23760.25 | 84798.3054 | 23760.25 | 0 | 23760.25
2025-08-02 | 84917.1785 | 23760.25 | 84917.1785 | 23760.25 | 0 | 23760.25
2025-08-03 | 85036.0516 | 23760.25 | 85036.0516 | 23760.25 | 0 | 23760.25
2025-08-04 | 85154.9247 | 24028.25 | 85154.9247 | 24028.25 | 0 | 24028.25
2025-08-05 | 85273.7978 | 24296.25 | 85273.7978 | 24296.25 | 0 | 24296.25
2025-08-06 | 85392.671 | 24564.25 | 85392.671 | 24564.25 | 0 | 24564.25
2025-08-07 | 85511.5441 | 24832.25 | 85511.5441 | 24832.25 | 0 | 24832.25
2025-08-08 | 85630.4172 | 25100.25 | 85630.4172 | 25100.25 | 0 | 25100.25
2025-08-09 | 85749.2903 | 25100.25 | 85749.2903 | 25100.25 | 0 | 25100.25
2025-08-10 | 85868.1634 | 25100.25 | 85868.1634 | 25100.25 | 0 | 25100.25
2025-08-11 | 85987.0366 | 25314.65 | 85987.0366 | 25314.65 | 0 | 25314.65
2025-08-12 | 86105.9097 | 25529.05 | 86105.9097 | 25529.05 | 0 | 25529.05
2025-08-13 | 86224.7828 | 25743.45 | 86224.7828 | 25743.45 | 0 | 25743.45
2025-08-14 | 86343.6559 | 25957.85 | 86343.6559 | 25957.85 | 0 | 25957.85
2025-08-15 | 86462.529 | 26172.25 | 86462.529 | 26172.25 | 0 | 26172.25
2025-08-16 | 86581.4022 | 26172.25 | 86581.4022 | 26172.25 | 0 | 26172.25
2025-08-17 | 86700.2753 | 26172.25 | 86700.2753 | 26172.25 | 0 | 26172.25
2025-08-18 | 86819.1484 | 26708.25 | 86819.1484 | 26708.25 | 0 | 26708.25
2025-08-19 | 86938.0215 | 27244.25 | 86938.0215 | 27244.25 | 0 | 27244.25
2025-08-20 | 87056.8946 | 27780.25 | 87056.8946 | 27780.25 | 0 | 27780.25
2025-08-21 | 87175.7677 | 28316.25 | 87175.7677 | 28316.25 | 0 | 28316.25
2025-08-22 | 87294.6409 | 28852.25 | 87294.6409 | 28852.25 | 0 | 28852.25
2025-08-23 | 87413.514 | 28852.25 | 87413.514 | 28852.25 | 0 | 28852.25
2025-08-24 | 87532.3871 | 28852.25 | 87532.3871 | 28852.25 | 0 | 28852.25
2025-08-25 | 87651.2602 | 29952.05 | 87651.2602 | 29952.05 | 0 | 29952.05
2025-08-26 | 87770.1333 | 31051.85 | 87770.1333 | 31051.85 | 0 | 31051.85
2025-08-27 | 87889.0065 | 32151.65 | 87889.0065 | 32151.65 | 0 | 32151.65
2025-08-28 | 88007.8796 | 33251.45 | 88007.8796 | 33251.45 | 0 | 33251.45
2025-08-29 | 88126.7527 | 34351.25 | 88126.7527 | 34351.25 | 0 | 34351.25
2025-08-30 | 88245.6258 | 34351.25 | 88245.6258 | 34351.25 | 0 | 34351.25
2025-08-31 | 88364.4989 | 34351.25 | 88364.4989 | 34351.25 | 0 | 34351.25
2025-09-01 | 88483.372 | 35095.2 | 88483.372 | 35095.2 | 0 | 35095.2
2025-09-02 | 88602.2452 | 35839.15 | 88602.2452 | 35839.15 | 0 | 35839.15
2025-09-03 | 88721.1183 | 36583.1 | 88721.1183 | 36583.1 | 0 | 36583.1
2025-09-04 | 88839.9914 | 37327.05 | 88839.9914 | 37327.05 | 0 | 37327.05
2025-09-05 | 88958.8645 | 38071 | 88958.8645 | 38071 | 0 | 38071
2025-09-06 | 89077.7376 | 38071 | 89077.7376 | 38071 | 0 | 38071
2025-09-07 | 89196.6108 | 38071 | 89196.6108 | 38071 | 0 | 38071
2025-09-08 | 89315.4839 | 38573.75 | 89315.4839 | 38573.75 | 0 | 38573.75
2025-09-09 | 89434.357 | 39076.5 | 89434.357 | 39076.5 | 0 | 39076.5
2025-09-10 | 89553.2301 | 39579.25 | 89553.2301 | 39579.25 | 0 | 39579.25
2025-09-11 | 89672.1032 | 40082 | 89672.1032 | 40082 | 0 | 40082
2025-09-12 | 89790.9763 | 40584.75 | 89790.9763 | 40584.75 | 0 | 40584.75
2025-09-13 | 89909.8495 | 40584.75 | 89909.8495 | 40584.75 | 0 | 40584.75
2025-09-14 | 90028.7226 | 40584.75 | 90028.7226 | 40584.75 | 0 | 40584.75
2025-09-15 | 90147.5957 | 42546.625 | 90147.5957 | 42546.625 | 0 | 42546.625
2025-09-16 | 90266.4688 | 44508.5 | 90266.4688 | 44508.5 | 0 | 44508.5
2025-09-17 | 90385.3419 | 46470.375 | 90385.3419 | 46470.375 | 0 | 46470.375
2025-09-18 | 90504.2151 | 48432.25 | 90504.2151 | 48432.25 | 0 | 48432.25
2025-09-19 | 90623.0882 | 50394.125 | 90623.0882 | 50394.125 | 0 | 50394.125
2025-09-20 | 90741.9613 | 50394.125 | 90741.9613 | 50394.125 | 0 | 50394.125
2025-09-21 | 90860.8344 | 50394.125 | 90860.8344 | 50394.125 | 0 | 50394.125
2025-09-22 | 90979.7075 | 51446.2 | 90979.7075 | 51446.2 | 0 | 51446.2
2025-09-23 | 91098.5806 | 52498.275 | 91098.5806 | 52498.275 | 0 | 52498.275
2025-09-24 | 91098.5806 | 53550.35 | 91098.5806 | 53550.35 | 0 | 53550.35
2025-09-25 | 91098.5806 | 54602.425 | 91098.5806 | 54602.425 | 0 | 54602.425
2025-09-26 | 91098.5806 | 55654.5 | 91098.5806 | 55654.5 | 0 | 55654.5
2025-09-27 | 91098.5806 | 55654.5 | 91098.5806 | 55654.5 | 0 | 55654.5
2025-09-28 | 91098.5806 | 55654.5 | 91098.5806 | 55654.5 | 0 | 55654.5
2025-09-29 | 94337.9597 | 56981.625 | 94337.9597 | 56981.625 | 0 | 56981.625
2025-09-30 | 97577.3387 | 58308.75 | 97577.3387 | 58308.75 | 0 | 58308.75
2025-10-01 | 100816.7177 | 59635.875 | 100816.7177 | 59635.875 | 0 | 59635.875
2025-10-02 | 104056.0968 | 60963 | 104056.0968 | 60963 | 0 | 60963
2025-10-03 | 107295.4758 | 62290.125 | 107295.4758 | 62290.125 | 0 | 62290.125
2025-10-04 | 110534.8548 | 62290.125 | 110534.8548 | 62290.125 | 0 | 62290.125
2025-10-05 | 113774.2339 | 62290.125 | 113774.2339 | 62290.125 | 0 | 62290.125
2025-10-06 | 117013.6129 | 63946.875 | 117013.6129 | 63946.875 | 0 | 63946.875
2025-10-07 | 120252.9919 | 65603.625 | 120252.9919 | 65603.625 | 0 | 65603.625
2025-10-08 | 123492.371 | 67260.375 | 123492.371 | 67260.375 | 0 | 67260.375
2025-10-09 | 126731.75 | 68917.125 | 126731.75 | 68917.125 | 0 | 68917.125
2025-10-10 | 129971.129 | 70573.875 | 129971.129 | 70573.875 | 0 | 70573.875
2025-10-11 | 133210.5081 | 70573.875 | 133210.5081 | 70573.875 | 0 | 70573.875
2025-10-12 | 136449.8871 | 70573.875 | 136449.8871 | 70573.875 | 0 | 70573.875
2025-10-13 | 139689.2661 |  | 139689.2661 |  | 0
2025-10-14 | 142928.6452 |  | 142928.6452 |  | 0
2025-10-15 | 146168.0242 |  | 146168.0242 |  | 0
2025-10-16 | 149407.4032 |  | 149407.4032 |  | 0
2025-10-17 | 152646.7823 |  | 152646.7823 |  | 0
2025-10-18 | 155886.1613 |  | 155886.1613 |  | 0
2025-10-19 | 159125.5403 |  | 159125.5403 |  | 0
2025-10-20 | 162364.9194 |  | 162364.9194 |  | 0
2025-10-21 | 165604.2984 |  | 165604.2984 |  | 0
2025-10-22 | 168843.6774 |  | 168843.6774 |  | 0
2025-10-23 | 172083.0565 |  | 172083.0565 |  | 0
2025-10-24 | 175322.4355 |  | 175322.4355 |  | 0
2025-10-25 | 178561.8145 |  | 178561.8145 |  | 0
2025-10-26 | 181801.1935 |  | 181801.1935 |  | 0
2025-10-27 | 185040.5726 |  | 185040.5726 |  | 0
2025-10-28 | 188279.9516 |  | 188279.9516 |  | 0
2025-10-29 | 191519.3306 |  | 191519.3306 |  | 0
2025-10-30 | 194758.7097 |  | 194758.7097 |  | 0
2025-10-31 | 197998.0887 |  | 197998.0887 |  | 0
2025-11-01 | 201237.4677 |  | 201237.4677 |  | 0
2025-11-02 | 204476.8468 |  | 204476.8468 |  | 0
2025-11-03 | 207716.2258 |  | 207716.2258 |  | 0
2025-11-04 | 210955.6048 |  | 210955.6048 |  | 0
2025-11-05 | 214194.9839 |  | 214194.9839 |  | 0
2025-11-06 | 217434.3629 |  | 217434.3629 |  | 0
2025-11-07 | 220673.7419 |  | 220673.7419 |  | 0
2025-11-08 | 223913.121 |  | 223913.121 |  | 0
2025-11-09 | 227152.5 |  | 227152.5 |  | 0
2025-11-10 | 230391.879 |  | 230391.879 |  | 0
2025-11-11 | 233631.2581 |  | 233631.2581 |  | 0
2025-11-12 | 236870.6371 |  | 236870.6371 |  | 0
2025-11-13 | 240110.0161 |  | 240110.0161 |  | 0
2025-11-14 | 243349.3952 |  | 243349.3952 |  | 0
2025-11-15 | 246588.7742 |  | 246588.7742 |  | 0
2025-11-16 | 249828.1532 |  | 249828.1532 |  | 0
2025-11-17 | 253067.5323 |  | 253067.5323 |  | 0
2025-11-18 | 256306.9113 |  | 256306.9113 |  | 0
2025-11-19 | 259546.2903 |  | 259546.2903 |  | 0
2025-11-20 | 261077.3122 |  | 261077.3122 |  | 0
2025-11-21 | 262608.3341 |  | 262608.3341 |  | 0
2025-11-22 | 264139.3559 |  | 264139.3559 |  | 0
2025-11-23 | 265670.3778 |  | 265670.3778 |  | 0
2025-11-24 | 267201.3997 |  | 267201.3997 |  | 0
2025-11-25 | 268732.4215 |  | 268732.4215 |  | 0
2025-11-26 | 270263.4434 |  | 270263.4434 |  | 0
2025-11-27 | 271794.4653 |  | 271794.4653 |  | 0
2025-11-28 | 273325.4871 |  | 273325.4871 |  | 0
2025-11-29 | 274856.509 |  | 274856.509 |  | 0
2025-11-30 | 276387.5309 |  | 276387.5309 |  | 0
2025-12-01 | 277918.5527 |  | 277918.5527 |  | 0
2025-12-02 | 279449.5746 |  | 279449.5746 |  | 0
2025-12-03 | 280980.5965 |  | 280980.5965 |  | 0
2025-12-04 | 282511.6183 |  | 282511.6183 |  | 0
2025-12-05 | 284042.6402 |  | 284042.6402 |  | 0
2025-12-06 | 285573.6621 |  | 285573.6621 |  | 0
2025-12-07 | 287104.684 |  | 287104.684 |  | 0
2025-12-08 | 288635.7058 |  | 288635.7058 |  | 0
2025-12-09 | 290166.7277 |  | 290166.7277 |  | 0
2025-12-10 | 291697.7496 |  | 291697.7496 |  | 0
2025-12-11 | 293228.7714 |  | 293228.7714 |  | 0
2025-12-12 | 294759.7933 |  | 294759.7933 |  | 0
2025-12-13 | 296290.8152 |  | 296290.8152 |  | 0
2025-12-14 | 297821.837 |  | 297821.837 |  | 0
2025-12-15 | 299352.8589 |  | 299352.8589 |  | 0
2025-12-16 | 300883.8808 |  | 300883.8808 |  | 0
2025-12-17 | 302414.9026 |  | 302414.9026 |  | 0
2025-12-18 | 303945.9245 |  | 303945.9245 |  | 0
2025-12-19 | 305476.9464 |  | 305476.9464 |  | 0
2025-12-20 | 307007.9682 |  | 307007.9682 |  | 0
2025-12-21 | 308538.9901 |  | 308538.9901 |  | 0
2025-12-22 | 310070.012 |  | 310070.012 |  | 0
2025-12-23 | 311601.0338 |  | 311601.0338 |  | 0
2025-12-24 | 313132.0557 |  | 313132.0557 |  | 0
2025-12-25 | 314663.0776 |  | 314663.0776 |  | 0
2025-12-26 | 316194.0994 |  | 316194.0994 |  | 0
2025-12-27 | 317725.1213 |  | 317725.1213 |  | 0
2025-12-28 | 319256.1432 |  | 319256.1432 |  | 0
2025-12-29 | 320787.1651 |  | 320787.1651 |  | 0
2025-12-30 | 322318.1869 |  | 322318.1869 |  | 0
2025-12-31 | 323849.2088 |  | 323849.2088 |  | 0
2026-01-01 | 325380.2307 |  | 325380.2307 |  | 0
2026-01-02 | 326911.2525 |  | 326911.2525 |  | 0
2026-01-03 | 328442.2744 |  | 328442.2744 |  | 0
2026-01-04 | 329973.2963 |  | 329973.2963 |  | 0
2026-01-05 | 331504.3181 |  | 331504.3181 |  | 0
2026-01-06 | 333035.34 |  | 333035.34 |  | 0
2026-01-07 | 334566.3619 |  | 334566.3619 |  | 0
2026-01-08 | 336097.3837 |  | 336097.3837 |  | 0
2026-01-09 | 337628.4056 |  | 337628.4056 |  | 0
2026-01-10 | 339159.4275 |  | 339159.4275 |  | 0
2026-01-11 | 340690.4493 |  | 340690.4493 |  | 0
2026-01-12 | 342221.4712 |  | 342221.4712 |  | 0
2026-01-13 | 343752.4931 |  | 343752.4931 |  | 0
2026-01-14 | 345283.5149 |  | 345283.5149 |  | 0
2026-01-15 | 346814.5368 |  | 346814.5368 |  | 0
2026-01-16 | 348345.5587 |  | 348345.5587 |  | 0
2026-01-17 | 349876.5806 |  | 349876.5806 |  | 0
2026-01-18 | 351407.6024 |  | 351407.6024 |  | 0
2026-01-19 | 352938.6243 |  | 352938.6243 |  | 0
2026-01-20 | 354469.6462 |  | 354469.6462 |  | 0
2026-01-21 | 356000.668 |  | 356000.668 |  | 0
2026-01-22 | 357531.6899 |  | 357531.6899 |  | 0
2026-01-23 | 359062.7118 |  | 359062.7118 |  | 0
2026-01-24 | 360593.7336 |  | 360593.7336 |  | 0
2026-01-25 | 362124.7555 |  | 362124.7555 |  | 0
2026-01-26 | 363655.7774 |  | 363655.7774 |  | 0
2026-01-27 | 365186.7992 |  | 365186.7992 |  | 0
2026-01-28 | 366717.8211 |  | 366717.8211 |  | 0
2026-01-29 | 368248.843 |  | 368248.843 |  | 0
2026-01-30 | 369779.8648 |  | 369779.8648 |  | 0
2026-01-31 | 371310.8867 |  | 371310.8867 |  | 0
2026-02-01 | 372841.9086 |  | 372841.9086 |  | 0
2026-02-02 | 374372.9304 |  | 374372.9304 |  | 0
2026-02-03 | 375903.9523 |  | 375903.9523 |  | 0
2026-02-04 | 377434.9742 |  | 377434.9742 |  | 0
2026-02-05 | 378965.996 |  | 378965.996 |  | 0
2026-02-06 | 380497.0179 |  | 380497.0179 |  | 0
2026-02-07 | 382028.0398 |  | 382028.0398 |  | 0
2026-02-08 | 383559.0617 |  | 383559.0617 |  | 0
2026-02-09 | 385090.0835 |  | 385090.0835 |  | 0
2026-02-10 | 386621.1054 |  | 386621.1054 |  | 0
2026-02-11 | 388152.1273 |  | 388152.1273 |  | 0
2026-02-12 | 389683.1491 |  | 389683.1491 |  | 0
2026-02-13 | 390971.2259 |  | 390971.2259 |  | 0
2026-02-14 | 392259.3028 |  | 392259.3028 |  | 0
2026-02-15 | 393547.3796 |  | 393547.3796 |  | 0
2026-02-16 | 394835.4564 |  | 394835.4564 |  | 0
2026-02-17 | 396123.5332 |  | 396123.5332 |  | 0
2026-02-18 | 397411.61 |  | 397411.61 |  | 0
2026-02-19 | 398699.6869 |  | 398699.6869 |  | 0
2026-02-20 | 399987.7637 |  | 399987.7637 |  | 0
2026-02-21 | 401275.8405 |  | 401275.8405 |  | 0
2026-02-22 | 402563.9173 |  | 402563.9173 |  | 0
2026-02-23 | 403851.9941 |  | 403851.9941 |  | 0
2026-02-24 | 405140.0709 |  | 405140.0709 |  | 0
2026-02-25 | 406428.1478 |  | 406428.1478 |  | 0
2026-02-26 | 407716.2246 |  | 407716.2246 |  | 0
2026-02-27 | 409004.3014 |  | 409004.3014 |  | 0
2026-02-28 | 410292.3782 |  | 410292.3782 |  | 0
2026-03-01 | 411580.455 |  | 411580.455 |  | 0
2026-03-02 | 412868.5319 |  | 412868.5319 |  | 0
2026-03-03 | 414156.6087 |  | 414156.6087 |  | 0
2026-03-04 | 415444.6855 |  | 415444.6855 |  | 0
2026-03-05 | 416732.7623 |  | 416732.7623 |  | 0
2026-03-06 | 418020.8391 |  | 418020.8391 |  | 0
2026-03-07 | 419308.9159 |  | 419308.9159 |  | 0
2026-03-08 | 420596.9928 |  | 420596.9928 |  | 0
2026-03-09 | 421885.0696 |  | 421885.0696 |  | 0
2026-03-10 | 423173.1464 |  | 423173.1464 |  | 0
2026-03-11 | 424461.2232 |  | 424461.2232 |  | 0
2026-03-12 | 425749.3 |  | 425749.3 |  | 0
2026-03-13 | 427037.3769 |  | 427037.3769 |  | 0
2026-03-14 | 428325.4537 |  | 428325.4537 |  | 0
2026-03-15 | 429613.5305 |  | 429613.5305 |  | 0
2026-03-16 | 430901.6073 |  | 430901.6073 |  | 0
2026-03-17 | 432189.6841 |  | 432189.6841 |  | 0
2026-03-18 | 433477.7609 |  | 433477.7609 |  | 0
2026-03-19 | 434765.8378 |  | 434765.8378 |  | 0
2026-03-20 | 436053.9146 |  | 436053.9146 |  | 0
2026-03-21 | 437341.9914 |  | 437341.9914 |  | 0
2026-03-22 | 438630.0682 |  | 438630.0682 |  | 0
2026-03-23 | 439918.145 |  | 439918.145 |  | 0
2026-03-24 | 441206.2219 |  | 441206.2219 |  | 0
2026-03-25 | 442494.2987 |  | 442494.2987 |  | 0
2026-03-26 | 443782.3755 |  | 443782.3755 |  | 0
2026-03-27 | 445070.4523 |  | 445070.4523 |  | 0
2026-03-28 | 446358.5291 |  | 446358.5291 |  | 0
2026-03-29 | 447646.6059 |  | 447646.6059 |  | 0
2026-03-30 | 448934.6828 |  | 448934.6828 |  | 0
2026-03-31 | 450222.7596 |  | 450222.7596 |  | 0
2026-04-01 | 451510.8364 |  | 451510.8364 |  | 0
2026-04-02 | 452798.9132 |  | 452798.9132 |  | 0
2026-04-03 | 454086.99 |  | 454086.99 |  | 0
2026-04-04 | 455375.0669 |  | 455375.0669 |  | 0
2026-04-05 | 456663.1437 |  | 456663.1437 |  | 0
2026-04-06 | 457951.2205 |  | 457951.2205 |  | 0
2026-04-07 | 459239.2973 |  | 459239.2973 |  | 0
2026-04-08 | 460527.3741 |  | 460527.3741 |  | 0
2026-04-09 | 461815.4509 |  | 461815.4509 |  | 0
2026-04-10 | 463103.5278 |  | 463103.5278 |  | 0
2026-04-11 | 464391.6046 |  | 464391.6046 |  | 0
2026-04-12 | 465679.6814 |  | 465679.6814 |  | 0
2026-04-13 | 466967.7582 |  | 466967.7582 |  | 0
2026-04-14 | 468255.835 |  | 468255.835 |  | 0
2026-04-15 | 469543.9119 |  | 469543.9119 |  | 0
2026-04-16 | 470831.9887 |  | 470831.9887 |  | 0
2026-04-17 | 472120.0655 |  | 472120.0655 |  | 0
2026-04-18 | 473408.1423 |  | 473408.1423 |  | 0
2026-04-19 | 474696.2191 |  | 474696.2191 |  | 0
2026-04-20 | 475984.2959 |  | 475984.2959 |  | 0
2026-04-21 | 477272.3728 |  | 477272.3728 |  | 0
2026-04-22 | 478560.4496 |  | 478560.4496 |  | 0
2026-04-23 | 479848.5264 |  | 479848.5264 |  | 0
2026-04-24 | 481136.6032 |  | 481136.6032 |  | 0
2026-04-25 | 482424.68 |  | 482424.68 |  | 0
2026-04-26 | 483712.7569 |  | 483712.7569 |  | 0
2026-04-27 | 485000.8337 |  | 485000.8337 |  | 0
2026-04-28 | 486288.9105 |  | 486288.9105 |  | 0
2026-04-29 | 487576.9873 |  | 487576.9873 |  | 0
2026-04-30 | 488865.0641 |  | 488865.0641 |  | 0
2026-05-01 | 490153.1409 |  | 490153.1409 |  | 0
2026-05-02 | 491441.2178 |  | 491441.2178 |  | 0
2026-05-03 | 492729.2946 |  | 492729.2946 |  | 0
2026-05-04 | 494017.3714 |  | 494017.3714 |  | 0
2026-05-05 | 495305.4482 |  | 495305.4482 |  | 0
2026-05-06 | 496593.525 |  | 496593.525 |  | 0
2026-05-07 | 497881.6019 |  | 497881.6019 |  | 0
2026-05-08 | 499169.6787 |  | 499169.6787 |  | 0
2026-05-09 | 500457.7555 |  | 500457.7555 |  | 0
2026-05-10 | 501745.8323 |  | 501745.8323 |  | 0
2026-05-11 | 503033.9091 |  | 503033.9091 |  | 0
2026-05-12 | 504321.9859 |  | 504321.9859 |  | 0
2026-05-13 | 505610.0628 |  | 505610.0628 |  | 0
2026-05-14 | 506898.1396 |  | 506898.1396 |  | 0
2026-05-15 | 508186.2164 |  | 508186.2164 |  | 0
2026-05-16 | 509474.2932 |  | 509474.2932 |  | 0
2026-05-17 | 510762.37 |  | 510762.37 |  | 0
2026-05-18 | 512050.4469 |  | 512050.4469 |  | 0
2026-05-19 | 513338.5237 |  | 513338.5237 |  | 0
2026-05-20 | 514626.6005 |  | 514626.6005 |  | 0
2026-05-21 | 515914.6773 |  | 515914.6773 |  | 0
2026-05-22 | 517202.7541 |  | 517202.7541 |  | 0
2026-05-23 | 518490.8309 |  | 518490.8309 |  | 0
2026-05-24 | 519778.9078 |  | 519778.9078 |  | 0
2026-05-25 | 521066.9846 |  | 521066.9846 |  | 0
2026-05-26 | 522355.0614 |  | 522355.0614 |  | 0
2026-05-27 | 523643.1382 |  | 523643.1382 |  | 0
2026-05-28 | 524931.215 |  | 524931.215 |  | 0
2026-05-29 | 526219.2919 |  | 526219.2919 |  | 0
2026-05-30 | 527507.3687 |  | 527507.3687 |  | 0
2026-05-31 | 528795.4455 |  | 528795.4455 |  | 0
2026-06-01 | 530083.5223 |  | 530083.5223 |  | 0
2026-06-02 | 531371.5991 |  | 531371.5991 |  | 0
2026-06-03 | 532659.6759 |  | 532659.6759 |  | 0
2026-06-04 | 533947.7528 |  | 533947.7528 |  | 0
2026-06-05 | 535235.8296 |  | 535235.8296 |  | 0
2026-06-06 | 536523.9064 |  | 536523.9064 |  | 0
2026-06-07 | 537811.9832 |  | 537811.9832 |  | 0
2026-06-08 | 539100.06 |  | 539100.06 |  | 0
2026-06-09 | 540388.1369 |  | 540388.1369 |  | 0
2026-06-10 | 541676.2137 |  | 541676.2137 |  | 0
2026-06-11 | 542964.2905 |  | 542964.2905 |  | 0
2026-06-12 | 544252.3673 |  | 544252.3673 |  | 0
2026-06-13 | 545540.4441 |  | 545540.4441 |  | 0
2026-06-14 | 546828.5209 |  | 546828.5209 |  | 0
2026-06-15 | 548116.5978 |  | 548116.5978 |  | 0
2026-06-16 | 549404.6746 |  | 549404.6746 |  | 0
2026-06-17 | 550692.7514 |  | 550692.7514 |  | 0
2026-06-18 | 551980.8282 |  | 551980.8282 |  | 0
2026-06-19 | 553268.905 |  | 553268.905 |  | 0
2026-06-20 | 554556.9819 |  | 554556.9819 |  | 0
2026-06-21 | 555845.0587 |  | 555845.0587 |  | 0
2026-06-22 | 557133.1355 |  | 557133.1355 |  | 0
2026-06-23 | 558421.2123 |  | 558421.2123 |  | 0
2026-06-24 | 559709.2891 |  | 559709.2891 |  | 0
2026-06-25 | 560997.3659 |  | 560997.3659 |  | 0
2026-06-26 | 562285.4428 |  | 562285.4428 |  | 0
2026-06-27 | 563573.5196 |  | 563573.5196 |  | 0
2026-06-28 | 564861.5964 |  | 564861.5964 |  | 0
2026-06-29 | 566149.6732 |  | 566149.6732 |  | 0
2026-06-30 | 567437.75 |  | 567437.75 |  | 0
2026-07-01 | 568725.8269 |  | 568725.8269 |  | 0
2026-07-02 | 570013.9037 |  | 570013.9037 |  | 0
2026-07-03 | 571301.9805 |  | 571301.9805 |  | 0
2026-07-04 | 572590.0573 |  | 572590.0573 |  | 0
2026-07-05 | 573878.1341 |  | 573878.1341 |  | 0
2026-07-06 | 575166.2109 |  | 575166.2109 |  | 0
2026-07-07 | 576454.2878 |  | 576454.2878 |  | 0
2026-07-08 | 577742.3646 |  | 577742.3646 |  | 0
2026-07-09 | 579030.4414 |  | 579030.4414 |  | 0
2026-07-10 | 580318.5182 |  | 580318.5182 |  | 0
2026-07-11 | 581606.595 |  | 581606.595 |  | 0
2026-07-12 | 582894.6719 |  | 582894.6719 |  | 0
2026-07-13 | 584182.7487 |  | 584182.7487 |  | 0
2026-07-14 | 585470.8255 |  | 585470.8255 |  | 0
2026-07-15 | 586758.9023 |  | 586758.9023 |  | 0
2026-07-16 | 588046.9791 |  | 588046.9791 |  | 0
2026-07-17 | 589335.0559 |  | 589335.0559 |  | 0
2026-07-18 | 590623.1328 |  | 590623.1328 |  | 0
2026-07-19 | 591911.2096 |  | 591911.2096 |  | 0
2026-07-20 | 593199.2864 |  | 593199.2864 |  | 0
2026-07-21 | 594487.3632 |  | 594487.3632 |  | 0
2026-07-22 | 595775.44 |  | 595775.44 |  | 0
2026-07-23 | 597063.5169 |  | 597063.5169 |  | 0
2026-07-24 | 598351.5937 |  | 598351.5937 |  | 0
2026-07-25 | 599639.6705 |  | 599639.6705 |  | 0
2026-07-26 | 600927.7473 |  | 600927.7473 |  | 0
2026-07-27 | 602215.8241 |  | 602215.8241 |  | 0
2026-07-28 | 603503.9009 |  | 603503.9009 |  | 0
2026-07-29 | 604791.9778 |  | 604791.9778 |  | 0
2026-07-30 | 606080.0546 |  | 606080.0546 |  | 0
2026-07-31 | 607368.1314 |  | 607368.1314 |  | 0
2026-08-01 | 608656.2082 |  | 608656.2082 |  | 0
2026-08-02 | 609944.285 |  | 609944.285 |  | 0
2026-08-03 | 611232.3619 |  | 611232.3619 |  | 0
2026-08-04 | 612520.4387 |  | 612520.4387 |  | 0
2026-08-05 | 613808.5155 |  | 613808.5155 |  | 0
2026-08-06 | 615096.5923 |  | 615096.5923 |  | 0
2026-08-07 | 616384.6691 |  | 616384.6691 |  | 0
2026-08-08 | 617672.7459 |  | 617672.7459 |  | 0
2026-08-09 | 618960.8228 |  | 618960.8228 |  | 0
2026-08-10 | 620248.8996 |  | 620248.8996 |  | 0
2026-08-11 | 621536.9764 |  | 621536.9764 |  | 0
2026-08-12 | 622825.0532 |  | 622825.0532 |  | 0
2026-08-13 | 624113.13 |  | 624113.13 |  | 0
2026-08-14 | 625401.2069 |  | 625401.2069 |  | 0
2026-08-15 | 626689.2837 |  | 626689.2837 |  | 0
2026-08-16 | 627977.3605 |  | 627977.3605 |  | 0
2026-08-17 | 629265.4373 |  | 629265.4373 |  | 0
2026-08-18 | 630553.5141 |  | 630553.5141 |  | 0
2026-08-19 | 631841.5909 |  | 631841.5909 |  | 0
2026-08-20 | 633129.6678 |  | 633129.6678 |  | 0
2026-08-21 | 634417.7446 |  | 634417.7446 |  | 0
2026-08-22 | 634417.7446 |  | 634417.7446 |  | 0
2026-08-23 | 634417.7446 |  | 634417.7446 |  | 0
2026-08-24 | 635634.2252 |  | 635634.2252 |  | 0
2026-08-25 | 636850.7058 |  | 636850.7058 |  | 0
2026-08-26 | 638067.1864 |  | 638067.1864 |  | 0
2026-08-27 | 639283.6671 |  | 639283.6671 |  | 0
2026-08-28 | 640500.1477 |  | 640500.1477 |  | 0
2026-08-29 | 641716.6283 |  | 641716.6283 |  | 0
2026-08-30 | 642933.1089 |  | 642933.1089 |  | 0
2026-08-31 | 644149.5895 |  | 644149.5895 |  | 0
2026-09-01 | 645366.0701 |  | 645366.0701 |  | 0
2026-09-02 | 646582.5508 |  | 646582.5508 |  | 0
2026-09-03 | 647799.0314 |  | 647799.0314 |  | 0
2026-09-04 | 649015.512 |  | 649015.512 |  | 0
2026-09-05 | 650231.9926 |  | 650231.9926 |  | 0
2026-09-06 | 651448.4732 |  | 651448.4732 |  | 0
2026-09-07 | 652664.9538 |  | 652664.9538 |  | 0
2026-09-08 | 653881.4345 |  | 653881.4345 |  | 0
2026-09-09 | 655097.9151 |  | 655097.9151 |  | 0
2026-09-10 | 656314.3957 |  | 656314.3957 |  | 0
2026-09-11 | 657530.8763 |  | 657530.8763 |  | 0
2026-09-12 | 658747.3569 |  | 658747.3569 |  | 0
2026-09-13 | 659963.8376 |  | 659963.8376 |  | 0
2026-09-14 | 661180.3182 |  | 661180.3182 |  | 0
2026-09-15 | 662396.7988 |  | 662396.7988 |  | 0
2026-09-16 | 663613.2794 |  | 663613.2794 |  | 0
2026-09-17 | 664829.76 |  | 664829.76 |  | 0
2026-09-18 | 666046.2406 |  | 666046.2406 |  | 0
2026-09-19 | 667262.7213 |  | 667262.7213 |  | 0
2026-09-20 | 668479.2019 |  | 668479.2019 |  | 0
2026-09-21 | 669695.6825 |  | 669695.6825 |  | 0
2026-09-22 | 670912.1631 |  | 670912.1631 |  | 0
2026-09-23 | 672128.6437 |  | 672128.6437 |  | 0
2026-09-24 | 673345.1244 |  | 673345.1244 |  | 0
2026-09-25 | 674561.605 |  | 674561.605 |  | 0

## Travel&perdiem (Direct Cost)
Date | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Planned 5105 · Travel - Airfare (Direct) (Cumulative) | Actual 5105 · Travel - Airfare (Direct) (Cumulative) | Planned 5106 · Travel - Hotel (Direct) (Cumulative) | Actual 5106 · Travel - Hotel (Direct) (Cumulative) | Planned 5107 · Travel - Other (Direct) (Cumulative) | Actual 5107 · Travel - Other (Direct) (Cumulative) | Planned 5108 · Meals & entertainment (Direct) (Cumulative) | Actual 5108 · Meals & entertainment (Direct) (Cumulative) | Planned 5122 · Motor vehicle exp (Direct) (Cumulative) | Actual 5122 · Motor vehicle exp (Direct) (Cumulative) | Planned 5123 · Auto fuel (Direct) (Cumulative) | Actual 5123 · Auto fuel (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 209.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 0 | 227.92 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-26 | 138.2843 | 227.92 | 23.0474 | 0 | 23.0474 | 0 | 23.0474 | 18 | 23.0474 | 0 | 23.0474 | 0 | 23.0474 | 0
2025-06-27 | 276.5686 | 227.92 | 46.0948 | 0 | 46.0948 | 0 | 46.0948 | 18 | 46.0948 | 0 | 46.0948 | 0 | 46.0948 | 0
2025-06-28 | 414.8529 | 227.92 | 69.1422 | 0 | 69.1422 | 0 | 69.1422 | 18 | 69.1422 | 0 | 69.1422 | 0 | 69.1422 | 0
2025-06-29 | 553.1373 | 227.92 | 92.1895 | 0 | 92.1895 | 0 | 92.1895 | 18 | 92.1895 | 0 | 92.1895 | 0 | 92.1895 | 0
2025-06-30 | 691.4216 | 227.92 | 115.2369 | 0 | 115.2369 | 0 | 115.2369 | 18 | 115.2369 | 0 | 115.2369 | 0 | 115.2369 | 0
2025-07-01 | 829.7059 | 227.92 | 138.2843 | 0 | 138.2843 | 0 | 138.2843 | 18 | 138.2843 | 0 | 138.2843 | 0 | 138.2843 | 0
2025-07-02 | 967.9902 | 227.92 | 161.3317 | 0 | 161.3317 | 0 | 161.3317 | 18 | 161.3317 | 0 | 161.3317 | 0 | 161.3317 | 0
2025-07-03 | 1106.2745 | 227.92 | 184.3791 | 0 | 184.3791 | 0 | 184.3791 | 18 | 184.3791 | 0 | 184.3791 | 0 | 184.3791 | 0
2025-07-04 | 1244.5588 | 227.92 | 207.4265 | 0 | 207.4265 | 0 | 207.4265 | 18 | 207.4265 | 0 | 207.4265 | 0 | 207.4265 | 0
2025-07-05 | 1382.8432 | 227.92 | 230.4739 | 0 | 230.4739 | 0 | 230.4739 | 18 | 230.4739 | 0 | 230.4739 | 0 | 230.4739 | 0
2025-07-06 | 1521.1275 | 227.92 | 253.5212 | 0 | 253.5212 | 0 | 253.5212 | 18 | 253.5212 | 0 | 253.5212 | 0 | 253.5212 | 0
2025-07-07 | 1659.4118 | 227.92 | 276.5686 | 0 | 276.5686 | 0 | 276.5686 | 18 | 276.5686 | 0 | 276.5686 | 0 | 276.5686 | 0
2025-07-08 | 1797.6961 | 227.92 | 299.616 | 0 | 299.616 | 0 | 299.616 | 18 | 299.616 | 0 | 299.616 | 0 | 299.616 | 0
2025-07-09 | 1935.9804 | 227.92 | 322.6634 | 0 | 322.6634 | 0 | 322.6634 | 18 | 322.6634 | 0 | 322.6634 | 0 | 322.6634 | 0
2025-07-10 | 2074.2647 | 227.92 | 345.7108 | 0 | 345.7108 | 0 | 345.7108 | 18 | 345.7108 | 0 | 345.7108 | 0 | 345.7108 | 0
2025-07-11 | 2212.549 | 227.92 | 368.7582 | 0 | 368.7582 | 0 | 368.7582 | 18 | 368.7582 | 0 | 368.7582 | 0 | 368.7582 | 0
2025-07-12 | 2350.8334 | 227.92 | 391.8056 | 0 | 391.8056 | 0 | 391.8056 | 18 | 391.8056 | 0 | 391.8056 | 0 | 391.8056 | 0
2025-07-13 | 2489.1177 | 227.92 | 414.8529 | 0 | 414.8529 | 0 | 414.8529 | 18 | 414.8529 | 0 | 414.8529 | 0 | 414.8529 | 0
2025-07-14 | 2627.402 | 1769.82 | 437.9003 | 1541.9 | 437.9003 | 0 | 437.9003 | 18 | 437.9003 | 0 | 437.9003 | 0 | 437.9003 | 0
2025-07-15 | 2765.6863 | 1769.82 | 460.9477 | 1541.9 | 460.9477 | 0 | 460.9477 | 18 | 460.9477 | 0 | 460.9477 | 0 | 460.9477 | 0
2025-07-16 | 2903.9706 | 1769.82 | 483.9951 | 1541.9 | 483.9951 | 0 | 483.9951 | 18 | 483.9951 | 0 | 483.9951 | 0 | 483.9951 | 0
2025-07-17 | 3042.2549 | 1834.27 | 507.0425 | 1541.9 | 507.0425 | 0 | 507.0425 | 18 | 507.0425 | 0 | 507.0425 | 0 | 507.0425 | 0
2025-07-18 | 3180.5393 | 1861.41 | 530.0899 | 1569.04 | 530.0899 | 0 | 530.0899 | 18 | 530.0899 | 0 | 530.0899 | 0 | 530.0899 | 0
2025-07-19 | 3318.8236 | 1891.41 | 553.1373 | 1569.04 | 553.1373 | 0 | 553.1373 | 48 | 553.1373 | 0 | 553.1373 | 0 | 553.1373 | 0
2025-07-20 | 3457.1079 | 1891.41 | 576.1846 | 1569.04 | 576.1846 | 0 | 576.1846 | 48 | 576.1846 | 0 | 576.1846 | 0 | 576.1846 | 0
2025-07-21 | 3595.3922 | 1891.41 | 599.232 | 1569.04 | 599.232 | 0 | 599.232 | 48 | 599.232 | 0 | 599.232 | 0 | 599.232 | 0
2025-07-22 | 3733.6765 | 1891.41 | 622.2794 | 1569.04 | 622.2794 | 0 | 622.2794 | 48 | 622.2794 | 0 | 622.2794 | 0 | 622.2794 | 0
2025-07-23 | 3871.9608 | 1891.41 | 645.3268 | 1569.04 | 645.3268 | 0 | 645.3268 | 48 | 645.3268 | 0 | 645.3268 | 0 | 645.3268 | 0
2025-07-24 | 4010.2452 | 1891.41 | 668.3742 | 1569.04 | 668.3742 | 0 | 668.3742 | 48 | 668.3742 | 0 | 668.3742 | 0 | 668.3742 | 0
2025-07-25 | 4148.5295 | 1891.41 | 691.4216 | 1569.04 | 691.4216 | 0 | 691.4216 | 48 | 691.4216 | 0 | 691.4216 | 0 | 691.4216 | 0
2025-07-26 | 4286.8138 | 1891.41 | 714.469 | 1569.04 | 714.469 | 0 | 714.469 | 48 | 714.469 | 0 | 714.469 | 0 | 714.469 | 0
2025-07-27 | 4425.0981 | 1891.41 | 737.5163 | 1569.04 | 737.5163 | 0 | 737.5163 | 48 | 737.5163 | 0 | 737.5163 | 0 | 737.5163 | 0
2025-07-28 | 4563.3824 | 1891.41 | 760.5637 | 1569.04 | 760.5637 | 0 | 760.5637 | 48 | 760.5637 | 0 | 760.5637 | 0 | 760.5637 | 0
2025-07-29 | 4701.6667 | 1891.41 | 783.6111 | 1569.04 | 783.6111 | 0 | 783.6111 | 48 | 783.6111 | 0 | 783.6111 | 0 | 783.6111 | 0
2025-07-30 | 4839.951 | 1891.41 | 806.6585 | 1569.04 | 806.6585 | 0 | 806.6585 | 48 | 806.6585 | 0 | 806.6585 | 0 | 806.6585 | 0
2025-07-31 | 4978.2354 | 1891.41 | 829.7059 | 1569.04 | 829.7059 | 0 | 829.7059 | 48 | 829.7059 | 0 | 829.7059 | 0 | 829.7059 | 0
2025-08-01 | 5116.5197 | 1891.41 | 852.7533 | 1569.04 | 852.7533 | 0 | 852.7533 | 48 | 852.7533 | 0 | 852.7533 | 0 | 852.7533 | 0
2025-08-02 | 5254.804 | 1891.41 | 875.8007 | 1569.04 | 875.8007 | 0 | 875.8007 | 48 | 875.8007 | 0 | 875.8007 | 0 | 875.8007 | 0
2025-08-03 | 5393.0883 | 1891.41 | 898.8481 | 1569.04 | 898.8481 | 0 | 898.8481 | 48 | 898.8481 | 0 | 898.8481 | 0 | 898.8481 | 0
2025-08-04 | 5531.3726 | 1891.41 | 921.8954 | 1569.04 | 921.8954 | 0 | 921.8954 | 48 | 921.8954 | 0 | 921.8954 | 0 | 921.8954 | 0
2025-08-05 | 5669.6569 | 1891.41 | 944.9428 | 1569.04 | 944.9428 | 0 | 944.9428 | 48 | 944.9428 | 0 | 944.9428 | 0 | 944.9428 | 0
2025-08-06 | 5807.9413 | 1891.41 | 967.9902 | 1569.04 | 967.9902 | 0 | 967.9902 | 48 | 967.9902 | 0 | 967.9902 | 0 | 967.9902 | 0
2025-08-07 | 5946.2256 | 1891.41 | 991.0376 | 1569.04 | 991.0376 | 0 | 991.0376 | 48 | 991.0376 | 0 | 991.0376 | 0 | 991.0376 | 0
2025-08-08 | 6084.5099 | 1891.41 | 1014.085 | 1569.04 | 1014.085 | 0 | 1014.085 | 48 | 1014.085 | 0 | 1014.085 | 0 | 1014.085 | 0
2025-08-09 | 6222.7942 | 1891.41 | 1037.1324 | 1569.04 | 1037.1324 | 0 | 1037.1324 | 48 | 1037.1324 | 0 | 1037.1324 | 0 | 1037.1324 | 0
2025-08-10 | 6361.0785 | 1891.41 | 1060.1798 | 1569.04 | 1060.1798 | 0 | 1060.1798 | 48 | 1060.1798 | 0 | 1060.1798 | 0 | 1060.1798 | 0
2025-08-11 | 6499.3628 | 1891.41 | 1083.2271 | 1569.04 | 1083.2271 | 0 | 1083.2271 | 48 | 1083.2271 | 0 | 1083.2271 | 0 | 1083.2271 | 0
2025-08-12 | 6637.6471 | 1891.41 | 1106.2745 | 1569.04 | 1106.2745 | 0 | 1106.2745 | 48 | 1106.2745 | 0 | 1106.2745 | 0 | 1106.2745 | 0
2025-08-13 | 6775.9315 | 1891.41 | 1129.3219 | 1569.04 | 1129.3219 | 0 | 1129.3219 | 48 | 1129.3219 | 0 | 1129.3219 | 0 | 1129.3219 | 0
2025-08-14 | 6914.2158 | 1891.41 | 1152.3693 | 1569.04 | 1152.3693 | 0 | 1152.3693 | 48 | 1152.3693 | 0 | 1152.3693 | 0 | 1152.3693 | 0
2025-08-15 | 7052.5001 | 1891.41 | 1175.4167 | 1569.04 | 1175.4167 | 0 | 1175.4167 | 48 | 1175.4167 | 0 | 1175.4167 | 0 | 1175.4167 | 0
2025-08-16 | 7190.7844 | 1891.41 | 1198.4641 | 1569.04 | 1198.4641 | 0 | 1198.4641 | 48 | 1198.4641 | 0 | 1198.4641 | 0 | 1198.4641 | 0
2025-08-17 | 7329.0687 | 1891.41 | 1221.5115 | 1569.04 | 1221.5115 | 0 | 1221.5115 | 48 | 1221.5115 | 0 | 1221.5115 | 0 | 1221.5115 | 0
2025-08-18 | 7467.353 | 1891.41 | 1244.5588 | 1569.04 | 1244.5588 | 0 | 1244.5588 | 48 | 1244.5588 | 0 | 1244.5588 | 0 | 1244.5588 | 0
2025-08-19 | 7605.6374 | 1891.41 | 1267.6062 | 1569.04 | 1267.6062 | 0 | 1267.6062 | 48 | 1267.6062 | 0 | 1267.6062 | 0 | 1267.6062 | 0
2025-08-20 | 7743.9217 | 2030.22 | 1290.6536 | 1569.04 | 1290.6536 | 0 | 1290.6536 | 48 | 1290.6536 | 0 | 1290.6536 | 0 | 1290.6536 | 0
2025-08-21 | 7882.206 | 2030.22 | 1313.701 | 1569.04 | 1313.701 | 0 | 1313.701 | 48 | 1313.701 | 0 | 1313.701 | 0 | 1313.701 | 0
2025-08-22 | 8020.4903 | 2130.22 | 1336.7484 | 1569.04 | 1336.7484 | 0 | 1336.7484 | 48 | 1336.7484 | 100 | 1336.7484 | 0 | 1336.7484 | 0
2025-08-23 | 8158.7746 | 2130.22 | 1359.7958 | 1569.04 | 1359.7958 | 0 | 1359.7958 | 48 | 1359.7958 | 100 | 1359.7958 | 0 | 1359.7958 | 0
2025-08-24 | 8297.0589 | 2130.22 | 1382.8432 | 1569.04 | 1382.8432 | 0 | 1382.8432 | 48 | 1382.8432 | 100 | 1382.8432 | 0 | 1382.8432 | 0
2025-08-25 | 8435.3433 | 2130.22 | 1405.8905 | 1569.04 | 1405.8905 | 0 | 1405.8905 | 48 | 1405.8905 | 100 | 1405.8905 | 0 | 1405.8905 | 0
2025-08-26 | 8573.6276 | 2130.22 | 1428.9379 | 1569.04 | 1428.9379 | 0 | 1428.9379 | 48 | 1428.9379 | 100 | 1428.9379 | 0 | 1428.9379 | 0
2025-08-27 | 8711.9119 | 2130.22 | 1451.9853 | 1569.04 | 1451.9853 | 0 | 1451.9853 | 48 | 1451.9853 | 100 | 1451.9853 | 0 | 1451.9853 | 0
2025-08-28 | 8850.1962 | 2130.22 | 1475.0327 | 1569.04 | 1475.0327 | 0 | 1475.0327 | 48 | 1475.0327 | 100 | 1475.0327 | 0 | 1475.0327 | 0
2025-08-29 | 8988.4805 | 2130.22 | 1498.0801 | 1569.04 | 1498.0801 | 0 | 1498.0801 | 48 | 1498.0801 | 100 | 1498.0801 | 0 | 1498.0801 | 0
2025-08-30 | 9126.7648 | 2130.22 | 1521.1275 | 1569.04 | 1521.1275 | 0 | 1521.1275 | 48 | 1521.1275 | 100 | 1521.1275 | 0 | 1521.1275 | 0
2025-08-31 | 9265.0491 | 2130.22 | 1544.1749 | 1569.04 | 1544.1749 | 0 | 1544.1749 | 48 | 1544.1749 | 100 | 1544.1749 | 0 | 1544.1749 | 0
2025-09-01 | 9403.3335 | 2130.22 | 1567.2222 | 1569.04 | 1567.2222 | 0 | 1567.2222 | 48 | 1567.2222 | 100 | 1567.2222 | 0 | 1567.2222 | 0
2025-09-02 | 9541.6178 | 2130.22 | 1590.2696 | 1569.04 | 1590.2696 | 0 | 1590.2696 | 48 | 1590.2696 | 100 | 1590.2696 | 0 | 1590.2696 | 0
2025-09-03 | 9679.9021 | 2130.22 | 1613.317 | 1569.04 | 1613.317 | 0 | 1613.317 | 48 | 1613.317 | 100 | 1613.317 | 0 | 1613.317 | 0
2025-09-04 | 9818.1864 | 2130.22 | 1636.3644 | 1569.04 | 1636.3644 | 0 | 1636.3644 | 48 | 1636.3644 | 100 | 1636.3644 | 0 | 1636.3644 | 0
2025-09-05 | 9956.4707 | 2130.22 | 1659.4118 | 1569.04 | 1659.4118 | 0 | 1659.4118 | 48 | 1659.4118 | 100 | 1659.4118 | 0 | 1659.4118 | 0
2025-09-06 | 10094.755 | 2130.22 | 1682.4592 | 1569.04 | 1682.4592 | 0 | 1682.4592 | 48 | 1682.4592 | 100 | 1682.4592 | 0 | 1682.4592 | 0
2025-09-07 | 10233.0394 | 2130.22 | 1705.5066 | 1569.04 | 1705.5066 | 0 | 1705.5066 | 48 | 1705.5066 | 100 | 1705.5066 | 0 | 1705.5066 | 0
2025-09-08 | 10371.3237 | 2130.22 | 1728.5539 | 1569.04 | 1728.5539 | 0 | 1728.5539 | 48 | 1728.5539 | 100 | 1728.5539 | 0 | 1728.5539 | 0
2025-09-09 | 10509.608 | 2130.22 | 1751.6013 | 1569.04 | 1751.6013 | 0 | 1751.6013 | 48 | 1751.6013 | 100 | 1751.6013 | 0 | 1751.6013 | 0
2025-09-10 | 10647.8923 | 2130.22 | 1774.6487 | 1569.04 | 1774.6487 | 0 | 1774.6487 | 48 | 1774.6487 | 100 | 1774.6487 | 0 | 1774.6487 | 0
2025-09-11 | 10786.1766 | 2130.22 | 1797.6961 | 1569.04 | 1797.6961 | 0 | 1797.6961 | 48 | 1797.6961 | 100 | 1797.6961 | 0 | 1797.6961 | 0
2025-09-12 | 10924.4609 | 2241.16 | 1820.7435 | 1569.04 | 1820.7435 | 0 | 1820.7435 | 158.94 | 1820.7435 | 100 | 1820.7435 | 0 | 1820.7435 | 0
2025-09-13 | 11062.7452 | 2241.16 | 1843.7909 | 1569.04 | 1843.7909 | 0 | 1843.7909 | 158.94 | 1843.7909 | 100 | 1843.7909 | 0 | 1843.7909 | 0
2025-09-14 | 11201.0296 | 2241.16 | 1866.8383 | 1569.04 | 1866.8383 | 0 | 1866.8383 | 158.94 | 1866.8383 | 100 | 1866.8383 | 0 | 1866.8383 | 0
2025-09-15 | 11339.3139 | 2691.16 | 1889.8856 | 1569.04 | 1889.8856 | 0 | 1889.8856 | 158.94 | 1889.8856 | 550 | 1889.8856 | 0 | 1889.8856 | 0
2025-09-16 | 11477.5982 | 2691.16 | 1912.933 | 1569.04 | 1912.933 | 0 | 1912.933 | 158.94 | 1912.933 | 550 | 1912.933 | 0 | 1912.933 | 0
2025-09-17 | 11615.8825 | 2691.16 | 1935.9804 | 1569.04 | 1935.9804 | 0 | 1935.9804 | 158.94 | 1935.9804 | 550 | 1935.9804 | 0 | 1935.9804 | 0
2025-09-18 | 11754.1668 | 2691.16 | 1959.0278 | 1569.04 | 1959.0278 | 0 | 1959.0278 | 158.94 | 1959.0278 | 550 | 1959.0278 | 0 | 1959.0278 | 0
2025-09-19 | 11892.4511 | 2691.16 | 1982.0752 | 1569.04 | 1982.0752 | 0 | 1982.0752 | 158.94 | 1982.0752 | 550 | 1982.0752 | 0 | 1982.0752 | 0
2025-09-20 | 12030.7355 | 2691.16 | 2005.1226 | 1569.04 | 2005.1226 | 0 | 2005.1226 | 158.94 | 2005.1226 | 550 | 2005.1226 | 0 | 2005.1226 | 0
2025-09-21 | 12169.0198 | 2691.16 | 2028.17 | 1569.04 | 2028.17 | 0 | 2028.17 | 158.94 | 2028.17 | 550 | 2028.17 | 0 | 2028.17 | 0
2025-09-22 | 12307.3041 | 2991.16 | 2051.2173 | 1569.04 | 2051.2173 | 0 | 2051.2173 | 158.94 | 2051.2173 | 850 | 2051.2173 | 0 | 2051.2173 | 0
2025-09-23 | 12445.5884 | 2991.16 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-24 | 12445.5884 | 2991.16 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-25 | 12445.5884 | 2991.16 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-26 | 12445.5884 | 2991.16 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-27 | 12445.5884 | 2991.16 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-28 | 12445.5884 | 2991.16 | 2074.2647 | 1569.04 | 2074.2647 | 0 | 2074.2647 | 158.94 | 2074.2647 | 850 | 2074.2647 | 0 | 2074.2647 | 0
2025-09-29 | 13451.8732 | 4391.16 | 2241.9789 | 1569.04 | 2241.9789 | 0 | 2241.9789 | 158.94 | 2241.9789 | 2250 | 2241.9789 | 0 | 2241.9789 | 0
2025-09-30 | 14458.1581 | 4391.16 | 2409.693 | 1569.04 | 2409.693 | 0 | 2409.693 | 158.94 | 2409.693 | 2250 | 2409.693 | 0 | 2409.693 | 0
2025-10-01 | 15464.4429 | 4391.16 | 2577.4072 | 1569.04 | 2577.4072 | 0 | 2577.4072 | 158.94 | 2577.4072 | 2250 | 2577.4072 | 0 | 2577.4072 | 0
2025-10-02 | 16470.7278 | 4391.16 | 2745.1213 | 1569.04 | 2745.1213 | 0 | 2745.1213 | 158.94 | 2745.1213 | 2250 | 2745.1213 | 0 | 2745.1213 | 0
2025-10-03 | 17477.0126 | 4891.16 | 2912.8354 | 1569.04 | 2912.8354 | 0 | 2912.8354 | 158.94 | 2912.8354 | 2750 | 2912.8354 | 0 | 2912.8354 | 0
2025-10-04 | 18483.2974 | 4891.16 | 3080.5496 | 1569.04 | 3080.5496 | 0 | 3080.5496 | 158.94 | 3080.5496 | 2750 | 3080.5496 | 0 | 3080.5496 | 0
2025-10-05 | 19489.5823 | 4891.16 | 3248.2637 | 1569.04 | 3248.2637 | 0 | 3248.2637 | 158.94 | 3248.2637 | 2750 | 3248.2637 | 0 | 3248.2637 | 0
2025-10-06 | 20495.8671 | 4891.16 | 3415.9779 | 1569.04 | 3415.9779 | 0 | 3415.9779 | 158.94 | 3415.9779 | 2750 | 3415.9779 | 0 | 3415.9779 | 0
2025-10-07 | 21502.152 | 4891.16 | 3583.692 | 1569.04 | 3583.692 | 0 | 3583.692 | 158.94 | 3583.692 | 2750 | 3583.692 | 0 | 3583.692 | 0
2025-10-08 | 22508.4368 | 4891.16 | 3751.4061 | 1569.04 | 3751.4061 | 0 | 3751.4061 | 158.94 | 3751.4061 | 2750 | 3751.4061 | 0 | 3751.4061 | 0
2025-10-09 | 23514.7216 | 4891.16 | 3919.1203 | 1569.04 | 3919.1203 | 0 | 3919.1203 | 158.94 | 3919.1203 | 2750 | 3919.1203 | 0 | 3919.1203 | 0
2025-10-10 | 24521.0065 | 4891.16 | 4086.8344 | 1569.04 | 4086.8344 | 0 | 4086.8344 | 158.94 | 4086.8344 | 2750 | 4086.8344 | 0 | 4086.8344 | 0
2025-10-11 | 25527.2913 | 4891.16 | 4254.5486 | 1569.04 | 4254.5486 | 0 | 4254.5486 | 158.94 | 4254.5486 | 2750 | 4254.5486 | 0 | 4254.5486 | 0
2025-10-12 | 26533.5761 | 4891.16 | 4422.2627 | 1569.04 | 4422.2627 | 0 | 4422.2627 | 158.94 | 4422.2627 | 2750 | 4422.2627 | 0 | 4422.2627 | 0
2025-10-13 | 27539.861 |  | 4589.9768 |  | 4589.9768 |  | 4589.9768 |  | 4589.9768 |  | 4589.9768 |  | 4589.9768
2025-10-14 | 28546.1458 |  | 4757.691 |  | 4757.691 |  | 4757.691 |  | 4757.691 |  | 4757.691 |  | 4757.691
2025-10-15 | 29552.4307 |  | 4925.4051 |  | 4925.4051 |  | 4925.4051 |  | 4925.4051 |  | 4925.4051 |  | 4925.4051
2025-10-16 | 30558.7155 |  | 5093.1192 |  | 5093.1192 |  | 5093.1192 |  | 5093.1192 |  | 5093.1192 |  | 5093.1192
2025-10-17 | 31565.0003 |  | 5260.8334 |  | 5260.8334 |  | 5260.8334 |  | 5260.8334 |  | 5260.8334 |  | 5260.8334
2025-10-18 | 32571.2852 |  | 5428.5475 |  | 5428.5475 |  | 5428.5475 |  | 5428.5475 |  | 5428.5475 |  | 5428.5475
2025-10-19 | 33577.57 |  | 5596.2617 |  | 5596.2617 |  | 5596.2617 |  | 5596.2617 |  | 5596.2617 |  | 5596.2617
2025-10-20 | 34583.8548 |  | 5763.9758 |  | 5763.9758 |  | 5763.9758 |  | 5763.9758 |  | 5763.9758 |  | 5763.9758
2025-10-21 | 35590.1397 |  | 5931.6899 |  | 5931.6899 |  | 5931.6899 |  | 5931.6899 |  | 5931.6899 |  | 5931.6899
2025-10-22 | 36596.4245 |  | 6099.4041 |  | 6099.4041 |  | 6099.4041 |  | 6099.4041 |  | 6099.4041 |  | 6099.4041
2025-10-23 | 37602.7094 |  | 6267.1182 |  | 6267.1182 |  | 6267.1182 |  | 6267.1182 |  | 6267.1182 |  | 6267.1182
2025-10-24 | 38608.9942 |  | 6434.8324 |  | 6434.8324 |  | 6434.8324 |  | 6434.8324 |  | 6434.8324 |  | 6434.8324
2025-10-25 | 39615.279 |  | 6602.5465 |  | 6602.5465 |  | 6602.5465 |  | 6602.5465 |  | 6602.5465 |  | 6602.5465
2025-10-26 | 40621.5639 |  | 6770.2606 |  | 6770.2606 |  | 6770.2606 |  | 6770.2606 |  | 6770.2606 |  | 6770.2606
2025-10-27 | 41627.8487 |  | 6937.9748 |  | 6937.9748 |  | 6937.9748 |  | 6937.9748 |  | 6937.9748 |  | 6937.9748
2025-10-28 | 42634.1336 |  | 7105.6889 |  | 7105.6889 |  | 7105.6889 |  | 7105.6889 |  | 7105.6889 |  | 7105.6889
2025-10-29 | 43640.4184 |  | 7273.4031 |  | 7273.4031 |  | 7273.4031 |  | 7273.4031 |  | 7273.4031 |  | 7273.4031
2025-10-30 | 44646.7032 |  | 7441.1172 |  | 7441.1172 |  | 7441.1172 |  | 7441.1172 |  | 7441.1172 |  | 7441.1172
2025-10-31 | 45652.9881 |  | 7608.8313 |  | 7608.8313 |  | 7608.8313 |  | 7608.8313 |  | 7608.8313 |  | 7608.8313
2025-11-01 | 46659.2729 |  | 7776.5455 |  | 7776.5455 |  | 7776.5455 |  | 7776.5455 |  | 7776.5455 |  | 7776.5455
2025-11-02 | 47665.5577 |  | 7944.2596 |  | 7944.2596 |  | 7944.2596 |  | 7944.2596 |  | 7944.2596 |  | 7944.2596
2025-11-03 | 48671.8426 |  | 8111.9738 |  | 8111.9738 |  | 8111.9738 |  | 8111.9738 |  | 8111.9738 |  | 8111.9738
2025-11-04 | 49678.1274 |  | 8279.6879 |  | 8279.6879 |  | 8279.6879 |  | 8279.6879 |  | 8279.6879 |  | 8279.6879
2025-11-05 | 50684.4123 |  | 8447.402 |  | 8447.402 |  | 8447.402 |  | 8447.402 |  | 8447.402 |  | 8447.402
2025-11-06 | 51690.6971 |  | 8615.1162 |  | 8615.1162 |  | 8615.1162 |  | 8615.1162 |  | 8615.1162 |  | 8615.1162
2025-11-07 | 52696.9819 |  | 8782.8303 |  | 8782.8303 |  | 8782.8303 |  | 8782.8303 |  | 8782.8303 |  | 8782.8303
2025-11-08 | 53703.2668 |  | 8950.5445 |  | 8950.5445 |  | 8950.5445 |  | 8950.5445 |  | 8950.5445 |  | 8950.5445
2025-11-09 | 54709.5516 |  | 9118.2586 |  | 9118.2586 |  | 9118.2586 |  | 9118.2586 |  | 9118.2586 |  | 9118.2586
2025-11-10 | 55715.8365 |  | 9285.9727 |  | 9285.9727 |  | 9285.9727 |  | 9285.9727 |  | 9285.9727 |  | 9285.9727
2025-11-11 | 56722.1213 |  | 9453.6869 |  | 9453.6869 |  | 9453.6869 |  | 9453.6869 |  | 9453.6869 |  | 9453.6869
2025-11-12 | 57728.4061 |  | 9621.401 |  | 9621.401 |  | 9621.401 |  | 9621.401 |  | 9621.401 |  | 9621.401
2025-11-13 | 58734.691 |  | 9789.1152 |  | 9789.1152 |  | 9789.1152 |  | 9789.1152 |  | 9789.1152 |  | 9789.1152
2025-11-14 | 59740.9758 |  | 9956.8293 |  | 9956.8293 |  | 9956.8293 |  | 9956.8293 |  | 9956.8293 |  | 9956.8293
2025-11-15 | 60747.2606 |  | 10124.5434 |  | 10124.5434 |  | 10124.5434 |  | 10124.5434 |  | 10124.5434 |  | 10124.5434
2025-11-16 | 61753.5455 |  | 10292.2576 |  | 10292.2576 |  | 10292.2576 |  | 10292.2576 |  | 10292.2576 |  | 10292.2576
2025-11-17 | 62759.8303 |  | 10459.9717 |  | 10459.9717 |  | 10459.9717 |  | 10459.9717 |  | 10459.9717 |  | 10459.9717
2025-11-18 | 63766.1152 |  | 10627.6859 |  | 10627.6859 |  | 10627.6859 |  | 10627.6859 |  | 10627.6859 |  | 10627.6859
2025-11-19 | 64772.4 |  | 10795.4 |  | 10795.4 |  | 10795.4 |  | 10795.4 |  | 10795.4 |  | 10795.4
2025-11-20 | 65367.498 |  | 10894.583 |  | 10894.583 |  | 10894.583 |  | 10894.583 |  | 10894.583 |  | 10894.583
2025-11-21 | 65962.5961 |  | 10993.766 |  | 10993.766 |  | 10993.766 |  | 10993.766 |  | 10993.766 |  | 10993.766
2025-11-22 | 66557.6941 |  | 11092.949 |  | 11092.949 |  | 11092.949 |  | 11092.949 |  | 11092.949 |  | 11092.949
2025-11-23 | 67152.7922 |  | 11192.132 |  | 11192.132 |  | 11192.132 |  | 11192.132 |  | 11192.132 |  | 11192.132
2025-11-24 | 67747.8902 |  | 11291.315 |  | 11291.315 |  | 11291.315 |  | 11291.315 |  | 11291.315 |  | 11291.315
2025-11-25 | 68342.9882 |  | 11390.498 |  | 11390.498 |  | 11390.498 |  | 11390.498 |  | 11390.498 |  | 11390.498
2025-11-26 | 68938.0863 |  | 11489.681 |  | 11489.681 |  | 11489.681 |  | 11489.681 |  | 11489.681 |  | 11489.681
2025-11-27 | 69533.1843 |  | 11588.8641 |  | 11588.8641 |  | 11588.8641 |  | 11588.8641 |  | 11588.8641 |  | 11588.8641
2025-11-28 | 70128.2824 |  | 11688.0471 |  | 11688.0471 |  | 11688.0471 |  | 11688.0471 |  | 11688.0471 |  | 11688.0471
2025-11-29 | 70723.3804 |  | 11787.2301 |  | 11787.2301 |  | 11787.2301 |  | 11787.2301 |  | 11787.2301 |  | 11787.2301
2025-11-30 | 71318.4784 |  | 11886.4131 |  | 11886.4131 |  | 11886.4131 |  | 11886.4131 |  | 11886.4131 |  | 11886.4131
2025-12-01 | 71913.5765 |  | 11985.5961 |  | 11985.5961 |  | 11985.5961 |  | 11985.5961 |  | 11985.5961 |  | 11985.5961
2025-12-02 | 72508.6745 |  | 12084.7791 |  | 12084.7791 |  | 12084.7791 |  | 12084.7791 |  | 12084.7791 |  | 12084.7791
2025-12-03 | 73103.7725 |  | 12183.9621 |  | 12183.9621 |  | 12183.9621 |  | 12183.9621 |  | 12183.9621 |  | 12183.9621
2025-12-04 | 73698.8706 |  | 12283.1451 |  | 12283.1451 |  | 12283.1451 |  | 12283.1451 |  | 12283.1451 |  | 12283.1451
2025-12-05 | 74293.9686 |  | 12382.3281 |  | 12382.3281 |  | 12382.3281 |  | 12382.3281 |  | 12382.3281 |  | 12382.3281
2025-12-06 | 74889.0667 |  | 12481.5111 |  | 12481.5111 |  | 12481.5111 |  | 12481.5111 |  | 12481.5111 |  | 12481.5111
2025-12-07 | 75484.1647 |  | 12580.6941 |  | 12580.6941 |  | 12580.6941 |  | 12580.6941 |  | 12580.6941 |  | 12580.6941
2025-12-08 | 76079.2627 |  | 12679.8771 |  | 12679.8771 |  | 12679.8771 |  | 12679.8771 |  | 12679.8771 |  | 12679.8771
2025-12-09 | 76674.3608 |  | 12779.0601 |  | 12779.0601 |  | 12779.0601 |  | 12779.0601 |  | 12779.0601 |  | 12779.0601
2025-12-10 | 77269.4588 |  | 12878.2431 |  | 12878.2431 |  | 12878.2431 |  | 12878.2431 |  | 12878.2431 |  | 12878.2431
2025-12-11 | 77864.5569 |  | 12977.4261 |  | 12977.4261 |  | 12977.4261 |  | 12977.4261 |  | 12977.4261 |  | 12977.4261
2025-12-12 | 78459.6549 |  | 13076.6092 |  | 13076.6092 |  | 13076.6092 |  | 13076.6092 |  | 13076.6092 |  | 13076.6092
2025-12-13 | 79054.7529 |  | 13175.7922 |  | 13175.7922 |  | 13175.7922 |  | 13175.7922 |  | 13175.7922 |  | 13175.7922
2025-12-14 | 79649.851 |  | 13274.9752 |  | 13274.9752 |  | 13274.9752 |  | 13274.9752 |  | 13274.9752 |  | 13274.9752
2025-12-15 | 80244.949 |  | 13374.1582 |  | 13374.1582 |  | 13374.1582 |  | 13374.1582 |  | 13374.1582 |  | 13374.1582
2025-12-16 | 80840.0471 |  | 13473.3412 |  | 13473.3412 |  | 13473.3412 |  | 13473.3412 |  | 13473.3412 |  | 13473.3412
2025-12-17 | 81435.1451 |  | 13572.5242 |  | 13572.5242 |  | 13572.5242 |  | 13572.5242 |  | 13572.5242 |  | 13572.5242
2025-12-18 | 82030.2431 |  | 13671.7072 |  | 13671.7072 |  | 13671.7072 |  | 13671.7072 |  | 13671.7072 |  | 13671.7072
2025-12-19 | 82625.3412 |  | 13770.8902 |  | 13770.8902 |  | 13770.8902 |  | 13770.8902 |  | 13770.8902 |  | 13770.8902
2025-12-20 | 83220.4392 |  | 13870.0732 |  | 13870.0732 |  | 13870.0732 |  | 13870.0732 |  | 13870.0732 |  | 13870.0732
2025-12-21 | 83815.5373 |  | 13969.2562 |  | 13969.2562 |  | 13969.2562 |  | 13969.2562 |  | 13969.2562 |  | 13969.2562
2025-12-22 | 84410.6353 |  | 14068.4392 |  | 14068.4392 |  | 14068.4392 |  | 14068.4392 |  | 14068.4392 |  | 14068.4392
2025-12-23 | 85005.7333 |  | 14167.6222 |  | 14167.6222 |  | 14167.6222 |  | 14167.6222 |  | 14167.6222 |  | 14167.6222
2025-12-24 | 85600.8314 |  | 14266.8052 |  | 14266.8052 |  | 14266.8052 |  | 14266.8052 |  | 14266.8052 |  | 14266.8052
2025-12-25 | 86195.9294 |  | 14365.9882 |  | 14365.9882 |  | 14365.9882 |  | 14365.9882 |  | 14365.9882 |  | 14365.9882
2025-12-26 | 86791.0275 |  | 14465.1712 |  | 14465.1712 |  | 14465.1712 |  | 14465.1712 |  | 14465.1712 |  | 14465.1712
2025-12-27 | 87386.1255 |  | 14564.3542 |  | 14564.3542 |  | 14564.3542 |  | 14564.3542 |  | 14564.3542 |  | 14564.3542
2025-12-28 | 87981.2235 |  | 14663.5373 |  | 14663.5373 |  | 14663.5373 |  | 14663.5373 |  | 14663.5373 |  | 14663.5373
2025-12-29 | 88576.3216 |  | 14762.7203 |  | 14762.7203 |  | 14762.7203 |  | 14762.7203 |  | 14762.7203 |  | 14762.7203
2025-12-30 | 89171.4196 |  | 14861.9033 |  | 14861.9033 |  | 14861.9033 |  | 14861.9033 |  | 14861.9033 |  | 14861.9033
2025-12-31 | 89766.5176 |  | 14961.0863 |  | 14961.0863 |  | 14961.0863 |  | 14961.0863 |  | 14961.0863 |  | 14961.0863
2026-01-01 | 90361.6157 |  | 15060.2693 |  | 15060.2693 |  | 15060.2693 |  | 15060.2693 |  | 15060.2693 |  | 15060.2693
2026-01-02 | 90956.7137 |  | 15159.4523 |  | 15159.4523 |  | 15159.4523 |  | 15159.4523 |  | 15159.4523 |  | 15159.4523
2026-01-03 | 91551.8118 |  | 15258.6353 |  | 15258.6353 |  | 15258.6353 |  | 15258.6353 |  | 15258.6353 |  | 15258.6353
2026-01-04 | 92146.9098 |  | 15357.8183 |  | 15357.8183 |  | 15357.8183 |  | 15357.8183 |  | 15357.8183 |  | 15357.8183
2026-01-05 | 92742.0078 |  | 15457.0013 |  | 15457.0013 |  | 15457.0013 |  | 15457.0013 |  | 15457.0013 |  | 15457.0013
2026-01-06 | 93337.1059 |  | 15556.1843 |  | 15556.1843 |  | 15556.1843 |  | 15556.1843 |  | 15556.1843 |  | 15556.1843
2026-01-07 | 93932.2039 |  | 15655.3673 |  | 15655.3673 |  | 15655.3673 |  | 15655.3673 |  | 15655.3673 |  | 15655.3673
2026-01-08 | 94527.302 |  | 15754.5503 |  | 15754.5503 |  | 15754.5503 |  | 15754.5503 |  | 15754.5503 |  | 15754.5503
2026-01-09 | 95122.4 |  | 15853.7333 |  | 15853.7333 |  | 15853.7333 |  | 15853.7333 |  | 15853.7333 |  | 15853.7333
2026-01-10 | 95717.498 |  | 15952.9163 |  | 15952.9163 |  | 15952.9163 |  | 15952.9163 |  | 15952.9163 |  | 15952.9163
2026-01-11 | 96312.5961 |  | 16052.0993 |  | 16052.0993 |  | 16052.0993 |  | 16052.0993 |  | 16052.0993 |  | 16052.0993
2026-01-12 | 96907.6941 |  | 16151.2824 |  | 16151.2824 |  | 16151.2824 |  | 16151.2824 |  | 16151.2824 |  | 16151.2824
2026-01-13 | 97502.7922 |  | 16250.4654 |  | 16250.4654 |  | 16250.4654 |  | 16250.4654 |  | 16250.4654 |  | 16250.4654
2026-01-14 | 98097.8902 |  | 16349.6484 |  | 16349.6484 |  | 16349.6484 |  | 16349.6484 |  | 16349.6484 |  | 16349.6484
2026-01-15 | 98692.9882 |  | 16448.8314 |  | 16448.8314 |  | 16448.8314 |  | 16448.8314 |  | 16448.8314 |  | 16448.8314
2026-01-16 | 99288.0863 |  | 16548.0144 |  | 16548.0144 |  | 16548.0144 |  | 16548.0144 |  | 16548.0144 |  | 16548.0144
2026-01-17 | 99883.1843 |  | 16647.1974 |  | 16647.1974 |  | 16647.1974 |  | 16647.1974 |  | 16647.1974 |  | 16647.1974
2026-01-18 | 100478.2824 |  | 16746.3804 |  | 16746.3804 |  | 16746.3804 |  | 16746.3804 |  | 16746.3804 |  | 16746.3804
2026-01-19 | 101073.3804 |  | 16845.5634 |  | 16845.5634 |  | 16845.5634 |  | 16845.5634 |  | 16845.5634 |  | 16845.5634
2026-01-20 | 101668.4784 |  | 16944.7464 |  | 16944.7464 |  | 16944.7464 |  | 16944.7464 |  | 16944.7464 |  | 16944.7464
2026-01-21 | 102263.5765 |  | 17043.9294 |  | 17043.9294 |  | 17043.9294 |  | 17043.9294 |  | 17043.9294 |  | 17043.9294
2026-01-22 | 102858.6745 |  | 17143.1124 |  | 17143.1124 |  | 17143.1124 |  | 17143.1124 |  | 17143.1124 |  | 17143.1124
2026-01-23 | 103453.7725 |  | 17242.2954 |  | 17242.2954 |  | 17242.2954 |  | 17242.2954 |  | 17242.2954 |  | 17242.2954
2026-01-24 | 104048.8706 |  | 17341.4784 |  | 17341.4784 |  | 17341.4784 |  | 17341.4784 |  | 17341.4784 |  | 17341.4784
2026-01-25 | 104643.9686 |  | 17440.6614 |  | 17440.6614 |  | 17440.6614 |  | 17440.6614 |  | 17440.6614 |  | 17440.6614
2026-01-26 | 105239.0667 |  | 17539.8444 |  | 17539.8444 |  | 17539.8444 |  | 17539.8444 |  | 17539.8444 |  | 17539.8444
2026-01-27 | 105834.1647 |  | 17639.0275 |  | 17639.0275 |  | 17639.0275 |  | 17639.0275 |  | 17639.0275 |  | 17639.0275
2026-01-28 | 106429.2627 |  | 17738.2105 |  | 17738.2105 |  | 17738.2105 |  | 17738.2105 |  | 17738.2105 |  | 17738.2105
2026-01-29 | 107024.3608 |  | 17837.3935 |  | 17837.3935 |  | 17837.3935 |  | 17837.3935 |  | 17837.3935 |  | 17837.3935
2026-01-30 | 107619.4588 |  | 17936.5765 |  | 17936.5765 |  | 17936.5765 |  | 17936.5765 |  | 17936.5765 |  | 17936.5765
2026-01-31 | 108214.5569 |  | 18035.7595 |  | 18035.7595 |  | 18035.7595 |  | 18035.7595 |  | 18035.7595 |  | 18035.7595
2026-02-01 | 108809.6549 |  | 18134.9425 |  | 18134.9425 |  | 18134.9425 |  | 18134.9425 |  | 18134.9425 |  | 18134.9425
2026-02-02 | 109404.7529 |  | 18234.1255 |  | 18234.1255 |  | 18234.1255 |  | 18234.1255 |  | 18234.1255 |  | 18234.1255
2026-02-03 | 109999.851 |  | 18333.3085 |  | 18333.3085 |  | 18333.3085 |  | 18333.3085 |  | 18333.3085 |  | 18333.3085
2026-02-04 | 110594.949 |  | 18432.4915 |  | 18432.4915 |  | 18432.4915 |  | 18432.4915 |  | 18432.4915 |  | 18432.4915
2026-02-05 | 111190.0471 |  | 18531.6745 |  | 18531.6745 |  | 18531.6745 |  | 18531.6745 |  | 18531.6745 |  | 18531.6745
2026-02-06 | 111785.1451 |  | 18630.8575 |  | 18630.8575 |  | 18630.8575 |  | 18630.8575 |  | 18630.8575 |  | 18630.8575
2026-02-07 | 112380.2431 |  | 18730.0405 |  | 18730.0405 |  | 18730.0405 |  | 18730.0405 |  | 18730.0405 |  | 18730.0405
2026-02-08 | 112975.3412 |  | 18829.2235 |  | 18829.2235 |  | 18829.2235 |  | 18829.2235 |  | 18829.2235 |  | 18829.2235
2026-02-09 | 113570.4392 |  | 18928.4065 |  | 18928.4065 |  | 18928.4065 |  | 18928.4065 |  | 18928.4065 |  | 18928.4065
2026-02-10 | 114165.5373 |  | 19027.5895 |  | 19027.5895 |  | 19027.5895 |  | 19027.5895 |  | 19027.5895 |  | 19027.5895
2026-02-11 | 114760.6353 |  | 19126.7725 |  | 19126.7725 |  | 19126.7725 |  | 19126.7725 |  | 19126.7725 |  | 19126.7725
2026-02-12 | 115355.7333 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556 |  | 19225.9556
2026-02-13 | 115675.3825 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304 |  | 19279.2304
2026-02-14 | 115995.0316 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053 |  | 19332.5053
2026-02-15 | 116314.6807 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801 |  | 19385.7801
2026-02-16 | 116634.3298 |  | 19439.055 |  | 19439.055 |  | 19439.055 |  | 19439.055 |  | 19439.055 |  | 19439.055
2026-02-17 | 116953.9789 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298 |  | 19492.3298
2026-02-18 | 117273.6281 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047 |  | 19545.6047
2026-02-19 | 117593.2772 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795 |  | 19598.8795
2026-02-20 | 117912.9263 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544 |  | 19652.1544
2026-02-21 | 118232.5754 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292 |  | 19705.4292
2026-02-22 | 118552.2246 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041 |  | 19758.7041
2026-02-23 | 118871.8737 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789 |  | 19811.9789
2026-02-24 | 119191.5228 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538 |  | 19865.2538
2026-02-25 | 119511.1719 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287 |  | 19918.5287
2026-02-26 | 119830.8211 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035 |  | 19971.8035
2026-02-27 | 120150.4702 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784 |  | 20025.0784
2026-02-28 | 120470.1193 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532 |  | 20078.3532
2026-03-01 | 120789.7684 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281 |  | 20131.6281
2026-03-02 | 121109.4175 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029 |  | 20184.9029
2026-03-03 | 121429.0667 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778 |  | 20238.1778
2026-03-04 | 121748.7158 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526 |  | 20291.4526
2026-03-05 | 122068.3649 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275 |  | 20344.7275
2026-03-06 | 122388.014 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023 |  | 20398.0023
2026-03-07 | 122707.6632 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772 |  | 20451.2772
2026-03-08 | 123027.3123 |  | 20504.552 |  | 20504.552 |  | 20504.552 |  | 20504.552 |  | 20504.552 |  | 20504.552
2026-03-09 | 123346.9614 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269 |  | 20557.8269
2026-03-10 | 123666.6105 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018 |  | 20611.1018
2026-03-11 | 123986.2596 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766 |  | 20664.3766
2026-03-12 | 124305.9088 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515 |  | 20717.6515
2026-03-13 | 124625.5579 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263 |  | 20770.9263
2026-03-14 | 124945.207 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012 |  | 20824.2012
2026-03-15 | 125264.8561 |  | 20877.476 |  | 20877.476 |  | 20877.476 |  | 20877.476 |  | 20877.476 |  | 20877.476
2026-03-16 | 125584.5053 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509 |  | 20930.7509
2026-03-17 | 125904.1544 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257 |  | 20984.0257
2026-03-18 | 126223.8035 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006 |  | 21037.3006
2026-03-19 | 126543.4526 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754 |  | 21090.5754
2026-03-20 | 126863.1018 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503 |  | 21143.8503
2026-03-21 | 127182.7509 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251 |  | 21197.1251
2026-03-22 | 127502.4 |  | 21250.4 |  | 21250.4 |  | 21250.4 |  | 21250.4 |  | 21250.4 |  | 21250.4
2026-03-23 | 127822.0491 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749 |  | 21303.6749
2026-03-24 | 128141.6982 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497 |  | 21356.9497
2026-03-25 | 128461.3474 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246 |  | 21410.2246
2026-03-26 | 128780.9965 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994 |  | 21463.4994
2026-03-27 | 129100.6456 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743 |  | 21516.7743
2026-03-28 | 129420.2947 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491 |  | 21570.0491
2026-03-29 | 129739.9439 |  | 21623.324 |  | 21623.324 |  | 21623.324 |  | 21623.324 |  | 21623.324 |  | 21623.324
2026-03-30 | 130059.593 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988 |  | 21676.5988
2026-03-31 | 130379.2421 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737 |  | 21729.8737
2026-04-01 | 130698.8912 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485 |  | 21783.1485
2026-04-02 | 131018.5404 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234 |  | 21836.4234
2026-04-03 | 131338.1895 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982 |  | 21889.6982
2026-04-04 | 131657.8386 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731 |  | 21942.9731
2026-04-05 | 131977.4877 |  | 21996.248 |  | 21996.248 |  | 21996.248 |  | 21996.248 |  | 21996.248 |  | 21996.248
2026-04-06 | 132297.1368 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228 |  | 22049.5228
2026-04-07 | 132616.786 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977 |  | 22102.7977
2026-04-08 | 132936.4351 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725 |  | 22156.0725
2026-04-09 | 133256.0842 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474 |  | 22209.3474
2026-04-10 | 133575.7333 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222 |  | 22262.6222
2026-04-11 | 133895.3825 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971 |  | 22315.8971
2026-04-12 | 134215.0316 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719 |  | 22369.1719
2026-04-13 | 134534.6807 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468 |  | 22422.4468
2026-04-14 | 134854.3298 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216 |  | 22475.7216
2026-04-15 | 135173.9789 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965 |  | 22528.9965
2026-04-16 | 135493.6281 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713 |  | 22582.2713
2026-04-17 | 135813.2772 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462 |  | 22635.5462
2026-04-18 | 136132.9263 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211 |  | 22688.8211
2026-04-19 | 136452.5754 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959 |  | 22742.0959
2026-04-20 | 136772.2246 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708 |  | 22795.3708
2026-04-21 | 137091.8737 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456 |  | 22848.6456
2026-04-22 | 137411.5228 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205 |  | 22901.9205
2026-04-23 | 137731.1719 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953 |  | 22955.1953
2026-04-24 | 138050.8211 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702 |  | 23008.4702
2026-04-25 | 138370.4702 |  | 23061.745 |  | 23061.745 |  | 23061.745 |  | 23061.745 |  | 23061.745 |  | 23061.745
2026-04-26 | 138690.1193 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199 |  | 23115.0199
2026-04-27 | 139009.7684 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947 |  | 23168.2947
2026-04-28 | 139329.4175 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696 |  | 23221.5696
2026-04-29 | 139649.0667 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444 |  | 23274.8444
2026-04-30 | 139968.7158 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193 |  | 23328.1193
2026-05-01 | 140288.3649 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942 |  | 23381.3942
2026-05-02 | 140608.014 |  | 23434.669 |  | 23434.669 |  | 23434.669 |  | 23434.669 |  | 23434.669 |  | 23434.669
2026-05-03 | 140927.6632 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439 |  | 23487.9439
2026-05-04 | 141247.3123 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187 |  | 23541.2187
2026-05-05 | 141566.9614 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936 |  | 23594.4936
2026-05-06 | 141886.6105 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684 |  | 23647.7684
2026-05-07 | 142206.2596 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433 |  | 23701.0433
2026-05-08 | 142525.9088 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181 |  | 23754.3181
2026-05-09 | 142845.5579 |  | 23807.593 |  | 23807.593 |  | 23807.593 |  | 23807.593 |  | 23807.593 |  | 23807.593
2026-05-10 | 143165.207 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678 |  | 23860.8678
2026-05-11 | 143484.8561 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427 |  | 23914.1427
2026-05-12 | 143804.5053 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175 |  | 23967.4175
2026-05-13 | 144124.1544 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924 |  | 24020.6924
2026-05-14 | 144443.8035 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673 |  | 24073.9673
2026-05-15 | 144763.4526 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421 |  | 24127.2421
2026-05-16 | 145083.1018 |  | 24180.517 |  | 24180.517 |  | 24180.517 |  | 24180.517 |  | 24180.517 |  | 24180.517
2026-05-17 | 145402.7509 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918 |  | 24233.7918
2026-05-18 | 145722.4 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667 |  | 24287.0667
2026-05-19 | 146042.0491 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415 |  | 24340.3415
2026-05-20 | 146361.6982 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164 |  | 24393.6164
2026-05-21 | 146681.3474 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912 |  | 24446.8912
2026-05-22 | 147000.9965 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661 |  | 24500.1661
2026-05-23 | 147320.6456 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409 |  | 24553.4409
2026-05-24 | 147640.2947 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158 |  | 24606.7158
2026-05-25 | 147959.9439 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906 |  | 24659.9906
2026-05-26 | 148279.593 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655 |  | 24713.2655
2026-05-27 | 148599.2421 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404 |  | 24766.5404
2026-05-28 | 148918.8912 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152 |  | 24819.8152
2026-05-29 | 149238.5404 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901 |  | 24873.0901
2026-05-30 | 149558.1895 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649 |  | 24926.3649
2026-05-31 | 149877.8386 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398 |  | 24979.6398
2026-06-01 | 150197.4877 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146 |  | 25032.9146
2026-06-02 | 150517.1368 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895 |  | 25086.1895
2026-06-03 | 150836.786 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643 |  | 25139.4643
2026-06-04 | 151156.4351 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392 |  | 25192.7392
2026-06-05 | 151476.0842 |  | 25246.014 |  | 25246.014 |  | 25246.014 |  | 25246.014 |  | 25246.014 |  | 25246.014
2026-06-06 | 151795.7333 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889 |  | 25299.2889
2026-06-07 | 152115.3825 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637 |  | 25352.5637
2026-06-08 | 152435.0316 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386 |  | 25405.8386
2026-06-09 | 152754.6807 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135 |  | 25459.1135
2026-06-10 | 153074.3298 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883 |  | 25512.3883
2026-06-11 | 153393.9789 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632 |  | 25565.6632
2026-06-12 | 153713.6281 |  | 25618.938 |  | 25618.938 |  | 25618.938 |  | 25618.938 |  | 25618.938 |  | 25618.938
2026-06-13 | 154033.2772 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129 |  | 25672.2129
2026-06-14 | 154352.9263 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877 |  | 25725.4877
2026-06-15 | 154672.5754 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626 |  | 25778.7626
2026-06-16 | 154992.2246 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374 |  | 25832.0374
2026-06-17 | 155311.8737 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123 |  | 25885.3123
2026-06-18 | 155631.5228 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871 |  | 25938.5871
2026-06-19 | 155951.1719 |  | 25991.862 |  | 25991.862 |  | 25991.862 |  | 25991.862 |  | 25991.862 |  | 25991.862
2026-06-20 | 156270.8211 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368 |  | 26045.1368
2026-06-21 | 156590.4702 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117 |  | 26098.4117
2026-06-22 | 156910.1193 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865 |  | 26151.6865
2026-06-23 | 157229.7684 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614 |  | 26204.9614
2026-06-24 | 157549.4175 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363 |  | 26258.2363
2026-06-25 | 157869.0667 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111 |  | 26311.5111
2026-06-26 | 158188.7158 |  | 26364.786 |  | 26364.786 |  | 26364.786 |  | 26364.786 |  | 26364.786 |  | 26364.786
2026-06-27 | 158508.3649 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608 |  | 26418.0608
2026-06-28 | 158828.014 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357 |  | 26471.3357
2026-06-29 | 159147.6632 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105 |  | 26524.6105
2026-06-30 | 159467.3123 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854 |  | 26577.8854
2026-07-01 | 159786.9614 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602 |  | 26631.1602
2026-07-02 | 160106.6105 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351 |  | 26684.4351
2026-07-03 | 160426.2596 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099 |  | 26737.7099
2026-07-04 | 160745.9088 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848 |  | 26790.9848
2026-07-05 | 161065.5579 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596 |  | 26844.2596
2026-07-06 | 161385.207 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345 |  | 26897.5345
2026-07-07 | 161704.8561 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094 |  | 26950.8094
2026-07-08 | 162024.5053 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842 |  | 27004.0842
2026-07-09 | 162344.1544 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591 |  | 27057.3591
2026-07-10 | 162663.8035 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339 |  | 27110.6339
2026-07-11 | 162983.4526 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088 |  | 27163.9088
2026-07-12 | 163303.1018 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836 |  | 27217.1836
2026-07-13 | 163622.7509 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585 |  | 27270.4585
2026-07-14 | 163942.4 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333 |  | 27323.7333
2026-07-15 | 164262.0491 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082 |  | 27377.0082
2026-07-16 | 164581.6982 |  | 27430.283 |  | 27430.283 |  | 27430.283 |  | 27430.283 |  | 27430.283 |  | 27430.283
2026-07-17 | 164901.3474 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579 |  | 27483.5579
2026-07-18 | 165220.9965 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327 |  | 27536.8327
2026-07-19 | 165540.6456 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076 |  | 27590.1076
2026-07-20 | 165860.2947 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825 |  | 27643.3825
2026-07-21 | 166179.9439 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573 |  | 27696.6573
2026-07-22 | 166499.593 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322 |  | 27749.9322
2026-07-23 | 166819.2421 |  | 27803.207 |  | 27803.207 |  | 27803.207 |  | 27803.207 |  | 27803.207 |  | 27803.207
2026-07-24 | 167138.8912 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819 |  | 27856.4819
2026-07-25 | 167458.5404 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567 |  | 27909.7567
2026-07-26 | 167778.1895 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316 |  | 27963.0316
2026-07-27 | 168097.8386 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064 |  | 28016.3064
2026-07-28 | 168417.4877 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813 |  | 28069.5813
2026-07-29 | 168737.1368 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561 |  | 28122.8561
2026-07-30 | 169056.786 |  | 28176.131 |  | 28176.131 |  | 28176.131 |  | 28176.131 |  | 28176.131 |  | 28176.131
2026-07-31 | 169376.4351 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058 |  | 28229.4058
2026-08-01 | 169696.0842 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807 |  | 28282.6807
2026-08-02 | 170015.7333 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556 |  | 28335.9556
2026-08-03 | 170335.3825 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304 |  | 28389.2304
2026-08-04 | 170655.0316 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053 |  | 28442.5053
2026-08-05 | 170974.6807 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801 |  | 28495.7801
2026-08-06 | 171294.3298 |  | 28549.055 |  | 28549.055 |  | 28549.055 |  | 28549.055 |  | 28549.055 |  | 28549.055
2026-08-07 | 171613.9789 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298 |  | 28602.3298
2026-08-08 | 171933.6281 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047 |  | 28655.6047
2026-08-09 | 172253.2772 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795 |  | 28708.8795
2026-08-10 | 172572.9263 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544 |  | 28762.1544
2026-08-11 | 172892.5754 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292 |  | 28815.4292
2026-08-12 | 173212.2246 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041 |  | 28868.7041
2026-08-13 | 173531.8737 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789 |  | 28921.9789
2026-08-14 | 173851.5228 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538 |  | 28975.2538
2026-08-15 | 174171.1719 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287 |  | 29028.5287
2026-08-16 | 174490.8211 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035 |  | 29081.8035
2026-08-17 | 174810.4702 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784 |  | 29135.0784
2026-08-18 | 175130.1193 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532 |  | 29188.3532
2026-08-19 | 175449.7684 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281 |  | 29241.6281
2026-08-20 | 175769.4175 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029 |  | 29294.9029
2026-08-21 | 176089.0667 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778
2026-08-22 | 176089.0667 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778
2026-08-23 | 176089.0667 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778 |  | 29348.1778
2026-08-24 | 176538.0566 |  | 29423.0094 |  | 29423.0094 |  | 29423.0094 |  | 29423.0094 |  | 29423.0094 |  | 29423.0094
2026-08-25 | 176987.0465 |  | 29497.8411 |  | 29497.8411 |  | 29497.8411 |  | 29497.8411 |  | 29497.8411 |  | 29497.8411
2026-08-26 | 177436.0364 |  | 29572.6727 |  | 29572.6727 |  | 29572.6727 |  | 29572.6727 |  | 29572.6727 |  | 29572.6727
2026-08-27 | 177885.0263 |  | 29647.5044 |  | 29647.5044 |  | 29647.5044 |  | 29647.5044 |  | 29647.5044 |  | 29647.5044
2026-08-28 | 178334.0162 |  | 29722.336 |  | 29722.336 |  | 29722.336 |  | 29722.336 |  | 29722.336 |  | 29722.336
2026-08-29 | 178783.0061 |  | 29797.1677 |  | 29797.1677 |  | 29797.1677 |  | 29797.1677 |  | 29797.1677 |  | 29797.1677
2026-08-30 | 179231.996 |  | 29871.9993 |  | 29871.9993 |  | 29871.9993 |  | 29871.9993 |  | 29871.9993 |  | 29871.9993
2026-08-31 | 179680.9859 |  | 29946.831 |  | 29946.831 |  | 29946.831 |  | 29946.831 |  | 29946.831 |  | 29946.831
2026-09-01 | 180129.9758 |  | 30021.6626 |  | 30021.6626 |  | 30021.6626 |  | 30021.6626 |  | 30021.6626 |  | 30021.6626
2026-09-02 | 180578.9657 |  | 30096.4943 |  | 30096.4943 |  | 30096.4943 |  | 30096.4943 |  | 30096.4943 |  | 30096.4943
2026-09-03 | 181027.9556 |  | 30171.3259 |  | 30171.3259 |  | 30171.3259 |  | 30171.3259 |  | 30171.3259 |  | 30171.3259
2026-09-04 | 181476.9455 |  | 30246.1576 |  | 30246.1576 |  | 30246.1576 |  | 30246.1576 |  | 30246.1576 |  | 30246.1576
2026-09-05 | 181925.9354 |  | 30320.9892 |  | 30320.9892 |  | 30320.9892 |  | 30320.9892 |  | 30320.9892 |  | 30320.9892
2026-09-06 | 182374.9253 |  | 30395.8209 |  | 30395.8209 |  | 30395.8209 |  | 30395.8209 |  | 30395.8209 |  | 30395.8209
2026-09-07 | 182823.9152 |  | 30470.6525 |  | 30470.6525 |  | 30470.6525 |  | 30470.6525 |  | 30470.6525 |  | 30470.6525
2026-09-08 | 183272.9051 |  | 30545.4842 |  | 30545.4842 |  | 30545.4842 |  | 30545.4842 |  | 30545.4842 |  | 30545.4842
2026-09-09 | 183721.8949 |  | 30620.3158 |  | 30620.3158 |  | 30620.3158 |  | 30620.3158 |  | 30620.3158 |  | 30620.3158
2026-09-10 | 184170.8848 |  | 30695.1475 |  | 30695.1475 |  | 30695.1475 |  | 30695.1475 |  | 30695.1475 |  | 30695.1475
2026-09-11 | 184619.8747 |  | 30769.9791 |  | 30769.9791 |  | 30769.9791 |  | 30769.9791 |  | 30769.9791 |  | 30769.9791
2026-09-12 | 185068.8646 |  | 30844.8108 |  | 30844.8108 |  | 30844.8108 |  | 30844.8108 |  | 30844.8108 |  | 30844.8108
2026-09-13 | 185517.8545 |  | 30919.6424 |  | 30919.6424 |  | 30919.6424 |  | 30919.6424 |  | 30919.6424 |  | 30919.6424
2026-09-14 | 185966.8444 |  | 30994.4741 |  | 30994.4741 |  | 30994.4741 |  | 30994.4741 |  | 30994.4741 |  | 30994.4741
2026-09-15 | 186415.8343 |  | 31069.3057 |  | 31069.3057 |  | 31069.3057 |  | 31069.3057 |  | 31069.3057 |  | 31069.3057
2026-09-16 | 186864.8242 |  | 31144.1374 |  | 31144.1374 |  | 31144.1374 |  | 31144.1374 |  | 31144.1374 |  | 31144.1374
2026-09-17 | 187313.8141 |  | 31218.969 |  | 31218.969 |  | 31218.969 |  | 31218.969 |  | 31218.969 |  | 31218.969
2026-09-18 | 187762.804 |  | 31293.8007 |  | 31293.8007 |  | 31293.8007 |  | 31293.8007 |  | 31293.8007 |  | 31293.8007
2026-09-19 | 188211.7939 |  | 31368.6323 |  | 31368.6323 |  | 31368.6323 |  | 31368.6323 |  | 31368.6323 |  | 31368.6323
2026-09-20 | 188660.7838 |  | 31443.464 |  | 31443.464 |  | 31443.464 |  | 31443.464 |  | 31443.464 |  | 31443.464
2026-09-21 | 189109.7737 |  | 31518.2956 |  | 31518.2956 |  | 31518.2956 |  | 31518.2956 |  | 31518.2956 |  | 31518.2956
2026-09-22 | 189558.7636 |  | 31593.1273 |  | 31593.1273 |  | 31593.1273 |  | 31593.1273 |  | 31593.1273 |  | 31593.1273
2026-09-23 | 190007.7535 |  | 31667.9589 |  | 31667.9589 |  | 31667.9589 |  | 31667.9589 |  | 31667.9589 |  | 31667.9589
2026-09-24 | 190456.7434 |  | 31742.7906 |  | 31742.7906 |  | 31742.7906 |  | 31742.7906 |  | 31742.7906 |  | 31742.7906
2026-09-25 | 190905.7333 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222 |  | 31817.6222

## Parts&materials (Direct Cost)
Date | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Planned 5004 · GTR Cost of Sales - Parts (Cumulative) | Actual 5004 · GTR Cost of Sales - Parts (Cumulative) | Planned 5111 · Parts & material costs (Direct) (Cumulative) | Actual 5111 · Parts & material costs (Direct) (Cumulative) | Planned 5128 · Health & Safety Equip (Direct) (Cumulative) | Actual 5128 · Health & Safety Equip (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-12 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-13 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-14 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-15 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-16 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-17 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-18 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-19 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-20 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-21 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-22 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-23 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-24 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-25 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-26 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-27 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-28 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-29 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-04-30 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-01 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-02 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-03 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-04 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-05 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-06 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-07 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-08 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-09 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-10 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-11 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-12 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-13 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-14 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-15 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-16 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-17 | 0 | 37.03 | 0 | 0 | 0 | 37.03 | 0 | 0
2025-05-18 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-19 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-20 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-21 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-22 | 0 | 800.64 | 0 | 0 | 0 | 800.64 | 0 | 0
2025-05-23 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-24 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-25 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-26 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-27 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-28 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-29 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-30 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-05-31 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-01 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-02 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-03 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-04 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-05 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-06 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-07 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-08 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-09 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-10 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-11 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-12 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-13 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-14 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-15 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-16 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-17 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-18 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-19 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-20 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-21 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-22 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-23 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-24 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-25 | 0 | 979.62 | 0 | 0 | 0 | 979.62 | 0 | 0
2025-06-26 | 705.7078 | 979.62 | 235.2359 | 0 | 235.2359 | 979.62 | 235.2359 | 0
2025-06-27 | 1411.4156 | 979.62 | 470.4719 | 0 | 470.4719 | 979.62 | 470.4719 | 0
2025-06-28 | 2117.1233 | 979.62 | 705.7078 | 0 | 705.7078 | 979.62 | 705.7078 | 0
2025-06-29 | 2822.8311 | 979.62 | 940.9437 | 0 | 940.9437 | 979.62 | 940.9437 | 0
2025-06-30 | 3528.5389 | 979.62 | 1176.1796 | 0 | 1176.1796 | 979.62 | 1176.1796 | 0
2025-07-01 | 4234.2467 | 979.62 | 1411.4156 | 0 | 1411.4156 | 979.62 | 1411.4156 | 0
2025-07-02 | 4939.9544 | 979.62 | 1646.6515 | 0 | 1646.6515 | 979.62 | 1646.6515 | 0
2025-07-03 | 5645.6622 | 979.62 | 1881.8874 | 0 | 1881.8874 | 979.62 | 1881.8874 | 0
2025-07-04 | 6351.37 | 979.62 | 2117.1233 | 0 | 2117.1233 | 979.62 | 2117.1233 | 0
2025-07-05 | 7057.0778 | 979.62 | 2352.3593 | 0 | 2352.3593 | 979.62 | 2352.3593 | 0
2025-07-06 | 7762.7856 | 979.62 | 2587.5952 | 0 | 2587.5952 | 979.62 | 2587.5952 | 0
2025-07-07 | 8468.4933 | 979.62 | 2822.8311 | 0 | 2822.8311 | 979.62 | 2822.8311 | 0
2025-07-08 | 9174.2011 | 979.62 | 3058.067 | 0 | 3058.067 | 979.62 | 3058.067 | 0
2025-07-09 | 9879.9089 | 979.62 | 3293.303 | 0 | 3293.303 | 979.62 | 3293.303 | 0
2025-07-10 | 10585.6167 | 979.62 | 3528.5389 | 0 | 3528.5389 | 979.62 | 3528.5389 | 0
2025-07-11 | 11291.3244 | 979.62 | 3763.7748 | 0 | 3763.7748 | 979.62 | 3763.7748 | 0
2025-07-12 | 11997.0322 | 979.62 | 3999.0107 | 0 | 3999.0107 | 979.62 | 3999.0107 | 0
2025-07-13 | 12702.74 | 979.62 | 4234.2467 | 0 | 4234.2467 | 979.62 | 4234.2467 | 0
2025-07-14 | 13408.4478 | 979.62 | 4469.4826 | 0 | 4469.4826 | 979.62 | 4469.4826 | 0
2025-07-15 | 14114.1556 | 979.62 | 4704.7185 | 0 | 4704.7185 | 979.62 | 4704.7185 | 0
2025-07-16 | 14819.8633 | 979.62 | 4939.9544 | 0 | 4939.9544 | 979.62 | 4939.9544 | 0
2025-07-17 | 15525.5711 | 979.62 | 5175.1904 | 0 | 5175.1904 | 979.62 | 5175.1904 | 0
2025-07-18 | 16231.2789 | 979.62 | 5410.4263 | 0 | 5410.4263 | 979.62 | 5410.4263 | 0
2025-07-19 | 16936.9867 | 979.62 | 5645.6622 | 0 | 5645.6622 | 979.62 | 5645.6622 | 0
2025-07-20 | 17642.6944 | 979.62 | 5880.8981 | 0 | 5880.8981 | 979.62 | 5880.8981 | 0
2025-07-21 | 18348.4022 | 979.62 | 6116.1341 | 0 | 6116.1341 | 979.62 | 6116.1341 | 0
2025-07-22 | 19054.11 | 979.62 | 6351.37 | 0 | 6351.37 | 979.62 | 6351.37 | 0
2025-07-23 | 19759.8178 | 979.62 | 6586.6059 | 0 | 6586.6059 | 979.62 | 6586.6059 | 0
2025-07-24 | 20465.5256 | 979.62 | 6821.8419 | 0 | 6821.8419 | 979.62 | 6821.8419 | 0
2025-07-25 | 21171.2333 | 979.62 | 7057.0778 | 0 | 7057.0778 | 979.62 | 7057.0778 | 0
2025-07-26 | 21876.9411 | 979.62 | 7292.3137 | 0 | 7292.3137 | 979.62 | 7292.3137 | 0
2025-07-27 | 22582.6489 | 979.62 | 7527.5496 | 0 | 7527.5496 | 979.62 | 7527.5496 | 0
2025-07-28 | 23288.3567 | 979.62 | 7762.7856 | 0 | 7762.7856 | 979.62 | 7762.7856 | 0
2025-07-29 | 23994.0644 | 979.62 | 7998.0215 | 0 | 7998.0215 | 979.62 | 7998.0215 | 0
2025-07-30 | 24699.7722 | 979.62 | 8233.2574 | 0 | 8233.2574 | 979.62 | 8233.2574 | 0
2025-07-31 | 25405.48 | 979.62 | 8468.4933 | 0 | 8468.4933 | 979.62 | 8468.4933 | 0
2025-08-01 | 26111.1878 | 979.62 | 8703.7293 | 0 | 8703.7293 | 979.62 | 8703.7293 | 0
2025-08-02 | 26816.8956 | 979.62 | 8938.9652 | 0 | 8938.9652 | 979.62 | 8938.9652 | 0
2025-08-03 | 27522.6033 | 979.62 | 9174.2011 | 0 | 9174.2011 | 979.62 | 9174.2011 | 0
2025-08-04 | 28228.3111 | 2348.77 | 9409.437 | 0 | 9409.437 | 2348.77 | 9409.437 | 0
2025-08-05 | 28934.0189 | 2348.77 | 9644.673 | 0 | 9644.673 | 2348.77 | 9644.673 | 0
2025-08-06 | 29639.7267 | 2348.77 | 9879.9089 | 0 | 9879.9089 | 2348.77 | 9879.9089 | 0
2025-08-07 | 30345.4344 | 3299.64 | 10115.1448 | 0 | 10115.1448 | 3299.64 | 10115.1448 | 0
2025-08-08 | 31051.1422 | 3299.64 | 10350.3807 | 0 | 10350.3807 | 3299.64 | 10350.3807 | 0
2025-08-09 | 31756.85 | 3299.64 | 10585.6167 | 0 | 10585.6167 | 3299.64 | 10585.6167 | 0
2025-08-10 | 32462.5578 | 3299.64 | 10820.8526 | 0 | 10820.8526 | 3299.64 | 10820.8526 | 0
2025-08-11 | 33168.2656 | 3566.53 | 11056.0885 | 0 | 11056.0885 | 3566.53 | 11056.0885 | 0
2025-08-12 | 33873.9733 | 3566.53 | 11291.3244 | 0 | 11291.3244 | 3566.53 | 11291.3244 | 0
2025-08-13 | 34579.6811 | 3566.53 | 11526.5604 | 0 | 11526.5604 | 3566.53 | 11526.5604 | 0
2025-08-14 | 35285.3889 | 3566.53 | 11761.7963 | 0 | 11761.7963 | 3566.53 | 11761.7963 | 0
2025-08-15 | 35991.0967 | 3566.53 | 11997.0322 | 0 | 11997.0322 | 3566.53 | 11997.0322 | 0
2025-08-16 | 36696.8044 | 3566.53 | 12232.2681 | 0 | 12232.2681 | 3566.53 | 12232.2681 | 0
2025-08-17 | 37402.5122 | 3566.53 | 12467.5041 | 0 | 12467.5041 | 3566.53 | 12467.5041 | 0
2025-08-18 | 38108.22 | 3566.53 | 12702.74 | 0 | 12702.74 | 3566.53 | 12702.74 | 0
2025-08-19 | 38813.9278 | 16075.89 | 12937.9759 | 0 | 12937.9759 | 16075.89 | 12937.9759 | 0
2025-08-20 | 39519.6356 | 16075.89 | 13173.2119 | 0 | 13173.2119 | 16075.89 | 13173.2119 | 0
2025-08-21 | 40225.3433 | 16075.89 | 13408.4478 | 0 | 13408.4478 | 16075.89 | 13408.4478 | 0
2025-08-22 | 40931.0511 | 16075.89 | 13643.6837 | 0 | 13643.6837 | 16075.89 | 13643.6837 | 0
2025-08-23 | 41636.7589 | 16075.89 | 13878.9196 | 0 | 13878.9196 | 16075.89 | 13878.9196 | 0
2025-08-24 | 42342.4667 | 16075.89 | 14114.1556 | 0 | 14114.1556 | 16075.89 | 14114.1556 | 0
2025-08-25 | 43048.1744 | 16795.65 | 14349.3915 | 0 | 14349.3915 | 16795.65 | 14349.3915 | 0
2025-08-26 | 43753.8822 | 16795.65 | 14584.6274 | 0 | 14584.6274 | 16795.65 | 14584.6274 | 0
2025-08-27 | 44459.59 | 16795.65 | 14819.8633 | 0 | 14819.8633 | 16795.65 | 14819.8633 | 0
2025-08-28 | 45165.2978 | 16795.65 | 15055.0993 | 0 | 15055.0993 | 16795.65 | 15055.0993 | 0
2025-08-29 | 45871.0056 | 16795.65 | 15290.3352 | 0 | 15290.3352 | 16795.65 | 15290.3352 | 0
2025-08-30 | 46576.7133 | 16795.65 | 15525.5711 | 0 | 15525.5711 | 16795.65 | 15525.5711 | 0
2025-08-31 | 47282.4211 | 16795.65 | 15760.807 | 0 | 15760.807 | 16795.65 | 15760.807 | 0
2025-09-01 | 47988.1289 | 16795.65 | 15996.043 | 0 | 15996.043 | 16795.65 | 15996.043 | 0
2025-09-02 | 48693.8367 | 19920.45 | 16231.2789 | 0 | 16231.2789 | 19920.45 | 16231.2789 | 0
2025-09-03 | 49399.5444 | 19920.45 | 16466.5148 | 0 | 16466.5148 | 19920.45 | 16466.5148 | 0
2025-09-04 | 50105.2522 | 19920.45 | 16701.7507 | 0 | 16701.7507 | 19920.45 | 16701.7507 | 0
2025-09-05 | 50810.96 | 19920.45 | 16936.9867 | 0 | 16936.9867 | 19920.45 | 16936.9867 | 0
2025-09-06 | 51516.6678 | 19920.45 | 17172.2226 | 0 | 17172.2226 | 19920.45 | 17172.2226 | 0
2025-09-07 | 52222.3756 | 19920.45 | 17407.4585 | 0 | 17407.4585 | 19920.45 | 17407.4585 | 0
2025-09-08 | 52928.0833 | 19920.45 | 17642.6944 | 0 | 17642.6944 | 19920.45 | 17642.6944 | 0
2025-09-09 | 53633.7911 | 20562.81 | 17877.9304 | 0 | 17877.9304 | 20562.81 | 17877.9304 | 0
2025-09-10 | 54339.4989 | 20562.81 | 18113.1663 | 0 | 18113.1663 | 20562.81 | 18113.1663 | 0
2025-09-11 | 55045.2067 | 20562.81 | 18348.4022 | 0 | 18348.4022 | 20562.81 | 18348.4022 | 0
2025-09-12 | 55750.9144 | 20562.81 | 18583.6381 | 0 | 18583.6381 | 20562.81 | 18583.6381 | 0
2025-09-13 | 56456.6222 | 20562.81 | 18818.8741 | 0 | 18818.8741 | 20562.81 | 18818.8741 | 0
2025-09-14 | 57162.33 | 20562.81 | 19054.11 | 0 | 19054.11 | 20562.81 | 19054.11 | 0
2025-09-15 | 57868.0378 | 20562.81 | 19289.3459 | 0 | 19289.3459 | 20562.81 | 19289.3459 | 0
2025-09-16 | 58573.7456 | 20562.81 | 19524.5819 | 0 | 19524.5819 | 20562.81 | 19524.5819 | 0
2025-09-17 | 59279.4533 | 20562.81 | 19759.8178 | 0 | 19759.8178 | 20562.81 | 19759.8178 | 0
2025-09-18 | 59985.1611 | 20562.81 | 19995.0537 | 0 | 19995.0537 | 20562.81 | 19995.0537 | 0
2025-09-19 | 60690.8689 | 20562.81 | 20230.2896 | 0 | 20230.2896 | 20562.81 | 20230.2896 | 0
2025-09-20 | 61396.5767 | 20562.81 | 20465.5256 | 0 | 20465.5256 | 20562.81 | 20465.5256 | 0
2025-09-21 | 62102.2844 | 20562.81 | 20700.7615 | 0 | 20700.7615 | 20562.81 | 20700.7615 | 0
2025-09-22 | 62807.9922 | 20562.81 | 20935.9974 | 0 | 20935.9974 | 20562.81 | 20935.9974 | 0
2025-09-23 | 63513.7 | 20562.81 | 21171.2333 | 0 | 21171.2333 | 20562.81 | 21171.2333 | 0
2025-09-24 | 63513.7 | 23165.94 | 21171.2333 | 0 | 21171.2333 | 23165.94 | 21171.2333 | 0
2025-09-25 | 63513.7 | 23165.94 | 21171.2333 | 0 | 21171.2333 | 23165.94 | 21171.2333 | 0
2025-09-26 | 63513.7 | 23165.94 | 21171.2333 | 0 | 21171.2333 | 23165.94 | 21171.2333 | 0
2025-09-27 | 63513.7 | 23165.94 | 21171.2333 | 0 | 21171.2333 | 23165.94 | 21171.2333 | 0
2025-09-28 | 63513.7 | 23165.94 | 21171.2333 | 0 | 21171.2333 | 23165.94 | 21171.2333 | 0
2025-09-29 | 64326.5779 | 23165.94 | 21442.1926 | 0 | 21442.1926 | 23165.94 | 21442.1926 | 0
2025-09-30 | 65139.4559 | 23165.94 | 21713.152 | 0 | 21713.152 | 23165.94 | 21713.152 | 0
2025-10-01 | 65952.3338 | 23165.94 | 21984.1113 | 0 | 21984.1113 | 23165.94 | 21984.1113 | 0
2025-10-02 | 66765.2117 | 23165.94 | 22255.0706 | 0 | 22255.0706 | 23165.94 | 22255.0706 | 0
2025-10-03 | 67578.0896 | 23165.94 | 22526.0299 | 0 | 22526.0299 | 23165.94 | 22526.0299 | 0
2025-10-04 | 68390.9676 | 23165.94 | 22796.9892 | 0 | 22796.9892 | 23165.94 | 22796.9892 | 0
2025-10-05 | 69203.8455 | 23165.94 | 23067.9485 | 0 | 23067.9485 | 23165.94 | 23067.9485 | 0
2025-10-06 | 70016.7234 | 23165.94 | 23338.9078 | 0 | 23338.9078 | 23165.94 | 23338.9078 | 0
2025-10-07 | 70829.6013 | 23165.94 | 23609.8671 | 0 | 23609.8671 | 23165.94 | 23609.8671 | 0
2025-10-08 | 71642.4793 | 23165.94 | 23880.8264 | 0 | 23880.8264 | 23165.94 | 23880.8264 | 0
2025-10-09 | 72455.3572 | 23165.94 | 24151.7857 | 0 | 24151.7857 | 23165.94 | 24151.7857 | 0
2025-10-10 | 73268.2351 | 23165.94 | 24422.745 | 0 | 24422.745 | 23165.94 | 24422.745 | 0
2025-10-11 | 74081.113 | 23165.94 | 24693.7043 | 0 | 24693.7043 | 23165.94 | 24693.7043 | 0
2025-10-12 | 74893.991 | 23165.94 | 24964.6637 | 0 | 24964.6637 | 23165.94 | 24964.6637 | 0
2025-10-13 | 75706.8689 |  | 25235.623 |  | 25235.623 |  | 25235.623
2025-10-14 | 76519.7468 |  | 25506.5823 |  | 25506.5823 |  | 25506.5823
2025-10-15 | 77332.6247 |  | 25777.5416 |  | 25777.5416 |  | 25777.5416
2025-10-16 | 78145.5027 |  | 26048.5009 |  | 26048.5009 |  | 26048.5009
2025-10-17 | 78958.3806 |  | 26319.4602 |  | 26319.4602 |  | 26319.4602
2025-10-18 | 79771.2585 |  | 26590.4195 |  | 26590.4195 |  | 26590.4195
2025-10-19 | 80584.1365 |  | 26861.3788 |  | 26861.3788 |  | 26861.3788
2025-10-20 | 81397.0144 |  | 27132.3381 |  | 27132.3381 |  | 27132.3381
2025-10-21 | 82209.8923 |  | 27403.2974 |  | 27403.2974 |  | 27403.2974
2025-10-22 | 83022.7702 |  | 27674.2567 |  | 27674.2567 |  | 27674.2567
2025-10-23 | 83835.6482 |  | 27945.2161 |  | 27945.2161 |  | 27945.2161
2025-10-24 | 84648.5261 |  | 28216.1754 |  | 28216.1754 |  | 28216.1754
2025-10-25 | 85461.404 |  | 28487.1347 |  | 28487.1347 |  | 28487.1347
2025-10-26 | 86274.2819 |  | 28758.094 |  | 28758.094 |  | 28758.094
2025-10-27 | 87087.1599 |  | 29029.0533 |  | 29029.0533 |  | 29029.0533
2025-10-28 | 87900.0378 |  | 29300.0126 |  | 29300.0126 |  | 29300.0126
2025-10-29 | 88712.9157 |  | 29570.9719 |  | 29570.9719 |  | 29570.9719
2025-10-30 | 89525.7936 |  | 29841.9312 |  | 29841.9312 |  | 29841.9312
2025-10-31 | 90338.6716 |  | 30112.8905 |  | 30112.8905 |  | 30112.8905
2025-11-01 | 91151.5495 |  | 30383.8498 |  | 30383.8498 |  | 30383.8498
2025-11-02 | 91964.4274 |  | 30654.8091 |  | 30654.8091 |  | 30654.8091
2025-11-03 | 92777.3054 |  | 30925.7685 |  | 30925.7685 |  | 30925.7685
2025-11-04 | 93590.1833 |  | 31196.7278 |  | 31196.7278 |  | 31196.7278
2025-11-05 | 94403.0612 |  | 31467.6871 |  | 31467.6871 |  | 31467.6871
2025-11-06 | 95215.9391 |  | 31738.6464 |  | 31738.6464 |  | 31738.6464
2025-11-07 | 96028.8171 |  | 32009.6057 |  | 32009.6057 |  | 32009.6057
2025-11-08 | 96841.695 |  | 32280.565 |  | 32280.565 |  | 32280.565
2025-11-09 | 97654.5729 |  | 32551.5243 |  | 32551.5243 |  | 32551.5243
2025-11-10 | 98467.4508 |  | 32822.4836 |  | 32822.4836 |  | 32822.4836
2025-11-11 | 99280.3288 |  | 33093.4429 |  | 33093.4429 |  | 33093.4429
2025-11-12 | 100093.2067 |  | 33364.4022 |  | 33364.4022 |  | 33364.4022
2025-11-13 | 100906.0846 |  | 33635.3615 |  | 33635.3615 |  | 33635.3615
2025-11-14 | 101718.9625 |  | 33906.3208 |  | 33906.3208 |  | 33906.3208
2025-11-15 | 102531.8405 |  | 34177.2802 |  | 34177.2802 |  | 34177.2802
2025-11-16 | 103344.7184 |  | 34448.2395 |  | 34448.2395 |  | 34448.2395
2025-11-17 | 104157.5963 |  | 34719.1988 |  | 34719.1988 |  | 34719.1988
2025-11-18 | 104970.4742 |  | 34990.1581 |  | 34990.1581 |  | 34990.1581
2025-11-19 | 105783.3522 |  | 35261.1174 |  | 35261.1174 |  | 35261.1174
2025-11-20 | 106462.411 |  | 35487.4703 |  | 35487.4703 |  | 35487.4703
2025-11-21 | 107141.4698 |  | 35713.8233 |  | 35713.8233 |  | 35713.8233
2025-11-22 | 107820.5286 |  | 35940.1762 |  | 35940.1762 |  | 35940.1762
2025-11-23 | 108499.5875 |  | 36166.5292 |  | 36166.5292 |  | 36166.5292
2025-11-24 | 109178.6463 |  | 36392.8821 |  | 36392.8821 |  | 36392.8821
2025-11-25 | 109857.7051 |  | 36619.235 |  | 36619.235 |  | 36619.235
2025-11-26 | 110536.7639 |  | 36845.588 |  | 36845.588 |  | 36845.588
2025-11-27 | 111215.8228 |  | 37071.9409 |  | 37071.9409 |  | 37071.9409
2025-11-28 | 111894.8816 |  | 37298.2939 |  | 37298.2939 |  | 37298.2939
2025-11-29 | 112573.9404 |  | 37524.6468 |  | 37524.6468 |  | 37524.6468
2025-11-30 | 113252.9992 |  | 37750.9997 |  | 37750.9997 |  | 37750.9997
2025-12-01 | 113932.0581 |  | 37977.3527 |  | 37977.3527 |  | 37977.3527
2025-12-02 | 114611.1169 |  | 38203.7056 |  | 38203.7056 |  | 38203.7056
2025-12-03 | 115290.1757 |  | 38430.0586 |  | 38430.0586 |  | 38430.0586
2025-12-04 | 115969.2345 |  | 38656.4115 |  | 38656.4115 |  | 38656.4115
2025-12-05 | 116648.2934 |  | 38882.7645 |  | 38882.7645 |  | 38882.7645
2025-12-06 | 117327.3522 |  | 39109.1174 |  | 39109.1174 |  | 39109.1174
2025-12-07 | 118006.411 |  | 39335.4703 |  | 39335.4703 |  | 39335.4703
2025-12-08 | 118685.4698 |  | 39561.8233 |  | 39561.8233 |  | 39561.8233
2025-12-09 | 119364.5286 |  | 39788.1762 |  | 39788.1762 |  | 39788.1762
2025-12-10 | 120043.5875 |  | 40014.5292 |  | 40014.5292 |  | 40014.5292
2025-12-11 | 120722.6463 |  | 40240.8821 |  | 40240.8821 |  | 40240.8821
2025-12-12 | 121401.7051 |  | 40467.235 |  | 40467.235 |  | 40467.235
2025-12-13 | 122080.7639 |  | 40693.588 |  | 40693.588 |  | 40693.588
2025-12-14 | 122759.8228 |  | 40919.9409 |  | 40919.9409 |  | 40919.9409
2025-12-15 | 123438.8816 |  | 41146.2939 |  | 41146.2939 |  | 41146.2939
2025-12-16 | 124117.9404 |  | 41372.6468 |  | 41372.6468 |  | 41372.6468
2025-12-17 | 124796.9992 |  | 41598.9997 |  | 41598.9997 |  | 41598.9997
2025-12-18 | 125476.0581 |  | 41825.3527 |  | 41825.3527 |  | 41825.3527
2025-12-19 | 126155.1169 |  | 42051.7056 |  | 42051.7056 |  | 42051.7056
2025-12-20 | 126834.1757 |  | 42278.0586 |  | 42278.0586 |  | 42278.0586
2025-12-21 | 127513.2345 |  | 42504.4115 |  | 42504.4115 |  | 42504.4115
2025-12-22 | 128192.2934 |  | 42730.7645 |  | 42730.7645 |  | 42730.7645
2025-12-23 | 128871.3522 |  | 42957.1174 |  | 42957.1174 |  | 42957.1174
2025-12-24 | 129550.411 |  | 43183.4703 |  | 43183.4703 |  | 43183.4703
2025-12-25 | 130229.4698 |  | 43409.8233 |  | 43409.8233 |  | 43409.8233
2025-12-26 | 130908.5286 |  | 43636.1762 |  | 43636.1762 |  | 43636.1762
2025-12-27 | 131587.5875 |  | 43862.5292 |  | 43862.5292 |  | 43862.5292
2025-12-28 | 132266.6463 |  | 44088.8821 |  | 44088.8821 |  | 44088.8821
2025-12-29 | 132945.7051 |  | 44315.235 |  | 44315.235 |  | 44315.235
2025-12-30 | 133624.7639 |  | 44541.588 |  | 44541.588 |  | 44541.588
2025-12-31 | 134303.8228 |  | 44767.9409 |  | 44767.9409 |  | 44767.9409
2026-01-01 | 134982.8816 |  | 44994.2939 |  | 44994.2939 |  | 44994.2939
2026-01-02 | 135661.9404 |  | 45220.6468 |  | 45220.6468 |  | 45220.6468
2026-01-03 | 136340.9992 |  | 45446.9997 |  | 45446.9997 |  | 45446.9997
2026-01-04 | 137020.0581 |  | 45673.3527 |  | 45673.3527 |  | 45673.3527
2026-01-05 | 137699.1169 |  | 45899.7056 |  | 45899.7056 |  | 45899.7056
2026-01-06 | 138378.1757 |  | 46126.0586 |  | 46126.0586 |  | 46126.0586
2026-01-07 | 139057.2345 |  | 46352.4115 |  | 46352.4115 |  | 46352.4115
2026-01-08 | 139736.2934 |  | 46578.7645 |  | 46578.7645 |  | 46578.7645
2026-01-09 | 140415.3522 |  | 46805.1174 |  | 46805.1174 |  | 46805.1174
2026-01-10 | 141094.411 |  | 47031.4703 |  | 47031.4703 |  | 47031.4703
2026-01-11 | 141773.4698 |  | 47257.8233 |  | 47257.8233 |  | 47257.8233
2026-01-12 | 142452.5286 |  | 47484.1762 |  | 47484.1762 |  | 47484.1762
2026-01-13 | 143131.5875 |  | 47710.5292 |  | 47710.5292 |  | 47710.5292
2026-01-14 | 143810.6463 |  | 47936.8821 |  | 47936.8821 |  | 47936.8821
2026-01-15 | 144489.7051 |  | 48163.235 |  | 48163.235 |  | 48163.235
2026-01-16 | 145168.7639 |  | 48389.588 |  | 48389.588 |  | 48389.588
2026-01-17 | 145847.8228 |  | 48615.9409 |  | 48615.9409 |  | 48615.9409
2026-01-18 | 146526.8816 |  | 48842.2939 |  | 48842.2939 |  | 48842.2939
2026-01-19 | 147205.9404 |  | 49068.6468 |  | 49068.6468 |  | 49068.6468
2026-01-20 | 147884.9992 |  | 49294.9997 |  | 49294.9997 |  | 49294.9997
2026-01-21 | 148564.0581 |  | 49521.3527 |  | 49521.3527 |  | 49521.3527
2026-01-22 | 149243.1169 |  | 49747.7056 |  | 49747.7056 |  | 49747.7056
2026-01-23 | 149922.1757 |  | 49974.0586 |  | 49974.0586 |  | 49974.0586
2026-01-24 | 150601.2345 |  | 50200.4115 |  | 50200.4115 |  | 50200.4115
2026-01-25 | 151280.2934 |  | 50426.7645 |  | 50426.7645 |  | 50426.7645
2026-01-26 | 151959.3522 |  | 50653.1174 |  | 50653.1174 |  | 50653.1174
2026-01-27 | 152638.411 |  | 50879.4703 |  | 50879.4703 |  | 50879.4703
2026-01-28 | 153317.4698 |  | 51105.8233 |  | 51105.8233 |  | 51105.8233
2026-01-29 | 153996.5286 |  | 51332.1762 |  | 51332.1762 |  | 51332.1762
2026-01-30 | 154675.5875 |  | 51558.5292 |  | 51558.5292 |  | 51558.5292
2026-01-31 | 155354.6463 |  | 51784.8821 |  | 51784.8821 |  | 51784.8821
2026-02-01 | 156033.7051 |  | 52011.235 |  | 52011.235 |  | 52011.235
2026-02-02 | 156712.7639 |  | 52237.588 |  | 52237.588 |  | 52237.588
2026-02-03 | 157391.8228 |  | 52463.9409 |  | 52463.9409 |  | 52463.9409
2026-02-04 | 158070.8816 |  | 52690.2939 |  | 52690.2939 |  | 52690.2939
2026-02-05 | 158749.9404 |  | 52916.6468 |  | 52916.6468 |  | 52916.6468
2026-02-06 | 159428.9992 |  | 53142.9997 |  | 53142.9997 |  | 53142.9997
2026-02-07 | 160108.0581 |  | 53369.3527 |  | 53369.3527 |  | 53369.3527
2026-02-08 | 160787.1169 |  | 53595.7056 |  | 53595.7056 |  | 53595.7056
2026-02-09 | 161466.1757 |  | 53822.0586 |  | 53822.0586 |  | 53822.0586
2026-02-10 | 162145.2345 |  | 54048.4115 |  | 54048.4115 |  | 54048.4115
2026-02-11 | 162824.2934 |  | 54274.7645 |  | 54274.7645 |  | 54274.7645
2026-02-12 | 163503.3522 |  | 54501.1174 |  | 54501.1174 |  | 54501.1174
2026-02-13 | 163545.0101 |  | 54515.0034 |  | 54515.0034 |  | 54515.0034
2026-02-14 | 163586.668 |  | 54528.8893 |  | 54528.8893 |  | 54528.8893
2026-02-15 | 163628.3259 |  | 54542.7753 |  | 54542.7753 |  | 54542.7753
2026-02-16 | 163669.9838 |  | 54556.6613 |  | 54556.6613 |  | 54556.6613
2026-02-17 | 163711.6416 |  | 54570.5472 |  | 54570.5472 |  | 54570.5472
2026-02-18 | 163753.2995 |  | 54584.4332 |  | 54584.4332 |  | 54584.4332
2026-02-19 | 163794.9574 |  | 54598.3191 |  | 54598.3191 |  | 54598.3191
2026-02-20 | 163836.6153 |  | 54612.2051 |  | 54612.2051 |  | 54612.2051
2026-02-21 | 163878.2732 |  | 54626.0911 |  | 54626.0911 |  | 54626.0911
2026-02-22 | 163919.9311 |  | 54639.977 |  | 54639.977 |  | 54639.977
2026-02-23 | 163961.589 |  | 54653.863 |  | 54653.863 |  | 54653.863
2026-02-24 | 164003.2469 |  | 54667.749 |  | 54667.749 |  | 54667.749
2026-02-25 | 164044.9048 |  | 54681.6349 |  | 54681.6349 |  | 54681.6349
2026-02-26 | 164086.5627 |  | 54695.5209 |  | 54695.5209 |  | 54695.5209
2026-02-27 | 164128.2206 |  | 54709.4069 |  | 54709.4069 |  | 54709.4069
2026-02-28 | 164169.8785 |  | 54723.2928 |  | 54723.2928 |  | 54723.2928
2026-03-01 | 164211.5364 |  | 54737.1788 |  | 54737.1788 |  | 54737.1788
2026-03-02 | 164253.1943 |  | 54751.0648 |  | 54751.0648 |  | 54751.0648
2026-03-03 | 164294.8522 |  | 54764.9507 |  | 54764.9507 |  | 54764.9507
2026-03-04 | 164336.5101 |  | 54778.8367 |  | 54778.8367 |  | 54778.8367
2026-03-05 | 164378.168 |  | 54792.7227 |  | 54792.7227 |  | 54792.7227
2026-03-06 | 164419.8259 |  | 54806.6086 |  | 54806.6086 |  | 54806.6086
2026-03-07 | 164461.4838 |  | 54820.4946 |  | 54820.4946 |  | 54820.4946
2026-03-08 | 164503.1416 |  | 54834.3805 |  | 54834.3805 |  | 54834.3805
2026-03-09 | 164544.7995 |  | 54848.2665 |  | 54848.2665 |  | 54848.2665
2026-03-10 | 164586.4574 |  | 54862.1525 |  | 54862.1525 |  | 54862.1525
2026-03-11 | 164628.1153 |  | 54876.0384 |  | 54876.0384 |  | 54876.0384
2026-03-12 | 164669.7732 |  | 54889.9244 |  | 54889.9244 |  | 54889.9244
2026-03-13 | 164711.4311 |  | 54903.8104 |  | 54903.8104 |  | 54903.8104
2026-03-14 | 164753.089 |  | 54917.6963 |  | 54917.6963 |  | 54917.6963
2026-03-15 | 164794.7469 |  | 54931.5823 |  | 54931.5823 |  | 54931.5823
2026-03-16 | 164836.4048 |  | 54945.4683 |  | 54945.4683 |  | 54945.4683
2026-03-17 | 164878.0627 |  | 54959.3542 |  | 54959.3542 |  | 54959.3542
2026-03-18 | 164919.7206 |  | 54973.2402 |  | 54973.2402 |  | 54973.2402
2026-03-19 | 164961.3785 |  | 54987.1262 |  | 54987.1262 |  | 54987.1262
2026-03-20 | 165003.0364 |  | 55001.0121 |  | 55001.0121 |  | 55001.0121
2026-03-21 | 165044.6943 |  | 55014.8981 |  | 55014.8981 |  | 55014.8981
2026-03-22 | 165086.3522 |  | 55028.7841 |  | 55028.7841 |  | 55028.7841
2026-03-23 | 165128.0101 |  | 55042.67 |  | 55042.67 |  | 55042.67
2026-03-24 | 165169.668 |  | 55056.556 |  | 55056.556 |  | 55056.556
2026-03-25 | 165211.3259 |  | 55070.442 |  | 55070.442 |  | 55070.442
2026-03-26 | 165252.9838 |  | 55084.3279 |  | 55084.3279 |  | 55084.3279
2026-03-27 | 165294.6416 |  | 55098.2139 |  | 55098.2139 |  | 55098.2139
2026-03-28 | 165336.2995 |  | 55112.0998 |  | 55112.0998 |  | 55112.0998
2026-03-29 | 165377.9574 |  | 55125.9858 |  | 55125.9858 |  | 55125.9858
2026-03-30 | 165419.6153 |  | 55139.8718 |  | 55139.8718 |  | 55139.8718
2026-03-31 | 165461.2732 |  | 55153.7577 |  | 55153.7577 |  | 55153.7577
2026-04-01 | 165502.9311 |  | 55167.6437 |  | 55167.6437 |  | 55167.6437
2026-04-02 | 165544.589 |  | 55181.5297 |  | 55181.5297 |  | 55181.5297
2026-04-03 | 165586.2469 |  | 55195.4156 |  | 55195.4156 |  | 55195.4156
2026-04-04 | 165627.9048 |  | 55209.3016 |  | 55209.3016 |  | 55209.3016
2026-04-05 | 165669.5627 |  | 55223.1876 |  | 55223.1876 |  | 55223.1876
2026-04-06 | 165711.2206 |  | 55237.0735 |  | 55237.0735 |  | 55237.0735
2026-04-07 | 165752.8785 |  | 55250.9595 |  | 55250.9595 |  | 55250.9595
2026-04-08 | 165794.5364 |  | 55264.8455 |  | 55264.8455 |  | 55264.8455
2026-04-09 | 165836.1943 |  | 55278.7314 |  | 55278.7314 |  | 55278.7314
2026-04-10 | 165877.8522 |  | 55292.6174 |  | 55292.6174 |  | 55292.6174
2026-04-11 | 165919.5101 |  | 55306.5034 |  | 55306.5034 |  | 55306.5034
2026-04-12 | 165961.168 |  | 55320.3893 |  | 55320.3893 |  | 55320.3893
2026-04-13 | 166002.8259 |  | 55334.2753 |  | 55334.2753 |  | 55334.2753
2026-04-14 | 166044.4838 |  | 55348.1613 |  | 55348.1613 |  | 55348.1613
2026-04-15 | 166086.1416 |  | 55362.0472 |  | 55362.0472 |  | 55362.0472
2026-04-16 | 166127.7995 |  | 55375.9332 |  | 55375.9332 |  | 55375.9332
2026-04-17 | 166169.4574 |  | 55389.8191 |  | 55389.8191 |  | 55389.8191
2026-04-18 | 166211.1153 |  | 55403.7051 |  | 55403.7051 |  | 55403.7051
2026-04-19 | 166252.7732 |  | 55417.5911 |  | 55417.5911 |  | 55417.5911
2026-04-20 | 166294.4311 |  | 55431.477 |  | 55431.477 |  | 55431.477
2026-04-21 | 166336.089 |  | 55445.363 |  | 55445.363 |  | 55445.363
2026-04-22 | 166377.7469 |  | 55459.249 |  | 55459.249 |  | 55459.249
2026-04-23 | 166419.4048 |  | 55473.1349 |  | 55473.1349 |  | 55473.1349
2026-04-24 | 166461.0627 |  | 55487.0209 |  | 55487.0209 |  | 55487.0209
2026-04-25 | 166502.7206 |  | 55500.9069 |  | 55500.9069 |  | 55500.9069
2026-04-26 | 166544.3785 |  | 55514.7928 |  | 55514.7928 |  | 55514.7928
2026-04-27 | 166586.0364 |  | 55528.6788 |  | 55528.6788 |  | 55528.6788
2026-04-28 | 166627.6943 |  | 55542.5648 |  | 55542.5648 |  | 55542.5648
2026-04-29 | 166669.3522 |  | 55556.4507 |  | 55556.4507 |  | 55556.4507
2026-04-30 | 166711.0101 |  | 55570.3367 |  | 55570.3367 |  | 55570.3367
2026-05-01 | 166752.668 |  | 55584.2227 |  | 55584.2227 |  | 55584.2227
2026-05-02 | 166794.3259 |  | 55598.1086 |  | 55598.1086 |  | 55598.1086
2026-05-03 | 166835.9838 |  | 55611.9946 |  | 55611.9946 |  | 55611.9946
2026-05-04 | 166877.6416 |  | 55625.8805 |  | 55625.8805 |  | 55625.8805
2026-05-05 | 166919.2995 |  | 55639.7665 |  | 55639.7665 |  | 55639.7665
2026-05-06 | 166960.9574 |  | 55653.6525 |  | 55653.6525 |  | 55653.6525
2026-05-07 | 167002.6153 |  | 55667.5384 |  | 55667.5384 |  | 55667.5384
2026-05-08 | 167044.2732 |  | 55681.4244 |  | 55681.4244 |  | 55681.4244
2026-05-09 | 167085.9311 |  | 55695.3104 |  | 55695.3104 |  | 55695.3104
2026-05-10 | 167127.589 |  | 55709.1963 |  | 55709.1963 |  | 55709.1963
2026-05-11 | 167169.2469 |  | 55723.0823 |  | 55723.0823 |  | 55723.0823
2026-05-12 | 167210.9048 |  | 55736.9683 |  | 55736.9683 |  | 55736.9683
2026-05-13 | 167252.5627 |  | 55750.8542 |  | 55750.8542 |  | 55750.8542
2026-05-14 | 167294.2206 |  | 55764.7402 |  | 55764.7402 |  | 55764.7402
2026-05-15 | 167335.8785 |  | 55778.6262 |  | 55778.6262 |  | 55778.6262
2026-05-16 | 167377.5364 |  | 55792.5121 |  | 55792.5121 |  | 55792.5121
2026-05-17 | 167419.1943 |  | 55806.3981 |  | 55806.3981 |  | 55806.3981
2026-05-18 | 167460.8522 |  | 55820.2841 |  | 55820.2841 |  | 55820.2841
2026-05-19 | 167502.5101 |  | 55834.17 |  | 55834.17 |  | 55834.17
2026-05-20 | 167544.168 |  | 55848.056 |  | 55848.056 |  | 55848.056
2026-05-21 | 167585.8259 |  | 55861.942 |  | 55861.942 |  | 55861.942
2026-05-22 | 167627.4838 |  | 55875.8279 |  | 55875.8279 |  | 55875.8279
2026-05-23 | 167669.1416 |  | 55889.7139 |  | 55889.7139 |  | 55889.7139
2026-05-24 | 167710.7995 |  | 55903.5998 |  | 55903.5998 |  | 55903.5998
2026-05-25 | 167752.4574 |  | 55917.4858 |  | 55917.4858 |  | 55917.4858
2026-05-26 | 167794.1153 |  | 55931.3718 |  | 55931.3718 |  | 55931.3718
2026-05-27 | 167835.7732 |  | 55945.2577 |  | 55945.2577 |  | 55945.2577
2026-05-28 | 167877.4311 |  | 55959.1437 |  | 55959.1437 |  | 55959.1437
2026-05-29 | 167919.089 |  | 55973.0297 |  | 55973.0297 |  | 55973.0297
2026-05-30 | 167960.7469 |  | 55986.9156 |  | 55986.9156 |  | 55986.9156
2026-05-31 | 168002.4048 |  | 56000.8016 |  | 56000.8016 |  | 56000.8016
2026-06-01 | 168044.0627 |  | 56014.6876 |  | 56014.6876 |  | 56014.6876
2026-06-02 | 168085.7206 |  | 56028.5735 |  | 56028.5735 |  | 56028.5735
2026-06-03 | 168127.3785 |  | 56042.4595 |  | 56042.4595 |  | 56042.4595
2026-06-04 | 168169.0364 |  | 56056.3455 |  | 56056.3455 |  | 56056.3455
2026-06-05 | 168210.6943 |  | 56070.2314 |  | 56070.2314 |  | 56070.2314
2026-06-06 | 168252.3522 |  | 56084.1174 |  | 56084.1174 |  | 56084.1174
2026-06-07 | 168294.0101 |  | 56098.0034 |  | 56098.0034 |  | 56098.0034
2026-06-08 | 168335.668 |  | 56111.8893 |  | 56111.8893 |  | 56111.8893
2026-06-09 | 168377.3259 |  | 56125.7753 |  | 56125.7753 |  | 56125.7753
2026-06-10 | 168418.9838 |  | 56139.6613 |  | 56139.6613 |  | 56139.6613
2026-06-11 | 168460.6416 |  | 56153.5472 |  | 56153.5472 |  | 56153.5472
2026-06-12 | 168502.2995 |  | 56167.4332 |  | 56167.4332 |  | 56167.4332
2026-06-13 | 168543.9574 |  | 56181.3191 |  | 56181.3191 |  | 56181.3191
2026-06-14 | 168585.6153 |  | 56195.2051 |  | 56195.2051 |  | 56195.2051
2026-06-15 | 168627.2732 |  | 56209.0911 |  | 56209.0911 |  | 56209.0911
2026-06-16 | 168668.9311 |  | 56222.977 |  | 56222.977 |  | 56222.977
2026-06-17 | 168710.589 |  | 56236.863 |  | 56236.863 |  | 56236.863
2026-06-18 | 168752.2469 |  | 56250.749 |  | 56250.749 |  | 56250.749
2026-06-19 | 168793.9048 |  | 56264.6349 |  | 56264.6349 |  | 56264.6349
2026-06-20 | 168835.5627 |  | 56278.5209 |  | 56278.5209 |  | 56278.5209
2026-06-21 | 168877.2206 |  | 56292.4069 |  | 56292.4069 |  | 56292.4069
2026-06-22 | 168918.8785 |  | 56306.2928 |  | 56306.2928 |  | 56306.2928
2026-06-23 | 168960.5364 |  | 56320.1788 |  | 56320.1788 |  | 56320.1788
2026-06-24 | 169002.1943 |  | 56334.0648 |  | 56334.0648 |  | 56334.0648
2026-06-25 | 169043.8522 |  | 56347.9507 |  | 56347.9507 |  | 56347.9507
2026-06-26 | 169085.5101 |  | 56361.8367 |  | 56361.8367 |  | 56361.8367
2026-06-27 | 169127.168 |  | 56375.7227 |  | 56375.7227 |  | 56375.7227
2026-06-28 | 169168.8259 |  | 56389.6086 |  | 56389.6086 |  | 56389.6086
2026-06-29 | 169210.4838 |  | 56403.4946 |  | 56403.4946 |  | 56403.4946
2026-06-30 | 169252.1416 |  | 56417.3805 |  | 56417.3805 |  | 56417.3805
2026-07-01 | 169293.7995 |  | 56431.2665 |  | 56431.2665 |  | 56431.2665
2026-07-02 | 169335.4574 |  | 56445.1525 |  | 56445.1525 |  | 56445.1525
2026-07-03 | 169377.1153 |  | 56459.0384 |  | 56459.0384 |  | 56459.0384
2026-07-04 | 169418.7732 |  | 56472.9244 |  | 56472.9244 |  | 56472.9244
2026-07-05 | 169460.4311 |  | 56486.8104 |  | 56486.8104 |  | 56486.8104
2026-07-06 | 169502.089 |  | 56500.6963 |  | 56500.6963 |  | 56500.6963
2026-07-07 | 169543.7469 |  | 56514.5823 |  | 56514.5823 |  | 56514.5823
2026-07-08 | 169585.4048 |  | 56528.4683 |  | 56528.4683 |  | 56528.4683
2026-07-09 | 169627.0627 |  | 56542.3542 |  | 56542.3542 |  | 56542.3542
2026-07-10 | 169668.7206 |  | 56556.2402 |  | 56556.2402 |  | 56556.2402
2026-07-11 | 169710.3785 |  | 56570.1262 |  | 56570.1262 |  | 56570.1262
2026-07-12 | 169752.0364 |  | 56584.0121 |  | 56584.0121 |  | 56584.0121
2026-07-13 | 169793.6943 |  | 56597.8981 |  | 56597.8981 |  | 56597.8981
2026-07-14 | 169835.3522 |  | 56611.7841 |  | 56611.7841 |  | 56611.7841
2026-07-15 | 169877.0101 |  | 56625.67 |  | 56625.67 |  | 56625.67
2026-07-16 | 169918.668 |  | 56639.556 |  | 56639.556 |  | 56639.556
2026-07-17 | 169960.3259 |  | 56653.442 |  | 56653.442 |  | 56653.442
2026-07-18 | 170001.9838 |  | 56667.3279 |  | 56667.3279 |  | 56667.3279
2026-07-19 | 170043.6416 |  | 56681.2139 |  | 56681.2139 |  | 56681.2139
2026-07-20 | 170085.2995 |  | 56695.0998 |  | 56695.0998 |  | 56695.0998
2026-07-21 | 170126.9574 |  | 56708.9858 |  | 56708.9858 |  | 56708.9858
2026-07-22 | 170168.6153 |  | 56722.8718 |  | 56722.8718 |  | 56722.8718
2026-07-23 | 170210.2732 |  | 56736.7577 |  | 56736.7577 |  | 56736.7577
2026-07-24 | 170251.9311 |  | 56750.6437 |  | 56750.6437 |  | 56750.6437
2026-07-25 | 170293.589 |  | 56764.5297 |  | 56764.5297 |  | 56764.5297
2026-07-26 | 170335.2469 |  | 56778.4156 |  | 56778.4156 |  | 56778.4156
2026-07-27 | 170376.9048 |  | 56792.3016 |  | 56792.3016 |  | 56792.3016
2026-07-28 | 170418.5627 |  | 56806.1876 |  | 56806.1876 |  | 56806.1876
2026-07-29 | 170460.2206 |  | 56820.0735 |  | 56820.0735 |  | 56820.0735
2026-07-30 | 170501.8785 |  | 56833.9595 |  | 56833.9595 |  | 56833.9595
2026-07-31 | 170543.5364 |  | 56847.8455 |  | 56847.8455 |  | 56847.8455
2026-08-01 | 170585.1943 |  | 56861.7314 |  | 56861.7314 |  | 56861.7314
2026-08-02 | 170626.8522 |  | 56875.6174 |  | 56875.6174 |  | 56875.6174
2026-08-03 | 170668.5101 |  | 56889.5034 |  | 56889.5034 |  | 56889.5034
2026-08-04 | 170710.168 |  | 56903.3893 |  | 56903.3893 |  | 56903.3893
2026-08-05 | 170751.8259 |  | 56917.2753 |  | 56917.2753 |  | 56917.2753
2026-08-06 | 170793.4838 |  | 56931.1613 |  | 56931.1613 |  | 56931.1613
2026-08-07 | 170835.1416 |  | 56945.0472 |  | 56945.0472 |  | 56945.0472
2026-08-08 | 170876.7995 |  | 56958.9332 |  | 56958.9332 |  | 56958.9332
2026-08-09 | 170918.4574 |  | 56972.8191 |  | 56972.8191 |  | 56972.8191
2026-08-10 | 170960.1153 |  | 56986.7051 |  | 56986.7051 |  | 56986.7051
2026-08-11 | 171001.7732 |  | 57000.5911 |  | 57000.5911 |  | 57000.5911
2026-08-12 | 171043.4311 |  | 57014.477 |  | 57014.477 |  | 57014.477
2026-08-13 | 171085.089 |  | 57028.363 |  | 57028.363 |  | 57028.363
2026-08-14 | 171126.7469 |  | 57042.249 |  | 57042.249 |  | 57042.249
2026-08-15 | 171168.4048 |  | 57056.1349 |  | 57056.1349 |  | 57056.1349
2026-08-16 | 171210.0627 |  | 57070.0209 |  | 57070.0209 |  | 57070.0209
2026-08-17 | 171251.7206 |  | 57083.9069 |  | 57083.9069 |  | 57083.9069
2026-08-18 | 171293.3785 |  | 57097.7928 |  | 57097.7928 |  | 57097.7928
2026-08-19 | 171335.0364 |  | 57111.6788 |  | 57111.6788 |  | 57111.6788
2026-08-20 | 171376.6943 |  | 57125.5648 |  | 57125.5648 |  | 57125.5648
2026-08-21 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-22 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-23 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-24 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-25 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-26 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-27 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-28 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-29 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-30 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-08-31 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-01 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-02 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-03 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-04 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-05 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-06 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-07 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-08 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-09 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-10 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-11 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-12 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-13 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-14 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-15 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-16 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-17 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-18 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-19 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-20 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-21 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-22 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-23 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-24 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507
2026-09-25 | 171418.3522 |  | 57139.4507 |  | 57139.4507 |  | 57139.4507

## Outsource (Direct Cost)
Date | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Planned 5006 · Drilling Expense (Cumulative) | Actual 5006 · Drilling Expense (Cumulative) | Planned 5110 · Temporary labor (Direct) (Cumulative) | Actual 5110 · Temporary labor (Direct) (Cumulative) | Planned 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Actual 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Planned 5114 · Rent - Building (Direct) (Cumulative) | Actual 5114 · Rent - Building (Direct) (Cumulative) | Planned 5115 · Rent - Equipment (direct) (Cumulative) | Actual 5115 · Rent - Equipment (direct) (Cumulative) | Planned 5116 · Rent - Storage (Direct) (Cumulative) | Actual 5116 · Rent - Storage (Direct) (Cumulative) | Planned 5120 · Outside services (Direct) (Cumulative) | Actual 5120 · Outside services (Direct) (Cumulative) | Planned 5121 · Freight & Shipping (Direct) (Cumulative) | Actual 5121 · Freight & Shipping (Direct) (Cumulative) | Planned 5124 · License and permits (Direct) (Cumulative) | Actual 5124 · License and permits (Direct) (Cumulative) | Planned 5129 · Misc expenses (Direct) (Cumulative) | Actual 5129 · Misc expenses (Direct) (Cumulative) | Planned 5132 · Internet fee (Direct) (Cumulative) | Actual 5132 · Internet fee (Direct) (Cumulative) | Planned 6999 · Uncategorized Expenses (Cumulative) | Actual 6999 · Uncategorized Expenses (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-26 | 318.3575 | 0 | 26.5298 | 0 | 26.5298 | 0 | 26.5298 | 0 | 26.5298 | 0 | 26.5298 | 0 | 26.5298 | 0 | 26.5298 | 0 | 26.5298 | 0 | 26.5298 | 0 | 26.5298 | 0 | 26.5298 | 0 | 26.5298 | 0
2025-06-27 | 636.715 | 0 | 53.0596 | 0 | 53.0596 | 0 | 53.0596 | 0 | 53.0596 | 0 | 53.0596 | 0 | 53.0596 | 0 | 53.0596 | 0 | 53.0596 | 0 | 53.0596 | 0 | 53.0596 | 0 | 53.0596 | 0 | 53.0596 | 0
2025-06-28 | 955.0725 | 0 | 79.5894 | 0 | 79.5894 | 0 | 79.5894 | 0 | 79.5894 | 0 | 79.5894 | 0 | 79.5894 | 0 | 79.5894 | 0 | 79.5894 | 0 | 79.5894 | 0 | 79.5894 | 0 | 79.5894 | 0 | 79.5894 | 0
2025-06-29 | 1273.43 | 0 | 106.1192 | 0 | 106.1192 | 0 | 106.1192 | 0 | 106.1192 | 0 | 106.1192 | 0 | 106.1192 | 0 | 106.1192 | 0 | 106.1192 | 0 | 106.1192 | 0 | 106.1192 | 0 | 106.1192 | 0 | 106.1192 | 0
2025-06-30 | 1591.7874 | 0 | 132.649 | 0 | 132.649 | 0 | 132.649 | 0 | 132.649 | 0 | 132.649 | 0 | 132.649 | 0 | 132.649 | 0 | 132.649 | 0 | 132.649 | 0 | 132.649 | 0 | 132.649 | 0 | 132.649 | 0
2025-07-01 | 1910.1449 | 0 | 159.1787 | 0 | 159.1787 | 0 | 159.1787 | 0 | 159.1787 | 0 | 159.1787 | 0 | 159.1787 | 0 | 159.1787 | 0 | 159.1787 | 0 | 159.1787 | 0 | 159.1787 | 0 | 159.1787 | 0 | 159.1787 | 0
2025-07-02 | 2228.5024 | 0 | 185.7085 | 0 | 185.7085 | 0 | 185.7085 | 0 | 185.7085 | 0 | 185.7085 | 0 | 185.7085 | 0 | 185.7085 | 0 | 185.7085 | 0 | 185.7085 | 0 | 185.7085 | 0 | 185.7085 | 0 | 185.7085 | 0
2025-07-03 | 2546.8599 | 0 | 212.2383 | 0 | 212.2383 | 0 | 212.2383 | 0 | 212.2383 | 0 | 212.2383 | 0 | 212.2383 | 0 | 212.2383 | 0 | 212.2383 | 0 | 212.2383 | 0 | 212.2383 | 0 | 212.2383 | 0 | 212.2383 | 0
2025-07-04 | 2865.2174 | 0 | 238.7681 | 0 | 238.7681 | 0 | 238.7681 | 0 | 238.7681 | 0 | 238.7681 | 0 | 238.7681 | 0 | 238.7681 | 0 | 238.7681 | 0 | 238.7681 | 0 | 238.7681 | 0 | 238.7681 | 0 | 238.7681 | 0
2025-07-05 | 3183.5749 | 0 | 265.2979 | 0 | 265.2979 | 0 | 265.2979 | 0 | 265.2979 | 0 | 265.2979 | 0 | 265.2979 | 0 | 265.2979 | 0 | 265.2979 | 0 | 265.2979 | 0 | 265.2979 | 0 | 265.2979 | 0 | 265.2979 | 0
2025-07-06 | 3501.9324 | 0 | 291.8277 | 0 | 291.8277 | 0 | 291.8277 | 0 | 291.8277 | 0 | 291.8277 | 0 | 291.8277 | 0 | 291.8277 | 0 | 291.8277 | 0 | 291.8277 | 0 | 291.8277 | 0 | 291.8277 | 0 | 291.8277 | 0
2025-07-07 | 3820.2899 | 0 | 318.3575 | 0 | 318.3575 | 0 | 318.3575 | 0 | 318.3575 | 0 | 318.3575 | 0 | 318.3575 | 0 | 318.3575 | 0 | 318.3575 | 0 | 318.3575 | 0 | 318.3575 | 0 | 318.3575 | 0 | 318.3575 | 0
2025-07-08 | 4138.6473 | 0 | 344.8873 | 0 | 344.8873 | 0 | 344.8873 | 0 | 344.8873 | 0 | 344.8873 | 0 | 344.8873 | 0 | 344.8873 | 0 | 344.8873 | 0 | 344.8873 | 0 | 344.8873 | 0 | 344.8873 | 0 | 344.8873 | 0
2025-07-09 | 4457.0048 | 0 | 371.4171 | 0 | 371.4171 | 0 | 371.4171 | 0 | 371.4171 | 0 | 371.4171 | 0 | 371.4171 | 0 | 371.4171 | 0 | 371.4171 | 0 | 371.4171 | 0 | 371.4171 | 0 | 371.4171 | 0 | 371.4171 | 0
2025-07-10 | 4775.3623 | 0 | 397.9469 | 0 | 397.9469 | 0 | 397.9469 | 0 | 397.9469 | 0 | 397.9469 | 0 | 397.9469 | 0 | 397.9469 | 0 | 397.9469 | 0 | 397.9469 | 0 | 397.9469 | 0 | 397.9469 | 0 | 397.9469 | 0
2025-07-11 | 5093.7198 | 0 | 424.4767 | 0 | 424.4767 | 0 | 424.4767 | 0 | 424.4767 | 0 | 424.4767 | 0 | 424.4767 | 0 | 424.4767 | 0 | 424.4767 | 0 | 424.4767 | 0 | 424.4767 | 0 | 424.4767 | 0 | 424.4767 | 0
2025-07-12 | 5412.0773 | 0 | 451.0064 | 0 | 451.0064 | 0 | 451.0064 | 0 | 451.0064 | 0 | 451.0064 | 0 | 451.0064 | 0 | 451.0064 | 0 | 451.0064 | 0 | 451.0064 | 0 | 451.0064 | 0 | 451.0064 | 0 | 451.0064 | 0
2025-07-13 | 5730.4348 | 0 | 477.5362 | 0 | 477.5362 | 0 | 477.5362 | 0 | 477.5362 | 0 | 477.5362 | 0 | 477.5362 | 0 | 477.5362 | 0 | 477.5362 | 0 | 477.5362 | 0 | 477.5362 | 0 | 477.5362 | 0 | 477.5362 | 0
2025-07-14 | 6048.7923 | 0 | 504.066 | 0 | 504.066 | 0 | 504.066 | 0 | 504.066 | 0 | 504.066 | 0 | 504.066 | 0 | 504.066 | 0 | 504.066 | 0 | 504.066 | 0 | 504.066 | 0 | 504.066 | 0 | 504.066 | 0
2025-07-15 | 6367.1498 | 0 | 530.5958 | 0 | 530.5958 | 0 | 530.5958 | 0 | 530.5958 | 0 | 530.5958 | 0 | 530.5958 | 0 | 530.5958 | 0 | 530.5958 | 0 | 530.5958 | 0 | 530.5958 | 0 | 530.5958 | 0 | 530.5958 | 0
2025-07-16 | 6685.5072 | 0 | 557.1256 | 0 | 557.1256 | 0 | 557.1256 | 0 | 557.1256 | 0 | 557.1256 | 0 | 557.1256 | 0 | 557.1256 | 0 | 557.1256 | 0 | 557.1256 | 0 | 557.1256 | 0 | 557.1256 | 0 | 557.1256 | 0
2025-07-17 | 7003.8647 | 0 | 583.6554 | 0 | 583.6554 | 0 | 583.6554 | 0 | 583.6554 | 0 | 583.6554 | 0 | 583.6554 | 0 | 583.6554 | 0 | 583.6554 | 0 | 583.6554 | 0 | 583.6554 | 0 | 583.6554 | 0 | 583.6554 | 0
2025-07-18 | 7322.2222 | 0 | 610.1852 | 0 | 610.1852 | 0 | 610.1852 | 0 | 610.1852 | 0 | 610.1852 | 0 | 610.1852 | 0 | 610.1852 | 0 | 610.1852 | 0 | 610.1852 | 0 | 610.1852 | 0 | 610.1852 | 0 | 610.1852 | 0
2025-07-19 | 7640.5797 | 0 | 636.715 | 0 | 636.715 | 0 | 636.715 | 0 | 636.715 | 0 | 636.715 | 0 | 636.715 | 0 | 636.715 | 0 | 636.715 | 0 | 636.715 | 0 | 636.715 | 0 | 636.715 | 0 | 636.715 | 0
2025-07-20 | 7958.9372 | 0 | 663.2448 | 0 | 663.2448 | 0 | 663.2448 | 0 | 663.2448 | 0 | 663.2448 | 0 | 663.2448 | 0 | 663.2448 | 0 | 663.2448 | 0 | 663.2448 | 0 | 663.2448 | 0 | 663.2448 | 0 | 663.2448 | 0
2025-07-21 | 8277.2947 | 0 | 689.7746 | 0 | 689.7746 | 0 | 689.7746 | 0 | 689.7746 | 0 | 689.7746 | 0 | 689.7746 | 0 | 689.7746 | 0 | 689.7746 | 0 | 689.7746 | 0 | 689.7746 | 0 | 689.7746 | 0 | 689.7746 | 0
2025-07-22 | 8595.6522 | 500 | 716.3043 | 0 | 716.3043 | 0 | 716.3043 | 0 | 716.3043 | 0 | 716.3043 | 0 | 716.3043 | 0 | 716.3043 | 0 | 716.3043 | 0 | 716.3043 | 500 | 716.3043 | 0 | 716.3043 | 0 | 716.3043 | 0
2025-07-23 | 8914.0097 | 500 | 742.8341 | 0 | 742.8341 | 0 | 742.8341 | 0 | 742.8341 | 0 | 742.8341 | 0 | 742.8341 | 0 | 742.8341 | 0 | 742.8341 | 0 | 742.8341 | 500 | 742.8341 | 0 | 742.8341 | 0 | 742.8341 | 0
2025-07-24 | 9232.3671 | 500 | 769.3639 | 0 | 769.3639 | 0 | 769.3639 | 0 | 769.3639 | 0 | 769.3639 | 0 | 769.3639 | 0 | 769.3639 | 0 | 769.3639 | 0 | 769.3639 | 500 | 769.3639 | 0 | 769.3639 | 0 | 769.3639 | 0
2025-07-25 | 9550.7246 | 500 | 795.8937 | 0 | 795.8937 | 0 | 795.8937 | 0 | 795.8937 | 0 | 795.8937 | 0 | 795.8937 | 0 | 795.8937 | 0 | 795.8937 | 0 | 795.8937 | 500 | 795.8937 | 0 | 795.8937 | 0 | 795.8937 | 0
2025-07-26 | 9869.0821 | 500 | 822.4235 | 0 | 822.4235 | 0 | 822.4235 | 0 | 822.4235 | 0 | 822.4235 | 0 | 822.4235 | 0 | 822.4235 | 0 | 822.4235 | 0 | 822.4235 | 500 | 822.4235 | 0 | 822.4235 | 0 | 822.4235 | 0
2025-07-27 | 10187.4396 | 500 | 848.9533 | 0 | 848.9533 | 0 | 848.9533 | 0 | 848.9533 | 0 | 848.9533 | 0 | 848.9533 | 0 | 848.9533 | 0 | 848.9533 | 0 | 848.9533 | 500 | 848.9533 | 0 | 848.9533 | 0 | 848.9533 | 0
2025-07-28 | 10505.7971 | 500 | 875.4831 | 0 | 875.4831 | 0 | 875.4831 | 0 | 875.4831 | 0 | 875.4831 | 0 | 875.4831 | 0 | 875.4831 | 0 | 875.4831 | 0 | 875.4831 | 500 | 875.4831 | 0 | 875.4831 | 0 | 875.4831 | 0
2025-07-29 | 10824.1546 | 500 | 902.0129 | 0 | 902.0129 | 0 | 902.0129 | 0 | 902.0129 | 0 | 902.0129 | 0 | 902.0129 | 0 | 902.0129 | 0 | 902.0129 | 0 | 902.0129 | 500 | 902.0129 | 0 | 902.0129 | 0 | 902.0129 | 0
2025-07-30 | 11142.5121 | 500 | 928.5427 | 0 | 928.5427 | 0 | 928.5427 | 0 | 928.5427 | 0 | 928.5427 | 0 | 928.5427 | 0 | 928.5427 | 0 | 928.5427 | 0 | 928.5427 | 500 | 928.5427 | 0 | 928.5427 | 0 | 928.5427 | 0
2025-07-31 | 11460.8696 | 500 | 955.0725 | 0 | 955.0725 | 0 | 955.0725 | 0 | 955.0725 | 0 | 955.0725 | 0 | 955.0725 | 0 | 955.0725 | 0 | 955.0725 | 0 | 955.0725 | 500 | 955.0725 | 0 | 955.0725 | 0 | 955.0725 | 0
2025-08-01 | 11779.2271 | 500 | 981.6023 | 0 | 981.6023 | 0 | 981.6023 | 0 | 981.6023 | 0 | 981.6023 | 0 | 981.6023 | 0 | 981.6023 | 0 | 981.6023 | 0 | 981.6023 | 500 | 981.6023 | 0 | 981.6023 | 0 | 981.6023 | 0
2025-08-02 | 12097.5845 | 500 | 1008.132 | 0 | 1008.132 | 0 | 1008.132 | 0 | 1008.132 | 0 | 1008.132 | 0 | 1008.132 | 0 | 1008.132 | 0 | 1008.132 | 0 | 1008.132 | 500 | 1008.132 | 0 | 1008.132 | 0 | 1008.132 | 0
2025-08-03 | 12415.942 | 500 | 1034.6618 | 0 | 1034.6618 | 0 | 1034.6618 | 0 | 1034.6618 | 0 | 1034.6618 | 0 | 1034.6618 | 0 | 1034.6618 | 0 | 1034.6618 | 0 | 1034.6618 | 500 | 1034.6618 | 0 | 1034.6618 | 0 | 1034.6618 | 0
2025-08-04 | 12734.2995 | 500 | 1061.1916 | 0 | 1061.1916 | 0 | 1061.1916 | 0 | 1061.1916 | 0 | 1061.1916 | 0 | 1061.1916 | 0 | 1061.1916 | 0 | 1061.1916 | 0 | 1061.1916 | 500 | 1061.1916 | 0 | 1061.1916 | 0 | 1061.1916 | 0
2025-08-05 | 13052.657 | 500 | 1087.7214 | 0 | 1087.7214 | 0 | 1087.7214 | 0 | 1087.7214 | 0 | 1087.7214 | 0 | 1087.7214 | 0 | 1087.7214 | 0 | 1087.7214 | 0 | 1087.7214 | 500 | 1087.7214 | 0 | 1087.7214 | 0 | 1087.7214 | 0
2025-08-06 | 13371.0145 | 500 | 1114.2512 | 0 | 1114.2512 | 0 | 1114.2512 | 0 | 1114.2512 | 0 | 1114.2512 | 0 | 1114.2512 | 0 | 1114.2512 | 0 | 1114.2512 | 0 | 1114.2512 | 500 | 1114.2512 | 0 | 1114.2512 | 0 | 1114.2512 | 0
2025-08-07 | 13689.372 | 500 | 1140.781 | 0 | 1140.781 | 0 | 1140.781 | 0 | 1140.781 | 0 | 1140.781 | 0 | 1140.781 | 0 | 1140.781 | 0 | 1140.781 | 0 | 1140.781 | 500 | 1140.781 | 0 | 1140.781 | 0 | 1140.781 | 0
2025-08-08 | 14007.7295 | 500 | 1167.3108 | 0 | 1167.3108 | 0 | 1167.3108 | 0 | 1167.3108 | 0 | 1167.3108 | 0 | 1167.3108 | 0 | 1167.3108 | 0 | 1167.3108 | 0 | 1167.3108 | 500 | 1167.3108 | 0 | 1167.3108 | 0 | 1167.3108 | 0
2025-08-09 | 14326.087 | 500 | 1193.8406 | 0 | 1193.8406 | 0 | 1193.8406 | 0 | 1193.8406 | 0 | 1193.8406 | 0 | 1193.8406 | 0 | 1193.8406 | 0 | 1193.8406 | 0 | 1193.8406 | 500 | 1193.8406 | 0 | 1193.8406 | 0 | 1193.8406 | 0
2025-08-10 | 14644.4444 | 500 | 1220.3704 | 0 | 1220.3704 | 0 | 1220.3704 | 0 | 1220.3704 | 0 | 1220.3704 | 0 | 1220.3704 | 0 | 1220.3704 | 0 | 1220.3704 | 0 | 1220.3704 | 500 | 1220.3704 | 0 | 1220.3704 | 0 | 1220.3704 | 0
2025-08-11 | 14962.8019 | 500 | 1246.9002 | 0 | 1246.9002 | 0 | 1246.9002 | 0 | 1246.9002 | 0 | 1246.9002 | 0 | 1246.9002 | 0 | 1246.9002 | 0 | 1246.9002 | 0 | 1246.9002 | 500 | 1246.9002 | 0 | 1246.9002 | 0 | 1246.9002 | 0
2025-08-12 | 15281.1594 | 500 | 1273.43 | 0 | 1273.43 | 0 | 1273.43 | 0 | 1273.43 | 0 | 1273.43 | 0 | 1273.43 | 0 | 1273.43 | 0 | 1273.43 | 0 | 1273.43 | 500 | 1273.43 | 0 | 1273.43 | 0 | 1273.43 | 0
2025-08-13 | 15599.5169 | 500 | 1299.9597 | 0 | 1299.9597 | 0 | 1299.9597 | 0 | 1299.9597 | 0 | 1299.9597 | 0 | 1299.9597 | 0 | 1299.9597 | 0 | 1299.9597 | 0 | 1299.9597 | 500 | 1299.9597 | 0 | 1299.9597 | 0 | 1299.9597 | 0
2025-08-14 | 15917.8744 | 500 | 1326.4895 | 0 | 1326.4895 | 0 | 1326.4895 | 0 | 1326.4895 | 0 | 1326.4895 | 0 | 1326.4895 | 0 | 1326.4895 | 0 | 1326.4895 | 0 | 1326.4895 | 500 | 1326.4895 | 0 | 1326.4895 | 0 | 1326.4895 | 0
2025-08-15 | 16236.2319 | 500 | 1353.0193 | 0 | 1353.0193 | 0 | 1353.0193 | 0 | 1353.0193 | 0 | 1353.0193 | 0 | 1353.0193 | 0 | 1353.0193 | 0 | 1353.0193 | 0 | 1353.0193 | 500 | 1353.0193 | 0 | 1353.0193 | 0 | 1353.0193 | 0
2025-08-16 | 16554.5894 | 500 | 1379.5491 | 0 | 1379.5491 | 0 | 1379.5491 | 0 | 1379.5491 | 0 | 1379.5491 | 0 | 1379.5491 | 0 | 1379.5491 | 0 | 1379.5491 | 0 | 1379.5491 | 500 | 1379.5491 | 0 | 1379.5491 | 0 | 1379.5491 | 0
2025-08-17 | 16872.9469 | 500 | 1406.0789 | 0 | 1406.0789 | 0 | 1406.0789 | 0 | 1406.0789 | 0 | 1406.0789 | 0 | 1406.0789 | 0 | 1406.0789 | 0 | 1406.0789 | 0 | 1406.0789 | 500 | 1406.0789 | 0 | 1406.0789 | 0 | 1406.0789 | 0
2025-08-18 | 17191.3043 | 500 | 1432.6087 | 0 | 1432.6087 | 0 | 1432.6087 | 0 | 1432.6087 | 0 | 1432.6087 | 0 | 1432.6087 | 0 | 1432.6087 | 0 | 1432.6087 | 0 | 1432.6087 | 500 | 1432.6087 | 0 | 1432.6087 | 0 | 1432.6087 | 0
2025-08-19 | 17509.6618 | 500 | 1459.1385 | 0 | 1459.1385 | 0 | 1459.1385 | 0 | 1459.1385 | 0 | 1459.1385 | 0 | 1459.1385 | 0 | 1459.1385 | 0 | 1459.1385 | 0 | 1459.1385 | 500 | 1459.1385 | 0 | 1459.1385 | 0 | 1459.1385 | 0
2025-08-20 | 17828.0193 | 500 | 1485.6683 | 0 | 1485.6683 | 0 | 1485.6683 | 0 | 1485.6683 | 0 | 1485.6683 | 0 | 1485.6683 | 0 | 1485.6683 | 0 | 1485.6683 | 0 | 1485.6683 | 500 | 1485.6683 | 0 | 1485.6683 | 0 | 1485.6683 | 0
2025-08-21 | 18146.3768 | 500 | 1512.1981 | 0 | 1512.1981 | 0 | 1512.1981 | 0 | 1512.1981 | 0 | 1512.1981 | 0 | 1512.1981 | 0 | 1512.1981 | 0 | 1512.1981 | 0 | 1512.1981 | 500 | 1512.1981 | 0 | 1512.1981 | 0 | 1512.1981 | 0
2025-08-22 | 18464.7343 | 500 | 1538.7279 | 0 | 1538.7279 | 0 | 1538.7279 | 0 | 1538.7279 | 0 | 1538.7279 | 0 | 1538.7279 | 0 | 1538.7279 | 0 | 1538.7279 | 0 | 1538.7279 | 500 | 1538.7279 | 0 | 1538.7279 | 0 | 1538.7279 | 0
2025-08-23 | 18783.0918 | 500 | 1565.2576 | 0 | 1565.2576 | 0 | 1565.2576 | 0 | 1565.2576 | 0 | 1565.2576 | 0 | 1565.2576 | 0 | 1565.2576 | 0 | 1565.2576 | 0 | 1565.2576 | 500 | 1565.2576 | 0 | 1565.2576 | 0 | 1565.2576 | 0
2025-08-24 | 19101.4493 | 500 | 1591.7874 | 0 | 1591.7874 | 0 | 1591.7874 | 0 | 1591.7874 | 0 | 1591.7874 | 0 | 1591.7874 | 0 | 1591.7874 | 0 | 1591.7874 | 0 | 1591.7874 | 500 | 1591.7874 | 0 | 1591.7874 | 0 | 1591.7874 | 0
2025-08-25 | 19419.8068 | 515 | 1618.3172 | 0 | 1618.3172 | 0 | 1618.3172 | 0 | 1618.3172 | 0 | 1618.3172 | 0 | 1618.3172 | 0 | 1618.3172 | 0 | 1618.3172 | 15 | 1618.3172 | 500 | 1618.3172 | 0 | 1618.3172 | 0 | 1618.3172 | 0
2025-08-26 | 19738.1643 | 3265 | 1644.847 | 0 | 1644.847 | 0 | 1644.847 | 0 | 1644.847 | 0 | 1644.847 | 0 | 1644.847 | 0 | 1644.847 | 0 | 1644.847 | 2765 | 1644.847 | 500 | 1644.847 | 0 | 1644.847 | 0 | 1644.847 | 0
2025-08-27 | 20056.5217 | 3265 | 1671.3768 | 0 | 1671.3768 | 0 | 1671.3768 | 0 | 1671.3768 | 0 | 1671.3768 | 0 | 1671.3768 | 0 | 1671.3768 | 0 | 1671.3768 | 2765 | 1671.3768 | 500 | 1671.3768 | 0 | 1671.3768 | 0 | 1671.3768 | 0
2025-08-28 | 20374.8792 | 3265 | 1697.9066 | 0 | 1697.9066 | 0 | 1697.9066 | 0 | 1697.9066 | 0 | 1697.9066 | 0 | 1697.9066 | 0 | 1697.9066 | 0 | 1697.9066 | 2765 | 1697.9066 | 500 | 1697.9066 | 0 | 1697.9066 | 0 | 1697.9066 | 0
2025-08-29 | 20693.2367 | 3265 | 1724.4364 | 0 | 1724.4364 | 0 | 1724.4364 | 0 | 1724.4364 | 0 | 1724.4364 | 0 | 1724.4364 | 0 | 1724.4364 | 0 | 1724.4364 | 2765 | 1724.4364 | 500 | 1724.4364 | 0 | 1724.4364 | 0 | 1724.4364 | 0
2025-08-30 | 21011.5942 | 3265 | 1750.9662 | 0 | 1750.9662 | 0 | 1750.9662 | 0 | 1750.9662 | 0 | 1750.9662 | 0 | 1750.9662 | 0 | 1750.9662 | 0 | 1750.9662 | 2765 | 1750.9662 | 500 | 1750.9662 | 0 | 1750.9662 | 0 | 1750.9662 | 0
2025-08-31 | 21329.9517 | 3265 | 1777.496 | 0 | 1777.496 | 0 | 1777.496 | 0 | 1777.496 | 0 | 1777.496 | 0 | 1777.496 | 0 | 1777.496 | 0 | 1777.496 | 2765 | 1777.496 | 500 | 1777.496 | 0 | 1777.496 | 0 | 1777.496 | 0
2025-09-01 | 21648.3092 | 3265 | 1804.0258 | 0 | 1804.0258 | 0 | 1804.0258 | 0 | 1804.0258 | 0 | 1804.0258 | 0 | 1804.0258 | 0 | 1804.0258 | 0 | 1804.0258 | 2765 | 1804.0258 | 500 | 1804.0258 | 0 | 1804.0258 | 0 | 1804.0258 | 0
2025-09-02 | 21966.6667 | 3265 | 1830.5556 | 0 | 1830.5556 | 0 | 1830.5556 | 0 | 1830.5556 | 0 | 1830.5556 | 0 | 1830.5556 | 0 | 1830.5556 | 0 | 1830.5556 | 2765 | 1830.5556 | 500 | 1830.5556 | 0 | 1830.5556 | 0 | 1830.5556 | 0
2025-09-03 | 22285.0242 | 3265 | 1857.0853 | 0 | 1857.0853 | 0 | 1857.0853 | 0 | 1857.0853 | 0 | 1857.0853 | 0 | 1857.0853 | 0 | 1857.0853 | 0 | 1857.0853 | 2765 | 1857.0853 | 500 | 1857.0853 | 0 | 1857.0853 | 0 | 1857.0853 | 0
2025-09-04 | 22603.3816 | 3951.7 | 1883.6151 | 0 | 1883.6151 | 0 | 1883.6151 | 0 | 1883.6151 | 0 | 1883.6151 | 686.7 | 1883.6151 | 0 | 1883.6151 | 0 | 1883.6151 | 2765 | 1883.6151 | 500 | 1883.6151 | 0 | 1883.6151 | 0 | 1883.6151 | 0
2025-09-05 | 22921.7391 | 3951.7 | 1910.1449 | 0 | 1910.1449 | 0 | 1910.1449 | 0 | 1910.1449 | 0 | 1910.1449 | 686.7 | 1910.1449 | 0 | 1910.1449 | 0 | 1910.1449 | 2765 | 1910.1449 | 500 | 1910.1449 | 0 | 1910.1449 | 0 | 1910.1449 | 0
2025-09-06 | 23240.0966 | 3951.7 | 1936.6747 | 0 | 1936.6747 | 0 | 1936.6747 | 0 | 1936.6747 | 0 | 1936.6747 | 686.7 | 1936.6747 | 0 | 1936.6747 | 0 | 1936.6747 | 2765 | 1936.6747 | 500 | 1936.6747 | 0 | 1936.6747 | 0 | 1936.6747 | 0
2025-09-07 | 23558.4541 | 3951.7 | 1963.2045 | 0 | 1963.2045 | 0 | 1963.2045 | 0 | 1963.2045 | 0 | 1963.2045 | 686.7 | 1963.2045 | 0 | 1963.2045 | 0 | 1963.2045 | 2765 | 1963.2045 | 500 | 1963.2045 | 0 | 1963.2045 | 0 | 1963.2045 | 0
2025-09-08 | 23876.8116 | 3951.7 | 1989.7343 | 0 | 1989.7343 | 0 | 1989.7343 | 0 | 1989.7343 | 0 | 1989.7343 | 686.7 | 1989.7343 | 0 | 1989.7343 | 0 | 1989.7343 | 2765 | 1989.7343 | 500 | 1989.7343 | 0 | 1989.7343 | 0 | 1989.7343 | 0
2025-09-09 | 24195.1691 | 3951.7 | 2016.2641 | 0 | 2016.2641 | 0 | 2016.2641 | 0 | 2016.2641 | 0 | 2016.2641 | 686.7 | 2016.2641 | 0 | 2016.2641 | 0 | 2016.2641 | 2765 | 2016.2641 | 500 | 2016.2641 | 0 | 2016.2641 | 0 | 2016.2641 | 0
2025-09-10 | 24513.5266 | 3951.7 | 2042.7939 | 0 | 2042.7939 | 0 | 2042.7939 | 0 | 2042.7939 | 0 | 2042.7939 | 686.7 | 2042.7939 | 0 | 2042.7939 | 0 | 2042.7939 | 2765 | 2042.7939 | 500 | 2042.7939 | 0 | 2042.7939 | 0 | 2042.7939 | 0
2025-09-11 | 24831.8841 | 3951.7 | 2069.3237 | 0 | 2069.3237 | 0 | 2069.3237 | 0 | 2069.3237 | 0 | 2069.3237 | 686.7 | 2069.3237 | 0 | 2069.3237 | 0 | 2069.3237 | 2765 | 2069.3237 | 500 | 2069.3237 | 0 | 2069.3237 | 0 | 2069.3237 | 0
2025-09-12 | 25150.2415 | 18066.7 | 2095.8535 | 14115 | 2095.8535 | 0 | 2095.8535 | 0 | 2095.8535 | 0 | 2095.8535 | 686.7 | 2095.8535 | 0 | 2095.8535 | 0 | 2095.8535 | 2765 | 2095.8535 | 500 | 2095.8535 | 0 | 2095.8535 | 0 | 2095.8535 | 0
2025-09-13 | 25468.599 | 18066.7 | 2122.3833 | 14115 | 2122.3833 | 0 | 2122.3833 | 0 | 2122.3833 | 0 | 2122.3833 | 686.7 | 2122.3833 | 0 | 2122.3833 | 0 | 2122.3833 | 2765 | 2122.3833 | 500 | 2122.3833 | 0 | 2122.3833 | 0 | 2122.3833 | 0
2025-09-14 | 25786.9565 | 18066.7 | 2148.913 | 14115 | 2148.913 | 0 | 2148.913 | 0 | 2148.913 | 0 | 2148.913 | 686.7 | 2148.913 | 0 | 2148.913 | 0 | 2148.913 | 2765 | 2148.913 | 500 | 2148.913 | 0 | 2148.913 | 0 | 2148.913 | 0
2025-09-15 | 26105.314 | 18066.7 | 2175.4428 | 14115 | 2175.4428 | 0 | 2175.4428 | 0 | 2175.4428 | 0 | 2175.4428 | 686.7 | 2175.4428 | 0 | 2175.4428 | 0 | 2175.4428 | 2765 | 2175.4428 | 500 | 2175.4428 | 0 | 2175.4428 | 0 | 2175.4428 | 0
2025-09-16 | 26423.6715 | 18066.7 | 2201.9726 | 14115 | 2201.9726 | 0 | 2201.9726 | 0 | 2201.9726 | 0 | 2201.9726 | 686.7 | 2201.9726 | 0 | 2201.9726 | 0 | 2201.9726 | 2765 | 2201.9726 | 500 | 2201.9726 | 0 | 2201.9726 | 0 | 2201.9726 | 0
2025-09-17 | 26742.029 | 18066.7 | 2228.5024 | 14115 | 2228.5024 | 0 | 2228.5024 | 0 | 2228.5024 | 0 | 2228.5024 | 686.7 | 2228.5024 | 0 | 2228.5024 | 0 | 2228.5024 | 2765 | 2228.5024 | 500 | 2228.5024 | 0 | 2228.5024 | 0 | 2228.5024 | 0
2025-09-18 | 27060.3865 | 18066.7 | 2255.0322 | 14115 | 2255.0322 | 0 | 2255.0322 | 0 | 2255.0322 | 0 | 2255.0322 | 686.7 | 2255.0322 | 0 | 2255.0322 | 0 | 2255.0322 | 2765 | 2255.0322 | 500 | 2255.0322 | 0 | 2255.0322 | 0 | 2255.0322 | 0
2025-09-19 | 27378.744 | 18066.7 | 2281.562 | 14115 | 2281.562 | 0 | 2281.562 | 0 | 2281.562 | 0 | 2281.562 | 686.7 | 2281.562 | 0 | 2281.562 | 0 | 2281.562 | 2765 | 2281.562 | 500 | 2281.562 | 0 | 2281.562 | 0 | 2281.562 | 0
2025-09-20 | 27697.1014 | 18066.7 | 2308.0918 | 14115 | 2308.0918 | 0 | 2308.0918 | 0 | 2308.0918 | 0 | 2308.0918 | 686.7 | 2308.0918 | 0 | 2308.0918 | 0 | 2308.0918 | 2765 | 2308.0918 | 500 | 2308.0918 | 0 | 2308.0918 | 0 | 2308.0918 | 0
2025-09-21 | 28015.4589 | 18066.7 | 2334.6216 | 14115 | 2334.6216 | 0 | 2334.6216 | 0 | 2334.6216 | 0 | 2334.6216 | 686.7 | 2334.6216 | 0 | 2334.6216 | 0 | 2334.6216 | 2765 | 2334.6216 | 500 | 2334.6216 | 0 | 2334.6216 | 0 | 2334.6216 | 0
2025-09-22 | 28333.8164 | 20014.2 | 2361.1514 | 14115 | 2361.1514 | 0 | 2361.1514 | 0 | 2361.1514 | 0 | 2361.1514 | 1184.2 | 2361.1514 | 0 | 2361.1514 | 0 | 2361.1514 | 4215 | 2361.1514 | 500 | 2361.1514 | 0 | 2361.1514 | 0 | 2361.1514 | 0
2025-09-23 | 28652.1739 | 21151.72 | 2387.6812 | 14262.52 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-24 | 28652.1739 | 31325.53 | 2387.6812 | 24436.33 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-25 | 28652.1739 | 31325.53 | 2387.6812 | 24436.33 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-26 | 28652.1739 | 31325.53 | 2387.6812 | 24436.33 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-27 | 28652.1739 | 31325.53 | 2387.6812 | 24436.33 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-28 | 28652.1739 | 31325.53 | 2387.6812 | 24436.33 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 1184.2 | 2387.6812 | 990 | 2387.6812 | 0 | 2387.6812 | 4215 | 2387.6812 | 500 | 2387.6812 | 0 | 2387.6812 | 0 | 2387.6812 | 0
2025-09-29 | 28836.99 | 31325.53 | 2403.0825 | 24436.33 | 2403.0825 | 0 | 2403.0825 | 0 | 2403.0825 | 0 | 2403.0825 | 1184.2 | 2403.0825 | 990 | 2403.0825 | 0 | 2403.0825 | 4215 | 2403.0825 | 500 | 2403.0825 | 0 | 2403.0825 | 0 | 2403.0825 | 0
2025-09-30 | 29021.806 | 31325.53 | 2418.4838 | 24436.33 | 2418.4838 | 0 | 2418.4838 | 0 | 2418.4838 | 0 | 2418.4838 | 1184.2 | 2418.4838 | 990 | 2418.4838 | 0 | 2418.4838 | 4215 | 2418.4838 | 500 | 2418.4838 | 0 | 2418.4838 | 0 | 2418.4838 | 0
2025-10-01 | 29206.6221 | 31325.53 | 2433.8852 | 24436.33 | 2433.8852 | 0 | 2433.8852 | 0 | 2433.8852 | 0 | 2433.8852 | 1184.2 | 2433.8852 | 990 | 2433.8852 | 0 | 2433.8852 | 4215 | 2433.8852 | 500 | 2433.8852 | 0 | 2433.8852 | 0 | 2433.8852 | 0
2025-10-02 | 29391.4381 | 31325.53 | 2449.2865 | 24436.33 | 2449.2865 | 0 | 2449.2865 | 0 | 2449.2865 | 0 | 2449.2865 | 1184.2 | 2449.2865 | 990 | 2449.2865 | 0 | 2449.2865 | 4215 | 2449.2865 | 500 | 2449.2865 | 0 | 2449.2865 | 0 | 2449.2865 | 0
2025-10-03 | 29576.2542 | 31325.53 | 2464.6878 | 24436.33 | 2464.6878 | 0 | 2464.6878 | 0 | 2464.6878 | 0 | 2464.6878 | 1184.2 | 2464.6878 | 990 | 2464.6878 | 0 | 2464.6878 | 4215 | 2464.6878 | 500 | 2464.6878 | 0 | 2464.6878 | 0 | 2464.6878 | 0
2025-10-04 | 29761.0702 | 31325.53 | 2480.0892 | 24436.33 | 2480.0892 | 0 | 2480.0892 | 0 | 2480.0892 | 0 | 2480.0892 | 1184.2 | 2480.0892 | 990 | 2480.0892 | 0 | 2480.0892 | 4215 | 2480.0892 | 500 | 2480.0892 | 0 | 2480.0892 | 0 | 2480.0892 | 0
2025-10-05 | 29945.8863 | 31325.53 | 2495.4905 | 24436.33 | 2495.4905 | 0 | 2495.4905 | 0 | 2495.4905 | 0 | 2495.4905 | 1184.2 | 2495.4905 | 990 | 2495.4905 | 0 | 2495.4905 | 4215 | 2495.4905 | 500 | 2495.4905 | 0 | 2495.4905 | 0 | 2495.4905 | 0
2025-10-06 | 30130.7023 | 31325.53 | 2510.8919 | 24436.33 | 2510.8919 | 0 | 2510.8919 | 0 | 2510.8919 | 0 | 2510.8919 | 1184.2 | 2510.8919 | 990 | 2510.8919 | 0 | 2510.8919 | 4215 | 2510.8919 | 500 | 2510.8919 | 0 | 2510.8919 | 0 | 2510.8919 | 0
2025-10-07 | 30315.5184 | 31325.53 | 2526.2932 | 24436.33 | 2526.2932 | 0 | 2526.2932 | 0 | 2526.2932 | 0 | 2526.2932 | 1184.2 | 2526.2932 | 990 | 2526.2932 | 0 | 2526.2932 | 4215 | 2526.2932 | 500 | 2526.2932 | 0 | 2526.2932 | 0 | 2526.2932 | 0
2025-10-08 | 30500.3344 | 31325.53 | 2541.6945 | 24436.33 | 2541.6945 | 0 | 2541.6945 | 0 | 2541.6945 | 0 | 2541.6945 | 1184.2 | 2541.6945 | 990 | 2541.6945 | 0 | 2541.6945 | 4215 | 2541.6945 | 500 | 2541.6945 | 0 | 2541.6945 | 0 | 2541.6945 | 0
2025-10-09 | 30685.1505 | 31325.53 | 2557.0959 | 24436.33 | 2557.0959 | 0 | 2557.0959 | 0 | 2557.0959 | 0 | 2557.0959 | 1184.2 | 2557.0959 | 990 | 2557.0959 | 0 | 2557.0959 | 4215 | 2557.0959 | 500 | 2557.0959 | 0 | 2557.0959 | 0 | 2557.0959 | 0
2025-10-10 | 30869.9666 | 31325.53 | 2572.4972 | 24436.33 | 2572.4972 | 0 | 2572.4972 | 0 | 2572.4972 | 0 | 2572.4972 | 1184.2 | 2572.4972 | 990 | 2572.4972 | 0 | 2572.4972 | 4215 | 2572.4972 | 500 | 2572.4972 | 0 | 2572.4972 | 0 | 2572.4972 | 0
2025-10-11 | 31054.7826 | 31325.53 | 2587.8986 | 24436.33 | 2587.8986 | 0 | 2587.8986 | 0 | 2587.8986 | 0 | 2587.8986 | 1184.2 | 2587.8986 | 990 | 2587.8986 | 0 | 2587.8986 | 4215 | 2587.8986 | 500 | 2587.8986 | 0 | 2587.8986 | 0 | 2587.8986 | 0
2025-10-12 | 31239.5987 | 31325.53 | 2603.2999 | 24436.33 | 2603.2999 | 0 | 2603.2999 | 0 | 2603.2999 | 0 | 2603.2999 | 1184.2 | 2603.2999 | 990 | 2603.2999 | 0 | 2603.2999 | 4215 | 2603.2999 | 500 | 2603.2999 | 0 | 2603.2999 | 0 | 2603.2999 | 0
2025-10-13 | 31424.4147 |  | 2618.7012 |  | 2618.7012 |  | 2618.7012 |  | 2618.7012 |  | 2618.7012 |  | 2618.7012 |  | 2618.7012 |  | 2618.7012 |  | 2618.7012 |  | 2618.7012 |  | 2618.7012 |  | 2618.7012
2025-10-14 | 31609.2308 |  | 2634.1026 |  | 2634.1026 |  | 2634.1026 |  | 2634.1026 |  | 2634.1026 |  | 2634.1026 |  | 2634.1026 |  | 2634.1026 |  | 2634.1026 |  | 2634.1026 |  | 2634.1026 |  | 2634.1026
2025-10-15 | 31794.0468 |  | 2649.5039 |  | 2649.5039 |  | 2649.5039 |  | 2649.5039 |  | 2649.5039 |  | 2649.5039 |  | 2649.5039 |  | 2649.5039 |  | 2649.5039 |  | 2649.5039 |  | 2649.5039 |  | 2649.5039
2025-10-16 | 31978.8629 |  | 2664.9052 |  | 2664.9052 |  | 2664.9052 |  | 2664.9052 |  | 2664.9052 |  | 2664.9052 |  | 2664.9052 |  | 2664.9052 |  | 2664.9052 |  | 2664.9052 |  | 2664.9052 |  | 2664.9052
2025-10-17 | 32163.6789 |  | 2680.3066 |  | 2680.3066 |  | 2680.3066 |  | 2680.3066 |  | 2680.3066 |  | 2680.3066 |  | 2680.3066 |  | 2680.3066 |  | 2680.3066 |  | 2680.3066 |  | 2680.3066 |  | 2680.3066
2025-10-18 | 32348.495 |  | 2695.7079 |  | 2695.7079 |  | 2695.7079 |  | 2695.7079 |  | 2695.7079 |  | 2695.7079 |  | 2695.7079 |  | 2695.7079 |  | 2695.7079 |  | 2695.7079 |  | 2695.7079 |  | 2695.7079
2025-10-19 | 32533.311 |  | 2711.1093 |  | 2711.1093 |  | 2711.1093 |  | 2711.1093 |  | 2711.1093 |  | 2711.1093 |  | 2711.1093 |  | 2711.1093 |  | 2711.1093 |  | 2711.1093 |  | 2711.1093 |  | 2711.1093
2025-10-20 | 32718.1271 |  | 2726.5106 |  | 2726.5106 |  | 2726.5106 |  | 2726.5106 |  | 2726.5106 |  | 2726.5106 |  | 2726.5106 |  | 2726.5106 |  | 2726.5106 |  | 2726.5106 |  | 2726.5106 |  | 2726.5106
2025-10-21 | 32902.9431 |  | 2741.9119 |  | 2741.9119 |  | 2741.9119 |  | 2741.9119 |  | 2741.9119 |  | 2741.9119 |  | 2741.9119 |  | 2741.9119 |  | 2741.9119 |  | 2741.9119 |  | 2741.9119 |  | 2741.9119
2025-10-22 | 33087.7592 |  | 2757.3133 |  | 2757.3133 |  | 2757.3133 |  | 2757.3133 |  | 2757.3133 |  | 2757.3133 |  | 2757.3133 |  | 2757.3133 |  | 2757.3133 |  | 2757.3133 |  | 2757.3133 |  | 2757.3133
2025-10-23 | 33272.5753 |  | 2772.7146 |  | 2772.7146 |  | 2772.7146 |  | 2772.7146 |  | 2772.7146 |  | 2772.7146 |  | 2772.7146 |  | 2772.7146 |  | 2772.7146 |  | 2772.7146 |  | 2772.7146 |  | 2772.7146
2025-10-24 | 33457.3913 |  | 2788.1159 |  | 2788.1159 |  | 2788.1159 |  | 2788.1159 |  | 2788.1159 |  | 2788.1159 |  | 2788.1159 |  | 2788.1159 |  | 2788.1159 |  | 2788.1159 |  | 2788.1159 |  | 2788.1159
2025-10-25 | 33642.2074 |  | 2803.5173 |  | 2803.5173 |  | 2803.5173 |  | 2803.5173 |  | 2803.5173 |  | 2803.5173 |  | 2803.5173 |  | 2803.5173 |  | 2803.5173 |  | 2803.5173 |  | 2803.5173 |  | 2803.5173
2025-10-26 | 33827.0234 |  | 2818.9186 |  | 2818.9186 |  | 2818.9186 |  | 2818.9186 |  | 2818.9186 |  | 2818.9186 |  | 2818.9186 |  | 2818.9186 |  | 2818.9186 |  | 2818.9186 |  | 2818.9186 |  | 2818.9186
2025-10-27 | 34011.8395 |  | 2834.32 |  | 2834.32 |  | 2834.32 |  | 2834.32 |  | 2834.32 |  | 2834.32 |  | 2834.32 |  | 2834.32 |  | 2834.32 |  | 2834.32 |  | 2834.32 |  | 2834.32
2025-10-28 | 34196.6555 |  | 2849.7213 |  | 2849.7213 |  | 2849.7213 |  | 2849.7213 |  | 2849.7213 |  | 2849.7213 |  | 2849.7213 |  | 2849.7213 |  | 2849.7213 |  | 2849.7213 |  | 2849.7213 |  | 2849.7213
2025-10-29 | 34381.4716 |  | 2865.1226 |  | 2865.1226 |  | 2865.1226 |  | 2865.1226 |  | 2865.1226 |  | 2865.1226 |  | 2865.1226 |  | 2865.1226 |  | 2865.1226 |  | 2865.1226 |  | 2865.1226 |  | 2865.1226
2025-10-30 | 34566.2876 |  | 2880.524 |  | 2880.524 |  | 2880.524 |  | 2880.524 |  | 2880.524 |  | 2880.524 |  | 2880.524 |  | 2880.524 |  | 2880.524 |  | 2880.524 |  | 2880.524 |  | 2880.524
2025-10-31 | 34751.1037 |  | 2895.9253 |  | 2895.9253 |  | 2895.9253 |  | 2895.9253 |  | 2895.9253 |  | 2895.9253 |  | 2895.9253 |  | 2895.9253 |  | 2895.9253 |  | 2895.9253 |  | 2895.9253 |  | 2895.9253
2025-11-01 | 34935.9197 |  | 2911.3266 |  | 2911.3266 |  | 2911.3266 |  | 2911.3266 |  | 2911.3266 |  | 2911.3266 |  | 2911.3266 |  | 2911.3266 |  | 2911.3266 |  | 2911.3266 |  | 2911.3266 |  | 2911.3266
2025-11-02 | 35120.7358 |  | 2926.728 |  | 2926.728 |  | 2926.728 |  | 2926.728 |  | 2926.728 |  | 2926.728 |  | 2926.728 |  | 2926.728 |  | 2926.728 |  | 2926.728 |  | 2926.728 |  | 2926.728
2025-11-03 | 35305.5518 |  | 2942.1293 |  | 2942.1293 |  | 2942.1293 |  | 2942.1293 |  | 2942.1293 |  | 2942.1293 |  | 2942.1293 |  | 2942.1293 |  | 2942.1293 |  | 2942.1293 |  | 2942.1293 |  | 2942.1293
2025-11-04 | 35490.3679 |  | 2957.5307 |  | 2957.5307 |  | 2957.5307 |  | 2957.5307 |  | 2957.5307 |  | 2957.5307 |  | 2957.5307 |  | 2957.5307 |  | 2957.5307 |  | 2957.5307 |  | 2957.5307 |  | 2957.5307
2025-11-05 | 35675.1839 |  | 2972.932 |  | 2972.932 |  | 2972.932 |  | 2972.932 |  | 2972.932 |  | 2972.932 |  | 2972.932 |  | 2972.932 |  | 2972.932 |  | 2972.932 |  | 2972.932 |  | 2972.932
2025-11-06 | 35860 |  | 2988.3333 |  | 2988.3333 |  | 2988.3333 |  | 2988.3333 |  | 2988.3333 |  | 2988.3333 |  | 2988.3333 |  | 2988.3333 |  | 2988.3333 |  | 2988.3333 |  | 2988.3333 |  | 2988.3333
2025-11-07 | 36044.8161 |  | 3003.7347 |  | 3003.7347 |  | 3003.7347 |  | 3003.7347 |  | 3003.7347 |  | 3003.7347 |  | 3003.7347 |  | 3003.7347 |  | 3003.7347 |  | 3003.7347 |  | 3003.7347 |  | 3003.7347
2025-11-08 | 36229.6321 |  | 3019.136 |  | 3019.136 |  | 3019.136 |  | 3019.136 |  | 3019.136 |  | 3019.136 |  | 3019.136 |  | 3019.136 |  | 3019.136 |  | 3019.136 |  | 3019.136 |  | 3019.136
2025-11-09 | 36414.4482 |  | 3034.5373 |  | 3034.5373 |  | 3034.5373 |  | 3034.5373 |  | 3034.5373 |  | 3034.5373 |  | 3034.5373 |  | 3034.5373 |  | 3034.5373 |  | 3034.5373 |  | 3034.5373 |  | 3034.5373
2025-11-10 | 36599.2642 |  | 3049.9387 |  | 3049.9387 |  | 3049.9387 |  | 3049.9387 |  | 3049.9387 |  | 3049.9387 |  | 3049.9387 |  | 3049.9387 |  | 3049.9387 |  | 3049.9387 |  | 3049.9387 |  | 3049.9387
2025-11-11 | 36784.0803 |  | 3065.34 |  | 3065.34 |  | 3065.34 |  | 3065.34 |  | 3065.34 |  | 3065.34 |  | 3065.34 |  | 3065.34 |  | 3065.34 |  | 3065.34 |  | 3065.34 |  | 3065.34
2025-11-12 | 36968.8963 |  | 3080.7414 |  | 3080.7414 |  | 3080.7414 |  | 3080.7414 |  | 3080.7414 |  | 3080.7414 |  | 3080.7414 |  | 3080.7414 |  | 3080.7414 |  | 3080.7414 |  | 3080.7414 |  | 3080.7414
2025-11-13 | 37153.7124 |  | 3096.1427 |  | 3096.1427 |  | 3096.1427 |  | 3096.1427 |  | 3096.1427 |  | 3096.1427 |  | 3096.1427 |  | 3096.1427 |  | 3096.1427 |  | 3096.1427 |  | 3096.1427 |  | 3096.1427
2025-11-14 | 37338.5284 |  | 3111.544 |  | 3111.544 |  | 3111.544 |  | 3111.544 |  | 3111.544 |  | 3111.544 |  | 3111.544 |  | 3111.544 |  | 3111.544 |  | 3111.544 |  | 3111.544 |  | 3111.544
2025-11-15 | 37523.3445 |  | 3126.9454 |  | 3126.9454 |  | 3126.9454 |  | 3126.9454 |  | 3126.9454 |  | 3126.9454 |  | 3126.9454 |  | 3126.9454 |  | 3126.9454 |  | 3126.9454 |  | 3126.9454 |  | 3126.9454
2025-11-16 | 37708.1605 |  | 3142.3467 |  | 3142.3467 |  | 3142.3467 |  | 3142.3467 |  | 3142.3467 |  | 3142.3467 |  | 3142.3467 |  | 3142.3467 |  | 3142.3467 |  | 3142.3467 |  | 3142.3467 |  | 3142.3467
2025-11-17 | 37892.9766 |  | 3157.748 |  | 3157.748 |  | 3157.748 |  | 3157.748 |  | 3157.748 |  | 3157.748 |  | 3157.748 |  | 3157.748 |  | 3157.748 |  | 3157.748 |  | 3157.748 |  | 3157.748
2025-11-18 | 38077.7926 |  | 3173.1494 |  | 3173.1494 |  | 3173.1494 |  | 3173.1494 |  | 3173.1494 |  | 3173.1494 |  | 3173.1494 |  | 3173.1494 |  | 3173.1494 |  | 3173.1494 |  | 3173.1494 |  | 3173.1494
2025-11-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-11-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2025-12-31 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-01-31 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-02-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-03-31 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-04-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-05-31 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-06-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-24 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-25 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-26 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-27 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-28 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-29 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-30 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-07-31 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-01 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-02 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-03 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-04 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-05 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-06 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-07 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-08 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-09 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-10 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-11 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-12 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-13 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-14 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-15 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-16 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-17 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-18 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-19 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-20 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-21 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-22 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-23 | 38262.6087 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507 |  | 3188.5507
2026-08-24 | 38565.639 |  | 3213.8032 |  | 3213.8032 |  | 3213.8032 |  | 3213.8032 |  | 3213.8032 |  | 3213.8032 |  | 3213.8032 |  | 3213.8032 |  | 3213.8032 |  | 3213.8032 |  | 3213.8032 |  | 3213.8032
2026-08-25 | 38868.6693 |  | 3239.0558 |  | 3239.0558 |  | 3239.0558 |  | 3239.0558 |  | 3239.0558 |  | 3239.0558 |  | 3239.0558 |  | 3239.0558 |  | 3239.0558 |  | 3239.0558 |  | 3239.0558 |  | 3239.0558
2026-08-26 | 39171.6996 |  | 3264.3083 |  | 3264.3083 |  | 3264.3083 |  | 3264.3083 |  | 3264.3083 |  | 3264.3083 |  | 3264.3083 |  | 3264.3083 |  | 3264.3083 |  | 3264.3083 |  | 3264.3083 |  | 3264.3083
2026-08-27 | 39474.7299 |  | 3289.5608 |  | 3289.5608 |  | 3289.5608 |  | 3289.5608 |  | 3289.5608 |  | 3289.5608 |  | 3289.5608 |  | 3289.5608 |  | 3289.5608 |  | 3289.5608 |  | 3289.5608 |  | 3289.5608
2026-08-28 | 39777.7602 |  | 3314.8134 |  | 3314.8134 |  | 3314.8134 |  | 3314.8134 |  | 3314.8134 |  | 3314.8134 |  | 3314.8134 |  | 3314.8134 |  | 3314.8134 |  | 3314.8134 |  | 3314.8134 |  | 3314.8134
2026-08-29 | 40080.7905 |  | 3340.0659 |  | 3340.0659 |  | 3340.0659 |  | 3340.0659 |  | 3340.0659 |  | 3340.0659 |  | 3340.0659 |  | 3340.0659 |  | 3340.0659 |  | 3340.0659 |  | 3340.0659 |  | 3340.0659
2026-08-30 | 40383.8208 |  | 3365.3184 |  | 3365.3184 |  | 3365.3184 |  | 3365.3184 |  | 3365.3184 |  | 3365.3184 |  | 3365.3184 |  | 3365.3184 |  | 3365.3184 |  | 3365.3184 |  | 3365.3184 |  | 3365.3184
2026-08-31 | 40686.8511 |  | 3390.5709 |  | 3390.5709 |  | 3390.5709 |  | 3390.5709 |  | 3390.5709 |  | 3390.5709 |  | 3390.5709 |  | 3390.5709 |  | 3390.5709 |  | 3390.5709 |  | 3390.5709 |  | 3390.5709
2026-09-01 | 40989.8814 |  | 3415.8235 |  | 3415.8235 |  | 3415.8235 |  | 3415.8235 |  | 3415.8235 |  | 3415.8235 |  | 3415.8235 |  | 3415.8235 |  | 3415.8235 |  | 3415.8235 |  | 3415.8235 |  | 3415.8235
2026-09-02 | 41292.9117 |  | 3441.076 |  | 3441.076 |  | 3441.076 |  | 3441.076 |  | 3441.076 |  | 3441.076 |  | 3441.076 |  | 3441.076 |  | 3441.076 |  | 3441.076 |  | 3441.076 |  | 3441.076
2026-09-03 | 41595.942 |  | 3466.3285 |  | 3466.3285 |  | 3466.3285 |  | 3466.3285 |  | 3466.3285 |  | 3466.3285 |  | 3466.3285 |  | 3466.3285 |  | 3466.3285 |  | 3466.3285 |  | 3466.3285 |  | 3466.3285
2026-09-04 | 41898.9723 |  | 3491.581 |  | 3491.581 |  | 3491.581 |  | 3491.581 |  | 3491.581 |  | 3491.581 |  | 3491.581 |  | 3491.581 |  | 3491.581 |  | 3491.581 |  | 3491.581 |  | 3491.581
2026-09-05 | 42202.0026 |  | 3516.8336 |  | 3516.8336 |  | 3516.8336 |  | 3516.8336 |  | 3516.8336 |  | 3516.8336 |  | 3516.8336 |  | 3516.8336 |  | 3516.8336 |  | 3516.8336 |  | 3516.8336 |  | 3516.8336
2026-09-06 | 42505.0329 |  | 3542.0861 |  | 3542.0861 |  | 3542.0861 |  | 3542.0861 |  | 3542.0861 |  | 3542.0861 |  | 3542.0861 |  | 3542.0861 |  | 3542.0861 |  | 3542.0861 |  | 3542.0861 |  | 3542.0861
2026-09-07 | 42808.0632 |  | 3567.3386 |  | 3567.3386 |  | 3567.3386 |  | 3567.3386 |  | 3567.3386 |  | 3567.3386 |  | 3567.3386 |  | 3567.3386 |  | 3567.3386 |  | 3567.3386 |  | 3567.3386 |  | 3567.3386
2026-09-08 | 43111.0935 |  | 3592.5911 |  | 3592.5911 |  | 3592.5911 |  | 3592.5911 |  | 3592.5911 |  | 3592.5911 |  | 3592.5911 |  | 3592.5911 |  | 3592.5911 |  | 3592.5911 |  | 3592.5911 |  | 3592.5911
2026-09-09 | 43414.1238 |  | 3617.8437 |  | 3617.8437 |  | 3617.8437 |  | 3617.8437 |  | 3617.8437 |  | 3617.8437 |  | 3617.8437 |  | 3617.8437 |  | 3617.8437 |  | 3617.8437 |  | 3617.8437 |  | 3617.8437
2026-09-10 | 43717.1542 |  | 3643.0962 |  | 3643.0962 |  | 3643.0962 |  | 3643.0962 |  | 3643.0962 |  | 3643.0962 |  | 3643.0962 |  | 3643.0962 |  | 3643.0962 |  | 3643.0962 |  | 3643.0962 |  | 3643.0962
2026-09-11 | 44020.1845 |  | 3668.3487 |  | 3668.3487 |  | 3668.3487 |  | 3668.3487 |  | 3668.3487 |  | 3668.3487 |  | 3668.3487 |  | 3668.3487 |  | 3668.3487 |  | 3668.3487 |  | 3668.3487 |  | 3668.3487
2026-09-12 | 44323.2148 |  | 3693.6012 |  | 3693.6012 |  | 3693.6012 |  | 3693.6012 |  | 3693.6012 |  | 3693.6012 |  | 3693.6012 |  | 3693.6012 |  | 3693.6012 |  | 3693.6012 |  | 3693.6012 |  | 3693.6012
2026-09-13 | 44626.2451 |  | 3718.8538 |  | 3718.8538 |  | 3718.8538 |  | 3718.8538 |  | 3718.8538 |  | 3718.8538 |  | 3718.8538 |  | 3718.8538 |  | 3718.8538 |  | 3718.8538 |  | 3718.8538 |  | 3718.8538
2026-09-14 | 44929.2754 |  | 3744.1063 |  | 3744.1063 |  | 3744.1063 |  | 3744.1063 |  | 3744.1063 |  | 3744.1063 |  | 3744.1063 |  | 3744.1063 |  | 3744.1063 |  | 3744.1063 |  | 3744.1063 |  | 3744.1063
2026-09-15 | 45232.3057 |  | 3769.3588 |  | 3769.3588 |  | 3769.3588 |  | 3769.3588 |  | 3769.3588 |  | 3769.3588 |  | 3769.3588 |  | 3769.3588 |  | 3769.3588 |  | 3769.3588 |  | 3769.3588 |  | 3769.3588
2026-09-16 | 45535.336 |  | 3794.6113 |  | 3794.6113 |  | 3794.6113 |  | 3794.6113 |  | 3794.6113 |  | 3794.6113 |  | 3794.6113 |  | 3794.6113 |  | 3794.6113 |  | 3794.6113 |  | 3794.6113 |  | 3794.6113
2026-09-17 | 45838.3663 |  | 3819.8639 |  | 3819.8639 |  | 3819.8639 |  | 3819.8639 |  | 3819.8639 |  | 3819.8639 |  | 3819.8639 |  | 3819.8639 |  | 3819.8639 |  | 3819.8639 |  | 3819.8639 |  | 3819.8639
2026-09-18 | 46141.3966 |  | 3845.1164 |  | 3845.1164 |  | 3845.1164 |  | 3845.1164 |  | 3845.1164 |  | 3845.1164 |  | 3845.1164 |  | 3845.1164 |  | 3845.1164 |  | 3845.1164 |  | 3845.1164 |  | 3845.1164
2026-09-19 | 46444.4269 |  | 3870.3689 |  | 3870.3689 |  | 3870.3689 |  | 3870.3689 |  | 3870.3689 |  | 3870.3689 |  | 3870.3689 |  | 3870.3689 |  | 3870.3689 |  | 3870.3689 |  | 3870.3689 |  | 3870.3689
2026-09-20 | 46747.4572 |  | 3895.6214 |  | 3895.6214 |  | 3895.6214 |  | 3895.6214 |  | 3895.6214 |  | 3895.6214 |  | 3895.6214 |  | 3895.6214 |  | 3895.6214 |  | 3895.6214 |  | 3895.6214 |  | 3895.6214
2026-09-21 | 47050.4875 |  | 3920.874 |  | 3920.874 |  | 3920.874 |  | 3920.874 |  | 3920.874 |  | 3920.874 |  | 3920.874 |  | 3920.874 |  | 3920.874 |  | 3920.874 |  | 3920.874 |  | 3920.874
2026-09-22 | 47353.5178 |  | 3946.1265 |  | 3946.1265 |  | 3946.1265 |  | 3946.1265 |  | 3946.1265 |  | 3946.1265 |  | 3946.1265 |  | 3946.1265 |  | 3946.1265 |  | 3946.1265 |  | 3946.1265 |  | 3946.1265
2026-09-23 | 47656.5481 |  | 3971.379 |  | 3971.379 |  | 3971.379 |  | 3971.379 |  | 3971.379 |  | 3971.379 |  | 3971.379 |  | 3971.379 |  | 3971.379 |  | 3971.379 |  | 3971.379 |  | 3971.379
2026-09-24 | 47959.5784 |  | 3996.6315 |  | 3996.6315 |  | 3996.6315 |  | 3996.6315 |  | 3996.6315 |  | 3996.6315 |  | 3996.6315 |  | 3996.6315 |  | 3996.6315 |  | 3996.6315 |  | 3996.6315 |  | 3996.6315
2026-09-25 | 48262.6087 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841 |  | 4021.8841

## Equipment Cost
Date | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Planned 1805 · Equipment - Forklift (Cumulative) | Actual 1805 · Equipment - Forklift (Cumulative) | Planned 1818 · Equipment - BCU (Cumulative) | Actual 1818 · Equipment - BCU (Cumulative) | Planned 1819 · Equipment - TPMB (Cumulative) | Actual 1819 · Equipment - TPMB (Cumulative) | Planned 1820 · Equipment & Tools (Cumulative) | Actual 1820 · Equipment & Tools (Cumulative) | Planned 1821 · Equipment - C3 (Cumulative) | Actual 1821 · Equipment - C3 (Cumulative) | Planned 1822 · Equipment - C2 (Cumulative) | Actual 1822 · Equipment - C2 (Cumulative) | Planned 1823 · Equipment - TCU Basic (Cumulative) | Actual 1823 · Equipment - TCU Basic (Cumulative) | Planned 1824 · Equipment - TCU PLC (Cumulative) | Actual 1824 · Equipment - TCU PLC (Cumulative) | Planned 1825 · Equipment - Blower Skids (Cumulative) | Actual 1825 · Equipment - Blower Skids (Cumulative) | Planned 1826 · Equipment - Well Heads (Cumulative) | Actual 1826 · Equipment - Well Heads (Cumulative) | Planned 1827 · Equipment - Thermal Wells (Cumulative) | Actual 1827 · Equipment - Thermal Wells (Cumulative) | Planned 1829 · Equipment - Water Treatment Sys (Cumulative) | Actual 1829 · Equipment - Water Treatment Sys (Cumulative) | Planned 1830 · Equipment - Vapor Extraction (Cumulative) | Actual 1830 · Equipment - Vapor Extraction (Cumulative) | Planned 1831 · Equipment - GTR/C3 Components (Cumulative) | Actual 1831 · Equipment - GTR/C3 Components (Cumulative) | Planned 1832 · Equip - Control/Dist panels (Cumulative) | Actual 1832 · Equip - Control/Dist panels (Cumulative) | Planned 1833 · Equipment - Office & computer (Cumulative) | Actual 1833 · Equipment - Office & computer (Cumulative) | Planned 5113 · Repairs & maint (Direct) (Cumulative) | Actual 5113 · Repairs & maint (Direct) (Cumulative)
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-26 | 937.1 | 5000 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 5000 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0 | 55.1235 | 0
2025-06-27 | 1874.2 | 5000 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 5000 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0 | 110.2471 | 0
2025-06-28 | 2811.3 | 5000 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 5000 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0 | 165.3706 | 0
2025-06-29 | 3748.4 | 5000 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 5000 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0 | 220.4941 | 0
2025-06-30 | 4685.5 | 5000 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 5000 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0 | 275.6176 | 0
2025-07-01 | 5622.6 | 5000 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 5000 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0 | 330.7412 | 0
2025-07-02 | 6559.7 | 5000 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 5000 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0 | 385.8647 | 0
2025-07-03 | 7496.8 | 5000 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 5000 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0 | 440.9882 | 0
2025-07-04 | 8433.9 | 5000 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 5000 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0 | 496.1118 | 0
2025-07-05 | 9371 | 5000 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 5000 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0 | 551.2353 | 0
2025-07-06 | 10308.1 | 5000 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 5000 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0 | 606.3588 | 0
2025-07-07 | 11245.2 | 5000 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 5000 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0 | 661.4824 | 0
2025-07-08 | 12182.3 | 5000 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 5000 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0 | 716.6059 | 0
2025-07-09 | 13119.4 | 5000 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 5000 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0 | 771.7294 | 0
2025-07-10 | 14056.5 | 5000 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 5000 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0 | 826.8529 | 0
2025-07-11 | 14993.6 | 5000 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 5000 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0 | 881.9765 | 0
2025-07-12 | 15930.7 | 5000 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0 | 937.1 | 5000 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0 | 937.1 | 0
2025-07-13 | 16867.8 | 5000 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 5000 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0 | 992.2235 | 0
2025-07-14 | 17804.9 | 5000 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 5000 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0 | 1047.3471 | 0
2025-07-15 | 18742 | 5000 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 5000 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0 | 1102.4706 | 0
2025-07-16 | 19679.1 | 5000 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 5000 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0 | 1157.5941 | 0
2025-07-17 | 20616.2 | 5000 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 5000 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0 | 1212.7176 | 0
2025-07-18 | 21553.3 | 5000 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 5000 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0 | 1267.8412 | 0
2025-07-19 | 22490.4 | 5000 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 5000 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0 | 1322.9647 | 0
2025-07-20 | 23427.5 | 5000 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 5000 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0 | 1378.0882 | 0
2025-07-21 | 24364.6 | 5000 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 5000 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0 | 1433.2118 | 0
2025-07-22 | 25301.7 | 5000 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 5000 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0 | 1488.3353 | 0
2025-07-23 | 26238.8 | 5000 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 5000 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0 | 1543.4588 | 0
2025-07-24 | 27175.9 | 5000 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 5000 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0 | 1598.5824 | 0
2025-07-25 | 28113 | 5000 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 5000 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0 | 1653.7059 | 0
2025-07-26 | 29050.1 | 5000 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 5000 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0 | 1708.8294 | 0
2025-07-27 | 29987.2 | 5000 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 5000 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0 | 1763.9529 | 0
2025-07-28 | 30924.3 | 5000 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 5000 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0 | 1819.0765 | 0
2025-07-29 | 31861.4 | 5000 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 5000 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0 | 1874.2 | 0
2025-07-30 | 32798.5 | 5000 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 5000 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0 | 1929.3235 | 0
2025-07-31 | 33735.6 | 5000 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 5000 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0 | 1984.4471 | 0
2025-08-01 | 34672.7 | 5000 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 5000 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0 | 2039.5706 | 0
2025-08-02 | 35609.8 | 5000 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 5000 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0 | 2094.6941 | 0
2025-08-03 | 36546.9 | 5000 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 5000 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0 | 2149.8176 | 0
2025-08-04 | 37484 | 5000 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 5000 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0 | 2204.9412 | 0
2025-08-05 | 38421.1 | 5000 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 5000 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0 | 2260.0647 | 0
2025-08-06 | 39358.2 | 5000 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 5000 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0 | 2315.1882 | 0
2025-08-07 | 40295.3 | 5000 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 5000 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0 | 2370.3118 | 0
2025-08-08 | 41232.4 | 5000 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 5000 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0 | 2425.4353 | 0
2025-08-09 | 42169.5 | 5000 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 5000 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0 | 2480.5588 | 0
2025-08-10 | 43106.6 | 5000 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 5000 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0 | 2535.6824 | 0
2025-08-11 | 44043.7 | 5000 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 5000 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0 | 2590.8059 | 0
2025-08-12 | 44980.8 | 5000 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 5000 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0 | 2645.9294 | 0
2025-08-13 | 45917.9 | 5000 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 5000 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0 | 2701.0529 | 0
2025-08-14 | 46855 | 5000 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 5000 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0 | 2756.1765 | 0
2025-08-15 | 47792.1 | 5000 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 5000 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0 | 2811.3 | 0
2025-08-16 | 48729.2 | 5000 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 5000 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0 | 2866.4235 | 0
2025-08-17 | 49666.3 | 5000 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 5000 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0 | 2921.5471 | 0
2025-08-18 | 50603.4 | 5000 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 5000 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0 | 2976.6706 | 0
2025-08-19 | 51540.5 | 5000 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 5000 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0 | 3031.7941 | 0
2025-08-20 | 52477.6 | 5000 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 5000 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0 | 3086.9176 | 0
2025-08-21 | 53414.7 | 5000 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 5000 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0 | 3142.0412 | 0
2025-08-22 | 54351.8 | 5000 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 5000 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0 | 3197.1647 | 0
2025-08-23 | 55288.9 | 5000 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 5000 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0 | 3252.2882 | 0
2025-08-24 | 56226 | 5000 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 5000 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0 | 3307.4118 | 0
2025-08-25 | 57163.1 | 5000 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 5000 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0 | 3362.5353 | 0
2025-08-26 | 58100.2 | 5000 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 5000 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0 | 3417.6588 | 0
2025-08-27 | 59037.3 | 5000 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 5000 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0 | 3472.7824 | 0
2025-08-28 | 59974.4 | 5000 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 5000 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0 | 3527.9059 | 0
2025-08-29 | 60911.5 | 5000 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 5000 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0 | 3583.0294 | 0
2025-08-30 | 61848.6 | 5000 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 5000 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0 | 3638.1529 | 0
2025-08-31 | 62785.7 | 5000 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 5000 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0 | 3693.2765 | 0
2025-09-01 | 63722.8 | 5000 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 5000 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0 | 3748.4 | 0
2025-09-02 | 64659.9 | 5000 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 5000 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0 | 3803.5235 | 0
2025-09-03 | 65597 | 5000 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 5000 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0 | 3858.6471 | 0
2025-09-04 | 66534.1 | 5000 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 5000 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0 | 3913.7706 | 0
2025-09-05 | 67471.2 | 5000 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 5000 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0 | 3968.8941 | 0
2025-09-06 | 68408.3 | 5000 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 5000 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0 | 4024.0176 | 0
2025-09-07 | 69345.4 | 5000 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 5000 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0 | 4079.1412 | 0
2025-09-08 | 70282.5 | 5000 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 5000 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0 | 4134.2647 | 0
2025-09-09 | 71219.6 | 5000 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 5000 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0 | 4189.3882 | 0
2025-09-10 | 72156.7 | 5000 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 5000 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0 | 4244.5118 | 0
2025-09-11 | 73093.8 | 5000 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 5000 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0 | 4299.6353 | 0
2025-09-12 | 74030.9 | 5000 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 5000 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0 | 4354.7588 | 0
2025-09-13 | 74968 | 5000 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 5000 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0 | 4409.8824 | 0
2025-09-14 | 75905.1 | 5000 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 5000 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0 | 4465.0059 | 0
2025-09-15 | 76842.2 | 5000 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 5000 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0 | 4520.1294 | 0
2025-09-16 | 77779.3 | 5000 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 5000 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0 | 4575.2529 | 0
2025-09-17 | 78716.4 | 5000 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 5000 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0 | 4630.3765 | 0
2025-09-18 | 79653.5 | 5000 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 5000 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0 | 4685.5 | 0
2025-09-19 | 80590.6 | 5000 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 5000 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0 | 4740.6235 | 0
2025-09-20 | 81527.7 | 5000 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 5000 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0 | 4795.7471 | 0
2025-09-21 | 82464.8 | 5000 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 5000 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0 | 4850.8706 | 0
2025-09-22 | 83401.9 | 5000 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 5000 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0 | 4905.9941 | 0
2025-09-23 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-24 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-25 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-26 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-27 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-28 | 84339 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 5000 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0 | 4961.1176 | 0
2025-09-29 | 84575.6221 | 5000 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 5000 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0 | 4975.0366 | 0
2025-09-30 | 84812.2441 | 5000 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 5000 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0 | 4988.9555 | 0
2025-10-01 | 85048.8662 | 5000 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 5000 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0 | 5002.8745 | 0
2025-10-02 | 85285.4883 | 5000 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 5000 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0 | 5016.7934 | 0
2025-10-03 | 85522.1104 | 5000 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 5000 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0 | 5030.7124 | 0
2025-10-04 | 85758.7324 | 5000 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 5000 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0 | 5044.6313 | 0
2025-10-05 | 85995.3545 | 5000 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 5000 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0 | 5058.5503 | 0
2025-10-06 | 86231.9766 | 5000 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 5000 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0 | 5072.4692 | 0
2025-10-07 | 86468.5987 | 5000 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 5000 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0 | 5086.3882 | 0
2025-10-08 | 86705.2207 | 5000 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 5000 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0 | 5100.3071 | 0
2025-10-09 | 86941.8428 | 5000 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 5000 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0 | 5114.226 | 0
2025-10-10 | 87178.4649 | 5000 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 5000 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0 | 5128.145 | 0
2025-10-11 | 87415.087 | 5000 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 5000 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0 | 5142.0639 | 0
2025-10-12 | 87651.709 | 5000 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 5000 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0 | 5155.9829 | 0
2025-10-13 | 87888.3311 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018 |  | 5169.9018
2025-10-14 | 88124.9532 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208 |  | 5183.8208
2025-10-15 | 88361.5753 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397 |  | 5197.7397
2025-10-16 | 88598.1973 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587 |  | 5211.6587
2025-10-17 | 88834.8194 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776 |  | 5225.5776
2025-10-18 | 89071.4415 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966 |  | 5239.4966
2025-10-19 | 89308.0635 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155 |  | 5253.4155
2025-10-20 | 89544.6856 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344 |  | 5267.3344
2025-10-21 | 89781.3077 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534 |  | 5281.2534
2025-10-22 | 90017.9298 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723 |  | 5295.1723
2025-10-23 | 90254.5518 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913 |  | 5309.0913
2025-10-24 | 90491.1739 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102 |  | 5323.0102
2025-10-25 | 90727.796 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292 |  | 5336.9292
2025-10-26 | 90964.4181 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481 |  | 5350.8481
2025-10-27 | 91201.0401 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671 |  | 5364.7671
2025-10-28 | 91437.6622 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686 |  | 5378.686
2025-10-29 | 91674.2843 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605 |  | 5392.605
2025-10-30 | 91910.9064 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239 |  | 5406.5239
2025-10-31 | 92147.5284 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428 |  | 5420.4428
2025-11-01 | 92384.1505 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618 |  | 5434.3618
2025-11-02 | 92620.7726 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807 |  | 5448.2807
2025-11-03 | 92857.3946 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997 |  | 5462.1997
2025-11-04 | 93094.0167 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186 |  | 5476.1186
2025-11-05 | 93330.6388 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376 |  | 5490.0376
2025-11-06 | 93567.2609 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565 |  | 5503.9565
2025-11-07 | 93803.8829 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755 |  | 5517.8755
2025-11-08 | 94040.505 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944 |  | 5531.7944
2025-11-09 | 94277.1271 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134 |  | 5545.7134
2025-11-10 | 94513.7492 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323 |  | 5559.6323
2025-11-11 | 94750.3712 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512 |  | 5573.5512
2025-11-12 | 94986.9933 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702 |  | 5587.4702
2025-11-13 | 95223.6154 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891 |  | 5601.3891
2025-11-14 | 95460.2375 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081 |  | 5615.3081
2025-11-15 | 95696.8595 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227 |  | 5629.227
2025-11-16 | 95933.4816 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146 |  | 5643.146
2025-11-17 | 96170.1037 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649 |  | 5657.0649
2025-11-18 | 96406.7258 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839 |  | 5670.9839
2025-11-19 | 96643.3478 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028 |  | 5684.9028
2025-11-20 | 97137.4655 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686 |  | 5713.9686
2025-11-21 | 97631.5831 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343 |  | 5743.0343
2025-11-22 | 98125.7008 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1 |  | 5772.1
2025-11-23 | 98619.8184 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658 |  | 5801.1658
2025-11-24 | 99113.9361 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315 |  | 5830.2315
2025-11-25 | 99608.0537 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973 |  | 5859.2973
2025-11-26 | 100102.1714 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363 |  | 5888.363
2025-11-27 | 100596.289 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288 |  | 5917.4288
2025-11-28 | 101090.4066 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945 |  | 5946.4945
2025-11-29 | 101584.5243 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603 |  | 5975.5603
2025-11-30 | 102078.6419 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626 |  | 6004.626
2025-12-01 | 102572.7596 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917 |  | 6033.6917
2025-12-02 | 103066.8772 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575 |  | 6062.7575
2025-12-03 | 103560.9949 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232 |  | 6091.8232
2025-12-04 | 104055.1125 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889 |  | 6120.889
2025-12-05 | 104549.2302 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547 |  | 6149.9547
2025-12-06 | 105043.3478 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205 |  | 6179.0205
2025-12-07 | 105537.4655 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862 |  | 6208.0862
2025-12-08 | 106031.5831 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519 |  | 6237.1519
2025-12-09 | 106525.7008 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177 |  | 6266.2177
2025-12-10 | 107019.8184 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834 |  | 6295.2834
2025-12-11 | 107513.9361 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492 |  | 6324.3492
2025-12-12 | 108008.0537 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149 |  | 6353.4149
2025-12-13 | 108502.1714 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807 |  | 6382.4807
2025-12-14 | 108996.289 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464 |  | 6411.5464
2025-12-15 | 109490.4066 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122 |  | 6440.6122
2025-12-16 | 109984.5243 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779 |  | 6469.6779
2025-12-17 | 110478.6419 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436 |  | 6498.7436
2025-12-18 | 110972.7596 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094 |  | 6527.8094
2025-12-19 | 111466.8772 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751 |  | 6556.8751
2025-12-20 | 111960.9949 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409 |  | 6585.9409
2025-12-21 | 112455.1125 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066 |  | 6615.0066
2025-12-22 | 112949.2302 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724 |  | 6644.0724
2025-12-23 | 113443.3478 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381 |  | 6673.1381
2025-12-24 | 113937.4655 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039 |  | 6702.2039
2025-12-25 | 114431.5831 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696 |  | 6731.2696
2025-12-26 | 114925.7008 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353 |  | 6760.3353
2025-12-27 | 115419.8184 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011 |  | 6789.4011
2025-12-28 | 115913.9361 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668 |  | 6818.4668
2025-12-29 | 116408.0537 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326 |  | 6847.5326
2025-12-30 | 116902.1714 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983 |  | 6876.5983
2025-12-31 | 117396.289 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641 |  | 6905.6641
2026-01-01 | 117890.4066 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298 |  | 6934.7298
2026-01-02 | 118384.5243 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955 |  | 6963.7955
2026-01-03 | 118878.6419 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613 |  | 6992.8613
2026-01-04 | 119372.7596 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927 |  | 7021.927
2026-01-05 | 119866.8772 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928 |  | 7050.9928
2026-01-06 | 120360.9949 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585 |  | 7080.0585
2026-01-07 | 120855.1125 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243 |  | 7109.1243
2026-01-08 | 121349.2302 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19 |  | 7138.19
2026-01-09 | 121843.3478 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558 |  | 7167.2558
2026-01-10 | 122337.4655 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215 |  | 7196.3215
2026-01-11 | 122831.5831 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872 |  | 7225.3872
2026-01-12 | 123325.7008 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453 |  | 7254.453
2026-01-13 | 123819.8184 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187 |  | 7283.5187
2026-01-14 | 124313.9361 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845 |  | 7312.5845
2026-01-15 | 124808.0537 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502 |  | 7341.6502
2026-01-16 | 125302.1714 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716 |  | 7370.716
2026-01-17 | 125796.289 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817 |  | 7399.7817
2026-01-18 | 126290.4066 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474 |  | 7428.8474
2026-01-19 | 126784.5243 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132 |  | 7457.9132
2026-01-20 | 127278.6419 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789 |  | 7486.9789
2026-01-21 | 127772.7596 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447 |  | 7516.0447
2026-01-22 | 128266.8772 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104 |  | 7545.1104
2026-01-23 | 128760.9949 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762 |  | 7574.1762
2026-01-24 | 129255.1125 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419 |  | 7603.2419
2026-01-25 | 129749.2302 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077 |  | 7632.3077
2026-01-26 | 130243.3478 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734 |  | 7661.3734
2026-01-27 | 130737.4655 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391 |  | 7690.4391
2026-01-28 | 131231.5831 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049 |  | 7719.5049
2026-01-29 | 131725.7008 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706 |  | 7748.5706
2026-01-30 | 132219.8184 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364 |  | 7777.6364
2026-01-31 | 132713.9361 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021 |  | 7806.7021
2026-02-01 | 133208.0537 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679 |  | 7835.7679
2026-02-02 | 133702.1714 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336 |  | 7864.8336
2026-02-03 | 134196.289 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994 |  | 7893.8994
2026-02-04 | 134690.4066 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651 |  | 7922.9651
2026-02-05 | 135184.5243 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308 |  | 7952.0308
2026-02-06 | 135678.6419 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966 |  | 7981.0966
2026-02-07 | 136172.7596 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623 |  | 8010.1623
2026-02-08 | 136666.8772 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281 |  | 8039.2281
2026-02-09 | 137160.9949 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938 |  | 8068.2938
2026-02-10 | 137655.1125 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596 |  | 8097.3596
2026-02-11 | 138149.2302 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253 |  | 8126.4253
2026-02-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-02-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-03-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-04-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-05-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-06-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-07-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-26 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-27 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-28 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-29 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-30 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-08-31 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-01 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-02 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-03 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-04 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-05 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-06 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-07 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-08 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-09 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-10 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-11 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-12 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-13 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-14 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-15 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-16 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-17 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-18 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-19 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-20 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-21 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-22 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-23 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-24 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491
2026-09-25 | 138643.3478 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491 |  | 8155.491

## Labor Days
Month | Actual Geo Total (Monthly) | Actual On Site Personal (Monthly) | Actual Remote Personal (Monthly) | Planned GEO total personal (Monthly) | Planned on site personal (Monthly) | Planned remote personal (Monthly) | Planned Technician I (Monthly) | Actual Technician I (Monthly) | Planned Technician II (Monthly) | Actual Technician II (Monthly) | Planned Welder (Monthly) | Actual Welder (Monthly) | Planned Engineer/supervisor (Monthly) | Actual Engineer/supervisor (Monthly) | Planned Manager/senior Engineer (Monthly) | Actual Manager/senior Engineer (Monthly) | Planned Remote mid engineer (Monthly) | Actual Remote mid engineer (Monthly) | Planned Remote senior (Monthly) | Actual Remote senior (Monthly)
April 25 | 14.5 | 0 | 14.5 | 46.1311 | 0 | 46.1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.25 | 46.1311 | 6.25
May 25 | 0 | 0 | 0 | 48.3279 | 0 | 48.3279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.3279 | 0
June 25 | 13.125 | 0 | 13.125 | 40.5254 | 0.98438 | 39.541 | 0 | 0 | 0.65625 | 0 | 0 | 0 | 0.32812 | 0 | 0 | 0 | 0 | 10.625 | 39.541 | 2.5
July 25 | 14.5 | 0 | 14.5 | 7.5469 | 7.5469 | 0 | 0 | 0 | 5.0312 | 0 | 0 | 0 | 2.5156 | 0 | 0 | 0 | 0 | 14.5 | 0 | 0
August 25 | 18.5 | 0 | 18.5 | 6.8906 | 6.8906 | 0 | 0 | 0 | 4.5938 | 0 | 0 | 0 | 2.2969 | 0 | 0 | 0 | 0 | 13.5 | 0 | 5
September 25 | 52 | 23 | 29 | 22.2163 | 20.9531 | 1.2632 | 0 | 0 | 14.3569 | 23 | 3.1579 | 0 | 1.8594 | 0 | 1.5789 | 0 | 0 | 14.875 | 1.2632 | 14.125
October 25 | 15.625 | 10 | 5.625 | 191.3388 | 176.8125 | 14.5263 | 0 | 0 | 122.3388 | 10 | 36.3158 | 0 | 0 | 0 | 18.1579 | 0 | 0 | 0.375 | 14.5263 | 5.25
November 25 | 0 | 0 | 0 | 145.3668 | 130.2199 | 15.147 | 2.5882 | 0 | 75.2304 | 0 | 30.8793 | 0 | 4.7882 | 0 | 16.7337 | 0 | 0 | 0 | 15.147 | 0
December 25 | 0 | 0 | 0 | 104.8894 | 85.3412 | 19.5482 | 7.2941 | 0 | 17.1412 | 0 | 29.1765 | 0 | 13.4941 | 0 | 18.2353 | 0 | 0 | 0 | 19.5482 | 0
January 26 | 0 | 0 | 0 | 104.8894 | 85.3412 | 19.5482 | 7.2941 | 0 | 17.1412 | 0 | 29.1765 | 0 | 13.4941 | 0 | 18.2353 | 0 | 0 | 0 | 19.5482 | 0
February 26 | 0 | 0 | 0 | 70.5288 | 48.4029 | 22.1259 | 18.1912 | 0 | 6.6353 | 0 | 11.2941 | 0 | 5.2235 | 0 | 7.0588 | 0 | 0 | 0 | 22.1259 | 0
March 26 | 0 | 0 | 0 | 59.8529 | 30.7353 | 29.1176 | 30.7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.1176 | 0
April 26 | 0 | 0 | 0 | 59.8529 | 30.7353 | 29.1176 | 30.7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.1176 | 0
May 26 | 0 | 0 | 0 | 57.1324 | 29.3382 | 27.7941 | 29.3382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7941 | 0
June 26 | 0 | 0 | 0 | 59.8529 | 30.7353 | 29.1176 | 30.7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.1176 | 0
July 26 | 0 | 0 | 0 | 62.5735 | 32.1324 | 30.4412 | 32.1324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.4412 | 0
August 26 | 0 | 0 | 0 | 64.3768 | 37.7559 | 26.6209 | 24.3159 | 0 | 3.36 | 0 | 6.72 | 0 | 3.36 | 0 | 0 | 0 | 0 | 0 | 26.6209 | 0
September 26 | 0 | 0 | 0 | 74.632 | 53.2 | 21.432 | 10.64 | 0 | 10.64 | 0 | 21.28 | 0 | 10.64 | 0 | 0 | 0 | 0 | 0 | 21.432 | 0

## Deleted Duplicates
Date | Account | Amount | Type | Num | Memo | Split | Source_File | Category
No duplicates found